{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":6,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":13,"n_cols":24,"rows_kept":13,"cut":false,"hidden":false,"merged":[[2,0,2,14]]}
["Updated ","2022-09-22"]
["Arlington Storage Company, LLC 2022 Pipeline Outage and Maintenance Summary"]
["This is a summary of the current status of all Arlington Storage Company 2022 Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  \nAdditionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
["*** Indicates revision"]
["Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","Location","Segment","Zone","Maintenance Activity","Anticipated Impact","Potential Restriction Level","TOS Potential Restrictions","Meter(s) in Impacted Area","Loc",null,null,null,null,null,null,null,"\\\\houCORP\\TRANS\\TRANSERVICES\\OPPLAN\\COMMON\\Outages\\Outage_DB\\STAR\\Files"]
["X22-932317","***","2022-09-16","2022-09-16","Completed",null,null,"Thomas Corners Storage",200,"AL","Dehy Flush & Burner Inspection",null,null,null,"302015 THOMAS CORNERS STO",null,"------","***Thomas Corners Storage:  Dehy Flush & Burner Inspection\n***Completed\nThe following meters are available for nominations:\n302015 THOMAS CORNERS STO"]
["X22-322495","***","2022-09-19","2022-09-20","Completed",null,null,"Steuben Storage",300,"AL","Relief valve testing",null,null,null,"303000 STEUBEN STO",null,"------","***Steuben Storage:  Relief valve testing\n***Completed\nThe following meters are available for nominations:\n303000 STEUBEN STO"]
["X22-322473","***","2022-09-20","2022-09-21","Completed",null,null,"Thomas Corners Storage",200,"AL","Relief valve testing",null,null,null,"302015 THOMAS CORNERS STO",null,"------","***Thomas Corners Storage:  Relief valve testing\n***Completed\nThe following meters are available for nominations:\n302015 THOMAS CORNERS STO"]
["X22-322467","***","2022-09-21","2022-09-22","Project Change","2022-09-22","2022-09-23","Seneca Lake Storage",900,"AL","Relief Valve Testing",null,null,null,"311010 SENECA LAKE STO",null,"--start_date--end_date------------model_loc--","***Seneca Lake Storage:  Relief Valve Testing\n--9/21/22 through 9/22/22:    \n311010 SENECA LAKE STO\n***\nDate Change, Previously scheduled 9/22/22 to 9/23/22.\n………………………………"]
["X22-322470",null,"2022-10-19","2022-10-19",null,null,null,"Seneca Lake Storage",900,"AL","Point to Point and Trans Cals",null,null,null,"311010 SENECA LAKE STO",null,null,"Seneca Lake Storage:  Point to Point and Trans Cals\n--10/19/22:    \n311010 SENECA LAKE STO\n………………………………"]
["X22-322497",null,"2022-10-20","2022-10-20",null,null,null,"Steuben Storage",300,"AL","Point to Point and Trans Cals",null,null,null,"303000 STEUBEN STO",null,null,"Steuben Storage:  Point to Point and Trans Cals\n--10/20/22:    \n303000 STEUBEN STO\n………………………………"]
["X22-322474",null,"2022-10-21","2022-10-21",null,null,null,"Thomas Corners Storage",200,"AL","Point to Point and Trans Cals",null,null,null,"302015 THOMAS CORNERS STO",null,null,"Thomas Corners Storage:  Point to Point and Trans Cals\n--10/21/22:    \n302015 THOMAS CORNERS STO\n………………………………"]
["X22-311506","***","2022-11-28","2022-12-15","Project Change","2022-10-03","2022-10-28","Seneca Lake Storage",900,"AL","Automation Upgrade",null,null,null,"311010 SENECA LAKE STO",null,"--start_date--end_date------------model_loc--","***Seneca Lake Storage:  Automation Upgrade\n--11/28/22 through 12/15/22:    \n311010 SENECA LAKE STO\n***\nDate Change, Previously scheduled 10/3/22 to 10/28/22.\n………………………………"]