{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":6,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":7,"n_cols":24,"rows_kept":7,"cut":false,"hidden":false,"merged":[[2,0,2,14]]}
["Updated ","2023-09-07"]
["Arlington Storage Company, LLC 2023 Pipeline Outage and Maintenance Summary"]
["This is a summary of the current status of all Arlington Storage Company 2023 Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  \nAdditionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
["*** Indicates revision"]
["Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","Location","Segment","Zone","Maintenance Activity","Anticipated Impact","Potential Restriction Level","TOS Potential Restrictions","Meter(s) in Impacted Area","Loc",null,null,null,null,null,null,null,"\\\\houCORP\\TRANS\\TRANSERVICES\\OPPLAN\\COMMON\\Outages\\Outage_DB\\STAR\\Files"]
["X23-621500","***","2024-07-09","2024-07-24","Project Change","2023-09-05","2023-09-20","Steuben Adrian Storage",300,"AL","8\" Line Pig Run - Cleaning, MFL 7/16/24","'This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","303000 STEUBEN STO",null,"--start_date--end_date------mantenance_desc------model_loc--","***Steuben Adrian Storage:  8\" Line Pig Run - Cleaning, MFL 7/16/24\n--7/9/24 through 7/24/24:  'This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.  Potential out of path restrictions may be at risk.\n303000 STEUBEN STO\n***\nDate Change, Previously scheduled 9/5/23 to 9/20/23.\n………………………………"]
["X23-621504","***","2024-07-09","2024-07-24","Project Change","2023-09-05","2023-09-20","Steuben Adrian Storage",300,"AL","10\"/12\" Line Pig Run - Cleaning, MFL 7/17/24","'This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","303000 STEUBEN STO",null,"--start_date--end_date------mantenance_desc------model_loc--","***Steuben Adrian Storage:  10\"/12\" Line Pig Run - Cleaning, MFL 7/17/24\n--7/9/24 through 7/24/24:  'This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.  Potential out of path restrictions may be at risk.\n303000 STEUBEN STO\n***\nDate Change, Previously scheduled 9/5/23 to 9/20/23.\n………………………………"]