{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":6,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":11,"n_cols":22,"rows_kept":11,"cut":false,"hidden":false,"merged":[[2,0,2,12]]}
["Updated ","2025-09-18"]
["Arlington Storage Company, LLC 2025 Pipeline Outage and Maintenance Summary"]
["This is a summary of the current status of Arlington Storage Company Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  \nAdditionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
["*** Indicates revision"]
["Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","Location","Segment","Zone","Maintenance Activity","Anticipated Impact","Meter(s) in Impacted Area","Loc",null,null,null,null,null,null,null,"\\\\houCORP\\TRANS\\TRANSERVICES\\OPPLAN\\COMMON\\Outages\\Outage_DB\\STAR\\Files"]
["X25-1001007",null,"2025-11-03","2025-11-07",null,null,null,"Seneca Lake Storage",900,"AL","Shut-in Test","This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","311010 SENECA LAKE STO",1,null,"Seneca Lake Storage:  Shut-in Test\n--11/3/25 through 11/7/25:  This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n311010 SENECA LAKE STO\n………………………………"]
["X25-1001009",null,"2025-11-17","2025-11-21",null,null,null,"Steuben Storage",900,"AL","Shut-in Test","This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","303000 STEUBEN STO",2.2000000000000002,null,"Steuben Storage:  Shut-in Test\n--11/17/25 through 11/21/25:  This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n303000 STEUBEN STO\n………………………………"]
["X25-1036919",null,"2025-09-25","2025-09-25",null,null,null,"Steuben Storage",900,"AL","Filter Changes","This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","303000 STEUBEN STO",2.2999999999999998,null,"Steuben Storage:  Filter Changes\n--9/25/25:  This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n303000 STEUBEN STO\n………………………………"]
["X25-307388","***","2025-08-04","2025-09-19","Project Change",null,"2025-09-12","Thomas Corners Storage",200,"AL","Unit 1 Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","302015 THOMAS CORNERS STO",3.1,"----end_date--------------model_loc--","***Thomas Corners Storage:  Unit 1 Overhaul\n--8/4/25 through 9/19/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n302015 THOMAS CORNERS STO\n***\nDate Change, Previously scheduled 8/4/25 to 9/12/25.\n………………………………"]
["X25-1001010",null,"2025-11-17","2025-11-21",null,null,null,"Thomas Corners Storage",200,"AL","Shut-In Test","This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","302015 THOMAS CORNERS STO",3.2,null,"Thomas Corners Storage:  Shut-In Test\n--11/17/25 through 11/21/25:  This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n302015 THOMAS CORNERS STO\n………………………………"]
["X25-1036916",null,"2025-09-22","2025-09-24",null,null,null,"Thomas Corners Storage",200,"AL","Dehi flush and internal inspection / Station filter changes","This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","302015 THOMAS CORNERS STO",3.3,null,"Thomas Corners Storage:  Dehi flush and internal inspection / Station filter changes\n--9/22/25 through 9/24/25:  This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n302015 THOMAS CORNERS STO\n………………………………"]