{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":6,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":10,"n_cols":22,"rows_kept":10,"cut":false,"hidden":false,"merged":[[2,0,2,12]]}
["Updated ","2026-02-05"]
["Arlington Storage Company, LLC 2026 Pipeline Outage and Maintenance Summary"]
["This is a summary of the current status of Arlington Storage Company Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  \nAdditionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
["*** Indicates revision"]
["Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","Location","Segment","Zone","Maintenance Activity","Anticipated Impact","Meter(s) in Impacted Area","Loc",null,null,null,null,null,null,null,"\\\\houCORP\\TRANS\\TRANSERVICES\\OPPLAN\\COMMON\\Outages\\Outage_DB\\STAR\\Files"]
["X25-1428295",null,"2026-08-03","2026-08-03",null,null,null,"Seneca Lake Gas Facility Tether Run   Cavern Delivery Line",9200,"AL","Pig Run - Gauge/Cleaning","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","311010 SENECA LAKE STO",1.1000000000000001,null,"Seneca Lake Gas Facility Tether Run   Cavern Delivery Line:  Pig Run - Gauge/Cleaning\n--8/3/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  \n311010 SENECA LAKE STO\n………………………………"]
["X25-1428297",null,"2026-08-05","2026-08-05",null,null,null,"Seneca Lake Gas Facility Tether Run   Cavern Delivery Line",900,"AL","Pig Run - Cal/IMU/MFL-A Combo","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","311010 SENECA LAKE STO",1.2,null,"Seneca Lake Gas Facility Tether Run   Cavern Delivery Line:  Pig Run - Cal/IMU/MFL-A Combo\n--8/5/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  \n311010 SENECA LAKE STO\n………………………………"]
["X26-53670",null,"2026-05-11","2026-05-15",null,null,null,"Thomas Corners Storage",200,"AL","Shut-In Test","This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meters listed below may be limited during the project.","302015 THOMAS CORNERS STO",2,null,"Thomas Corners Storage:  Shut-In Test\n--5/11/26 through 5/15/26:  This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meters listed below may be limited during the project.  \n302015 THOMAS CORNERS STO\n………………………………"]
["X25-1293081",null,"2026-05-28","2026-06-06",null,null,null,"Thomas Corner South Lateral 8\"",200,"AL","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,2.1,null,"Thomas Corner South Lateral 8\":  Anomaly Remediation\n--5/28/26 through 6/6/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-53669",null,"2026-04-13","2026-04-17",null,null,null,"Steuben Storage",300,"AL","Shut-in Test","This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meters listed below may be limited during the project.","303000 STEUBEN STO",3,null,"Steuben Storage:  Shut-in Test\n--4/13/26 through 4/17/26:  This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meters listed below may be limited during the project.  \n303000 STEUBEN STO\n………………………………"]