## outsched_NGPL
Kinder Morgan Louisiana Pipeline LLC
Outage Impact Report
Last Updated: April 10, 2024
Estimated Start Date | Estimated Finish Date | Day(s) | Previous Start Date | Previous End Date | IMPACTED SEG/LOC | Compressor Station(s) | Unit / Line | Description | Scheduling Location | Transport Impact
2024-08-07 | 2024-08-07 | 1 |  |  | 140 |  |  | ILI Tool Runs - Cleaning | Seg 140 | KMLP will schedule Primary Firm and Secondary in-path Firm transports to a minimum of 47% of contract MDQ through Segment 140. AOR/ITS and Secondary out-of-path Firm transports will not be available.
2024-08-09 | 2024-08-09 | 1 |  |  | 140 |  |  | ILI Tool Runs - Cleaning | Seg 140 | KMLP will schedule Primary Firm and Secondary in-path Firm transports to a minimum of 47% of contract MDQ through Segment 140. AOR/ITS and Secondary out-of-path Firm transports will not be available.
2024-08-12 | 2024-08-12 | 1 |  |  | 140 |  |  | ILI Tool Runs - MFL/Caliper | Seg 140 | KMLP will schedule Primary Firm and Secondary in-path Firm transports to a minimum of 87% of contract MDQ through Segment 140. AOR/ITS and Secondary out-of-path Firm transports will not be available.
2024-08-14 | 2024-08-14 | 1 |  |  | LOC 44398, LOC 44404, LOC 44395 |  |  | ILI Tool Runs - Cleaning | LOC 44398, LOC 44404, LOC 44395 | LOC 44398 Columbia Gulf Evangeline will be limited to 350,000 dth/day. In addition LOC 44404 Pine Praire and LOC 44395 ANR are unavailable.
2024-08-16 | 2024-08-16 | 1 |  |  | LOC 44398, LOC 44404, LOC 44395 |  |  | ILI Tool Runs - Cleaning | LOC 44398, LOC 44404, LOC 44395 | LOC 44398 Columbia Gulf Evangeline will be limited to 350,000 dth/day. In addition LOC 44404 Pine Praire and LOC 44395 ANR are unavailable.
2024-08-17 | 2024-08-17 | 1 |  |  | LOC 44398, LOC 44404, LOC 44395 |  |  | ILI Tool Runs - MFL/Caliper | LOC 44398, LOC 44404, LOC 44395 | LOC 44398 Columbia Gulf Evangeline will be limited to 350,000 dth/day. In addition LOC 44404 Pine Praire and LOC 44395 ANR are unavailable.
NOTES:
1. Changes are shaded in yellow.
2. If no outages are planned, you will see a blank row.