## outsched_NGPL
Kinder Morgan Louisiana Pipeline LLC
Outage Impact Report
Last Updated: 3/12/2026
Estimated Start Date | Estimated Finish Date | Day(s) | Previous Start Date | Previous End Date | IMPACTED SEG/LOC | Compressor Station(s) | Unit / Line | Description | Scheduling Location | Transport Impact
2026-06-01 | 2026-06-12 | 12 | 2026-06-08 | 2026-06-12 | LOC 49448 SPLIQ/KMLP SP LIQUEFACTION |  | KMLP 36 IN PARALLEL LEG 2 (36") | Pipeline Integrity - ILI Tool Runs | LOC 49448 | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, KMLP does not anticipate limiting primary firm transport services, at this time. If conditions change KMLP will post an update.
2026-06-15 | 2026-06-26 | 12 | 2026-06-01 | 2026-06-05 | LOC 49448 SPLIQ/KMLP SP LIQUEFACTION |  | KMLP MAINLINE (42") | Pipeline Integrity - ILI Tool Runs | LOC 49448 | LOC 49448 SPLIQ/KMLP SP LIQUEFACTION is limited to a capacity of 1,400,000 dth/day until the integrity project has been completed.
NOTES:
1. Changes are shaded in yellow.
2. If no outages are planned, you will see a blank row.