## outsched_MEP
Midcontinent Express Pipeline LLC
Outage Impact Report
Last Updated: June 9, 2022
Estimated Start Date | Estimated Finish Date | Day(s) | Previous Start Date | Previous End Date | IMPACTED SEG/LOC | Compressor Station(s) | Unit / Line | Description | Scheduling Location | Transport Impact
2022-05-02 | 2022-07-15 | 74 |  |  |  | MEP 2 |  | Unit Maintenance |  | No anticipated impact
2022-06-16 | 2022-06-16 | 1 |  |  | LOC 44451 Transco Choctaw |  |  | Meter Maintenace | LOC 44451 Transco Choctaw | MEP will schedule to at least a total delivery capacity for the entire gas day of 900,000 dth/day. AOR/ITS and Secondary out-of-path Firm transports will not be available until the work has been completed.
1. Changes are shaded in yellow.
2. If no outages are planned, you will see a blank row.
Formulas:
Day(s) = DAYS([Estimated Finish Date],[Estimated Start Date])