## outsched_MEP
Midcontinent Express Pipeline LLC
Outage Impact Report
Last Updated: March 7, 2024
Estimated Start Date | Estimated Finish Date | Day(s) | Previous Start Date | Previous End Date | IMPACTED SEG/LOC | Compressor Station(s) | Unit / Line | Description | Scheduling Location | Transport Impact
2024-01-29 | 2024-02-15 | 18 |  |  |  | MEP 3 | Unit #4 | Unit Maintenance |  | No anticipated impact
2024-02-19 | 2024-02-29 | 11 |  |  |  | MEP 3 | Unit #3 | Unit Maintenance |  | No anticipated impact
2024-02-26 | 2024-03-15 | 19 |  |  |  | MEP 2 | Unit #3 | Unit Maintenance |  | No anticipated impact
2024-03-25 | 2024-04-12 | 19 |  |  |  | MEP 2 | Unit #4 | Unit Maintenance |  | No anticipated impact
2024-05-01 | 2024-05-03 | 3 |  |  | 120 | MEP 1/MEP 3A |  | ILI Tool Run - MFL/Caliper | Seg 120 | Primary/SIP Firm transports will be scheduled to no less than 68% of contract MDQ into segment 120. AOR/ITS and Secondary out-of-path Firm transports are not available. Additionally, all park and loan services under Rate Schedule PALS will not be available anywhere on the system.
2024-05-08 | 2024-05-09 | 2 |  |  | 200 |  |  | ILI Tool Run - MFL/Caliper | Seg 200/LOCs 44448,44449, 45015, 44577, 44450 | Primary/SIP Firm transports will be scheduled to no less than 57% of contract MDQ into segment 200. AOR/ITS and Secondary out-of-path Firm transports are not available. Additionally the following locations are unavailable: LOC 44448 TET Hinds, LOC 44449 SNG Smith, LOC 45015 Leaf River Jasper, LOC 44577 Tenn Gas Jasper, LOC 44450 AMID/Destin Clark. All park and loan services under Rate Schedule PALS will not be available anywhere on the system.
1. Changes are shaded in yellow.
2. If no outages are planned, you will see a blank row.
Formulas:
Day(s) = DAYS([Estimated Finish Date],[Estimated Start Date])+1