## outsched_MEP
Midcontinent Express Pipeline LLC
Outage Impact Report
Last Updated: April 25, 2024
Estimated Start Date | Estimated Finish Date | Day(s) | Previous Start Date | Previous End Date | IMPACTED SEG/LOC | Compressor Station(s) | Unit / Line | Description | Scheduling Location | Transport Impact
2024-04-01 | 2024-04-30 | 30 |  |  |  | MEP 3A | Unit #2 | Unit Maintenance |  | No anticipated impact
2024-05-01 | 2024-06-30 | 61 |  |  | LOC 44577 |  |  | Meter Maintenance | LOC 44577 | LOC 44577 TGP Jasper is unavailable. No transport services will be scheduled.
2024-05-01 | 2024-05-03 | 3 |  |  | 120 | MEP 1/MEP 3A |  | ILI Tool Run - MFL/Caliper | Seg 120 | Primary/SIP Firm transports will be scheduled to no less than 68% of contract MDQ into segment 120. AOR/ITS and Secondary out-of-path Firm transports are not available. Additionally, all park and loan services under Rate Schedule PALS will not be available anywhere on the system.
2024-05-08 | 2024-05-09 | 2 |  |  | 200 |  |  | ILI Tool Run - MFL/Caliper | Seg 200/LOCs 44448,44449, 45015, 44577, 44450 | Primary/SIP Firm transports will be scheduled to no less than 57% of contract MDQ into segment 200. AOR/ITS and Secondary out-of-path Firm transports are not available. Additionally the following locations are unavailable: LOC 44448 TET Hinds, LOC 44449 SNG Smith, LOC 45015 Leaf River Jasper, LOC 44577 Tenn Gas Jasper, LOC 44450 AMID/Destin Clark. All park and loan services under Rate Schedule PALS will not be available anywhere on the system.
2024-05-15 | 2024-05-15 | 1 |  |  |  | MEP 1 |  | ESD Test |  | No anticipated impact
2024-06-11 | 2024-06-11 | 1 |  |  |  | MEP 2 |  | ESD Test |  | No anticipated impact
2024-06-25 | 2024-06-28 | 4 |  |  |  | MEP 2 | Unit #1 | Unit Maintenance |  | No anticipated impact
2024-08-26 | 2024-09-20 | 26 |  |  |  | MEP 3 | Unit #1 | Unit Maintenance |  | No anticipated impact
1. Changes are shaded in yellow.
2. If no outages are planned, you will see a blank row.
Formulas:
Day(s) = DAYS([Estimated Finish Date],[Estimated Start Date])+1