## Closed (hidden)
|  |  | Updated | 2016
Tennessee Gas Pipeline 2015 Pipeline Outage and Maintenance Summary
This is a summary of the current status of all TGP Winter 2014-2015 Pipeline Outages and Maintenance Projects. This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions. Additionally, anticipated impact and restrictions are subject to change. *Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project. *Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time).
*** Indicates revision
Date Change | Project New/Completed/Closed | Outage # | Revised | Start Date | End Date | Reason Changed | Prev. Start Date | Prev. End Date | Location | Leg | Zone | Maintenance Activity | Anticipated Impact | Potential Restriction Level | TOS Potential Restrictions | Meter(s) in Impacted Area | Customer Notifications | Loc | Email Text | Posting Text | Completion Text
| Project Completed |  | *** | 2015-01-11 | 2016-01-11 | Project Completed |  |  | MS #412494 DCP Warren | 400 | 0 | Meter Station | This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | 412494 DCP Warren | 401 | () MS #412494 DCP Warren: Meter Station (1/11/15 to 1/11/16) | ***MS #412494 DCP Warren: Meter Station --1/11/15 through 1/11/16: This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. 412494 DCP Warren ***Project Completed ……………………………… | ***MS #412494 DCP Warren: Meter Station ***Project Completed The following meters are available for nominations: 412494 DCP Warren ………………………………
| Project Completed |  | *** | 2015-01-11 | 2016-01-11 | Project Completed |  |  | MS #412400 King Ranch | 400 | 0 | Meter Station | This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | 412400 King Ranch | 402.1 | () MS #412400 King Ranch: Meter Station (1/11/15 to 1/11/16) | ***MS #412400 King Ranch: Meter Station --1/11/15 through 1/11/16: This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. 412400 King Ranch ***Project Completed ……………………………… | ***MS #412400 King Ranch: Meter Station ***Project Completed The following meters are available for nominations: 412400 King Ranch ………………………………
| Project Completed |  | *** | 2015-01-12 | 2016-01-12 | Project Completed |  |  | MS #410539 Duvak Gas Gathering | 400 | 0 | Meter Station | This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | 410539 Duvak Gas Gathering | 402.1 | () MS #410539 Duvak Gas Gathering: Meter Station (1/12/15 to 1/12/16) | ***MS #410539 Duvak Gas Gathering: Meter Station --1/12/15 through 1/12/16: This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. 410539 Duvak Gas Gathering ***Project Completed ……………………………… | ***MS #410539 Duvak Gas Gathering: Meter Station ***Project Completed The following meters are available for nominations: 410539 Duvak Gas Gathering ………………………………
| Project Completed |  | *** | 2015-01-13 | 2016-01-13 | Project Completed |  |  | MS #412356 DCP LaGloria | 400 | 0 | Meter Station | This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | 412356 DCP LaGloria | 403.1 | () MS #412356 DCP LaGloria: Meter Station (1/13/15 to 1/13/16) | ***MS #412356 DCP LaGloria: Meter Station --1/13/15 through 1/13/16: This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. 412356 DCP LaGloria ***Project Completed ……………………………… | ***MS #412356 DCP LaGloria: Meter Station ***Project Completed The following meters are available for nominations: 412356 DCP LaGloria ………………………………
| Project Completed |  | *** | 2015-01-13 | 2016-01-13 | Project Completed |  |  | MS #410173 Enterprise LaReforma | 400 | 0 | Meter Station | This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | 410173 Enterprise LaReforma | 406.1 | () MS #410173 Enterprise LaReforma: Meter Station (1/13/15 to 1/13/16) | ***MS #410173 Enterprise LaReforma: Meter Station --1/13/15 through 1/13/16: This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. 410173 Enterprise LaReforma ***Project Completed ……………………………… | ***MS #410173 Enterprise LaReforma: Meter Station ***Project Completed The following meters are available for nominations: 410173 Enterprise LaReforma ………………………………
| Project Completed |  | *** | 2015-01-12 | 2016-01-12 | Project Completed |  |  | MS #411903 Enterprise El Benito | 400 | 0 | Meter Station | This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | 411903 Enterprise El Benito | 407.1 | () MS #411903 Enterprise El Benito: Meter Station (1/12/15 to 1/12/16) | ***MS #411903 Enterprise El Benito: Meter Station --1/12/15 through 1/12/16: This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. 411903 Enterprise El Benito ***Project Completed ……………………………… | ***MS #411903 Enterprise El Benito: Meter Station ***Project Completed The following meters are available for nominations: 411903 Enterprise El Benito ………………………………
| Project Completed |  | *** | 2015-01-11 | 2016-01-11 | Project Completed |  |  | MS #412088 Enterprise Sullivan | 400 | 0 | Meter Station | This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | 412088 Enterprise Sullivan | 407.1 | () MS #412088 Enterprise Sullivan: Meter Station (1/11/15 to 1/11/16) | ***MS #412088 Enterprise Sullivan: Meter Station --1/11/15 through 1/11/16: This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. 412088 Enterprise Sullivan ***Project Completed ……………………………… | ***MS #412088 Enterprise Sullivan: Meter Station ***Project Completed The following meters are available for nominations: 412088 Enterprise Sullivan ………………………………
| Project Completed |  | *** | 2015-01-11 | 2016-01-11 | Project Completed |  |  | MS #412683 HESCO | 400 | 0 | Meter Station | This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | 412683 HESCO | 408.1 | () MS #412683 HESCO: Meter Station (1/11/15 to 1/11/16) | ***MS #412683 HESCO: Meter Station --1/11/15 through 1/11/16: This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. 412683 HESCO ***Project Completed ……………………………… | ***MS #412683 HESCO: Meter Station ***Project Completed The following meters are available for nominations: 412683 HESCO ………………………………
| Project Completed | X16-36843 | *** | 2016-01-27 | 2016-01-27 | Project Completed |  |  | Sta. 237 | 200 | 5 | Unit Maintenance | This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. |  | 237 | (X16-36843) Sta. 237: Unit Maintenance (1/27/16) | ***Sta. 237: Unit Maintenance --1/27/16: This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. ***Project Completed ……………………………… | ***Sta. 237: Unit Maintenance ***Project Completed ………………………………
| Project Completed | X14-1478563 | *** | 2015-11-16 | 2016-02-12 | Project Completed |  |  | MLV 32-1D to 33-1 | 100 | 0 | Hydrotest | This project will require taking the pipeline section out of service. This will limit throughput and may result in restrictions based on customer nominations. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. |  | 32.2 | (X14-1478563) MLV 32-1D to 33-1: Hydrotest (11/16/15 to 2/12/16) | ***MLV 32-1D to 33-1: Hydrotest --11/16/15 through 2/12/16: This project will require taking the pipeline section out of service. This will limit throughput and may result in restrictions based on customer nominations. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. ***Project Completed ……………………………… | ***MLV 32-1D to 33-1: Hydrotest ***Project Completed ………………………………
| Project Completed | X16-16074 |  | 2016-01-18 | 2016-01-28 | Project Completed |  |  | Station 550 | 500 | 1 | Station Maintenance | This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. |  | 550 | (X16-16074) Station 550: Station Maintenance (1/18/16 to 1/28/16) | Station 550: Station Maintenance --1/18/16 through 1/28/16: This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. ***Project Completed ……………………………… | Station 550: Station Maintenance ***Project Completed ………………………………
| Project Completed | X16-46202 | *** | 2016-02-01 | 2016-02-07 | Project Completed |  |  | Station 9 | 100 | 0 | Station Maintenance (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items) | This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time. | SIP | Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations. |  | 9 | (X16-46202) Station 9: Station Maintenance (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items) (2/1/16 to 2/7/16) | ***Station 9: Station Maintenance (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items) --2/1/16 through 2/7/16: This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time. Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations. ***Project Completed ……………………………… | ***Station 9: Station Maintenance (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items) ***Project Completed ………………………………
| Project Completed | X15-925633 | *** | 2016-02-09 | 2016-02-11 | Project Completed |  |  | Sta. 266A | 200 | 6 | Unit Maintenance | This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. |  | 266 | (X15-925633) Sta. 266A: Unit Maintenance (2/9/16 to 2/11/16) | ***Sta. 266A: Unit Maintenance --2/9/16 through 2/11/16: This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. ***Project Completed ……………………………… | ***Sta. 266A: Unit Maintenance ***Project Completed ………………………………
| Project Completed | X15-929733 | *** | 2016-01-27 | 2016-02-10 | Project Completed |  |  | MLV 834-1 to 838-1 | 800 | 5 | ILI/Cleaning Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | To Be Determined | 834.1 | (X15-929733) MLV 834-1 to 838-1: ILI/Cleaning Pig (1/27/16 to 2/10/16) | ***MLV 834-1 to 838-1: ILI/Cleaning Pig --1/27/16 through 2/10/16: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. To Be Determined ***Project Completed ……………………………… | ***MLV 834-1 to 838-1: ILI/Cleaning Pig ***Project Completed The following meters are available for nominations: To Be Determined ………………………………
| Project Completed | X14-1562506 | *** | 2015-11-02 | 2016-02-19 | Project Completed |  |  | MLV 5-1 to 6-1 | 100 | 0 | Hydrotest | This project will require taking the pipeline section out of service. The listed meters will be shut in during the outage. This will limit throughput and may result in restrictions based on customer nominations. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | 410063 ROCHE DEHYDRATION | 5.1 | (X14-1562506) MLV 5-1 to 6-1: Hydrotest (11/2/15 to 2/19/16) | ***MLV 5-1 to 6-1: Hydrotest --11/2/15 through 2/19/16: This project will require taking the pipeline section out of service. The listed meters will be shut in during the outage. This will limit throughput and may result in restrictions based on customer nominations. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. 410063 ROCHE DEHYDRATION ***Project Completed ……………………………… | ***MLV 5-1 to 6-1: Hydrotest ***Project Completed The following meters are available for nominations: 410063 ROCHE DEHYDRATION ………………………………
| Project Completed | X14-1562506 | *** | 2015-11-02 | 2016-02-19 | Project Completed |  |  | MLV 7-1 to 9-1 | 100 | 0 | Hydrotest | This project will require taking the pipeline section out of service. The listed meters will be shut in during the outage. This will limit throughput and may result in restrictions based on customer nominations. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | 412490 Charro 421083 Eagle Ford Field Service | 5.1 | (X14-1562506) MLV 7-1 to 9-1: Hydrotest (11/2/15 to 2/19/16) | ***MLV 7-1 to 9-1: Hydrotest --11/2/15 through 2/19/16: This project will require taking the pipeline section out of service. The listed meters will be shut in during the outage. This will limit throughput and may result in restrictions based on customer nominations. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. 412490 Charro 421083 Eagle Ford Field Service ***Project Completed ……………………………… | ***MLV 7-1 to 9-1: Hydrotest ***Project Completed The following meters are available for nominations: 412490 Charro 421083 Eagle Ford Field Service ………………………………
Date change. Previously scheduled 2/18/16 to 2/20/16. | Project Completed | X15-882289 | *** | 2016-02-22 | 2016-02-24 | Project Completed | 2016-02-18 | 2016-02-20 | MLV 24-2 to 25-2S | 100 | 0 | Anomaly Remediation | This outage will require pressure reductions and possibly line isolations. However no other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | To Be Determined | 24.2 | (X15-882289) MLV 24-2 to 25-2S: Anomaly Remediation (2/22/16 to 2/24/16) | ***MLV 24-2 to 25-2S: Anomaly Remediation --2/22/16 through 2/24/16: This outage will require pressure reductions and possibly line isolations. However no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. To Be Determined ***Project Completed ……………………………… | ***MLV 24-2 to 25-2S: Anomaly Remediation ***Project Completed The following meters are available for nominations: To Be Determined ………………………………
| Project Completed | X15-925630 | *** | 2016-02-23 | 2016-02-23 | Project Completed |  |  | WORCESTER DELIVERY NO. 2 LINE (265C-101.1 to 265C-101B) | 200 | L | ILI/Cleaning Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. |  | 265.1 | (X15-925630) WORCESTER DELIVERY NO. 2 LINE (265C-101.1 to 265C-101B): ILI/Cleaning Pig (2/23/16) | ***WORCESTER DELIVERY NO. 2 LINE (265C-101.1 to 265C-101B): ILI/Cleaning Pig --2/23/16: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. ***Project Completed ……………………………… | ***WORCESTER DELIVERY NO. 2 LINE (265C-101.1 to 265C-101B): ILI/Cleaning Pig ***Project Completed ………………………………
| Project Completed | X16-23748 | *** | 2016-02-15 | 2016-02-18 | Project Completed |  |  | MLV 530-3 to 532-3 | 500 | L | ILI/Cleaning Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. |  | 530.3 | (X16-23748) MLV 530-3 to 532-3: ILI/Cleaning Pig (2/15/16 to 2/18/16) | ***MLV 530-3 to 532-3: ILI/Cleaning Pig --2/15/16 through 2/18/16: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. ***Project Completed ……………………………… | ***MLV 530-3 to 532-3: ILI/Cleaning Pig ***Project Completed ………………………………
| Project Canceled | X16-98720 | *** | 2016-03-06 | 2016-03-06 | Project Canceled |  |  | Sta. 1 | 100 | 0 | Station Maintenance | This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. |  | 1 | (X16-98720) Sta. 1: Station Maintenance (3/6/16) | ***Sta. 1: Station Maintenance --3/6/16: This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. ***Project Canceled ……………………………… | ***Sta. 1: Station Maintenance ***Project Canceled ………………………………
| Project Completed | X14-1562513 X14-1540661 | *** | 2015-07-01 | 2016-03-04 | Project Completed |  |  | Station 32 | 100 | 0 | Station Maintenance | This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. |  | 32 | (X14-1562513 X14-1540661) Station 32: Station Maintenance (7/1/15 to 3/4/16) | ***Station 32: Station Maintenance --7/1/15 through 3/4/16: This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. ***Project Completed ……………………………… | ***Station 32: Station Maintenance ***Project Completed ………………………………
| Project Canceled | X15-926822 | *** | 2016-06-06 | 2016-06-11 | Project Canceled |  |  | BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1) | 300 | 6 | Pipe Inspection | This project involves inspecting multiple sites. We do not anticipate having to do any repairs, however if a repair is needed there is a potential that the pipe may require replacement which will require isolation of the pipe. This may limit throughput and will result in restrictions based on customer nominations. Customers may experience pressure fluctuations during this timeframe. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | To Be Determined | 343.1 | (X15-926822) BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1): Pipe Inspection (6/6/16 to 6/11/16) | ***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1): Pipe Inspection --6/6/16 through 6/11/16: This project involves inspecting multiple sites. We do not anticipate having to do any repairs, however if a repair is needed there is a potential that the pipe may require replacement which will require isolation of the pipe. This may limit throughput and will result in restrictions based on customer nominations. Customers may experience pressure fluctuations during this timeframe. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. To Be Determined ***Project Canceled ……………………………… | ***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1): Pipe Inspection ***Project Canceled The following meters are available for nominations: To Be Determined ………………………………
| Project Canceled | X15-928271 | *** | TBD | TBD | Project Canceled |  |  | MLV 555-1 to 550-1 | 500 | 1 | ILI/Cleaning Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | To Be Determined | 555.1 | (X15-928271) MLV 555-1 to 550-1: ILI/Cleaning Pig (TBD) | ***MLV 555-1 to 550-1: ILI/Cleaning Pig --TBD: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. To Be Determined ***Project Canceled ……………………………… | ***MLV 555-1 to 550-1: ILI/Cleaning Pig ***Project Canceled The following meters are available for nominations: To Be Determined ………………………………
| Project Canceled | X15-928272 | *** | TBD | TBD | Project Canceled |  |  | MLV 555-2 to 550-2 | 500 | 1 | ILI/Cleaning Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | To Be Determined | 555.2 | (X15-928272) MLV 555-2 to 550-2: ILI/Cleaning Pig (TBD) | ***MLV 555-2 to 550-2: ILI/Cleaning Pig --TBD: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. To Be Determined ***Project Canceled ……………………………… | ***MLV 555-2 to 550-2: ILI/Cleaning Pig ***Project Canceled The following meters are available for nominations: To Be Determined ………………………………
| Project Canceled | X15-928273 | *** | TBD | TBD | Project Canceled |  |  | MLV 555-3 to 552-3 | 500 | 1 | ILI/Cleaning Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | To Be Determined | 555.3 | (X15-928273) MLV 555-3 to 552-3: ILI/Cleaning Pig (TBD) | ***MLV 555-3 to 552-3: ILI/Cleaning Pig --TBD: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. To Be Determined ***Project Canceled ……………………………… | ***MLV 555-3 to 552-3: ILI/Cleaning Pig ***Project Canceled The following meters are available for nominations: To Be Determined ………………………………
| Project Completed | X15-882281 | *** | 2016-02-24 | 2016-03-03 | Project Completed |  |  | 24-1A to 25-1S | 100 | 0 | Anomaly Remediation | This outage will require pressure reductions and possibly line isolations. However no other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | To Be Determined | 24.1 | (X15-882281) 24-1A to 25-1S: Anomaly Remediation (2/24/16 to 3/3/16) | ***24-1A to 25-1S: Anomaly Remediation --2/24/16 through 3/3/16: This outage will require pressure reductions and possibly line isolations. However no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. To Be Determined ***Project Completed ……………………………… | ***24-1A to 25-1S: Anomaly Remediation ***Project Completed The following meters are available for nominations: To Be Determined ………………………………
| Project Completed | X15-882291 | *** | 2016-03-03 | 2016-03-04 | Project Completed |  |  | MLV 24-3 to 25-3S | 100 | 0 | Anomaly Remediation | This outage will require pressure reductions and possibly line isolations. However no other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | To Be Determined | 24.3 | (X15-882291) MLV 24-3 to 25-3S: Anomaly Remediation (3/3/16 to 3/4/16) | ***MLV 24-3 to 25-3S: Anomaly Remediation --3/3/16 through 3/4/16: This outage will require pressure reductions and possibly line isolations. However no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. To Be Determined ***Project Completed ……………………………… | ***MLV 24-3 to 25-3S: Anomaly Remediation ***Project Completed The following meters are available for nominations: To Be Determined ………………………………
| Project Completed | X14-1178175 | *** | 2015-06-15 | 2016-03-31 | Project Completed |  |  | Station 63 | 100 | 1 | Station Maintenance | This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. |  | 63 | (X14-1178175) Station 63: Station Maintenance (6/15/15 to 3/31/16) | ***Station 63: Station Maintenance --6/15/15 through 3/31/16: This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. ***Project Completed ……………………………… | ***Station 63: Station Maintenance ***Project Completed ………………………………
| Project Cancelled | X15-913224 | *** | 2016-04-16 | 2016-05-21 | Project Cancelled |  |  | MLV 109-2 | 100 | 2 | Pipe Replacement | This project will require taking the pipeline section out of service. This will limit throughput and will result in restrictions based on customer nominations. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | To Be Determined | 109.2 | (X15-913224) MLV 109-2: Pipe Replacement (4/16/16 to 5/21/16) | ***MLV 109-2: Pipe Replacement --4/16/16 through 5/21/16: This project will require taking the pipeline section out of service. This will limit throughput and will result in restrictions based on customer nominations. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. To Be Determined ***Project Cancelled ……………………………… | ***MLV 109-2: Pipe Replacement ***Project Cancelled The following meters are available for nominations: To Be Determined ………………………………
| Project Completed | X15-926830 | *** | 2016-03-07 | 2016-03-11 | Project Completed |  |  | MLV 400-1 to 408-1 | 100 | 0 | ILI/Cleaning Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. | SIP | Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations. | To Be Determined | 400.1 | (X15-926830) MLV 400-1 to 408-1: ILI/Cleaning Pig (3/7/16 to 3/11/16) | ***MLV 400-1 to 408-1: ILI/Cleaning Pig --3/7/16 through 3/11/16: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations. To Be Determined ***Project Completed ……………………………… | ***MLV 400-1 to 408-1: ILI/Cleaning Pig ***Project Completed The following meters are available for nominations: To Be Determined ………………………………
| Project Cancelled | X16-143836 | *** | 2016-03-28 | 2016-04-04 | Project Cancelled |  |  | Sta. 409 | 100 | 0 | Unit Maintenance | This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations. | SIP | Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations. |  | 409 | (X16-143836) Sta. 409: Unit Maintenance (3/28/16 to 4/4/16) | ***Sta. 409: Unit Maintenance --3/28/16 through 4/4/16: This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations. Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations. ***Project Cancelled ……………………………… | ***Sta. 409: Unit Maintenance ***Project Cancelled ………………………………
| Project Cancelled | X15-929680 | *** | 2016-04-18 | 2016-04-27 | Project Cancelled |  |  | SABINE - KINDER LINE to 822-1 | 800 | L | Anomaly Remediation | This outage will require pressure reductions and possibly line isolations. However no other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | To Be Determined | 822.1 | (X15-929680) SABINE - KINDER LINE to 822-1: Anomaly Remediation (4/18/16 to 4/27/16) | ***SABINE - KINDER LINE to 822-1: Anomaly Remediation --4/18/16 through 4/27/16: This outage will require pressure reductions and possibly line isolations. However no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. To Be Determined ***Project Cancelled ……………………………… | ***SABINE - KINDER LINE to 822-1: Anomaly Remediation ***Project Cancelled The following meters are available for nominations: To Be Determined ………………………………

## Sheet1
Updated | 2024-05-09
Natural Gas Pipeline 2024 Pipeline Outage and Maintenance Summary
This is a summary of the current status of NGPL Pipeline Outages and Maintenance Projects. This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions. Additionally, anticipated impact and restrictions are subject to change. *Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project. *Unless otherwise noted, all scheduled dates represent gas days as defined in the Natural Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time). *Typical Timeline for ILI reporting is below.
Type of In-Line Inspection tool | # of weeks to determine a successful run | # of weeks to Preliminary Report | # of Weeks to Final Aligned Report
MFL | 1-2 | 3-4 | 8-13
AFD | 2-3 | 3-4 | 12-16
EMAT | 2-3 | N/A | 17-30
*** Indicates revision | [17 empty] | \\houCORP\TRANS\TRANSERVICES\OPPLAN\COMMON\Outages\NGPL
Outage # | Revised | Start Date | End Date | Reason Changed | Prev. Start Date | Prev. End Date | System | Line | Segment | Location | Scheduling Location | Maintenance Activity | Restriction Level | Pool Location | Meter(s) in Impacted Area
X20-877776 |  | 2020-09-24 | UFN |  |  |  | AM | INDIAN BASIN | 7 | CS 167 | CS 167 | Force Majeure - See latest Force Majeure Posting on Natural's EBB | Effective for gas day Thursday, September 24, 2020, Intraday 1 Cycle, Natural will schedule all transports to 0% of contract MDQ into and out of Segment 7. Segment 8 and Segment 9 of the Permian Zone are not impacted by this force majeure event. |  |  |  | 100
X23-374812 |  | 2023-04-06 | 2024-07-31 |  |  |  | AM |  | 8 | 168 |  | Station Maintenance | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  |  | 0
X24-373725 |  | 2024-04-03 | 2024-05-16 |  |  |  | MKT | ILLINOIS LATERAL #2 | 29 | 110 | TBD | Pipeline Integrity | If remediation is required, all transport services are at risk of not being fully scheduled. |  |  |  | 0
X23-867709 | *** | 2024-04-07 | 2024-06-16 | Project Change |  | 2024-05-26 | GC | LA #2 | 25 | 302/343 | 302 | LA #2 Hydrotest Phase 3 | Primary/SIP Firm transports will be scheduled to no less than 65.6% of contract MDQ eastbound through CS 302 . AOR/ITS and Secondary out-of-path Firm transports are not available. Firm transportation associated with storage injections or withdrawals may be impacted. | TEXOK GC: West of Constraint |  | ----end_date--------prl----model_loc-- | 66
X23-1281370 | *** | 2024-04-10 | 2024-05-09 | Completed |  |  | GC | GC #2 | 22 | 301/300 | TBD | Pipeline Integrity | If remediation is required, all transport services are at risk of not being fully scheduled. |  |  | ------ | 0
X23-1152941 | *** | 2024-04-15 | 2024-05-29 | Project Change |  | 2024-05-15 | GC | GC #2 | 22 | 302/301 | TBD | Pipeline Integrity | If remediation is required, all transport services are at risk of not being fully scheduled. |  |  | ----end_date------------model_loc-- | 0
X24-361818 |  | 2024-04-16 | 2024-05-30 |  |  |  | AM | OE #2 | 6 | 154 |  | ILI Tool Runs - Cleaning/Gauge 4/16, AFD 5/28, Caliper 5/29, EMAT 5/30 | No anticpated impact |  |  |  | 0
X23-1238630 |  | 2024-04-22 | 2024-06-07 |  |  |  | GC | GC #1 | 27 | 306 | TBD | Pipeline Integrity | If remediation is required, all transport services are at risk of not being fully scheduled. |  |  |  | 0
X24-449139 | *** | 2024-04-26 | UFN | Project Change |  |  | AM | LOCKRIDGE LATERAL | 9 | Lockridge Lateral | LOC 47662 | Force Majeure | LOC 47662 ATMOS PYOTE is unavailable. No transport services will be scheduled. |  | LOC 47662 ATMOS PYOTE | ------meters_affected------prl----model_loc-- | 0
X24-105782 | *** | 2024-04-27 | 2024-05-18 | Project Change |  | 2024-05-13 | GC | GC #3 | 26 | 303 |  | Pipeline Maintenance | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | ----end_date------------model_loc-- | 0
X23-1259804 |  | 2024-04-29 | 2024-05-31 |  |  |  | GC | GC #3 | 27 | 307 |  | Pipeline Maintenance | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  |  | 0
X23-1041160 | *** | 2024-04-29 | 2024-05-09 | Project Change |  | 2024-05-08 | GC | GC #3 | 28 | 310 |  | ILI Tool Runs - Cleaning 4/29 to 4/30, Cleaning/Gauge 5/2 to 5/3, MFL/Caliper 5/8 to 5/9 | No anticipated impact |  |  | ----end_date------mantenance_desc------model_loc-- | 0
X23-1130721 | *** | 2024-04-30 | 2024-05-03 | Completed |  |  | GC | AG #2 | 17 | 802 |  | ILI Tool Runs - Cleaning/Gauge 4/30, Cleaning 5/1, MFL/Caliper 5/3 | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | ------ | 0
X23-1095358 |  | 2024-04-30 | 2024-05-10 |  |  |  | MKT | HERSCHER DISCHARGE | 35 | 201/113 |  | Pipeline Maintenance | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  |  | 0
X23-983361 | *** | 2024-05-01 | 2024-05-04 | Completed |  |  | AM | AMA#4 | 14 | 113 | TBD | Pipeline Integrity | If remediation is required, all transport services are at risk of not being fully scheduled. |  |  | ------ | 0
X23-983379 | *** | 2024-05-06 | 2024-05-15 | Project Change |  | 2024-05-10 | AM | DAVENPORT #2 | 14 | 110 | TBD | Pipeline Integrity | If remediation is required, all transport services are at risk of not being fully scheduled. |  |  | ----end_date------------model_loc-- | 0
X23-1142520 |  | 2024-05-07 | 2024-05-23 |  |  |  | AM | AM #3 | 11 | 102/103 | 103 | ILI Tool Runs - Cleaning/Gauge 5/7 to 5/8, Cleaning 5/9 to 5/10, AFD 5/14 to 5/15, EMAT 5/21 to 5/23 | Primary/SIP Firm transports will be scheduled to no less than 65% of contract MDQ through CS 103. AOR/ITS and Secondary out-of-path Firm transports are not available. Firm transportation associated with storage injections or withdrawals may be impacted. | Midcontinent: South of Constraint |  |  | 65
X24-167078 |  | 2024-05-08 | 2024-05-14 |  |  |  | AM | PERMIAN #1 | 8 | 169 | Permian Zone Border | Pipeline Maintenance | Primary/SIP Firm transports will be scheduled to no less than 0% of contract MDQ north and southbound though the Permain Zone Border. AOR/ITS and Secondary out-of-path Firm transports are not available. Firm transportation associated with storage injections or withdrawals may be impacted. | Permian: South of Constraint |  |  | 0
X23-1025124 | *** | 2024-05-11 | 2024-05-21 | Project Change | 2024-04-30 | 2024-05-14 | MKT | ILL #1 | 29 | 110 | TBD | Pipeline Integrity | If remediation is required, all transport services are at risk of not being fully scheduled. |  |  | --start_date--end_date------------model_loc-- | 0
X23-1035082 |  | 2024-05-13 | 2024-05-18 |  |  |  | GC | GC #2 | 27 | 308/309 | TBD | Pipeline Integrity | If remediation is required, all transport services are at risk of not being fully scheduled. |  |  |  | 0
X24-428590 |  | 2024-05-15 | 2024-05-23 |  |  |  | AM | O/E #1 | 2 | 156/801 | LOC 44652, LOC 48931, LOC 3661 | ILI Tool Runs - Cleaning 5/15, AFD 5/23 | The following locations are unavailable: LOC 44652 TARGA STEPHENS, LOC 48931 ET G&P COX CITY GRADY, LOC 3661 BOUNTY CADDO. No transport services will be scheduled. |  | LOC 44652 TARGA STEPHENS, LOC 48931 ET G&P COX CITY GRADY, LOC 3661 BOUNTY CADDO |  | 0
X24-484681 |  | 2024-05-16 | 2024-05-19 |  |  |  | AM |  | 11 | 103 |  | Station Maintenance | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  |  | 0
X24-72953 | *** | 2024-05-17 | 2024-05-24 | Project Change | 2024-05-14 | 2024-05-21 | GC | GC #3 | 26 | 303 | 303 | Pipeline Maintenance | Primary/SIP Firm transports will be scheduled to no less than 69% of contract MDQ through CS 303. AOR/ITS and Secondary out-of-path Firm transports are not available. Firm transportation associated with storage injections or withdrawals may be impacted. | TEXOK GC: North of Constraint |  | --start_date--end_date------------model_loc-- | 69
X23-1025115 | *** | 2024-05-27 | 2024-06-04 | Project Change |  | 2024-05-31 | GC | GC#3 | 28 | 311 | TBD | Pipeline Integrity | If remediation is required, all transport services are at risk of not being fully scheduled. |  |  | ----end_date------------model_loc-- | 0
X23-1035246 |  | 2024-05-28 | 2024-06-04 |  |  |  | AM | AMA#2 | 13 | 108/109 | TBD | Pipeline Integrity | If remediation is required, all transport services are at risk of not being fully scheduled. |  |  |  | 0
X23-1173954 |  | 2024-05-28 | 2024-05-31 |  |  |  | GC | GC #1 | 26 | 303/302 | TBD | Pipeline Integrity | If remediation is required, all transport services are at risk of not being fully scheduled. |  |  |  | 0
X23-1026485 | *** | 2024-05-30 | 2024-06-05 | Project Change | 2024-05-03 | 2024-05-14 | MKT | HERSCHER SUCTION | 34 | 201 | TBD | Pipeline Integrity | If remediation is required, all transport services are at risk of not being fully scheduled. |  |  | --start_date--end_date------------model_loc-- | 0
X23-1196902 |  | 2024-06-03 | 2024-06-07 |  |  |  | GC |  | 22 | 301 |  | Unit Maintenance | No anticipated impact |  |  |  | 0
X24-144539 |  | 2024-06-03 | 2024-07-12 |  |  |  | GC | GC #2 | 28 | 310 |  | Pipeline Maintenance | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  |  | 0
X23-983521 | *** | 2024-06-03 | 2024-06-05 | Completed |  |  | MKT | VOLO #2 | 40 | 113 | TBD | Pipeline Integrity | If remediation is required, all transport services are at risk of not being fully scheduled. |  |  | ------ | 0
X23-1152983 |  | 2024-06-04 | 2024-07-31 |  |  |  | GC | GC #1 | 22 | 302/301 | TBD | Pipeline Integrity | If remediation is required, all transport services are at risk of not being fully scheduled. |  |  |  | 0
X23-1130710 |  | 2024-06-04 | 2024-06-12 |  |  |  | GC | GC #1 | 26 | 304/303 |  | ILI Tool Runs - Cleaning/Guage 6/4 to 6/5, Cleaning 6/6 to 6/7, MFL/Caliper/Hardspot 6/11 to 6/12 | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  |  | 0
X23-1038163 |  | 2024-06-04 | 2024-06-12 |  |  |  | GC | GC#1 | 27 | 307 |  | ILI Tool Runs - Cleaning/Guage 6/4 to 6/5, Cleaning 6/6 to 6/7, MFL/Caliper 6/11 to 6/12 | No anticipated impact |  |  |  | 0
X23-1026486 | *** | 2024-06-06 | 2024-06-12 | Project Change | 2024-05-15 | 2024-05-22 | GC |  | 28 | 312 | TBD | Pipeline Integrity | If remediation is required, all transport services are at risk of not being fully scheduled. |  |  | --start_date--end_date------------model_loc-- | 0
X23-1142512 |  | 2024-06-11 | 2024-06-21 |  |  |  | AM | AM #3 | 11 | 103/104 | 103/104 | ILI Tool Runs - Cleaning/Gauge 6/11, Cleaning 6/13, MFL/Caliper 6/18, AFD 6/20 | Primary/SIP Firm transports will be scheduled to no less than 44% of contract MDQ through CS 104. AOR/ITS and Secondary out-of-path Firm transports are not available. Firm transportation associated with storage injections or withdrawals may be impacted. | Midcontinent: South of Constraint |  |  | 44
X23-1152980 |  | 2024-06-15 | 2024-06-28 |  |  |  | GC | GC #1 | 27 | 307 | TBD | Pipeline Integrity | If remediation is required, all transport services are at risk of not being fully scheduled. |  |  |  | 0
X23-867716 | *** | 2024-06-17 | 2024-06-18 | Project Change | 2024-05-27 | 2024-05-28 | GC | LA #2 | 25 | 302/343 | 302 | LA #2 Hydrotest Phase 4 | Primary/SIP Firm transports will be scheduled to no less than 56% of contract MDQ eastbound through CS 302 . AOR/ITS and Secondary out-of-path Firm transports are not available. Firm transportation associated with storage injections or withdrawals may be impacted. | TEXOK GC: West of Constraint |  | --start_date--end_date------------model_loc-- | 56
X24-494722 | *** | 2024-06-18 | 2024-07-11 | Added |  |  | AM | AM #2 | 14 | 109 |  | ILI Tool Runs - Cleaning/Gauge 6/18, Cleaning 6/20, Caliper 7/9, AFD 7/11 | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | ------ | 0
X23-1130713 |  | 2024-06-18 | 2024-06-26 |  |  |  | GC | GC #2 | 26 | 303 |  | ILI Tool Runs - Cleaning/Gauge 6/18 to 6/19, Cleaning 6/20 to 6/21, MFL/Caliper 6/25 to 6/26 | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  |  | 0
X23-867714 | *** | 2024-06-19 | 2024-06-21 | Project Change | 45441 | 45443 | GC | LA #2 | 25 | 302/343 | 302 | LA #2 Hydrotest Phase 5 | Primary/SIP Firm transports will be scheduled to no less than 80% of contract MDQ eastbound through CS 302 . AOR/ITS and Secondary out-of-path Firm transports are not available. Firm transportation associated with storage injections or withdrawals may be impacted. | TEXOK GC: West of Constraint |  | --start_date--end_date------------model_loc-- | 80
X23-1130724 |  | 2024-06-20 | 2024-06-26 |  |  |  | GC | AG #1 | 17 | 802/803 |  | ILI Tool Runs - Cleaning/Gauge 6/20 to 6/21, MFL/Caliper 6/25 to 6/26 | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  |  | 0
X23-1142524 | *** | 2024-06-25 | 2024-07-09 | Project Change |  |  | AM | AM #3 | 12 | 106 | 106 | ILI Tool Runs - Cleaning/Gauge 6/25, Cleaning - 6/27, AFD 7/9 | Primary/SIP Firm transports will be scheduled to no less than 87% of contract MDQ through CS 106. AOR/ITS and Secondary out-of-path Firm transports are not available. Firm transportation associated with storage injections or withdrawals may be impacted. | Midcontinent: South of Constraint |  | --------------NGPL_percent_cap--model_loc-- | 87
X24-402028 |  | 2024-07-08 | 2024-07-15 |  |  |  | AM |  | 11 | 105 |  | Station Maintenance | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  |  | 0
X24-72963 |  | 2024-07-08 | 2024-07-18 |  |  |  | GC | GC #1 | 26 | 303 |  | Pipeline Maintenance | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  |  | 0
X23-1130714 |  | 2024-07-09 | 2024-07-24 |  |  |  | GC | GC #2 | 27 | 306 |  | ILI Tool Runs - Cleaning/Gauge 7/9 to 7/10, Cleaning 7/11 to 7/12, AFD 7/16 to 7/17, EMAT 7/18 to 7/19, MFL/Caliper 7/23 to 7/24 | No anticipated impact |  |  |  | 0
X23-1232810 |  | 2024-07-10 | 2024-07-20 |  |  |  | GC | HAGIST RANCH LATERAL | 21 | 341 |  | ILI Tool Runs - Cleaning/Gauge 7/10, Cleaning 7/11, Cleaning 7/12, Cleaning 7/14, MFL/Caliper 7/18. AFD 7/19, EMAT 7/20 | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  |  | 0
X23-1152986 |  | 2024-07-15 | 2024-08-30 |  |  |  | AM | OE #1 | 2 | 156/801 | TBD | Pipeline Integrity | If remediation is required, all transport services are at risk of not being fully scheduled. |  |  |  | 0
X23-1259807 |  | 2024-07-15 | 2024-09-02 |  |  |  | GC | GC #2 | 27 | 307 |  | Pipeline Maintenance | No anticipated impact |  |  |  | 0
X23-1028146 |  | 2024-07-15 | 2024-07-23 |  |  |  | GC |  | 28 | 113 | TBD | Pipeline Integrity | If remediation is required, all transport services are at risk of not being fully scheduled. |  |  |  | 0
X23-1041062 |  | 2024-07-15 | 2024-07-25 |  |  |  | GC | GC #1 | 28 | 310 |  | ILI Tool Runs - Cleaning 7/15, Cleaning/Gauge 7/17, MFL/Caliper 7/23, AFD 7/25 | No anticipated impact |  |  |  | 0
X24-144536 |  | 2024-07-15 | 2024-08-23 |  |  |  | GC | GC #1 | 28 | 310 |  | Pipeline Maintenance | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  |  | 0
X23-1238542 |  | 2024-07-22 | 2024-07-25 |  |  |  | AM | AM #2 | 11 | 105 |  | ILI Tool Runs - Cleaning/Gauge 7/22, Cleaning 7/23, Cleaning 7/24, AFD 7/25 | No anticipated impact |  |  |  | 0
X23-1259780 |  | 2024-07-22 | 2024-09-30 |  |  |  | GC | GC #1 | 27 | 308 |  | Install Launcher and Receiver | No anticipated impact |  |  |  | 0
X23-1028147 |  | 2024-07-24 | 2024-07-31 |  |  |  | MKT | CALUMET #1 | 32 | 113 | TBD | Pipeline Integrity | If remediation is required, all transport services are at risk of not being fully scheduled. |  |  |  | 0
X23-1035248 |  | 2024-07-29 | 2024-08-06 |  |  |  | AM | AMA#4 | 14 | 109 | TBD | Pipeline Integrity | If remediation is required, all transport services are at risk of not being fully scheduled. |  |  |  | 0
X23-1075687 |  | 2024-08-19 | 2024-08-27 |  |  |  | AM | AMA#4 | 13 | 108 |  | ILI Tool Runs - Cleaning/Gauge 8/19, Cleaning 8/21, MFL/Caliper 8/27 | No anticipated impact |  |  |  | 0
X23-1152910 |  | 2024-09-03 | 2024-10-25 |  |  |  | AM | AM #2 | 11 | 104 | TBD | Pipeline Integrity | If remediation is required, all transport services are at risk of not being fully scheduled. |  |  |  | 0
X23-1173951 |  | 2024-10-04 | 2024-10-15 |  |  |  | GC | LA #1 | 25 | 302/343 | 302 | ILI Tool Runs - Cleaning 10/4, Cleaning 10/8, Cleaning/Gauge 10/9, AFD 10/15 | Primary/SIP Firm transports will be scheduled to no less than 74% of contract MDQ through CS 302. AOR/ITS and Secondary out-of-path Firm transports are not available. Firm transportation associated with storage injections or withdrawals may be impacted. | TEXOK GC: West of Constraint |  |  | 74
X23-1062843 | *** | 2024-11-19 | 2024-11-20 | Added |  |  | AM | AM #2 | 11 | 103/104 |  | ILI Tool Run - EMAT 11/19 to 11/20 | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | ------ | 0