## Closed (hidden)
|  |  | Updated | 2016
Tennessee Gas Pipeline 2015 Pipeline Outage and Maintenance Summary
This is a summary of the current status of all TGP Winter 2014-2015 Pipeline Outages and Maintenance Projects. This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions. Additionally, anticipated impact and restrictions are subject to change. *Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project. *Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time).
*** Indicates revision
Date Change | Project New/Completed/Closed | Outage # | Revised | Start Date | End Date | Reason Changed | Prev. Start Date | Prev. End Date | Location | Leg | Zone | Maintenance Activity | Anticipated Impact | Potential Restriction Level | TOS Potential Restrictions | Meter(s) in Impacted Area | Customer Notifications | Loc | Email Text | Posting Text | Completion Text
| Project Completed |  | *** | 2015-01-11 | 2016-01-11 | Project Completed |  |  | MS #412494 DCP Warren | 400 | 0 | Meter Station | This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | 412494 DCP Warren | 401 | () MS #412494 DCP Warren: Meter Station (1/11/15 to 1/11/16) | ***MS #412494 DCP Warren: Meter Station --1/11/15 through 1/11/16: This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. 412494 DCP Warren ***Project Completed ……………………………… | ***MS #412494 DCP Warren: Meter Station ***Project Completed The following meters are available for nominations: 412494 DCP Warren ………………………………
| Project Completed |  | *** | 2015-01-11 | 2016-01-11 | Project Completed |  |  | MS #412400 King Ranch | 400 | 0 | Meter Station | This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | 412400 King Ranch | 402.1 | () MS #412400 King Ranch: Meter Station (1/11/15 to 1/11/16) | ***MS #412400 King Ranch: Meter Station --1/11/15 through 1/11/16: This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. 412400 King Ranch ***Project Completed ……………………………… | ***MS #412400 King Ranch: Meter Station ***Project Completed The following meters are available for nominations: 412400 King Ranch ………………………………
| Project Completed |  | *** | 2015-01-12 | 2016-01-12 | Project Completed |  |  | MS #410539 Duvak Gas Gathering | 400 | 0 | Meter Station | This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | 410539 Duvak Gas Gathering | 402.1 | () MS #410539 Duvak Gas Gathering: Meter Station (1/12/15 to 1/12/16) | ***MS #410539 Duvak Gas Gathering: Meter Station --1/12/15 through 1/12/16: This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. 410539 Duvak Gas Gathering ***Project Completed ……………………………… | ***MS #410539 Duvak Gas Gathering: Meter Station ***Project Completed The following meters are available for nominations: 410539 Duvak Gas Gathering ………………………………
| Project Completed |  | *** | 2015-01-13 | 2016-01-13 | Project Completed |  |  | MS #412356 DCP LaGloria | 400 | 0 | Meter Station | This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | 412356 DCP LaGloria | 403.1 | () MS #412356 DCP LaGloria: Meter Station (1/13/15 to 1/13/16) | ***MS #412356 DCP LaGloria: Meter Station --1/13/15 through 1/13/16: This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. 412356 DCP LaGloria ***Project Completed ……………………………… | ***MS #412356 DCP LaGloria: Meter Station ***Project Completed The following meters are available for nominations: 412356 DCP LaGloria ………………………………
| Project Completed |  | *** | 2015-01-13 | 2016-01-13 | Project Completed |  |  | MS #410173 Enterprise LaReforma | 400 | 0 | Meter Station | This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | 410173 Enterprise LaReforma | 406.1 | () MS #410173 Enterprise LaReforma: Meter Station (1/13/15 to 1/13/16) | ***MS #410173 Enterprise LaReforma: Meter Station --1/13/15 through 1/13/16: This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. 410173 Enterprise LaReforma ***Project Completed ……………………………… | ***MS #410173 Enterprise LaReforma: Meter Station ***Project Completed The following meters are available for nominations: 410173 Enterprise LaReforma ………………………………
| Project Completed |  | *** | 2015-01-12 | 2016-01-12 | Project Completed |  |  | MS #411903 Enterprise El Benito | 400 | 0 | Meter Station | This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | 411903 Enterprise El Benito | 407.1 | () MS #411903 Enterprise El Benito: Meter Station (1/12/15 to 1/12/16) | ***MS #411903 Enterprise El Benito: Meter Station --1/12/15 through 1/12/16: This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. 411903 Enterprise El Benito ***Project Completed ……………………………… | ***MS #411903 Enterprise El Benito: Meter Station ***Project Completed The following meters are available for nominations: 411903 Enterprise El Benito ………………………………
| Project Completed |  | *** | 2015-01-11 | 2016-01-11 | Project Completed |  |  | MS #412088 Enterprise Sullivan | 400 | 0 | Meter Station | This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | 412088 Enterprise Sullivan | 407.1 | () MS #412088 Enterprise Sullivan: Meter Station (1/11/15 to 1/11/16) | ***MS #412088 Enterprise Sullivan: Meter Station --1/11/15 through 1/11/16: This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. 412088 Enterprise Sullivan ***Project Completed ……………………………… | ***MS #412088 Enterprise Sullivan: Meter Station ***Project Completed The following meters are available for nominations: 412088 Enterprise Sullivan ………………………………
| Project Completed |  | *** | 2015-01-11 | 2016-01-11 | Project Completed |  |  | MS #412683 HESCO | 400 | 0 | Meter Station | This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | 412683 HESCO | 408.1 | () MS #412683 HESCO: Meter Station (1/11/15 to 1/11/16) | ***MS #412683 HESCO: Meter Station --1/11/15 through 1/11/16: This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. 412683 HESCO ***Project Completed ……………………………… | ***MS #412683 HESCO: Meter Station ***Project Completed The following meters are available for nominations: 412683 HESCO ………………………………
| Project Completed | X16-36843 | *** | 2016-01-27 | 2016-01-27 | Project Completed |  |  | Sta. 237 | 200 | 5 | Unit Maintenance | This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. |  | 237 | (X16-36843) Sta. 237: Unit Maintenance (1/27/16) | ***Sta. 237: Unit Maintenance --1/27/16: This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. ***Project Completed ……………………………… | ***Sta. 237: Unit Maintenance ***Project Completed ………………………………
| Project Completed | X14-1478563 | *** | 2015-11-16 | 2016-02-12 | Project Completed |  |  | MLV 32-1D to 33-1 | 100 | 0 | Hydrotest | This project will require taking the pipeline section out of service. This will limit throughput and may result in restrictions based on customer nominations. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. |  | 32.2 | (X14-1478563) MLV 32-1D to 33-1: Hydrotest (11/16/15 to 2/12/16) | ***MLV 32-1D to 33-1: Hydrotest --11/16/15 through 2/12/16: This project will require taking the pipeline section out of service. This will limit throughput and may result in restrictions based on customer nominations. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. ***Project Completed ……………………………… | ***MLV 32-1D to 33-1: Hydrotest ***Project Completed ………………………………
| Project Completed | X16-16074 |  | 2016-01-18 | 2016-01-28 | Project Completed |  |  | Station 550 | 500 | 1 | Station Maintenance | This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. |  | 550 | (X16-16074) Station 550: Station Maintenance (1/18/16 to 1/28/16) | Station 550: Station Maintenance --1/18/16 through 1/28/16: This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. ***Project Completed ……………………………… | Station 550: Station Maintenance ***Project Completed ………………………………
| Project Completed | X16-46202 | *** | 2016-02-01 | 2016-02-07 | Project Completed |  |  | Station 9 | 100 | 0 | Station Maintenance (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items) | This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time. | SIP | Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations. |  | 9 | (X16-46202) Station 9: Station Maintenance (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items) (2/1/16 to 2/7/16) | ***Station 9: Station Maintenance (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items) --2/1/16 through 2/7/16: This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time. Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations. ***Project Completed ……………………………… | ***Station 9: Station Maintenance (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items) ***Project Completed ………………………………
| Project Completed | X15-925633 | *** | 2016-02-09 | 2016-02-11 | Project Completed |  |  | Sta. 266A | 200 | 6 | Unit Maintenance | This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. |  | 266 | (X15-925633) Sta. 266A: Unit Maintenance (2/9/16 to 2/11/16) | ***Sta. 266A: Unit Maintenance --2/9/16 through 2/11/16: This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. ***Project Completed ……………………………… | ***Sta. 266A: Unit Maintenance ***Project Completed ………………………………
| Project Completed | X15-929733 | *** | 2016-01-27 | 2016-02-10 | Project Completed |  |  | MLV 834-1 to 838-1 | 800 | 5 | ILI/Cleaning Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | To Be Determined | 834.1 | (X15-929733) MLV 834-1 to 838-1: ILI/Cleaning Pig (1/27/16 to 2/10/16) | ***MLV 834-1 to 838-1: ILI/Cleaning Pig --1/27/16 through 2/10/16: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. To Be Determined ***Project Completed ……………………………… | ***MLV 834-1 to 838-1: ILI/Cleaning Pig ***Project Completed The following meters are available for nominations: To Be Determined ………………………………
| Project Completed | X14-1562506 | *** | 2015-11-02 | 2016-02-19 | Project Completed |  |  | MLV 5-1 to 6-1 | 100 | 0 | Hydrotest | This project will require taking the pipeline section out of service. The listed meters will be shut in during the outage. This will limit throughput and may result in restrictions based on customer nominations. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | 410063 ROCHE DEHYDRATION | 5.1 | (X14-1562506) MLV 5-1 to 6-1: Hydrotest (11/2/15 to 2/19/16) | ***MLV 5-1 to 6-1: Hydrotest --11/2/15 through 2/19/16: This project will require taking the pipeline section out of service. The listed meters will be shut in during the outage. This will limit throughput and may result in restrictions based on customer nominations. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. 410063 ROCHE DEHYDRATION ***Project Completed ……………………………… | ***MLV 5-1 to 6-1: Hydrotest ***Project Completed The following meters are available for nominations: 410063 ROCHE DEHYDRATION ………………………………
| Project Completed | X14-1562506 | *** | 2015-11-02 | 2016-02-19 | Project Completed |  |  | MLV 7-1 to 9-1 | 100 | 0 | Hydrotest | This project will require taking the pipeline section out of service. The listed meters will be shut in during the outage. This will limit throughput and may result in restrictions based on customer nominations. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | 412490 Charro 421083 Eagle Ford Field Service | 5.1 | (X14-1562506) MLV 7-1 to 9-1: Hydrotest (11/2/15 to 2/19/16) | ***MLV 7-1 to 9-1: Hydrotest --11/2/15 through 2/19/16: This project will require taking the pipeline section out of service. The listed meters will be shut in during the outage. This will limit throughput and may result in restrictions based on customer nominations. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. 412490 Charro 421083 Eagle Ford Field Service ***Project Completed ……………………………… | ***MLV 7-1 to 9-1: Hydrotest ***Project Completed The following meters are available for nominations: 412490 Charro 421083 Eagle Ford Field Service ………………………………
Date change. Previously scheduled 2/18/16 to 2/20/16. | Project Completed | X15-882289 | *** | 2016-02-22 | 2016-02-24 | Project Completed | 2016-02-18 | 2016-02-20 | MLV 24-2 to 25-2S | 100 | 0 | Anomaly Remediation | This outage will require pressure reductions and possibly line isolations. However no other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | To Be Determined | 24.2 | (X15-882289) MLV 24-2 to 25-2S: Anomaly Remediation (2/22/16 to 2/24/16) | ***MLV 24-2 to 25-2S: Anomaly Remediation --2/22/16 through 2/24/16: This outage will require pressure reductions and possibly line isolations. However no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. To Be Determined ***Project Completed ……………………………… | ***MLV 24-2 to 25-2S: Anomaly Remediation ***Project Completed The following meters are available for nominations: To Be Determined ………………………………
| Project Completed | X15-925630 | *** | 2016-02-23 | 2016-02-23 | Project Completed |  |  | WORCESTER DELIVERY NO. 2 LINE (265C-101.1 to 265C-101B) | 200 | L | ILI/Cleaning Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. |  | 265.1 | (X15-925630) WORCESTER DELIVERY NO. 2 LINE (265C-101.1 to 265C-101B): ILI/Cleaning Pig (2/23/16) | ***WORCESTER DELIVERY NO. 2 LINE (265C-101.1 to 265C-101B): ILI/Cleaning Pig --2/23/16: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. ***Project Completed ……………………………… | ***WORCESTER DELIVERY NO. 2 LINE (265C-101.1 to 265C-101B): ILI/Cleaning Pig ***Project Completed ………………………………
| Project Completed | X16-23748 | *** | 2016-02-15 | 2016-02-18 | Project Completed |  |  | MLV 530-3 to 532-3 | 500 | L | ILI/Cleaning Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. |  | 530.3 | (X16-23748) MLV 530-3 to 532-3: ILI/Cleaning Pig (2/15/16 to 2/18/16) | ***MLV 530-3 to 532-3: ILI/Cleaning Pig --2/15/16 through 2/18/16: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. ***Project Completed ……………………………… | ***MLV 530-3 to 532-3: ILI/Cleaning Pig ***Project Completed ………………………………
| Project Canceled | X16-98720 | *** | 2016-03-06 | 2016-03-06 | Project Canceled |  |  | Sta. 1 | 100 | 0 | Station Maintenance | This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. |  | 1 | (X16-98720) Sta. 1: Station Maintenance (3/6/16) | ***Sta. 1: Station Maintenance --3/6/16: This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. ***Project Canceled ……………………………… | ***Sta. 1: Station Maintenance ***Project Canceled ………………………………
| Project Completed | X14-1562513 X14-1540661 | *** | 2015-07-01 | 2016-03-04 | Project Completed |  |  | Station 32 | 100 | 0 | Station Maintenance | This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. |  | 32 | (X14-1562513 X14-1540661) Station 32: Station Maintenance (7/1/15 to 3/4/16) | ***Station 32: Station Maintenance --7/1/15 through 3/4/16: This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. ***Project Completed ……………………………… | ***Station 32: Station Maintenance ***Project Completed ………………………………
| Project Canceled | X15-926822 | *** | 2016-06-06 | 2016-06-11 | Project Canceled |  |  | BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1) | 300 | 6 | Pipe Inspection | This project involves inspecting multiple sites. We do not anticipate having to do any repairs, however if a repair is needed there is a potential that the pipe may require replacement which will require isolation of the pipe. This may limit throughput and will result in restrictions based on customer nominations. Customers may experience pressure fluctuations during this timeframe. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | To Be Determined | 343.1 | (X15-926822) BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1): Pipe Inspection (6/6/16 to 6/11/16) | ***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1): Pipe Inspection --6/6/16 through 6/11/16: This project involves inspecting multiple sites. We do not anticipate having to do any repairs, however if a repair is needed there is a potential that the pipe may require replacement which will require isolation of the pipe. This may limit throughput and will result in restrictions based on customer nominations. Customers may experience pressure fluctuations during this timeframe. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. To Be Determined ***Project Canceled ……………………………… | ***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1): Pipe Inspection ***Project Canceled The following meters are available for nominations: To Be Determined ………………………………
| Project Canceled | X15-928271 | *** | TBD | TBD | Project Canceled |  |  | MLV 555-1 to 550-1 | 500 | 1 | ILI/Cleaning Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | To Be Determined | 555.1 | (X15-928271) MLV 555-1 to 550-1: ILI/Cleaning Pig (TBD) | ***MLV 555-1 to 550-1: ILI/Cleaning Pig --TBD: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. To Be Determined ***Project Canceled ……………………………… | ***MLV 555-1 to 550-1: ILI/Cleaning Pig ***Project Canceled The following meters are available for nominations: To Be Determined ………………………………
| Project Canceled | X15-928272 | *** | TBD | TBD | Project Canceled |  |  | MLV 555-2 to 550-2 | 500 | 1 | ILI/Cleaning Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | To Be Determined | 555.2 | (X15-928272) MLV 555-2 to 550-2: ILI/Cleaning Pig (TBD) | ***MLV 555-2 to 550-2: ILI/Cleaning Pig --TBD: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. To Be Determined ***Project Canceled ……………………………… | ***MLV 555-2 to 550-2: ILI/Cleaning Pig ***Project Canceled The following meters are available for nominations: To Be Determined ………………………………
| Project Canceled | X15-928273 | *** | TBD | TBD | Project Canceled |  |  | MLV 555-3 to 552-3 | 500 | 1 | ILI/Cleaning Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | To Be Determined | 555.3 | (X15-928273) MLV 555-3 to 552-3: ILI/Cleaning Pig (TBD) | ***MLV 555-3 to 552-3: ILI/Cleaning Pig --TBD: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. To Be Determined ***Project Canceled ……………………………… | ***MLV 555-3 to 552-3: ILI/Cleaning Pig ***Project Canceled The following meters are available for nominations: To Be Determined ………………………………
| Project Completed | X15-882281 | *** | 2016-02-24 | 2016-03-03 | Project Completed |  |  | 24-1A to 25-1S | 100 | 0 | Anomaly Remediation | This outage will require pressure reductions and possibly line isolations. However no other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | To Be Determined | 24.1 | (X15-882281) 24-1A to 25-1S: Anomaly Remediation (2/24/16 to 3/3/16) | ***24-1A to 25-1S: Anomaly Remediation --2/24/16 through 3/3/16: This outage will require pressure reductions and possibly line isolations. However no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. To Be Determined ***Project Completed ……………………………… | ***24-1A to 25-1S: Anomaly Remediation ***Project Completed The following meters are available for nominations: To Be Determined ………………………………
| Project Completed | X15-882291 | *** | 2016-03-03 | 2016-03-04 | Project Completed |  |  | MLV 24-3 to 25-3S | 100 | 0 | Anomaly Remediation | This outage will require pressure reductions and possibly line isolations. However no other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | To Be Determined | 24.3 | (X15-882291) MLV 24-3 to 25-3S: Anomaly Remediation (3/3/16 to 3/4/16) | ***MLV 24-3 to 25-3S: Anomaly Remediation --3/3/16 through 3/4/16: This outage will require pressure reductions and possibly line isolations. However no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. To Be Determined ***Project Completed ……………………………… | ***MLV 24-3 to 25-3S: Anomaly Remediation ***Project Completed The following meters are available for nominations: To Be Determined ………………………………
| Project Completed | X14-1178175 | *** | 2015-06-15 | 2016-03-31 | Project Completed |  |  | Station 63 | 100 | 1 | Station Maintenance | This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. |  | 63 | (X14-1178175) Station 63: Station Maintenance (6/15/15 to 3/31/16) | ***Station 63: Station Maintenance --6/15/15 through 3/31/16: This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. ***Project Completed ……………………………… | ***Station 63: Station Maintenance ***Project Completed ………………………………
| Project Cancelled | X15-913224 | *** | 2016-04-16 | 2016-05-21 | Project Cancelled |  |  | MLV 109-2 | 100 | 2 | Pipe Replacement | This project will require taking the pipeline section out of service. This will limit throughput and will result in restrictions based on customer nominations. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | To Be Determined | 109.2 | (X15-913224) MLV 109-2: Pipe Replacement (4/16/16 to 5/21/16) | ***MLV 109-2: Pipe Replacement --4/16/16 through 5/21/16: This project will require taking the pipeline section out of service. This will limit throughput and will result in restrictions based on customer nominations. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. To Be Determined ***Project Cancelled ……………………………… | ***MLV 109-2: Pipe Replacement ***Project Cancelled The following meters are available for nominations: To Be Determined ………………………………
| Project Completed | X15-926830 | *** | 2016-03-07 | 2016-03-11 | Project Completed |  |  | MLV 400-1 to 408-1 | 100 | 0 | ILI/Cleaning Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. | SIP | Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations. | To Be Determined | 400.1 | (X15-926830) MLV 400-1 to 408-1: ILI/Cleaning Pig (3/7/16 to 3/11/16) | ***MLV 400-1 to 408-1: ILI/Cleaning Pig --3/7/16 through 3/11/16: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations. To Be Determined ***Project Completed ……………………………… | ***MLV 400-1 to 408-1: ILI/Cleaning Pig ***Project Completed The following meters are available for nominations: To Be Determined ………………………………
| Project Cancelled | X16-143836 | *** | 2016-03-28 | 2016-04-04 | Project Cancelled |  |  | Sta. 409 | 100 | 0 | Unit Maintenance | This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations. | SIP | Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations. |  | 409 | (X16-143836) Sta. 409: Unit Maintenance (3/28/16 to 4/4/16) | ***Sta. 409: Unit Maintenance --3/28/16 through 4/4/16: This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations. Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations. ***Project Cancelled ……………………………… | ***Sta. 409: Unit Maintenance ***Project Cancelled ………………………………
| Project Cancelled | X15-929680 | *** | 2016-04-18 | 2016-04-27 | Project Cancelled |  |  | SABINE - KINDER LINE to 822-1 | 800 | L | Anomaly Remediation | This outage will require pressure reductions and possibly line isolations. However no other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | To Be Determined | 822.1 | (X15-929680) SABINE - KINDER LINE to 822-1: Anomaly Remediation (4/18/16 to 4/27/16) | ***SABINE - KINDER LINE to 822-1: Anomaly Remediation --4/18/16 through 4/27/16: This outage will require pressure reductions and possibly line isolations. However no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. To Be Determined ***Project Cancelled ……………………………… | ***SABINE - KINDER LINE to 822-1: Anomaly Remediation ***Project Cancelled The following meters are available for nominations: To Be Determined ………………………………

## Sheet1
Updated | 2026-04-16
Natural Gas Pipeline 2026 Pipeline Outage and Maintenance Summary
This is a summary of the current status of NGPL Pipeline Outages and Maintenance Projects. This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions. Additionally, anticipated impact and restrictions are subject to change. *Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project. *Unless otherwise noted, all scheduled dates represent gas days as defined in the Natural Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time). *Typical Timeline for ILI reporting is below.
Type of In-Line Inspection tool | # of weeks to determine a successful run | # of weeks to Preliminary Report | # of Weeks to Final Aligned Report
MFL | 1-2 | 3-4 | 8-13
AFD | 2-3 | 3-4 | 12-16
EMAT | 2-3 | N/A | 17-30
*** Indicates revision | [18 empty] | \\houCORP\TRANS\TRANSERVICES\OPPLAN\COMMON\Outages\NGPL
Outage # | Revised | Start Date | End Date | Reason Changed | Prev. Start Date | Prev. End Date | System | Line | Segment | Location | Scheduling Location | Maintenance Activity | Restriction Level | Pool Location | Meter(s) in Impacted Area | Mega Rule Eligible Project
X20-877776 | *** | 2020-09-24 | UFN | Project Change |  |  | AM | INDIAN BASIN | 7 | 167 | 167 | Force Majeure | Effective for gas day Thursday, September 24, 2020, Intraday 1 Cycle, Natural will schedule all transports to 0% of contract MDQ into and out of Segment 7. Segment 8 and Segment 9 of the Permian Zone are not impacted by this force majeure event. |  |  | No | ------------mantenance_desc------model_loc-- | 0
X24-449139 |  | 2024-04-26 | UFN |  |  |  | AM | LOCKRIDGE LATERAL | 9 | Lockridge Lateral | LOC 47662 | Force Majeure | LOC 47662 ATMOS PYOTE is unavailable. No transport services will be scheduled. |  | LOC 47662 ATMOS PYOTE | No |  | 0
X25-477891 |  | 2025-04-20 | UFN |  |  |  | AM | MT VIEW TO MINEOLA | 4 | LOC 3000 | LOC 3000 | Force Majeure | The following location is unavailable: LOC 3000 ONEOKGT/NGPL WOODWARD No transport services will be scheduled. |  | LOC 3000 ONEOKGT/NGPL WOODWARD | No |  | 0
X26-347324 | *** | 2026-03-24 | 2026-05-08 | Project Change |  | 2026-04-10 | AM |  | 11 | 195 | 106 | Unit Maintenance | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No | ----end_date--------------model_loc-- | 0
X25-1527903 |  | 2026-04-01 | 2026-05-01 |  |  |  | GC |  | 25 | 302 | 302 | Station Maintenance | Primary/SIP Firm transports will be scheduled to no less than 55% of contract MDQ through CS 302. AOR/ITS and Secondary out-of-path Firm transports are not available. Firm transportation associated with storage injections or withdrawals may be impacted. |  |  | No |  | 55
X26-60450 |  | 2026-04-06 | 2026-04-21 |  |  |  | AM | AM #4 | 11 | 106 | 106 | Remediation | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No |  | 0
X25-1508693 | *** | 2026-04-06 | 2026-04-09 | Completed |  |  | GC | COOKS MILLS LATERAL | 28 | 203 | 203 | Pipeline Integrity | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. The following location will be impacted: 4879 - AMEREN CIPS MATTOON DOUGLAS (Shut in apx 3 hours during runs) |  | 4879 - AMEREN CIPS MATTOON DOUGLAS (Shut in apx 3 hours during runs) | No | ------ | 0
X25-1158495 | *** | 2026-04-06 | 2026-04-15 | Completed |  |  | MKT | ILLINOIS #3 | 29 | 116 | 116 | Pipeline Integrity | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No | ------ | 0
X25-1514422 | *** | 2026-04-06 | 2026-04-18 | Completed |  |  | AM | PERMIAN LN #1 | 8 | 168 | 167 | Remediation | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No | ------ | 0
X25-1094362 |  | 2026-04-07 | 2026-04-16 |  |  |  | AM | AM #3 / #5 | 6 | 111 | 111 | Pipeline Integrity | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | Yes |  | 0
X26-435770 | *** | 2026-04-07 | UFN | Project Change |  | 2026-04-19 | AM |  | 9 | 168 | 167 | Force Majeure | Primary/SIP Firm transports will be scheduled at Segment 9 to no less than 94% of contract MDQ through CS 104. AOR/ITS and Secondary out-of-path Firm transports are not available. Firm transportation associated with storage injections or withdrawals may be impacted. |  |  | No | ----end_date--------------model_loc-- | 94
X25-1474603 | *** | 2026-04-09 | 2026-04-21 | Project Change |  | 2026-04-16 | GC | GC #3 | 26 | 394 | 394 | Pipeline Integrity | LOCATIONS UNAVAILABLE FOR RECEIPTS: LOC 42741 ET G&P ETML NACOGDOCHES LOC 45310 BTA ETG EAST TEXAS GATHERING LOC 45397 ET G&P NACOGDOCHES LOC 46389 TGG NACOGDOGDOCES LOC 55704 MARKWEST HARRISON TOOL RUN DATES: Gas day Thursday, April 9, 2026 (Cleaning Tool) Gas day Tuesday April 14, 2026 and continuing through gas day Tuesday, April 21, 2026 (Cleaning and MFL Tool) |  | LOC 55704 MARKWEST/NGPL BLOCKER RECEIPT HARRISON LOC 45310 BTA ETG/NGPL EAST TEXAS GATHERING LOC 42741 ET G&P/NGPL ETML NACOGDOCHES LOC 45397 ET G&P/NGPL NACOGDOCHES LOC 46389 TGG/NGPL NACOGDOGDOCES | No | ----end_date----------prl----model_loc-- | 0
X25-1365848 |  | 2026-04-13 | 2026-04-24 |  |  |  | GC | AG TEXOMA | 17 | 803 | 394 | Remediation | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No |  | 0
X26-60449 |  | 2026-04-13 | 2026-04-30 |  |  |  | GC | LOUDON LAT 4 | 28 | Loudon Storage | Loudon Storage | Pipeline Integrity | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No |  | 0
X25-1410126 | *** | 2026-04-14 | 2026-04-14 | Completed |  |  | AM |  | 2 | 156 | 156 | Station Maintenance | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No | ------ | 0
X25-1166550 |  | 2026-04-17 | 2026-05-01 |  |  |  | AM | AM #3 | 13 | 108 | 107 | Pipeline Integrity | Primary/SIP Firm transports will be scheduled at Segment 13 to no less than 44% of contract MDQ through CS 107. AOR/ITS and Secondary out-of-path Firm transports are not available. Firm transportation associated with storage injections or withdrawals may be impacted. Impacted days: April GD 17, 21, 23, 27, 29 & May GD 1, 2 |  |  | Yes |  | 44
X25-1240570 |  | 2026-04-21 | 2026-04-28 |  |  |  | AM | AM #3 | 11 | 106 | 106 | Pipeline Integrity | Primary/SIP Firm transports will be scheduled at Segment 11 to no less than 60% of contract MDQ through CS 106. AOR/ITS and Secondary out-of-path Firm transports are not available. Firm transportation associated with storage injections or withdrawals may be impacted. Impacted days: GD 21, 23, 28 |  |  | No |  | 60
X26-220667 | *** | 2026-04-21 | 2026-04-23 | Project Change |  |  | AM |  | 9 | 168 | 167 | Unit Maintenance | Primary/SIP Firm transports will be scheduled at Segment 9 to no less than 94% of contract MDQ through CS 167. AOR/ITS and Secondary out-of-path Firm transports are not available. Firm transportation associated with storage injections or withdrawals may be impacted. |  |  | No | ----------------NGPL_percent_cap--model_loc-- | 94
X25-1479896 | *** | 2026-04-22 | 2026-04-25 | Project Change | 2026-04-21 | 2026-04-24 | GC | GC #3 | 26 | 394 | 394 | Pipeline Integrity | LOCATIONS UNAVAILABLE FOR RECEIPTS: LOC 42741 ET G&P ETML NACOGDOCHES LOC 45310 BTA ETG EAST TEXAS GATHERING LOC 45397 ET G&P NACOGDOCHES LOC 46389 TGG NACOGDOGDOCES LOC 55704 MARKWEST HARRISON TOOL RUN DATES: Gas day Wednesday April 22, 2026 and continuing through gas day Saturday, April 25, 2026 (MFL and EMAT Tool) |  | LOC 55704 MARKWEST/NGPL BLOCKER RECEIPT HARRISON LOC 45310 BTA ETG/NGPL EAST TEXAS GATHERING LOC 42741 ET G&P/NGPL ETML NACOGDOCHES LOC 45397 ET G&P/NGPL NACOGDOCHES LOC 46389 TGG/NGPL NACOGDOGDOCES | No | --start_date--end_date----------prl----model_loc-- | 0
X25-1487345 |  | 2026-04-27 | 2026-05-07 |  |  |  | AM |  | 12 | 106 | 106 | Unit Maintenance | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No |  | 0
X25-1410128 |  | 2026-04-28 | 2026-04-29 |  |  |  | AM |  | 2 | 156 | 801 | Unit Maintenance | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No |  | 0
X25-1216074 |  | 2026-04-29 | 2026-04-29 |  |  |  | MKT | VOLO #1 (CS113 TO STREAMWOOD) | 40 | 113 | 113 | Remediation | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No |  | 0
X26-36336 |  | 2026-05-01 | 2026-05-22 |  |  |  | GC |  | 25 | 302 | 302 | Station Maintenance | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No |  | 0
X26-155555 |  | 2026-05-04 | 2026-05-22 |  |  |  | AM |  | 10 | 102 | 102 | Unit Maintenance | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No |  | 0
X25-1166563 |  | 2026-05-04 | 2026-05-15 |  |  |  | AM | AM #2 | 13 | 108 | 109 | Pipeline Integrity | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | Yes |  | 0
X25-1492843 |  | 2026-05-04 | 2026-07-31 |  |  |  | GC |  | 27 | 307 | 307 | Station Maintenance | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No |  | 0
X25-1158503 |  | 2026-05-04 | 2026-05-08 |  |  |  | MKT | VOLO #2 | 30 | 113 | 113 | Pipeline Integrity | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No |  | 0
X25-1216091 |  | 2026-05-04 | 2026-05-27 |  |  |  | MKT | CRAWFORD #3 | 31 | 113 | 113 | Remediation | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No |  | 0
X25-1240574 |  | 2026-05-05 | 2026-05-21 |  |  |  | AM | AM #4 | 10 | 103 | 103 | Pipeline Integrity | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No |  | 0
X25-1514417 |  | 2026-05-05 | 2026-05-15 |  |  |  | GC | LOUDON LAT 1 | 28 | Loudon Storage | Loudon Storage | Remediation | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No |  | 0
X26-278987 |  | 2026-05-05 | 2026-05-08 |  |  |  | AM |  | 8 | 169 | 167 | Unit Maintenance | Primary/SIP Firm transports will be scheduled to no less than 84% of contract MDQ through CS 167. AOR/ITS and Secondary out-of-path Firm transports are not available. Firm transportation associated with storage injections or withdrawals may be impacted. |  |  | No |  | 84
X25-1479924 |  | 2026-05-11 | 2026-05-14 |  |  |  | GC |  | 26 | 394 | 305 | Unit Maintenance | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No |  | 0
X25-1477828 |  | 2026-05-12 | 2026-05-15 |  |  |  | AM | AM #4 | 10 | 102 | 103 | Pipeline Integrity | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No |  | 0
X23-1238605 | *** | 2026-05-12 | 2026-05-17 | Project Change |  |  | GC | GC #1 | 20 |  |  | Force Majeure | The following Segment 20 locations will be unavailable for the duration of the outage: LOC 905572 - DCP INTR/NGPL THOMPSONVILLE JIM HOG LOC 3107 - KMTEJAS/NGPL #2 JIM HOGG LOC 24001 - ETP/NGPL THOMPSONVILLE JIM HOGG LOC 900532 - HPL/NGPL JIM HOG LOC 900439 - DCP OPER/NGPL LA GLORIA JIM WELLS LOC 900436 - TRIN GAS/NGPL SEJITA DUVAL LOC 25259 - LOBO/NGPL KING RANCH KLEBERG LOC 53776 - VCP/NGPL MUSTANG M/L 1 NUECES 54849 - WHISTLEP/NGPL WHISTLE REC NUECES |  | 905572 - DCP INTR/NGPL THOMPSONVILLE JIM HOG 3107 - KMTEJAS/NGPL #2 JIM HOGG 24001 - ETP/NGPL THOMPSONVILLE JIM HOGG 900532 - HPL/NGPL JIM HOG 900439 - DCP OPER/NGPL LA GLORIA JIM WELLS 900436 - TRIN GAS/NGPL SEJITA DUVAL 25259 - LOBO/NGPL KING RANCH KLEBERG 53776 - VCP/NGPL MUSTANG M/L 1 NUECES 54849 - WHISTLEP/NGPL WHISTLE REC NUECES | No | --------------prl----model_loc-- | 0
X26-53725 |  | 2026-05-12 | 2026-05-15 |  |  |  | AM |  | 9 | 167 | 167 | Station Maintenance | Primary/SIP Firm transports will be scheduled to no less than 92% of contract MDQ through CS 167. AOR/ITS and Secondary out-of-path Firm transports are not available. Firm transportation associated with storage injections or withdrawals may be impacted. |  |  | No |  | 92
X25-686871 | *** | 2026-05-18 | 2026-05-21 | Added |  |  | AM |  | 12 | 196 | 106 | Station Maintenance | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No | ------ | 0
X25-1487450 |  | 2026-05-18 | 2026-05-22 |  |  |  | GC | GC #2 | 22 | 301 | 301 | Remediation | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No |  | 0
X25-1514433 |  | 2026-05-18 | 2026-05-21 |  |  |  | GC | GC #3 | 28 | 310 | 310 | Remediation | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No |  | 0
X25-1355218 |  | 2026-05-19 | 2026-05-28 |  |  |  | GC | LA #1 | 23 | 342 | 342 | Pipeline Integrity | Primary/SIP Firm transports will be scheduled at Segment 23 to no less than 46% of contract MDQ through CS 342. AOR/ITS and Secondary out-of-path Firm transports are not available. Firm transportation associated with storage injections or withdrawals may be impacted. LOCATIONS NOT AVAILBALE FOR RECEIPTS: LOC 3592 SABPL HENRY HUB LOC 25731 JEFFERSON VERMILION LOCATIONS NOT AVAILABLE FOR DELIVERIES: LOC 7936 FLORIDA VERMILION TOOL RUN DATES: Gas day Tuesday, May 19, 2026 and continuing through gas day Friday, May 22,2026 – Cleaning Tool Gas day Wednesday, May 27, 2026 and continuing through gas day Thursday, May 28,2026 – MFL Tool |  | LOC 3592 SABPL HENRY HUB (No receipts) LOC 25731 JEFFERSON VERMILION (No receipts) LOC 7936 FLORIDA VERMILION (No deliveries) | No |  | 46
X25-1432007 |  | 2026-05-19 | 2026-05-28 |  |  |  | GC | GC #3 | 26 | 302 | 302 | Pipeline Integrity | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No |  | 0
X25-1527875 |  | 2026-05-25 | 2026-06-25 |  |  |  | GC |  | 25 | 343 | 302 | Station Maintenance | Primary/SIP Firm transports will be scheduled to no less than 95% of contract MDQ through CS 302. AOR/ITS and Secondary out-of-path Firm transports are not available. Firm transportation associated with storage injections or withdrawals may be impacted. |  |  | No |  | 95
X26-60445 |  | 2026-05-26 | 2026-06-06 |  |  |  | GC | GC #1 | 28 | 310 | 310 | Remediation | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No |  | 0
X25-1094390 | *** | 2026-05-26 | 2026-06-05 | Project Change |  |  | AM | OE #1 | 6 | 154 | 154 | Pipeline Integrity | The following Segment 6 locations will be unavailable on each tool run date: LOC 47097 MARKWEST/NGPL BUFFALO CREEK PROCESS Impacted days May 26-28, June 2-4 |  | LOC 47097 MARKWEST/NGPL BUFFALO CREEK PROCESS | Yes | ------meters_affected--------prl----model_loc-- | 0
X25-1216096 |  | 2026-05-28 | 2026-06-01 |  |  |  | MKT | CRAWFORD #3 | 31 | 113 | 113 | Remediation | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No |  | 0
X25-1166577 |  | 2026-06-01 | 2026-06-20 |  |  |  | AM | AM #4 | 13 | 109 | 109 | Pipeline Integrity | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No |  | 0
X25-149398 |  | 2026-06-01 | 2026-06-08 |  |  |  | AM |  | 2 | 801 | 801 | Unit Maintenance | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No |  | 0
X25-1528019 |  | 2026-06-01 | 2026-08-03 |  |  |  | GC | GC #2 | 27 | 307 | 394 | Pipeline Maintenance | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No |  | 0
X25-1474596 |  | 2026-06-01 | 2026-07-01 |  |  |  | MKT |  | 34 | 201 | 201 | Remediation | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No |  | 0
X25-1527869 |  | 2026-06-01 | 2026-07-13 |  |  |  | AM |  | 9 | 167 | 167 | Unit Maintenance | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No |  | 0
X25-1240583 | *** | 2026-06-02 | 2026-06-05 | Added |  |  | AM | AM #2 | 13 | 107 | 107 | Pipeline Integrity | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | Yes | ------------mantenance_desc--prl----model_loc-- | 0
X25-1216101 |  | 2026-06-02 | 2026-06-22 |  |  |  | MKT | HOWARD STREET LN #2 | 30 | 113 | 113 | Remediation | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No |  | 0
X25-1355213 |  | 2026-06-08 | 2026-06-17 |  |  |  | GC | GC #1 | 27 | 307 | 394 | Remediation | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No |  | 0
X25-1240585 | *** | 2026-06-09 | 2026-06-29 | Added |  |  | AM | AM #2 | 11 | 104 | 103 | Remediation | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No | ------------mantenance_desc--prl----model_loc-- | 0
X25-1487488 | *** | 2026-06-09 | 2026-06-28 | Added |  |  | AM | AM #2 | 11 | 104 | 103 | Remediation | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No | ------------mantenance_desc--prl----model_loc-- | 0
X25-1514435 |  | 2026-06-11 | 2026-06-11 |  |  |  | MKT | CALUMET #3 | 33 | 113 | 113 | Remediation | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No |  | 0
X25-1276449 | *** | 2026-06-15 | 2026-06-16 | Added |  |  | AM |  | 11 | 105 | 103 | Station Maintenance | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No | ------ | 0
X25-1259914 | *** | 2026-06-17 | 2026-06-18 | Added |  |  | AM |  | 11 | 104 | 103 | Station Maintenance | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No | ------ | 0
X25-751122 | *** | 2026-06-22 | 2026-06-24 | Added |  |  | AM |  | 11 | 193 | 103 | Station Maintenance | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No | ------ | 0
X25-1487339 | *** | 2026-06-22 | 2026-06-25 | Completed |  |  | AM |  | 13 | 107 | 109 | Unit Maintenance | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No | ------ | 0
X26-175974 | *** | 2026-07-06 | 2026-07-10 | Added |  |  | AM |  | 2 | 801 | 801 | Unit Maintenance | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No | --------------prl----model_loc-- | 0
X26-162085 | *** | 2026-07-06 | 2026-08-14 | Added |  |  | GC |  | 27 | 305 | 394 | Station Maintenance | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No | ------------mantenance_desc--prl----model_loc-- | 0
X25-1240588 | *** | 2026-07-07 | 2026-07-24 | Added |  |  | AM | AM #3 | 11 | 104 | 103 | Remediation | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No | ------------mantenance_desc--prl----model_loc-- | 0
X25-1506154 | *** | 2026-07-07 | 2026-07-24 | Added |  |  | AM | AM #3 | 11 | 104 | 103 | Remediation | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No | ------------mantenance_desc--prl----model_loc-- | 0
X26-231394 | *** | 2026-07-13 | 2026-07-20 | Added |  |  | AM |  | 11 | 196 | 107 | Station Maintenance | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No | ------ | 0
X25-1094406 | *** | 2026-07-14 | 2026-07-17 | Added |  |  | AM | AM #3 | 6 | 111 | 103 | Pipeline Integrity | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No | ------------mantenance_desc--prl----model_loc-- | 0
X25-1506148 | *** | 2026-07-20 | 2026-08-06 | Added |  |  | GC | GC #2 | 22 | 300 | 302 | Pipeline Integrity | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | Yes | ------ | 0
X25-1527874 | *** | 2026-07-20 | 2026-08-31 | Added |  |  | AM |  | 9 | 167 | 167 | Unit Maintenance | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No | ------------mantenance_desc--prl----model_loc-- | 0
X25-1514416 | *** | 2026-07-23 | 2026-07-23 | Added |  |  | GC | GC #2 | 27 | 307 | 394 | Remediation | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No | ------------mantenance_desc--prl----model_loc-- | 0
X25-1477845 |  | 2026-08-03 | 2026-08-14 |  |  |  | GC | NE THOMPSONVILLE LATERAL | 18 | 341 | 341 | Remediation | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No |  | 0
X25-1528022 |  | 2026-08-04 | 2026-08-18 |  |  |  | GC | GC #3 | 27 | 307 | 394 | Pipeline Maintenance | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No |  | 0
X25-1094418 | *** | 2026-08-04 | 2026-08-06 | Added |  |  | AM | OE #2 | 6 | 111 | 103 | Pipeline Integrity | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No | ------------mantenance_desc--prl----model_loc-- | 0
X25-974579 | *** | 2026-08-11 | 2026-08-12 | Added |  |  | AM |  | 11 | 105 | 103 | Station Maintenance | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No | ------ | 0
X26-231396 | *** | 2026-08-17 | 2026-08-26 | Added |  |  | AM |  | 12 | 106 | 106 | Station Maintenance | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No | ------ | 0
X25-1004364 | *** | 2026-08-18 | 2026-08-19 | Added |  |  | AM |  | 13 | 107 | 107 | Station Maintenance | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No | ------ | 0
X25-1528017 |  | 2026-08-19 | 2026-11-02 |  |  |  | GC | GC #1 | 27 | 307 | 394 | Pipeline Maintenance | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No |  | 0
X25-1514127 |  | 2026-08-31 | 2026-08-31 |  |  |  | GC | GC #2 | 27 | 306 | 305 | Remediation | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No |  | 0
X25-1147515 | *** | 2026-09-15 | 2026-09-17 | Added |  |  | AM |  | 11 | 103 | 103 | Station Maintenance | This project has an impact to maximum capacity. However, in order to mitigate customer impact and based on current operating conditions, Natural does not anticipate limiting primary firm transport services, at this time. If conditions change Natural will post an update. |  |  | No | ------ | 0