## Slide 1: Southern Natural Gas Company 2024 Outage Review
August 21st , 2024

## Slide 2: Welcome

## Slide 3: Agenda
Review of current and upcoming notable Outages
  August/September/October/November
  Unscheduled outages
    North System
    South System
    South Louisiana System
    EEC
The next outage meeting will be on September 18th, 2024, at 1:30PM CST
Contacts

## Slide 4: Disclaimers
Anticipated Impacts are estimates. Actual nominations, market demand, weather and pipeline conditions, etc. will determine if, and through what level, restrictions become necessary.
Unless otherwise stated, all scheduled dates represent gas days as defined in the Southern Natural Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time).
Scheduled dates are subject to change.
Projects may be added, altered, delayed or cancelled.
SNG will provide notice of such additions or changes via Southern’s electronic bulletin board postings.
Dates as posted on the EBB should be deemed correct in the event of conflicts between the EBB posted dates and dates within this presentation.

## Slide 5: Color Key for Maps
Yellow
  Restrictions are possible
  With extended duration, restrictions could be necessary from time to time
  Lower than normal pressures may be experienced
  Meter(s) affected are noted with (PIN #)
Red
  Restrictions are probable

## Slide 6: Southern Natural Gas Pipeline
LA
MS
AL
GA
FL
Enterprise
White Castle
Bear Creek
Muldon
Chattanooga
Atlanta
Thomaston
Albany
Elba
SC
Aiken
Elba Express
North System
South Louisiana
South System
Pearl River
Franklinton
Gwinville
Logansport
Bienville
Onward
Pickens
Rankin
Toca
Shady Side
Louisville
Bay Springs
York
Gallion
Selma
Elmore
Auburn
Holy Trinity
Pavo
Reform
McConnells
Providence
Tarrant
Pell City
DeArmanville
Bell Mills
Rome
Ellerslie
Ocmulgee
Hall Gate
Wrens
Hartwell
Riceboro
Brookman
Compressor Station
Storage Field
LNG

## Slide 7: Southern Natural Gas Pipeline
Unscheduled Outage Update
LA
MS
AL
GA
FL
Enterprise
White Castle
Bear Creek
Muldon
Chattanooga
Atlanta
Thomaston
Albany
Elba
SC
Aiken
North System
South Louisiana
South System
Pearl River
Franklinton
Gwinville
Logansport
Bienville
Onward
Pickens
Rankin
Toca
Shady Side
Louisville
Bay Springs
York
Gallion
Selma
Elmore
Auburn
Holy Trinity
Pavo
Reform
McConnells
Providence
Tarrant
Pell City
DeArmanville
Bell Mills
Rome
Ellerslie
Ocmulgee
Hall Gate
Wrens
Hartwell
Riceboro
Brookman
Compressor Station
Storage Field
LNG
Elba Express
Unscheduled unit outage
Rankin compressor station
Proj-46102
8-6-24 to 9-1-24
Unscheduled unit outage Gallion compressor station
11-29-23 to 10-31-24

## Slide 8: SNG North System Pigging Review
August/September/October/November
LA
MS
AL
GA
Logansport
Bienville
Bear Creek Storage
Onward
Pickens
Rankin
Louisville
Muldon Storage
Reform
McConnells
Providence
Tarrant
Pell City
DeArmanville
Bell Mills
Rome
Huntsville
Chattanooga
Atlanta
Southern will be conducting other general maintenance during this period
AL
Pigging on Miss. Chemical line
8-27-24
Proj-18560-west of Pickens
Pigging on Miss. Chemical LL
8-29-24
Proj-18562-west of Pickens
Compressor Station
Storage Field
LNG
Pigging on NMLL
10-1-24 to 10-2-24
Proj-15346-east of Tarrant

## Slide 9: SNG North System Maintenance Review
August/September/October/November
Compressor Station
Storage Field
LA
MS
AL
GA
Logansport
Bienville
Bear Creek Storage
Onward
Pickens
Rankin
Louisville
Muldon Storage
Reform
McConnells
Providence
Tarrant
Pell City
DeArmanville
Bell Mills
Rome
Huntsville
Chattanooga
Atlanta
Southern will be conducting other general maintenance during this period
AL
Pipeline maintenance Bessemer Calera line and loop line
5-28-24 to 9-13-24
9-14-24 to 9-18-24
10-15-24 to 10-19-24
10-22-24 to 10-26-24
east of Providence
Pipeline maintenance Talladega Branch loop line
9-6-24 to 10-25-24
Proj-36904 south of Dearmanville
Muldon unit maintenance
9-9-24 to 11-8-24
Muldon Shut-in test
10-1-24 to 10-7-24
Restrictions first into ISS then CSS-not to exceed 36% of CSS DIQ /DWQ
Bear Creek Shut-in test
10-15-24 to 9 AM 10-21-24
Restrictions first into ISS then CSS-not to exceed 64% of CSS DIQ /DWQ

## Slide 10: SNG North System Maint. Review Cont.
August/September/October/November
Compressor Station
Storage Field
LA
MS
AL
GA
Logansport
Bienville
Bear Creek Storage
Onward
Pickens
Rankin
Louisville
Muldon Storage
Reform
McConnells
Providence
Tarrant
Pell City
DeArmanville
Bell Mills
Rome
Huntsville
Chattanooga
Atlanta
Southern will be conducting other general maintenance during this period
AL
Pipeline maintenance 2ndNML
10-8-24 to 10-16-24
Seg. 400 capacity of 234 Mdth/d impacted up to 84 Mdth/d
Proj-2328 east of Pickens
Pipeline maintenance 2ndNML
10-10-24 to 10-13-24
Seg. 120 capacity of 652 Mdth/d impacted up to 355 Mdth/d
east of Providence

## Slide 11: SNG South System Pigging Review
August/September/October/November
Southern will be conducting other general maintenance during this period
MS
AL
GA
Enterprise
Gwinville
Selma
Auburn
Ellerslie
Thomaston
Ocmulgee
Hallgate
Wrens
Elmore
York
Gallion
Bay Springs
Atlanta
Elba
Hartwell
Aiken
Holy Trinity
Albany
Pavo
Brookman
Riceboro
Compressor Station
Storage Field
LNG
Pigging on SMLL 9-24-24
Proj-18931 west of Ellerslie
Pigging on Ocmulgee Atlanta line-Ocmulgee to Bass Junction 9-17-24 to 9-18-24
Pigging on North Terrell line 6 9-4-24 to 9-7-24
Exact date TBD
Proj-15224 south of Holy Trinity

## Slide 12: SNG South System Maintenance Review
August/September/October/November
MS
AL
GA
Enterprise
Gwinville
Selma
Auburn
Ellerslie
Thomaston
Ocmulgee
Hallgate
Wrens
Elmore
York
Gallion
Bay Springs
Atlanta
Elba
Hartwell
Aiken
Holy Trinity
Albany
Pavo
Brookman
Riceboro
Rincon
Southern will be conducting other general maintenance during this period
Compressor Station
Storage Field
LNG
Pipeline maintenance SML
9-9-24 to 9-18-24
We do not anticipate an impact to customers
Proj-2496B
east of Ocmulgee
Elmore unit maintenance
9-25-24 to 9-26-24
Seg. 460 capacity of 2,293 Mdth/d impacted 450 Mdth/d
Gallion unit maintenance
9-23-24 to 9-24-24
Seg. 440 capacity of 2,300 Mdth/d impacted 265 Mdth/d
Thomaston unit outage
5-23-24 to 9-30-24
Seg. 490 Cap. Of 1,535 Mdth/d impacted 170 Mdth/d
Gwinville unit maintenance Proj-52677
8-12-24 to 9-11-24
Seg. 390 capacity of 1,607 Mdth/d impacted 30 Mdth/d
Holy Trinity station outage
10-7-24 to 10-12-24
Seg. 655 Cap. of 127 Mdth/d impacted 37 Mdth/d

## Slide 13: SNG South System Maint. Review cont.
August/September/October/November
MS
AL
GA
Enterprise
Gwinville
Selma
Auburn
Ellerslie
Thomaston
Ocmulgee
Hallgate
Wrens
Elmore
York
Gallion
Bay Springs
Atlanta
Elba
Hartwell
Aiken
Holy Trinity
Albany
Pavo
Brookman
Riceboro
Rincon
Compressor Station
Storage Field
LNG
Southern will be conducting other general maintenance during this period
Pipeline maintenance
TG2ndLL
10-7-24 to 10-16-24
north of Thomaston
Proj-231009
Elmore unit maintenance
10-17-24
Seg. 460 capacity of 2,293 Mdth/d impacted 450 Mdth/d
Gallion unit maintenance
10-15-24
Seg. 440 capacity of 2,300 Mdth/d impacted 445 Mdth/d
York station maintenance
10-14-24
Seg. 430 capacity of 2,306 Mdth/d impacted 340 Mdth/d
York unit maintenance
10-23-24 to 10-24-24
Seg. 430 capacity of 2,306 Mdth/d impacted 340 Mdth/d
Selma station maintenance
10-1-24 to 10-28-24
Seg. 460 capacity of 2,273 Mdth/d impacted 265 Mdth/d
Proj-2593
Auburn unit maintenance
10-7-24 to 10-8-24
Seg. 460 capacity of 2,293 Mdth/d impacted 340 Mdth/d
Auburn unit maintenance
10-18-24
Seg. 460 capacity of 2,293 Mdth/d impacted 340 Mdth/d

## Slide 14: SNG South Louisiana System Pigging Review
Shadyside
White Castle
Franklinton
Toca
Gwinville
LA
MS
West Leg
East Leg
Pearl River
August/September/October/November
Southern will be conducting other general maintenance during this period
Compressor Station
Storage Field

## Slide 15: SNG South Louisiana System Maint. Review
August/September/October/November
Shadyside
White Castle
Franklinton
Toca
Gwinville
LA
MS
West Leg
East Leg
Pearl River
Southern will be conducting other general maintenance during this period
Compressor Station
Storage Field
Pipeline maintenance
FGLL
8-19-24 to 8-26-24
Seg. 370 cap. 1,123 Mdth/d impacted 150 Mdth/d north of Pearl River
Pipeline maintenance
FG2ndLL
8-29-24 to 9-6-24
Seg. 370 cap. 1,123 Mdth/d impacted 160 Mdth/d north of Pearl River
Franklinton unit maintenance
8-12-24 to 8-30-24
Pearl River station outage
9-20-24 to 10-4-24
Seg. 370 cap. of 1,123 Mdth/d impacted 280 Mdth/d

## Slide 16: SNG South Louisiana System Maint. Review Cont.
August/September/October/November
Shadyside
White Castle
Franklinton
Toca
Gwinville
LA
MS
West Leg
East Leg
Pearl River
Southern will be conducting other general maintenance during this period
Compressor Station
Storage Field
Pipeline maintenance
DLFL
9-4-24 to 9-14-24
Seg. 350 cap. 735 Mdth/d impacted 115 Mdth/d
9-15-24 to 10-3-24
Seg. 350 cap. 735 Mdth/d impacted 15 Mdth/d
Proj-2754-north of White Castle
Pipeline maintenance on WCFLL
10-4-24 to 11-1-24
Seg. 350 cap. 735 Mdth/d impacted 200 Mdth/d
Proj-2861-north of White Castle
Pipeline maintenance on FGL
9-13-24 to 10-3-24
Seg. 370 cap. of 1,123 Mdth/d impacted 180 Mdth/d
south of Pearl River
Pipeline maintenance on FGLL
10-11-24 to 10-18-24
Seg. 370 cap. of 1,123 Mdth/d impacted 190 Mdth/d
south of Pearl River
Pipeline maintenance on FG2ndLL
10-18-24 to 10-25-24
Seg. 370 cap. of 1,123 Mdth/d impacted 200 Mdth/d
south of Pearl River

## Slide 17: EEC Line
August/September/October/November
LA
MS
AL
GA
FL
Enterprise
White Castle
Bear Creek
Muldon
Atlanta
Thomaston
Albany
Elba
SC
Aiken
Elba Express
North System
South Louisiana
South System
Pearl River
Franklinton
Gwinville
Bienville
Onward
Pickens
Rankin
Toca
Shady Side
Louisville
Bay Springs
York
Gallion
Selma
Elmore
Auburn
Holy Trinity
Pavo
Reform
McConnells
Providence
Tarrant
Pell City
DeArmanville
Bell Mills
Rome
Ellerslie
Ocmulgee
Hall Gate
Wrens
Hartwell
Riceboro
Brookman

## Slide 18: SNG North System Pigging Review
Remainder of year
LA
MS
AL
GA
Logansport
Bienville
Bear Creek Storage
Onward
Pickens
Rankin
Louisville
Muldon Storage
Reform
McConnells
Providence
Tarrant
Pell City
DeArmanville
Bell Mills
Rome
Huntsville
Chattanooga
Atlanta
AL
Southern will be conducting other general maintenance during this period
Compressor Station
Storage Field

## Slide 19: SNG North System Maint. Review
Remainder of year
LA
MS
AL
GA
Bienville
Bear Creek Storage
Onward
Pickens
Rankin
Louisville
Muldon Storage
Reform
McConnells
Providence
Tarrant
Pell City
DeArmanville
Bell Mills
Rome
Huntsville
Atlanta
AL
Logansport
Compressor Station
Storage Field
LNG
Southern will be conducting other general maintenance during this period

## Slide 20: SNG South System Pigging Review
Remainder of year
Southern will be conducting other general maintenance during this period
MS
AL
GA
Enterprise
Gwinville
Selma
Auburn
Ellerslie
Thomaston
Ocmulgee
Hallgate
Wrens
Elmore
York
Gallion
Bay Springs
Atlanta
Elba
Hartwell
Elba Express
Aiken
Holy Trinity
Albany
Pavo
Brookman
Riceboro
Compressor Station
Storage Field
LNG

## Slide 21: SNG South System Maint. Review
Remainder of year
MS
AL
GA
Enterprise
Gwinville
Selma
Auburn
Ellerslie
Thomaston
Ocmulgee
Hallgate
Wrens
Elmore
York
Gallion
Bay Springs
Atlanta
Elba
Hartwell
Elba Express
Aiken
Holy Trinity
Albany
Pavo
Brookman
Riceboro
Compressor Station
Storage Field
LNG
Southern will be conducting other general maintenance during this period

## Slide 22: SNG South Louisiana System Pigging Review
Remainder of year
Shadyside
White Castle
Franklinton
Toca
Gwinville
LA
MS
West Leg
East Leg
Pearl River
Compressor Station
Storage Field
Southern will be conducting other general maintenance during this period

## Slide 23: SNG South Louisiana System Maint. Review
Remainder of year
Shadyside
White Castle
Franklinton
Toca
Gwinville
LA
MS
West Leg
East Leg
Pearl River
Compressor Station
Storage Field
Southern will be conducting other general maintenance during this period
Pipeline maintenance on WCFLL
11-4-24 to 11-30-24
Proj-2861-north of White Castle

## Slide 24: EEC Line
Remainder of year
LA
MS
AL
GA
FL
Enterprise
White Castle
Bear Creek
Muldon
Chattanooga
Atlanta
Thomaston
Albany
Elba
SC
Aiken
Elba Express
North System
South Louisiana
South System
Pearl River
Franklinton
Gwinville
Bienville
Onward
Pickens
Rankin
Toca
Shady Side
Louisville
Bay Springs
York
Gallion
Selma
Elmore
Auburn
Holy Trinity
Pavo
Reform
McConnells
Providence
Tarrant
Pell City
DeArmanville
Bell Mills
Rome
Ellerslie
Ocmulgee
Hall Gate
Wrens
Hartwell
Riceboro
Brookman
Compressor Station
Storage Field
LNG

## Slide 25: Gas Control Contacts
Skyler Spyker – Manager
  (713) – 420 – 2386 (office)
  (806)-470-7743 (cell)
  skyler_spyker@kindermorgan.com
Kal Dankovich – Outage Coordinator
  (205) – 533 – 4795 (cell)
  kalman_dankovich@kindermorgan.com
Mario Murillo – Outage Coordinator
  (281) – 753 – 6530 (cell)
  mario_murillo@kindermorgan.com
Jimmy Reese – Lead Controller
  (205) – 577 – 3204 (cell)
  jimmy_reese@kindermorgan.com
Darren LaPoint – Lead Controller
  (713) – 927 – 3894 (cell)
  darren_lapoint@kindermorgan.com

## Slide 26: Questions?