## Slide 1: Southern Natural Gas Company 2024 Outage Review
May 22, 2024

## Slide 2: Welcome

## Slide 3: Agenda
Review of current and upcoming notable Outages
  May/June/July/August
  Unscheduled outages
    North System
    South System
    South Louisiana System
    EEC
The next outage meeting will be on June 19th, at 1:30 CST
Contacts

## Slide 4: Disclaimers
Anticipated Impacts are estimates. Actual nominations, market demand, weather and pipeline conditions, etc. will determine if, and through what level, restrictions become necessary.
Unless otherwise stated, all scheduled dates represent gas days as defined in the Southern Natural Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time).
Scheduled dates are subject to change.
Projects may be added, altered, delayed or cancelled.
SNG will provide notice of such additions or changes via Southern’s electronic bulletin board postings.
Dates as posted on the EBB should be deemed correct in the event of conflicts between the EBB posted dates and dates within this presentation.

## Slide 5: Color Key for Maps
Yellow
Restrictions are possible
With extended duration, restrictions could be necessary from time to time
Lower than normal pressures may be experienced
Meter(s) affected are noted with (PIN #)
Red
Restrictions are probable

## Slide 6: Southern Natural Gas Pipeline
LA
MS
AL
GA
FL
Enterprise
White Castle
Bear Creek
Muldon
Chattanooga
Atlanta
Thomaston
Albany
Elba
SC
Aiken
Elba Express
North System
South Louisiana
South System
Pearl River
Franklinton
Gwinville
Logansport
Bienville
Onward
Pickens
Rankin
Toca
Shady Side
Louisville
Bay Springs
York
Gallion
Selma
Elmore
Auburn
Holy Trinity
Pavo
Reform
McConnells
Providence
Tarrant
Pell City
DeArmanville
Bell Mills
Rome
Ellerslie
Ocmulgee
Hall Gate
Wrens
Hartwell
Riceboro
Brookman
Compressor Station
Storage Field
LNG

## Slide 7: Southern Natural Gas Pipeline
Unscheduled Outage Update
LA
MS
AL
GA
FL
Enterprise
White Castle
Bear Creek
Muldon
Chattanooga
Atlanta
Thomaston
Albany
Elba
SC
Aiken
Elba Express
North System
South Louisiana
South System
Pearl River
Franklinton
Gwinville
Logansport
Bienville
Onward
Pickens
Rankin
Toca
Shady Side
Louisville
Bay Springs
York
Gallion
Selma
Elmore
Auburn
Holy Trinity
Pavo
Reform
McConnells
Providence
Tarrant
Pell City
DeArmanville
Bell Mills
Rome
Ellerslie
Ocmulgee
Hall Gate
Wrens
Hartwell
Riceboro
Brookman
Unscheduled Pipeline maintenance SMLL west of Hall Gate 2-13-24 to RTS-TBD
Seg. 560 cap. 700 Mdth/d impacted 95 Mdth/d
Unscheduled unit outage Gallion compressor station
11-29-23 to 6-14-24
Compressor Station
Storage Field
LNG

## Slide 8: SNG North System Pigging Review
May/June/July/August
LA
MS
AL
GA
Logansport
Bienville
Bear Creek Storage
Onward
Pickens
Rankin
Louisville
Muldon Storage
Reform
McConnells
Providence
Tarrant
Pell City
DeArmanville
Bell Mills
Rome
Huntsville
Chattanooga
Atlanta
Southern will be conducting other general maintenance during this period
AL
Pigging on LLL
6-24-24 to 6-27-24
Pro.5026-east of Bienville
Pigging on Miss. Chemical line
Will be rescheduled date TBD
Pro.18560-west of Pickens
Pigging on Miss. Chemical LL
Will be rescheduled date TBD
Pro.18562-west of Pickens
Pigging on LL
6-4-24 to 6-6-24
Pro.18556-east of Logansport
Pigging on Logansport Supply line
6-10-24 to 6-13-24
Pro.5454-east of Logansport
Pigging on NML
6-25-24 to 6-27-24
Pro. 5663-west of Tarrant
Compressor Station
Storage Field
LNG
Pigging on LLL
7-16-24 to 7-17-24
Pro.14574-east of Bienville

## Slide 9: SNG North System Maintenance Review
May/June/July/August
Compressor Station
Storage Field
LA
MS
AL
GA
Logansport
Bienville
Bear Creek Storage
Onward
Pickens
Rankin
Louisville
Muldon Storage
Reform
McConnells
Providence
Tarrant
Pell City
DeArmanville
Bell Mills
Rome
Huntsville
Chattanooga
Atlanta
Southern will be conducting other general maintenance during this period
AL
GPL Pipeline maintenance
5-22-24 to 5-29-24
Seg. 400 cap. of 234 Mdth/d
Impacted 79 Mdth/d
Pro.21650-north of Rankin
Bessemer Calera loop line Pipeline maintenance
5-28-24 to 7-15-24
7-16-24 to 7-20-24
8-21-24 to 8-26-24
8-27-24 to 8-30-24
9-3-24 to 9-6-24
10-1-24 to 10-7-24
10-8-24 to 10-15-24
East of Providence
PL. remediation Gadsden Branch loop line
5-13-24 to 8-2-24
Pro. 21261 north of Pell City
PL. maintenance Talladega Branch loop line
9-6-24 to 10-25-24
Pro. 36904 south of Dearmanville
Pipeline maintenance Rome Calhoun loop line
8-19-24 to 9-13-24
Pro.15374
north of Bell Mills

## Slide 10: SNG South System Pigging Review
May/June/July/August
Southern will be conducting other general maintenance during this period
MS
AL
GA
Enterprise
Gwinville
Selma
Auburn
Ellerslie
Thomaston
Ocmulgee
Hallgate
Wrens
Elmore
York
Gallion
Bay Springs
Atlanta
Elba
Hartwell
Elba Express
Aiken
Holy Trinity
Albany
Pavo
Brookman
Riceboro
Pigging on L-64 Jacksonville line
7-23-24 to 7-25-24
Pro. 5462 south of Pavo
Compressor Station
Storage Field
LNG
Pigging on SMLL 7-16-24 to 7-18-24
Pro. 18931 west of Ellerslie
Pigging on WSLL 7-9-24 to 7-11-24
Pro. 18717 south of Wrens
Pigging on SMLL 5-28-24 to 5-30-24
Pro. 36087 west of Hall Gate
Pigging on Brunswick line 6-5-24 to 6-13-24
Pro. 28814 south of Ocmulgee
Pigging on SMLL 8-5-24 to 8-8-24
Pro. 18926 east of Gallion
Pigging on North Terrell line 6 8-13-24 to 8-15-24
Pro. 15224 south of Holy Trinity

## Slide 11: SNG South System Maint. Review
May/June/July/August
MS
AL
GA
Enterprise
Gwinville
Selma
Auburn
Ellerslie
Thomaston
Ocmulgee
Hallgate
Wrens
Elmore
York
Gallion
Bay Springs
Atlanta
Elba
Hartwell
Elba Express
Aiken
Holy Trinity
Albany
Pavo
Brookman
Riceboro
Rincon
Southern will be conducting other general maintenance during this period
Compressor Station
Storage Field
LNG
Bay Springs unit outage
6-24-24 to 6-26-24
Seg. 420 Cap. Of 1,675 Mdth/d impacted 375 Mdth/d
Remediation on Mulcoa line 62
6-17-24 to 6-19-24
We will be coordinating this with customer outage
Unit maintenance at Hall Gate
4-1-24 to 5-24-24
Thomaston unit outage
5-16-24 to 8-14-24
Seg. 490 Cap. Of 1,535 Mdth/d impacted 15 Mdth/d

## Slide 12: SNG South System Maint. Review cont.
May/June/July/August
MS
AL
GA
Enterprise
Gwinville
Selma
Auburn
Ellerslie
Thomaston
Ocmulgee
Hallgate
Wrens
Elmore
York
Gallion
Bay Springs
Atlanta
Elba
Hartwell
Elba Express
Aiken
Holy Trinity
Albany
Pavo
Brookman
Riceboro
Rincon
Southern will be conducting other general maintenance during this period
Compressor Station
Storage Field
LNG
Pipeline maintenance SML
5-22-24 to 6-18-24
Seg. 420 capacity of 1,675 Mdth/d impacted up to 50 Mdth/d
east of Bay Springs
Pipeline maintenance SML
5-20-24 to 6-18-24
Seg. 430 capacity of 2,283 Mdth/d impacted up to 148 Mdth/d
west of Enterprise
Pipeline maintenance SMLL
5-21-24 to 5-25-24
Seg. 460 capacity of 2,283 Mdth/d impacted up to 175 Mdth/d
Pro. 2577C west of Elmore
PL. maintenance SML
8-19-24 to 8-23-24
We do not anticipate an impact to customers
east of Ocmulgee
Pro.2496D

## Slide 13: SNG South System Maint. Review cont.
May/June/July/August
MS
AL
GA
Enterprise
Gwinville
Selma
Auburn
Ellerslie
Thomaston
Ocmulgee
Hallgate
Wrens
Elmore
York
Gallion
Bay Springs
Atlanta
Elba
Hartwell
Elba Express
Aiken
Holy Trinity
Albany
Pavo
Brookman
Riceboro
Rincon
Compressor Station
Storage Field
LNG
Southern will be conducting other general maintenance during this period
SM2ndLL Pipeline remediation
6-3-24 to 6-7-24
Seg. 460 capacity of 2,140 Mdth/d impacted 65 Mdth/d
Pro. 21649 east of Elmore
Pipeline remediation SML
6-24-24 to 6-28-24
Pro.17842/34908
west of Thomaston
Pipeline maintenance SML
6-15-24 to 6-16-24
Seg. 430 capacity of 2,283 Mdth/d impacted up to 473 Mdth/d
west of Enterprise
Pipeline remediation SML
6-17-24 to 6-24-24
Pro. 21236
east of Thomaston
WSLL Pipeline remediation
6-10-24 to 6-14-24
Pro. 21078 Wrens to Savannah

## Slide 14: SNG South Louisiana System Pigging Review
Shadyside
White Castle
Franklinton
Toca
Gwinville
LA
MS
West Leg
East Leg
Pearl River
May/June/July/August
Southern will be conducting other general maintenance during this period
Compressor Station
Storage Field
Pigging on MPFLL
7-15-24 to 7-19-24
Pro. 5942-south of Franklinton
Pigging on SS28 line
7-15-24 to 7-19-24
Pro. 28751-west of White Castle

## Slide 15: SNG South Louisiana System Maint. Review
May/June/July/August
Shadyside
White Castle
Franklinton
Toca
Gwinville
LA
MS
West Leg
East Leg
Pearl River
Southern will be conducting other general maintenance during this period
Compressor Station
Storage Field
Sesh maintenance at Delhi
5-21-24 to 5-22-24 Cap. = 456 Mdth/d
5-23-24 = Cap. 482 Mdth/d
5-29-24 to 5-31-24=Cap. 445 Mdth/d
SESH pipeline maintenance
7-13-24 and
8-10-24 to 8-11-24
Meters affected
606610 SESH - SESH TO SNG
606400 SESH - GULFRUN TO SNG
606500 SESH - GULF SOUTH TO SNG
606700 SESH - ETC TIGER TO SNG
Southern will not be able to accept nominations during this maintenance
Pipeline maintenance
FGL
7-8-24 to 8-8-24
Seg. 370 cap. 1,123 Mdth/d impacted 20 Mdth/d
South of Gwinville
Pipeline remediation
DLFL
5-10-24 to 5-27-24
Pipeline maintenance
FGLL
8-19-24 to 8-26-24
Seg. 370 cap. 1,123 Mdth/d impacted 150 Mdth/d
South of Gwinville
Pipeline maintenance
FG2ndLL
8-27-24 to 9-3-24
Seg. 370 cap. 1,123 Mdth/d impacted 160 Mdth/d
South of Gwinville

## Slide 16: EEC Line
May/June/July/August
LA
MS
AL
GA
FL
Enterprise
White Castle
Bear Creek
Muldon
Atlanta
Thomaston
Albany
Elba
SC
Aiken
Elba Express
North System
South Louisiana
South System
Pearl River
Franklinton
Gwinville
Bienville
Onward
Pickens
Rankin
Toca
Shady Side
Louisville
Bay Springs
York
Gallion
Selma
Elmore
Auburn
Holy Trinity
Pavo
Reform
McConnells
Providence
Tarrant
Pell City
DeArmanville
Bell Mills
Rome
Ellerslie
Ocmulgee
Hall Gate
Wrens
Hartwell
Riceboro
Brookman

## Slide 17: SNG North System Pigging Review
Remainder of year
LA
MS
AL
GA
Logansport
Bienville
Bear Creek Storage
Onward
Pickens
Rankin
Louisville
Muldon Storage
Reform
McConnells
Providence
Tarrant
Pell City
DeArmanville
Bell Mills
Rome
Huntsville
Chattanooga
Atlanta
AL
Pigging on NMLL
10-8-24 to 10-9-24
Pro. 15346-east of Tarrant
Southern will be conducting other general maintenance during this period
Compressor Station
Storage Field

## Slide 18: SNG North System Maint. Review
Remainder of year
LA
MS
AL
GA
Bienville
Bear Creek Storage
Onward
Pickens
Rankin
Louisville
Muldon Storage
Reform
McConnells
Providence
Tarrant
Pell City
DeArmanville
Bell Mills
Rome
Huntsville
Atlanta
AL
Bear Creek Shut-in test
10-15-24 to 9 AM 10-22-24
Restrictions first into ISS then CSS-not to exceed 64% of CSS DIQ /DWQ
Muldon Shut-in test
10-1-24 to 10-7-24
Restrictions first into ISS then CSS-not to exceed 36% of CSS DIQ /DWQ
Logansport
Compressor Station
Storage Field
LNG
Southern will be conducting other general maintenance during this period
Pipeline maintenance 2ndNML
10-8-24 to 10-16-24
Seg. 400 capacity of 234 Mdth/d impacted up to 84 Mdth/d
Pro. 2328 east of Pickens
Muldon unit maintenance
9-9-24 to 11-8-24
Pipeline maintenance 2ndNML
10-10-24 to 10-13-24
Seg. 120 capacity of 652 Mdth/d impacted up to 355 Mdth/d
East of Providence

## Slide 19: SNG South System Pigging Review
Remainder of year
Southern will be conducting other general maintenance during this period
MS
AL
GA
Enterprise
Gwinville
Selma
Auburn
Ellerslie
Thomaston
Ocmulgee
Hallgate
Wrens
Elmore
York
Gallion
Bay Springs
Atlanta
Elba
Hartwell
Elba Express
Aiken
Holy Trinity
Albany
Pavo
Brookman
Riceboro
Compressor Station
Storage Field
LNG
Pigging on Ocmulgee Atlanta line-Ocmulgee to Bass Junction 9-17-24 to 9-18-24

## Slide 20: SNG South System Maint. Review
Remainder of year
MS
AL
GA
Enterprise
Gwinville
Selma
Auburn
Ellerslie
Thomaston
Ocmulgee
Hallgate
Wrens
Elmore
York
Gallion
Bay Springs
Atlanta
Elba
Hartwell
Elba Express
Aiken
Holy Trinity
Albany
Pavo
Brookman
Riceboro
Selma station maintenance
10-1-24 to 10-28-24
Seg. 460 capacity of 2,273 Mdth/d impacted 265 Mdth/d
Pro. 2593
Compressor Station
Storage Field
LNG
Southern will be conducting other general maintenance during this period
Thomaston Griffin 2nd loop line Pipeline maintenance
9-16-24 to 9-20-24
North of Thomaston
Pro. 231009
Gallion unit maintenance
9-23-24 to 9-24-24
Seg. 440 capacity of 2,300 Mdth/d impacted 445 Mdth/d
Elmore unit maintenance
9-25-24 to 9-26-24
Seg. 460 capacity of 2,293 Mdth/d impacted 450 Mdth/d
Auburn unit maintenance
10-7-24 to 10-8-24
Seg. 460 capacity of 2,293 Mdth/d impacted 340 Mdth/d
York unit maintenance
10-14-24
Seg. 430 capacity of 2,306 Mdth/d impacted 340 Mdth/d
Gallion unit maintenance
10-15-24
Seg. 440 capacity of 2,300 Mdth/d impacted 445 Mdth/d
Elmore unit maintenance
10-17-24
Seg. 460 capacity of 2,293 Mdth/d impacted 450 Mdth/d
Auburn unit maintenance
10-18-24
Seg. 460 capacity of 2,293 Mdth/d impacted 340 Mdth/d
York unit maintenance
10-23-24 to 10-24-24
Seg. 430 capacity of 2,306 Mdth/d impacted 340 Mdth/d

## Slide 21: SNG South Louisiana System Pigging Review
Remainder of year
Shadyside
White Castle
Franklinton
Toca
Gwinville
LA
MS
West Leg
East Leg
Pearl River
Compressor Station
Storage Field
Southern will be conducting other general maintenance during this period

## Slide 22: SNG South Louisiana System Maint. Review
Remainder of year
Shadyside
White Castle
Franklinton
Toca
Gwinville
LA
MS
West Leg
East Leg
Pearl River
Compressor Station
Storage Field
Southern will be conducting other general maintenance during this period

## Slide 23: EEC Line
Remainder of year
LA
MS
AL
GA
FL
Enterprise
White Castle
Bear Creek
Muldon
Chattanooga
Atlanta
Thomaston
Albany
Elba
SC
Aiken
Elba Express
North System
South Louisiana
South System
Pearl River
Franklinton
Gwinville
Bienville
Onward
Pickens
Rankin
Toca
Shady Side
Louisville
Bay Springs
York
Gallion
Selma
Elmore
Auburn
Holy Trinity
Pavo
Reform
McConnells
Providence
Tarrant
Pell City
DeArmanville
Bell Mills
Rome
Ellerslie
Ocmulgee
Hall Gate
Wrens
Hartwell
Riceboro
Brookman
Compressor Station
Storage Field
LNG

## Slide 24: Gas Control Contacts
Skyler Spyker – Manager
  (713) – 420 – 2386 (office)
  (806)-470-7743 (cell)
  skyler_spyker@kindermorgan.com
Kal Dankovich – Outage Coordinator
  (205) – 533 – 4795 (cell)
  kalman_dankovich@kindermorgan.com
Jimmy Reese – Lead Controller
  (205) – 577 – 3204 (cell)
  jimmy_reese@kindermorgan.com
Darren LaPoint – Lead Controller
  (713) – 927 – 3894 (cell)
  darren_lapont@kindermorgan.com

## Slide 25: Questions?