## Slide 1: Southern Natural Gas Company 2025 Outage Review
May 21st, 2025

## Slide 2: Welcome

## Slide 3: Agenda
Review of current and upcoming notable Outages
  May/June/July/August
Unscheduled Outages
  North System
  South System
  South Louisiana System
  Elba Express Pipeline(EEC)
The next outage meeting will be on June 18th, 2025, at 1:30PM CST
Contacts

## Slide 4: Disclaimers
Anticipated Impacts are estimates. Actual nominations, market demand, weather and pipeline conditions, etc. will determine if, and through what level, restrictions become necessary.
Unless otherwise stated, all scheduled dates represent gas days as defined in the Southern Natural Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time).
Scheduled dates are subject to change.
Projects may be added, altered, delayed or cancelled.
SNG will provide notice of such additions or changes via Southern’s electronic bulletin board postings.
Dates as posted on the EBB should be deemed correct in the event of conflicts between the EBB posted dates and dates within this presentation.

## Slide 5: Color Key for Maps
Yellow
  Restrictions are possible
  With extended duration, restrictions could be necessary from time to time
  Lower than normal pressures may be experienced
  Meter(s) affected are noted with (PIN #)
Red
  Restrictions are probable

## Slide 6: Southern Natural Gas Pipeline
LA
MS
AL
GA
FL
Enterprise
White Castle
Bear Creek
Muldon
Chattanooga
Atlanta
Thomaston
Albany
Elba
SC
Aiken
Elba Express
North System
South Louisiana
South System
Pearl River
Franklinton
Gwinville
Logansport
Bienville
Onward
Pickens
Rankin
Toca
Shady Side
Louisville
Bay Springs
York
Gallion
Selma
Elmore
Auburn
Holy Trinity
Pavo
Reform
McConnells
Providence
Tarrant
Pell City
DeArmanville
Bell Mills
Rome
Ellerslie
Ocmulgee
Hall Gate
Wrens
Hartwell
Riceboro
Brookman
Compressor Station
Storage Field
LNG
Fairburn
Hilliard
Jefferson
Rincon

## Slide 7: Southern Natural Gas Pipeline
Unscheduled Outage Update
LA
MS
AL
GA
FL
Enterprise
White Castle
Bear Creek
Muldon
Chattanooga
Atlanta
Thomaston
Albany
Elba
SC
Aiken
North System
South Louisiana
South System
Pearl River
Franklinton
Gwinville
Logansport
Bienville
Onward
Pickens
Rankin
Toca
Shady Side
Louisville
Bay Springs
York
Gallion
Selma
Elmore
Auburn
Holy Trinity
Pavo
Reform
McConnells
Providence
Tarrant
Pell City
DeArmanville
Bell Mills
Rome
Ellerslie
Ocmulgee
Hall Gate
Wrens
Hartwell
Riceboro
Brookman
Compressor Station
Storage Field
LNG
Fairburn
Jefferson
Rincon
Hilliard
Unscheduled Unit Outage
Proj-52723
Thomaston compressor station
1-30-25 to 5-25-25
Seg. 490 capacity of 1,535 Mdth/d impacted up to 40 Mdth/d
Elba Express

## Slide 8: SNG North System Pigging Review
May/June/July/August
LA
MS
AL
GA
Logansport
Bienville
Bear Creek Storage
Onward
Pickens
Rankin
Louisville
Muldon Storage
Reform
McConnells
Providence
Tarrant
Pell City
DeArmanville
Bell Mills
Rome
Huntsville
Chattanooga
Atlanta
Southern will be conducting other general maintenance during this period
AL
Compressor Station
Storage Field
LNG
Duncanville
Pigging on 2nd North Main line
Proj-SNG-4754
5-20-25 to 5-22-25
east of McConnells
Pigging on West Point loop line
Proj-SNG-18566
6-3-25 to 6-6-25
south of Muldon
Pigging on Gadsden Branch line
Proj-SNG-5473
5-28-25 to 5-29-25
north of Pell City

## Slide 9: SNG North System Maintenance Review
May/June/July/August
Compressor Station
Storage Field
LA
MS
GA
Logansport
Bienville
Bear Creek Storage
Onward
Pickens
Rankin
Louisville
Muldon Storage
Reform
McConnells
Providence
Tarrant
Pell City
DeArmanville
Bell Mills
Rome
Huntsville
Chattanooga
Atlanta
Southern will be conducting other general maintenance during this period
AL
Duncanville
Unit Maintenance
Proj-41251
Pickens compressor station
5-19-25 to 6-6-25
Seg. 400 capacity of 234 Mdth/d impacted 85 Mdth/d
Pipeline Maintenance
North Main line
Proj-SNG-15331/SNG-38939
5-5-25 to 5-31-25
Seg. 130 capacity of 563 Mdth/d impacted 120 Mdth/d
west of Tarrant
Pipeline Maintenance
North Main line
6-9-25 to 6-12-25
Seg. 50 capacity of 520 Mdth/d impacted 170 Mdth/d
east of Louisville
Pipeline Maintenance
Heflin Lateral line
6-18-25 to 6-20-25
We do not anticipate an impact to customers at this time,
east of Dearmanville

## Slide 10: SNG South System Pigging Review
May/June/July/August
Southern will be conducting other general maintenance during this period
MS
AL
GA
Enterprise
Gwinville
Selma
Auburn
Ellerslie
Thomaston
Ocmulgee
Hall Gate
Wrens
Elmore
York
Gallion
Bay Springs
Atlanta
Elba
Hartwell
Aiken
Holy Trinity
Albany
Pavo
Brookman
Compressor Station
Storage Field
LNG
Fairburn
Hilliard
Jefferson
Rincon
Pigging on Main Line 01
Proj-SNG-38132
5-28-25 to 5-30-25
north of Albany
SC
FL
Pigging on South Main loop line
Proj-SNG-11272
6-9-25 to 6-13-25
west of Ellerslie
Riceboro
Pigging on Phenix City Columbus line
Proj-SNG-4665
7-15-25 to 7-17-25
east of Auburn
Pigging on Auburn Grantville loop line
Proj-SNG-15062
7-29-25
north of Auburn
Pigging on South Main loop line
Proj-SNG-37217
5-20-25 to 5-22-25
east of Ocmulgee
Pigging on North Terrell Line 6
Proj-SNG-15224
8-26-25 to 8-28-25
south of Holy Trinity

## Slide 11: SNG South System Maintenance Review
May/June/July/August
MS
AL
GA
Enterprise
Gwinville
Selma
Auburn
Ellerslie
Thomaston
Ocmulgee
Hall Gate
Wrens
Elmore
York
Gallion
Bay Springs
Atlanta
Elba
Hartwell
Aiken
Holy Trinity
Albany
Pavo
Brookman
Riceboro
Southern will be conducting other general maintenance during this period
Compressor Station
Storage Field
LNG
Fairburn
Hilliard
Jefferson
Rincon
SC
FL
Unit Maintenance
Proj-52833
Hall Gate compressor station
4-28-25 to 5-25-25
Seg. 560 capacity of 705 Mdth/d impacted 70 Mdth/d
Unit Maintenance
Proj-52301
Selma compressor station
5-8-25 to 7-13-25
Seg. 460 capacity of 2,293 Mdth/d impacted 165 Mdth/d
Unit Maintenance
Proj-525112
Elmore compressor station
5-19-25 to 5-23-25
Seg. 460 capacity of 2,293 Mdth/d impacted 450 Mdth/d
Unit Maintenance
Proj-52113
Gwinville compressor station
5-12-25 to 6-1-25
Seg. 400 capacity of 234 Mdth/d impacted 45 Mdth/d
Station Maintenance
Gwinville compressor station
Proj-5211P6a
5-16-25 to 5-23-25
Seg. 410 capacity of 1,655 Mdth/d impacted 210 Mdth/d
Pipeline Maintenance
South Main line
Proj-SNG-21939
5-27-25 to 6-6-25
Seg. 440 capacity of 2,300 Mdth/d impacted 55 Mdth/d
east of Gallion

## Slide 12: SNG South System Maintenance Review continued
May/June/July/August
MS
AL
GA
Enterprise
Gwinville
Selma
Auburn
Ellerslie
Thomaston
Ocmulgee
Hall Gate
Wrens
Elmore
York
Gallion
Bay Springs
Atlanta
Elba
Hartwell
Aiken
Holy Trinity
Albany
Pavo
Brookman
Riceboro
Compressor Station
Storage Field
LNG
Southern will be conducting other general maintenance during this period
Fairburn
Hilliard
Jefferson
Rincon
SC
FL
Station Maintenance
Gwinville compressor station
Proj-5211P6b
5-27-25 to 5-30-25
Seg. 390 capacity of 1,607 Mdth/d impacted 390 Mdth/d
Pipeline Maintenance
South Main 2nd loop line
Proj-SNG-8793
8-1-25 to 8-14-25
Seg. 440 capacity of 2,300 Mdth/d impacted 105 Mdth/d
east of Gallion
Pipeline Maintenance
South Main 2nd loop line
Proj-SNG-8793
8-15-25 to 8-24-25
Seg. 460 capacity of 2,293 Mdth/d impacted 135 Mdth/d
east of Selma

## Slide 13: SNG South Louisiana System Pigging Review
Shadyside
White Castle
Franklinton
Toca
Gwinville
LA
MS
West Leg
East Leg
Pearl River
May/June/July/August
Southern will be conducting other general maintenance during this period
Compressor Station
Storage Field
Pigging on Franklinton Gwinville line
7-22-25 to 7-24-25
Proj-SNG-18722
south of Gwinville
Pigging on Erath SS28 line
Proj-SNG-4706
7-14-25 to 7-17-25
south of White Castle
Pigging on Franklinton Gwinville loop line
7-29-25 to 7-30-25
Proj-SNG-5873
8-5-25 to 8-7-25
Proj-SNG-4585
south of Gwinville

## Slide 14: SNG South Louisiana System Maintenance Review
May/June/July/August
Shadyside
White Castle
Franklinton
Toca
Gwinville
LA
MS
West Leg
East Leg
Pearl River
Southern will be conducting other general maintenance during this period
Compressor Station
Storage Field
Pipeline Maintenance
Duck Lake Franklinton line
Proj-SNG-2753
5-22-25 to 6-5-25
Proj-SNG-22856
8-25-25 to 8-29-25
Seg. 350 capacity of 695 Mdth/d impacted 160 Mdth/d
north of White Castle
SESH planned maintenance affecting SNG capacity
5-21-25
Capacity restricted to 476 Mdth/d
Meters affected
606400 SESH - ENABLE TO SNG
606500 SESH - GULF SOUTH TO SNG
606700 SESH - ETC TIGER TO SNG
All services may be at risk during this maintenance.
Pipeline Maintenance
Franklinton Gwinville 2nd loop line
Proj-SNG-36213
7-9-25 to 7-24-25
Seg. 390 capacity of 1,607 Mdth/d impacted 230 Mdth/d
south of Gwinville

## Slide 15: EEC Line Pigging and Maintenance Review
May/June/July/August
LA
MS
AL
GA
FL
Enterprise
White Castle
Bear Creek
Muldon
Atlanta
Thomaston
Albany
Elba
SC
Aiken
North System
South Louisiana
South System
Pearl River
Franklinton
Gwinville
Bienville
Onward
Pickens
Rankin
Toca
Shady Side
Louisville
Bay Springs
York
Gallion
Selma
Elmore
Auburn
Holy Trinity
Pavo
Reform
McConnells
Providence
Tarrant
Pell City
DeArmanville
Bell Mills
Rome
Ellerslie
Ocmulgee
Hall Gate
Wrens
Hartwell
Riceboro
Brookman
Fairburn
Hilliard
Jefferson
Rincon
Duncanville
Elba Express

## Slide 16: SNG North System Pigging Review
Remainder of the year
Compressor Station
Storage Field
LA
MS
GA
Logansport
Bienville
Bear Creek Storage
Onward
Pickens
Rankin
Louisville
Muldon Storage
Reform
McConnells
Providence
Tarrant
Pell City
DeArmanville
Bell Mills
Rome
Huntsville
Chattanooga
Atlanta
Southern will be conducting other general maintenance during this period
AL
Duncanville
Pigging on Chattanooga Branch line
Proj-SNG-29149
11-11-25 to 11-14-25
north of Bell Mills
Pigging on Rome Calhoun line
Proj-SNG-4763
11-11-25 to 11-13-25
south of Rome

## Slide 17: SNG North System Maintenance Review
Remainder of the year
Compressor Station
Storage Field
LA
MS
GA
Logansport
Bienville
Bear Creek Storage
Onward
Pickens
Rankin
Louisville
Muldon Storage
Reform
McConnells
Providence
Tarrant
Pell City
DeArmanville
Bell Mills
Rome
Huntsville
Chattanooga
Atlanta
Southern will be conducting other general maintenance during this period
AL
Bear Creek Shut-in test
10-21-25 to 9 AM 10-28-25
Restrictions first into ISS then CSS-not to exceed 64% of CSS DIQ /DWQ
Muldon Shut-in test
10-7-25 to 9 AM 10-14-25
Restrictions first into ISS then CSS-not to exceed 36% of CSS DIQ /DWQ
Duncanville

## Slide 18: SNG South System Pigging Review
Remainder of the year
MS
AL
GA
Enterprise
Gwinville
Selma
Auburn
Ellerslie
Thomaston
Ocmulgee
Hallgate
Wrens
Elmore
York
Gallion
Bay Springs
Atlanta
Elba
Hartwell
Aiken
Holy Trinity
Albany
Pavo
Brookman
Riceboro
Compressor Station
Storage Field
LNG
Southern will be conducting other general maintenance during this period
Fairburn
Hilliard
Jefferson
Rincon
Pigging on Brunswick line
Proj-SNG-9076
12-8-25 to 12-12-25
south of Ocmulgee
FL
SC

## Slide 19: SNG South System Maintenance Review
Remainder of the year
MS
AL
GA
Enterprise
Gwinville
Selma
Auburn
Ellerslie
Thomaston
Ocmulgee
Hallgate
Wrens
Elmore
York
Gallion
Bay Springs
Atlanta
Elba
Hartwell
Aiken
Holy Trinity
Albany
Pavo
Brookman
Riceboro
Compressor Station
Storage Field
LNG
Southern will be conducting other general maintenance during this period
Fairburn
Hilliard
Jefferson
Rincon
FL
SC

## Slide 20: SNG South Louisiana System Pigging Review
Remainder of the year
Shadyside
White Castle
Franklinton
Toca
Gwinville
LA
MS
West Leg
East Leg
Pearl River
Southern will be conducting other general maintenance during this period
Compressor Station
Storage Field

## Slide 21: SNG South Louisiana System Maintenance Review
Remainder of the year
Shadyside
White Castle
Franklinton
Toca
Gwinville
LA
MS
West Leg
East Leg
Pearl River
Southern will be conducting other general maintenance during this period
Compressor Station
Storage Field
Pipeline Maintenance
White Castle Franklinton loop line
Proj-SNG-22856
9-3-25 to 9-8-25
Seg. 350 capacity of 735 Mdth/d impacted 100 Mdth/d
Proj-SNG-2933/SNG-3089
9-8-25 to 10-7-25
Seg. 350 capacity of 735 Mdth/d impacted 200 Mdth/d
north of White Castle
Pipeline Maintenance
Duck Lake Franklinton line
Proj-SNG-2933
10-13-25 to 11-3-25
Seg. 350 capacity of 735 Mdth/d impacted 15 Mdth/d
north of White Castle

## Slide 22: EEC Line Pigging and Maintenance Review
Remainder of the year
LA
MS
AL
GA
FL
Enterprise
White Castle
Bear Creek
Muldon
Atlanta
Thomaston
Albany
Elba
SC
Aiken
North System
South Louisiana
South System
Pearl River
Franklinton
Gwinville
Bienville
Onward
Pickens
Rankin
Toca
Shady Side
Louisville
Bay Springs
York
Gallion
Selma
Elmore
Auburn
Holy Trinity
Pavo
Reform
McConnells
Providence
Tarrant
Pell City
DeArmanville
Bell Mills
Rome
Ellerslie
Ocmulgee
Hall Gate
Wrens
Hartwell
Riceboro
Brookman
Fairburn
Hilliard
Jefferson
Rincon

## Slide 23: Gas Control Contacts
Skyler Spyker – Manager
  (713) – 420 – 2386 (office)
  (806)-470-7743 (cell)
  skyler_spyker@kindermorgan.com
Mario Murillo – Outage Coordinator
  (281) – 753 – 6530 (cell)
  mario_murillo@kindermorgan.com
Jimmy Reese – Lead Controller
  (205) – 577 – 3204 (cell)
  jimmy_reese@kindermorgan.com
Darren LaPoint – Lead Controller
  (713) – 927 – 3894 (cell)
  darren_lapoint@kindermorgan.com

## Slide 24: Questions?