{"text_format":"1","workbook":"xlsx","n_sheets":4,"sheets":["Closed","Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":8,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Closed","index":0,"n_rows":37,"n_cols":22,"rows_kept":37,"cut":false,"hidden":true,"merged":[[1,3,1,15],[2,3,2,15],[3,3,3,15]]}
[null,null,null,"Updated ","2016"]
[null,null,null,"Tennessee Gas Pipeline 2015 Pipeline Outage and Maintenance Summary"]
[null,null,null,"This is a summary of the current status of all TGP Winter 2014-2015 Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  Additionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
[null,null,null,"*** Indicates revision"]
["Date Change","Project New/Completed/Closed","Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","Location","Leg","Zone","Maintenance Activity","Anticipated Impact","Potential Restriction Level","TOS Potential Restrictions","Meter(s) in Impacted Area","Customer Notifications","Loc","Email Text","Posting Text","Completion Text"]
[{"$f":"IF(AND(H6<>\"\",I6<>\"\"), \"Date change. Previously scheduled \" & TEXT(H6,\"m/d/y;@\") &IF(H6=I6,\"\",\" to \" & TEXT(I6,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed",null,{"$f":"IF(G6<>\"\",\"***\",\"\")","v":"***"},"2015-01-11","2016-01-11",{"$f":"IF(AND(A6=\"\",B6=\"\"),\"\",IF(B6=\"\",A6,B6))","v":"Project Completed"},null,null,"MS #412494 DCP Warren","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412494 DCP Warren",401,{"$f":"\"(\"&C6&\") \"&J6&\":  \"&M6&IF(AND(E6=\"\",F6=\"\"),\"\",\" (\")&IF(E6=\"\",\"\",\"\"&TEXT(E6,\"m/d/y;@\"))&IF(OR(F6=E6,E6=\"\",F6=\"\"),\"\",\" to \")&IF(OR(F6=\"\",F6=E6),\"\",TEXT(F6,\"m/d/y;@\"))&IF(AND(E6=\"\",F6=\"\"),\"\",\")\")","v":"() MS #412494 DCP Warren:  Meter Station (1/11/15 to 1/11/16)"},{"$f":"D6&J6&\":  \"&M6&IF(AND(E6=\"\",F6=\"\"),\"\",\"\n\")&IF(E6=\"\",\"\",\"--\"&TEXT(E6,\"m/d/y;@\"))&IF(OR(F6=E6,E6=\"\",F6=\"\"),\"\",\" through \")&IF(OR(F6=\"\",F6=E6),\"\",TEXT(F6,\"m/d/y;@\"))&IF(AND(E6=\"\",F6=\"\"),\"\",\":  \")&N6&\"  \"&P6&IF(Q6=\"\",\"\",\"\n\"&Q6)&IF(G6=\"\",\"\",\"\n***\")&G6&\"\n………………………………\"","v":"***MS #412494 DCP Warren:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412494 DCP Warren\n***Project Completed\n………………………………"},{"$f":"D6&J6&\":  \"&M6&IF(G6=\"\",\"\",\"\n***\")&G6&IF(Q6=\"\",\"\",\"\nThe following meters are available for nominations:\n\")&Q6&\"\n………………………………\"","v":"***MS #412494 DCP Warren:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412494 DCP Warren\n………………………………"}]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412400 King Ranch","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412400 King Ranch",402.1,"() MS #412400 King Ranch:  Meter Station (1/11/15 to 1/11/16)","***MS #412400 King Ranch:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412400 King Ranch\n***Project Completed\n………………………………","***MS #412400 King Ranch:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412400 King Ranch\n………………………………"]
["","Project Completed",null,"***","2015-01-12","2016-01-12","Project Completed",null,null,"MS #410539 Duvak Gas Gathering","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410539 Duvak Gas Gathering",402.1,"() MS #410539 Duvak Gas Gathering:  Meter Station (1/12/15 to 1/12/16)","***MS #410539 Duvak Gas Gathering:  Meter Station\n--1/12/15 through 1/12/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410539 Duvak Gas Gathering\n***Project Completed\n………………………………","***MS #410539 Duvak Gas Gathering:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n410539 Duvak Gas Gathering\n………………………………"]
["","Project Completed",null,"***","2015-01-13","2016-01-13","Project Completed",null,null,"MS #412356 DCP LaGloria","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412356 DCP LaGloria",403.1,"() MS #412356 DCP LaGloria:  Meter Station (1/13/15 to 1/13/16)","***MS #412356 DCP LaGloria:  Meter Station\n--1/13/15 through 1/13/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412356 DCP LaGloria\n***Project Completed\n………………………………","***MS #412356 DCP LaGloria:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412356 DCP LaGloria\n………………………………"]
["","Project Completed",null,"***","2015-01-13","2016-01-13","Project Completed",null,null,"MS #410173 Enterprise LaReforma","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410173 Enterprise LaReforma",406.1,"() MS #410173 Enterprise LaReforma:  Meter Station (1/13/15 to 1/13/16)","***MS #410173 Enterprise LaReforma:  Meter Station\n--1/13/15 through 1/13/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410173 Enterprise LaReforma\n***Project Completed\n………………………………","***MS #410173 Enterprise LaReforma:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n410173 Enterprise LaReforma\n………………………………"]
["","Project Completed",null,"***","2015-01-12","2016-01-12","Project Completed",null,null,"MS #411903 Enterprise El Benito","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","411903 Enterprise El Benito",407.1,"() MS #411903 Enterprise El Benito:  Meter Station (1/12/15 to 1/12/16)","***MS #411903 Enterprise El Benito:  Meter Station\n--1/12/15 through 1/12/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n411903 Enterprise El Benito\n***Project Completed\n………………………………","***MS #411903 Enterprise El Benito:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n411903 Enterprise El Benito\n………………………………"]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412088 Enterprise Sullivan","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412088 Enterprise Sullivan",407.1,"() MS #412088 Enterprise Sullivan:  Meter Station (1/11/15 to 1/11/16)","***MS #412088 Enterprise Sullivan:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412088 Enterprise Sullivan\n***Project Completed\n………………………………","***MS #412088 Enterprise Sullivan:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412088 Enterprise Sullivan\n………………………………"]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412683 HESCO","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412683 HESCO",408.1,"() MS #412683 HESCO:  Meter Station (1/11/15 to 1/11/16)","***MS #412683 HESCO:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412683 HESCO\n***Project Completed\n………………………………","***MS #412683 HESCO:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412683 HESCO\n………………………………"]
[{"$f":"IF(AND(H14<>\"\",I14<>\"\"), \"Date change. Previously scheduled \" & TEXT(H14,\"m/d/y;@\") &IF(H14=I14,\"\",\" to \" & TEXT(I14,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X16-36843",{"$f":"IF(G14<>\"\",\"***\",\"\")","v":"***"},"2016-01-27","2016-01-27","Project Completed",null,null,"Sta. 237",200,5,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,237,"(X16-36843) Sta. 237:  Unit  Maintenance (1/27/16)","***Sta. 237:  Unit  Maintenance\n--1/27/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Sta. 237:  Unit  Maintenance\n***Project Completed\n………………………………"]
[{"$f":"IF(AND(H15<>\"\",I15<>\"\"), \"Date change. Previously scheduled \" & TEXT(H15,\"m/d/y;@\") &IF(H15=I15,\"\",\" to \" & TEXT(I15,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X14-1478563",{"$f":"IF(G15<>\"\",\"***\",\"\")","v":"***"},"2015-11-16","2016-02-12","Project Completed",null,null,"MLV 32-1D to 33-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,32.200000000000003,"(X14-1478563) MLV 32-1D to 33-1:  Hydrotest (11/16/15 to 2/12/16)","***MLV 32-1D to 33-1:  Hydrotest\n--11/16/15 through 2/12/16:  This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***MLV 32-1D to 33-1:  Hydrotest\n***Project Completed\n………………………………"]
[null,"Project Completed","X16-16074",null,"2016-01-18","2016-01-28","Project Completed",null,null,"Station 550","500","1","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,550,"(X16-16074) Station 550:  Station Maintenance (1/18/16 to 1/28/16)","Station 550:  Station Maintenance\n--1/18/16 through 1/28/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","Station 550:  Station Maintenance\n***Project Completed\n………………………………"]
[{"$f":"IF(AND(H17<>\"\",I17<>\"\"), \"Date change. Previously scheduled \" & TEXT(H17,\"m/d/y;@\") &IF(H17=I17,\"\",\" to \" & TEXT(I17,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X16-46202",{"$f":"IF(G17<>\"\",\"***\",\"\")","v":"***"},"2016-02-01","2016-02-07","Project Completed",null,null,"Station 9","100","0","Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.",null,9,"(X16-46202) Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items) (2/1/16 to 2/7/16)","***Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)\n--2/1/16 through 2/7/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\n***Project Completed\n………………………………","***Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)\n***Project Completed\n………………………………"]
["","Project Completed","X15-925633","***","2016-02-09","2016-02-11","Project Completed",null,null,"Sta. 266A",200,6,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,266,"(X15-925633) Sta. 266A:  Unit  Maintenance (2/9/16 to 2/11/16)","***Sta. 266A:  Unit  Maintenance\n--2/9/16 through 2/11/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Sta. 266A:  Unit  Maintenance\n***Project Completed\n………………………………"]
["","Project Completed","X15-929733","***","2016-01-27","2016-02-10","Project Completed",null,null,"MLV 834-1 to 838-1",800,5,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",834.1,"(X15-929733) MLV 834-1 to 838-1:  ILI/Cleaning Pig (1/27/16 to 2/10/16)","***MLV 834-1 to 838-1:  ILI/Cleaning Pig\n--1/27/16 through 2/10/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 834-1 to 838-1:  ILI/Cleaning Pig\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X14-1562506","***","2015-11-02","2016-02-19","Project Completed",null,null,"MLV 5-1 to 6-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410063 ROCHE DEHYDRATION             \n",5.0999999999999996,"(X14-1562506) MLV 5-1 to 6-1:  Hydrotest (11/2/15 to 2/19/16)","***MLV 5-1 to 6-1:  Hydrotest\n--11/2/15 through 2/19/16:  This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410063 ROCHE DEHYDRATION             \n\n***Project Completed\n………………………………","***MLV 5-1 to 6-1:  Hydrotest\n***Project Completed\nThe following meters are available for nominations:\n410063 ROCHE DEHYDRATION             \n\n………………………………"]
["","Project Completed","X14-1562506","***","2015-11-02","2016-02-19","Project Completed",null,null,"MLV 7-1 to 9-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","\n412490 Charro\n421083 Eagle Ford Field Service",5.0999999999999996,"(X14-1562506) MLV 7-1 to 9-1:  Hydrotest (11/2/15 to 2/19/16)","***MLV 7-1 to 9-1:  Hydrotest\n--11/2/15 through 2/19/16:  This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n\n412490 Charro\n421083 Eagle Ford Field Service\n***Project Completed\n………………………………","***MLV 7-1 to 9-1:  Hydrotest\n***Project Completed\nThe following meters are available for nominations:\n\n412490 Charro\n421083 Eagle Ford Field Service\n………………………………"]
["Date change. Previously scheduled 2/18/16 to 2/20/16.","Project Completed","X15-882289","***","2016-02-22","2016-02-24","Project Completed","2016-02-18","2016-02-20","MLV 24-2 to 25-2S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.2,"(X15-882289) MLV 24-2 to 25-2S:  Anomaly Remediation (2/22/16 to 2/24/16)","***MLV 24-2 to 25-2S:  Anomaly Remediation\n--2/22/16 through 2/24/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 24-2 to 25-2S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-925630","***","2016-02-23","2016-02-23","Project Completed",null,null,"WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B)",200,"L","ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,265.10000000000002,"(X15-925630) WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig (2/23/16)","***WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig\n--2/23/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig\n***Project Completed\n………………………………"]
["","Project Completed","X16-23748","***","2016-02-15","2016-02-18","Project Completed",null,null,"MLV 530-3 to 532-3",500,"L","ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,530.29999999999995,"(X16-23748) MLV 530-3 to 532-3:  ILI/Cleaning Pig (2/15/16 to 2/18/16)","***MLV 530-3 to 532-3:  ILI/Cleaning Pig\n--2/15/16 through 2/18/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***MLV 530-3 to 532-3:  ILI/Cleaning Pig\n***Project Completed\n………………………………"]
["","Project Canceled","X16-98720","***","2016-03-06","2016-03-06","Project Canceled",null,null,"Sta. 1",100,0,"Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,1,"(X16-98720) Sta. 1:  Station Maintenance (3/6/16)","***Sta. 1:  Station Maintenance\n--3/6/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Canceled\n………………………………","***Sta. 1:  Station Maintenance\n***Project Canceled\n………………………………"]
["","Project Completed","X14-1562513\nX14-1540661","***","2015-07-01","2016-03-04","Project Completed",null,null,"Station 32","100","0","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,32,"(X14-1562513\nX14-1540661) Station 32:  Station Maintenance (7/1/15 to 3/4/16)","***Station 32:  Station Maintenance\n--7/1/15 through 3/4/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Station 32:  Station Maintenance\n***Project Completed\n………………………………"]
["","Project Canceled","X15-926822","***","2016-06-06","2016-06-11","Project Canceled",null,null,"BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1)",300,6,"Pipe Inspection","This project involves inspecting multiple sites.  We do not anticipate having to do any repairs, however if a repair is needed  there is a potential that the pipe  may require replacement which will require isolation of the pipe.  This may limit throughput and will result in restrictions based on customer nominations.  Customers may experience pressure fluctuations during this timeframe.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",343.1,"(X15-926822) BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection (6/6/16 to 6/11/16)","***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection\n--6/6/16 through 6/11/16:  This project involves inspecting multiple sites.  We do not anticipate having to do any repairs, however if a repair is needed  there is a potential that the pipe  may require replacement which will require isolation of the pipe.  This may limit throughput and will result in restrictions based on customer nominations.  Customers may experience pressure fluctuations during this timeframe.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928271","***","TBD","TBD","Project Canceled",null,null,"MLV 555-1 to 550-1",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.1,"(X15-928271) MLV 555-1 to 550-1:  ILI/Cleaning Pig (TBD)","***MLV 555-1 to 550-1:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-1 to 550-1:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928272","***","TBD","TBD","Project Canceled",null,null,"MLV 555-2 to 550-2",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.20000000000005,"(X15-928272) MLV 555-2 to 550-2:  ILI/Cleaning Pig (TBD)","***MLV 555-2 to 550-2:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-2 to 550-2:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928273","***","TBD","TBD","Project Canceled",null,null,"MLV 555-3 to 552-3",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.29999999999995,"(X15-928273) MLV 555-3 to 552-3:  ILI/Cleaning Pig (TBD)","***MLV 555-3 to 552-3:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-3 to 552-3:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-882281","***","2016-02-24","2016-03-03","Project Completed",null,null,"24-1A to 25-1S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.1,"(X15-882281) 24-1A to 25-1S:  Anomaly Remediation (2/24/16 to 3/3/16)","***24-1A to 25-1S:  Anomaly Remediation\n--2/24/16 through 3/3/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***24-1A to 25-1S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-882291","***","2016-03-03","2016-03-04","Project Completed",null,null,"MLV 24-3 to 25-3S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.3,"(X15-882291) MLV 24-3 to 25-3S:  Anomaly Remediation (3/3/16 to 3/4/16)","***MLV 24-3 to 25-3S:  Anomaly Remediation\n--3/3/16 through 3/4/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 24-3 to 25-3S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X14-1178175","***","2015-06-15","2016-03-31","Project Completed",null,null,"Station 63","100","1","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,63,"(X14-1178175) Station 63:  Station Maintenance (6/15/15 to 3/31/16)","***Station 63:  Station Maintenance\n--6/15/15 through 3/31/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Station 63:  Station Maintenance\n***Project Completed\n………………………………"]
["","Project Cancelled","X15-913224","***","2016-04-16","2016-05-21","Project Cancelled",null,null,"MLV 109-2",100,2,"Pipe Replacement","This project will require taking the pipeline section out of service.   This will limit throughput and will result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",109.2,"(X15-913224) MLV 109-2:  Pipe Replacement (4/16/16 to 5/21/16)","***MLV 109-2:  Pipe Replacement\n--4/16/16 through 5/21/16:  This project will require taking the pipeline section out of service.   This will limit throughput and will result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Cancelled\n………………………………","***MLV 109-2:  Pipe Replacement\n***Project Cancelled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-926830","***","2016-03-07","2016-03-11","Project Completed",null,null,"MLV 400-1 to 408-1",100,0,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.","To Be Determined",400.1,"(X15-926830) MLV 400-1 to 408-1:  ILI/Cleaning Pig (3/7/16 to 3/11/16)","***MLV 400-1 to 408-1:  ILI/Cleaning Pig\n--3/7/16 through 3/11/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 400-1 to 408-1:  ILI/Cleaning Pig\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Cancelled","X16-143836","***","2016-03-28","2016-04-04","Project Cancelled",null,null,"Sta. 409",100,0,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.",null,409,"(X16-143836) Sta. 409:  Unit  Maintenance (3/28/16 to 4/4/16)","***Sta. 409:  Unit  Maintenance\n--3/28/16 through 4/4/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\n***Project Cancelled\n………………………………","***Sta. 409:  Unit  Maintenance\n***Project Cancelled\n………………………………"]
["","Project Cancelled","X15-929680","***","2016-04-18","2016-04-27","Project Cancelled",null,null,"SABINE - KINDER LINE to 822-1",800,"L","Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",822.1,"(X15-929680) SABINE - KINDER LINE to 822-1:  Anomaly Remediation (4/18/16 to 4/27/16)","***SABINE - KINDER LINE to 822-1:  Anomaly Remediation\n--4/18/16 through 4/27/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Cancelled\n………………………………","***SABINE - KINDER LINE to 822-1:  Anomaly Remediation\n***Project Cancelled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]

{"sheet":"Sheet1","index":1,"n_rows":34,"n_cols":32,"rows_kept":34,"cut":false,"hidden":false,"merged":[[2,0,2,14]]}
["Updated ","2020-08-13"]
["Southern Natural Gas Pipeline 2020 Pipeline Outage and Maintenance Summary"]
["This is a summary of the current status of all SNG 2020 Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  \nAdditionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Southern Natural Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
["*** Indicates revision"]
["Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","System","Zone","Segment","Location","Maintenance Activity","Anticipated Impact","Potential Restriction Level","Meter(s) in Impacted Area",null,null,null,null,null,null,null,null,null,"\\\\corp\\trans\\TranServices\\OPPLAN\\COMMON\\Outages\\Outage_DB\\SNG"]
["X19-951378",null,"2020-06-08","2020-11-06",null,null,null,"South","1","430","Enterprise compressor station","Controls Upgrade","This project will require unit outages one unit at a time, which could limit throughput through the station and result in restrictions based on customer nominations.","OP",null,null,null,null,null,null,null,null,null,null,"X19-951378",0,0,0,0,0,0,0]
["X19-1034993",null,"2020-07-20","2020-10-08",null,null,null,"South","1","400","Gwinville compressor station","Unit maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","OP",null,null,null,null,null,null,null,null,null,null,"X19-1034993",0,0,0,0,0,0,0]
["X19-979799",null,"2020-08-03","2020-08-28",null,null,null,"South","1","400","Rankin compressor station","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","OP",null,null,null,null,null,null,null,null,null,null,"X19-979799",0,0,0,0,0,0,0]
["X20-228579","***","2020-08-04","2020-08-07","Completed",null,null,"2","North","120","West of Tarrant compressor station","pigging 8-3-20 to 8-7-20","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,null,null,null,null,null,null,null,null,null,"X20-228579",1,0,0,0,0,0,0]
["X20-725824","***","2020-08-05","2020-08-09","Completed",null,null,"3","South","660","Albany compressor station","Unit maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.",null,null,null,null,null,null,null,null,null,null,null,"X20-725824",1,0,0,0,0,0,0]
["X20-555734","***","2020-08-11","2020-08-11","Completed",null,null,"2","North","120","2nd north main line west of Tarrant compressor station","pigging-8-11-20","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,null,null,null,null,null,null,null,null,null,"X20-555734",1,0,0,0,0,0,0]
["X20-683577",null,"2020-08-11","2020-09-10",null,null,null,"North","0","20","Logansports line Bienville to Perryville","Pigging-gauge--8-11-20\ncaliper - 8-12-20\nAFD 9-8-20\nEMAT-9-10-20","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,null,null,null,null,null,null,null,null,null,"X20-683577",0,0,0,0,0,0,0]
["X20-658531",null,"2020-08-11","2020-08-13",null,null,null,"South","1","430","Enterprise to York compressor station","Pigging-\n8-11-20--brush/gage\n8-13-20--smart","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,null,null,null,null,null,null,null,null,null,"X20-658531",0,0,0,0,0,0,0]
["X19-814613",null,"2020-08-17","2020-08-20",null,null,null,"South LA","1","370","Franklinton Gwinville 2nd loop line south of Pearl River compressor station","Pigging-clean/gage--8-17-20 to 8-18-20\nCombo tool--8-19-20\nAFD tool--8-20-20","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,null,null,null,null,null,null,null,null,null,"X19-814613",0,0,0,0,0,0,0]
["X19-814557","***","2020-08-18","2020-08-19","Project Change","8/18/20","8/18/20","Elba Expr","3","250","Elba Express Line north of Rincon compressor station","Pigging\ncleaning pig-8-18-20\nMFL-8-19-20","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,null,null,null,null,null,null,null,null,null,"X19-814557",0,0,1,1,0,0,0]
["X19-820011",null,"2020-08-18","2020-08-19",null,null,null,"South","1","400","Gwinville Pickens loop line north of Gwinville","Pigging-3-17-20---clean/gage\n3-19-20--MFL\n3-24-20--Hardspot\n3-26-20--AFD","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,null,null,null,null,null,null,null,null,null,"X19-820011",0,0,0,0,0,0,0]
["X19-814558",null,"2020-08-20","2020-08-25",null,null,null,"Elba Expr","3","250","Elba Express Line south of Hartwell compressor station","Pigging:\nclean/gage-8-20-20\nMFL-8-25-20","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,null,null,null,null,null,null,null,null,null,"X19-814558",0,0,0,0,0,0,0]
["X17-761446",null,"2020-08-24","2020-09-03",null,null,null,"South","2","460","Auburn compressor station","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","OP",null,null,null,null,null,null,null,null,null,null,"X17-761446",0,0,0,0,0,0,0]
["X19-890772",null,"2020-08-30","2020-09-12",null,null,null,"North","2","130","Ragland Line east of Pell City compressor station off of the Gadsden Line","Make Piggable","This project will require taking the pipeline section out of service.  SNG will utilize a stopple bypass and do not anticipate an impact to customers.",null,null,null,null,null,null,null,null,null,null,null,"X19-890772",0,0,0,0,0,0,0]
["X19-951520",null,"2020-08-31","2020-09-25",null,null,null,"South","1","400","Rankin compressor station","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","OP",null,null,null,null,null,null,null,null,null,null,"X19-951520",0,0,0,0,0,0,0]
["X19-979791",null,"2020-08-31","2020-09-25",null,null,null,"North","1","400","Pickens compressor station","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","OP",null,null,null,null,null,null,null,null,null,null,"X19-979791",0,0,0,0,0,0,0]
["X20-129319",null,"2020-09-01","2020-10-31",null,null,null,null,null,"340","Shady Side and White Castle compressor stations","Unit Maintenance","This will require unit maintenance at White Castle and shady side compressor station, which could limit throughput through the station and result in restrictions based on customer nominations.","OP",null,null,null,null,null,null,null,null,null,null,"X20-129319",0,0,0,0,0,0,0]
["X19-890762","***","2020-09-14","2020-10-16","Added",null,null,"North","0","10","Bear Creek Storage Facilities","Make Piggable","This project will require taking part of the facility out of service.  ",null,null,null,null,null,null,null,null,null,null,null,"X19-890762",1,0,0,0,0,0,0]
["X19-951527",null,"2020-09-14","2020-10-08",null,null,null,"North","2","150","Dearmanville compressor station","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station. We do not anticipate an impact to customers as this time.",null,null,null,null,null,null,null,null,null,null,null,"X19-951527",0,0,0,0,0,0,0]
["X19-839324",null,"2020-09-15","2020-09-16",null,null,null,"North","2","120","North Main Loop Line west of Providence compressor station","Pigging\n9-15-20--clean/gage\n9-16-20--caliper/MDS","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,null,null,null,null,null,null,null,null,null,"X19-839324",0,0,0,0,0,0,0]
["X19-973173",null,"2020-09-15","2020-09-18",null,null,null,"North","2","120","North Main Loop Line east of Providence compressor station","Pigging\n9-15-20--clean/gage\n9-17-20--caliper\n9-18-20--MDS","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,null,null,null,null,null,null,null,null,null,"X19-973173",0,0,0,0,0,0,0]
["X20-392042",null,"2020-09-21","2020-09-22",null,null,null,null,null,"410","South Main Loop line east of Gwinville compressor station","Clean/gage--9-21-20\nMFL-9-22-20","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,null,null,null,null,null,null,null,null,null,"X20-392042",0,0,0,0,0,0,0]
["X19-951396",null,"2020-10-05","2020-11-05",null,null,null,"South","2","440","York compressor station","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","OP",null,null,null,null,null,null,null,null,null,null,"X19-951396",0,0,0,0,0,0,0]
["X19-979821",null,"2020-10-06","2020-10-07",null,null,null,"North","2","140","Pell City compressor station","Compressor Station Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","OP",null,null,null,null,null,null,null,null,null,null,"X19-979821",0,0,0,0,0,0,0]
["X19-1003768",null,"2020-10-06","2020-10-12",null,null,null,"North","1","45","Muldon Storage Facilities","Shut-in Test","This project will require taking the facility out of service.  This will limit throughput and may result in restrictions based on customer nominations.","DIQ/DWQ Allocated 36%",null,null,null,null,null,null,null,null,null,null,"X19-1003768",0,0,0,0,0,0,0]
["X19-951507",null,"2020-10-09","2020-10-13",null,null,null,"North","2","170","Bell Mills compressor station","Controls Upgrade","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","OP",null,null,null,null,null,null,null,null,null,null,"X19-951507",0,0,0,0,0,0,0]
["X20-683546",null,"2020-10-13","2020-10-15",null,null,null,"North","1","50","2NDNML east of Louisville compressor station","Pigging-\n9-28-20--clean/gage\n9-30-20--EMAT","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,null,null,null,null,null,null,null,null,null,"X20-683546",0,0,0,0,0,0,0]
["X19-1070490",null,"2020-10-13","2020-10-31",null,null,null,"North","1","90","North main loop line/North main line east of Lousiville","Make piggable","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","OP",null,null,null,null,null,null,null,null,null,null,"X19-1070490",0,0,0,0,0,0,0]
["X19-1003783",null,"2020-10-20","2020-10-26",null,null,null,"South","0","10","Bear Creek storage facilities","Shut-in Test","This project will require taking the facility out of service.  This will limit throughput and may result in restrictions based on customer nominations.","DIQ/DWQ Allocated 64%",null,null,null,null,null,null,null,null,null,null,"X19-1003783",0,0,0,0,0,0,0]

{"sheet":"Sheet2","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}

{"sheet":"Sheet3","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}