{"text_format":"1","workbook":"xlsx","n_sheets":4,"sheets":["Closed","Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":8,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Closed","index":0,"n_rows":37,"n_cols":22,"rows_kept":37,"cut":false,"hidden":true,"merged":[[1,3,1,15],[2,3,2,15],[3,3,3,15]]}
[null,null,null,"Updated ","2016"]
[null,null,null,"Tennessee Gas Pipeline 2015 Pipeline Outage and Maintenance Summary"]
[null,null,null,"This is a summary of the current status of all TGP Winter 2014-2015 Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  Additionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
[null,null,null,"*** Indicates revision"]
["Date Change","Project New/Completed/Closed","Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","Location","Leg","Zone","Maintenance Activity","Anticipated Impact","Potential Restriction Level","TOS Potential Restrictions","Meter(s) in Impacted Area","Customer Notifications","Loc","Email Text","Posting Text","Completion Text"]
[{"$f":"IF(AND(H6<>\"\",I6<>\"\"), \"Date change. Previously scheduled \" & TEXT(H6,\"m/d/y;@\") &IF(H6=I6,\"\",\" to \" & TEXT(I6,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed",null,{"$f":"IF(G6<>\"\",\"***\",\"\")","v":"***"},"2015-01-11","2016-01-11",{"$f":"IF(AND(A6=\"\",B6=\"\"),\"\",IF(B6=\"\",A6,B6))","v":"Project Completed"},null,null,"MS #412494 DCP Warren","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412494 DCP Warren",401,{"$f":"\"(\"&C6&\") \"&J6&\":  \"&M6&IF(AND(E6=\"\",F6=\"\"),\"\",\" (\")&IF(E6=\"\",\"\",\"\"&TEXT(E6,\"m/d/y;@\"))&IF(OR(F6=E6,E6=\"\",F6=\"\"),\"\",\" to \")&IF(OR(F6=\"\",F6=E6),\"\",TEXT(F6,\"m/d/y;@\"))&IF(AND(E6=\"\",F6=\"\"),\"\",\")\")","v":"() MS #412494 DCP Warren:  Meter Station (1/11/15 to 1/11/16)"},{"$f":"D6&J6&\":  \"&M6&IF(AND(E6=\"\",F6=\"\"),\"\",\"\n\")&IF(E6=\"\",\"\",\"--\"&TEXT(E6,\"m/d/y;@\"))&IF(OR(F6=E6,E6=\"\",F6=\"\"),\"\",\" through \")&IF(OR(F6=\"\",F6=E6),\"\",TEXT(F6,\"m/d/y;@\"))&IF(AND(E6=\"\",F6=\"\"),\"\",\":  \")&N6&\"  \"&P6&IF(Q6=\"\",\"\",\"\n\"&Q6)&IF(G6=\"\",\"\",\"\n***\")&G6&\"\n………………………………\"","v":"***MS #412494 DCP Warren:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412494 DCP Warren\n***Project Completed\n………………………………"},{"$f":"D6&J6&\":  \"&M6&IF(G6=\"\",\"\",\"\n***\")&G6&IF(Q6=\"\",\"\",\"\nThe following meters are available for nominations:\n\")&Q6&\"\n………………………………\"","v":"***MS #412494 DCP Warren:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412494 DCP Warren\n………………………………"}]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412400 King Ranch","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412400 King Ranch",402.1,"() MS #412400 King Ranch:  Meter Station (1/11/15 to 1/11/16)","***MS #412400 King Ranch:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412400 King Ranch\n***Project Completed\n………………………………","***MS #412400 King Ranch:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412400 King Ranch\n………………………………"]
["","Project Completed",null,"***","2015-01-12","2016-01-12","Project Completed",null,null,"MS #410539 Duvak Gas Gathering","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410539 Duvak Gas Gathering",402.1,"() MS #410539 Duvak Gas Gathering:  Meter Station (1/12/15 to 1/12/16)","***MS #410539 Duvak Gas Gathering:  Meter Station\n--1/12/15 through 1/12/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410539 Duvak Gas Gathering\n***Project Completed\n………………………………","***MS #410539 Duvak Gas Gathering:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n410539 Duvak Gas Gathering\n………………………………"]
["","Project Completed",null,"***","2015-01-13","2016-01-13","Project Completed",null,null,"MS #412356 DCP LaGloria","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412356 DCP LaGloria",403.1,"() MS #412356 DCP LaGloria:  Meter Station (1/13/15 to 1/13/16)","***MS #412356 DCP LaGloria:  Meter Station\n--1/13/15 through 1/13/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412356 DCP LaGloria\n***Project Completed\n………………………………","***MS #412356 DCP LaGloria:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412356 DCP LaGloria\n………………………………"]
["","Project Completed",null,"***","2015-01-13","2016-01-13","Project Completed",null,null,"MS #410173 Enterprise LaReforma","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410173 Enterprise LaReforma",406.1,"() MS #410173 Enterprise LaReforma:  Meter Station (1/13/15 to 1/13/16)","***MS #410173 Enterprise LaReforma:  Meter Station\n--1/13/15 through 1/13/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410173 Enterprise LaReforma\n***Project Completed\n………………………………","***MS #410173 Enterprise LaReforma:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n410173 Enterprise LaReforma\n………………………………"]
["","Project Completed",null,"***","2015-01-12","2016-01-12","Project Completed",null,null,"MS #411903 Enterprise El Benito","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","411903 Enterprise El Benito",407.1,"() MS #411903 Enterprise El Benito:  Meter Station (1/12/15 to 1/12/16)","***MS #411903 Enterprise El Benito:  Meter Station\n--1/12/15 through 1/12/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n411903 Enterprise El Benito\n***Project Completed\n………………………………","***MS #411903 Enterprise El Benito:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n411903 Enterprise El Benito\n………………………………"]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412088 Enterprise Sullivan","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412088 Enterprise Sullivan",407.1,"() MS #412088 Enterprise Sullivan:  Meter Station (1/11/15 to 1/11/16)","***MS #412088 Enterprise Sullivan:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412088 Enterprise Sullivan\n***Project Completed\n………………………………","***MS #412088 Enterprise Sullivan:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412088 Enterprise Sullivan\n………………………………"]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412683 HESCO","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412683 HESCO",408.1,"() MS #412683 HESCO:  Meter Station (1/11/15 to 1/11/16)","***MS #412683 HESCO:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412683 HESCO\n***Project Completed\n………………………………","***MS #412683 HESCO:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412683 HESCO\n………………………………"]
[{"$f":"IF(AND(H14<>\"\",I14<>\"\"), \"Date change. Previously scheduled \" & TEXT(H14,\"m/d/y;@\") &IF(H14=I14,\"\",\" to \" & TEXT(I14,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X16-36843",{"$f":"IF(G14<>\"\",\"***\",\"\")","v":"***"},"2016-01-27","2016-01-27","Project Completed",null,null,"Sta. 237",200,5,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,237,"(X16-36843) Sta. 237:  Unit  Maintenance (1/27/16)","***Sta. 237:  Unit  Maintenance\n--1/27/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Sta. 237:  Unit  Maintenance\n***Project Completed\n………………………………"]
[{"$f":"IF(AND(H15<>\"\",I15<>\"\"), \"Date change. Previously scheduled \" & TEXT(H15,\"m/d/y;@\") &IF(H15=I15,\"\",\" to \" & TEXT(I15,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X14-1478563",{"$f":"IF(G15<>\"\",\"***\",\"\")","v":"***"},"2015-11-16","2016-02-12","Project Completed",null,null,"MLV 32-1D to 33-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,32.200000000000003,"(X14-1478563) MLV 32-1D to 33-1:  Hydrotest (11/16/15 to 2/12/16)","***MLV 32-1D to 33-1:  Hydrotest\n--11/16/15 through 2/12/16:  This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***MLV 32-1D to 33-1:  Hydrotest\n***Project Completed\n………………………………"]
[null,"Project Completed","X16-16074",null,"2016-01-18","2016-01-28","Project Completed",null,null,"Station 550","500","1","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,550,"(X16-16074) Station 550:  Station Maintenance (1/18/16 to 1/28/16)","Station 550:  Station Maintenance\n--1/18/16 through 1/28/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","Station 550:  Station Maintenance\n***Project Completed\n………………………………"]
[{"$f":"IF(AND(H17<>\"\",I17<>\"\"), \"Date change. Previously scheduled \" & TEXT(H17,\"m/d/y;@\") &IF(H17=I17,\"\",\" to \" & TEXT(I17,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X16-46202",{"$f":"IF(G17<>\"\",\"***\",\"\")","v":"***"},"2016-02-01","2016-02-07","Project Completed",null,null,"Station 9","100","0","Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.",null,9,"(X16-46202) Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items) (2/1/16 to 2/7/16)","***Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)\n--2/1/16 through 2/7/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\n***Project Completed\n………………………………","***Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)\n***Project Completed\n………………………………"]
["","Project Completed","X15-925633","***","2016-02-09","2016-02-11","Project Completed",null,null,"Sta. 266A",200,6,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,266,"(X15-925633) Sta. 266A:  Unit  Maintenance (2/9/16 to 2/11/16)","***Sta. 266A:  Unit  Maintenance\n--2/9/16 through 2/11/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Sta. 266A:  Unit  Maintenance\n***Project Completed\n………………………………"]
["","Project Completed","X15-929733","***","2016-01-27","2016-02-10","Project Completed",null,null,"MLV 834-1 to 838-1",800,5,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",834.1,"(X15-929733) MLV 834-1 to 838-1:  ILI/Cleaning Pig (1/27/16 to 2/10/16)","***MLV 834-1 to 838-1:  ILI/Cleaning Pig\n--1/27/16 through 2/10/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 834-1 to 838-1:  ILI/Cleaning Pig\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X14-1562506","***","2015-11-02","2016-02-19","Project Completed",null,null,"MLV 5-1 to 6-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410063 ROCHE DEHYDRATION             \n",5.0999999999999996,"(X14-1562506) MLV 5-1 to 6-1:  Hydrotest (11/2/15 to 2/19/16)","***MLV 5-1 to 6-1:  Hydrotest\n--11/2/15 through 2/19/16:  This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410063 ROCHE DEHYDRATION             \n\n***Project Completed\n………………………………","***MLV 5-1 to 6-1:  Hydrotest\n***Project Completed\nThe following meters are available for nominations:\n410063 ROCHE DEHYDRATION             \n\n………………………………"]
["","Project Completed","X14-1562506","***","2015-11-02","2016-02-19","Project Completed",null,null,"MLV 7-1 to 9-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","\n412490 Charro\n421083 Eagle Ford Field Service",5.0999999999999996,"(X14-1562506) MLV 7-1 to 9-1:  Hydrotest (11/2/15 to 2/19/16)","***MLV 7-1 to 9-1:  Hydrotest\n--11/2/15 through 2/19/16:  This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n\n412490 Charro\n421083 Eagle Ford Field Service\n***Project Completed\n………………………………","***MLV 7-1 to 9-1:  Hydrotest\n***Project Completed\nThe following meters are available for nominations:\n\n412490 Charro\n421083 Eagle Ford Field Service\n………………………………"]
["Date change. Previously scheduled 2/18/16 to 2/20/16.","Project Completed","X15-882289","***","2016-02-22","2016-02-24","Project Completed","2016-02-18","2016-02-20","MLV 24-2 to 25-2S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.2,"(X15-882289) MLV 24-2 to 25-2S:  Anomaly Remediation (2/22/16 to 2/24/16)","***MLV 24-2 to 25-2S:  Anomaly Remediation\n--2/22/16 through 2/24/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 24-2 to 25-2S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-925630","***","2016-02-23","2016-02-23","Project Completed",null,null,"WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B)",200,"L","ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,265.10000000000002,"(X15-925630) WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig (2/23/16)","***WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig\n--2/23/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig\n***Project Completed\n………………………………"]
["","Project Completed","X16-23748","***","2016-02-15","2016-02-18","Project Completed",null,null,"MLV 530-3 to 532-3",500,"L","ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,530.29999999999995,"(X16-23748) MLV 530-3 to 532-3:  ILI/Cleaning Pig (2/15/16 to 2/18/16)","***MLV 530-3 to 532-3:  ILI/Cleaning Pig\n--2/15/16 through 2/18/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***MLV 530-3 to 532-3:  ILI/Cleaning Pig\n***Project Completed\n………………………………"]
["","Project Canceled","X16-98720","***","2016-03-06","2016-03-06","Project Canceled",null,null,"Sta. 1",100,0,"Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,1,"(X16-98720) Sta. 1:  Station Maintenance (3/6/16)","***Sta. 1:  Station Maintenance\n--3/6/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Canceled\n………………………………","***Sta. 1:  Station Maintenance\n***Project Canceled\n………………………………"]
["","Project Completed","X14-1562513\nX14-1540661","***","2015-07-01","2016-03-04","Project Completed",null,null,"Station 32","100","0","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,32,"(X14-1562513\nX14-1540661) Station 32:  Station Maintenance (7/1/15 to 3/4/16)","***Station 32:  Station Maintenance\n--7/1/15 through 3/4/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Station 32:  Station Maintenance\n***Project Completed\n………………………………"]
["","Project Canceled","X15-926822","***","2016-06-06","2016-06-11","Project Canceled",null,null,"BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1)",300,6,"Pipe Inspection","This project involves inspecting multiple sites.  We do not anticipate having to do any repairs, however if a repair is needed  there is a potential that the pipe  may require replacement which will require isolation of the pipe.  This may limit throughput and will result in restrictions based on customer nominations.  Customers may experience pressure fluctuations during this timeframe.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",343.1,"(X15-926822) BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection (6/6/16 to 6/11/16)","***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection\n--6/6/16 through 6/11/16:  This project involves inspecting multiple sites.  We do not anticipate having to do any repairs, however if a repair is needed  there is a potential that the pipe  may require replacement which will require isolation of the pipe.  This may limit throughput and will result in restrictions based on customer nominations.  Customers may experience pressure fluctuations during this timeframe.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928271","***","TBD","TBD","Project Canceled",null,null,"MLV 555-1 to 550-1",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.1,"(X15-928271) MLV 555-1 to 550-1:  ILI/Cleaning Pig (TBD)","***MLV 555-1 to 550-1:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-1 to 550-1:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928272","***","TBD","TBD","Project Canceled",null,null,"MLV 555-2 to 550-2",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.20000000000005,"(X15-928272) MLV 555-2 to 550-2:  ILI/Cleaning Pig (TBD)","***MLV 555-2 to 550-2:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-2 to 550-2:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928273","***","TBD","TBD","Project Canceled",null,null,"MLV 555-3 to 552-3",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.29999999999995,"(X15-928273) MLV 555-3 to 552-3:  ILI/Cleaning Pig (TBD)","***MLV 555-3 to 552-3:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-3 to 552-3:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-882281","***","2016-02-24","2016-03-03","Project Completed",null,null,"24-1A to 25-1S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.1,"(X15-882281) 24-1A to 25-1S:  Anomaly Remediation (2/24/16 to 3/3/16)","***24-1A to 25-1S:  Anomaly Remediation\n--2/24/16 through 3/3/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***24-1A to 25-1S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-882291","***","2016-03-03","2016-03-04","Project Completed",null,null,"MLV 24-3 to 25-3S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.3,"(X15-882291) MLV 24-3 to 25-3S:  Anomaly Remediation (3/3/16 to 3/4/16)","***MLV 24-3 to 25-3S:  Anomaly Remediation\n--3/3/16 through 3/4/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 24-3 to 25-3S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X14-1178175","***","2015-06-15","2016-03-31","Project Completed",null,null,"Station 63","100","1","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,63,"(X14-1178175) Station 63:  Station Maintenance (6/15/15 to 3/31/16)","***Station 63:  Station Maintenance\n--6/15/15 through 3/31/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Station 63:  Station Maintenance\n***Project Completed\n………………………………"]
["","Project Cancelled","X15-913224","***","2016-04-16","2016-05-21","Project Cancelled",null,null,"MLV 109-2",100,2,"Pipe Replacement","This project will require taking the pipeline section out of service.   This will limit throughput and will result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",109.2,"(X15-913224) MLV 109-2:  Pipe Replacement (4/16/16 to 5/21/16)","***MLV 109-2:  Pipe Replacement\n--4/16/16 through 5/21/16:  This project will require taking the pipeline section out of service.   This will limit throughput and will result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Cancelled\n………………………………","***MLV 109-2:  Pipe Replacement\n***Project Cancelled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-926830","***","2016-03-07","2016-03-11","Project Completed",null,null,"MLV 400-1 to 408-1",100,0,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.","To Be Determined",400.1,"(X15-926830) MLV 400-1 to 408-1:  ILI/Cleaning Pig (3/7/16 to 3/11/16)","***MLV 400-1 to 408-1:  ILI/Cleaning Pig\n--3/7/16 through 3/11/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 400-1 to 408-1:  ILI/Cleaning Pig\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Cancelled","X16-143836","***","2016-03-28","2016-04-04","Project Cancelled",null,null,"Sta. 409",100,0,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.",null,409,"(X16-143836) Sta. 409:  Unit  Maintenance (3/28/16 to 4/4/16)","***Sta. 409:  Unit  Maintenance\n--3/28/16 through 4/4/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\n***Project Cancelled\n………………………………","***Sta. 409:  Unit  Maintenance\n***Project Cancelled\n………………………………"]
["","Project Cancelled","X15-929680","***","2016-04-18","2016-04-27","Project Cancelled",null,null,"SABINE - KINDER LINE to 822-1",800,"L","Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",822.1,"(X15-929680) SABINE - KINDER LINE to 822-1:  Anomaly Remediation (4/18/16 to 4/27/16)","***SABINE - KINDER LINE to 822-1:  Anomaly Remediation\n--4/18/16 through 4/27/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Cancelled\n………………………………","***SABINE - KINDER LINE to 822-1:  Anomaly Remediation\n***Project Cancelled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]

{"sheet":"Sheet1","index":1,"n_rows":75,"n_cols":33,"rows_kept":75,"cut":false,"hidden":false,"merged":[[2,0,2,14]]}
["Updated ","2021-05-06"]
["Southern Natural Gas Pipeline 2021 Pipeline Outage and Maintenance Summary"]
["This is a summary of the current status of all SNG 2021 Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  \nAdditionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Southern Natural Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
["*** Indicates revision"]
["Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","System","Zone","Segment","Location","Maintenance Activity","Anticipated Impact","Potential Restriction Level","Meter(s) in Impacted Area",null,null,null,null,null,null,null,null,null,"\\\\houCORP\\TRANS\\TRANSERVICES\\OPPLAN\\COMMON\\Outages\\Outage_DB\\SNG"]
["X21-29259",null,"2021-01-04","2021-09-30",null,null,null,"South LA","1","360","Franklinton Compressor Station","Unit maintenance","This project will require a unit outage, no customer impact anticipated at this time.",null,null,null,null,null,null,null,null,null,null,null,"X21-29259",0,0,0,0,0,0,0,0]
["X20-1026372","***","2021-04-07","2021-05-08","Completed",null,null,"North","2","140","North Main line east of Pell City compressor station-P13741","Pipeline maintenance","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.   An impact to Interruptible and Out of Path nominations may become necessary.","OP",null,null,null,null,null,null,null,null,null,null,"X20-1026372",1,0,0,0,0,0,0,0]
["X20-940035","***","2021-04-18","2021-05-08","Project Change","4/18/21","5/31/21","North","2","120","2ndNML east of Providence compressor station","Pipeline maintenance","This project will require reduced pressure on the 2ndNML,  based on system demand, an impact to Interruptible and Out of Path nominations may become necessary.","OP",null,null,null,null,null,null,null,null,null,null,"X20-940035",0,0,1,0,0,0,0,0]
["X21-81058",null,"2021-04-19","2021-05-14",null,null,null,"North","1","400","Pickens compressor station","Unit maintenance","This project will require a unit outage, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path nominations may become necessary.","OP",null,null,null,null,null,null,null,null,null,null,"X21-81058",0,0,0,0,0,0,0,0]
["X21-239501","***","2021-04-26","2021-04-27","Completed",null,null,"South","2","460","Auburn compressor station","Unit maintenance","This project will require a unit outage, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path nominations may become necessary.","OP",null,null,null,null,null,null,null,null,null,null,"X21-239501",1,0,0,0,0,0,0,0]
["X21-110269","***","2021-04-27","2021-04-30","Completed",null,null,"South","1","390","Gwinville compressor station","Station maintenance","This project will require a Station outage, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path nominations may become necessary.","OP",null,null,null,null,null,null,null,null,null,null,"X21-110269",1,0,0,0,0,0,0,0]
["X19-951387","***","2021-04-27","2021-04-30","Completed",null,null,"South","1","400","Gwinville compressor station","Station maintenance","This project will require a Station outage, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path nominations may become necessary.","OP",null,null,null,null,null,null,null,null,null,null,"X19-951387",1,0,0,0,0,0,0,0]
["X21-406178","***","2021-04-27","2021-05-28","Added",null,null,null,null,"490","Thomaston compressor station","unit maintenance","'This project will require a unit outage, which could limit throughput through the station, however we do not anticipate an impact to customers at this time.",null,null,null,null,null,null,null,null,null,null,null,"X21-406178",1,0,0,0,0,0,0,0]
["X20-1012270","***","2021-04-30","2021-05-03","Completed",null,null,"North","2","120","North Main Loop Line West of Tarrant Compressor Station-P12300","Pigging\nClean/gauge--4-30-21\nMFL--4-30-21\nHard Spot--5-3-21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,null,null,null,null,null,null,null,null,null,"X20-1012270",1,0,0,0,0,0,0,0]
["X20-1105767",null,"2021-04-30","2021-05-06",null,null,null,"South","3","490","South Main 2nd Loop line east of Ellerslie compressor station","Pipeline maintenance","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.  An impact to Interruptible and Out of Path nominations may become necessary.","OP",null,null,null,null,null,null,null,null,null,null,"X20-1105767",0,0,0,0,0,0,0,0]
["X21-365817","***","2021-05-03","2021-05-04","Completed",null,null,null,null,"580","Wrens Savannah 2nd Loop Line South of Wrens Compressor Station","Pigging\nEMAT--5-4-21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,null,null,null,null,null,null,null,null,null,"X21-365817",1,0,0,0,0,0,0,0]
["X20-942913",null,"2021-05-04","2021-05-10",null,null,null,"North","0","10","Bear Creek Storage Facilities","Shut-in Test","This project will require taking the facility out of service.  This will limit throughput and may result in restrictions based on customer nominations.\nOutage to start 5-4-21 to 9 AM on 5-11-21.","DIQ/DWQ Allocated 64%",null,null,null,null,null,null,null,null,null,null,"X20-942913",0,0,0,0,0,0,0,0]
["X20-228645",null,"2021-05-04","2021-05-13",null,null,null,"North","2","150","Chattanooga Branch Line North of Bell Mills Compressor Station-P9057","Pigging\nBrush/gauge--5-4-21\nMFL--5-6-21\nAFD-5-13-21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,null,null,null,null,null,null,null,null,null,"X20-228645",0,0,0,0,0,0,0,0]
["X21-144420",null,"2021-05-07","2021-05-14",null,null,null,"South","3","490","Ellerslie compressor station","Station maintenance","This project will require a station outage, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path nominations may become necessary.","OP",null,null,null,null,null,null,null,null,null,null,"X21-144420",0,0,0,0,0,0,0,0]
["X20-1012279","***","2021-05-10","2021-05-13","Project Change",null,null,"North","2","130","North Main Loop Line East of Tarrant Compressor Station-P4905","Pigging\n5-10-21----Brush and MFL pig\n\n5-13-21----Hard spot","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,null,null,null,null,null,null,null,null,null,"X20-1012279",0,0,0,1,0,0,0,0]
["X21-239505",null,"2021-05-10","2021-05-11",null,null,null,"South","2","460","Selma compressor station","Unit maintenance","This project will require a unit outage, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path nominations may become necessary.","OP",null,null,null,null,null,null,null,null,null,null,"X21-239505",0,0,0,0,0,0,0,0]
["X21-442008","***","2021-05-11","2021-05-16","Added",null,null,null,1,"400","2ndNML east of Louisville","Pipeline maintenance","This project will require a pressure restriction resulting in limiting throughput and will result in restrictions based on customer nominations.","OP",null,null,null,null,null,null,null,null,null,null,"X21-442008",1,0,0,0,0,0,0,0]
["X21-292769","***","2021-05-11","2021-05-16","Added","5/12/21","5/16/21","North","1","50","2ndNML east of Louisville","Pipeline maintenance","This project will require a pressure restriction resulting in limiting throughput and will result in restrictions based on customer nominations.","IP",null,null,null,null,null,null,null,null,null,null,"X21-292769",0,1,0,0,1,1,0,1]
["X20-940180",null,"2021-05-11","2021-05-13",null,null,null,"South","3","710","Main Line 02 South of Pavo compressor station","Pigging\ngauge--5-11-21\nSmart-5-13-21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,null,null,null,null,null,null,null,null,null,"X20-940180",0,0,0,0,0,0,0,0]
["X21-239509",null,"2021-05-12","2021-05-13",null,null,null,"South","2","440","Gallion Station","Unit maintenance","This project will require a unit outage, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path nominations may become necessary.","OP",null,null,null,null,null,null,null,null,null,null,"X21-239509",0,0,0,0,0,0,0,0]
["X21-387952","***","2021-05-17","2021-05-19",null,null,null,"South","1","380","Sesh Delhi compressor station","Maintenance","This maintenance, Will limit capacity to 451,000 Dth/d and based on system demand, an impact to In Path nominations may become necessary.","IP",null,null,null,null,null,null,null,null,null,null,"X21-387952",0,0,0,0,0,0,0,0]
["X21-81061",null,"2021-05-17","2021-06-04",null,null,null,"South","1","400","Rankin compressor station","Unit maintenance","This project will require a unit outage, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path nominations may become necessary.","OP",null,null,null,null,null,null,null,null,null,null,"X21-81061",0,0,0,0,0,0,0,0]
["X20-1012274","***","2021-05-19","2021-05-25","Project Change","6/14/21","6/23/21","North","2","120","NMLL east and west of Providence compressor station","Pipeline maintenance","This project may require a pressure reduction on the NMLL.  We do not anticipate an impact to customers at this time.",null,null,null,null,null,null,null,null,null,null,null,"X20-1012274",0,1,1,0,0,0,0,0]
["X20-973448",null,"2021-05-19","2021-05-31",null,null,null,"South LA","0","330","South of Franklinton compressor station","Pipeline maintenance","This project will require taking the pipeline out of service, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path nominations may become necessary.","OP",null,null,null,null,null,null,null,null,null,null,"X20-973448",0,0,0,0,0,0,0,0]
["X20-1012278",null,"2021-05-25","2021-06-02",null,null,null,"North","0","20","North Main Loop Line East of Bienville Compressor Station-P4903","Pigging\ncleaning pigs--5-25-21 to 5-28-21\nAFD tool--6-1-21\nEMAT--6-2-21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,null,null,null,null,null,null,null,null,null,"X20-1012278",0,0,0,0,0,0,0,0]
["X21-387954","***","2021-05-25","2021-05-26","Project Change",null,null,"South","1","380","Sesh Gwinville compressor station","Maintenance","This maintenance, Will limit capacity to 452,000 Dth/d and based on system demand, an impact to In Path nominations may become necessary.","IP",null,null,null,null,null,null,null,null,null,null,"X21-387954",0,0,0,0,0,0,0,0]
["X21-400572",null,"2021-05-25","2021-05-27",null,null,null,"South","2","460","SML west of Auburn compressor station","Pig runs","\"This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.",null,null,null,null,null,null,null,null,null,null,null,"X21-400572",0,0,0,0,0,0,0,0]
["X20-1012271","***","2021-05-26","2021-06-04","Project Change","6/14/21","6/23/21","North","2","120","NMLL west of Tarrant compressor station","Pipeline maintenance","This project may require a pressure reduction on the NMLL.  We do not anticipate an impact to customers at this time.",null,null,null,null,null,null,null,null,null,null,null,"X20-1012271",0,1,1,0,0,0,0,0]
["X20-1012275","***","2021-05-26","2021-09-30","Project Change","6/28/21","9/30/21","North","2","120","NMLL west of Tarrant compressor station","Pipeline maintenance","This project may require a pressure reduction on the NMLL.  We do not anticipate an impact to customers at this time.",null,null,null,null,null,null,null,null,null,null,null,"X20-1012275",0,1,0,0,0,0,0,0]
["X21-387956","***","2021-05-27","2021-05-27","Project Change",null,null,"South","1","380","Sesh Lucedale compressor station","Maintenance","This maintenance, Will limit capacity to 500,000 Dth/d and based on system demand, an impact to Interruptible and Out of Path nominations may become necessary.","OP",null,null,null,null,null,null,null,null,null,null,"X21-387956",0,0,0,0,0,0,0,0]
["X21-416331","***","2021-05-31","2021-06-24","Added",null,null,null,null,"490","Thomaston compressor station","unit maintenance","This project will require a unit outage, which could limit throughput through the station, however we do not anticipate an impact to customers at this time.",null,null,null,null,null,null,null,null,null,null,null,"X21-416331",1,0,0,0,0,0,0,0]
["X20-981572",null,"2021-06-01","2021-06-09",null,null,null,"North","2","120","North Mail line west of Tarrant compressor station-P13754","Pipeline Maintenance","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.   An impact to Interruptible and Out of Path nominations may become necessary.","OP","Oak Grove #7---646020--will be shut in",null,null,null,null,null,null,null,null,null,"X20-981572",0,0,0,0,0,0,0,0]
["X20-1105780",null,"2021-06-02","2021-07-10",null,null,null,"North","0","10","Bienville compressor station","Station maintenance","This project will require a unit outage, which could limit throughput through the station and based on system demand, no impact is currently anticipated.",null,null,null,null,null,null,null,null,null,null,null,"X20-1105780",0,0,0,0,0,0,0,0]
["X20-940151",null,"2021-06-08","2021-06-08",null,null,null,"South","1","400","Gwinville Pickens Loop Line South of Pickens Compressor Station-P4854","Pigging\nbrush/gauge--6-8-21\nMFL--6-8-21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,null,null,null,null,null,null,null,null,null,"X20-940151",0,0,0,0,0,0,0,0]
["X20-1012329",null,"2021-06-08","2021-06-15",null,null,null,"South","3","490","South Main 2nd Loop line East of Ellerslie compressor station-P4928","Pigging\nBrush--6-8-21\ngauge--6-9-21\ncaliper--6-10-21\nSmart--6-15-21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,null,null,null,null,null,null,null,null,null,"X20-1012329",0,0,0,0,0,0,0,0]
["X20-1012286",null,"2021-06-15","2021-07-01",null,null,null,"North","1","40","North Main Loop Line West of Pickens Compressor Station-P9951","Pigging\nbrush/gauge--6-15-21\nAFD--6-17-21\nMFL--6-22-21\nHardspot--6-24-21\nTDW go/nogo--6-29-21\nTDW low res.--7-1","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,null,null,null,null,null,null,null,null,null,"X20-1012286",0,0,0,0,0,0,0,0]
["X20-1012344",null,"2021-06-21","2021-07-09",null,null,null,"South","2","460","South Main line west of Auburn compressor station","Hydro-test","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.   An impact to Interruptible and Out of Path nominations may become necessary.","OP",null,null,null,null,null,null,null,null,null,null,"X20-1012344",0,0,0,0,0,0,0,0]
["X20-973512",null,"2021-06-22","2021-06-24",null,null,null,"North","2","140","North Main Line East of Pell City Compressor Station-P6316","Pigging\nBrush/Gauge--6-22-21\nCaliper--6-23-21\nAFD--6-24-21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,null,null,null,null,null,null,null,null,null,"X20-973512",0,0,0,0,0,0,0,0]
["X20-1012332",null,"2021-06-22","2021-06-24",null,null,null,"South","3","490","South Main 3rd Loop line east of Ellerslie compressor station-P5662","Pigging\nbrush--6-22-21\nGauge--6-23-21\nSmart--6-24-21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,null,null,null,null,null,null,null,null,null,"X20-1012332",0,0,0,0,0,0,0,0]
["X20-1012367",null,"2021-06-29","2021-06-30",null,null,null,"South","3","500","Thomaston Griffin 3rd Loop line north of Thomaston compressor station-P5724","Pigging\nbrush/gauge--3-30-21\nMFL--3-31-21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,null,null,null,null,null,null,null,null,null,"X20-1012367",0,0,0,0,0,0,0,0]
["X20-1012334",null,"2021-06-29","2021-07-01",null,null,null,"South","3","530","South Main 3RD Loop Line East of Ocmulgee Compressor Station-P6130","Pigging\nbrush--6-29-21\ngauge--6-30-21\nsmart--7-1-21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,null,null,null,null,null,null,null,null,null,"X20-1012334",0,0,0,0,0,0,0,0]
["X20-1101387",null,"2021-07-12","2021-07-26",null,null,null,"South","3","760","Tifton Line 26 East of Albany compressor station","Hydro-test","This project will require taking the pipeline section out of service.  We will be coordinating with the customer to swap supply from Tifton #1 to Tifton #2..",null,"Tifton #1-Pin-000370",null,null,null,null,null,null,null,null,null,"X20-1101387",0,0,0,0,0,0,0,0]
["X20-940261",null,"2021-07-13","2021-07-14",null,null,null,"South","2","440","Montgomery Columbus Line West of Selma Compressor Station-P4982","Pigging\nbrush/gauge--7-13-21\nMFL--7-14-21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,null,null,null,null,null,null,null,null,null,"X20-940261",0,0,0,0,0,0,0,0]
["X20-1012335",null,"2021-07-13","2021-07-15",null,null,null,"South","2","460","South Main 3RD Loop Line East of Gallion Compressor Station-P6134","Pigging\nbrush--7-13-21\ngauge--7-14-21\nsmart--7-15-21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,null,null,null,null,null,null,null,null,null,"X20-1012335",0,0,0,0,0,0,0,0]
["X20-1012339",null,"2021-07-20","2021-07-22",null,null,null,"South","2","460","South Main Line East of Auburn Compressor Station-P4637","Pigging\nbrush--7-20-21\ngauge--7-21-21\nsmart--7-22-21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,null,null,null,null,null,null,null,null,null,"X20-1012339",0,0,0,0,0,0,0,0]
["X20-1012289",null,"2021-07-20","2021-07-22",null,null,null,"North","1","50","North Main Loop Line East of Louisville Compressor Station-P5158","Pigging\nBrush/gauge--7-20-21\nMFL--7-21-21\nHard spot--7-21-21\nAFD--7-22-21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,null,null,null,null,null,null,null,null,null,"X20-1012289",0,0,0,0,0,0,0,0]
["X20-1012294",null,"2021-07-26","2021-07-28",null,null,null,"North","1","50","North Main Loop Line East of Louisville Compressor Station-P9066","Pigging\nBrush/gauge--7-26-21\nMFL--7-27-21\nHard Spot--7-27-21\nAFD--7-28-21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,null,null,null,null,null,null,null,null,null,"X20-1012294",0,0,0,0,0,0,0,0]
["X20-228680",null,"2021-07-26","2021-08-06",null,null,null,"South","3","680","Moultrie line 10 South of Albany compressor station","Hydro-test","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.  Will be done during low flow period.","OP","Moultrie #1 meter station",null,null,null,null,null,null,null,null,null,"X20-228680",0,0,0,0,0,0,0,0]
["X20-1012340",null,"2021-07-27","2021-07-28",null,null,null,"South","2","460","South Main Line East of Auburn Compressor Station-P9054","Pigging\ngauge--7-27-21\nsmart--7-28-21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,null,null,null,null,null,null,null,null,null,"X20-1012340",0,0,0,0,0,0,0,0]
["X20-981563","***","2021-08-02","2021-08-04","Project Change","6/24/21","6/29/21","North","1","40","North Main Line East of Onward Compressor Station","Pigging\ncleaning pig--8-2-21\ncleaning/gauge pig-8-3-21\nILI pig-8-4-21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,null,null,null,null,null,null,null,null,null,"X20-981563",0,1,1,1,0,0,0,0]
["X20-1012330",null,"2021-08-03","2021-08-05",null,null,null,"South","2","460","South Main 2ND Loop Line East of Elmore Compressor Station-P6314","Pigging\nbrush--8-3-21\ngauge--8-4-21\nsmart--8-5-21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,null,null,null,null,null,null,null,null,null,"X20-1012330",0,0,0,0,0,0,0,0]
["X20-1012342",null,"2021-08-10","2021-08-12",null,null,null,"South","1","410","South Main Line East of Gwinville Compressor Station-P4776","Pigging\nbrush--8-10-21\nGauge--8-11-21\ncombo tool--8-12-21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,null,null,null,null,null,null,null,null,null,"X20-1012342",0,0,0,0,0,0,0,0]
["X20-1012288",null,"2021-08-16","2021-08-17",null,null,null,"North","2","130","North Main Loop Line East of Tarrant Compressor Station-P9051","Pigging\nBrush/gauge--8-16-21\nMFL--8-17-21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,null,null,null,null,null,null,null,null,null,"X20-1012288",0,0,0,0,0,0,0,0]
["X20-1012281",null,"2021-08-18","2021-08-20",null,null,null,"North","2","140","North Main Loop Line West of Dearmanville Compressor Station-P5078","Pigging\nBrush/gauge--8-18-21\nMFL--8-20-21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,null,null,null,null,null,null,null,null,null,"X20-1012281",0,0,0,0,0,0,0,0]
["X21-339868",null,"2021-08-23","2021-09-03",null,null,null,"North","3","190","Dalton meter station #2","Piping maintenance","\"This project will require taking the meter station out of service.  The meter listed below is expected to be shut-in 7-12-21 to 7-17-21\nPin-600175.  This will coordinated with the customer.",null,"Dalton #2 (PIN-600175)",null,null,null,null,null,null,null,null,null,"X21-339868",0,0,0,0,0,0,0,0]
["X20-1012384",null,"2021-08-23","2021-09-17",null,null,null,"South","2","460","Riverview Mills line west of Auburn","Pressure test","This project will require taking the pipeline sections out of service, however no impact is anticipated as CNG will be supplied.",null,"813400, 813500, 814200, 815200, 815500, 900800, 901100 and 814500",null,null,null,null,null,null,null,null,null,"X20-1012384",0,0,0,0,0,0,0,0]
["X20-940084",null,"2021-08-23","2021-08-28",null,null,null,"South","2","460","Auburn Grantville line west of Auburn","Pipeline maintenance","This activity will include pipe inspections and repairs, as needed, in specified areas. Customer may experience lower than normal pressures during this maintenance.",null,null,null,null,null,null,null,null,null,null,null,"X20-940084",0,0,0,0,0,0,0,0]
["X20-1108211",null,"2021-08-30","2021-09-30",null,null,null,"South","2","460","Elmore compressor station","Unit maintenance","This project will require a unit outage, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path nominations may become necessary.","OP",null,null,null,null,null,null,null,null,null,null,"X20-1108211",0,0,0,0,0,0,0,0]
["X21-113735",null,"2021-09-01","2021-10-31",null,null,null,"South","0","340","White Castle and Shady Side compressor stations","Unit Maintenance","These projects will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","OP",null,null,null,null,null,null,null,null,null,null,"X21-113735",0,0,0,0,0,0,0,0]
["X20-1105776",null,"2021-09-06","2021-10-29",null,null,null,"North","1","400","Pickens compressor station","Station maintenance","This project will require a unit outage, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path nominations may become necessary.","OP",null,null,null,null,null,null,null,null,null,null,"X20-1105776",0,0,0,0,0,0,0,0]
["X20-981567",null,"2021-09-14","2021-09-15",null,null,null,"North","1","70","North Main Line West of Reform Compressor Station-P9065","Pigging\nBrush/gauge--9-14-21\nMFL--9-15-21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,null,null,null,null,null,null,null,null,null,"X20-981567",0,0,0,0,0,0,0,0]
["X20-1012311",null,"2021-09-21","2021-09-22",null,null,null,"South","3","510","Plant McDonough line North of Thomaston Compressor station-P13257","Pigging\nBrush/gauge--9-21-21\nMFL--9-22-21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,null,null,null,null,null,null,null,null,null,"X20-1012311",0,0,0,0,0,0,0,0]
["X21-384580",null,"2021-10-01","2021-11-01",null,null,null,"South","2","440","York compressor station","Unit maintenance","This project will require a unit outage, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path nominations may become necessary.","OP",null,null,null,null,null,null,null,null,null,null,"X21-384580",0,0,0,0,0,0,0,0]
["X20-1108213",null,"2021-10-01","2021-10-31",null,null,null,"South","2","460","Auburn compressor station","Unit maintenance","This project will require a unit outage, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path nominations may become necessary.","OP",null,null,null,null,null,null,null,null,null,null,"X20-1108213",0,0,0,0,0,0,0,0]
["X20-940231",null,"2021-10-04","2021-10-20",null,null,null,"South","3","710","Main line 02 south of Pavo compressor station","Hydro-test","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","OP",null,null,null,null,null,null,null,null,null,null,"X20-940231",0,0,0,0,0,0,0,0]
["X20-942912",null,"2021-10-05","2021-10-11",null,null,null,"North","1","45","Muldon storage facilities","Shut-in Test","This project will require taking the facility out of service.  This will limit throughput and may result in restrictions based on customer nominations.","DIQ/DWQ Allocated 36%",null,null,null,null,null,null,null,null,null,null,"X20-942912",0,0,0,0,0,0,0,0]
["X21-258832",null,"2021-10-05","2021-10-07",null,null,null,"North","3","510","Fairburn compressor station","Station outage for maintenance work","This project will require taking a compressor building out of service.  IT and Out of Path services will not be scheduled at TRNSCO/SNG FAIRBURN TO SNG FAYETTE - PIN 50069","PIP",null,null,null,null,null,null,null,null,null,null,"X21-258832",0,0,0,0,0,0,0,0]
["X20-1105793",null,"2021-10-11","2021-10-18",null,null,null,"South","1","430","Enterprise compressor station","Unit  maintenance","This project will require a unit outage, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path nominations may become necessary.","OP",null,null,null,null,null,null,null,null,null,null,"X20-1105793",0,0,0,0,0,0,0,0]
["X20-942914",null,"2021-10-19","2021-10-25",null,null,null,"North","0","10","Bear Creek Storage Facilities","Shut-in test","This project will require taking the facility out of service.  This will limit throughput and may result in restrictions based on customer nominations.","DIQ/DWQ Allocated 64%",null,null,null,null,null,null,null,null,null,null,"X20-942914",0,0,0,0,0,0,0,0]
["X20-973456","***","2021-10-31","2021-10-31","Project Change","5/17/21","5/20/21","South","1","400","Rankin compressor station","Station maintenance","This project will require a station outage, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path nominations may become necessary.","OP",null,null,null,null,null,null,null,null,null,null,"X20-973456",0,1,1,0,0,0,0,0]

{"sheet":"Sheet2","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}

{"sheet":"Sheet3","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}