{"text_format":"1","workbook":"xlsx","n_sheets":4,"sheets":["Closed","Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":8,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Closed","index":0,"n_rows":37,"n_cols":22,"rows_kept":37,"cut":false,"hidden":true,"merged":[[1,3,1,15],[2,3,2,15],[3,3,3,15]]}
[null,null,null,"Updated ","2016"]
[null,null,null,"Tennessee Gas Pipeline 2015 Pipeline Outage and Maintenance Summary"]
[null,null,null,"This is a summary of the current status of all TGP Winter 2014-2015 Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  Additionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
[null,null,null,"*** Indicates revision"]
["Date Change","Project New/Completed/Closed","Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","Location","Leg","Zone","Maintenance Activity","Anticipated Impact","Potential Restriction Level","TOS Potential Restrictions","Meter(s) in Impacted Area","Customer Notifications","Loc","Email Text","Posting Text","Completion Text"]
[{"$f":"IF(AND(H6<>\"\",I6<>\"\"), \"Date change. Previously scheduled \" & TEXT(H6,\"m/d/y;@\") &IF(H6=I6,\"\",\" to \" & TEXT(I6,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed",null,{"$f":"IF(G6<>\"\",\"***\",\"\")","v":"***"},"2015-01-11","2016-01-11",{"$f":"IF(AND(A6=\"\",B6=\"\"),\"\",IF(B6=\"\",A6,B6))","v":"Project Completed"},null,null,"MS #412494 DCP Warren","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412494 DCP Warren",401,{"$f":"\"(\"&C6&\") \"&J6&\":  \"&M6&IF(AND(E6=\"\",F6=\"\"),\"\",\" (\")&IF(E6=\"\",\"\",\"\"&TEXT(E6,\"m/d/y;@\"))&IF(OR(F6=E6,E6=\"\",F6=\"\"),\"\",\" to \")&IF(OR(F6=\"\",F6=E6),\"\",TEXT(F6,\"m/d/y;@\"))&IF(AND(E6=\"\",F6=\"\"),\"\",\")\")","v":"() MS #412494 DCP Warren:  Meter Station (1/11/15 to 1/11/16)"},{"$f":"D6&J6&\":  \"&M6&IF(AND(E6=\"\",F6=\"\"),\"\",\"\n\")&IF(E6=\"\",\"\",\"--\"&TEXT(E6,\"m/d/y;@\"))&IF(OR(F6=E6,E6=\"\",F6=\"\"),\"\",\" through \")&IF(OR(F6=\"\",F6=E6),\"\",TEXT(F6,\"m/d/y;@\"))&IF(AND(E6=\"\",F6=\"\"),\"\",\":  \")&N6&\"  \"&P6&IF(Q6=\"\",\"\",\"\n\"&Q6)&IF(G6=\"\",\"\",\"\n***\")&G6&\"\n………………………………\"","v":"***MS #412494 DCP Warren:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412494 DCP Warren\n***Project Completed\n………………………………"},{"$f":"D6&J6&\":  \"&M6&IF(G6=\"\",\"\",\"\n***\")&G6&IF(Q6=\"\",\"\",\"\nThe following meters are available for nominations:\n\")&Q6&\"\n………………………………\"","v":"***MS #412494 DCP Warren:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412494 DCP Warren\n………………………………"}]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412400 King Ranch","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412400 King Ranch",402.1,"() MS #412400 King Ranch:  Meter Station (1/11/15 to 1/11/16)","***MS #412400 King Ranch:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412400 King Ranch\n***Project Completed\n………………………………","***MS #412400 King Ranch:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412400 King Ranch\n………………………………"]
["","Project Completed",null,"***","2015-01-12","2016-01-12","Project Completed",null,null,"MS #410539 Duvak Gas Gathering","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410539 Duvak Gas Gathering",402.1,"() MS #410539 Duvak Gas Gathering:  Meter Station (1/12/15 to 1/12/16)","***MS #410539 Duvak Gas Gathering:  Meter Station\n--1/12/15 through 1/12/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410539 Duvak Gas Gathering\n***Project Completed\n………………………………","***MS #410539 Duvak Gas Gathering:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n410539 Duvak Gas Gathering\n………………………………"]
["","Project Completed",null,"***","2015-01-13","2016-01-13","Project Completed",null,null,"MS #412356 DCP LaGloria","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412356 DCP LaGloria",403.1,"() MS #412356 DCP LaGloria:  Meter Station (1/13/15 to 1/13/16)","***MS #412356 DCP LaGloria:  Meter Station\n--1/13/15 through 1/13/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412356 DCP LaGloria\n***Project Completed\n………………………………","***MS #412356 DCP LaGloria:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412356 DCP LaGloria\n………………………………"]
["","Project Completed",null,"***","2015-01-13","2016-01-13","Project Completed",null,null,"MS #410173 Enterprise LaReforma","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410173 Enterprise LaReforma",406.1,"() MS #410173 Enterprise LaReforma:  Meter Station (1/13/15 to 1/13/16)","***MS #410173 Enterprise LaReforma:  Meter Station\n--1/13/15 through 1/13/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410173 Enterprise LaReforma\n***Project Completed\n………………………………","***MS #410173 Enterprise LaReforma:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n410173 Enterprise LaReforma\n………………………………"]
["","Project Completed",null,"***","2015-01-12","2016-01-12","Project Completed",null,null,"MS #411903 Enterprise El Benito","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","411903 Enterprise El Benito",407.1,"() MS #411903 Enterprise El Benito:  Meter Station (1/12/15 to 1/12/16)","***MS #411903 Enterprise El Benito:  Meter Station\n--1/12/15 through 1/12/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n411903 Enterprise El Benito\n***Project Completed\n………………………………","***MS #411903 Enterprise El Benito:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n411903 Enterprise El Benito\n………………………………"]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412088 Enterprise Sullivan","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412088 Enterprise Sullivan",407.1,"() MS #412088 Enterprise Sullivan:  Meter Station (1/11/15 to 1/11/16)","***MS #412088 Enterprise Sullivan:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412088 Enterprise Sullivan\n***Project Completed\n………………………………","***MS #412088 Enterprise Sullivan:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412088 Enterprise Sullivan\n………………………………"]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412683 HESCO","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412683 HESCO",408.1,"() MS #412683 HESCO:  Meter Station (1/11/15 to 1/11/16)","***MS #412683 HESCO:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412683 HESCO\n***Project Completed\n………………………………","***MS #412683 HESCO:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412683 HESCO\n………………………………"]
[{"$f":"IF(AND(H14<>\"\",I14<>\"\"), \"Date change. Previously scheduled \" & TEXT(H14,\"m/d/y;@\") &IF(H14=I14,\"\",\" to \" & TEXT(I14,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X16-36843",{"$f":"IF(G14<>\"\",\"***\",\"\")","v":"***"},"2016-01-27","2016-01-27","Project Completed",null,null,"Sta. 237",200,5,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,237,"(X16-36843) Sta. 237:  Unit  Maintenance (1/27/16)","***Sta. 237:  Unit  Maintenance\n--1/27/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Sta. 237:  Unit  Maintenance\n***Project Completed\n………………………………"]
[{"$f":"IF(AND(H15<>\"\",I15<>\"\"), \"Date change. Previously scheduled \" & TEXT(H15,\"m/d/y;@\") &IF(H15=I15,\"\",\" to \" & TEXT(I15,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X14-1478563",{"$f":"IF(G15<>\"\",\"***\",\"\")","v":"***"},"2015-11-16","2016-02-12","Project Completed",null,null,"MLV 32-1D to 33-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,32.200000000000003,"(X14-1478563) MLV 32-1D to 33-1:  Hydrotest (11/16/15 to 2/12/16)","***MLV 32-1D to 33-1:  Hydrotest\n--11/16/15 through 2/12/16:  This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***MLV 32-1D to 33-1:  Hydrotest\n***Project Completed\n………………………………"]
[null,"Project Completed","X16-16074",null,"2016-01-18","2016-01-28","Project Completed",null,null,"Station 550","500","1","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,550,"(X16-16074) Station 550:  Station Maintenance (1/18/16 to 1/28/16)","Station 550:  Station Maintenance\n--1/18/16 through 1/28/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","Station 550:  Station Maintenance\n***Project Completed\n………………………………"]
[{"$f":"IF(AND(H17<>\"\",I17<>\"\"), \"Date change. Previously scheduled \" & TEXT(H17,\"m/d/y;@\") &IF(H17=I17,\"\",\" to \" & TEXT(I17,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X16-46202",{"$f":"IF(G17<>\"\",\"***\",\"\")","v":"***"},"2016-02-01","2016-02-07","Project Completed",null,null,"Station 9","100","0","Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.",null,9,"(X16-46202) Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items) (2/1/16 to 2/7/16)","***Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)\n--2/1/16 through 2/7/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\n***Project Completed\n………………………………","***Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)\n***Project Completed\n………………………………"]
["","Project Completed","X15-925633","***","2016-02-09","2016-02-11","Project Completed",null,null,"Sta. 266A",200,6,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,266,"(X15-925633) Sta. 266A:  Unit  Maintenance (2/9/16 to 2/11/16)","***Sta. 266A:  Unit  Maintenance\n--2/9/16 through 2/11/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Sta. 266A:  Unit  Maintenance\n***Project Completed\n………………………………"]
["","Project Completed","X15-929733","***","2016-01-27","2016-02-10","Project Completed",null,null,"MLV 834-1 to 838-1",800,5,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",834.1,"(X15-929733) MLV 834-1 to 838-1:  ILI/Cleaning Pig (1/27/16 to 2/10/16)","***MLV 834-1 to 838-1:  ILI/Cleaning Pig\n--1/27/16 through 2/10/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 834-1 to 838-1:  ILI/Cleaning Pig\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X14-1562506","***","2015-11-02","2016-02-19","Project Completed",null,null,"MLV 5-1 to 6-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410063 ROCHE DEHYDRATION             \n",5.0999999999999996,"(X14-1562506) MLV 5-1 to 6-1:  Hydrotest (11/2/15 to 2/19/16)","***MLV 5-1 to 6-1:  Hydrotest\n--11/2/15 through 2/19/16:  This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410063 ROCHE DEHYDRATION             \n\n***Project Completed\n………………………………","***MLV 5-1 to 6-1:  Hydrotest\n***Project Completed\nThe following meters are available for nominations:\n410063 ROCHE DEHYDRATION             \n\n………………………………"]
["","Project Completed","X14-1562506","***","2015-11-02","2016-02-19","Project Completed",null,null,"MLV 7-1 to 9-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","\n412490 Charro\n421083 Eagle Ford Field Service",5.0999999999999996,"(X14-1562506) MLV 7-1 to 9-1:  Hydrotest (11/2/15 to 2/19/16)","***MLV 7-1 to 9-1:  Hydrotest\n--11/2/15 through 2/19/16:  This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n\n412490 Charro\n421083 Eagle Ford Field Service\n***Project Completed\n………………………………","***MLV 7-1 to 9-1:  Hydrotest\n***Project Completed\nThe following meters are available for nominations:\n\n412490 Charro\n421083 Eagle Ford Field Service\n………………………………"]
["Date change. Previously scheduled 2/18/16 to 2/20/16.","Project Completed","X15-882289","***","2016-02-22","2016-02-24","Project Completed","2016-02-18","2016-02-20","MLV 24-2 to 25-2S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.2,"(X15-882289) MLV 24-2 to 25-2S:  Anomaly Remediation (2/22/16 to 2/24/16)","***MLV 24-2 to 25-2S:  Anomaly Remediation\n--2/22/16 through 2/24/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 24-2 to 25-2S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-925630","***","2016-02-23","2016-02-23","Project Completed",null,null,"WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B)",200,"L","ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,265.10000000000002,"(X15-925630) WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig (2/23/16)","***WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig\n--2/23/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig\n***Project Completed\n………………………………"]
["","Project Completed","X16-23748","***","2016-02-15","2016-02-18","Project Completed",null,null,"MLV 530-3 to 532-3",500,"L","ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,530.29999999999995,"(X16-23748) MLV 530-3 to 532-3:  ILI/Cleaning Pig (2/15/16 to 2/18/16)","***MLV 530-3 to 532-3:  ILI/Cleaning Pig\n--2/15/16 through 2/18/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***MLV 530-3 to 532-3:  ILI/Cleaning Pig\n***Project Completed\n………………………………"]
["","Project Canceled","X16-98720","***","2016-03-06","2016-03-06","Project Canceled",null,null,"Sta. 1",100,0,"Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,1,"(X16-98720) Sta. 1:  Station Maintenance (3/6/16)","***Sta. 1:  Station Maintenance\n--3/6/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Canceled\n………………………………","***Sta. 1:  Station Maintenance\n***Project Canceled\n………………………………"]
["","Project Completed","X14-1562513\nX14-1540661","***","2015-07-01","2016-03-04","Project Completed",null,null,"Station 32","100","0","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,32,"(X14-1562513\nX14-1540661) Station 32:  Station Maintenance (7/1/15 to 3/4/16)","***Station 32:  Station Maintenance\n--7/1/15 through 3/4/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Station 32:  Station Maintenance\n***Project Completed\n………………………………"]
["","Project Canceled","X15-926822","***","2016-06-06","2016-06-11","Project Canceled",null,null,"BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1)",300,6,"Pipe Inspection","This project involves inspecting multiple sites.  We do not anticipate having to do any repairs, however if a repair is needed  there is a potential that the pipe  may require replacement which will require isolation of the pipe.  This may limit throughput and will result in restrictions based on customer nominations.  Customers may experience pressure fluctuations during this timeframe.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",343.1,"(X15-926822) BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection (6/6/16 to 6/11/16)","***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection\n--6/6/16 through 6/11/16:  This project involves inspecting multiple sites.  We do not anticipate having to do any repairs, however if a repair is needed  there is a potential that the pipe  may require replacement which will require isolation of the pipe.  This may limit throughput and will result in restrictions based on customer nominations.  Customers may experience pressure fluctuations during this timeframe.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928271","***","TBD","TBD","Project Canceled",null,null,"MLV 555-1 to 550-1",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.1,"(X15-928271) MLV 555-1 to 550-1:  ILI/Cleaning Pig (TBD)","***MLV 555-1 to 550-1:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-1 to 550-1:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928272","***","TBD","TBD","Project Canceled",null,null,"MLV 555-2 to 550-2",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.20000000000005,"(X15-928272) MLV 555-2 to 550-2:  ILI/Cleaning Pig (TBD)","***MLV 555-2 to 550-2:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-2 to 550-2:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928273","***","TBD","TBD","Project Canceled",null,null,"MLV 555-3 to 552-3",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.29999999999995,"(X15-928273) MLV 555-3 to 552-3:  ILI/Cleaning Pig (TBD)","***MLV 555-3 to 552-3:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-3 to 552-3:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-882281","***","2016-02-24","2016-03-03","Project Completed",null,null,"24-1A to 25-1S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.1,"(X15-882281) 24-1A to 25-1S:  Anomaly Remediation (2/24/16 to 3/3/16)","***24-1A to 25-1S:  Anomaly Remediation\n--2/24/16 through 3/3/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***24-1A to 25-1S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-882291","***","2016-03-03","2016-03-04","Project Completed",null,null,"MLV 24-3 to 25-3S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.3,"(X15-882291) MLV 24-3 to 25-3S:  Anomaly Remediation (3/3/16 to 3/4/16)","***MLV 24-3 to 25-3S:  Anomaly Remediation\n--3/3/16 through 3/4/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 24-3 to 25-3S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X14-1178175","***","2015-06-15","2016-03-31","Project Completed",null,null,"Station 63","100","1","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,63,"(X14-1178175) Station 63:  Station Maintenance (6/15/15 to 3/31/16)","***Station 63:  Station Maintenance\n--6/15/15 through 3/31/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Station 63:  Station Maintenance\n***Project Completed\n………………………………"]
["","Project Cancelled","X15-913224","***","2016-04-16","2016-05-21","Project Cancelled",null,null,"MLV 109-2",100,2,"Pipe Replacement","This project will require taking the pipeline section out of service.   This will limit throughput and will result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",109.2,"(X15-913224) MLV 109-2:  Pipe Replacement (4/16/16 to 5/21/16)","***MLV 109-2:  Pipe Replacement\n--4/16/16 through 5/21/16:  This project will require taking the pipeline section out of service.   This will limit throughput and will result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Cancelled\n………………………………","***MLV 109-2:  Pipe Replacement\n***Project Cancelled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-926830","***","2016-03-07","2016-03-11","Project Completed",null,null,"MLV 400-1 to 408-1",100,0,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.","To Be Determined",400.1,"(X15-926830) MLV 400-1 to 408-1:  ILI/Cleaning Pig (3/7/16 to 3/11/16)","***MLV 400-1 to 408-1:  ILI/Cleaning Pig\n--3/7/16 through 3/11/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 400-1 to 408-1:  ILI/Cleaning Pig\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Cancelled","X16-143836","***","2016-03-28","2016-04-04","Project Cancelled",null,null,"Sta. 409",100,0,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.",null,409,"(X16-143836) Sta. 409:  Unit  Maintenance (3/28/16 to 4/4/16)","***Sta. 409:  Unit  Maintenance\n--3/28/16 through 4/4/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\n***Project Cancelled\n………………………………","***Sta. 409:  Unit  Maintenance\n***Project Cancelled\n………………………………"]
["","Project Cancelled","X15-929680","***","2016-04-18","2016-04-27","Project Cancelled",null,null,"SABINE - KINDER LINE to 822-1",800,"L","Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",822.1,"(X15-929680) SABINE - KINDER LINE to 822-1:  Anomaly Remediation (4/18/16 to 4/27/16)","***SABINE - KINDER LINE to 822-1:  Anomaly Remediation\n--4/18/16 through 4/27/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Cancelled\n………………………………","***SABINE - KINDER LINE to 822-1:  Anomaly Remediation\n***Project Cancelled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]

{"sheet":"Sheet1","index":1,"n_rows":91,"n_cols":24,"rows_kept":91,"cut":false,"hidden":false,"merged":[[2,0,2,14]]}
["Updated ","2024-05-23"]
["Southern Natural Gas Pipeline 2024 Pipeline Outage and Maintenance Summary"]
["This is a summary of the current status of SNG Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  \nAdditionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Southern Natural Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
["*** Indicates revision"]
["Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","System","Zone","Segment","Location","Maintenance Activity","Anticipated Impact","Potential Restriction Level","Meter(s) in Impacted Area","ref_notes",null,null,null,null,null,null,null,"\\\\houCORP\\TRANS\\TRANSERVICES\\OPPLAN\\COMMON\\Outages\\Outage_DB\\SNG"]
["X23-1208676","***","2023-11-29","2024-07-15","Project Change",null,"2024-06-14","South","2","440","Gallion compressor station","Unscheduled unit outage","This unscheduled unit outage could limit throughput through the station and result in restrictions based on customer nominations.",null,null,"----end_date------------model_loc--"]
["X24-159587",null,"2024-02-13","2024-05-31",null,null,null,"South","3","560","South main loop line west of Hall Gate compressor station","Unscheduled pipeline maintenance","This unscheduled pipeline maintenance will require taking the pipe segment out of service. Interruptible and Out of Path Services may be impacted. Should demand increase an impact to Firm In Path services may be required.","OP"]
["X24-45832","***","2024-04-01","2024-06-04","Project Change",null,"2024-05-24","South","3","560","Hall Gate compressor station","scheduled unit maintenance","This project will require a unit outage, however we do not anticipate an impact to customers at this time.",null,null,"----end_date------------model_loc--"]
["X24-217092","***","2024-04-29","2024-05-17","Completed",null,null,"South LA","0","340","White Castle compressor station","unit maintenance","This activity will require a unit outage. Interruptible and Out of Path Services may be impacted","OP",null,"------"]
["X23-1130719","***","2024-04-29","2024-05-17","Completed",null,null,"South","1","400","Gwinville Picknes line north of Rankin","Pipeline maintenance (remediation) 22336-74","This activity will require taking the pipe segment out of service. Interruptible and Out of Path Services may be impacted.","OP",null,"------"]
["X24-505703","***","2024-05-10","2024-05-24","Project Change",null,"2024-05-27","South LA","0","350","Duck Lake Franklinton line north of White Castle","Pipeline maintenance (remediation)-21332-175","This activity will include pipe inspections and repairs, as needed, in specified areas. We do not anticipate an impact to customers at this time.",null,null,"----end_date------------model_loc--"]
["X23-1134665",null,"2024-05-13","2024-08-02",null,null,null,"North","2","130","Gadsden Branch loop line north of Pell City","Southern will be conducting pipeline maintenance on our 12 inch Gadsden Branch loop line, (anomalies) .","This activity will require taking the pipe segment out of service. Customers may experience lower than normal pressures during this maintenance activity."]
["X23-928409","***","2024-05-13","2024-05-19","Completed",null,null,"South","2","430","South main line west of Enterprise compressor staton","Pipeline maintenance","This activity will require taking the pipe segment out of service. Customers may experience lower than normal pressures during this maintenance activity. Interruptible and Out of Path Services may be impacted","OP",null,"------"]
["X23-514103","***","2024-05-13","2024-05-19","Completed",null,null,"South","2","460","Elmore compressor station","Station electrical maintenance","This project will require a station outage, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path nominations may become necessary.","OP",null,"------"]
["X22-819364","***","2024-05-13","2024-05-20","Completed",null,null,"South","3","560","Wrens compressor station","Unit maintenance","This activity will require a unit outage. Interruptible and Out of Path Services may be impacted","OP",null,"------"]
["X24-260341","***","2024-05-13","2024-05-17","Completed",null,null,"South","3","655","Holy Trinity compressor station","Unit maintenance","This unit outage could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path nominations may become necessary.","OP",null,"------"]
["X23-1198922","***","2024-05-14","2024-05-16","Completed",null,null,"North","2","120","North main loop line west of TArrant compressor station","Pigging\n5-14-24 Brush\n5-15-24 AFD\n5-16-24 EMAT","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,"------"]
["X24-494788","***","2024-05-14","2024-05-14","Completed",null,null,"South LA","0","330","Main Pass Franklinton loop line south of Franklinton","Pigging\n5-14-24--clean/gage-two pigs","This activity will include pipe inspections and repairs, as needed, in specified areas. Customer may experience lower than normal pressures during this maintenance activity.",null,null,"------"]
["X24-383671","***","2024-05-14","2024-05-14","Completed",null,null,"South","1","380","Sesh","SESH maintenance at Gwinville","SESH pipeline's operator notified Southern that it will be conducting maintenance at its Gwinville Compressor Station on May 14, 2024 which will reduce the available SNG - SESH capacity (Segment 380). This maintenance will result in a service reduction of SNG - SESH capacity from 504,150 Dth/d to the capacities listed below:  \nMay 14: 455,000 \nPoints impacted in Segment 380 are listed below. \n606400 SESH – GULF RUN TO SNG \n606500 SESH - GULF SOUTH TO SNG \n606700 SESH - ETC TIGER TO SNG \nBased on the current nominations and the reduced available capacity, all transportation service levels, including Primary in the Path, may be at risk for the duration of this outage.\n\nThis reduction in available capacity constitutes an event of Force Majeure under Section 8.3 of the General Terms and Conditions of the Southern Natural Gas Tariff.","IP",null,"------"]
["X23-1198890","***","2024-05-14","2024-05-16","Completed",null,null,"South","2","440","South main line east of Gallion","Pigging\n5-14-24--brush/gage\n5-16-24--MFL","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,"------"]
["X24-369694","***","2024-05-15","2024-05-15","Completed",null,null,"South","1","380","Sesh","SESH maintenance at Gwinville","SESH pipeline's operator notified Southern that it will be conducting maintenance at its Gwinville Compressor Station on May 15, 2024, which will reduce the available SNG - SESH capacity (Segment 380). This maintenance will result in a service reduction of SNG - SESH capacity from 504,150 Dth/d to the capacity listed below:  \nMay 15: 446,000\nPoints impacted in Segment 380 are listed below. \n\n606400 SESH – GULF RUN TO SNG \n606500 SESH - GULF SOUTH TO SNG \n606700 SESH - ETC TIGER TO SNG \nBased on the current nominations and the reduced available capacity, all transportation service levels, including Primary in the Path, may be at risk for the duration of this outage.\n\nThis reduction in available capacity constitutes an event of Force Majeure under Section 8.3 of the General Terms and Conditions of the Southern Natural Gas Tariff.","IP",null,"------"]
["X24-383672","***","2024-05-16","2024-05-16","Completed",null,null,"South","1","380","Sesh","SESH maintenance at Gwinville","SESH pipeline's operator notified Southern that it will be conducting maintenance at its Gwinville Compressor Station on May 16, 2024, which will reduce the available SNG - SESH capacity (Segment 380). This maintenance will result in a service reduction of SNG - SESH capacity from 504,150 Dth/d to the capacity listed below:  \nMay 16: 476,000 \nPoints impacted in Segment 380 are listed below. \n\n606400 SESH – GULF RUN TO SNG \n606500 SESH - GULF SOUTH TO SNG \n606700 SESH - ETC TIGER TO SNG \nBased on the current nominations and the reduced available capacity, all transportation service levels, including Primary in the Path, may be at risk for the duration of this outage.\n\nThis reduction in available capacity constitutes an event of Force Majeure under Section 8.3 of the General Terms and Conditions of the Southern Natural Gas Tariff.","IP",null,"------"]
["X24-524450","***","2024-05-16","2024-05-24","Project Change",null,"2024-05-23","South","2","440","Gallion compressor","unscheduled unit maintenance","This unscheduled unit outage will not add any additional impact in addition to the current planned south main pipeline work impact.",null,null,"----end_date------------model_loc--"]
["X24-527538",null,"2024-05-16","2024-08-14",null,null,null,"South","3","490","Thomaston compressor station","Unscheduled unit outage","This unscheduled unit outage could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path nominations may become necessary.","OP"]
["X24-369695","***","2024-05-20","2024-05-20","Completed",null,null,"South","1","380","Sesh","SESH maintenance at Delhi","SESH pipeline's operator notified Southern that it will be conducting maintenance at its Delhi Compressor Station on May 20, 2024, which will reduce the available SNG - SESH capacity (Segment 380). This maintenance will result in a service reduction of SNG - SESH capacity from 504,150 Dth/d to the capacity listed below:  \nMay 20th: 432,000\nPoints impacted in Segment 380 are listed below. \n\n606400 SESH – GULF RUN TO SNG \n606500 SESH - GULF SOUTH TO SNG \n606700 SESH - ETC TIGER TO SNG \nBased on the current nominations and the reduced available capacity, all transportation service levels, including Primary in the Path, may be at risk for the duration of this outage.\n\nThis reduction in available capacity constitutes an event of Force Majeure under Section 8.3 of the General Terms and Conditions of the Southern Natural Gas Tariff.","IP",null,"------"]
["X23-251323",null,"2024-05-20","2024-06-18",null,null,null,"South","2","430","South main line west of Enterprise compressor station","Pipeline maintenance","This activity will require taking the pipe segment out of service. Customers may experience lower than normal pressures during this maintenance activity. Interruptible and Out of Path Services may be impacted","OP"]
["X24-383677","***","2024-05-21","2024-05-22","Completed",null,null,"South","1","380","Sesh","SESH maintenance at Delhi","SESH pipeline's operator notified Southern that it will be conducting maintenance at its Delhi Compressor Station on May 21st to May 22nd, 2024, which will reduce the available SNG - SESH capacity (Segment 380). This maintenance will result in a service reduction of SNG - SESH capacity from 504,150 Dth/d to the capacity listed below:  \nMay 21st thru May 22ndh: 456,000\nPoints impacted in Segment 380 are listed below. \n\n606400 SESH – GULF RUN TO SNG \n606500 SESH - GULF SOUTH TO SNG \n606700 SESH - ETC TIGER TO SNG \nBased on the current nominations and the reduced available capacity, all transportation service levels, including Primary in the Path, may be at risk for the duration of this outage.\n\nThis reduction in available capacity constitutes an event of Force Majeure under Section 8.3 of the General Terms and Conditions of the Southern Natural Gas Tariff.","IP",null,"------"]
["X23-980361",null,"2024-05-21","2024-05-25",null,null,null,"South","2","460","South main loop line west of Elmore compressor station","Pipeline maintenance (replacement)-2577C","This activity will require taking the pipe segment out of service. Customers may experience lower than normal pressures during this maintenance activity. Interruptible and Out of Path Services may be impacted","OP"]
["X23-1194045","***","2024-05-21","2024-05-23","Completed",null,null,"South","3","480","Southh main loop line west of Ellerslie","Pigging\n5-21-24--brush/gage\n5-23-24--caliper/IMU","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,"------"]
["X24-144369","***","2024-05-22","2024-05-29","Project Change","2024-05-20","2024-05-23","South","1","400","Gwinville Pickens line south of Pickens","Pipeline maintenance (remediation)","This activity will require taking the pipe segment out of service. Interruptible and Out of Path Services may be impacted.","OP",null,"--start_date--end_date------------model_loc--"]
["X23-556035",null,"2024-05-22","2024-06-18",null,null,null,"South","2","420","South main line east of Bay Springs","Pipeline maintenance","This activity will require taking the pipe segment out of service. Customers may experience lower than normal pressures during this maintenance activity. Interruptible and Out of Path Services may be impacted","OP"]
["X24-383679",null,"2024-05-23","2024-05-23",null,null,null,"South","1","380","Sesh","SESH maintenance at Delhi","SESH pipeline's operator notified Southern that it will be conducting maintenance at its Delhi Compressor Station on May 23rd, 2024, which will reduce the available SNG - SESH capacity (Segment 380). This maintenance will result in a service reduction of SNG - SESH capacity from 504,150 Dth/d to the capacity listed below:  \nMay 23rd: 482,000\nPoints impacted in Segment 380 are listed below. \n\n606400 SESH – GULF RUN TO SNG \n606500 SESH - GULF SOUTH TO SNG \n606700 SESH - ETC TIGER TO SNG \nBased on the current nominations and the reduced available capacity, all transportation service levels, including Primary in the Path, may be at risk for the duration of this outage.\n\nThis reduction in available capacity constitutes an event of Force Majeure under Section 8.3 of the General Terms and Conditions of the Southern Natural Gas Tariff.","IP"]
["X24-138068",null,"2024-05-28","2024-07-15",null,null,null,"North","2","120","Bessemer Calera loop line east of Providence","Pipeline maintenance","This activity will require taking the pipe segment out of service. Customers may experience lower than normal pressures during this maintenance activity."]
["X24-505595","***","2024-05-29","2024-05-29","Added",null,null,"South LA","0","340","Shadyside compressor station","Station outage for maintenance","This activity will require a station outage for 8 hours. Customer may experience higher than normal pressures during the station maintenance. Interruptible and Out of Path Services may be impacted","OP",null,"------"]
["X24-524354",null,"2024-05-29","2024-05-31",null,null,null,"South","1","380","Sesh","SESH maintenance at Delhi","SESH pipeline's operator notified Southern that it will be conducting maintenance at its Delhi Compressor Station on May 29th thru May 31st, 2024, which will reduce the available SNG - SESH capacity (Segment 380). This maintenance will result in a service reduction of SNG - SESH capacity from 504,150 Dth/d to the capacity listed below:  \nMay 29th to May 31st: 445,000\nPoints impacted in Segment 380 are listed below. \n\n606400 SESH – GULF RUN TO SNG \n606500 SESH - GULF SOUTH TO SNG \n606700 SESH - ETC TIGER TO SNG \nBased on the current nominations and the reduced available capacity, all transportation service levels, including Primary in the Path, may be at risk for the duration of this outage.\n\nThis reduction in available capacity constitutes an event of Force Majeure under Section 8.3 of the General Terms and Conditions of the Southern Natural Gas Tariff.","IP"]
["X24-428707","***","2024-05-30","2024-05-31","Project Change","2024-05-28","2024-05-30","South","3","560","South main loop line west of Hall Gate","Pigging\nbrush-5-30-24\nCLP/IMU-5-31-24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,"--start_date--end_date------mantenance_desc------model_loc--"]
["X24-542215","***","2024-06-01","2024-07-03","Added",null,null,"South","3","560","South main loop line west of Hall Gate compressor station","Unscheduled pipeline maintenance","This unscheduled pipeline maintenance will require taking the pipe segment out of service. Interruptible and Out of Path Services may be impacted. Should demand increase an impact to Firm In Path services may be required.","OP",null,"------"]
["X24-49168","***","2024-06-03","2024-06-14","Added",null,null,"South","2","400","Gwinville compressor station","unit maintenance","This activity will require a unit outage. Interruptible and Out of Path Services may be impacted","OP",null,"------"]
["X24-27809",null,"2024-06-03","2024-06-07",null,null,null,"South","2","460","South main 2nd loop line east of Elmore","Pipeline maintenance - anomaly","This activity will include pipe inspections and repairs, as needed, in specified areas. Customer may experience lower than normal pressures during this maintenance activity. Interruptible and Out of Path Services may be impacted..","OP"]
["X23-1017382",null,"2024-06-05","2024-06-13",null,null,null,"South","3","540","Brunswick line south of Ocmulgee","Pigging\nBrush gage-6-5-24\nMFL-c-6-11-24\nEMAT-6-13-24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated."]
["X23-1134668",null,"2024-06-10","2024-06-14",null,null,null,"South","3","580","Wrens Savannah loop line-Wrens to Savannah","Pipeline maintenance-anomalies","This activity will include pipe inspections and repairs, as needed, in specified areas. Customer may experience lower than normal pressures during this maintenance activity. Interruptible and Out of Path Services may be impacted","OP"]
["X23-928422",null,"2024-06-15","2024-06-16",null,null,null,"South","2","430","South main line west of Enterprise compressor station","Pipeline maintenance","This activity will require taking the pipe segment out of service. Customers may experience lower than normal pressures during this maintenance activity. Interruptible and Out of Path Services may be impacted","OP"]
["X23-1134671",null,"2024-06-17","2024-06-24",null,null,null,"South","3","530","South main line east of Thomaston","Pipeline maintenance-anomalies","This activity will include pipe inspections and repairs, as needed, in specified areas. We do not anticipate an impact to customers at this time."]
["X23-1134678",null,"2024-06-17","2024-06-29",null,null,null,"South","3","750","Mulcoa line 62 east of Holy Trinity","Pipeline maintenance (remediation)","This activity will include pipe inspections and repairs, as needed, in specified areas. We do not anticipate an impact to customers at this time."]
["X23-1198988","***","2024-06-30","2024-06-30","Project Change","2024-06-10","2024-06-13","North","0","10","Logansport Supply line Logansport to Bienville","Pigging\n","This activity will include pipe inspections and repairs, as needed, in specified areas. Customer may experience lower than normal pressures during this maintenance activity.",null,null,"--start_date--end_date------------model_loc--"]
["X23-1227085","***","2024-06-30","2024-06-30","Project Change","2024-06-04","2024-06-06","North","0","10","Logansport line  - Logansport to Bienville","Pigging\n","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,"J.W. Gathering PIN(651350)  J. W. Gathering may be required to be shut in during the pigging operation.  SNG Gas Control will be in contact.","--start_date--end_date------------model_loc--"]
["X23-1173926",null,"2024-06-24","2024-06-27",null,null,null,"North","0","20","Logansport loop line east of Bienville","Pigging\n6-24-24 to 6-25-24--cleaning/gage\n6-26-24--combo tool\n6-27-24--AFD tool","This activity will include pipe inspections and repairs, as needed, in specified areas. Customer may experience lower than normal pressures during this maintenance activity."]
["X24-217044",null,"2024-06-24","2024-06-26",null,null,null,"South","1","420","Bay Springs compressor station","unit outage","This unit outage could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path nominations may become necessary.","OP"]
["X22-1138185",null,"2024-06-24","2024-06-28",null,null,null,"South","3","490","South Main line west of Thomaston","Pipeline maintenance (anomalies) Project 17842","This activity will include pipe inspections and repairs, as needed, in specified areas. Customer may experience lower than normal pressures during this maintenance activity. Interruptible and Out of Path Services may be impacted","OP"]
["X23-643070",null,"2024-06-24","2024-06-28",null,null,null,"South","3","530","South Main line west of Thomaston","Pipeline maintenance (anomalies) Project 34908","This activity will include pipe inspections and repairs, as needed, in specified areas. Customer may experience lower than normal pressures during this maintenance activity. Interruptible and Out of Path Services may be impacted","OP"]
["X23-1198951",null,"2024-06-25","2024-06-27",null,null,null,"North","2","120","North main line west of Tarrant","Pigging\n6-25-24--brush/gage\n6-26-24--caliper/IMU\n6-27-24--AFD","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated."]
["X23-411588",null,"2024-07-08","2024-08-08",null,null,null,"South","1","370","Franklinton Gwinville line south of Gwinville","Pipeline maintenance (pressure test)","This activity will require taking the pipe segment out of service. Customers may experience lower than normal pressures during this maintenance activity. Interruptible and Out of Path Services may be impacted","OP"]
["X23-1017392",null,"2024-07-09","2024-07-11",null,null,null,"South","3","580","Wrens Savannah Loop Line south of Wrens compressor station","Pigging\nbrush gage-7-9-24\nMFL-C-7-10-24\nEMAT-7-11-24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated."]
["X23-910984",null,"2024-07-13","2024-07-13",null,null,null,"South","1","380","SESH","Pipeline maintenance","Southern will be conducting maintenance on the Franklinton Gwinville Line in Segment 390 on July 13th, 2024 and from August 10th - August 11th, 2024.  As a result of this maintenance, Southern will not be able to accept nominations at the following locations:\n606610 SESH - SESH TO SNG\n606400 SESH - GULFRUN TO SNG \n606500 SESH - GULF SOUTH TO SNG \n606700 SESH - ETC TIGER TO SNG\nIf you have any questions concerning this notice please contact your Scheduling Representative or Account Manager.\nGas Control","IP","606610 SESH - SESH TO SNG\n606400 SESH - GULFRUN TO SNG \n606500 SESH - GULF SOUTH TO SNG \n606700 SESH - ETC TIGER TO SNG"]
["X24-432106",null,"2024-07-15","2024-07-20",null,null,null,"North","2","120","Bessemer Calera line east of Providence","Pipeline maintenance","This activity will require taking the pipe segment out of service. Customers may experience lower than normal pressures during this maintenance activity."]
["X23-1198943",null,"2024-07-15","2024-07-19",null,null,null,"South LA","0","330","Main Pass Franklinton loop line south of Franklinton","Pigging\n7-15-24--clean/gage\n7-16-24--IMU\n7-17-24--AFD\n7-19-24--EMAT","This activity will include pipe inspections and repairs, as needed, in specified areas. Customer may experience lower than normal pressures during this maintenance activity."]
["X23-1198850",null,"2024-07-15","2024-07-18",null,null,null,"South LA","0","340","SS28 line south of White Castle","pigging\ncleaning-7-15-24 to 7-16-24\naddition cleaning pigs if necessary-7-17-24\nEMAT-7-18-24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated."]
["X23-1173933",null,"2024-07-16","2024-07-17",null,null,null,"North","0","20","Logansport loop line east of Bienville","Pigging\nbrush/gage--7-16-24\nAFD-7-17-24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated."]
["X24-73034",null,"2024-07-16","2024-07-18",null,null,null,"South","3","480","South main loop line west of Ellerslie","Pigging\n7-16-24--AFD\n7-18-24--EMAT","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated."]
["X23-1199004",null,"2024-07-23","2024-07-25",null,null,null,"South","3","710","Line - 64 Jacksonville line south of Pavo","Pigging\nbrush/gage-7-23-24\nMFL-A-7-25-24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated."]
["X24-64563",null,"2024-08-05","2024-08-08",null,null,null,"South","2","440","South main loop line east of Gallion","Pigging\n8-5-24--brush/gage\n8-6-24--AFD\n8-8-24--EMAT","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated."]
["X23-910986",null,"2024-08-10","2024-08-11",null,null,null,"South","1","380","SESH","Pipeline maintenance..","Southern will be conducting maintenance on the Franklinton Gwinville Line in Segment 390 on July 13th, 2024 and from August 10th - August 11th, 2024.  As a result of this maintenance, Southern will not be able to accept nominations at the following locations:\n606610 SESH - SESH TO SNG\n606400 SESH - GULFRUN TO SNG \n606500 SESH - GULF SOUTH TO SNG \n606700 SESH - ETC TIGER TO SNG\nIf you have any questions concerning this notice please contact your Scheduling Representative or Account Manager.\nGas Control","IP","606610 SESH - SESH TO SNG\n606400 SESH - GULFRUN TO SNG \n606500 SESH - GULF SOUTH TO SNG \n606700 SESH - ETC TIGER TO SNG"]
["X23-1173938",null,"2024-08-13","2024-08-15",null,null,null,"South","3","750","North Terrell line 6 south of Holy Trinity","Pigging\nbrush/gage-8-13-24\nMFL-A-8-14-24\nMFL-C-8-15-24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated."]
["X23-1134631",null,"2024-08-19","2024-09-13",null,null,null,"North","3","180","Rome Calhoun loop line","Pipeline maintenance-replacement-15374","This activity will require taking the pipe segment out of service. We do not anticipate an impact at this time."]
["X23-411610",null,"2024-08-19","2024-08-26",null,null,null,"South","1","370","Franklinton Gwinville loop line north of Pearl River","Pipeline valve maintenance","This activity will require taking the pipe segment out of service. Customers may experience lower than normal pressures during this maintenance activity. Interruptible and Out of Path Services may be impacted","OP"]
["X23-980351",null,"2024-08-19","2024-08-23",null,null,null,"South","3","560","South Main line est of Ocmulgee","Pipeline maintenance (replacement) 2496B","This activity will require taking the pipe segment out of service. We do not anticipate and impact to customers at this time."]
["X24-138080",null,"2024-08-21","2024-08-26",null,null,null,"North","2","120","Bessemer Calera line east of Providence","Pipeline maintenance","This activity will require taking the pipe segment out of service. Customers may experience lower than normal pressures during this maintenance activity."]
["X24-138089",null,"2024-08-27","2024-08-30",null,null,null,"North","2","120","Bessemer Calera line east of Providence","Pipeline maintenance","This activity will require taking the pipe segment out of service. Customers may experience lower than normal pressures during this maintenance activity."]
["X23-411612",null,"2024-08-27","2024-09-03",null,null,null,"South","1","370","Franklinton Gwinville 2nd loop line north of Pearl River","Pipeline valve maintenance","This activity will require taking the pipe segment out of service. Customers may experience lower than normal pressures during this maintenance activity. Interruptible and Out of Path Services may be impacted","OP"]
["X24-138093",null,"2024-09-03","2024-09-06",null,null,null,"North","2","120","Bessemer Calera loop line east of Providence","Pipeline maintenance","This activity will require taking the pipe segment out of service. Customers may experience lower than normal pressures during this maintenance activity."]
["X23-1230685",null,"2024-09-06","2024-10-25",null,null,null,"North","2","140","Talladega Branch loop to Sylacauga line","Pipeline maintenance-36904","This activity will require taking the pipe segment out of service. We do not anticipate an impact to customers at this time..",null,"Talladega #2-meter station (PIN 847700)\nChildersburg meter station (PIN 844400)\nSylacauga meter station (PIN 848000)"]
["X24-524376",null,"2024-09-09","2024-11-08",null,null,null,"North","1","45","Muldon storage","Unit maintenance","This activity will require a unit outage restricting injection capacity from 345 Mdth/d to 230 Mdth/d."]
["X23-1246531",null,"2024-09-16","2024-09-20",null,null,null,"South","3","500","Thomaston Griffin 2nd loop line north of Thomaston","Pipeline maintenance-pipe replacement","This activity will require taking the pipe segment out of service.  We do not anticipate an impact to customers at this time."]
["X23-1173941",null,"2024-09-17","2024-09-18",null,null,null,"South","3","500","Ocmulgee Atlanta line segment-Ocmulgee to Bass Junction","Pigging\nbrush/gage--9-17-24\nAFD---9-18-24","Southern will be conducting maintenance pigging on the Ocmulgee Atlanta line segment-Ocmulgee to Bass Junction.  Customers may experience pressure fluctuations during this pigging operation."]
["X22-449885",null,"2024-09-23","2024-09-24",null,null,null,"South","2","440","Gallion compressor station","Unit maintenance","This activity will require a unit outage. Interruptible and Out of Path Services may be impacted.","OP"]
["X23-1238633",null,"2024-09-25","2024-09-26",null,null,null,"South","2","460","Elmore compressor station","Unit maintenance","This activity will require a unit outage. Interruptible and Out of Path Services may be impacted.","OP"]
["X24-431951",null,"2024-10-01","2024-10-07",null,null,null,"North","2","120","Bessemer Calera line east of Providence","Pipeline maintenance","This activity will require taking the pipe segment out of service. Customers may experience lower than normal pressures during this maintenance activity."]
["X23-1130406",null,"2024-10-01","2024-10-07",null,null,null,"North","1","45","Muldon storage facilities","Shut-in Test","This project will require taking the facility out of service.  This will limit throughput and may result in restrictions based on customer nominations.","To the extent total storage demand exceeds Southern’s injection abilities, restrictions will be made first into ISS nominations and if necessary, into CSS, not to exceed a reduction to each CSS customers account of more than thirty six percent (36%) of their currently effective DIQ and DWQ."]
["X23-1238619",null,"2024-10-01","2024-10-28",null,null,null,"South","2","460","Selma Compressor station","Unit maintenance","This project will require a unit outage, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path nominations may become necessary.","OP"]
["X23-1238631",null,"2024-10-07","2024-10-08",null,null,null,"South","2","460","Auburn compressor station","unit maintenance","This activity will require a unit outage. Interruptible and Out of Path Services may be impacted..","OP"]
["X24-431952",null,"2024-10-08","2024-10-15",null,null,null,"North","2","120","Bessemer Calera loop line east of Providence","Pipeline maintenance","This activity will require taking the pipe segment out of service. Customers may experience lower than normal pressures during this maintenance activity."]
["X23-1173940",null,"2024-10-08","2024-10-09",null,null,null,"North","2","130","North main loop line east of Tarrant","pigging\n10-8-24--brush/gage\n10-9-24--AFD","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated."]
["X23-1266383",null,"2024-10-08","2024-10-16",null,null,null,"South","1","400","2ndNML east of Pickens","Pipeline maintenance-SNG-2328","This activity will require taking the pipe segment out of service. Customers may experience lower than normal pressures during this maintenance activity. Interruptible and Out of Path Services may be impacted.","OP"]
["X24-277933",null,"2024-10-10","2024-10-13",null,null,null,"North","2","120","2nd North main line east of Providence","Pipeline maintenance (valve maintenance)","This activity will require taking the pipe segment out of service. Customers may experience lower than normal pressures during this maintenance activity. Interruptible and Out of Path Services may be impacted.","OP"]
["X24-304282",null,"2024-10-14","2024-10-14",null,null,null,"South","1","430","York compressor station","station maintenance","This activity will require a station outage. Interruptible and Out of Path Services may be impacted.","OP"]
["X23-1130423",null,"2024-10-15","2024-10-21",null,null,null,"North","0","10","Bear Creek Storage Facilities","Shut-in test","This project will require taking the facility out of service.  This will limit throughput and may result in restrictions based on customer nominations.","To the extent total storage demand exceeds Southern’s injection abilities, restrictions will be made first into ISS nominations and if necessary, into CSS, not to exceed a reduction to each CSS customers account of more than sixty four percent (64%) of their currently effective DIQ and DWQ."]
["X24-304283",null,"2024-10-15","2024-10-15",null,null,null,"South","2","440","Gallion compressor station","Station maintenance","This activity will require a stationt outage. Interruptible and Out of Path Services may be impacted.","OP"]
["X24-304286",null,"2024-10-17","2024-10-17",null,null,null,"South","2","460","Elmore compressor station","Station maintenance","This activity will require a station outage. Interruptible and Out of Path Services may be impacted.","OP"]
["X24-304287",null,"2024-10-18","2024-10-18",null,null,null,"South","2","460","Auburn compressor station","station  maintenance","This activity will require a station outage. Interruptible and Out of Path Services may be impacted","OP"]
["X22-449882",null,"2024-10-23","2024-10-24",null,null,null,"South","2","430","York compressor station","Unit maintenance","This activity will require a unit outage. Interruptible and Out of Path Services may be impacted.","OP"]
["X23-935500",null,"2024-12-31","2024-12-31",null,null,null,"South","2","460","Auburn compressor station","Station outage for maintenance","This project will require a station outage, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path nominations may become necessary.","OP"]

{"sheet":"Sheet2","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}

{"sheet":"Sheet3","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}