{"text_format":"1","workbook":"xlsx","n_sheets":4,"sheets":["Closed","Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":8,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Closed","index":0,"n_rows":37,"n_cols":22,"rows_kept":37,"cut":false,"hidden":true,"merged":[[1,3,1,15],[2,3,2,15],[3,3,3,15]]}
[null,null,null,"Updated ","2016"]
[null,null,null,"Tennessee Gas Pipeline 2015 Pipeline Outage and Maintenance Summary"]
[null,null,null,"This is a summary of the current status of all TGP Winter 2014-2015 Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  Additionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
[null,null,null,"*** Indicates revision"]
["Date Change","Project New/Completed/Closed","Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","Location","Leg","Zone","Maintenance Activity","Anticipated Impact","Potential Restriction Level","TOS Potential Restrictions","Meter(s) in Impacted Area","Customer Notifications","Loc","Email Text","Posting Text","Completion Text"]
[{"$f":"IF(AND(H6<>\"\",I6<>\"\"), \"Date change. Previously scheduled \" & TEXT(H6,\"m/d/y;@\") &IF(H6=I6,\"\",\" to \" & TEXT(I6,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed",null,{"$f":"IF(G6<>\"\",\"***\",\"\")","v":"***"},"2015-01-11","2016-01-11",{"$f":"IF(AND(A6=\"\",B6=\"\"),\"\",IF(B6=\"\",A6,B6))","v":"Project Completed"},null,null,"MS #412494 DCP Warren","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412494 DCP Warren",401,{"$f":"\"(\"&C6&\") \"&J6&\":  \"&M6&IF(AND(E6=\"\",F6=\"\"),\"\",\" (\")&IF(E6=\"\",\"\",\"\"&TEXT(E6,\"m/d/y;@\"))&IF(OR(F6=E6,E6=\"\",F6=\"\"),\"\",\" to \")&IF(OR(F6=\"\",F6=E6),\"\",TEXT(F6,\"m/d/y;@\"))&IF(AND(E6=\"\",F6=\"\"),\"\",\")\")","v":"() MS #412494 DCP Warren:  Meter Station (1/11/15 to 1/11/16)"},{"$f":"D6&J6&\":  \"&M6&IF(AND(E6=\"\",F6=\"\"),\"\",\"\n\")&IF(E6=\"\",\"\",\"--\"&TEXT(E6,\"m/d/y;@\"))&IF(OR(F6=E6,E6=\"\",F6=\"\"),\"\",\" through \")&IF(OR(F6=\"\",F6=E6),\"\",TEXT(F6,\"m/d/y;@\"))&IF(AND(E6=\"\",F6=\"\"),\"\",\":  \")&N6&\"  \"&P6&IF(Q6=\"\",\"\",\"\n\"&Q6)&IF(G6=\"\",\"\",\"\n***\")&G6&\"\n………………………………\"","v":"***MS #412494 DCP Warren:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412494 DCP Warren\n***Project Completed\n………………………………"},{"$f":"D6&J6&\":  \"&M6&IF(G6=\"\",\"\",\"\n***\")&G6&IF(Q6=\"\",\"\",\"\nThe following meters are available for nominations:\n\")&Q6&\"\n………………………………\"","v":"***MS #412494 DCP Warren:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412494 DCP Warren\n………………………………"}]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412400 King Ranch","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412400 King Ranch",402.1,"() MS #412400 King Ranch:  Meter Station (1/11/15 to 1/11/16)","***MS #412400 King Ranch:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412400 King Ranch\n***Project Completed\n………………………………","***MS #412400 King Ranch:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412400 King Ranch\n………………………………"]
["","Project Completed",null,"***","2015-01-12","2016-01-12","Project Completed",null,null,"MS #410539 Duvak Gas Gathering","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410539 Duvak Gas Gathering",402.1,"() MS #410539 Duvak Gas Gathering:  Meter Station (1/12/15 to 1/12/16)","***MS #410539 Duvak Gas Gathering:  Meter Station\n--1/12/15 through 1/12/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410539 Duvak Gas Gathering\n***Project Completed\n………………………………","***MS #410539 Duvak Gas Gathering:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n410539 Duvak Gas Gathering\n………………………………"]
["","Project Completed",null,"***","2015-01-13","2016-01-13","Project Completed",null,null,"MS #412356 DCP LaGloria","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412356 DCP LaGloria",403.1,"() MS #412356 DCP LaGloria:  Meter Station (1/13/15 to 1/13/16)","***MS #412356 DCP LaGloria:  Meter Station\n--1/13/15 through 1/13/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412356 DCP LaGloria\n***Project Completed\n………………………………","***MS #412356 DCP LaGloria:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412356 DCP LaGloria\n………………………………"]
["","Project Completed",null,"***","2015-01-13","2016-01-13","Project Completed",null,null,"MS #410173 Enterprise LaReforma","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410173 Enterprise LaReforma",406.1,"() MS #410173 Enterprise LaReforma:  Meter Station (1/13/15 to 1/13/16)","***MS #410173 Enterprise LaReforma:  Meter Station\n--1/13/15 through 1/13/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410173 Enterprise LaReforma\n***Project Completed\n………………………………","***MS #410173 Enterprise LaReforma:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n410173 Enterprise LaReforma\n………………………………"]
["","Project Completed",null,"***","2015-01-12","2016-01-12","Project Completed",null,null,"MS #411903 Enterprise El Benito","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","411903 Enterprise El Benito",407.1,"() MS #411903 Enterprise El Benito:  Meter Station (1/12/15 to 1/12/16)","***MS #411903 Enterprise El Benito:  Meter Station\n--1/12/15 through 1/12/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n411903 Enterprise El Benito\n***Project Completed\n………………………………","***MS #411903 Enterprise El Benito:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n411903 Enterprise El Benito\n………………………………"]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412088 Enterprise Sullivan","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412088 Enterprise Sullivan",407.1,"() MS #412088 Enterprise Sullivan:  Meter Station (1/11/15 to 1/11/16)","***MS #412088 Enterprise Sullivan:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412088 Enterprise Sullivan\n***Project Completed\n………………………………","***MS #412088 Enterprise Sullivan:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412088 Enterprise Sullivan\n………………………………"]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412683 HESCO","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412683 HESCO",408.1,"() MS #412683 HESCO:  Meter Station (1/11/15 to 1/11/16)","***MS #412683 HESCO:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412683 HESCO\n***Project Completed\n………………………………","***MS #412683 HESCO:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412683 HESCO\n………………………………"]
[{"$f":"IF(AND(H14<>\"\",I14<>\"\"), \"Date change. Previously scheduled \" & TEXT(H14,\"m/d/y;@\") &IF(H14=I14,\"\",\" to \" & TEXT(I14,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X16-36843",{"$f":"IF(G14<>\"\",\"***\",\"\")","v":"***"},"2016-01-27","2016-01-27","Project Completed",null,null,"Sta. 237",200,5,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,237,"(X16-36843) Sta. 237:  Unit  Maintenance (1/27/16)","***Sta. 237:  Unit  Maintenance\n--1/27/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Sta. 237:  Unit  Maintenance\n***Project Completed\n………………………………"]
[{"$f":"IF(AND(H15<>\"\",I15<>\"\"), \"Date change. Previously scheduled \" & TEXT(H15,\"m/d/y;@\") &IF(H15=I15,\"\",\" to \" & TEXT(I15,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X14-1478563",{"$f":"IF(G15<>\"\",\"***\",\"\")","v":"***"},"2015-11-16","2016-02-12","Project Completed",null,null,"MLV 32-1D to 33-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,32.200000000000003,"(X14-1478563) MLV 32-1D to 33-1:  Hydrotest (11/16/15 to 2/12/16)","***MLV 32-1D to 33-1:  Hydrotest\n--11/16/15 through 2/12/16:  This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***MLV 32-1D to 33-1:  Hydrotest\n***Project Completed\n………………………………"]
[null,"Project Completed","X16-16074",null,"2016-01-18","2016-01-28","Project Completed",null,null,"Station 550","500","1","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,550,"(X16-16074) Station 550:  Station Maintenance (1/18/16 to 1/28/16)","Station 550:  Station Maintenance\n--1/18/16 through 1/28/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","Station 550:  Station Maintenance\n***Project Completed\n………………………………"]
[{"$f":"IF(AND(H17<>\"\",I17<>\"\"), \"Date change. Previously scheduled \" & TEXT(H17,\"m/d/y;@\") &IF(H17=I17,\"\",\" to \" & TEXT(I17,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X16-46202",{"$f":"IF(G17<>\"\",\"***\",\"\")","v":"***"},"2016-02-01","2016-02-07","Project Completed",null,null,"Station 9","100","0","Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.",null,9,"(X16-46202) Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items) (2/1/16 to 2/7/16)","***Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)\n--2/1/16 through 2/7/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\n***Project Completed\n………………………………","***Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)\n***Project Completed\n………………………………"]
["","Project Completed","X15-925633","***","2016-02-09","2016-02-11","Project Completed",null,null,"Sta. 266A",200,6,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,266,"(X15-925633) Sta. 266A:  Unit  Maintenance (2/9/16 to 2/11/16)","***Sta. 266A:  Unit  Maintenance\n--2/9/16 through 2/11/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Sta. 266A:  Unit  Maintenance\n***Project Completed\n………………………………"]
["","Project Completed","X15-929733","***","2016-01-27","2016-02-10","Project Completed",null,null,"MLV 834-1 to 838-1",800,5,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",834.1,"(X15-929733) MLV 834-1 to 838-1:  ILI/Cleaning Pig (1/27/16 to 2/10/16)","***MLV 834-1 to 838-1:  ILI/Cleaning Pig\n--1/27/16 through 2/10/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 834-1 to 838-1:  ILI/Cleaning Pig\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X14-1562506","***","2015-11-02","2016-02-19","Project Completed",null,null,"MLV 5-1 to 6-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410063 ROCHE DEHYDRATION             \n",5.0999999999999996,"(X14-1562506) MLV 5-1 to 6-1:  Hydrotest (11/2/15 to 2/19/16)","***MLV 5-1 to 6-1:  Hydrotest\n--11/2/15 through 2/19/16:  This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410063 ROCHE DEHYDRATION             \n\n***Project Completed\n………………………………","***MLV 5-1 to 6-1:  Hydrotest\n***Project Completed\nThe following meters are available for nominations:\n410063 ROCHE DEHYDRATION             \n\n………………………………"]
["","Project Completed","X14-1562506","***","2015-11-02","2016-02-19","Project Completed",null,null,"MLV 7-1 to 9-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","\n412490 Charro\n421083 Eagle Ford Field Service",5.0999999999999996,"(X14-1562506) MLV 7-1 to 9-1:  Hydrotest (11/2/15 to 2/19/16)","***MLV 7-1 to 9-1:  Hydrotest\n--11/2/15 through 2/19/16:  This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n\n412490 Charro\n421083 Eagle Ford Field Service\n***Project Completed\n………………………………","***MLV 7-1 to 9-1:  Hydrotest\n***Project Completed\nThe following meters are available for nominations:\n\n412490 Charro\n421083 Eagle Ford Field Service\n………………………………"]
["Date change. Previously scheduled 2/18/16 to 2/20/16.","Project Completed","X15-882289","***","2016-02-22","2016-02-24","Project Completed","2016-02-18","2016-02-20","MLV 24-2 to 25-2S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.2,"(X15-882289) MLV 24-2 to 25-2S:  Anomaly Remediation (2/22/16 to 2/24/16)","***MLV 24-2 to 25-2S:  Anomaly Remediation\n--2/22/16 through 2/24/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 24-2 to 25-2S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-925630","***","2016-02-23","2016-02-23","Project Completed",null,null,"WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B)",200,"L","ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,265.10000000000002,"(X15-925630) WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig (2/23/16)","***WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig\n--2/23/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig\n***Project Completed\n………………………………"]
["","Project Completed","X16-23748","***","2016-02-15","2016-02-18","Project Completed",null,null,"MLV 530-3 to 532-3",500,"L","ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,530.29999999999995,"(X16-23748) MLV 530-3 to 532-3:  ILI/Cleaning Pig (2/15/16 to 2/18/16)","***MLV 530-3 to 532-3:  ILI/Cleaning Pig\n--2/15/16 through 2/18/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***MLV 530-3 to 532-3:  ILI/Cleaning Pig\n***Project Completed\n………………………………"]
["","Project Canceled","X16-98720","***","2016-03-06","2016-03-06","Project Canceled",null,null,"Sta. 1",100,0,"Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,1,"(X16-98720) Sta. 1:  Station Maintenance (3/6/16)","***Sta. 1:  Station Maintenance\n--3/6/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Canceled\n………………………………","***Sta. 1:  Station Maintenance\n***Project Canceled\n………………………………"]
["","Project Completed","X14-1562513\nX14-1540661","***","2015-07-01","2016-03-04","Project Completed",null,null,"Station 32","100","0","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,32,"(X14-1562513\nX14-1540661) Station 32:  Station Maintenance (7/1/15 to 3/4/16)","***Station 32:  Station Maintenance\n--7/1/15 through 3/4/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Station 32:  Station Maintenance\n***Project Completed\n………………………………"]
["","Project Canceled","X15-926822","***","2016-06-06","2016-06-11","Project Canceled",null,null,"BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1)",300,6,"Pipe Inspection","This project involves inspecting multiple sites.  We do not anticipate having to do any repairs, however if a repair is needed  there is a potential that the pipe  may require replacement which will require isolation of the pipe.  This may limit throughput and will result in restrictions based on customer nominations.  Customers may experience pressure fluctuations during this timeframe.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",343.1,"(X15-926822) BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection (6/6/16 to 6/11/16)","***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection\n--6/6/16 through 6/11/16:  This project involves inspecting multiple sites.  We do not anticipate having to do any repairs, however if a repair is needed  there is a potential that the pipe  may require replacement which will require isolation of the pipe.  This may limit throughput and will result in restrictions based on customer nominations.  Customers may experience pressure fluctuations during this timeframe.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928271","***","TBD","TBD","Project Canceled",null,null,"MLV 555-1 to 550-1",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.1,"(X15-928271) MLV 555-1 to 550-1:  ILI/Cleaning Pig (TBD)","***MLV 555-1 to 550-1:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-1 to 550-1:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928272","***","TBD","TBD","Project Canceled",null,null,"MLV 555-2 to 550-2",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.20000000000005,"(X15-928272) MLV 555-2 to 550-2:  ILI/Cleaning Pig (TBD)","***MLV 555-2 to 550-2:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-2 to 550-2:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928273","***","TBD","TBD","Project Canceled",null,null,"MLV 555-3 to 552-3",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.29999999999995,"(X15-928273) MLV 555-3 to 552-3:  ILI/Cleaning Pig (TBD)","***MLV 555-3 to 552-3:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-3 to 552-3:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-882281","***","2016-02-24","2016-03-03","Project Completed",null,null,"24-1A to 25-1S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.1,"(X15-882281) 24-1A to 25-1S:  Anomaly Remediation (2/24/16 to 3/3/16)","***24-1A to 25-1S:  Anomaly Remediation\n--2/24/16 through 3/3/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***24-1A to 25-1S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-882291","***","2016-03-03","2016-03-04","Project Completed",null,null,"MLV 24-3 to 25-3S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.3,"(X15-882291) MLV 24-3 to 25-3S:  Anomaly Remediation (3/3/16 to 3/4/16)","***MLV 24-3 to 25-3S:  Anomaly Remediation\n--3/3/16 through 3/4/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 24-3 to 25-3S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X14-1178175","***","2015-06-15","2016-03-31","Project Completed",null,null,"Station 63","100","1","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,63,"(X14-1178175) Station 63:  Station Maintenance (6/15/15 to 3/31/16)","***Station 63:  Station Maintenance\n--6/15/15 through 3/31/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Station 63:  Station Maintenance\n***Project Completed\n………………………………"]
["","Project Cancelled","X15-913224","***","2016-04-16","2016-05-21","Project Cancelled",null,null,"MLV 109-2",100,2,"Pipe Replacement","This project will require taking the pipeline section out of service.   This will limit throughput and will result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",109.2,"(X15-913224) MLV 109-2:  Pipe Replacement (4/16/16 to 5/21/16)","***MLV 109-2:  Pipe Replacement\n--4/16/16 through 5/21/16:  This project will require taking the pipeline section out of service.   This will limit throughput and will result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Cancelled\n………………………………","***MLV 109-2:  Pipe Replacement\n***Project Cancelled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-926830","***","2016-03-07","2016-03-11","Project Completed",null,null,"MLV 400-1 to 408-1",100,0,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.","To Be Determined",400.1,"(X15-926830) MLV 400-1 to 408-1:  ILI/Cleaning Pig (3/7/16 to 3/11/16)","***MLV 400-1 to 408-1:  ILI/Cleaning Pig\n--3/7/16 through 3/11/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 400-1 to 408-1:  ILI/Cleaning Pig\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Cancelled","X16-143836","***","2016-03-28","2016-04-04","Project Cancelled",null,null,"Sta. 409",100,0,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.",null,409,"(X16-143836) Sta. 409:  Unit  Maintenance (3/28/16 to 4/4/16)","***Sta. 409:  Unit  Maintenance\n--3/28/16 through 4/4/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\n***Project Cancelled\n………………………………","***Sta. 409:  Unit  Maintenance\n***Project Cancelled\n………………………………"]
["","Project Cancelled","X15-929680","***","2016-04-18","2016-04-27","Project Cancelled",null,null,"SABINE - KINDER LINE to 822-1",800,"L","Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",822.1,"(X15-929680) SABINE - KINDER LINE to 822-1:  Anomaly Remediation (4/18/16 to 4/27/16)","***SABINE - KINDER LINE to 822-1:  Anomaly Remediation\n--4/18/16 through 4/27/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Cancelled\n………………………………","***SABINE - KINDER LINE to 822-1:  Anomaly Remediation\n***Project Cancelled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]

{"sheet":"Sheet1","index":1,"n_rows":105,"n_cols":24,"rows_kept":105,"cut":false,"hidden":false,"merged":[[2,0,2,14]]}
["Updated ","2026-04-16"]
["Southern Natural Gas Pipeline 2026 Pipeline Outage and Maintenance Summary"]
["This is a summary of the current status of SNG Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  \nAdditionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Southern Natural Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
["*** Indicates revision"]
["Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","System","Zone","Segment","Location","Maintenance Activity","Anticipated Impact","Potential Restriction Level","Meter(s) in Impacted Area","ref_notes",null,null,null,null,null,null,null,"\\\\houCORP\\TRANS\\TRANSERVICES\\OPPLAN\\COMMON\\Outages\\Outage_DB\\SNG"]
["X26-60669",null,"2025-07-08","2026-10-31",null,null,null,"South","1","420","Bay Springs Compressor Station","Scheduled Unit Maintenance\nProj-52161","This project will require taking a unit out of service, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path Services may be necessary.","OP"]
["X25-1474560",null,"2025-12-04","2026-04-26",null,null,null,"South","2","440","Gallion Compressor Station","Unscheduled Unit Maintenance\nProj-52366","This unscheduled unit maintenance will require taking a unit out of service, however, we do not anticipate an impact to customers at this time."]
["X26-39800",null,"2025-12-22","2026-05-31",null,null,null,"South","2","460","Selma Compressor Station","Unscheduled Unit Maintenance\nProj-52301","This unscheduled unit maintenance will require taking a unit out of service, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path nominations may become necessary.","OP"]
["X25-1492697","***","2026-03-09","2026-04-16","Completed",null,"2026-04-19","North","2","130","Tarrant Compressor Station","Scheduled Unit Maintenance\nProj-415212","This project will require taking a unit out of service, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path Services may be necessary.","OP",null,"------"]
["X26-60435",null,"2026-03-16","2026-05-15",null,null,null,"South","1","430","Enterprise Compressor Station","Scheduled Unit Maintenance\nProj-522212","This project will require taking a unit out of service, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path Services may be necessary.","OP"]
["X25-1474705",null,"2026-03-23","2026-04-17",null,null,null,"South","3","655","Holy Trinity Compressor Station","Scheduled Unit Maintenance\nProj-58051-2","This project will require taking a unit out of service, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path Services may be necessary.","OP"]
["X22-1123696","***","2026-03-30","2026-04-23","Project Change",null,"2026-04-17","North","2","150","Dearmanville Compressor Station","Scheduled Pipeline Maintenance(PT)\nProj-SNG-15344(HS)","This project will require taking the pipeline segment out of service which could limit throughput and based on system demand, an impact to Interruptible and Out of Path nominations may become necessary.","OP",null,"----end_date--------------model_loc--"]
["X26-34130","***","2026-04-01","2026-05-18","Project Change",null,"2026-05-09","North","2","120","Bessemer Calera Line north of Helena Regulator","Scheduled Pipeline Maintenance\nProj-SNG-38163(PT)","This project will require taking the pipeline segment out of service which could limit throughput and based on system demand, an impact to Interruptible and Out of Path nominations may become necessary.","OP",null,"----end_date--------------model_loc--"]
["X26-78345",null,"2026-04-06","2026-04-19",null,null,null,"South","1","400","Gwinville Compressor Station","Scheduled Unit Maintenance\nProj-52112","This project will require taking a unit out of service, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path Services may be necessary.","OP"]
["X19-548324","***","2026-04-06","2026-04-09","Completed",null,null,"South","1","430","Enterprise Compressor Station","Scheduled Unit Maintenance\nProj-5222-8-9-10","This project will require taking a unit out of service, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path Services may be necessary.","OP",null,"------"]
["X24-45833",null,"2026-04-06","2026-05-24",null,null,null,"South","3","530","Ocmulgee Compressor Station","Scheduled Unit Maintenance\nProj-52775","This project will require taking a unit out of service, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path Services may be necessary.","OP"]
["X25-1516464","***","2026-04-07","2026-04-13","Completed",null,null,"North","1","60","Muldon Storage Facilities","Spring Shut In Test","This project will require taking the facility out of service. This will limit throughput and may result in restrictions based on customer nominations.","To the extent total storage demand exceeds Southern’s injection abilities, restrictions will be made first into ISS nominations and if necessary, into CSS, not to exceed a reduction to each CSS customers account of more than thirty six percent (36%) of their currently effective DIQ and DWQ.",null,"------"]
["X24-871347",null,"2026-04-08","2026-04-17",null,null,null,"North","2","150","Dearmanville Compressor Station","Scheduled Pipeline Maintenance(PT)\nProj-SNG-15344","This project will require taking the pipeline segment out of service which could limit throughput and based on system demand, an impact to Interruptible and Out of Path nominations may become necessary.","OP"]
["X24-1054258","***","2026-04-08","2026-04-16","Completed",null,null,"South","3","570","South Main loop line east of Wrens","Pigging\nBrush/Gauge---4-8-26\nCAL/IMU---4-9-26\nMFL-C--4-14-26\nEMAT---4-16-26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,"932400 - PCS NITROGEN","------"]
["X24-428775","***","2026-04-13","2026-04-17","Project Change","2026-04-16","2026-04-25","South","3","490","South Main 2nd loop line west of Ellerslie","Scheduled Pipeline Maintenance(valve replacement)\nProj-SNG-24946-11","This project will require taking the pipeline segment out of service however, we will be utilizing a stopple bypass. No impact to customers is anticipated at this time.",null,null,"--start_date--end_date--------------model_loc--"]
["X26-51746","***","2026-04-14","2026-04-14","Completed",null,null,"South","3","500","Upson County line north of Thomaston","Pigging\nBrush/Gauge/Combo--4-14-26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated at this time.",null,null,"------"]
["X26-94870","***","2026-04-16","2026-08-10","Project Change","2026-04-13",null,"South LA","0","350","Franklinton Compressor Station","Scheduled Unit Maintenance\nProj-512215","This project will require taking a unit out of service; however, we do not anticipate an impact to customers at this time.",null,null,"--start_date----------------model_loc--"]
["X26-228625",null,"2026-04-16","2026-04-17",null,null,null,"South","1","380","SESH","Scheduled Maintenance","SESH pipeline's operator notified Southern that it will be conducting planned Compressor Station and/or Unit maintenance. Interruptible, Out of Path Services or In Path may be impacted.","IP","606400 SESH - ENABLE TO SNG \n606500 SESH - GULF SOUTH TO SNG \n606700 SESH - ETC TIGER TO SNG"]
["X26-417558",null,"2026-04-16","2026-04-17",null,null,null,"South","1","380","SESH","Pigging--4-16-26 to 4-17-26","SESH pipeline's operator notified Southern that it will be conducting pigging operations. This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated at this time.",null,"606400 SESH - ENABLE TO SNG \n606500 SESH - GULF SOUTH TO SNG \n606700 SESH - ETC TIGER TO SNG"]
["X26-158840",null,"2026-04-20","2026-05-03",null,null,null,"South","1","400","Gwinville Compressor Station","Scheduled Unit Maintenance\nProj-52112","This project will require taking a unit out of service, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path Services may be necessary.","OP"]
["X26-468734","***","2026-04-20","2026-04-29","Added",null,null,"South","1","430","Enterprise Compressor Station","Scheduled Unit Maintenance\nProj-5222-16","This project will require taking a unit out of service, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path Services may be necessary.","OP",null,"------"]
["X26-54627",null,"2026-04-20","2026-04-20",null,null,null,"South","2","460","Auburn Compressor Station","Scheduled Unit Maintenance\nProj-52593","This project will require taking a unit out of service, which could(will) limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path Services may be necessary.","OP"]
["X26-101903",null,"2026-04-20","2026-05-24",null,null,null,"South","3","560","Hall Gate Compressor Station","Scheduled Unit Maintenance\nProj-52833","This project will require taking a unit out of service, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path Services may be necessary.","OP"]
["X22-1207875",null,"2026-04-20","2026-04-21",null,null,null,"South","3","570","Wrens Compressor Station","Scheduled Unit Maintenance\nProj-52881-2-3","This project will require taking multiple units out of service, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path Services may be necessary.","OP"]
["X25-1553775","***","2026-04-21","2026-04-29","Added",null,null,"South","2","440","Demopolis line west of Gallion","Scheduled Pipeline Maintenance(direct assessment)\nProj-SNG-9166","This project will require visual inspections of the pipeline, and possible remediation; however, we do not anticipate an impact to customers at this time.",null,null,"------"]
["X26-54625",null,"2026-04-21","2026-04-21",null,null,null,"South","2","460","Elmore Compressor Station","Scheduled Unit Maintenance\nProj-525112","This project will require taking a unit out of service, which could(will) limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path Services may be necessary.","OP"]
["X23-728014",null,"2026-04-21","2026-04-23",null,null,null,"North","1","50","North Main line east of Pickens","Pigging\nBrush/Gauge--4-21-26\nCAL/IMU/MFL-A--4-23-26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated."]
["X26-39954","***","2026-04-21","2026-05-04","Project Change","2026-04-23","2026-05-03","South","3","570","South Main loop AUX line east of Wrens","Scheduled Pipeline Maintenance\nProj-291152R","This project will require taking the pipeline segment out of service; however, we will be utilizing a stopple by-pass. We do not anticipate an impact to customers at this time.",null,null,"--start_date--end_date--------------model_loc--"]
["X26-60484",null,"2026-04-21","2026-04-22",null,null,null,"South","3","570","Wrens Compressor Station","Scheduled Unit Maintenance\nProj-52884","This project will require taking a unit out of service, which could(will) limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path Services may be necessary.","OP"]
["X26-54623",null,"2026-04-22","2026-04-22",null,null,null,"South","2","460","Selma Compressor Station","Scheduled Unit Maintenance\nProj-52453","This project will require taking a unit out of service, which could(will) limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path Services may be necessary.","OP"]
["X26-54621",null,"2026-04-23","2026-04-23",null,null,null,"South","2","440","Gallion Compressor Station","Scheduled Unit Maintenance \nProj-523610","This project will require taking a unit out of service, which could(will) limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path Services may be necessary.","OP"]
["X24-675014",null,"2026-04-23","2026-04-28",null,null,null,"South","2","460","South Main 2nd loop line east of Elmore","Scheduled Pipeline Maintenance(valve replacement)\nProj-SNG-24946-18","This project will require taking the pipeline segment out of service however, we will be utilizing a stopple bypass. No impact to customers is anticipated at this time."]
["X26-60494",null,"2026-04-23","2026-04-24",null,null,null,"South","3","570","Wrens Compressor Station","Scheduled Unit Maintenance\nProj-52885","This project will require taking a unit out of service, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path Services may be necessary.","OP"]
["X26-54280",null,"2026-04-24","2026-05-03",null,null,null,"South","1","430","South Main 2nd loop line east of Enterprise","Scheduled Pipeline Maintenance\nProj-SNG-8792","This project will require taking the pipeline segment out of service which could limit throughput and based on system demand, an impact to Interruptible and Out of Path nominations may become necessary.","OP"]
["X26-54617",null,"2026-04-24","2026-04-24",null,null,null,"South","2","440","York Compressor Station","Scheduled Unit Maintenance\nProj-52303","This project will require taking a unit out of service, which could(will) limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path Services may be necessary.","OP"]
["X22-497742",null,"2026-04-27","2026-05-10",null,null,null,"South","2","440","Gallion Compressor Station","Scheduled Unit Maintenance\nProj-52369","This project will require taking a unit out of service, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path Services may be necessary.","OP"]
["X24-1054252",null,"2026-04-27","2026-05-01",null,null,null,"South","2","440","South Main loop line east of Gallion","Scheduled Pipeline Maintenance(remediation)\nProj-SNG-22002","This project will require taking the pipeline segment out of service which could(will) limit throughput and based on system demand, an impact to Interruptible and Out of Path nominations may become necessary.","OP"]
["X26-460324","***","2026-04-27","2026-05-11","Added",null,null,"South","3","490","Thomaston Compressor Station","Scheduled Unit Maintenance\nProj-5272-5","This project will require taking a unit out of service, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path Services may be necessary.","OP",null,"------"]
["X25-1225557",null,"2026-04-27","2026-05-01",null,null,null,"North","1","50","Louisville Compressor Station","Scheduled Unit Maintenance\nProj-4132LS","This project will require taking a unit out of service, which could limit throughput through the station and customers may experience lower than normal pressures. Based on system demand, an impact to Interruptible and Out of Path Services may be necessary.","OP"]
["X26-438645","***","2026-04-28","2026-04-29","Project Change","2026-04-17","2026-04-18","North","2","120","Bessemer Calera line and loop line north of Helena Regulator","Scheduled Pipeline Maintenance\nProj-SNG-38163(M/S)","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter(s) listed will be shut in during the project.",null,"Ala Genery Gap MS (830400)","--start_date--end_date--------------model_loc--"]
["X25-1508278",null,"2026-04-28","2026-05-07",null,null,null,"South","3","680","Line-2 Main Line south of Albany","Pigging\nBrush/Gauge--4-28-26\nCAL--4-30-26\nMFL-C--5-5-26\nEMAT--5-7-26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated at this time."]
["X26-438674","***","2026-04-30","2026-05-09","Project Change","2026-04-22","2026-04-29","North","2","120","Bessemer Calera line and loop line north of Helena Regulator","Scheduled Pipeline Maintenance\nProj-SNG-38163(M/S)","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter(s) listed will be shut in during the project.",null,"Ala - Helena # 2 (831000)","--start_date--end_date--------------model_loc--"]
["X26-417965",null,"2026-05-04","2026-05-04",null,null,null,"South","1","380","SESH","Scheduled Maintenance","SESH pipeline's operator notified Southern that it will be conducting planned Compressor Station and/or Unit maintenance. Interruptible, Out of Path Services or In Path may be impacted.","IP","606400 SESH - ENABLE TO SNG \n606500 SESH - GULF SOUTH TO SNG \n606700 SESH - ETC TIGER TO SNG"]
["X25-77545",null,"2026-05-04","2026-05-06",null,null,null,"South","2","440","South Main line east of Gallion","Scheduled Pipeline Maintenance(remediation)\nProj-SNG-19219(1)","This project will require taking the pipeline segment out of service which could limit throughput and based on system demand, an impact to Interruptible and Out of Path nominations may become necessary.","OP"]
["X20-973429",null,"2026-05-04","2026-05-08",null,null,null,"South","2","460","Elmore Compressor Station","Scheduled Unit Maintenance\nProj-5251B","This project will require taking a unit out of service, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path Services may be necessary.","OP"]
["X25-1516486",null,"2026-05-05","2026-05-11",null,null,null,"North","0","20","Bear Creek Storage Facilities","Spring Shut In Test","This project will require taking the facility out of service. This will limit throughput and may result in restrictions based on customer nominations.","To the extent total storage demand exceeds Southern’s injection abilities, restrictions will be made first into ISS nominations and if necessary, into CSS, not to exceed a reduction to each CSS customers account of more than thirty six percent (64%) of their currently effective DIQ and DWQ."]
["X26-418051",null,"2026-05-05","2026-05-05",null,null,null,"South","1","380","SESH","Scheduled Maintenance","SESH pipeline's operator notified Southern that it will be conducting planned Compressor Station and/or Unit maintenance. Interruptible, Out of Path Services or In Path may be impacted.","IP","606400 SESH - ENABLE TO SNG \n606500 SESH - GULF SOUTH TO SNG \n606700 SESH - ETC TIGER TO SNG"]
["X26-53636",null,"2026-05-05","2026-05-07",null,null,null,"South","3","710","Line-53 East Hamilton line, Line-54 Occidental Line south of Pavo","Pigging\nBrush/Gauge--5-5-26\nCAL/IMU--5-6-26\nMFL-C--5-7-26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated at this time."]
["X26-418061",null,"2026-05-06","2026-05-06",null,null,null,"South","1","380","SESH","Scheduled Maintenance","SESH pipeline's operator notified Southern that it will be conducting planned Compressor Station and/or Unit maintenance. Interruptible, Out of Path Services or In Path may be impacted.","IP","606400 SESH - ENABLE TO SNG \n606500 SESH - GULF SOUTH TO SNG \n606700 SESH - ETC TIGER TO SNG"]
["X26-282566",null,"2026-05-07","2026-05-12",null,null,null,"South","2","440","South Main line west of Selma","Scheduled Pipeline Maintenance(remediation)\nProj-SNG-19219(2)","This project will require taking the pipeline segment out of service which could limit throughput and based on system demand, an impact to Interruptible and Out of Path nominations may become necessary.","OP"]
["X26-418082",null,"2026-05-11","2026-05-11",null,null,null,"South","1","380","SESH","Scheduled Maintenance","SESH pipeline's operator notified Southern that it will be conducting planned Compressor Station and/or Unit maintenance. Interruptible, Out of Path Services or In Path may be impacted.","IP","606400 SESH - ENABLE TO SNG \n606500 SESH - GULF SOUTH TO SNG \n606700 SESH - ETC TIGER TO SNG"]
["X25-1338630",null,"2026-05-11","2026-05-21",null,null,null,"South","2","440","Gallion Compressor Station","Scheduled Unit Maintenance\nProj-52368","This project will require taking a unit out of service, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path Services may be necessary.","OP"]
["X26-161801",null,"2026-05-11","2026-05-13",null,null,null,"South","2","460","Auburn Compressor Station","Scheduled Unit Maintenance\nProj-52593","This project will require taking a unit out of service, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path Services may be necessary.","OP"]
["X24-1146697",null,"2026-05-11","2026-06-04",null,null,null,"South","3","490","Thomaston Compressor Station","Scheudled Unit Maintenance\nProj-52722","This project will require taking a unit out of service, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path Services may be necessary.","OP"]
["X25-1508277",null,"2026-05-12","2026-05-13",null,null,null,"North","2","120","North Main Loop line west of Tarrant","Pigging\nBrush/Gauge/CAL--5-12-26\nMFL-C--5-13-26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated at this time."]
["X26-418101",null,"2026-05-12","2026-05-12",null,null,null,"South","1","380","SESH","Scheduled Maintenance","SESH pipeline's operator notified Southern that it will be conducting planned Compressor Station and/or Unit maintenance. Interruptible, Out of Path Services or In Path may be impacted.","IP","606400 SESH - ENABLE TO SNG \n606500 SESH - GULF SOUTH TO SNG \n606700 SESH - ETC TIGER TO SNG"]
["X25-1554235",null,"2026-05-12","2026-05-14",null,null,null,"South","2","460","South Main 2nd loop line west of Elmore","Pigging\nBrush/Gauge--5-12-26\nCaliper/MFL-C/IMU--5-13-26\nEMAT--5-14-26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated at this time."]
["X25-1492707",null,"2026-05-14","2026-05-16",null,null,null,"South","2","460","Elmore Compressor Station","Scheduled Unit Maintenance\nProj-525112","This project will require taking a unit out of service, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path Services may be necessary.","OP"]
["X26-418115",null,"2026-05-17","2026-05-17",null,null,null,"South","1","380","SESH","Scheduled Maintenance","SESH pipeline's operator notified Southern that it will be conducting planned Compressor Station and/or Unit maintenance. Interruptible, Out of Path Services or In Path may be impacted.","IP","606400 SESH - ENABLE TO SNG \n606500 SESH - GULF SOUTH TO SNG \n606700 SESH - ETC TIGER TO SNG"]
["X26-418153",null,"2026-05-18","2026-05-22",null,null,null,"South","1","380","SESH","Scheduled Maintenance","SESH pipeline's operator notified Southern that it will be conducting planned Compressor Station and/or Unit maintenance. Interruptible, Out of Path Services or In Path may be impacted.","IP","606400 SESH - ENABLE TO SNG \n606500 SESH - GULF SOUTH TO SNG \n606700 SESH - ETC TIGER TO SNG"]
["X25-1516603",null,"2026-05-18","2026-06-21",null,null,null,"South","1","430","Enterprise Compressor Station","Scheduled Unit Maintenance\nProj-522215","This project will require taking a unit out of service, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path Services may be necessary.","OP"]
["X26-161803",null,"2026-05-18","2026-05-20",null,null,null,"South","2","460","Selma Compressor Station","Scheduled Unit Maintenance\nProj-52453","This project will require taking a unit out of service, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path Services may be necessary.","OP"]
["X26-195247",null,"2026-05-18","2026-05-22",null,null,null,"South","2","460","South Main loop line east of Auburn","Scheduled Pipeline Maintenance(remediation)\nProj-SNG-20457(1)","This project will require taking the pipeline segment out of service which could limit throughput and based on system demand, an impact to Interruptible and Out of Path nominations may become necessary.","OP"]
["X24-1054471",null,"2026-05-18","2026-05-21",null,null,null,"South","3","490","Ellerslie Compressor Station","Scheduled Unit Maintenance \nProj-52678-9","This project will require taking a unit out of service, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path Services may be necessary.","OP"]
["X24-957507",null,"2026-05-19","2026-05-21",null,null,null,"South","2","460","Auburn Grantville line east of Auburn","Pigging\nBrush/Gauge--5-19-26\nCAL/IMU/MFL-A--5-21-26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated at this time."]
["X25-1557453",null,"2026-05-19","2026-05-21",null,null,null,"South","2","460","South Main 2nd loop line east of Gallion","Pigging\nBrush/Gauge--5-19-26\nCAL/IMU/MFL-A/--5-21-26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated at this time."]
["X26-161805",null,"2026-05-21","2026-05-23",null,null,null,"South","2","460","York Compressor Station","Scheduled Unit Maintenance\nProj-52303","This project will require taking a unit out of service, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path Services may be necessary.","OP"]
["X26-418170",null,"2026-05-23","2026-05-23",null,null,null,"South","1","380","SESH","Scheduled Maintenance","SESH pipeline's operator notified Southern that it will be conducting planned Compressor Station and/or Unit maintenance. Interruptible, Out of Path Services or In Path may be impacted.","IP","606400 SESH - ENABLE TO SNG \n606500 SESH - GULF SOUTH TO SNG \n606700 SESH - ETC TIGER TO SNG"]
["X24-1054253",null,"2026-05-23","2026-05-29",null,null,null,"South","2","460","South Main loop line east of Auburn","Scheduled Pipeline Maintenance(remediation)\nProj-SNG-20457(2)","This project will require taking the pipeline segment out of service which could limit throughput and based on system demand, an impact to Interruptible and Out of Path nominations may become necessary.","OP"]
["X24-957542","***","2026-05-25","2026-07-04","Project Change","2026-05-16","2026-06-25","North","2","120","Bessemer Calera Line south of Helena Regulator","Scheduled Pipeline Maintenance\nProj-SNG-38163(PT)","This project will require taking the pipeline section out of service and customers may experience lower than normal pressures. All Interruptible and Out of Path services will be impacted, and all priorities of service may be impacted at the meter(s) listed.","IP","SPIREAL/SNG Bessemer Calera South (55087) \nAlabaster #3 (831600)"]
["X24-500934",null,"2026-05-25","2026-05-31",null,null,null,"South","2","440","South Main 2nd loop line east of York","Scheduled Pipeline Maintenance\nProj-SNG-36214","This project will require taking the pipeline segment out of service which could limit throughput and based on system demand, an impact to Interruptible and Out of Path nominations may become necessary.","OP"]
["X26-51570",null,"2026-05-26","2026-05-28",null,null,null,"North","2","120","2nd North Main line east of Providence","Pigging\nBrush/Gauge--5-26-26\nCAL/IMU/MFL-C--5-28-26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated at this time."]
["X19-839400",null,"2026-05-26","2026-05-29",null,null,null,"South","3","580","Wrens Savannah loop line south of Wrens","Pigging\nBrush/Gauge--5-26-26\nCAL/IMU--5-27-26\nMFL-C--5-28-26\nEMAT--5-29-26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated."]
["X23-1194046",null,"2026-06-01","2026-06-09",null,null,null,"South","2","460","South Main loop line east of Auburn","Scheduled Pipeline Maintenance(remediation)\nProj-SNG-22003(1)","This project will require taking the pipeline segment out of service which could limit throughput and based on system demand, an impact to Interruptible and Out of Path nominations may become necessary.","OP"]
["X26-51573","***","2026-06-16","2026-06-19","Project Change","2026-06-02","2026-06-05","North","2","110","2nd North Main loop line west of McConnells","Pigging\nBrush/Gauge--6-16-26\nCaliper/IMU--6-17-26\nMFL-C--6-18-26\nEMAT--6-19-26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated at this time."]
["X23-1227075",null,"2026-06-02","2026-06-11",null,null,null,"South","3","540","Brunswick line south of Ocmulgee","Pigging\nBrush/Gauge--6-2-26\nCAL/IMU--6-4-26\nMFL-C--6-9-26\nEMAT--6-11-26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated at this time."]
["X20-940261",null,"2026-06-09","2026-06-10",null,null,null,"North","2","110","Montgomery Columbus line south of McConnells","Pigging\nBrush/Gauge--6-9-26\nCAL/IMU/MFL-A--6-10-26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated."]
["X25-1554647",null,"2026-06-09","2026-06-11",null,null,null,"South","2","460","South Main 2nd loop line west of Elmore","Pigging\nBrush/Gauge--6-9-26\nCAL/IMU/MFL-C--6-10-26\nEMAT--6-11-26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated at this time."]
["X26-95197",null,"2026-06-10","2026-06-14",null,null,null,"South","2","460","South Main loop line east of Auburn","Scheduled Pipeline Maintenance(remediation)\nProj-SNG-22003(2)","This project will require taking the pipeline segment out of service which could(will) limit throughput and based on system demand, an impact to Interruptible and Out of Path nominations may become necessary.","OP"]
["X24-500929",null,"2026-06-15","2026-06-25",null,null,null,"South","1","410","South Main 2nd loop line west of Bay Springs","Scheduled Pipeline Maintenance\nProj-SNG-36212(1)","This project will require taking the pipeline segment out of service; however, we do not anticipate an impact to customers at this time."]
["X26-51587",null,"2026-06-23","2026-06-27",null,null,null,"North","1","50","North Main loop line west of Louisville","Pigging\nBrush/Gauge--6-23-26\nMFL-A--6-24-26\nResidual--6-27-26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated at this time."]
["X26-124066",null,"2026-07-06","2026-09-13",null,null,null,"North","2","130","Tarrant Compressor Station","Scheduled Unit Maintenance(panel)\nProj-41527-8-9-10-11","This project will require taking a unit out of service, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path Services may be necessary.","OP"]
["X25-1490514","***","2026-07-10","2026-08-24","Project Change","2026-07-01","2026-08-14","North","2","120","Bessemer Calera loop line south of Helena Regulator","Scheduled Pipeline Maintenance\nProj-SNG-38163(PT)","This project will require taking the pipeline section out of service and customers may experience lower than normal pressures. All Interruptible and Out of Path services will be impacted, and all priorities of service may be impacted at the meter(s) listed.","IP","SPIREAL/SNG Bessemer Calera South (55087) \nAlabaster #3 (831600)"]
["X24-1054462",null,"2026-07-14","2026-07-16",null,null,null,"North","2","150","White Plains Line east of Dearmanville","Pigging\nBrush/Gauge--7-14-26\nIMU/CAL/MFL-A--7-16-26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated."]
["X26-438678","***","2026-07-16","2026-07-25","Project Change","2026-07-01","2026-07-08","North","2","120","Bessemer Calera line and loop line south of Helena Regulator","Scheduled Pipeline Maintenance\nProj-SNG-38163(M/S)","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter(s) listed will be shut in during the project.",null,"Alabaster #2 (831500)","--start_date--end_date--------------model_loc--"]
["X25-1557586",null,"2026-07-20","2026-07-24",null,null,null,"South","1","460","South Main line east of Enterprise","Pigging\nBrush/Gauge--7-20-26\nCaliper/MFL-C/IMU--7-22-26\nEMAT--7-24-26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated at this time."]
["X26-438685","***","2026-07-27","2026-08-27","Project Change","2026-07-08","2026-08-05","North","2","120","Bessemer Calera line and loop line south of Helena Regulator","Scheduled Pipeline Maintenance\nProj-SNG-38163(M/S)","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter(s) listed will be shut in during the project.",null,"Alabaster #1 (831400)","--start_date--end_date--------------model_loc--"]
["X26-82692",null,"2026-07-27","2026-08-05",null,null,null,"South","1","420","South Main 2nd loop line west of Enterprise","Scheduled Pipeline Maintenance\nProj-SNG-36212(2)","This project will require taking the pipeline segment out of service; however, we do not anticipate an impact to customers at this time."]
["X25-1553940",null,"2026-07-28","2026-07-30",null,null,null,"South","1","370","Franklinton Gwinville 2nd loop line north of Pearl River","Pigging\nBrush/Gauge--7-28-26\nCaliper/MFL-C/IMU--7-29-26\nEMAT--7-30-26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated at this time."]
["X23-1245030",null,"2026-08-04","2026-08-13",null,null,null,"South","3","750","North Terrell line 6 south of Holy Trinity","Pigging\nChemical Clean--8-4-26\nBrush/Gauge--8-12-26\nCAL/IMU/MFL-C--8-13-26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated at this time."]
["X24-957552","***","2026-08-09","2026-09-11","Project Change","2026-08-20","2026-09-02","North","2","120","Longview Saginaw Lateral east of Providence","Scheduled Pipeline Maintenance\nProj-SNG-4145PT","This project will require taking the pipeline segment out of service; however, we do not anticipate an impact to customers at this time.",null,null,"--start_date--end_date--------------model_loc--"]
["X25-1474674",null,"2026-08-18","2026-08-20",null,null,null,"South","3","490","Ellerslie Compressor Station","Scheduled Station Maintenance\nProj-5267","This project will require taking the station out of service which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path nominations may become necessary.","OP"]
["X26-124120",null,"2026-09-14","2026-09-30",null,null,null,"North","2","130","Tarrant Compressor Station","Scheduled Unit Maintenance(panel)\nProj-415212-13-14","This project will require taking a unit out of service, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path Services may be necessary.","OP"]
["X24-888716",null,"2026-09-14","2026-09-20",null,null,null,"South","2","460","Selma Compressor Station","Scheduled Unit Maintenance\nProj-52453","This project will require taking a unit out of service, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path Services may be necessary.","OP"]
["X25-1557658",null,"2026-09-21","2026-09-25",null,null,null,"South","2","460","South Main loop line east of Elmore","Pigging\nBrush/Gauge--9-21-26\nCaliper/IMU--9-22-26\nMFL-C--9-23-26\nEMAT--9-25-26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated at this time."]
["X25-1554119",null,"2026-10-05","2026-10-08",null,null,null,"North","1","40","North Main 2nd loop line east of Onward","Pigging\nBrush/Gauge--10-5-26\nCaliper/MFL-C/IMU--10-6-26\nEMAT--10-8-26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated at this time."]
["X25-1516484",null,"2026-10-06","2026-10-12",null,null,null,"North","1","60","Muldon Storage Facilities","Fall Shut In Test","This project will require taking the facility out of service. This will limit throughput and may result in restrictions based on customer nominations.","To the extent total storage demand exceeds Southern’s injection abilities, restrictions will be made first into ISS nominations and if necessary, into CSS, not to exceed a reduction to each CSS customers account of more than thirty six percent (36%) of their currently effective DIQ and DWQ."]
["X26-60437",null,"2026-10-12","2026-11-01",null,null,null,"South","2","440","York Compressor Station","Scheduled Unit Maintenance\nProj-52301","This project will require taking a unit out of service, which could limit throughput through the station and based on system demand, an impact to Interruptible and Out of Path Services may be necessary.","OP"]
["X25-1516487",null,"2026-10-20","2026-10-26",null,null,null,"North","0","20","Bear Creek Storage Facilities","Fall Shut In Test","This project will require taking the facility out of service. This will limit throughput and may result in restrictions based on customer nominations.","To the extent total storage demand exceeds Southern’s injection abilities, restrictions will be made first into ISS nominations and if necessary, into CSS, not to exceed a reduction to each CSS customers account of more than thirty six percent (64%) of their currently effective DIQ and DWQ."]
["X26-44672",null,"2026-11-17","2026-11-19",null,null,null,"North","2","120","Bessemer Calera loop line east of Providence","Pigging\nBrush/Gauge--11-17-26\nCAL/IMU--11-18-26\nMFL-C--11-19-26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated at this time."]

{"sheet":"Sheet2","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}

{"sheet":"Sheet3","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}