## Sheet1
Updated | 2023-03-30
Stagecoach Pipeline & Storage Company, LLC 2023 Pipeline Outage and Maintenance Summary
This is a summary of the current status of all Stagecoach Pipeline & Storage Company 2023 Pipeline Outages and Maintenance Projects. This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions. Additionally, anticipated impact and restrictions are subject to change. *Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project. *Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time).
*** Indicates revision
Outage # | Revised | Start Date | End Date | Reason Changed | Prev. Start Date | Prev. End Date | Location | Segment | Zone | Maintenance Activity | Anticipated Impact | Potential Restriction Level | TOS Potential Restrictions | Meter(s) in Impacted Area | Loc |  | \\houCORP\TRANS\TRANSERVICES\OPPLAN\COMMON\Outages\Outage_DB\STAR\Files
X22-641077 |  | 2022-06-27 | 2023-05-19 |  |  |  | Stagecoach Owego Station | 300 | NS | Unit 2 - Motor & Rotor | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. The meter listed below may be limited during the project. |  |  | 201020 SC STORAGE |  | Stagecoach Owego Station: Unit 2 - Motor & Rotor --6/27/22 through 5/19/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. The meter listed below may be limited during the project. 201020 SC STORAGE ………………………………
X23-100963 |  | 2023-04-17 | 2023-04-25 |  |  |  | Stagecoach Owego Station | 300 | NS | Automation Upgrade |  |  |  | 201020 SC STORAGE |  | Stagecoach Owego Station: Automation Upgrade --4/17/23 through 4/25/23: 201020 SC STORAGE ………………………………
X23-100964 |  | 2023-04-17 | 2023-04-25 |  |  |  | Stagecoach Owego Station | 300 | NS | Shut-In Test |  |  |  | 201020 SC STORAGE |  | Stagecoach Owego Station: Shut-In Test --4/17/23 through 4/25/23: 201020 SC STORAGE ………………………………