{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":6,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":14,"n_cols":24,"rows_kept":14,"cut":false,"hidden":false,"merged":[[2,0,2,14]]}
["Updated ","2024-08-08"]
["Stagecoach Pipeline & Storage Company, LLC 2024 Pipeline Outage and Maintenance Summary"]
["This is a summary of the current status of Stagecoach Pipeline & Storage Company Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  \nAdditionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
["*** Indicates revision"]
["Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","Location","Segment","Zone","Maintenance Activity","Anticipated Impact","Potential Restriction Level","TOS Potential Restrictions","Meter(s) in Impacted Area","Loc",null,null,null,null,null,null,null,"\\\\houCORP\\TRANS\\TRANSERVICES\\OPPLAN\\COMMON\\Outages\\Outage_DB\\STAR\\Files"]
["X24-850577","***","2024-08-04","2024-08-20","Added",null,null,"Sta NS1",300,"NS","Unit 1 - VFD Transformer","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below may be limited during the project.","SOP","Potential out of path restrictions may be at risk.","201010  MILL PL/STAGEPS OWEGO TIOGA",null,"------","***Sta NS1:  Unit 1 - VFD Transformer\n--8/4/24 through 8/20/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below may be limited during the project.  Potential out of path restrictions may be at risk.\n201010  MILL PL/STAGEPS OWEGO TIOGA\n***Added\n………………………………"]
["X24-850578","***","2024-08-05","2024-12-30","Added",null,null,"Sta NS2",150,"NS","Unit 1 - VFD Transformer","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below may be limited during the project.","SOP","Potential out of path restrictions may be at risk.","201080 APPLACHA/STAGEPS SC JCT BRADFORD\n421046 STAGEPS/TGP STA 319 OWEGO BRADFORD",null,"------","***Sta NS2:  Unit 1 - VFD Transformer\n--8/5/24 through 12/30/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below may be limited during the project.  Potential out of path restrictions may be at risk.\n201080 APPLACHA/STAGEPS SC JCT BRADFORD\n421046 STAGEPS/TGP STA 319 OWEGO BRADFORD\n***Added\n………………………………"]
["X24-402032","***","2024-08-06","2024-08-06","Completed",null,null,"Sta NS2",150,"NS","Annual Maintenance","This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below may be limited during the project.","SOP","Potential out of path restrictions may be at risk.","201080 APPLACHA/STAGEPS SC JCT BRADFORD\n421046 STAGEPS/TGP STA 319 OWEGO BRADFORD",null,"------","***Sta NS2:  Annual Maintenance\n***Completed\nThe following meters are available for nominations:\n201080 APPLACHA/STAGEPS SC JCT BRADFORD\n421046 STAGEPS/TGP STA 319 OWEGO BRADFORD"]
["X24-616281",null,"2024-08-12","2024-08-12",null,null,null,"Sta NS2",150,"NS","Electrical Maintenance","This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meters listed below may be limited during the project.","SOP","Potential out of path restrictions may be at risk.","201080 APPLACHA/STAGEPS SC JCT BRADFORD\n421046 STAGEPS/TGP STA 319 OWEGO BRADFORD",null,null,"Sta NS2:  Electrical Maintenance\n--8/12/24:  This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meters listed below may be limited during the project.  Potential out of path restrictions may be at risk.\n201080 APPLACHA/STAGEPS SC JCT BRADFORD\n421046 STAGEPS/TGP STA 319 OWEGO BRADFORD\n………………………………"]
["X24-809925",null,"2024-08-16","2024-08-16",null,null,null,"Sta NS2",150,"NS","Electrical Maintenance","This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meters listed below may be limited during the project.","SOP","Potential out of path restrictions may be at risk.","201080 APPLACHA/STAGEPS SC JCT BRADFORD\n421046 STAGEPS/TGP STA 319 OWEGO BRADFORD",null,null,"Sta NS2:  Electrical Maintenance\n--8/16/24:  This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meters listed below may be limited during the project.  Potential out of path restrictions may be at risk.\n201080 APPLACHA/STAGEPS SC JCT BRADFORD\n421046 STAGEPS/TGP STA 319 OWEGO BRADFORD\n………………………………"]
["X24-794465",null,"2024-08-19","2024-12-10",null,null,null,"Stagecoach Owego Station",300,"NS","Unit 3 - Motor Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below may be limited during the project.","SOP","Potential out of path restrictions may be at risk.","201020 SC STORAGE",null,null,"Stagecoach Owego Station:  Unit 3 - Motor Maintenance\n--8/19/24 through 12/10/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below may be limited during the project.  Potential out of path restrictions may be at risk.\n201020 SC STORAGE\n………………………………"]
["X24-258084",null,"2024-09-09","2024-09-13",null,null,null,"Stagecoach Owego Station",300,"NS","Annual ESD Testing and Maintenance","This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below may be limited during the project.","SOP","Potential out of path restrictions may be at risk.","201020 SC STORAGE",null,null,"Stagecoach Owego Station:  Annual ESD Testing and Maintenance\n--9/9/24 through 9/13/24:  This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below may be limited during the project.  Potential out of path restrictions may be at risk.\n201020 SC STORAGE\n………………………………"]
["X24-402029","***","2024-08-06","2024-08-07","Completed","2024-09-23","2024-09-24","Sta NS1",300,"NS","Annual PMs and DOT tasks","This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below may be limited during the project.","SOP","Potential out of path restrictions may be at risk.","201010  MILL PL/STAGEPS OWEGO TIOGA",null,"------","***Sta NS1:  Annual PMs and DOT tasks\n***Completed\nThe following meters are available for nominations:\n201010  MILL PL/STAGEPS OWEGO TIOGA"]
["X24-850737","***","2024-11-18","2024-11-22","Added",null,null,"Stagecoach Owego Station",300,"NS","Shut-In Test","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","201020 SC STORAGE",null,"------","***Stagecoach Owego Station:  Shut-In Test\n--11/18/24 through 11/22/24:  This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.  Potential out of path restrictions may be at risk.\n201020 SC STORAGE\n***Added\n………………………………"]