{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["Export"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":2,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Export","index":0,"n_rows":499,"n_cols":16,"rows_kept":499,"cut":false,"hidden":false,"merged":[[2,1,2,15]]}
[null,"Updated ","2018-04-19"]
[null,"Tennessee Gas Pipeline 2018 Pipeline Outage and Maintenance Summary"]
[null,"This is a summary of the current status of all TGP 2018 Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  Additionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
[null,"*** Indicates revision"]
["Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","Location","Leg","Zone","Maintenance Activity","Anticipated Impact","Potential Restriction Level","TOS Potential Restrictions","Meter(s) in Impacted Area","Loc"]
["X17-839882","","2018-01-18T09:58:00","2018-06-15T09:58:00",null,null,null,"MLV 1-1D to MLV 9-1S",100,"0","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.  The meters listed below will be shut-in for the duration of the project.","SIP","Potential in the path restrictions may be at risk.","421083 – DEVON GS/TGP PORT OF VICTORIA: DIP",1.0099999904632568]
["X17-852571","***","2018-05-15T13:26:00","2018-05-24T13:26:00","Date Change","5/15/2018","5/25/2018","MLV 1-2 to MLV 5-2",100,"0","Pig runs  - Cleaning 5/15/18, Cleaning 5/16/18, Gauge 5/17/18, MFL 5/24/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  For up to 3 hours during the pig run, the NET meter (47799) will be fed from line 1 only, the Shoup meter (412669) will be shut-in completely.","SIP","Potential in the path restrictions may be at risk.","47799   NET MEXI/TGP GILLRINA ROAD NUECES\n412669  ETP/TGP SHOUP NUECES",1.2000000476837158]
["X17-914204","","2018-03-13T10:35:00","2018-05-01T10:35:00",null,null,null,"MLV 2-1 to MLV 4-1",100,"0","Pressure Weld Replacement","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,2.0999999046325684]
["X18-109152","","2018-03-12T05:41:00","2018-04-30T05:41:00",null,null,null,"Sta 3A",100,"0","New Station Tie-In (100-1 line)","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,3.0999999046325684]
["X18-37920","","2018-05-07T06:00:00","2018-05-14T18:00:00",null,null,null,"Sta 3A",100,"0","New Station Tie-In (100-2 line)","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,3.2000000476837158]
["X17-852537","","2018-07-09T12:51:00","2018-07-26T12:51:00",null,null,null,"MLV 5-2 to MLV 8-2",100,"0","Pig runs  - Cleaning 7/9/18, Cleaning 7/18/18, Gauge 7/19/18, MFL 7/24/18, Hard Spot 7/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,5.1999998092651367]
["X17-914205","","2018-04-14T10:37:00","2018-06-15T10:37:00",null,null,null,"MLV 10-1 to MLV 12-1",100,"0","Pressure Weld Replacement","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,10.100000381469727]
["X18-109154","","2018-05-01T05:46:00","2018-06-15T05:46:00",null,null,null,"Sta 11A",100,"0","New Station Tie-In (100-1 line)","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,11.100000381469727]
["X18-37926","","2018-06-18T06:00:00","2018-06-25T18:00:00",null,null,null,"Sta 11A",100,"0","New Station Tie-In (100-2 line)","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,11.199999809265137]
["X18-110962","","2018-05-05T10:41:00","2018-05-12T10:41:00",null,null,null,"MLVS 14E-100",100,"0","Line Lowering","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.  The meter listed below will be shut-in for the duration of the project.","SOP","Potential out of path restrictions may be at risk.","410144 CPNOPROC/TGP UDP HCP COLORADO",14]
["X18-110959","","2018-05-17T10:38:00","2018-05-19T10:38:00",null,null,null,"MLVS 15A-100",100,"0","Drip Removal","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.  The meter listed below will be shut-in for the duration of the project.","SOP","Potential out of path restrictions may be at risk.","420162 COKINOS/TGP RAUN FARM 2 TX COLORAD\n420479 COKINOS/TGP CATTLE TX FARM WHARTON\n412023 HGI/TGP UDP ENGLEHARDT COLORADO",15]
["X17-852569","","2018-05-02T13:23:00","2018-05-15T13:23:00",null,null,null,"MLV 17-1S to MLV 20-1",100,"0","Pig runs  - Cleaning 5/2/18, Gauge 5/3/18, MFL 5/10/18, Hard Spot 5/15/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,17.100000381469727]
["X17-852573","","2018-06-12T13:29:00","2018-06-21T13:29:00",null,null,null,"MLV 17-2S to MLV 20-2",100,"0","Pig runs  - Cleaning 6/12/18, Gauge 6/13/18, Geometry 6/19/18, MFL 6/21/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,17.200000762939453]
["X17-852592","","2018-05-22T13:51:00","2018-05-31T13:51:00",null,null,null,"MLV 17-3D to MLV 20-3",100,"0","Pig runs  - Cleaning 5/22/18, Gauge 5/23/18, MFL 5/31/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,17.299999237060547]
["X18-231693","","2018-05-16T05:52:00","2018-05-17T05:52:00",null,null,null,"Sta 25: Station Maintenance",100,"0","Electrical Inspection","This project will require the station outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,25]
["X18-60479","***","2018-03-13T14:00:00","2018-04-16T14:00:00","Completed",null,null,"MLV 25-3D to MLV 27-3",100,"0","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.  The meter listed below will be shut-in for the duration of the project.","SOP","Potential out of path restrictions may be at risk.","400448 – CICO/TGP MERCY GU 1 LIBERTY",25.299999237060547]
["X18-60483","","2018-04-17T14:06:00","2018-04-21T14:06:00",null,null,null,"MLV 27-3A to 28-3",100,"0","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,27.299999237060547]
["X18-60484","","2018-04-19T14:08:00","2018-04-30T14:08:00",null,null,null,"MLV 28-3 to 30-3",100,"0","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.  The meter listed below will be shut-in for the duration of the project.","SOP","Potential out of path restrictions may be at risk.","412738 – TECOGATH/TGP TECO INDIAN SPRINGS PO",28.299999237060547]
["X18-292959","","2018-04-30T06:39:00","2018-05-04T06:39:00",null,null,null,"MLVS 31-1",100,"0","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.  The meter listed below will be shut-in for the duration of the project.","SOP","Potential out of path restrictions may be at risk.",null,31.100000381469727]
["X17-839891","","2018-06-04T10:17:00","2018-07-27T10:17:00",null,null,null,"MLV 32-1 to MLV 34-1",100,"0","Spike Test","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,33]
["X18-99331","","2019-01-07T11:40:00","2019-03-01T11:40:00",null,null,null,"MLVS 36-1",100,"0","Pipe Replacement and Install New Valve","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,36.099998474121094]
["X18-99333","","2018-10-22T11:45:00","2018-12-28T11:45:00",null,null,null,"MLVS 36-2",100,"0","Pipe Replacement and Install New Valve","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,36.200000762939453]
["X18-99335","","2018-08-13T11:48:00","2018-10-19T11:48:00",null,null,null,"MLVS 36-3",100,"0","Pipe Replacement and Install New Valve","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,36.299999237060547]
["X17-839890","***","2018-02-12T10:11:00","2018-04-13T10:11:00","Completed",null,null,"MLV 40-2 to MLV 41-2",100,"1","Spike Test","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,40]
["X17-852470","","2018-07-10T10:34:00","2018-07-19T10:34:00",null,null,null,"MLV 40-1D to MLV 47-1",100,"1","Pig runs  - Cleaning & Gauge 7/10/18-7/13/18, DEF Inspection 7/17/18, TDW MDS 7/19/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,40.099998474121094]
["X17-852400","","2018-09-10T08:18:00","2018-11-30T08:18:00",null,null,null,"MLV 40-3S to MLV 47-3",100,"1","Make Piggable","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,40.299999237060547]
["X18-99207","","2018-04-24T08:09:00","2018-05-01T08:09:00",null,null,null,"Beer Creek Storage",100,"1","Shut In Test","This project will require taking the facility out of service.  This will limit throughput and may result in restrictions based on customer nominations.   The meter listed below will be shut-in for the entire duration of the project.","SOP","Potential out of path restrictions may be at risk.","460017 STORAGE – BEAR CREEK",43]
["X17-852484","","2018-06-05T10:51:00","2018-06-14T10:51:00",null,null,null,"MLV 42-2 to MLV 47-2",100,"1","Pig runs  - Cleaning & Gauge 6/5/18-6/8/18, DEF Inspection 6/12/18, TDW MDS 6/14/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,47.200000762939453]
["X17-852405","","2018-09-24T08:32:00","2018-10-04T08:32:00",null,null,null,"MLV 54-4 to MLV 63-4",100,"1","Pig runs - AFD 9/24/18, EMAT 10/4/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,54.400001525878906]
["X17-852459","","2018-06-04T10:20:00","2018-06-28T10:20:00",null,null,null,"MLV 63-1 to MLV 69-1",100,"1","Pig runs - Chem Cleaning 6/4/18 to 6/16/18, AFD 6/26/18, EMAT 6/28/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,63.099998474121094]
["X17-852528","","2018-08-02T12:36:00","2018-08-07T12:36:00",null,null,null,"MLV 63-1 to MLV 69-1",100,"1","Pig runs - MFL 8/2/18, Hard Spot 8/7/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,63.099998474121094]
["X17-852469","","2018-07-20T10:30:00","2018-07-26T10:30:00",null,null,null,"MLV 63-3 to MLV 71-3",100,"1","Pig runs - Chem Cleaning 7/20/18, Gauge Plate 7/23/18, Caliper 7/24/18, MDS 7/26/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,63.299999237060547]
["X17-852408","","2018-10-06T08:39:00","2018-10-25T08:39:00",null,null,null,"MLV 63-4D to MLV 71-4",100,"1","Pig runs - AFD 10/6/18, EMAT 10/25/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,63.400001525878906]
["X18-310415","","2018-02-01T07:58:00","2018-05-15T07:58:00",null,null,null,"MLVS 65-1",100,"1","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,65]
["X17-852534","","2018-08-13T12:44:00","2018-08-16T12:44:00",null,null,null,"MLV 77-1 to MLV 79-1",100,"1","Pig runs - Chem Cleaning 8/20/18, AFD 8/21/18, EMAT 8/22/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,77.099998474121094]
["X18-310417","***","2018-01-23T08:02:00","2018-06-04T08:02:00","Date Change","1/23/2018","5/31/2018","MLVS 83-2",100,"1","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,83]
["X17-858905","***","2018-04-18T12:58:00","2018-04-18T12:58:00","Completed",null,null,"Sta 87",100,"2","Annual ESD Test","This project will require the station outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,87]
["X18-293073","","2018-06-18T10:05:00","2018-07-13T10:05:00",null,null,null,"Sta 87: Unit 1E",100,"2","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,87.599998474121094]
["X18-225447","","2018-04-02T06:55:00","2018-06-29T06:55:00",null,null,null,"Sta 106: Unit 1C",100,"2","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,106.33000183105469]
["X18-296849","","2018-05-21T09:03:00","2018-05-31T09:03:00",null,null,null,"MLVS 107-7",100,"2","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,107.69999694824219]
["X17-857411","","2018-06-18T14:02:00","2018-06-22T14:02:00",null,null,null,"Sta 110",100,"2","Annual ESD Test","This project will require the station outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,110]
["X17-852527","","2018-07-10T12:30:00","2018-07-17T12:30:00",null,null,null,"MLV 110-2 to MLV 114-2",100,"2","Pig runs  - Cleaning / Gauge 7/10/18, MFL 7/12/18, Hard Spot Tool 7/17/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.    The meters listed below will be shut-in for a brief period of time during the pig run.","SOP","Potential out of path restrictions may be at risk.","412742 BIGSANDY/TGP GLANCY CARTER",110.19999694824219]
["X17-852554","","2018-07-09T13:11:00","2018-07-19T13:11:00",null,null,null,"MLV 110-6 to MLV 114-6",100,"2","Pig runs  - Cleaning / Gauge 7/9/18, MFL 7/19/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,110.59999847412109]
["X17-838136","***","2018-03-20T12:56:00","2018-04-16T12:56:00","Completed",null,null,"MLV 111-3 to MLV 114-3",100,"2","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,111]
["X18-296847","","2018-05-07T08:47:00","2018-05-19T08:47:00",null,null,null,"MLVS 111-2",100,"3","Pipeline Maintenance","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,111.19999694824219]
["X17-852411","","2018-10-10T08:44:00","2018-10-18T08:44:00",null,null,null,"MLV 111-3 to MLV 114-3",100,"2","Pig runs - Cleaning & Gauge Tool 10/10/18, AFD Tool 10/16/18, EMAT 10/18/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,111.30000305175781]
["X17-840017","","2018-05-11T14:57:00","2018-06-22T14:57:00",null,null,null,"MLVS 118-3",100,"3","Make Piggable","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,114]
["X18-310854","","2018-05-07T14:08:00","2018-05-12T14:08:00",null,null,null,"Sta 114: Unit 1C",100,"3","Unit Inspection","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,114.09999847412109]
["X18-310855","","2018-04-30T14:11:00","2018-05-05T14:11:00",null,null,null,"Sta 114: Unit 2C",100,"3","Unit Inspection","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,114.19999694824219]
["X18-310856","","2018-04-23T14:12:00","2018-04-28T14:12:00",null,null,null,"Sta 114: Unit 3C",100,"3","Unit Inspection","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,114.30000305175781]
["X17-904072","","2018-04-16T13:50:00","2018-04-30T13:50:00",null,null,null,"MLV 115-3",100,"3","Pipe Replacement","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,115.30000305175781]
["X17-852575","***","2018-04-25T13:32:00","2018-05-02T13:32:00","Date Change","5/1/2018","5/2/2018","MLV 118-1 to MLV 121-1",100,"3","Pig runs  - Cleaning / Gauge 5/1/18, MFL 5/2/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,118.09999847412109]
["X17-857413","","2018-05-24T14:04:00","2018-05-24T14:04:00",null,null,null,"Sta 200",200,"2","Annual ESD Test","This project will require the station outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,200]
["X18-125274","","2018-05-30T06:07:00","2018-06-06T06:07:00",null,null,null,"MLV 200-1D to MLV 200-1A",200,"2","Drip Removal","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,200]
["X17-852542","","2018-07-12T12:57:00","2018-07-19T12:57:00",null,null,null,"MLV 200-2D to MLV 204-2",200,"4","Pig runs  - Caliper 7/12/18, MFL 7/19/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,200.19999694824219]
["X17-852557","","2018-05-15T13:13:00","2018-05-22T13:13:00",null,null,null,"MLV 200-3A to MLV 200-3",200,"4","Pig runs  - Cleaning / Gauge 5/15/18, MFL 5/17/18, Hard Spot Tool 5/22/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,200.30000305175781]
["X17-857415","","2018-04-23T14:08:00","2018-04-27T14:08:00",null,null,null,"Sta 204",200,"4","Annual ESD Test","This project will require the station outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,204]
["X18-125275","","2018-05-16T06:10:00","2018-05-23T06:10:00",null,null,null,"MLV 204-2D to MLV 205-2",200,"4","Drip Removal","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,204.19999694824219]
["X18-125276","","2018-05-07T06:12:00","2018-05-14T06:12:00",null,null,null,"MLV 204-4BL to MLV 205-4",200,"4","Drip Removal","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,204.39999389648437]
["X17-852544","","2018-08-14T13:04:00","2018-08-16T13:04:00",null,null,null,"MLV 204-4 to MLV 209-4",200,"4","Pig runs  - Cleaning / Gauge 8/14/18, MFL 8/16/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,204.39999389648437]
["X17-857416","","2018-04-30T14:09:00","2018-05-04T14:09:00",null,null,null,"Sta 209",200,"4","Annual ESD Test","This project will require the station outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,209]
["X18-166402","","2018-04-02T05:29:00","2018-07-13T05:29:00",null,null,null,"Sta 209: Unit 1A",200,"4","Foundaton Repair","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,209.10000610351562]
["X17-852513","","2018-06-21T12:13:00","2018-06-28T12:13:00",null,null,null,"MLV 209-1 to MLV 214-1",200,"4","Pig runs  - Cleaning / Gauge 6/21/18, MFL 6/26/18, Hard spot 6/28/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  The meter listed below will be shut-in for a brief period of time during the pig run.","SIP","Potential in the path restrictions may be at risk.","47652 UTICA EO/TGP LEESVILLE PROC PLNT CA",209.10000610351562]
["X17-852515","","2018-07-24T12:16:00","2018-07-31T12:16:00",null,null,null,"MLV 209-3 to MLV 214-3",200,"4","Pig runs  - Cleaning / Gauge 7/24/18, MFL 7/26/18, Hard spot 7/31/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,209.30000305175781]
["X18-216606","***","2018-03-19T15:14:00","2018-04-24T15:14:00","Date Change","3/19/2018","4/13/2018","Sta 209: Unit 5A",200,"4","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,209.5]
["X18-216412","***","2018-03-19T06:29:00","2018-05-18T06:29:00","Date Change","3/19/2018","4/27/2018","Sta 209",200,"4","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,209.99000549316406]
["X17-857417","","2018-05-07T14:11:00","2018-05-14T14:11:00",null,null,null,"Sta 214",200,"4","Annual ESD Test","This project will require the station outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,214]
["X17-840015","","2018-09-17T07:00:00","2018-09-28T17:00:00",null,null,null,"218-2 to 219-2",200,"4","Pipe Replacement","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,214]
["X17-141864","***","2017-03-27T16:07:00","2018-04-23T18:00:00","Date Change","3/27/2017","4/16/2018","Sta. 214-1A",200,"4","Foundation Replacement","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,214.10000610351562]
["X17-852566","","2018-06-05T13:19:00","2018-06-08T13:19:00",null,null,null,"MLV 217A-201.3 to MLV 217A-202.3",200,"4","Pig runs  - Cleaning / Gauge 6/5/18, MFL 6/8/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,217.20100402832031]
["X18-320557","***","2018-05-07T05:29:00","2018-05-11T05:29:00","Added",null,null,"MLVS 217",200,"4","New Meter Hot Taps for Hickory Run","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,217.5]
["X17-852410","","2018-09-25T08:42:00","2018-10-25T08:42:00",null,null,null,"MLV 219-2D to MLV 307-1",300,"4","Pig runs  - Cleaning / Gauge 10/19/18, AFD 10/23/18, EMAT 10/25/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,219.19999694824219]
["X17-852547","","2018-09-11T13:07:00","2018-09-13T13:07:00",null,null,null,"MLV 224-1 to MLV 229-1",200,"4","Pig runs  - Cleaning / Gauge 9/11/18, MFL 9/13/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,224.10000610351562]
["X18-305380","","2018-04-16T10:53:00","2018-04-20T10:53:00",null,null,null,"Sta 229: Unit 1A",200,"5","Turbocharger Replacement","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,229.10000610351562]
["X17-858874","","2018-05-08T10:21:00","2018-05-10T10:21:00",null,null,null,"Sta 230C",200,"5","Annual ESD Test","This project will require the station outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,230]
["X17-838129","","2018-09-17T12:41:00","2018-10-05T12:41:00",null,null,null,"MLV 230-1 to MLV 237-1",200,"5","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,230]
["X18-155121","","2018-07-09T09:06:00","2018-07-18T09:06:00",null,null,null,"230B-101 TO 230B-106",200,"5","Make Piggable","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,230.00999450683594]
["X18-295163","","2018-08-07T15:00:00","2018-08-07T15:00:00",null,null,null,"230B-101 TO 230B-106",200,"5","Make Piggable","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,230.01100158691406]
["X17-840014","","2018-07-19T14:48:00","2018-07-28T14:48:00",null,null,null,"230B-201 TO 230B-206A",200,"5","Make Piggable","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,230.02000427246094]
["X18-295166","","2018-08-14T15:03:00","2018-08-14T15:03:00",null,null,null,"230B-201 TO 230B-206A",200,"5","Make Piggable","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,230.02099609375]
["X18-213117","","2018-05-14T07:22:00","2018-05-18T07:22:00",null,null,null,"Sta 230C: Unit 2A",200,"5","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,230.22000122070312]
["X17-857428","","2018-06-05T14:21:00","2018-06-06T14:21:00",null,null,null,"Sta 233",200,"5","Annual ESD Test","This project will require the station outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,233]
["X18-302554","","2018-06-11T13:23:00","2018-06-14T13:23:00",null,null,null,"Sta 237: Unit 1A",200,"5","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,237.10000610351562]
["X17-852593","","2018-08-06T13:54:00","2018-08-17T13:54:00",null,null,null,"MLV 237-2 to MLV 238-2",200,"5","SCCDA","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,237.19999694824219]
["X18-225574","","2018-09-17T10:58:00","2018-09-22T10:58:00",null,null,null,"MLV 313A-405A to MLV 313A-409",200,"5","Replace Actuators","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.  The meter listed below will be shut-in for the entire duration of the project.","SIP","Potential in the path restrictions may be at risk.","420644 NYSEG/TGP PRATTSBURG SALES STEUBEN\n420746 NYSEG/TGP WALLACE SALES STEUBEN",237.89999389648437]
["X17-857432","","2018-05-17T14:26:00","2018-05-25T14:26:00",null,null,null,"Sta 241",200,"5","Annual ESD Test","This project will require the station outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,241]
["X18-45906","","2018-04-23T11:23:00","2018-04-27T11:23:00",null,null,null,"Sta 241: Unit 1A",200,"5","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,241.10000610351562]
["X18-45911","","2018-04-30T11:26:00","2018-05-11T11:26:00",null,null,null,"Sta 241: Unit 1B",200,"5","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,241.11000061035156]
["X18-45931","","2018-04-23T11:38:00","2018-05-04T11:38:00",null,null,null,"Sta 249: Unit 2B",200,"5","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,241.1199951171875]
["X18-45919","","2018-05-07T11:31:00","2018-05-11T11:31:00",null,null,null,"Sta 245: Unit 1C",200,"5","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,241.21000671386719]
["X18-45914","","2018-05-21T11:29:00","2018-06-01T11:29:00",null,null,null,"Sta 241: Unit 2B",200,"5","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,241.22000122070312]
["X17-857433","","2018-06-11T14:27:00","2018-06-15T14:27:00",null,null,null,"Sta 245",200,"5","Annual ESD Test","This project will require the station outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,245]
["X17-852589","","2018-05-08T13:49:00","2018-05-09T13:49:00",null,null,null,"MLV 245-2D to MLV 249-2",200,"5","Pig runs  - Cleaning / Gauge 5/8/18, Combo 5/9/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,245.19999694824219]
["X17-857434","","2018-05-07T14:30:00","2018-05-07T14:30:00",null,null,null,"Sta 249",200,"5","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,249]
["X18-45933","***","2018-06-18T11:41:00","2018-06-29T11:41:00","Date Change","5/7/2018","5/18/2018","Sta 249: Unit 1A",200,"5","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,249.10000610351562]
["X18-45929","","2018-04-09T11:36:00","2018-04-20T11:36:00",null,null,null,"Sta 249: Unit 1B",200,"5","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,249.11000061035156]
["X18-45934","***","2018-07-09T11:43:00","2018-07-20T11:43:00","Date Change","5/28/2018","6/8/2018","Sta 249: Unit 2A",200,"5","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,249.19999694824219]
["X17-839914","","2018-06-04T10:55:00","2018-07-06T10:55:00",null,null,null,"MLV 252-1 to MLV 252-1",200,"5","Pressure Test","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,252]
["X17-857435","","2018-05-17T14:32:00","2018-05-27T14:32:00",null,null,null,"Sta 254",200,"5","Annual ESD Test","This project will require the station outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,254]
["X18-75371","","2018-05-17T14:50:00","2018-05-27T14:50:00",null,null,null,"Sta 254",200,"5","Station Automation and Maintenance","This project will require the station outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,254]
["X17-839880","","2018-04-02T09:55:00","2018-05-12T09:55:00",null,null,null,"MLV 254-1 to MLV 261-1",200,"5","Remediation - Phase 1","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,254.00100708007813]
["X18-166488","","2018-08-20T08:47:00","2018-10-04T08:47:00",null,null,null,"MLV 254-1 to MLV 261-1",200,"5","Remediation - Phase 2","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,254.00199890136719]
["X17-852414","","2018-05-15T08:51:00","2018-05-16T08:51:00",null,null,null,"MLV 254-2 to MLV 261-2",200,"5","Pig runs  - Cleaning / Gauge 5/15/18, AFD 5/16/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,254.00300598144531]
["X18-155316","","2018-10-23T14:29:00","2018-10-24T14:29:00",null,null,null,"MLV 254-2 to MLV 261-2",200,"5","Pig runs  - Cleaning 10/23/18, EMAT 10/24/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,254.00399780273437]
["X18-110952","","2018-05-28T09:51:00","2018-07-28T09:51:00",null,null,null,"Sta 254: Building A",200,"5","Automation Upgrade - 2 weeks/unit - up to 2 units may be down at a same time","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,254.10000610351563]
["X18-46067","","2018-03-05T11:57:00","2018-06-30T11:57:00",null,null,null,"Sta 254: Unit 2A",200,"5","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,254.19999694824219]
["X18-45935","","2018-05-21T11:45:00","2018-05-25T11:45:00",null,null,null,"Sta 254: Unit 2B",200,"5","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,254.99220275878906]
["X18-255303","***","2018-04-13T12:57:00","2018-04-20T12:57:00","Completed",null,null,"Westfield City Del Meter",200,"6","Meter Maintenance","This project will require taking the meter station out of service.  The meter listed below will be shut-in for the entire duration of the project.",null,null,"420104 WESTFLD/TGP WESTFIELD MA HAMPDEN",260]
["X18-295180","","2018-06-18T15:37:00","2018-06-20T15:37:00",null,null,null,"Sta 261",200,"6","Station Safety System","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in for the entire duration of the project.","SIP","Potential in the path restrictions may be at risk.","420901 SHELL/TGP BERKSHIRE POWER SALES HAM",261]
["X18-295178","","2018-06-06T15:34:00","2018-06-17T15:34:00",null,null,null,"Sta 261: A Building",200,"6","BPS Upgrade","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,261.010009765625]
["X18-295176","","2018-05-27T15:30:00","2018-06-05T15:30:00",null,null,null,"Sta 261: C Building",200,"6","BPS Upgrade","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,261.01998901367187]
["X18-295175","","2018-05-14T15:27:00","2018-05-24T15:27:00",null,null,null,"Sta 261: D Building",200,"6","BPS Upgrade","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,261.02999877929687]
["X18-295170","","2018-05-07T15:11:00","2018-05-26T15:11:00",null,null,null,"Sta 261: D Building",200,"6","Silencer Replacement","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,261.04998779296875]
["X18-201903","***","2018-04-09T07:15:00","2018-04-13T07:15:00","Completed",null,null,"Sta 261: Unit Maintenance",200,"6","Water Wash","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,261.10000610351562]
["X17-854305","","2018-06-18T06:07:00","2018-06-25T06:07:00",null,null,null,"MLV 261BP-101-BERKSHIRE POWER DELIVERY: 1000 - 0+00 to MLV 261BP-101-BERKSHIRE POWER DELIVERY",200,"6","ECDA","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.  The meter listed below will be shut-in for the entire duration of the project.","SOP","Potential out of path restrictions may be at risk.","420901 SHELL/TGP BERKSHIRE POWER SALES HAM",261.10101318359375]
["X18-201906","","2018-04-17T07:19:00","2018-04-20T07:19:00",null,null,null,"Sta 261: Unit Maintenance",200,"6","Boroscope Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,261.20001220703125]
["X18-201904","","2018-09-10T07:18:00","2018-09-14T07:18:00",null,null,null,"Sta 261: Unit Maintenance",200,"6","Water Wash","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,261.29998779296875]
["X18-201907","","2018-09-11T07:20:00","2018-09-13T07:20:00",null,null,null,"Sta 261: Unit Maintenance",200,"6","Boroscope Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,261.29998779296875]
["X18-201913","","2018-09-11T07:33:00","2018-09-14T07:33:00",null,null,null,"Sta 261: Unit 4A",200,"6","Compressor Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,261.39999389648437]
["X18-201899","","2018-05-07T07:13:00","2018-05-11T07:13:00",null,null,null,"Sta 264: Unit 1C",200,"6","Turbine Exchange","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,264.10000610351562]
["X18-201910","","2018-09-12T07:29:00","2018-09-13T07:29:00",null,null,null,"Sta 264: Unit Maintenance",200,"6","Water Wash","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,264.10000610351562]
["X18-201898","","2018-04-30T07:10:00","2018-05-06T07:10:00",null,null,null,"Sta 264: Unit 2C",200,"6","Turbine Exchange","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,264.20001220703125]
["X18-201911","","2018-09-18T07:31:00","2018-09-19T07:31:00",null,null,null,"Sta 264: Unit Maintenance",200,"6","Boroscope Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,264.20001220703125]
["X17-839910","","2018-07-30T10:47:00","2018-08-09T10:47:00",null,null,null,"MLV 265E-201 to MLV 265E-202",200,"6","Pressure Test","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.   The meter listed below will be shut-in for the entire duration of the project.","SOP","Potential out of path restrictions may be at risk.","420758 – NARNGST/TGP LINCOLN SMS PROVIDENCE",265]
["X18-115705","","2018-05-05T08:41:00","2018-05-18T08:41:00",null,null,null,"Sta 265E",200,"6","4000 hr Inspection","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,265.10000610351562]
["X18-115706","","2018-11-05T08:44:00","2018-11-15T08:44:00",null,null,null,"265E",200,"6","4000 hr Inspection","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,265.20001220703125]
["X17-858878","","2018-10-01T10:26:00","2018-10-05T10:26:00",null,null,null,"Sta 266A",200,"6","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,266]
["X17-852588","***","2018-04-17T13:47:00","2018-04-18T13:47:00","Completed",null,null,"MLV 266A-101R to MLV 266A-101L",200,"6","Pig runs  - Cleaning / Gauge 4/17/18, Combo 4/18/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,266.10101318359375]
["X17-852581","","2018-06-19T13:32:00","2018-06-20T13:32:00",null,null,null,"MLV 266C-101.1 to MLV 266C-102",200,"6","Pig runs  - Cleaning / Gauge 6/19/18, Combo 6/20/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,266.10101318359375]
["X17-852586","","2018-04-23T13:43:00","2018-04-24T13:43:00",null,null,null,"MLV 266A-102A to 266A-103R",200,"6","Pig runs  - Cleaning / Gauge 4/23/18, Combo 4/24/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,266.10198974609375]
["X18-115708","","2018-06-11T08:45:00","2018-06-15T08:45:00",null,null,null,"Sta 266A: Unit 1B",200,"6","4000 hr Inspection","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,266.5]
["X17-840013","","2018-07-01T14:43:00","2018-08-31T14:43:00",null,null,null,"267-1",200,"6","Class Change","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,267]
["X17-858814","","2018-08-21T08:57:00","2018-08-22T08:57:00",null,null,null,"Sta 267",200,"6","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,267]
["X17-852524","","2018-05-29T12:27:00","2018-06-04T12:27:00",null,null,null,"MLV 267-1 to MLV 270C-101.1",200,"6","Pig runs  - Cleaning / Gauge 5/29/18, Combo 5/30/18, Hard Spot Tool 6/4/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,267.10000610351562]
["X17-852578","***","2018-04-11T13:34:00","2018-04-12T13:34:00","Completed",null,null,"MLV 267-2 to MLV 273-2",200,"6","Pig runs  - Cleaning / Gauge 4/11/18, Combo 4/12/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,267.20001220703125]
["X17-839896","","2018-07-09T10:25:00","2018-07-19T10:25:00",null,null,null,"MLV 268A-301 to MLV 268A-302",200,"6","Pressure Test","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.   The meter listed below will be shut-in for the entire duration of the project.","SOP","Potential out of path restrictions may be at risk.","420111 – BOSTN/TGP LEOMINSTER MA WORCHESTER",268]
["X17-838155","","2018-05-07T13:34:00","2018-05-16T13:34:00",null,null,null,"MLV 270C-101 to MLV 270C-102",200,"6","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,270]
["X17-838152","","2018-05-18T13:31:00","2018-05-26T13:31:00",null,null,null,"MLV 270C-501 to MLV 270C-502",200,"6","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,270]
["X17-858882","","2018-10-23T10:31:00","2018-10-25T10:31:00",null,null,null,"Sta 270B",200,"6","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,270]
["X17-852530","","2018-06-06T12:39:00","2018-06-12T12:39:00",null,null,null,"MLV 270B-101.1 to MLV 270B-102",200,"6","Pig runs  - Cleaning / Gauge 6/6/18, Combo 6/7/18, Hard Spot Tool 6/12/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,270.10101318359375]
["X17-852585","","2018-05-22T13:43:00","2018-05-23T13:43:00",null,null,null,"MLV 270B-103 to MLV 270B-104",200,"6","Pig runs  - Cleaning / Gauge 5/22/18, Combo 5/23/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,270.10299682617187]
["X17-852570","","2018-04-26T13:26:00","2018-04-27T13:26:00",null,null,null,"MLV 270B-104 to MLV 270B-105",200,"6","Pig runs  - Cleaning / Gauge 4/26/18, Combo 4/27/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,270.10400390625]
["X17-852594","","2018-05-02T13:57:00","2018-05-03T13:57:00",null,null,null,"MLV 270B-105 to MLV 270B-105",200,"6","Pig runs  - Cleaning / Gauge 5/2/18, Combo 5/3/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,270.10501098632812]
["X17-838157","","2018-05-29T13:37:00","2018-06-01T13:37:00",null,null,null,"MLV 273B-101 to MLV 273B-102",200,"6","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,273]
["X17-838158","","2018-06-04T13:39:00","2018-06-16T13:39:00",null,null,null,"MLV 273C-101 to MLV 273C-103",200,"6","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,273]
["X18-99212","","2018-05-21T08:18:00","2018-06-01T08:18:00",null,null,null,"Sta 303A: Unit 1A",300,"4","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,303.10000610351562]
["X17-838122","","2018-07-23T12:10:00","2018-08-10T12:10:00",null,null,null,"MLV 313-1 to MLV 317-1",300,"4","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,313]
["X18-50605","","2018-04-16T15:23:00","2018-04-23T15:23:00",null,null,null,"Ellisburg Storage",300,"4","Shut-In Test","This project will require taking the facility out of service.  This will limit throughput and may result in restrictions based on customer nominations.   The meter listed below will be shut-in for the entire duration of the project.","SOP","Potential out of path restrictions may be at risk.","460012 – DOMINION/TGP ELLISBURG INJECTION PO",313.20999145507812]
["X18-99194","","2018-04-16T07:38:00","2018-04-23T07:38:00",null,null,null,"Hebron Storage",300,"4","Shut In Test","This project will require taking the facility out of service.  This will limit throughput and may result in restrictions based on customer nominations.   The meter listed below will be shut-in for the entire duration of the project.","SOP","Potential out of path restrictions may be at risk.","400485 HEBRON STORAGE INJECTION POTTER\n470001 HEBRON STORAGE WITHDRAWAL POTTER",313.5]
["X18-214559","","2018-05-15T08:01:00","2018-05-15T08:01:00",null,null,null,"MLV 313 to MLV 237",400,"4","Efficiency Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,313.89999389648438]
["X17-858886","","2018-05-15T10:36:00","2018-05-16T10:36:00",null,null,null,"Sta 405A",400,"4","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,313.89999389648438]
["X17-858820","","2018-05-02T09:10:00","2018-05-03T09:10:00",null,null,null,"Sta 315",300,"4","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,315]
["X17-838123","","2018-08-13T12:14:00","2018-08-17T12:14:00",null,null,null,"MLV 315-2 to MLV 317-2",300,"4","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,315]
["X17-838117","","2018-06-04T11:59:00","2018-06-08T11:59:00",null,null,null,"MLV 317-1BL to MLV 319-1",300,"4","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,317]
["X18-106008","","2018-06-01T13:25:00","2018-06-30T13:25:00",null,null,null,"Sta 317: Unit 1B",300,"4","Compressor Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,317.10000610351562]
["X18-133853","","2018-04-20T13:58:00","2018-04-23T13:58:00",null,null,null,"Sta 317: Unit 1B",300,"4","Electric Company Outage","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,317.1300048828125]
["X18-133865","","2018-05-18T14:01:00","2018-05-21T14:01:00",null,null,null,"Sta 317: Unit 1B",300,"4","Electric Company Outage","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,317.1300048828125]
["X17-838116","","2018-05-21T11:55:00","2018-06-01T11:55:00",null,null,null,"MLV 319-1 to MLV 321-1",300,"4","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,319]
["X17-852580","","2018-04-17T13:37:00","2018-04-26T13:37:00",null,null,null,"MLV 319-2 to MLV 321-2",300,"4","Pig runs  - Cleaning / Gauge 4/17/18, Caliper 4/25/18, MFL 4/26/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,319.20001220703125]
["X18-106005","","2018-04-24T13:17:00","2018-05-18T13:17:00",null,null,null,"MLVS 319",300,"4","Meter Tie-In","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,319.5]
["X17-838120","","2018-06-18T12:07:00","2018-07-20T12:07:00",null,null,null,"MLV 321-1 to MLV 325-1",300,"4","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,321]
["X18-290841","","2018-04-16T14:51:00","2018-04-21T14:51:00",null,null,null,"Sta 325",300,"5","Station Maintenance","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,325]
["X17-839886","","2018-04-09T10:01:00","2018-04-27T10:01:00",null,null,null,"MLV 400-1 (STATION 1) to MLV 409-1",400,"0","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,400]
["X17-839888","","2018-06-11T10:05:00","2018-06-29T10:05:00",null,null,null,"MLV 400-2 (STATION 1) to MLV 409-2",400,"0","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,400.01998901367187]
["X17-839889","","2018-06-25T10:08:00","2018-07-13T10:08:00",null,null,null,"MLV 409A-101 TO MLV 409A-103",400,"0","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,409]
["X18-135348","***","2018-03-12T10:36:00","2018-04-16T10:36:00","Completed",null,null,"Sta 409: Unit 1A",400,"0","Unit Maintenance","This project will require the station outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,409.10000610351562]
["X17-852491","","2018-06-11T11:04:00","2018-07-06T11:04:00",null,null,null,"MLV 409A-901 to MLV 409A-902",400,"0","Pig runs  - Maintenance, Gauge, MFL","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,409.89999389648437]
["X18-163543","","2018-05-15T13:12:00","2018-05-15T13:12:00",null,null,null,"Sta 507K to Sta 823",null,"L","Pig run - Maintenance/Brush 5/15/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,507]
["X18-163541","","2018-09-11T13:10:00","2018-09-11T13:10:00",null,null,null,"Sta 507F to Sta 823",null,"L","Pig run - Maintenance/Brush 9/11/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,507]
["X18-166636","","2018-06-25T13:19:00","2018-07-02T13:19:00",null,null,null,"Sta 527",500,"L","Vessel Valve Replacement","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,527]
["X17-852559","","2018-05-23T13:17:00","2018-05-31T13:17:00",null,null,null,"MLV 529-1 to MLV 530-1",500,"L","Pig runs  - Cleaning 5/22,23,24 Caliper 5/29/18, ILI 5/31/18","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,529.0999755859375]
["X17-838108","","2018-06-11T11:34:00","2018-06-27T11:34:00",null,null,null,"MLV 530-3 to MLV 532-2",500,"L","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,530]
["X17-838113","","2018-07-09T11:48:00","2018-07-16T11:48:00",null,null,null,"MLV 538-1 to MLV 542-1",500,"1","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,538]
["X18-75131","","2018-09-10T07:15:00","2018-09-14T07:15:00",null,null,null,"Sta 542",500,"1","Station Maintenance","This project will require the station outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,542]
["X17-858832","","2018-09-17T09:43:00","2018-09-18T09:43:00",null,null,null,"Sta 542",500,"1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,542]
["X18-192975","","2018-06-18T05:42:00","2018-07-06T05:42:00",null,null,null,"Sta 542: Unit 1B",500,"1","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,542.5]
["X17-858904","","2018-10-17T12:51:00","2018-10-18T12:51:00",null,null,null,"Sta 546",500,"1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,546]
["X18-59184","","2018-06-11T11:58:00","2018-06-22T11:58:00",null,null,null,"Sta 546: Unit 1A",500,"1","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,546.0999755859375]
["X18-59187","","2018-06-25T12:02:00","2018-07-06T12:02:00",null,null,null,"Sta 546: Unit 2A",500,"1","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,546.20001220703125]
["X18-59188","","2018-07-30T12:03:00","2018-08-10T12:03:00",null,null,null,"Sta 546: Unit 4A",500,"1","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictionThis project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.s based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,546.4000244140625]
["X17-852582","","2018-08-07T13:40:00","2018-08-08T13:40:00",null,null,null,"MLV 549-3 to MLV 550-3",500,"1","ILI Only","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,549.29998779296875]
["X17-711176","","2017-08-15T06:00:00","2018-06-01T18:00:00",null,null,null,"Sta. 550-1A",500,"1","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,550.0999755859375]
["X17-858834","","2018-05-14T09:47:00","2018-05-20T09:47:00",null,null,null,"Sta 555",500,"1","Annual ESD Test","This project will require the station outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,555]
["X17-839903","","2018-06-11T10:31:00","2018-07-13T10:31:00",null,null,null,"MLV 561-1 to MLV 563-1",500,"1","Pressure Test","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,560]
["X17-852480","","2018-06-27T10:47:00","2018-06-27T10:47:00",null,null,null,"MLV 561-1 to MLV 563-1",500,"1","Tethered ILI","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,560.0999755859375]
["X17-854295","","2018-06-11T05:54:00","2018-07-13T05:54:00",null,null,null,"MLV 561-1 to MLV 563-1",500,"1","ECDA","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,561.0999755859375]
["X18-86431","***","2018-05-11T08:20:00","2018-06-01T08:20:00","Date Change","4/9/2018","5/10/2018","Sta 563",500,"1","Tie-In to 500-1, 500-2, & 800-1","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,563]
["X17-852512","","2018-09-17T12:10:00","2018-09-24T12:10:00",null,null,null,"MLV 700-1 to MLV 706-1",700,"0","Pig runs  - Cleaning / Gauge 9/17/18 - 9/19/18, Combo 9/20/18, Hard Spot Tool 9/24/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,700.0999755859375]
["X18-163545","","2018-07-24T13:16:00","2018-07-24T13:16:00",null,null,null,"Sta 820-1 to Sta 823",800,"L","Pig run - Maintenance/Brush 7/24/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,820]
["X18-163535","","2018-06-19T12:59:00","2018-06-19T12:59:00",null,null,null,"Sta 823 to MLV 516",500,"L","Pig run - Maintenance/Brush 6/19/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,823]
["X17-914206","","2018-08-27","2018-08-30",null,null,null,"Sta 823",800,"L","Purchase Power Conversion","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Higher than normal pressures in the area are probable during this outage.","SOP","Potential out of path restrictions may be at risk.",null,823.010009765625]
["X18-163539","","2018-04-25T13:07:00","2018-04-25T13:07:00",null,null,null,"Sta 823 to Sta 40",500,"L","Pig run - Maintenance/Brush 4/25/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  The meters listed below will be shut-in for a brief period of time during the pig run.","SOP","Potential out of path restrictions may be at risk.","420373 TRNSCO/TGP KINDER LA EXCH (BI 1\n420708 ELIZ NG/TGP GRANT LA SALES ALLEN\n420436 VERNON/TGP PITKIN LA VERNON\n420793 ELIZ NG/TGP J R FRANKS 1 VERNON\n420388 PROVNCAL/TGP PROVENCAL LA NATCHITOC",823.0999755859375]
["X18-163544","","2018-06-05T13:15:00","2018-06-05T13:15:00",null,null,null,"Sta 827 to Sta 823",800,"L","Pig run - Maintenance/Brush 6/5/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,827]
["X17-604939","***","2018-03-07","2018-04-13","Completed",null,null,"MLV 824-1 to 825-1",800,"L","Pipe Recoat","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,832]
["X17-839919","","2018-04-17","2018-05-31",null,null,null,"MLV 834-1 to MLV 835-1",800,"1","Spike Test","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations. The meters listed below will be shut-in for the entire duration of the project.","SOP","Potential out of path restrictions may be at risk.","412691 REGENCY/TGP PEOPLES ROAD FRANKLIN\n49554 – AM MIDLA/TGP NORTH PEOPLES RD FRANK\n420279- ATMOS TL/TGP CROWVILLE LA FRANKLIN",834]
["X17-838106","","2018-04-23","2018-04-26",null,null,null,"MLV 834-1 to MLV 838-1",800,"1","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,834]
["X17-852493","","2018-06-14T11:10:00","2018-06-22T11:10:00",null,null,null,"MLV 843-1 to MLV 847-1",800,"1","Pig runs - Cleaning 6/14/18, Gauge Plate 6/15/18, MFL 6/18/18, Hard Spot 6/22/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,843.0999755859375]
["X17-89954","","2018-04-17","2018-05-31",null,null,null,"MLV 846-1 to MLV 847-1",800,"1","Hydrotest","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.","420328 – ATMOS-MS/TGP HARDY STA MS GRENADA",846]
["X17-839912","","2018-07-18","2018-09-28",null,null,null,"MLV 851-1 to MLV 852-1",800,"1","Spike Test","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,851]
["X17-852521","","2018-07-10T12:25:00","2018-07-17",null,null,null,"MLV 856-1 to MLV 859-1",800,"1","Pig runs - Cleaning 7/10/18, Gauge 7/11/18, MFL 7/12/18, Hard Spot 7/17/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,856.0999755859375]
["X17-858872","***","2018-06-19T10:17:00","2018-06-20T10:17:00","Added",null,null,"Sta 860",800,"1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,860]
["X17-838138","","2018-07-09T13:05:00","2018-07-20T13:05:00",null,null,null,"MLV 866-1D to MLV 871-1",800,"2","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,866]
["X17-858873","***","2018-04-17T10:19:00","2018-04-17T10:19:00","Completed",null,null,"Sta 871",800,"2","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,871]
["X17-838140","","2018-07-23T13:08:00","2018-08-31T13:08:00",null,null,null,"MLV 871-1 to MLV 876-1",800,"2","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,871]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]