{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["Export"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":2,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Export","index":0,"n_rows":499,"n_cols":16,"rows_kept":499,"cut":false,"hidden":false,"merged":[[2,1,2,15]]}
[null,"Updated ","2018-07-12"]
[null,"Tennessee Gas Pipeline 2018 Pipeline Outage and Maintenance Summary"]
[null,"This is a summary of the current status of all TGP 2018 Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  Additionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
[null,"*** Indicates revision"]
["Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","Location","Leg","Zone","Maintenance Activity","Anticipated Impact","Potential Restriction Level","TOS Potential Restrictions","Meter(s) in Impacted Area","Loc"]
["X18-475323","","2018-09-03T06:00:00","2018-10-19T18:00:00",null,null,null,"MLVS 1",100,"0","New Meter Tie-in","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,1]
["X17-839882","***","2018-01-18T09:58:00","2018-08-31T18:00:00","Date Change","1/18/2018","7/20/2018","MLV 1-1D to MLV 9-1S",100,"0","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.  The meters listed below will be shut-in for the duration of the project.","SIP","Potential in the path restrictions may be at risk.",null,1.0099999904632568]
["X18-37920","","2018-12-31T06:00:00","2018-12-31T18:00:00",null,null,null,"Sta 3A",100,"0","New Station Tie-In (100-2 line)","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,3.2000000476837158]
["X18-509046","","2018-07-09T06:00:00","2018-07-23T18:00:00",null,null,null,"MLVS 8-1: Port of Victoria",100,"0","Meter Shut-In","This project will require taking the meter out of service.  This will limit the flow to zero and may result in restrictions based on customer nominations.  This is related to the Force Majeure at Station 1 and Station 9.",null,null,"421083 ENLINK/TGP PORT OF VICTORIA: DIP 8H",8]
["X18-504482","","2018-07-27T06:00:00","2018-07-29T18:00:00",null,null,null,"Jackson Meter",100,"0","Modification","This project will require taking the meter out of service.  This will limit the flow to zero and may result in restrictions based on customer nominations.",null,null,"49803 KMTEJAS/TGP JACKSON    (GANADO)",13.100000381469727]
["X18-504480","","2018-07-27T06:00:00","2018-07-29T18:00:00",null,null,null,"Ganado Meter",100,"0","Modification","This project will require taking the meter out of service.  This will limit the flow to zero and may result in restrictions based on customer nominations.",null,null,"412860 ETC TX/TGP UDP GANADO PLANT JACKSON",13.199999809265137]
["X18-472186","","2018-08-20T06:00:00","2018-08-30T18:00:00",null,null,null,"MLV 17-1S to MLV 9-1D",100,"0","Pig runs - Cleaning 8/20 - 8/24, AFD 8/28, EMAT 8/30","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,17.100000381469727]
["X18-231693","","2018-10-23T06:00:00","2018-10-27T18:00:00",null,null,null,"Sta 25: Station Maintenance",100,"0","Electrical Inspection","This project will require the station outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,25]
["X18-454628","","2018-08-06T06:00:00","2018-08-12T18:00:00",null,null,null,"Sta 32",100,"0","Replace Jacket Water Tank","This project will require the station outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,32]
["X17-857397","","2018-08-06T06:00:00","2018-08-06T18:00:00",null,null,null,"Sta 32",100,"0","Annual ESD Test","This project will require the station outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,32]
["X17-839891","","2018-06-04T10:17:00","2018-07-27T10:17:00",null,null,null,"MLV 32-1 to MLV 34-1",100,"0","Spike Test","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,33]
["X18-99331","","2019-01-07T11:40:00","2019-03-01T11:40:00",null,null,null,"MLVS 36-1",100,"0","Pipe Replacement and Install New Valve","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,36.099998474121094]
["X18-99333","","2018-10-22T11:45:00","2018-12-28T11:45:00",null,null,null,"MLVS 36-2",100,"0","Pipe Replacement and Install New Valve","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,36.200000762939453]
["X18-99335","","2018-08-13T11:48:00","2018-10-19T11:48:00",null,null,null,"MLVS 36-3",100,"0","Pipe Replacement and Install New Valve","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,36.299999237060547]
["X17-852470","","2018-07-10T10:34:00","2018-07-19T10:34:00",null,null,null,"MLV 40-1D to MLV 47-1",100,"1","Pig runs  - Cleaning & Gauge 7/10/18-7/13/18, DEF Inspection 7/17/18, TDW MDS 7/19/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,40.099998474121094]
["X17-852400","***","2018-08-01T06:00:00","2018-09-14T18:00:00","Date Change","7/23/2018","8/31/2018","MLV 40-3S to MLV 47-3",100,"1","Make Piggable","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,40.299999237060547]
["X18-340693","","2018-10-16T06:35:00","2018-10-23T06:35:00",null,null,null,"Beer Creek Storage",100,"1","Shut In Test","This project will require taking the facility out of service.  This will limit throughput and may result in restrictions based on customer nominations.   The meter listed below will be shut-in for the entire duration of the project.","SOP","Potential out of path restrictions may be at risk.","460017 STORAGE – BEAR CREEK",43.009998321533203]
["X17-852405","","2018-10-08T06:00:00","2018-11-07T18:00:00",null,null,null,"MLV 54-4 to MLV 63-4",100,"1","Pig runs - Chem Cleaning 10/8/18 - 10/11/18, AFD 11/5/18, EMAT 11/7/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,54.400001525878906]
["X17-852459","***","2018-06-06T10:20:00","2018-07-05T10:20:00","Completed",null,null,"MLV 63-1 to MLV 69-1",100,"1","Pig runs - Chem Cleaning 6/6/18 to 6/19/18, AFD 7/3/18, EMAT 7/5/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,63.099998474121094]
["X17-852528","","2018-08-02T12:36:00","2018-08-07T12:36:00",null,null,null,"MLV 63-1 to MLV 69-1",100,"1","Pig runs - MFL 8/2/18, Hard Spot 8/7/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,63.099998474121094]
["X17-852469","","2018-07-20T10:30:00","2018-07-26T10:30:00",null,null,null,"MLV 63-3 to MLV 71-3",100,"1","Pig runs - Chem Cleaning 7/20/18, Gauge Plate 7/23/18, Caliper 7/24/18, MDS 7/26/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,63.299999237060547]
["X17-852408","","2018-09-24T06:00:00","2018-10-04T18:00:00",null,null,null,"MLV 63-4D to MLV 71-4",100,"1","Pig runs - Chem Cleaning 9/24/18 - 9/27/18, AFD 10/2/18, EMAT 10/4/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,63.400001525878906]
["X18-517456","","2018-06-25T06:00:00","2018-07-14T18:00:00",null,null,null,"MLVS 67-2",100,null,"Pipeline Maintenance","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.  The meters listed below will be shut-in for the duration of the project.","SOP","Potential out of path restrictions may be at risk.",null,67.199996948242187]
["X17-852534","","2018-08-13T12:44:00","2018-08-16T12:44:00",null,null,null,"MLV 77-1 to MLV 79-1",100,"1","Pig runs - Chem Cleaning 8/13/18, AFD 8/14/18, EMAT 8/16/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,77.099998474121094]
["X18-426508","","2018-08-20T06:00:00","2018-08-31T17:00:00",null,null,null,"Sta 87: Unit 8C",100,"2","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,87.008003234863281]
["X18-489701","","2018-07-16T06:00:00","2018-07-18T18:00:00",null,null,null,"Sta 87: Building C",100,"2","Valve Maintenance","This project will require a building outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,87.031997680664063]
["X18-293073","","2018-07-23T06:00:00","2018-08-18T17:00:00",null,null,null,"Sta 87: Unit 1E",100,"2","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,87.599998474121094]
["X18-342867","","2018-09-04T06:00:00","2018-09-14T18:00:00",null,null,null,"Sta 96: Unit 2D",100,"2","Electrical Panel Replacement","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,96.199996948242187]
["X17-838150","","2018-06-07T06:00:00","2018-07-27T18:00:00",null,null,null,"MLV 106-4D to MLV 200-1S",100,"2","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106]
["X18-225447","","2018-04-02T06:55:00","2018-07-27T06:55:00",null,null,null,"Sta 106: Unit 1C",100,"2","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,106.33000183105469]
["X18-571528","***","2018-09-04T06:00:00","2018-10-19T18:00:00","Added",null,null,"Sta 110",100,"2","Unit Controls Upgrade","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,110]
["X17-852527","","2018-07-10T12:30:00","2018-07-17T12:30:00",null,null,null,"MLV 110-2 to MLV 114-2",100,"2","Pig runs  - Cleaning / Gauge 7/10/18, MFL 7/12/18, Hard Spot Tool 7/17/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.    The meters listed below will be shut-in for a brief period of time during the pig run.","SOP","Potential out of path restrictions may be at risk.","412742 BIGSANDY/TGP GLANCY CARTER",110.19999694824219]
["X17-852554","","2018-06-26T06:00:00","2018-07-19T18:00:00",null,null,null,"MLV 110-6 to MLV 114-6",100,"2","Pig runs  - Cleaning / Gauge 6/26/18-6/27/18, MFL 7/19/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,110.59999847412109]
["X17-852411","","2018-10-10T08:44:00","2018-10-18T08:44:00",null,null,null,"MLV 111-3 to MLV 114-3",100,"2","Pig runs - Cleaning & Gauge Tool 10/10/18, AFD Tool 10/16/18, EMAT 10/18/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,111.30000305175781]
["X17-840017","","2018-06-18T14:57:00","2018-07-30T14:57:00",null,null,null,"MLVS 118-3",100,"3","Make Piggable","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,114]
["X17-852467","***","2018-06-04T06:00:00","2018-07-31T18:00:00","Added",null,null,"MLV 118-3 to MLV 121-2",100,"3","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.  The meters listed below will be shut-in for the duration of the project.","SIP","Potential in the path restrictions may be at risk.",null,114.30000305175781]
["X18-524941","","2018-07-16T06:00:00","2018-07-20T18:00:00",null,null,null,"Sta 200: Unit 5A",200,"4","Inspection","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,200.0050048828125]
["X17-852542","","2018-07-12T12:57:00","2018-07-19T12:57:00",null,null,null,"MLV 200-2D to MLV 204-2",200,"4","Pig runs  - Cleaning Gauge 7/12, MFL 7/17, Caliper 7/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed below will be shut-in for the duration of the pig runs.","SIP","Potential in the path restrictions may be at risk.","421018 TET/TGP HANGING ROCK SCIOTO",200.19999694824219]
["X17-852544","","2018-08-14T13:04:00","2018-08-16T13:04:00",null,null,null,"MLV 209-4 to MLV 204-4",200,"4","Pig runs  - Cleaning / Gauge 8/14/18, MFL 8/16/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,204.39999389648437]
["X18-166402","","2018-04-02T05:29:00","2018-07-13T05:29:00",null,null,null,"Sta 209: Unit 1A",200,"4","Foundaton Repair","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,209.10000610351562]
["X17-852513","","2018-06-26T06:00:00","2018-07-26T18:00:00",null,null,null,"MLV 209-1 to MLV 214-1",200,"4","Pig runs  - Cleaning / Gauge 6/26/18, MFL 7/24/18, Hard spot 7/26/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  The meter listed below will be shut-in for a brief period of time during the pig run.","SIP","Potential in the path restrictions may be at risk.","47652 UTICA EO/TGP LEESVILLE PROC PLNT CA",209.10000610351562]
["X17-852515","","2018-06-28T06:00:00","2018-08-02T18:00:00",null,null,null,"MLV 209-3 to MLV 214-3",200,"4","Pig runs  - Cleaning / Gauge 6/28/18, MFL 7/31/18, Hard spot 8/02/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,209.30000305175781]
["X18-571459","***","2018-08-03T06:00:00","2018-08-03T18:00:00","Added",null,null,"Sta 214",200,"4","Electrical Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,214]
["X17-840015","","2018-09-17T07:00:00","2018-09-28T17:00:00",null,null,null,"218-2 to 219-2",200,"4","Pipe Replacement","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,214]
["X18-424588","***","2018-06-18T06:00:00","2018-07-06T18:00:00","Completed",null,null,"Sta 214: Unit 11A",200,"4","Compressor Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,214.01100158691406]
["X18-532337","***","2018-07-09T06:00:00","2018-07-18T18:00:00","Date Change","7/9/2018","7/13/2018","Sta 214: Unit 11A",200,"4","Compressor Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,214.01100158691406]
["X18-320557","","2018-07-31T05:29:00","2018-07-31T05:29:00",null,null,null,"MLVS 217",200,"4","New Meter Hot Taps for Hickory Run","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,217.5]
["X17-852410","","2018-09-25T08:42:00","2018-10-25T08:42:00",null,null,null,"MLV 219-2D to MLV 307-1",300,"4","Pig runs  - Cleaning / Gauge 9/25/18, AFD 9/27/18, EMAT 10/25/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,219.19999694824219]
["X17-852547","***","2018-09-06T06:00:00","2018-09-13T18:00:00","Date Change","9/11/2018","9/13/2018","MLV 224-1 to MLV 229-1",200,"4","Pig runs  - Cleaning / Gauge 9/6, Caliper 9/11, MFL 9/13","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,224.10000610351562]
["X17-838129","","2018-09-04T06:00:00","2018-09-14T18:00:00",null,null,null,"MLV 230-1 to MLV 237-1",200,"5","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,230]
["X18-155121","","2018-07-09T09:06:00","2018-07-18T09:06:00",null,null,null,"230B-101 TO 230B-106",200,"5","Make Piggable","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,230.00999450683594]
["X18-295163","","2018-08-07T15:00:00","2018-08-07T15:00:00",null,null,null,"230B-101 TO 230B-106",200,"5","Make Piggable","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,230.01100158691406]
["X17-840014","","2018-07-19T14:48:00","2018-07-28T14:48:00",null,null,null,"230B-201 TO 230B-206A",200,"5","Make Piggable","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,230.02000427246094]
["X18-295166","","2018-08-14T15:03:00","2018-08-14T15:03:00",null,null,null,"230B-201 TO 230B-206A",200,"5","Make Piggable","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,230.02099609375]
["X18-302554","***","2018-06-11T13:23:00","2018-07-26T18:00:00","Date Change","6/11/2018","7/12/2018","Sta 237: Unit 1A",200,"5","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,237.10000610351562]
["X17-852593","","2018-08-06T13:54:00","2018-08-17T13:54:00",null,null,null,"MLV 237-2 to MLV 238-2",200,"5","SCCDA","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,237.19999694824219]
["X18-225574","","2018-09-17T10:58:00","2018-09-22T10:58:00",null,null,null,"MLV 313A-405A to MLV 313A-409",200,"5","Replace Actuators","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.  The meter listed below will be shut-in for the entire duration of the project.","SIP","Potential in the path restrictions may be at risk.","420644 NYSEG/TGP PRATTSBURG SALES STEUBEN\n420746 NYSEG/TGP WALLACE SALES STEUBEN",237.89999389648437]
["X18-45911","","2018-07-16T06:00:00","2018-07-27T18:00:00",null,null,null,"Sta 241: Unit 1B",200,"5","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,241.11000061035156]
["X18-45934","","2018-07-09T11:43:00","2018-07-20T11:43:00",null,null,null,"Sta 249: Unit 2A",200,"5","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,249.19999694824219]
["X17-839914","","2018-09-05T10:55:00","2018-10-19T10:55:00",null,null,null,"MLV 251-1 to MLV 253-1",200,"5","Pressure Test","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,252]
["X17-839880","***","2018-04-02T06:00:00","2018-07-23T18:00:00","Date Change","4/2/2018","7/30/2018","MLV 254-1 to MLV 261-1",200,"5","Remediation - Phase 1","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,254.00100708007813]
["X18-155316","","2018-10-22T14:29:00","2018-10-24T14:29:00",null,null,null,"MLV 254-2 to MLV 261-2",200,"5","Pig runs  - Cleaning 10/22/18, EMAT 10/24/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,254.00399780273437]
["X18-110952","","2018-06-01T06:00:00","2018-07-29T17:00:00",null,null,null,"Sta 254: Building A",200,"5","Automation Upgrade - 2 weeks/unit - up to 2 units may be down at a same time","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,254.10000610351563]
["X18-95516","","2018-10-01T08:50:00","2018-10-23T08:50:00",null,null,null,"Sta 261",200,"6","Automation Upgrade","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,261]
["X18-295178","","2018-08-20T15:34:00","2018-08-30T15:34:00",null,null,null,"Sta 261: A Building",200,"6","BPS Upgrade","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,261.010009765625]
["X18-295176","","2018-09-10T15:30:00","2018-09-21T15:30:00",null,null,null,"Sta 261: C Building",200,"6","BPS Upgrade","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,261.01998901367187]
["X18-295175","","2018-06-11T15:27:00","2018-07-13T18:00:00",null,null,null,"Sta 261: D Building",200,"6","BPS Upgrade","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,261.02999877929687]
["X18-295170","***","2018-06-04T06:00:00","2018-07-19T18:00:00","Date Change","6/4/2018","7/13/2018","Sta 261: D Building",200,"6","Silencer Replacement","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,261.04998779296875]
["X17-854305","","2018-07-09T06:00:00","2018-07-12T18:00:00",null,null,null,"MLV 261BP-101-BERKSHIRE POWER DELIVERY: 1000 - 0+00 to MLV 261BP-101-BERKSHIRE POWER DELIVERY",200,"6","ECDA","During this pipeline inspection project, we do not anticipate any reduction in pressure at this time.  As a result, this meter will not be impacted: 420901 SHELL/TGP BERKSHIRE POWER SALES HAM","SOP","Potential out of path restrictions may be at risk.",null,261.10101318359375]
["X18-201904","","2018-09-10T07:18:00","2018-09-14T07:18:00",null,null,null,"Sta 261: Unit Maintenance",200,"6","Water Wash","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,261.29998779296875]
["X18-201907","","2018-09-11T07:20:00","2018-09-13T07:20:00",null,null,null,"Sta 261: Unit Maintenance",200,"6","Boroscope Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,261.29998779296875]
["X18-386485","","2018-08-20T12:17:00","2018-09-07T12:17:00",null,null,null,"Sta 261; Unit 4A",200,"6","Automation Upgrade","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,261.39999389648437]
["X18-201913","","2018-09-11T07:33:00","2018-09-14T07:33:00",null,null,null,"Sta 261: Unit 4A",200,"6","Compressor Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,261.39999389648437]
["X18-201910","","2018-09-12T07:29:00","2018-09-13T07:29:00",null,null,null,"Sta 264: Unit Maintenance",200,"6","Water Wash","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,264.10000610351562]
["X18-201911","","2018-09-18T07:31:00","2018-09-19T07:31:00",null,null,null,"Sta 264: Unit Maintenance",200,"6","Boroscope Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,264.20001220703125]
["X17-839910","","2018-07-30T10:47:00","2018-08-09T10:47:00",null,null,null,"MLV 265E-201 to MLV 265E-202",200,"6","Pressure Test","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.   The meter listed below will be shut-in for the entire duration of the project.","SOP","Potential out of path restrictions may be at risk.","420758 – NARNGST/TGP LINCOLN SMS PROVIDENCE",265]
["X18-115706","","2018-11-05T08:44:00","2018-11-15T08:44:00",null,null,null,"265E",200,"6","4000 hr Inspection","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,265.20001220703125]
["X17-858878","","2018-10-01T10:26:00","2018-10-05T10:26:00",null,null,null,"Sta 266A",200,"6","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,266]
["X17-840013","","2019-05-10T14:43:00","2019-07-10T14:43:00",null,null,null,"267-1",200,"6","Class Change","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,267]
["X17-839896","","2018-07-09T10:25:00","2018-07-19T10:25:00",null,null,null,"MLV 268A-301 to MLV 268A-302",200,"6","Pressure Test","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.   The meter listed below will be shut-in for the entire duration of the project.","SOP","Potential out of path restrictions may be at risk.","420111 – BOSTN/TGP LEOMINSTER MA WORCHESTER",268]
["X17-858882","","2018-10-23T10:31:00","2018-10-25T10:31:00",null,null,null,"Sta 270B",200,"6","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,270]
["X17-858818","","2018-07-17T06:00:00","2018-07-20T18:00:00",null,null,null,"Sta 307",300,"4","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,307]
["X17-838122","","2018-07-23T12:10:00","2018-08-10T12:10:00",null,null,null,"MLV 313-1 to MLV 317-1",300,"4","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,313]
["X18-340702","***","2018-05-18T07:44:00","2018-07-27T18:00:00","Date Change","5/18/2018","7/6/2018","Sta 313: Dehy System",300,"4","Maintenance","This project will require taking the facility out of service.  This will  result in no withdrawals out of Hebron Storage during this period.",null,null,null,313.79998779296875]
["X17-838123","","2018-08-13T12:14:00","2018-08-17T12:14:00",null,null,null,"MLV 315-2 to MLV 317-2",300,"4","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,315]
["X18-475140","","2018-07-21T08:12:00","2018-07-26T08:12:00",null,null,null,"Sta 317",300,"4","Standby Generator","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,317]
["X18-106008","","2018-06-01T06:00:00","2018-07-31T18:00:00",null,null,null,"Sta 317: Unit 1B",300,"4","Compressor Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,317.10000610351562]
["X18-133865","","2018-07-13T06:00:00","2018-07-16T18:00:00",null,null,null,"Sta 317: Unit 1B",300,"4","Electric Company Outage","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,317.1300048828125]
["X18-489865","","2018-10-03T06:00:00","2018-10-05T18:00:00",null,null,null,"MLVS 318-1: Stagecoach/Latini",300,"4","Meter Tie-In","This activity will require operating at reduced pressures. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,318.10000610351562]
["X18-489869","","2018-10-08T06:00:00","2018-10-10T18:00:00",null,null,null,"MLVS 318-2: Stagecoach/Latini",300,"4","Meter Tie-In","This activity will require operating at reduced pressures. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,318.20001220703125]
["X18-571561","***","2018-07-17T14:13:00","2018-07-17T14:13:00","Added",null,null,"Sta 319",300,"4","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,319]
["X17-838120","","2018-06-18T12:07:00","2018-07-20T12:07:00",null,null,null,"MLV 321-1 to MLV 325-1",300,"4","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,321]
["X18-571562","***","2018-07-19T14:15:00","2018-07-19T14:15:00","Added",null,null,"Sta 321",300,"4","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,321]
["X18-380769","","2018-05-21T06:00:00","2018-07-14T18:00:00",null,null,null,"MLVS 407D-300",400,"0","Line Lowering","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.","420913 MISSIONP/TGP TABASCO #2 DELIVERY BI\n412562 MISSIONP/TGP TABASCO #2 RECEIPT BID\n412656 FIDELITY/TGP TABASCO WEST HIDALGO",407.29998779296875]
["X18-475332","","2018-09-03T06:00:00","2018-10-19T18:00:00",null,null,null,"Sta 409",400,"0","Adding Gas Coolers","This project will require the station outage, which could limit throughput through the station and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,409]
["X17-839889","","2018-09-10T06:00:00","2018-09-28T18:00:00",null,null,null,"MLV 409A-101 TO MLV 409A-103",400,"0","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,409]
["X17-852491","","2018-07-05T06:00:00","2018-07-11T18:00:00",null,null,null,"MLV 409A-901 to MLV 409A-902",400,"0","Pig runs  - Cleaning 7/5/18, Gauge 7/6/18, Cleaning 7/9/18(if needed), MFL 7/11/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,409.89999389648437]
["X18-163541","","2018-09-11T13:10:00","2018-09-11T13:10:00",null,null,null,"Sta 507F to Sta 823",null,"L","Pig run - Maintenance/Brush 9/11/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,507]
["X18-381281","***","2018-11-01T06:00:00","2018-11-16T18:00:00","Date Change","10/1/2018","10/16/2018","MLVS 522-1",500,"L","Repair Line Covering","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,522]
["X18-166636","***","2018-06-29T06:00:00","2018-07-09T18:00:00","Completed",null,null,"Sta 527",500,"L","Vessel Valve Replacement","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.","411145 OGS/TGP BAY BATISTE TRANSPORT PLAQU\n412658 C.W.ENER/TGP FLEUR PLAQUEMINES",527]
["X18-381434","","2018-09-15T05:45:00","2018-10-31T05:45:00",null,null,null,"MLVS 528-1",500,"L","Line Lowering","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,528]
["X17-858832","***","2018-09-05T06:00:00","2018-09-06T18:00:00","Date Change","9/17/2018","9/18/2018","Sta 542",500,"1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,542]
["X18-75131","","2018-09-10T07:15:00","2018-09-14T07:15:00",null,null,null,"Sta 542",500,"1","Station Maintenance","This project will require the station outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,542]
["X18-192975","***","2018-07-16T06:00:00","2018-11-09T18:00:00","Date Change","6/18/2018","7/6/2018","Sta 542: Unit 1B",500,"1","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,542.5]
["X17-858904","***","2018-09-18T06:00:00","2018-09-19T18:00:00","Date Change","10/17/2018","10/18/2018","Sta 546",500,"1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,546]
["X18-59184","***","2018-07-16T06:00:00","2018-08-03T18:00:00","Date Change","6/11/2018","7/20/2018","Sta 546: Unit 1A",500,"1","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,546.0999755859375]
["X18-59187","***","2018-08-06T06:00:00","2018-08-24T18:00:00","Date Change","6/25/2018","7/6/2018","Sta 546: Unit 2A",500,"1","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,546.20001220703125]
["X18-59188","***","2018-08-27T06:00:00","2018-09-14T18:00:00","Date Change","7/30/2018","8/10/2018","Sta 546: Unit 4A",500,"1","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,546.4000244140625]
["X17-852582","","2018-08-07T13:40:00","2018-08-08T13:40:00",null,null,null,"MLV 549-3 to MLV 550-3",500,"1","ILI Only","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,549.29998779296875]
["X18-472029","","2018-06-04T06:00:00","2018-08-31T17:00:00",null,null,null,"Sta 550: Unit 1A",500,"1","Regrout","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,550.0009765625]
["X18-575423","***","2018-07-16T06:00:00","2018-07-22T18:00:00","Added",null,null,"Sta 550",500,"1","Repair 3A Discharge Load Line Saddle Pad","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,550.00299072265625]
["X17-839903","","2018-06-11T10:31:00","2018-07-13T10:31:00",null,null,null,"MLV 561-1 to MLV 563-1",500,"1","Pressure Test","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,560]
["X18-406211","***","2018-06-22T06:00:00","2018-07-17T18:00:00","Date Change","6/22/2018","7/7/2018","MLVS 560-2",500,"1","Prepare 500-1 for Hydrotest - 562-1 to 563-1","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,560.22998046875]
["X18-406212","***","2018-06-11T06:00:00","2018-07-17T18:00:00","Date Change","6/11/2018","7/7/2018","MLVS 560-2",500,"1","Prepare 500-1 for Hydrotest - PT 561-1 to 562-1","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,560.239990234375]
["X18-406213","***","2018-07-05T06:00:00","2018-07-17T18:00:00","Date Change","7/5/2018","7/10/2018","MLVS 560-2",500,"1","Reconnect Hydrotest Segment - 560-1 to 561-1","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,560.25]
["X18-406214","","2018-07-10T06:00:00","2018-07-14T18:00:00",null,null,null,"MLVS 560-2",500,"1","Reconnect Hydrotest Segment 562-1 to 563-1","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,560.260009765625]
["X17-854295","","2018-06-11T05:54:00","2018-07-13T05:54:00",null,null,null,"MLV 561-1 to MLV 563-1",500,"1","ECDA","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,561.0999755859375]
["X18-86431","","2018-06-25T06:00:00","2018-07-27T18:00:00",null,null,null,"Sta 563",500,"1","Tie-In to 500-1, 500-2, & 800-1","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,563]
["X17-852512","","2018-09-17T12:10:00","2018-09-24T12:10:00",null,null,null,"MLV 700-1 to MLV 706-1",700,"0","Pig runs  - Cleaning / Gauge 9/17/18 - 9/19/18, Combo 9/20/18, Hard Spot Tool 9/24/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,700.0999755859375]
["X18-494072","***","2018-07-11T06:00:00","2018-07-11T18:00:00","Completed",null,null,"MLV 707-1 to MLV 700-1",700,"0","Pig - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,707]
["X17-915836","***","2018-07-10T06:00:00","2018-07-10T18:00:00","Completed",null,null,"Sta 823",800,"L","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,823]
["X18-163535","","2018-08-07T06:00:00","2018-08-07T18:00:00",null,null,null,"Sta 823 to MLV 516",500,"L","Pig run - Maintenance/Brush 8/7/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,823]
["X17-914206","","2018-10-15T06:00:00","2018-10-18T06:00:00",null,null,null,"Sta 823",800,"L","Purchase Power Conversion","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Higher than normal pressures in the area are probable during this outage.","SOP","Potential out of path restrictions may be at risk.",null,823.010009765625]
["X17-604939","***","2018-09-20T06:00:00","2018-10-20T18:00:00","Added",null,null,"MLV 824-1 to 825-1",800,"L","Pipe Recoat","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,832]
["X17-839912","***","2018-07-26T06:00:00","2018-09-08T18:00:00","Date Change","7/21/2018","9/3/2018","MLV 851-1 to MLV 852-1",800,"1","Spike Test","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,851]
["X18-58849","***","2018-09-08T06:00:00","2018-09-26T18:00:00","Date Change","9/3/2018","9/21/2018","MLV 851-1",800,"1","Drip Removal and Install New Valve","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,851]
["X17-858869","","2018-09-17T06:00:00","2018-09-17T17:00:00",null,null,null,"Sta 851",800,"1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,851]
["X17-858871","","2018-09-11T06:00:00","2018-09-12T18:00:00",null,null,null,"Sta 856",800,"1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,856]
["X17-852521","","2018-07-10T12:25:00","2018-07-17",null,null,null,"MLV 856-1 to MLV 859-1",800,"1","Pig runs - Cleaning 7/10/18, Gauge 7/11/18, MFL 7/12/18, Hard Spot 7/17/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,856.0999755859375]
["X18-558231","","2018-07-09T06:00:00","2018-07-13T18:00:00",null,null,null,"Sta 860: Unit 11A",800,"1","Replace Turbo Charger","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,860.010986328125]
["X17-838138","","2018-07-09T13:05:00","2018-07-20T13:05:00",null,null,null,"MLV 866-1D to MLV 871-1",800,"2","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,866]
["X17-838140","","2018-07-23T13:08:00","2018-08-31T13:08:00",null,null,null,"MLV 871-1 to MLV 876-1",800,"2","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,871]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]