{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["Export"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":2,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Export","index":0,"n_rows":499,"n_cols":16,"rows_kept":499,"cut":false,"hidden":false,"merged":[[2,1,2,15]]}
[null,"Updated ","2018-09-20"]
[null,"Tennessee Gas Pipeline 2018 Pipeline Outage and Maintenance Summary"]
[null,"This is a summary of the current status of all TGP 2018 Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  Additionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
[null,"*** Indicates revision"]
["Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","Location","Leg","Zone","Maintenance Activity","Anticipated Impact","Potential Restriction Level","TOS Potential Restrictions","Meter(s) in Impacted Area","Loc"]
["X18-475323","","2018-09-03T06:00:00","2018-10-19T18:00:00",null,null,null,"MLVS 1",100,"0","New Meter Tie-in","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,1]
["X17-839882","***","2018-01-18T09:58:00","2018-09-30T18:00:00","Date Change","1/18/2018","9/13/2018","MLV 1-1D to MLV 9-1S",100,"0","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,1.0099999904632568]
["X18-37920","***","2018-10-01T06:00:00","2018-10-07T18:00:00","Date Change","9/24/2018","9/30/2018","Sta 3A",100,"0","New Station Tie-In (100-2 line)","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,3.2000000476837158]
["X18-631513","***","2018-10-16T06:00:00","2018-10-30T18:00:00","Date Change","10/22/2018","10/30/2018","MLV 17-2 to MLV 9-2",100,"0","Pig runs - Cleaning 10/16 - 10/18, Gauge 10/19, Combo 10/30","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,10]
["X18-163553","","2018-10-02T06:00:00","2018-10-02T18:00:00",null,null,null,"Sta 17",100,"0","Annual ESD Test","This project will require the station outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,17]
["X17-857394","***","2018-09-25T06:00:00","2018-09-26T18:00:00","Date Change","9/18/2018","9/19/2018","Sta 25",100,"0","Annual ESD Test","This project will require the station outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,25]
["X18-231693","","2018-10-22T06:00:00","2018-10-27T18:00:00",null,null,null,"Sta 25: Station Maintenance",100,"0","Electrical Inspection","This project will require the station outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,25]
["X18-612385","***","2018-09-10T06:00:00","2018-09-15T18:00:00","Completed",null,null,"MLVS 25-1",100,"0","Install New Ball Valve - 100-1","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,25.100000381469727]
["X18-612387","","2018-09-15T06:00:00","2018-09-22T18:00:00",null,null,null,"MLVS 25-2",100,"0","Install New Ball Valve - 100-2","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,25.200000762939453]
["X18-612389","","2018-09-22T06:00:00","2018-09-29T18:00:00",null,null,null,"MLVS 25-3",100,"0","Install New Ball Valve - 100-3","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,25.299999237060547]
["X18-99331","","2019-01-07T11:40:00","2019-03-01T11:40:00",null,null,null,"MLVS 36-1",100,"0","Pipe Replacement and Install New Valve","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,36.099998474121094]
["X18-99333","","2018-10-22T11:45:00","2018-12-28T11:45:00",null,null,null,"MLVS 36-2",100,"0","Pipe Replacement and Install New Valve","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,36.200000762939453]
["X18-99335","","2018-08-13T11:48:00","2018-10-19T11:48:00",null,null,null,"MLVS 36-3",100,"0","Pipe Replacement and Install New Valve","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,36.299999237060547]
["X17-941241","","2018-09-28T06:00:00","2018-09-28T18:00:00",null,null,null,"Sta 40",100,"0","Annual ESD Test","This project will require the station outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,40]
["X17-852400","***","2018-07-30T06:00:00","2018-10-30T18:00:00","Date Change","7/30/2018","10/15/2018","MLV 40-3S to MLV 47-3",100,"1","Make Piggable","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,40.299999237060547]
["X18-340693","","2018-10-16T06:35:00","2018-10-23T06:35:00",null,null,null,"Beer Creek Storage",100,"1","Shut In Test","This project will require taking the facility out of service.  This will limit throughput and may result in restrictions based on customer nominations.   The meter listed below will be shut-in for the entire duration of the project.","SOP","Potential out of path restrictions may be at risk.","460017 STORAGE – BEAR CREEK",43.009998321533203]
["X18-687989","","2018-09-18T06:00:00","2018-10-19T18:00:00",null,null,null,"Sta 47",100,"1","Clean Suction Piping","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,47]
["X17-852604","","2018-10-15T06:00:00","2018-10-31T18:00:00",null,null,null,"MLV 53-3B to MLV 54-3D",100,"1","ECDA","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,53.299999237060547]
["X17-852405","","2018-10-08T06:00:00","2018-11-07T18:00:00",null,null,null,"MLV 54-4 to MLV 63-4",100,"1","Pig runs - Chem Cleaning 10/8/18 - 10/11/18, AFD 11/5/18, EMAT 11/7/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,54.400001525878906]
["X18-678802","","2018-10-09T05:00:00","2018-10-09T18:00:00",null,null,null,"MLV 71-3 to 63-3D",100,"1","Pig run - MDS 10/9","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,63.299999237060547]
["X17-852408","","2018-09-24T06:00:00","2018-10-04T18:00:00",null,null,null,"MLV 63-4D to MLV 71-4",100,"1","Pig runs - Chem Cleaning 9/24/18 - 9/27/18, AFD 10/2/18, EMAT 10/4/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,63.400001525878906]
["X17-857405","","2018-10-10T06:00:00","2018-10-10T18:00:00",null,null,null,"Sta 71",100,"1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,71]
["X18-681021","","2018-09-17T06:00:00","2018-09-28T18:00:00",null,null,null,"Sta 87: Unit 2A",100,"2","Replace Cracked Bolts in the Compressor","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,87.001998901367188]
["X18-642454","","2018-09-17T06:00:00","2018-09-21T18:00:00",null,null,null,"Sta 87: Unit 4C",100,"2","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,87.036003112792969]
["X18-642324","","2018-09-17T06:00:00","2018-09-20T18:00:00",null,null,null,"Sta 87: Building D",100,"2","Replace Scrubber Filters","This project will require a building outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,87.049003601074219]
["X18-642381","","2018-09-13T06:00:00","2018-09-23T18:00:00",null,null,null,"Sta 87: Unit 3D",100,"2","Bearing Protection System","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,87.051002502441406]
["X18-293073","***","2018-08-12T06:00:00","2018-09-12T18:00:00","Completed",null,null,"Sta 87: Unit 1E",100,"2","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,87.599998474121094]
["X18-342867","","2018-10-01T06:00:00","2018-10-08T18:00:00",null,null,null,"Sta 96: Unit 2D",100,"2","Electrical Panel Replacement","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,96.199996948242187]
["X17-838146","","2018-09-05T06:00:00","2018-09-30T18:00:00",null,null,null,"MLV 105-2L to MLV 106-2S",100,"2","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,105]
["X18-687851","***","2018-09-11T06:00:00","2018-09-13T18:00:00","Completed",null,null,"Sta 106",100,"2","ESD Test and Turbine Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106]
["X18-225447","","2018-04-02T06:00:00","2018-09-30T18:00:00",null,null,null,"Sta 106: Unit 1C",100,"2","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,106.33000183105469]
["X18-475249","","2018-07-31T06:00:00","2018-10-31T18:00:00",null,null,null,"MLV 108-2 to MLV 110-2",100,"2","Pipe Replacement","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.    The meter listed below will be shut-in for the entire duration of the project.","SOP","Potential out of path restrictions may be at risk.","420212 DELTA NG/TGP SALT LICK KY BATH\n420462 DELTA NG/TGP DELTA FARMERS KY ROWAN",108]
["X18-664519","***","2018-09-04T06:00:00","2018-09-17T18:00:00","Completed",null,null,"Sta 110",100,"2","Exciter Panel Upgrade","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,110]
["X18-571528","","2018-09-17T06:00:00","2018-11-04T18:00:00",null,null,null,"Sta 110",100,"2","Unit Controls Upgrade","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,110]
["X17-852411","","2018-10-10T08:44:00","2018-10-18T08:44:00",null,null,null,"MLV 111-3 to MLV 114-3",100,"2","Pig runs - Cleaning & Gauge Tool 10/10/18, AFD Tool 10/16/18, EMAT 10/18/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,111.30000305175781]
["X17-852467","","2018-06-04T06:00:00","2018-10-31T18:00:00",null,null,null,"MLV 118-3 to MLV 121-2",100,"3","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.  The meters listed below will be shut-in for the duration of the project.","SIP","Potential in the path restrictions may be at risk.",null,114.30000305175781]
["X18-767045","***","2018-09-17T06:00:00","2018-12-31T18:00:00","Added",null,null,"Sta 204: Unit 1A",200,"4","Repair Crankshaft","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,204.00100708007812]
["X18-769283","***","2018-09-24T06:00:00","2018-10-12T18:00:00","Added",null,null,"Sta 209: Unit 8A",200,"4","Turbo Charger Replacement","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,209.00799560546875]
["X18-651151","","2018-10-15T06:00:00","2018-10-19T06:00:00",null,null,null,"MLVS 213-4",200,"4","Remediation","This activity will require operating at reduced pressures. The meters listed may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,213.39999389648437]
["X17-840015","","2018-09-17T07:00:00","2018-10-09T18:00:00",null,null,null,"218-2 to 219-2",200,"4","Pipe Replacement","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,214]
["X18-571459","","2018-10-01T06:00:00","2018-10-03T18:00:00",null,null,null,"Sta 214",200,"4","Electrical Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,214]
["X18-734687","***","2018-09-10T06:00:00","2018-09-14T18:00:00","Completed",null,null,"Sta 214: Unit 7A",200,"4","Main Bearing Inspection","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,214.00700378417969]
["X18-753815","***","2018-09-12T09:32:00","2018-10-05T18:00:00","Date Change","9/12/2018","9/21/2018","Sta 214: Unit 8A",200,"4","Compressor Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,214.00799560546875]
["X17-852410","","2018-09-25T08:42:00","2018-10-25T08:42:00",null,null,null,"MLV 219-2D to MLV 307-1",300,"4","Pig runs  - Cleaning / Gauge 9/25/18, AFD 9/27/18, EMAT 10/25/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,219.19999694824219]
["X18-684115","","2018-10-08T06:00:00","2018-10-10T18:00:00",null,null,null,"MLV 219-3 to MLV 301-2",300,"4","SCCDA","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,219.30000305175781]
["X18-753903","","2018-10-24T06:00:00","2018-10-24T18:00:00",null,null,null,"MLVS 220-1",200,"4","New Meter Tie-In - TGP/RH Energytrans Interconnect Meadville","This activity will require operating at reduced pressures. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,220.10000610351562]
["X17-852547","***","2018-09-07T06:00:00","2018-09-13T18:00:00","Completed",null,null,"MLV 224-1 to MLV 229-1",200,"4","Pig runs  - Cleaning / Gauge 9/6, Caliper 9/11, MFL 9/13","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,224.10000610351562]
["X17-838129","","2018-10-01T06:00:00","2018-10-19T18:00:00",null,null,null,"MLV 230-1 to MLV 237-1",200,"5","Remediation","This activity will require operating at reduced pressures. The meters listed may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.","411106 HONEOYE/TGP STORAGE WDL ONTARIO\n420526 HONEOYE/TGP UDP HONEOYE NEW YORK ON\n412856 EMPIREPL/TGP CANANDAIGUA ONTARIO\n420617 DOMINION/TGP HOPEWELL SALES ONTARIO",230]
["X18-588453","","2018-10-08T06:00:00","2018-10-12T18:00:00",null,null,null,"Sta 230C: Unit 1A",200,"5","Fuel System Upgrade","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,230.00100708007812]
["X18-588452","***","2018-09-10T06:00:00","2018-09-14T18:00:00","Completed",null,null,"Sta 230C: Unit 2A",200,"5","Fuel System Upgrade","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,230.00199890136719]
["X18-588450","","2018-09-17T06:00:00","2018-09-28T18:00:00",null,null,null,"Sta 230C: Unit 3A",200,"5","Engine Overhaul and Fuel System Upgrade","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,230.00300598144531]
["X18-642792","***","2018-08-27T06:00:00","2018-09-15T18:00:00","Completed",null,null,"Sta 237: Unit 2A",200,"5","Fuel Injection System","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,237.00199890136719]
["X18-225574","","2018-09-24T06:00:00","2018-09-28T18:00:00",null,null,null,"MLV 313A-405A to MLV 313A-409",200,"5","Replace Actuators","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.  The meter listed below will be shut-in for the entire duration of the project.","SIP","Potential in the path restrictions may be at risk.","420644 NYSEG/TGP PRATTSBURG SALES STEUBEN\n420746 NYSEG/TGP WALLACE SALES STEUBEN",237.89999389648437]
["X18-603729","***","2018-08-20T06:00:00","2018-09-12T18:00:00","Completed",null,null,"Sta 241: Unit 2A",200,"5","Catalyst Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,241.00199890136719]
["X18-702179","***","2018-10-08T06:00:00","2018-10-12T18:00:00","Date Change","10/1/2018","10/5/2018","Sta 245: Unit 1C",200,"5","Repair Station Blow Off","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.  The meter station below will be shut-in as a result of this project.","SOP","Potential out of path restrictions may be at risk.",null,245.00100708007812]
["X18-702178","","2018-10-01T06:00:00","2018-10-16T18:00:00",null,null,null,"Sta 245: Unit 1C",200,"5","Filter Installation","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,245.0010986328125]
["X18-751220","","2018-09-27T06:00:00","2018-09-28T18:00:00",null,null,null,"Sta 245: Unit 1C",200,"5","Water Wash","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,245.03300476074219]
["X17-839914","","2018-09-05T10:55:00","2018-10-19T10:55:00",null,null,null,"MLV 251-1 to MLV 253-1",200,"5","Pressure Test","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,252]
["X18-155316","","2018-10-22T14:29:00","2018-10-24T14:29:00",null,null,null,"MLV 254-2 to MLV 261-2",200,"5","Pig runs  - Cleaning 10/22/18, EMAT 10/24/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,254.00399780273437]
["X18-769308","***","2018-10-23T06:00:00","2018-10-29T18:00:00","Added",null,null,"Sta 254: Unit 2B",200,"5","Protective Device - Unit will be unavailable 3 days: 10/22, 10/24, and 10/29","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,254.01800537109375]
["X18-736728","","2018-09-19T06:00:00","2018-09-20T18:00:00",null,null,null,"Sta 260A",200,"5","Preventative Maintenance for VFD","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.  The meter station below will be shut-in as a result of this project.","SOP","Potential out of path restrictions may be at risk.",null,260]
["X18-95516","","2018-10-01T08:50:00","2018-10-23T08:50:00",null,null,null,"Sta 261",200,"6","Automation Upgrade","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.  The meter station below will be shut-in as a result of this project.","SIP","Potential in the path restrictions may be at risk.","420901 BERKPWR/TGP BERKSHIRE POWER SALES H",261]
["X18-295176","","2018-09-10T15:30:00","2018-09-23T18:00:00",null,null,null,"Sta 261: C Building",200,"6","BPS Upgrade","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,261.01998901367187]
["X18-295172","","2018-09-10T06:00:00","2018-09-23T18:00:00",null,null,null,"Sta 261: C Building",200,"6","Silencer Replacement","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,261.04000854492187]
["X18-201904","***","2018-09-10T07:18:00","2018-09-14T07:18:00","Completed",null,null,"Sta 261: Unit Maintenance",200,"6","Water Wash","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,261.29998779296875]
["X18-201907","","2018-09-18T06:00:00","2018-09-20T18:00:00",null,null,null,"Sta 261: Unit Maintenance",200,"6","Boroscope Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,261.29998779296875]
["X18-201913","","2018-09-18T06:00:00","2018-09-21T18:00:00",null,null,null,"Sta 261: Unit 4A",200,"6","Compressor Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,261.39999389648437]
["X18-386485","","2018-09-23T06:00:00","2018-10-10T18:00:00",null,null,null,"Sta 261; Unit 4A",200,"6","Automation Upgrade","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,261.39999389648437]
["X18-201910","***","2018-09-19T06:00:00","2018-09-20T18:00:00","Completed",null,null,"Sta 264: Unit Maintenance",200,"6","Water Wash","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,264.10000610351562]
["X18-201911","","2018-09-25T06:00:00","2018-09-26T18:00:00",null,null,null,"Sta 264: Unit Maintenance",200,"6","Boroscope Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,264.20001220703125]
["X18-115706","","2018-11-05T08:44:00","2018-11-15T08:44:00",null,null,null,"265E",200,"6","4000 hr Inspection","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,265.20001220703125]
["X17-858878","","2018-10-02T06:00:00","2018-10-03T18:00:00",null,null,null,"Sta 266A",200,"6","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,266]
["X17-840013","","2019-05-10T14:43:00","2019-07-10T14:43:00",null,null,null,"267-1",200,"6","Class Change","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,267]
["X17-858882","","2018-10-23T10:31:00","2018-10-25T10:31:00",null,null,null,"Sta 270B",200,"6","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,270]
["X18-740456","","2018-10-15T06:00:00","2018-10-19T18:00:00",null,null,null,"Sta 303: Unit 1A",300,"4","Water Wash & Protective Device Testing","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,303.00100708007813]
["X18-736962","","2018-09-27T06:00:00","2018-09-27T18:00:00",null,null,null,"Sta 310: Unit 1A",300,"4","Water Wash","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,310.00100708007812]
["X18-653320","","2018-11-05T06:00:00","2018-11-09T18:00:00",null,null,null,"Ellisburg Storage",300,"4","Shut-in Test","This project will require taking the facility out of service.  This will limit throughput and may result in restrictions based on customer nominations.   The meter listed below will be shut-in for the entire duration of the project.","SOP","Potential out of path restrictions may be at risk.","460012 – DOMINION/TGP ELLISBURG INJECTION PO",312.70001220703125]
["X18-653321","","2018-10-08T06:00:00","2018-10-12T18:00:00",null,null,null,"Harrison Storage",300,"4","Shut-in Test","This project will require taking the facility out of service.  This will limit throughput and may result in restrictions based on customer nominations.   The meter listed below will be shut-in for the entire duration of the project.","SOP","Potential out of path restrictions may be at risk.","460004 – DOMINION/TGP HARRISON INJECTION POT",312.79998779296875]
["X18-653322","","2018-11-05T06:00:00","2018-11-09T18:00:00",null,null,null,"Hebron Storage",300,"4","Shut-in Test","This project will require taking the facility out of service.  This will limit throughput and may result in restrictions based on customer nominations.   The meter listed below will be shut-in for the entire duration of the project.","SOP","Potential out of path restrictions may be at risk.","400485 HEBRON STORAGE INJECTION POTTER\n470001 HEBRON STORAGE WITHDRAWAL POTTER",312.89999389648437]
["X17-893533","***","2018-09-17T06:00:00","2018-09-17T18:00:00","Completed",null,null,"Sta 313",300,"4","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,313]
["X18-769256","***","2018-09-24T06:00:00","2018-09-25T18:00:00","Added",null,null,"Sta 313: Unit 1C",300,"4","Electrical Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,313.03298950195312]
["X18-642575","","2018-10-15T06:00:00","2018-10-16T18:00:00",null,null,null,"Sta 405A",400,"5","Station Filter Separator Filter Change-Out","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,313.989990234375]
["X17-838123","***","2018-09-10T06:00:00","2018-09-15T18:00:00","Completed",null,null,"MLV 315-2 to MLV 317-2",300,"4","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,315]
["X18-666488","","2018-09-25T06:00:00","2018-09-27T18:00:00",null,null,null,"Sta 315",300,"4","Water Wash (1 Unit at a Time)","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,315]
["X18-770994","***","2018-10-29T06:00:00","2018-11-02T18:00:00","Added",null,null,"Sta 317: Unit 1B",300,"4","Utility Company needs to make infrastructure repairs","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,317.03298950195312]
["X18-489865","","2018-10-03T06:00:00","2018-10-05T18:00:00",null,null,null,"MLVS 318-1: Stagecoach/Latini",300,"4","Meter Tie-In","This activity will require operating at reduced pressures.  The meters listed may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.","420652 LSTOCKNG/TGP WYALUSING SALES BRADFO\n412769 APPLACHA/TGP EVANCHICK DEHY: RIP 31",318.10000610351562]
["X18-489869","","2018-10-08T06:00:00","2018-10-10T18:00:00",null,null,null,"MLVS 318-2: Stagecoach/Latini",300,"4","Meter Tie-In","This activity will require operating at reduced pressures. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,318.20001220703125]
["X18-236957","","2018-09-03T07:06:00","2018-09-07T07:06:00",null,null,null,"Sta 321: Unit 1C",300,"4","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,321.10000610351562]
["X17-901424","***","2018-09-19T06:00:00","2018-09-19T18:00:00","Completed",null,null,"Sta 323A",300,"4","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,323]
["X18-648493","","2018-10-01T07:00:00","2018-10-04T18:00:00",null,null,null,"Sta 323 Unit 2A",300,"4","Substation inspection work","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,323.00201416015625]
["X18-236963","","2018-09-17T06:00:00","2018-09-20T18:00:00",null,null,null,"Sta 323A: Unit 2A",300,"4","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,323.10000610351562]
["X18-475332","","2018-09-04T06:00:00","2018-10-19T18:00:00",null,null,null,"Sta 409",400,"0","Adding Gas Coolers","This project will require the station outage, which could limit throughput through the station and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,409]
["X17-839889","","2018-09-25T06:00:00","2018-10-05T18:00:00",null,null,null,"MLV 409A-101 TO MLV 409A-103",400,"0","Remediation","This project could require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,409]
["X17-852598","***","2018-08-31T06:00:00","2018-09-28T18:00:00","Completed",null,null,"MLV 409A-101.1 to MLV 409A-102",400,"0","SCCDA","This project could require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,409.10101318359375]
["X18-678769","***","2018-09-13T06:00:00","2018-09-13T18:00:00","Completed",null,null,"Sta 504",500,"L","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,504]
["X18-381281","","2018-11-01T06:00:00","2018-11-16T18:00:00",null,null,null,"MLVS 522-1",500,"L","Repair Line Covering","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,522]
["X18-381434","","2018-10-01T06:00:00","2018-10-31T06:00:00",null,null,null,"MLVS 528-1",500,"L","Line Lowering","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,528]
["X18-75131","***","2018-09-24T06:00:00","2018-10-02T18:00:00","Date Change","9/24/2018","9/29/2018","Sta 542",500,"1","Station Maintenance","This project will require the station outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,542]
["X17-858832","","2018-09-24T06:00:00","2018-09-24T18:00:00",null,null,null,"Sta 542",500,"1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,542]
["X18-770997","***","2018-09-25T06:00:00","2018-09-25T18:00:00","Added",null,null,"Sta 542",500,"1","Repair ESD Vent","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,542]
["X18-192975","","2018-07-16T06:00:00","2018-11-09T18:00:00",null,null,null,"Sta 542: Unit 1B",500,"1","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,542.5]
["X17-858904","***","2018-10-09T06:00:00","2018-10-10T18:00:00","Date Change","9/18/2018","9/19/2018","Sta 546",500,"1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,546]
["X18-59187","","2018-08-20T06:00:00","2018-09-26T18:00:00",null,null,null,"Sta 546: Unit 2A",500,"1","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,546.20001220703125]
["X18-59188","***","2018-08-27T06:00:00","2018-09-14T18:00:00","Completed",null,null,"Sta 546: Unit 4A",500,"1","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,546.4000244140625]
["X18-472029","","2018-06-04T06:00:00","2018-10-31T18:00:00",null,null,null,"Sta 550: Unit 1A",500,"1","Regrout","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,550.0009765625]
["X18-707684","","2018-08-28T06:00:00","2018-10-30T18:00:00",null,null,null,"Sta 550: Unit 4A",500,"1","Oil Pump Repair","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,550.0040283203125]
["X18-736884","","2018-09-13T06:00:00","2018-09-28T18:00:00",null,null,null,"MLV 563-2 to MLV 565-2",500,"1","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,562]
["X17-852512","","2018-10-15T12:10:00","2018-10-22T12:10:00",null,null,null,"MLV 700-1 to MLV 706-1",700,"0","Pig runs  - Cleaning / Gauge 10/15/18 - 10/17/18, Combo 10/18/18, Hard Spot Tool 10/22/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,700.0999755859375]
["X18-571582","","2018-11-05T06:00:00","2018-11-20T18:00:00",null,null,null,"MLV 820 to MLV 823",800,"L","KS Line Trap Installation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.  The meters listed below will be shut-in for the duration of the project.","SOP","Potential out of path restrictions may be at risk.","412013 ENTRPRSE/TGP SABINE RIVER TRANS NEW\n420550 ENTRPRSE/TGP SABINE RIVER (1 6179\n412690 HPL/TGP SABINE NEWTON\n412737 CAM IPL/TGP DEQUINCY GAS STORAGE C\n412015 HEC/TGP STARKS HANKAMER 1 CALCASIE\n411586 TRNSCO/TGP STARKS LA TRANSPORT CALC\n420581 ENTRGYLA/TGP BECKWITH CREEK CALCASI\n49446 CAM IPL/TGP BANKEN RD AT  HWY 27 DE",820]
["X18-571584","","2018-10-22T06:00:00","2018-10-29T18:00:00",null,null,null,"Sta 823",800,"L","Modify ESD System","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Higher than normal pressures in the area are probable during this outage.","SOP","Potential out of path restrictions may be at risk.",null,823]
["X18-764319","***","2018-10-29T06:00:00","2018-11-05T18:00:00","Added",null,null,"Sta 823",800,"L","Modify ESD System","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Higher than normal pressures in the area are probable during this outage.","SOP","Potential out of path restrictions may be at risk.",null,823.0009765625]
["X17-914206","","2018-10-15T06:00:00","2018-10-22T06:00:00",null,null,null,"Sta 823",800,"L","Purchase Power Conversion","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Higher than normal pressures in the area are probable during this outage.","SOP","Potential out of path restrictions may be at risk.",null,823.010009765625]
["X17-604939","","2018-09-04T06:00:00","2018-10-16T18:00:00",null,null,null,"MLV 824-1 to 825-1",800,"L","Pipe Recoat","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,832]
["X17-858869","","2018-10-15T06:00:00","2018-10-15T18:00:00",null,null,null,"Sta 851",800,"1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,851]
["X17-858871","","2018-08-28T06:00:00","2018-08-30T18:00:00",null,null,null,"Sta 856",800,"1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,856]
["X18-707602","","2018-09-20T06:00:00","2018-09-21T18:00:00",null,null,null,"Sta 860",800,"1","Discharge Header Inspection","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,860]
["X18-558231","","2018-07-09T06:00:00","2018-09-21T18:00:00",null,null,null,"Sta 860: Unit 11A",800,"1","Replace Turbo Charger","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,860.010986328125]
["X17-838138","","2018-08-20T06:00:00","2018-09-26T18:00:00",null,null,null,"MLV 866-1D to MLV 871-1",800,"2","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,866]
["X17-838140","","2018-08-16T06:00:00","2018-09-30T18:00:00",null,null,null,"MLV 871-1 to MLV 876-1",800,"2","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,871]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]