{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["Export"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":2,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Export","index":0,"n_rows":499,"n_cols":16,"rows_kept":499,"cut":false,"hidden":false,"merged":[[2,1,2,15]]}
[null,"Updated ","2018-11-08"]
[null,"Tennessee Gas Pipeline 2018 Pipeline Outage and Maintenance Summary"]
[null,"This is a summary of the current status of all TGP 2018 Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  Additionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
[null,"*** Indicates revision"]
["Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","Location","Leg","Zone","Maintenance Activity","Anticipated Impact","Potential Restriction Level","TOS Potential Restrictions","Meter(s) in Impacted Area","Loc"]
["X18-475323","***","2018-09-03T06:00:00","2018-11-16T18:00:00","Date Change","9/3/2018","11/13/2018","MLVS 1",100,"0","New Meter Tie-in","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations. The welding and taping will be 11/8 to 11/13.","SIP","Potential in the path restrictions may be at risk.",null,1]
["X17-852571","","2018-11-27T06:00:00","2018-12-04T18:00:00",null,null,null,"MLV 1-2 to MLV 5-2",100,"0","Pig runs  - Cleaning 11/27 - 11/28, Gauge 11/29, MFL 12/4","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  During the pig run, the NET meter (47799) will be fed from line 1 only, the Shoup meter (412669) will be shut-in completely.",null,null,"47799   NET MEXI/TGP GILLRINA ROAD NUECES\n412669  ETP/TGP SHOUP NUECES",1.2000000476837158]
["X17-852537","","2018-11-06T06:00:00","2018-11-15T18:00:00",null,null,null,"MLV 5-2 to MLV 8-2",100,"0","Pig runs  - Cleaning 11/6 - 11/7, Gauge 11/8, MFL 11/13 , Hard Spot 11/15","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,null,null,5.1999998092651367]
["X18-528002","","2018-12-03T06:00:00","2018-12-15T18:00:00",null,null,null,"Sta 9",100,"0","Install New Valves","This project will require the station outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,9]
["X18-863040","***","2018-11-06T06:00:00","2018-11-06T18:00:00","Completed",null,null,"MLV 32-1 to MLV 25-1",100,"0","Pig - Brush and Disc","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,32.099998474121094]
["X18-863042","***","2018-11-01T06:00:00","2018-11-01T18:00:00","Completed",null,null,"MLV 32-3 to MLV 25-3",100,"0","Pig - Brush and Disc","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The following meters will be temporarily shut-in as the pig passes.","SOP","Potential out of path restrictions may be at risk.","412738 TECOGATH/TGP TECO INDIAN SPRINGS PO\n412747 GEOPETRA/TGP DREWS LANDING NO 2: RI",32.299999237060547]
["X18-99331","","2019-01-07T11:40:00","2019-03-01T11:40:00",null,null,null,"MLVS 36-1",100,"0","Pipe Replacement and Install New Valve","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,36.099998474121094]
["X18-99333","","2018-10-09T06:00:00","2018-12-14T18:00:00",null,null,null,"MLVS 36-2",100,"0","Pipe Replacement and Install New Valve","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,36.200000762939453]
["X17-852400","***","2018-07-30T06:00:00","2018-11-21T18:00:00","Date Change","7/30/2018","11/15/2018","MLV 40-3S to MLV 47-3",100,"1","Make Piggable","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,40.299999237060547]
["X17-852604","","2018-10-15T06:00:00","2018-11-12T18:00:00",null,null,null,"MLV 53-3B to MLV 54-3D",100,"1","ECDA","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,53.299999237060547]
["X18-820044","","2018-11-08T06:00:00","2018-11-08T18:00:00",null,null,null,"Sta 54",100,"1","Sub-Station Inspection","This project will require a building outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,54]
["X17-852405","***","2018-10-10T06:00:00","2018-12-12T18:00:00","Date Change","10/10/2018","11/7/2018","MLV 54-4 to MLV 63-4",100,"1","Pig runs - Chem Cleaning 10/10 - 10/13, Gauge 12/6, AFD 12/10, EMAT 12/12","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,54.400001525878906]
["X17-854319","","2018-11-12T06:00:00","2018-11-23T18:00:00",null,null,null,"Meter Station #2-0142",100,"1","Replace Gate Valve","This project will require taking the meter station out of service.  The meter listed below will be shut-in for the duration of the project.","SOP","Potential out of path restrictions may be at risk.","420142 – CPTENTEX/TGP RULEVILLE MS SUNFLOWER",57.099998474121094]
["X18-909920","***","2018-11-15T06:00:00","2018-11-17T18:00:00","Added",null,null,"Sta 79",100,"1","Blowdown Silencer","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,79]
["X18-681021","","2018-10-15T06:00:00","2018-11-09T18:00:00",null,null,null,"Sta 87: Unit 2A",100,"2","Replace Cracked Bolts in the Compressor","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,87.001998901367188]
["X18-863044","***","2018-10-29T06:00:00","2018-11-09T18:00:00","Date Change","10/29/2018","11/2/2018","Sta 87: Unit 4C",100,"2","Repair Packing Leaks","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,87.036003112792969]
["X17-838142","","2018-10-08T06:00:00","2018-11-09T18:00:00",null,null,null,"MLV 87-1D to MLV 96-1S",100,"2","Remediation","This activity will require operating at reduced pressures. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,87.599998474121094]
["X18-808807","","2018-10-22T06:00:00","2018-11-19T18:00:00",null,null,null,"MLV 102-1A to MLV 103-1",100,"2","Remediation","This activity will require operating at reduced pressures. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,102.09999847412109]
["X18-903443","***","2018-11-13T06:00:00","2018-11-13T18:00:00","Added",null,null,"Sta 106",100,"2","Building B - Repair Fuel Saver System","This project will require a building outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106.01699829101562]
["X18-225447","***","2018-04-02T06:00:00","2018-12-01T18:00:00","Date Change","4/2/2018","11/1/2018","Sta 106: Unit 1C",100,"2","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,106.33000183105469]
["X18-475249","","2018-07-31T06:00:00","2018-11-20T18:00:00",null,null,null,"MLV 108-2 to MLV 110-2",100,"2","Pipe Replacement","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.    The meters listed below will be shut-in for the entire duration of the project.","SOP","Potential out of path restrictions may be at risk.","420212 DELTA NG/TGP SALT LICK KY BATH\n420462 DELTA NG/TGP DELTA FARMERS KY ROWAN",108]
["X18-767045","","2018-09-17T06:00:00","2019-02-15T18:00:00",null,null,null,"Sta 204: Unit 1A",200,"4","Repair Crankshaft","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,204.00100708007812]
["X18-845241","***","2018-11-05T06:00:00","2018-11-15T18:00:00","Date Change","11/5/2018","11/10/2018","Sta 204: Unit 11A",200,"4","Crankcase Inspection","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,204.01100158691406]
["X18-769283","","2018-10-29T06:00:00","2018-11-09T18:00:00",null,null,null,"Sta 209: Unit 8A",200,"4","Turbo Charger Replacement","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,209.00799560546875]
["X18-821881","","2018-09-23T12:30:00","2018-11-09T18:00:00",null,null,null,"Sta 209: Unit 13A",200,"4","Compressor Repair","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,209.01300048828125]
["X18-764396","***","2019-04-03T06:00:00","2019-04-09T18:00:00","Added",null,null,"MLV 209-2 TO MLV 214-2",200,"4","Pig Runs  - Cleaning 4/3/19, Gauge 4/4/19, AFE 4/9/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,209.19999694824219]
["X18-895603","***","2018-11-05T06:00:00","2018-11-08T18:00:00","Date Change","11/5/2018","11/5/2018","Sta 214: Unit 5A",200,"4","Engine Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,214.0050048828125]
["X18-910041","***","2018-11-12T06:00:00","2018-11-16T18:00:00","Added",null,null,"Sta 214: Unit 11A",200,"4","Engine Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,214.01100158691406]
["X17-840015","***","2018-09-17T07:00:00","2018-11-10T18:00:00","Date Change","9/17/2018","11/7/2018","218-2 to 219-2",200,"4","Pipe Replacement","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,218]
["X18-895545","***","2018-11-05T06:00:00","2018-11-09T18:00:00","Completed",null,null,"Sta 219: Unit 9A",200,"4","Crankcase Inspection","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,219.00900268554688]
["X18-753903","***","2018-11-07T06:00:00","2018-11-21T18:00:00","Date Change","11/7/2018","11/7/2018","MLVS 220-1",200,"4","New Meter Tie-In - TGP/RH Energytrans Interconnect Meadville","This activity will require operating at reduced pressures. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,220.10000610351562]
["X18-820101","","2018-11-05T06:00:00","2018-11-16T18:00:00",null,null,null,"Sta 224",200,"5","Jacket Water Fan Motor","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,224]
["X18-862209","***","2018-11-01T06:00:00","2018-11-01T18:00:00","Completed",null,null,"Sta 237",200,"5","Repair Header","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,237]
["X18-880669","","2018-11-04T06:00:00","2018-11-08T18:00:00",null,null,null,"Sta 241: Unit 3A",200,"5","Replace Compressor Packing","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,241.00300598144531]
["X18-862302","***","2018-11-05T06:00:00","2018-11-05T18:00:00","Completed",null,null,"Sta 249",200,"5","Voltage Regulator Repair","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,249]
["X18-862213","***","2018-11-01T06:00:00","2018-11-06T18:00:00","Completed",null,null,"Sta 249: Unit 2A",200,"5","Replace Unit Valve Operators","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,249.01699829101562]
["X18-769308","***","2018-11-07T06:00:00","2018-11-07T18:00:00","Completed",null,null,"Sta 254: Unit 2B",200,"5","Protective Device Inspections","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,254.01800537109375]
["X18-386485","***","2018-09-23T06:00:00","2018-11-09T18:00:00","Date Change","9/23/2018","11/2/2018","Sta 261; Unit 4A",200,"6","Automation Upgrade","This project will require a unit outage.  The meter listed below may experience pressure fluctuations including low pressures on Wednesday (10/31/18) through Friday (11/2/18).","SIP","Potential in the path restrictions may be at risk.","420901 BERKPWR/TGP BERKSHIRE POWER SALES H",261.39999389648437]
["X18-115706","","2018-11-05T06:00:00","2018-11-15T18:00:00",null,null,null,"265E",200,"6","4000 hr Inspection","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,265.20001220703125]
["X17-840013","","2019-05-10T14:43:00","2019-07-10T14:43:00",null,null,null,"267-1",200,"6","Class Change","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,267]
["X18-863131","***","2018-10-29T05:00:00","2018-11-02T18:00:00","Completed",null,null,"Sta 307: Unit 5A",200,"6","Replace Compressor Packing","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,307.0050048828125]
["X18-895564","","2018-11-05T06:00:00","2018-11-09T18:00:00",null,null,null,"Sta 307: Unit 6A",200,"6","Crankcase Inspection","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,307.00601196289062]
["X18-653320","","2018-11-05T06:00:00","2018-11-09T18:00:00",null,null,null,"Ellisburg Storage",300,"4","Shut-in Test","This project will require taking the facility out of service.  This will limit throughput and may result in restrictions based on customer nominations.   The meter listed below will be shut-in for the entire duration of the project.","SOP","Potential out of path restrictions may be at risk.","460012 – DOMINION/TGP ELLISBURG INJECTION PO",312.70001220703125]
["X18-653322","","2018-11-05T06:00:00","2018-11-09T18:00:00",null,null,null,"Hebron Storage",300,"4","Shut-in Test","This project will require taking the facility out of service.  This will limit throughput and may result in restrictions based on customer nominations.   The meters listed below will be shut-in for the entire duration of the project.","SOP","Potential out of path restrictions may be at risk.","400485 HEBRON STORAGE INJECTION POTTER\n470001 HEBRON STORAGE WITHDRAWAL POTTER",312.89999389648437]
["X18-851198","***","2018-10-29T06:00:00","2018-11-02T18:00:00","Completed",null,null,"Sta 317: Unit 1B",300,"4","Electrical Company Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,317.01699829101562]
["X18-770994","","2018-10-27T06:00:00","2018-11-08T18:00:00",null,null,null,"Sta 317: Unit 1B",300,"4","Utility Company needs to make infrastructure repairs","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,317.03298950195312]
["X18-906080","***","2018-11-19T12:25:00","2018-11-21T12:25:00","Added",null,null,"Sta 321: Unit 1C",300,"4","Replace Speed Probes in Unit 1C","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,321.03298950195312]
["X18-571586","","2018-11-01T06:00:00","2018-12-20T18:00:00",null,null,null,"Sta 504: Unit 2B",500,"L","Controls upgrade & convert to simple cycle","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,504]
["X18-381281","***","2018-12-10T06:00:00","2018-12-15T18:00:00","Date Change","11/5/2018","11/10/2018","MLVS 522-1",500,"L","Repair Line Covering","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,522]
["X17-915835","","2018-11-08T06:00:00","2018-11-08T18:00:00",null,null,null,"Sta 527",500,"L","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,527]
["X18-381434","","2018-11-05T06:00:00","2018-12-07T06:00:00",null,null,null,"MLVS 528-1",500,"L","Line Lowering","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,528]
["X18-192975","","2018-07-16T06:00:00","2018-11-09T18:00:00",null,null,null,"Sta 542: Unit 1B",500,"1","Unit Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,542.5]
["X18-865810","","2018-11-27T06:00:00","2018-11-28T18:00:00",null,null,null,"Sta 550",500,"1","Install ESD Valves","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,550]
["X18-472029","","2018-06-04T06:00:00","2018-11-30T18:00:00",null,null,null,"Sta 550: Unit 1A",500,"1","Regrout","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,550.0009765625]
["X18-707684","","2018-08-28T06:00:00","2018-11-08T18:00:00",null,null,null,"Sta 550: Unit 4A",500,"1","Oil Pump Repair","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,550.0040283203125]
["X18-571582","","2018-11-05T06:00:00","2018-11-20T18:00:00",null,null,null,"MLV 820 to MLV 823",800,"L","KS Line Trap Installation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.  The meters listed below will be shut-in for the duration of the project.","SOP","Potential out of path restrictions may be at risk.","412013 ENTRPRSE/TGP SABINE RIVER TRANS NEW\n412690 HPL/TGP SABINE NEWTON\n412015 HEC/TGP STARKS HANKAMER 1 CALCASIE\n411586 TRNSCO/TGP STARKS LA TRANSPORT CALC\n49446 CAM IPL/TGP BANKEN RD AT  HWY 27 DE\n412839 DUNCAN/TGP LABOKAY NO. 1: RIP 820P\n401366 TRNSCO/TGP UTOS EXCH\n412588 CSVHOLDG/TGP STARKS CALCASIEU\n412737 CAM IPL/TGP DEQUINCY GAS STORAGE C\n412717 MAYNE/.TGP BURLINGTON CALCASIEU",820]
["X18-571584","***","2018-10-29T06:00:00","2018-11-08T18:00:00","Date Change","10/29/2018","11/5/2018","Sta 823",800,"L","Modify ESD System","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Higher than normal pressures in the area are probable during this outage.","SOP","Potential out of path restrictions may be at risk.",null,823]
["X18-903293","***","2018-11-19T06:00:00","2018-11-19T18:00:00","Added",null,null,"Sta 823",800,"L","Purchase Power Tie-In","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,823]
["X18-764319","","2018-11-05T06:00:00","2018-11-12T18:00:00",null,null,null,"Sta 823",800,"L","Modify ESD System","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Higher than normal pressures in the area are probable during this outage.","SOP","Potential out of path restrictions may be at risk.",null,823.0009765625]
["X17-914206","***","2018-10-29T06:00:00","2018-11-05T06:00:00","Completed",null,null,"Sta 823",800,"L","Purchase Power Conversion","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Higher than normal pressures in the area are probable during this outage.","SOP","Potential out of path restrictions may be at risk.",null,823.010009765625]
["X17-858869","***","2018-11-27T06:00:00","2018-11-27T18:00:00","Date Change","11/6/2018","11/6/2018","Sta 851",800,"1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,851]
["X18-865808","","2018-11-29T06:00:00","2018-11-30T18:00:00",null,null,null,"Sta 851",800,"1","Install ESD Blowdown Valve","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,851]
["X18-860579","","2018-11-21T06:00:00","2018-11-29T18:00:00",null,null,null,"MLV 854-1 to MLV 851-1",800,"1","Pig runs - Cleaning 11/21, Gauge 11/22, ILI 11/27 & 11/29","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,851.0999755859375]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]