{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["Export"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":2,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Export","index":0,"n_rows":499,"n_cols":16,"rows_kept":499,"cut":false,"hidden":false,"merged":[[2,1,2,15]]}
[null,"Updated ","2019-01-17"]
[null,"Tennessee Gas Pipeline 2019 Pipeline Outage and Maintenance Summary"]
[null,"This is a summary of the current status of all TGP 2019 Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  Additionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
[null,"*** Indicates revision"]
["Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","Location","Leg","Zone","Maintenance Activity","Anticipated Impact","Potential Restriction Level","TOS Potential Restrictions","Meter(s) in Impacted Area","Loc"]
["X19-21058","***","2019-01-14T06:00:00","2019-01-14T18:00:00","Completed",null,null,"Sta 3A",100,"0","Station Maintenance","This project will require a 12 hour station outage with no anticipated customer impact.","SOP","Potential out of path restrictions may be at risk.",null,3]
["X18-764335","","2019-05-21T06:00:00","2019-05-29T18:00:00",null,null,null,"MLV 9-3D TO MLV 11-3",100,"0","Pig run - Cleaning 5/21/19 - 5/24/19, Gauge 5/24/19, MFL 5/29/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,9.3000001907348633]
["X18-764338","","2019-05-07T08:00:00","2019-05-16T18:00:00",null,null,null,"MLV 13-3 TO MLV 17-3S",100,"0","Pig run - Cleaning 5/7/19 - 5/10/19, Gauge 5/10/19, MFL 5/14/19, Hard Spot 5/16/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,13.300000190734863]
["X18-820161","","2019-09-12T06:00:00","2019-09-26T18:00:00",null,null,null,"MLV 17-2 to MLV 9-2D",100,"0","Pig runs - Chem Clean 9/12/19 - 9/18/19, Gauge 9/20/19, AFD 9/24/19, EMAT 9/26/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,14.199999809265137]
["X19-27283","","2019-07-15T06:00:00","2019-07-24T18:00:00",null,null,null,"MLV 17-1 to MLV 14-1",100,"0","Pig Run - Cleaning 7/15 - 7/20, Gauge 4/23, EMAT 7/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,17]
["X18-764344","","2019-08-27T06:00:00","2019-08-29T18:00:00",null,null,null,"MLV 27A-101.3 TO MLV27A-102",100,"0","Pig run - Cleaning 8/27/19, Gauge 8/27/19, MFL 8/29/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,27.100000381469727]
["X18-820125","","2019-10-15T06:00:00","2019-10-24T18:00:00",null,null,null,"MLV 32-2D to MLV 40-2S",100,"0","Wrinkle Bend","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,32.200000762939453]
["X18-99331","","2019-01-15T06:00:00","2019-03-08T18:00:00",null,null,null,"MLVS 36-1",100,"0","Pipe Replacement and Install New Valve","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,36.099998474121094]
["X17-852400","","2018-07-30T06:00:00","2019-01-31T18:00:00",null,null,null,"MLV 40-3S to MLV 47-3",100,"1","Make Piggable","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,40.299999237060547]
["X18-922256","","2019-04-23T06:00:00","2019-04-29T18:00:00",null,null,null,"Bear Creek Storage",100,"1","Shut-in Test","This project will require taking the facility out of service.  This will limit throughput and may result in restrictions based on customer nominations.  The meter listed below will be shut-in for the duration of the project.","SOP","Potential out of path restrictions may be at risk.","460017 STORAGE – BEAR CREEK",43]
["X18-922260","","2019-10-15T06:00:00","2019-10-21T18:00:00",null,null,null,"Bear Creek Storage",100,"1","Shut-in Test","This project will require taking the facility out of service.  This will limit throughput and may result in restrictions based on customer nominations.  The meter listed below will be shut-in for the duration of the project.","SOP","Potential out of path restrictions may be at risk.","460017 STORAGE – BEAR CREEK",43]
["X18-684231","","2019-04-02T06:00:00","2019-04-23T18:00:00",null,null,null,"MLV 54-2D TO MLV 63-2S",100,"1","Pig run - Cleaning 4/2/19 - 4/5/19, Gauge 4/5/19, MFL 4/16/19, Hard Spot 4/23/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,54.200000762939453]
["X18-764371","","2019-04-10T06:00:00","2019-04-10T18:00:00",null,null,null,"MLV 54-2D TO MLV 63-2S",100,"1","Pig run - AFD 4/10/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,54.200000762939453]
["X17-854319","","TBD","TBD",null,null,null,"Meter Station #2-0142",100,"1","Replace Gate Valve","This project will require taking the meter station out of service.  The meter listed below will be shut-in for the duration of the project.","SOP","Potential out of path restrictions may be at risk.","420142 – CPTENTEX/TGP RULEVILLE MS SUNFLOWER",57.099998474121094]
["X18-1003978","***","2019-01-07T06:00:00","2019-01-11T18:00:00","Completed",null,null,"Sta 63",100,"1","Replace compressor packing on unit 2D","This project will require a building outage, which will limit throughput through the station and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,63]
["X18-764366","","2019-02-28T06:00:00","2019-03-07T18:00:00",null,null,null,"MLV 71-4S TO MLV 63-4D",100,"1","Pig Runs - Cleaning 2/28/19, Gauge 3/1/19, MFL 3/4/19, Hard Spot 3/7/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,63.400001525878906]
["X18-684174","","2019-02-25T08:00:00","2019-02-26T18:00:00",null,null,null,"MLV 69-1R TO 69-1L",100,"1","Pig run - Cleaning/Gauge 2/25/19, MFL 2/26/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,69.099998474121094]
["X18-684176","","2019-03-11T06:00:00","2019-03-19T18:00:00",null,null,null,"MLV 79-2S TO MLV 71-2D",100,"1","Pig run - Cleaning 3/11/19, Gauge 3/12/19, MFL 3/13/19, Hard Spot 3/19/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,71.199996948242187]
["X18-764369","","2019-03-28T06:00:00","2019-03-28T18:00:00",null,null,null,"MLV 71-2D TO MLV 79-2S",100,"1","Pig Runs - AFD 3/28/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,71.199996948242187]
["X18-684202","","2019-03-15T06:00:00","2019-03-26T18:00:00",null,null,null,"MLV 78-4 TO MLV 71-4D",100,"1","Pig run - Cleaning 3/15/19, Gauge 3/18/19, MFL 3/21/19, Hard Spot 3/26/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,71.400001525878906]
["X18-764341","","2019-04-01T06:00:00","2019-04-15T18:00:00",null,null,null,"MLV 82-1 TO MLV 79-1D",100,"1","Pig Runs - Cleaning 4/1/19, Gauge 4/2/19, Combo 4/3/19, Hard Spot 4/8/19, AFD 4/10/19, Caliper 4/12/19, MDS 4/15/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,79.099998474121094]
["X18-764375","","2019-04-10T06:00:00","2019-04-10T18:00:00",null,null,null,"MLV 79-1D TO MLV 82-1",100,"1","Pig Runs - AFD 4/10/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,79.099998474121094]
["X18-686555","***","2019-07-23T06:00:00","2019-07-31T18:00:00","Added",null,null,"MLVS 80A-100",100,"1","Remediaton","This activity will include pipe inspections and repairs, as needed, in specified areas. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,80.099998474121094]
["X19-44779","***","2019-01-22T06:00:00","2019-02-01T18:00:00","Added",null,null,"Sta 87: Unit 6C",100,"1","Compressor Pistons and Rods Replacement","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,87.038002014160156]
["X18-764376","","2019-07-09T06:00:00","2019-07-30T18:00:00",null,null,null,"MLV 96-1S TO MLV 87-1D",100,"2","Pig Runs - Cleaning 7/9/19, Caliper 7/16/19, MDS 7/30/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,87.099998474121094]
["X18-820127","","2019-07-18T06:00:00","2019-08-01T18:00:00",null,null,null,"MLV 96-2S to MLV 87-2D",100,"2","Pig Runs - Caliper 7/18/19, MDS 8/1/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,87.199996948242188]
["X19-27231","","2019-06-05T06:00:00","2019-06-18T18:00:00",null,null,null,"MLV 95-2 to MLV 87-2D",100,"2","Pig Runs - Cleaning 6/5, AFD 6/12, EMAT 6/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,95]
["X18-684256","","2019-04-02T06:00:00","2019-04-09T18:00:00",null,null,null,"MLV 106-1S TO MLV 96-1D",100,"2","Pig run - Cleaning 4/2/19, MFL 4/4/19, Hardspot 4/9/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,96.099998474121094]
["X18-820117","","2019-05-22T06:00:00","2019-06-01T18:00:00",null,null,null,"MLV 96-1D TO MLV 106-1S",100,"2","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,96.099998474121094]
["X18-764365","","2019-06-04T06:00:00","2019-06-04T18:00:00",null,null,null,"MLV 106-1S TO MLV 96-1D",100,"2","Pig Runs - AFD 6/4/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,96.099998474121094]
["X18-764424","","2019-04-29T06:00:00","2019-05-18T18:00:00",null,null,null,"MLV 106-1D TO MLV 111-7R",100,"2","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106.09999847412109]
["X18-684227","","2019-03-18T06:00:00","2019-03-26T18:00:00",null,null,null,"MLV 110-2 TO MLV 106-2D",100,"2","Pig run - Cleaning 3/18/19, Gauge 3/19/19, MFL 3/21/19, Hardspot 3/26/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,106.19999694824219]
["X19-19121","***","2019-01-07T06:00:00","2019-01-18T18:00:00","Date Change","1/7/2019","1/11/2019","Sta 107A : Unt 1A",100,"2","BPS Upgrade","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,107]
["X19-27238","","2019-02-04T06:00:00","2019-02-07T18:00:00",null,null,null,"MLV 113-3 to MLV 111-3",100,"2","Pig Runs - Cleaning & Gauge 2/4, AFD 2/5, EMAT 2/7","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,113]
["X18-684305","","2019-07-08T06:00:00","2019-07-20T18:00:00",null,null,null,"MLVS 117-1",100,"3","ECDA","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,117.09999847412109]
["X18-686533","","2019-08-20T06:00:00","2019-08-21T18:00:00",null,null,null,"MLV 121-2A to MLV 119-2",100,"3","Pig run - Cleaning 8/20/19, MDS 8/21/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,119.19999694824219]
["X18-767045","","2018-09-17T06:00:00","2019-02-15T18:00:00",null,null,null,"Sta 204: Unit 1A",200,"4","Repair Crankshaft","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,204.00100708007812]
["X18-764349","","2019-09-10T06:00:00","2019-09-17T18:00:00",null,null,null,"MLV 209-1 TO MLV 204-1",200,"4","Pig Runs - Cleaning/Gauge 9/10/19, MFL/AFD 9/12/19, Hardspot/EMAT 9/17/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,204.10000610351562]
["X18-684232","","2019-07-16T06:00:00","2019-07-23T18:00:00",null,null,null,"MLV 209-2 TO MLV 204-2",200,"4","Pig Run - Cleaning/Gauge 7/16/19, MFL/AFD 7/18/19, Hardspot/EMAT 7/23/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,204.19999694824219]
["X18-684167","","2019-06-11T06:00:00","2019-06-18T18:00:00",null,null,null,"MLV 209-3 TO MLV 204-3",200,"4","Pig Runs - Cleaning/Gauge 6/11/19, MFL/AFD 6/13/19, Hardspot/EMAT 6/18/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,204.30000305175781]
["X18-686516","","2019-06-17T06:00:00","2019-06-29T18:00:00",null,null,null,"MLV 204-3 TO MLV 205-3",200,"4","SCCDA","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,204.30000305175781]
["X18-686520","","2019-08-12T06:00:00","2019-08-24T18:00:00",null,null,null,"MLV 204-4 TO MLV 205-4",200,"4","SCCDA","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,204.39999389648437]
["X19-32914","***","2019-01-14T15:27:00","2019-01-25T15:27:00","Date Change","1/14/2019","1/18/2019","Sta 209: Unit 3A",200,"4","Carbon Removal","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209.00300598144531]
["X18-764396","","2019-04-03T06:00:00","2019-04-09T18:00:00",null,null,null,"MLV 214-2 TO MLV 209-2",200,"4","Pig Runs  - Cleaning 4/3/19, Gauge 4/4/19, AFD 4/9/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,209.19999694824219]
["X18-684210","","2019-05-14T06:00:00","2019-05-16T18:00:00",null,null,null,"MLV 214-4 to MLV 209-4",200,"4","Pig Run - Cleaning/Gauge 5/14/19, MFL/AFD 5/16/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,209.39999389648437]
["X18-992094","***","2018-12-13T06:00:00","2019-01-25T18:00:00","Date Change","12/13/2018","1/11/2019","Sta 214: Unit 3",200,"4","Compressor Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,214.00300598144531]
["X18-684268","","2019-04-15T06:00:00","2019-04-27T18:00:00",null,null,null,"MLV 214-1 to MLV 217-1",200,"4","SCCDA","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,214.10000610351562]
["X18-764370","","2019-07-16T06:00:00","2019-07-18T18:00:00",null,null,null,"MLV 219-1 TO MLV 214-1",200,"4","Pig run - Cleaning 7/16/19, ILI 7/18/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,214.10000610351562]
["X18-684222","","2019-07-25T06:00:00","2019-08-01T18:00:00",null,null,null,"MLV 219-1 TO MLV 214-1",200,"4","Pig Run - Cleaning/Gauge 7/25/19, ILI 7/30/19, Hardspot 8/1/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,214.10000610351562]
["X18-764413","","2019-08-13T06:00:00","2019-08-15T18:00:00",null,null,null,"MLV 218-2 to MLV 214-2",200,"4","Pig Runs  - Cleaning/Gauge 8/13/19, ILI 8/15/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,214.19999694824219]
["X18-684216","","2019-08-20T06:00:00","2019-08-22T18:00:00",null,null,null,"MLV 219-2 TO MLV 214-2",200,"4","Pig Run - ILI 8/20/19, Hardspot 8/22/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,214.19999694824219]
["X18-684212","","2019-04-04T06:00:00","2019-04-11T18:00:00",null,null,null,"MLV 219-3 to MLV 214-3",200,"4","Pig Run - Cleaning/Gauge 4/4/19, ILI 4/9/19, Hardspot 4/11/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,214.30000305175781]
["X18-684205","","2019-05-07T06:00:00","2019-05-09T18:00:00",null,null,null,"MLV 219-4 TO MLV 214-4",200,"4","Pig Run - Cleaning/Gauge 5/7/19, ILI 5/9/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,214.39999389648437]
["X18-684250","","2019-05-30T06:00:00","2019-06-06T18:00:00",null,null,null,"MLV 217A-101.1 to MLV 217A-104",200,"4","Pig Run - Cleaning/Gauge 5/30/19, ILI 6/4/19, Hardspot 6/6/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,217.10000610351562]
["X18-686541","","2019-04-08T06:00:00","2019-05-27T18:00:00",null,null,null,"MLV 219-2 TO MLV 307-1",200,"4","Remediaton","This project will require taking the pipeline section out of service which will limit throughput and result in restrictions based on customer nominations. The meter listed below will likely experience fluctuations in flow and/or pressures.","SOP","Potential out of path restrictions may be at risk.","420730 Nat Fuel Cranberry Del",219.19999694824219]
["X18-764347","","2019-05-21T06:00:00","2019-05-23T18:00:00",null,null,null,"MLV 219-2B TO 220-2",200,"4","Pig Run - Cleaning/Gauge 5/21/19, ILI 5/23/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,219.19999694824219]
["X18-686545","","2019-05-28T06:00:00","2019-05-31T18:00:00",null,null,null,"MLV 219-3 TO MLV 307-2",200,"4","Remediaton","This project will require taking the pipeline section out of service which will limit throughput and result in restrictions based on customer nominations. The meter listed below will likely experience fluctuations in flow and/or pressures.","SOP","Potential out of path restrictions may be at risk.","412871 Nat Fuel - Tionesta Rec",219.30000305175781]
["X18-753903","","2019-02-20T06:00:00","2019-02-21T18:00:00",null,null,null,"MLVS 220-1",200,"4","New Meter Tie-In - TGP/RH Energytrans Interconnect Meadville","This activity will require operating at reduced pressures. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,220.10000610351562]
["X18-684242","","2019-06-10T06:00:00","2019-06-12T18:00:00",null,null,null,"MLV 230B-201 TO MLV 230B-204",200,"5","Pig run - Cleaning & Gage 6/10, Combo 6/12","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,230.19999694824219]
["X18-684246","","2019-06-17T06:00:00","2019-06-19T18:00:00",null,null,null,"MLV 230B-205 TO 230B-206",200,"5","Pig run - Cleaning & Gage 6/17, Combo 6/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,230.21000671386719]
["X18-993521","","2019-05-13T06:00:00","2019-05-17T18:00:00",null,null,null,"Sta 241",200,"5","Annual ESD test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,241]
["X18-993523","","2019-06-17T06:00:00","2019-06-21T18:00:00",null,null,null,"Sta 245",200,"5","Annual ESD test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,245]
["X19-19000","","2019-04-15T06:00:00","2019-04-18T18:00:00",null,null,null,"Sta 245: Unit 1C",200,"5","Borescope and Water Wash","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,245.03300476074219]
["X19-19002","","2019-09-30T06:00:00","2019-10-04T18:00:00",null,null,null,"Sta 245: Unit 1C",200,"5","Borescope and Water Wash","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,245.03300476074219]
["X18-684261","","2019-06-24T06:00:00","2019-07-02T18:00:00",null,null,null,"MLV 245-1 to MLV 249-1",200,"5","Pig run - Cleaning & Gage 6/24, Combo 6/26, Hard Spot 7/2","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,245.10000610351562]
["X19-32602","","2019-04-15T06:00:00","2019-04-20T18:00:00",null,null,null,"Sta 249",200,"5","ESD Piping Modification & Filter Separator Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,249]
["X18-684224","","2019-05-13T06:00:00","2019-05-16T18:00:00",null,null,null,"MLV 249-2 TO MLV 254-2",200,"5","Pig Run - Cleaning/Gauge 5/13/19, Caliper 5/14/19, MFL 5/16/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,249.19999694824219]
["X19-32604","","2019-04-22T06:00:00","2019-04-27T18:00:00",null,null,null,"Sta 254",200,"5","Filter Separator Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,254]
["X18-684225","","2019-06-04T06:00:00","2019-06-06T18:00:00",null,null,null,"MLV 254-2 TO MLV 261-2",200,"6","Pig Run - Cleaning/Gauge 6/4/19, Combo 6/6/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,254.19999694824219]
["X18-684228","","2019-05-21T06:00:00","2019-05-22T18:00:00",null,null,null,"MLV 254-3 to MLV 258-3",200,"6","Pig Run - Cleaning/Gauge 5/21/19, Combo 5/22/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,254.30000305175781]
["X18-684208","","2019-04-23T06:00:00","2019-04-25T18:00:00",null,null,null,"MLV 265E-101.1 TO MLV 265E-104",200,"6","Pig run - Cleaning/Gauge 4/1/19, Caliper 4/2/19, MFL 4/3/19","This activity will require operating at controlled flow rates and will be coordinated with the customers.  The meter listed below will be shut-in for the duration of the project.","SIP","Potential in the path restrictions may be at risk.","420707 OCEAN ST/TGP PROVIDENCE",265]
["X17-840013","","2019-05-10T14:43:00","2019-08-10T14:43:00",null,null,null,"267-1",200,"6","Class Change","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,267]
["X18-764339","","2019-06-13T06:00:00","2019-06-20T18:00:00",null,null,null,"MLV 313-1 TO MLV 307-1",300,"4","Pig Runs  - Cleaning/Gauge 6/13/19, ILI 6/18/19, Hard Spot 6/20/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,307.10000610351562]
["X18-686543","","2019-06-03T06:00:00","2019-06-06T18:00:00",null,null,null,"MLVS 313A-100",300,"4","Remediaton","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,313.10000610351562]
["X19-44564","***","2019-05-06T06:00:00","2019-05-12T18:00:00","Added",null,null,"Sta 325: Unit 3A",300,"5","Turbine Exchange","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,325.00299072265625]
["X17-852402","","2019-04-01T06:00:00","2019-04-21T18:00:00",null,null,null,"Sta 409A",400,"0","Station Outage","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. The meter listed below will likely experience fluctuations in flow and/or pressures during this time.","PIP","Potential In the Path nominations may be at risk.","450261 CENEGAS/TGP PEMEX DELIVERY",409]
["X19-32713","","2019-02-05T06:00:00","2019-02-05T18:00:00",null,null,null,"Sta 40 to Sta 823",500,"L","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  The meters listed below will be shut-in for a brief period of time during the pig run.","SOP","Potential out of path restrictions may be at risk.","420373 TRNSCO/TGP KINDER LA EXCH (BI 1\n420708 ELIZ NG/TGP GRANT LA SALES ALLEN\n420436 VERNON/TGP PITKIN LA VERNON\n420793 ELIZ NG/TGP J R FRANKS 1 VERNON\n420388 PROVNCAL/TGP PROVENCAL LA NATCHITOC",500.10000610351562]
["X19-49535","***","2019-10-08T06:00:00","2019-10-08T18:00:00","Added",null,null,"Sta 40 to Sta 823",500,"L","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  The meters listed below will be shut-in for a brief period of time during the pig run.","SOP","Potential out of path restrictions may be at risk.","420373 TRNSCO/TGP KINDER LA EXCH (BI 1\n420708 ELIZ NG/TGP GRANT LA SALES ALLEN\n420436 VERNON/TGP PITKIN LA VERNON\n420793 ELIZ NG/TGP J R FRANKS 1 VERNON\n420388 PROVNCAL/TGP PROVENCAL LA NATCHITOC",500.10000610351562]
["X18-571586","","2018-11-01T06:00:00","2019-02-28T18:00:00",null,null,null,"Sta 504: Unit 2B",500,"L","Controls upgrade & convert to simple cycle","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,504]
["X18-381434","","2018-11-05T06:00:00","2019-01-31T18:00:00",null,null,null,"MLVS 528-1",500,"L","Line Lowering","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,528]
["X18-828757","***","MARCH","APRIL - Exact Dates TBD","Added",null,null,"MLV 534-2 TO MLV 538-2",500,"L","Make Piggable","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.  The meter listed below will be shut-in for approximately one month during the project.","SOP","Potential out of path restrictions may be at risk.","420719 SPIREMS/TGP CAMP SHELBY FORREST",534.20001220703125]
["X18-686599","***","2019-06-24T06:00:00","2019-07-11T18:00:00","Added",null,null,"MLV 534-2 TO MLV 538-2",500,"1","Pig run - Dates are tentative: Chem Cleaning 6/24/19 - 7/3/19, AFD 7/9/19, EMAT 7/11/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed below will be shut-in for the Chem Cleaning and during the pig runs.","SOP","Potential out of path restrictions may be at risk.","420719 SPIREMS/TGP CAMP SHELBY FORREST",534.20001220703125]
["X18-472029","***","2018-06-04T06:00:00","2019-01-18T18:00:00","Date Change","6/4/2018","1/15/2019","Sta 550: Unit 1A",500,"1","Regrout","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,550.0009765625]
["X18-686537","","2019-05-01T06:00:00","2019-05-21T18:00:00",null,null,null,"MLV 555-1L TO MLV 558-1R",500,"1","Remediaton","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,555.0999755859375]
["X18-684172","","2019-04-18T06:00:00","2019-04-23T18:00:00",null,null,null,"MLV 555-2 TO MLV 559-2",500,"1","Pig run - Cleaning 4/18/19, Gauge 4/19/19, MFL Combo 4/23/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,555.20001220703125]
["X18-684169","","2019-02-12T06:00:00","2019-02-14T18:00:00",null,null,null,"MLV 557-3 TO MLV 559-3",500,"1","Pig run - Cleaning 2/12/19, MFL Combo 2/14/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,557.29998779296875]
["X18-764438","","2019-05-22T06:00:00","2019-06-17T18:00:00",null,null,null,"MLV 559-1 to MLV 565-1",500,"1","Remediation","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,599.0999755859375]
["X18-684233","***","2019-04-18T06:00:00","2019-04-30T18:00:00","Date Change","8/13/2019","8/19/2019","MLV 847-1 TO MLV 851-1",800,"1","Pig Run - Cleaning 4/18/19, Gauge 4/23/19, MFL Combo 4/25/19, Hardspot/EMAT 4/30/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,847.0999755859375]
["X18-686606","","2019-03-14T06:00:00","2019-03-28T18:00:00",null,null,null,"MLV 860-1 TO MLV 856-1",800,"1","Pig Runs - Cleaning/Gauge 3/14/19 & 3/19/19 & 3/21/19, MFL/AFD 3/26/19, Hardspot/EMAT 3/28/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,856.0999755859375]
["X19-42297","***","2019-02-04T06:00:00","2019-02-09T18:00:00","Added",null,null,"Sta 871: Unit 3A",800,"2","Compressor Valve Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,871.00299072265625]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]