## Closed (hidden)
|  |  | Updated | 2016
Tennessee Gas Pipeline 2015 Pipeline Outage and Maintenance Summary
This is a summary of the current status of all TGP Winter 2014-2015 Pipeline Outages and Maintenance Projects. This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions. Additionally, anticipated impact and restrictions are subject to change. *Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project. *Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time).
*** Indicates revision
Date Change | Project New/Completed/Closed | Outage # | Revised | Start Date | End Date | Reason Changed | Prev. Start Date | Prev. End Date | Location | Leg | Zone | Maintenance Activity | Anticipated Impact | Potential Restriction Level | TOS Potential Restrictions | Meter(s) in Impacted Area | Customer Notifications | Loc | Email Text | Posting Text | Completion Text
| Project Completed |  | *** | 2015-01-11 | 2016-01-11 | Project Completed |  |  | MS #412494 DCP Warren | 400 | 0 | Meter Station | This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | 412494 DCP Warren | 401 | () MS #412494 DCP Warren: Meter Station (1/11/15 to 1/11/16) | ***MS #412494 DCP Warren: Meter Station --1/11/15 through 1/11/16: This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. 412494 DCP Warren ***Project Completed ……………………………… | ***MS #412494 DCP Warren: Meter Station ***Project Completed The following meters are available for nominations: 412494 DCP Warren ………………………………
| Project Completed |  | *** | 2015-01-11 | 2016-01-11 | Project Completed |  |  | MS #412400 King Ranch | 400 | 0 | Meter Station | This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | 412400 King Ranch | 402.1 | () MS #412400 King Ranch: Meter Station (1/11/15 to 1/11/16) | ***MS #412400 King Ranch: Meter Station --1/11/15 through 1/11/16: This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. 412400 King Ranch ***Project Completed ……………………………… | ***MS #412400 King Ranch: Meter Station ***Project Completed The following meters are available for nominations: 412400 King Ranch ………………………………
| Project Completed |  | *** | 2015-01-12 | 2016-01-12 | Project Completed |  |  | MS #410539 Duvak Gas Gathering | 400 | 0 | Meter Station | This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | 410539 Duvak Gas Gathering | 402.1 | () MS #410539 Duvak Gas Gathering: Meter Station (1/12/15 to 1/12/16) | ***MS #410539 Duvak Gas Gathering: Meter Station --1/12/15 through 1/12/16: This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. 410539 Duvak Gas Gathering ***Project Completed ……………………………… | ***MS #410539 Duvak Gas Gathering: Meter Station ***Project Completed The following meters are available for nominations: 410539 Duvak Gas Gathering ………………………………
| Project Completed |  | *** | 2015-01-13 | 2016-01-13 | Project Completed |  |  | MS #412356 DCP LaGloria | 400 | 0 | Meter Station | This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | 412356 DCP LaGloria | 403.1 | () MS #412356 DCP LaGloria: Meter Station (1/13/15 to 1/13/16) | ***MS #412356 DCP LaGloria: Meter Station --1/13/15 through 1/13/16: This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. 412356 DCP LaGloria ***Project Completed ……………………………… | ***MS #412356 DCP LaGloria: Meter Station ***Project Completed The following meters are available for nominations: 412356 DCP LaGloria ………………………………
| Project Completed |  | *** | 2015-01-13 | 2016-01-13 | Project Completed |  |  | MS #410173 Enterprise LaReforma | 400 | 0 | Meter Station | This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | 410173 Enterprise LaReforma | 406.1 | () MS #410173 Enterprise LaReforma: Meter Station (1/13/15 to 1/13/16) | ***MS #410173 Enterprise LaReforma: Meter Station --1/13/15 through 1/13/16: This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. 410173 Enterprise LaReforma ***Project Completed ……………………………… | ***MS #410173 Enterprise LaReforma: Meter Station ***Project Completed The following meters are available for nominations: 410173 Enterprise LaReforma ………………………………
| Project Completed |  | *** | 2015-01-12 | 2016-01-12 | Project Completed |  |  | MS #411903 Enterprise El Benito | 400 | 0 | Meter Station | This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | 411903 Enterprise El Benito | 407.1 | () MS #411903 Enterprise El Benito: Meter Station (1/12/15 to 1/12/16) | ***MS #411903 Enterprise El Benito: Meter Station --1/12/15 through 1/12/16: This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. 411903 Enterprise El Benito ***Project Completed ……………………………… | ***MS #411903 Enterprise El Benito: Meter Station ***Project Completed The following meters are available for nominations: 411903 Enterprise El Benito ………………………………
| Project Completed |  | *** | 2015-01-11 | 2016-01-11 | Project Completed |  |  | MS #412088 Enterprise Sullivan | 400 | 0 | Meter Station | This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | 412088 Enterprise Sullivan | 407.1 | () MS #412088 Enterprise Sullivan: Meter Station (1/11/15 to 1/11/16) | ***MS #412088 Enterprise Sullivan: Meter Station --1/11/15 through 1/11/16: This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. 412088 Enterprise Sullivan ***Project Completed ……………………………… | ***MS #412088 Enterprise Sullivan: Meter Station ***Project Completed The following meters are available for nominations: 412088 Enterprise Sullivan ………………………………
| Project Completed |  | *** | 2015-01-11 | 2016-01-11 | Project Completed |  |  | MS #412683 HESCO | 400 | 0 | Meter Station | This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | 412683 HESCO | 408.1 | () MS #412683 HESCO: Meter Station (1/11/15 to 1/11/16) | ***MS #412683 HESCO: Meter Station --1/11/15 through 1/11/16: This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. 412683 HESCO ***Project Completed ……………………………… | ***MS #412683 HESCO: Meter Station ***Project Completed The following meters are available for nominations: 412683 HESCO ………………………………
| Project Completed | X16-36843 | *** | 2016-01-27 | 2016-01-27 | Project Completed |  |  | Sta. 237 | 200 | 5 | Unit Maintenance | This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. |  | 237 | (X16-36843) Sta. 237: Unit Maintenance (1/27/16) | ***Sta. 237: Unit Maintenance --1/27/16: This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. ***Project Completed ……………………………… | ***Sta. 237: Unit Maintenance ***Project Completed ………………………………
| Project Completed | X14-1478563 | *** | 2015-11-16 | 2016-02-12 | Project Completed |  |  | MLV 32-1D to 33-1 | 100 | 0 | Hydrotest | This project will require taking the pipeline section out of service. This will limit throughput and may result in restrictions based on customer nominations. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. |  | 32.2 | (X14-1478563) MLV 32-1D to 33-1: Hydrotest (11/16/15 to 2/12/16) | ***MLV 32-1D to 33-1: Hydrotest --11/16/15 through 2/12/16: This project will require taking the pipeline section out of service. This will limit throughput and may result in restrictions based on customer nominations. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. ***Project Completed ……………………………… | ***MLV 32-1D to 33-1: Hydrotest ***Project Completed ………………………………
| Project Completed | X16-16074 |  | 2016-01-18 | 2016-01-28 | Project Completed |  |  | Station 550 | 500 | 1 | Station Maintenance | This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. |  | 550 | (X16-16074) Station 550: Station Maintenance (1/18/16 to 1/28/16) | Station 550: Station Maintenance --1/18/16 through 1/28/16: This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. ***Project Completed ……………………………… | Station 550: Station Maintenance ***Project Completed ………………………………
| Project Completed | X16-46202 | *** | 2016-02-01 | 2016-02-07 | Project Completed |  |  | Station 9 | 100 | 0 | Station Maintenance (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items) | This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time. | SIP | Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations. |  | 9 | (X16-46202) Station 9: Station Maintenance (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items) (2/1/16 to 2/7/16) | ***Station 9: Station Maintenance (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items) --2/1/16 through 2/7/16: This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time. Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations. ***Project Completed ……………………………… | ***Station 9: Station Maintenance (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items) ***Project Completed ………………………………
| Project Completed | X15-925633 | *** | 2016-02-09 | 2016-02-11 | Project Completed |  |  | Sta. 266A | 200 | 6 | Unit Maintenance | This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. |  | 266 | (X15-925633) Sta. 266A: Unit Maintenance (2/9/16 to 2/11/16) | ***Sta. 266A: Unit Maintenance --2/9/16 through 2/11/16: This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. ***Project Completed ……………………………… | ***Sta. 266A: Unit Maintenance ***Project Completed ………………………………
| Project Completed | X15-929733 | *** | 2016-01-27 | 2016-02-10 | Project Completed |  |  | MLV 834-1 to 838-1 | 800 | 5 | ILI/Cleaning Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | To Be Determined | 834.1 | (X15-929733) MLV 834-1 to 838-1: ILI/Cleaning Pig (1/27/16 to 2/10/16) | ***MLV 834-1 to 838-1: ILI/Cleaning Pig --1/27/16 through 2/10/16: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. To Be Determined ***Project Completed ……………………………… | ***MLV 834-1 to 838-1: ILI/Cleaning Pig ***Project Completed The following meters are available for nominations: To Be Determined ………………………………
| Project Completed | X14-1562506 | *** | 2015-11-02 | 2016-02-19 | Project Completed |  |  | MLV 5-1 to 6-1 | 100 | 0 | Hydrotest | This project will require taking the pipeline section out of service. The listed meters will be shut in during the outage. This will limit throughput and may result in restrictions based on customer nominations. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | 410063 ROCHE DEHYDRATION | 5.1 | (X14-1562506) MLV 5-1 to 6-1: Hydrotest (11/2/15 to 2/19/16) | ***MLV 5-1 to 6-1: Hydrotest --11/2/15 through 2/19/16: This project will require taking the pipeline section out of service. The listed meters will be shut in during the outage. This will limit throughput and may result in restrictions based on customer nominations. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. 410063 ROCHE DEHYDRATION ***Project Completed ……………………………… | ***MLV 5-1 to 6-1: Hydrotest ***Project Completed The following meters are available for nominations: 410063 ROCHE DEHYDRATION ………………………………
| Project Completed | X14-1562506 | *** | 2015-11-02 | 2016-02-19 | Project Completed |  |  | MLV 7-1 to 9-1 | 100 | 0 | Hydrotest | This project will require taking the pipeline section out of service. The listed meters will be shut in during the outage. This will limit throughput and may result in restrictions based on customer nominations. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | 412490 Charro 421083 Eagle Ford Field Service | 5.1 | (X14-1562506) MLV 7-1 to 9-1: Hydrotest (11/2/15 to 2/19/16) | ***MLV 7-1 to 9-1: Hydrotest --11/2/15 through 2/19/16: This project will require taking the pipeline section out of service. The listed meters will be shut in during the outage. This will limit throughput and may result in restrictions based on customer nominations. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. 412490 Charro 421083 Eagle Ford Field Service ***Project Completed ……………………………… | ***MLV 7-1 to 9-1: Hydrotest ***Project Completed The following meters are available for nominations: 412490 Charro 421083 Eagle Ford Field Service ………………………………
Date change. Previously scheduled 2/18/16 to 2/20/16. | Project Completed | X15-882289 | *** | 2016-02-22 | 2016-02-24 | Project Completed | 2016-02-18 | 2016-02-20 | MLV 24-2 to 25-2S | 100 | 0 | Anomaly Remediation | This outage will require pressure reductions and possibly line isolations. However no other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | To Be Determined | 24.2 | (X15-882289) MLV 24-2 to 25-2S: Anomaly Remediation (2/22/16 to 2/24/16) | ***MLV 24-2 to 25-2S: Anomaly Remediation --2/22/16 through 2/24/16: This outage will require pressure reductions and possibly line isolations. However no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. To Be Determined ***Project Completed ……………………………… | ***MLV 24-2 to 25-2S: Anomaly Remediation ***Project Completed The following meters are available for nominations: To Be Determined ………………………………
| Project Completed | X15-925630 | *** | 2016-02-23 | 2016-02-23 | Project Completed |  |  | WORCESTER DELIVERY NO. 2 LINE (265C-101.1 to 265C-101B) | 200 | L | ILI/Cleaning Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. |  | 265.1 | (X15-925630) WORCESTER DELIVERY NO. 2 LINE (265C-101.1 to 265C-101B): ILI/Cleaning Pig (2/23/16) | ***WORCESTER DELIVERY NO. 2 LINE (265C-101.1 to 265C-101B): ILI/Cleaning Pig --2/23/16: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. ***Project Completed ……………………………… | ***WORCESTER DELIVERY NO. 2 LINE (265C-101.1 to 265C-101B): ILI/Cleaning Pig ***Project Completed ………………………………
| Project Completed | X16-23748 | *** | 2016-02-15 | 2016-02-18 | Project Completed |  |  | MLV 530-3 to 532-3 | 500 | L | ILI/Cleaning Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. |  | 530.3 | (X16-23748) MLV 530-3 to 532-3: ILI/Cleaning Pig (2/15/16 to 2/18/16) | ***MLV 530-3 to 532-3: ILI/Cleaning Pig --2/15/16 through 2/18/16: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. ***Project Completed ……………………………… | ***MLV 530-3 to 532-3: ILI/Cleaning Pig ***Project Completed ………………………………
| Project Canceled | X16-98720 | *** | 2016-03-06 | 2016-03-06 | Project Canceled |  |  | Sta. 1 | 100 | 0 | Station Maintenance | This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. |  | 1 | (X16-98720) Sta. 1: Station Maintenance (3/6/16) | ***Sta. 1: Station Maintenance --3/6/16: This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. ***Project Canceled ……………………………… | ***Sta. 1: Station Maintenance ***Project Canceled ………………………………
| Project Completed | X14-1562513 X14-1540661 | *** | 2015-07-01 | 2016-03-04 | Project Completed |  |  | Station 32 | 100 | 0 | Station Maintenance | This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. |  | 32 | (X14-1562513 X14-1540661) Station 32: Station Maintenance (7/1/15 to 3/4/16) | ***Station 32: Station Maintenance --7/1/15 through 3/4/16: This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. ***Project Completed ……………………………… | ***Station 32: Station Maintenance ***Project Completed ………………………………
| Project Canceled | X15-926822 | *** | 2016-06-06 | 2016-06-11 | Project Canceled |  |  | BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1) | 300 | 6 | Pipe Inspection | This project involves inspecting multiple sites. We do not anticipate having to do any repairs, however if a repair is needed there is a potential that the pipe may require replacement which will require isolation of the pipe. This may limit throughput and will result in restrictions based on customer nominations. Customers may experience pressure fluctuations during this timeframe. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | To Be Determined | 343.1 | (X15-926822) BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1): Pipe Inspection (6/6/16 to 6/11/16) | ***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1): Pipe Inspection --6/6/16 through 6/11/16: This project involves inspecting multiple sites. We do not anticipate having to do any repairs, however if a repair is needed there is a potential that the pipe may require replacement which will require isolation of the pipe. This may limit throughput and will result in restrictions based on customer nominations. Customers may experience pressure fluctuations during this timeframe. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. To Be Determined ***Project Canceled ……………………………… | ***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1): Pipe Inspection ***Project Canceled The following meters are available for nominations: To Be Determined ………………………………
| Project Canceled | X15-928271 | *** | TBD | TBD | Project Canceled |  |  | MLV 555-1 to 550-1 | 500 | 1 | ILI/Cleaning Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | To Be Determined | 555.1 | (X15-928271) MLV 555-1 to 550-1: ILI/Cleaning Pig (TBD) | ***MLV 555-1 to 550-1: ILI/Cleaning Pig --TBD: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. To Be Determined ***Project Canceled ……………………………… | ***MLV 555-1 to 550-1: ILI/Cleaning Pig ***Project Canceled The following meters are available for nominations: To Be Determined ………………………………
| Project Canceled | X15-928272 | *** | TBD | TBD | Project Canceled |  |  | MLV 555-2 to 550-2 | 500 | 1 | ILI/Cleaning Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | To Be Determined | 555.2 | (X15-928272) MLV 555-2 to 550-2: ILI/Cleaning Pig (TBD) | ***MLV 555-2 to 550-2: ILI/Cleaning Pig --TBD: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. To Be Determined ***Project Canceled ……………………………… | ***MLV 555-2 to 550-2: ILI/Cleaning Pig ***Project Canceled The following meters are available for nominations: To Be Determined ………………………………
| Project Canceled | X15-928273 | *** | TBD | TBD | Project Canceled |  |  | MLV 555-3 to 552-3 | 500 | 1 | ILI/Cleaning Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | To Be Determined | 555.3 | (X15-928273) MLV 555-3 to 552-3: ILI/Cleaning Pig (TBD) | ***MLV 555-3 to 552-3: ILI/Cleaning Pig --TBD: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. To Be Determined ***Project Canceled ……………………………… | ***MLV 555-3 to 552-3: ILI/Cleaning Pig ***Project Canceled The following meters are available for nominations: To Be Determined ………………………………
| Project Completed | X15-882281 | *** | 2016-02-24 | 2016-03-03 | Project Completed |  |  | 24-1A to 25-1S | 100 | 0 | Anomaly Remediation | This outage will require pressure reductions and possibly line isolations. However no other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | To Be Determined | 24.1 | (X15-882281) 24-1A to 25-1S: Anomaly Remediation (2/24/16 to 3/3/16) | ***24-1A to 25-1S: Anomaly Remediation --2/24/16 through 3/3/16: This outage will require pressure reductions and possibly line isolations. However no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. To Be Determined ***Project Completed ……………………………… | ***24-1A to 25-1S: Anomaly Remediation ***Project Completed The following meters are available for nominations: To Be Determined ………………………………
| Project Completed | X15-882291 | *** | 2016-03-03 | 2016-03-04 | Project Completed |  |  | MLV 24-3 to 25-3S | 100 | 0 | Anomaly Remediation | This outage will require pressure reductions and possibly line isolations. However no other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | To Be Determined | 24.3 | (X15-882291) MLV 24-3 to 25-3S: Anomaly Remediation (3/3/16 to 3/4/16) | ***MLV 24-3 to 25-3S: Anomaly Remediation --3/3/16 through 3/4/16: This outage will require pressure reductions and possibly line isolations. However no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. To Be Determined ***Project Completed ……………………………… | ***MLV 24-3 to 25-3S: Anomaly Remediation ***Project Completed The following meters are available for nominations: To Be Determined ………………………………
| Project Completed | X14-1178175 | *** | 2015-06-15 | 2016-03-31 | Project Completed |  |  | Station 63 | 100 | 1 | Station Maintenance | This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. |  | 63 | (X14-1178175) Station 63: Station Maintenance (6/15/15 to 3/31/16) | ***Station 63: Station Maintenance --6/15/15 through 3/31/16: This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. ***Project Completed ……………………………… | ***Station 63: Station Maintenance ***Project Completed ………………………………
| Project Cancelled | X15-913224 | *** | 2016-04-16 | 2016-05-21 | Project Cancelled |  |  | MLV 109-2 | 100 | 2 | Pipe Replacement | This project will require taking the pipeline section out of service. This will limit throughput and will result in restrictions based on customer nominations. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | To Be Determined | 109.2 | (X15-913224) MLV 109-2: Pipe Replacement (4/16/16 to 5/21/16) | ***MLV 109-2: Pipe Replacement --4/16/16 through 5/21/16: This project will require taking the pipeline section out of service. This will limit throughput and will result in restrictions based on customer nominations. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. To Be Determined ***Project Cancelled ……………………………… | ***MLV 109-2: Pipe Replacement ***Project Cancelled The following meters are available for nominations: To Be Determined ………………………………
| Project Completed | X15-926830 | *** | 2016-03-07 | 2016-03-11 | Project Completed |  |  | MLV 400-1 to 408-1 | 100 | 0 | ILI/Cleaning Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. | SIP | Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations. | To Be Determined | 400.1 | (X15-926830) MLV 400-1 to 408-1: ILI/Cleaning Pig (3/7/16 to 3/11/16) | ***MLV 400-1 to 408-1: ILI/Cleaning Pig --3/7/16 through 3/11/16: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations. To Be Determined ***Project Completed ……………………………… | ***MLV 400-1 to 408-1: ILI/Cleaning Pig ***Project Completed The following meters are available for nominations: To Be Determined ………………………………
| Project Cancelled | X16-143836 | *** | 2016-03-28 | 2016-04-04 | Project Cancelled |  |  | Sta. 409 | 100 | 0 | Unit Maintenance | This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations. | SIP | Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations. |  | 409 | (X16-143836) Sta. 409: Unit Maintenance (3/28/16 to 4/4/16) | ***Sta. 409: Unit Maintenance --3/28/16 through 4/4/16: This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations. Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations. ***Project Cancelled ……………………………… | ***Sta. 409: Unit Maintenance ***Project Cancelled ………………………………
| Project Cancelled | X15-929680 | *** | 2016-04-18 | 2016-04-27 | Project Cancelled |  |  | SABINE - KINDER LINE to 822-1 | 800 | L | Anomaly Remediation | This outage will require pressure reductions and possibly line isolations. However no other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | To Be Determined | 822.1 | (X15-929680) SABINE - KINDER LINE to 822-1: Anomaly Remediation (4/18/16 to 4/27/16) | ***SABINE - KINDER LINE to 822-1: Anomaly Remediation --4/18/16 through 4/27/16: This outage will require pressure reductions and possibly line isolations. However no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. To Be Determined ***Project Cancelled ……………………………… | ***SABINE - KINDER LINE to 822-1: Anomaly Remediation ***Project Cancelled The following meters are available for nominations: To Be Determined ………………………………

## Sheet1
Updated | 2020-09-17
Tennessee Gas Pipeline 2019 Pipeline Outage and Maintenance Summary
This is a summary of the current status of all TGP 2019 Pipeline Outages and Maintenance Projects. This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions. Additionally, anticipated impact and restrictions are subject to change. *Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project. *Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time).
*** Indicates revision
Outage # | Revised | Start Date | End Date | Reason Changed | Prev. Start Date | Prev. End Date | Location | Leg | Zone | Maintenance Activity | Anticipated Impact | Potential Restriction Level | TOS Potential Restrictions | Meter(s) in Impacted Area | \\corp.epec.com\trans\TranServices\OPPLAN\COMMON\Outages\Outage_DB\TGP\Files
X20-773099 |  | 2020-10-26 | 2020-10-28 |  |  |  | Sta 1 | 100 | 0 | Building Protection System Upgrade | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SIP | Potential in the path restrictions may be at risk. |  | X20-773099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X19-761902 |  | 2020-10-05 | 2020-10-23 |  |  |  | MLV 5-2 to MLV 2-2 | 100 | 0 | Pipe Replacement | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X19-761902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X19-1003528 | *** | 2020-09-12 | 2020-09-12 | Completed |  |  | Station 9 | 100 | 0 | Annual ESD test | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X19-1003528 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-339034 |  | 2020-10-01 | 2020-10-08 |  |  |  | MLV 9-3 to MLV 4-3 | 100 | 0 | Pig Runs: Cleaning 10/1, Gauge 10/6, ILI 10/8 | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SIP | Potential in the path restrictions may be at risk. |  | X20-339034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-519187 |  | 2020-09-01 | 2020-09-30 |  |  |  | MLV 12-1 to MLV 13-1 | 100 | 0 | Pressure Weld Replacement | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-519187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-57719 |  | 2020-09-08 | 2020-10-23 |  |  |  | Sta 17: Unit 1C | 100 | 0 | Major Overhaul | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SIP | Potential in the path restrictions may be at risk. |  | X20-57719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-135714 | *** | 2020-08-31 | 2020-10-02 | Completed |  |  | MLV 17-3D to MLV 20-3 | 100 | 0 | Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-135714 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X19-1003538 |  | 2020-12-07 | 2020-12-11 |  |  |  | Sta. 25 | 100 | 0 | Annual ESD test | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X19-1003538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-658542 |  | 2020-12-07 | 2020-12-11 |  |  |  | Sta. 25 | 100 | 0 | Annual Electrical Inspection | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-658542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-832825 |  | 2020-09-08 | 2020-12-04 |  |  |  | MLV 25-1 to 32-1 | 100 | 0 | Anomaly Remediation | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-832825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-835648 | *** | 2020-09-16 | 2020-09-16 | Completed |  |  | MLV 40-1 to MLV 32-1 | 100 | 0 | Maintenance Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. | No meters affected on this maintenance pig run. | X20-835648 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-835661 | *** | 2020-11-17 | 2020-11-17 | Project Change | 9/17/20 | 9/17/20 | MLV 40-2 to MLV 32-2 | 100 | 0 | Maintenance Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. | No meters affected on this maintenance pig run. | X20-835661 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
X19-1003547 | *** | 2020-09-16 | 2020-09-16 | Completed |  |  | Sta. 40 | 100 | 1 | Annual ESD test | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X19-1003547 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-647061 |  | 2020-09-01 | 2020-11-15 |  |  |  | MLV 40-1 and 41-1 | 100 | 0 | TGP 100-1 & 2 RED RIVER BRIDGE RECOATING | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-647061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-79490 |  | 2020-10-20 | 2020-10-26 |  |  |  | Bear Creek Storage | 100 | 1 | Shut-in Test | This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations. The meter listed below will be shut-in during the project. | SOP | Potential out of path restrictions may be at risk. | 460017 STORAGE – BEAR CREEK | X20-79490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-832809 | *** | 2020-09-28 | 2020-10-01 | Project Change | 9/21/20 | 9/24/20 | Sta 47 | 100 | 1 | Building C Maintanance | This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-832809 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
X20-427567 |  | 2020-08-01 | 2020-10-30 |  |  |  | MLV 57-3 to MLV 58-3 | 100 | 1 | HDD of Big Sunflower Creek | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-427567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-733666 | *** | 2020-08-06 | 2020-09-25 | Project Change | 8/06/20 | 9/18/20 | MLV 59-3 to 61-3 | 100 | 1 | Anomaly Remediation | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-733666 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
X20-733667 | *** | 2020-09-25 | 2020-10-10 | Project Change | 9/18/20 | 9/28/20 | MLV 60-4 to 61-4 | 100 | 1 | Anomaly Remediation | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-733667 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
X19-1003555 |  | 2020-10-15 | 2020-10-15 |  |  |  | Sta. 63 | 100 | 1 | Annual ESD test | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X19-1003555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-733674 | *** | 2020-10-10 | 2020-10-30 | Project Change | 9/30/20 | 10/22/20 | MLV 63-3 to 64-3 | 100 | 1 | Anomaly Remediation | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-733674 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
X20-733669 | *** | 2020-10-30 | 2020-11-17 | Project Change | 10/22/20 | 11/12/20 | MLV 63-4 to 64-4 | 100 | 1 | Anomaly Remediation | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-733669 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
X19-1003556 |  | 2020-11-10 | 2020-11-11 |  |  |  | Sta. 71 | 100 | 1 | Annual ESD test | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X19-1003556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-733672 |  | 2020-09-01 | 2020-10-31 |  |  |  | MLV 71-2 to 79-2 | 100 | 1 | Anomaly Remediation | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-733672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-776750 | *** | 2020-09-16 | 2020-09-16 | Completed |  |  | Sta 87 | 100 | 2 | Building C Electrical | This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-776750 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-814873 |  | 2020-10-13 | 2020-10-20 |  |  |  | MLV 96-1 to MLV 87-1 | 100 | 2 | Pig Runs: Cleaning 10/13, Caliper 10/15, MDS 10/20 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | X20-814873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-776714 |  | 2020-09-14 | 2020-12-30 |  |  |  | MLV 87-2 to MLV 96-2 | 100 | 2 | Anomaly Remediation From ILI | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-776714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-838964 | *** | 2020-09-14 | 2020-09-17 | Completed |  |  | Sta 87: Unit 8C | 100 | 2 | Exhaust Leak | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-838964 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X19-703248 |  | 2019-08-01 | 2020-12-31 |  |  |  | MLV 106-1 to MLV 96-1 | 100 | 2 | Pressure Restriction from ILI | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X19-703248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-814870 | *** | 2020-09-16 | 2020-09-16 | Completed |  |  | MLV 102-2 to MLV 96-2 | 100 | 2 | Pig Runs: MFL 9/16/20 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | X20-814870 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-776683 |  | 2020-09-08 | 2020-10-31 |  |  |  | MLV 106-3 to MLV 107-3 | 100 | 2 | Wrinkle Bend Replacement | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-776683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-668944 |  | 2020-08-03 | 2020-09-18 |  |  |  | Sta 114: Unit 1C | 100 | 3 | Coupling Repair | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-668944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X19-1006040 |  | 2020-11-02 | 2020-11-06 |  |  |  | Sta. 118A | 100 | 3 | Annual ESD test & Station Maintenance | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X19-1006040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-848924 | *** | 2020-11-16 | 2020-11-20 | Added |  |  | Sta 200: Unit 2A | 200 | 4 | 10k Inspection | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-848924 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-848923 | *** | 2021-01-11 | 2021-01-15 | Added |  |  | Sta 200: Unit 3A | 200 | 4 | 10k Inspection | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-848923 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-848922 | *** | 2020-10-12 | 2020-10-16 | Added |  |  | Sta 200: Unit 8A | 200 | 4 | 10k Inspection | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-848922 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-848918 | *** | 2020-10-19 | 2020-10-23 | Added |  |  | Sta 200: Unit 10A | 200 | 4 | 10k Inspection | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-848918 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-848915 | *** | 2020-10-05 | 2020-10-09 | Added |  |  | Sta 200: Unit 11A | 200 | 4 | 10k Inspection | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-848915 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-143965 | *** | 2020-09-24 | 2020-10-25 | Project Change | 9/28/20 | 10/25/20 | Sta 204: Unit 10A | 200 | 4 | Automation Upgrade | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-143965 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
X20-158412 |  | 2020-09-30 | 2020-10-07 |  |  |  | MLV 207-2 to MLV 208-2 | 200 | 4 | Anomaly Remediation | This activity will include pipe inspections and repairs, as needed, in specified areas. Customers may experience lower pressures; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | X20-158412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-466842 |  | 2020-09-18 | 2020-10-09 |  |  |  | MLV 207-3 to MLV 208-3 | 200 | 4 | Installation of Strain Gauges | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-466842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-494996 |  | 2020-06-01 | 2020-11-20 |  |  |  | Sta 209: Unit 7A | 200 | 4 | Engine Inspection | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-494996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-158410 |  | 2020-09-15 | 2020-09-26 |  |  |  | MLV 209-4 to MLV 210-4 | 200 | 4 | SCCDA | This activity will include pipe inspections and repairs, as needed, in specified areas. Customers may experience lower pressures; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | X20-158410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-802118 |  | 2020-11-09 | 2020-11-12 |  |  |  | Sta 219: Unit 1B | 200 | 4 | Protective Devices | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-802118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-624160 |  | 2020-09-22 | 2020-09-24 |  |  |  | Sta 230C: Unit 2A | 200 | 5 | Recycle Valve Actuator | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-624160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-301488 |  | 2020-09-21 | 2020-09-22 |  |  |  | Sta 237 | 200 | 5 | Suction Filter Separator | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-301488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-301491 |  | 2020-09-28 | 2020-10-09 |  |  |  | Sta 237: Unit 1A | 200 | 5 | Fuel System Upgrade | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-301491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-301492 |  | 2020-08-31 | 2020-09-24 |  |  |  | Sta 237: Unit 3A | 200 | 5 | Inter Cooler Cleaning | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-301492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-57705 | *** | 2020-09-09 | 2020-09-10 | Completed |  |  | MLV 237-2 to MLV 245-2 | 200 | 5 | Maintenance Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SIP | Potential in the path restrictions may be at risk. |  | X20-57705 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-301489 |  | 2020-09-23 | 2020-09-24 |  |  |  | Sta 237 | 200 | 5 | 400 Line Filter Separator | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-301489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-768692 |  | 2020-08-01 | 2020-10-09 |  |  |  | Sta 241: Unit 2A | 200 | 5 | Compressor Liners | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-768692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-859769 | *** | 2020-10-12 | 2020-10-19 | Added |  |  | Sta 241: Unit 1B | 200 | 5 | Replace Chocks | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-859769 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-147829 |  | 2020-09-10 | 2020-10-20 |  |  |  | MLVS 243-1 | 200 | 5 | Pipe Replacement | This project may require taking the pipeline section out of service that could limit throughput and result in restrictions based on customer nominations. The following meter will be shut in on 8/13 and 9/25. | SOP | Potential out of path restrictions may be at risk. | 412065 DOMINION/TGP MORRISVILLE TRANSPORT | X20-147829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X19-1019963 | *** | 2020-10-12 | 2020-10-19 | Project Change | 9/28/20 | 10/05/20 | MLV 244-1 to MLV 245-1 | 200 | 5 | Anomaly Verification Dig | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X19-1019963 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
X20-57459 | *** | 2020-10-05 | 2020-11-12 | Project Change | 10/12/20 | 11/12/20 | Sta 245: Unit 1B | 200 | 5 | 50k Overhaul | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-57459 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
X20-859747 | *** | 2020-10-05 | 2020-10-12 | Added |  |  | Sta 245: Unit 2B | 200 | 5 | Replace Chocks | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-859747 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X19-1019981 |  | 2020-10-05 | 2020-10-09 |  |  |  | MLV 245-1 to MLV 246-1 | 200 | 5 | SCCDA | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X19-1019981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X19-1019983 | *** | 2020-09-28 | 2020-10-02 | Project Change | 10/12/20 | 10/16/20 | MLV 245-2 to MLV 246-2 | 200 | 5 | SCCDA | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X19-1019983 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
X19-1019965 | *** | 2020-10-12 | 2020-10-19 | Project Change | 9/28/20 | 10/05/20 | MLV 249-1 to MLV 254-1 | 200 | 5 | Anomaly Verification Dig | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X19-1019965 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
X19-1003673 | *** | 2020-09-25 | 2020-09-26 | Added |  |  | Station 261 | 200 | 6 | Annual ESD test | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. The meter listed below will be shut-in during the project. | SOP | Potential out of path restrictions may be at risk. | 420901 SHELL/TGP BERKSHIRE POWER SALES HAM | X19-1003673 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X19-653349 |  | 2021-04-01 | 2021-08-01 |  |  |  | Sta 261: Unit Replacement | 200 | 6 | Isolate systems from 1D (air compressor, generator, fuel gas, et al) | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X19-653349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X19-653351 |  | 2020-09-07 | 2020-09-26 |  |  |  | Sta 261: Station Outage | 200 | 6 | installation of the new suction header/filter | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. The meter listed below will be shut-in during the project. | SOP | Potential out of path restrictions may be at risk. | 420901 BERKPWR/TGP BERKSHIRE POWER SALES H | X19-653351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-34056 |  | 2020-10-02 | 2020-10-10 |  |  |  | Sta. 265E | 200 | 6 | Fall Outage | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-34056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-469001 |  | 2021-04-03 | 2021-04-19 |  |  |  | Sta 265E | 200 | 6 | Annual ESD Test & Maintenance | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-469001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X19-1003678 | *** | 2020-09-21 | 2020-09-23 | Added |  |  | Sta. 266A | 200 | 6 | Annual ESD test | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. The meter listed below will be shut-in during the project. | SOP | Potential out of path restrictions may be at risk. | 420285 AGT/TGP MENDON MASS TIE OVER WORCHE | X19-1003678 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-82424 | *** | 2020-08-17 | 2020-09-16 | Completed |  |  | MLVS 268-1, 269-1 & 270-1 | 200 | 6 | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-82424 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-736446 |  | 2020-10-09 | 2020-10-09 |  |  |  | MLV 307-2 to MLV 219-3 | 300 | 4 | Maintenance Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SIP | Potential out of path restrictions may be at risk. |  | X20-736446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-301228 |  | 2020-10-05 | 2020-10-10 |  |  |  | MLV 219-2D to MLV 303-1 | 300 | 4 | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SIP | Potential in the path restrictions may be at risk. |  | X20-301228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-647145 |  | 2020-10-12 | 2020-10-24 |  |  |  | MLV 304-2 to MLV 306-2 | 300 | 4 | SCCDA | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-647145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X19-814474 |  | 2020-03-16 | 2020-10-01 |  |  |  | Sta 307: Unit 6A | 300 | 4 | Engine Overhaul | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SIP | Potential in the path restrictions may be at risk. |  | X19-814474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-644508 |  | 2020-10-05 | 2020-10-08 |  |  |  | Sta 307 | 300 | 4 | Filter Separator Inspection | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SIP | Potential in the path restrictions may be at risk. |  | X20-644508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X19-829634 |  | 2020-10-01 | 2020-12-31 |  |  |  | Sta 307: Unit 3A | 300 | 4 | Foundation Replacement | This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations. | SIP | Potential in the path restrictions may be at risk. |  | X19-829634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X19-144300 |  | 2021-05-01 | 2021-08-20 |  |  |  | Sta 307: Unit 5A | 300 | 4 | Install Fuel Injection System and Fuel Gas Skid | This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X19-144300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X19-1003702 |  | 2020-09-22 | 2020-09-22 |  |  |  | Sta 313 | 300 | 4 | Annual ESD test | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SIP | Potential in the path restrictions may be at risk. |  | X19-1003702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-45321 |  | 2020-06-15 | 2020-10-19 |  |  |  | Sta 313: Units 1A, 2A, 4A, 5A | 300 | 4 | Automation Upgrade | This project will require unit outages, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-45321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-301505 | *** | 2020-09-15 | 2020-09-15 | Completed |  |  | Sta 313 to Sta 237 | 300 | 5 | Maintenance Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SIP | Potential in the path restrictions may be at risk. |  | X20-301505 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-301493 | *** | 2020-09-16 | 2020-09-17 | Completed |  |  | Sta 405A | 400(HC) | 5 | Filter Change Out | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SIP | Potential in the path restrictions may be at risk. |  | X20-301493 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-301494 |  | 2020-09-14 | 2020-09-19 |  |  |  | Sta 405A | 400(HC) | 5 | Turbine Exchange | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SIP | Potential in the path restrictions may be at risk. |  | X20-301494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-301496 |  | 2020-10-13 | 2020-10-14 |  |  |  | Sta 405A | 400(HC) | 5 | Discharge Valve Replacement | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-301496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-759531 | *** | 2020-09-14 | 2020-09-16 | Completed |  |  | Sta 315: Unit 2A | 300 | 4 | Suction Line | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SIP | Potential in the path restrictions may be at risk. |  | X20-759531 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X19-1003716 | *** | 2020-10-19 | 2020-10-19 | Completed |  |  | Station 321 | 300 | 4 | Annual ESD test | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X19-1003716 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X19-1003718 | *** | 2020-10-05 | 2020-10-09 | Added |  |  | Sta. 323A | 300 | 4 | Annual ESD test | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X19-1003718 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X19-1003720 | *** | 2020-09-28 | 2020-09-30 | Added |  |  | Sta 325 | 300 | 5 | Annual ESD test | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X19-1003720 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-848791 | *** | 2020-10-01 | 2020-10-02 | Added |  |  | Sta 325: Unit 4A | 300 | 5 | Unit 4A - Surge Valve | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-848791 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-35436 |  | 2020-10-26 | 2020-10-30 |  |  |  | Donna Lateral Replacement | 400(So TX) | 0 | Pipe Replacement | This project will require taking the pipeline section out of service which will limit throughput and result in restrictions based on customer nominations. The meters listed will be shut in during the project. | PIP | Potential in the path restrictions may be at risk. | 450261 CENAGAS/TGP PEMEX CHECK DELIV SOUTH 450262 CENAGAS/TGP REC NORTH HIDALGO 421017 GDR/TGP RIO BRAVO HIDALGO 410065 WAGNER/TGP UDP DONNA DEHY HIDALGO 412659 DEWBRE/TGP CIMMARRON HIDALGO | X20-35436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-280972 |  | 2020-10-27 | 2020-10-30 |  |  |  | MLV 400-2 to MLV 409-2 | 400(So TX) | 0 | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | PIP | Potential in the path restrictions may be at risk. |  | X20-280972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-280969 | *** | 2020-10-13 | 2020-10-15 | Project Change | 10/12/20 | 10/15/20 | MLV 409A-1101 to MLV 409A-1102 | 400(So TX) | 0 | Pig Run - Cleaning / Gauge 10/12/20, MFL 10/15/20 | This activity will require operating at controlled flow rates. The following meter may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. | 421017 GDR/TGP RIO BRAVO HIDALGO | X20-280969 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
X20-658546 |  | 2020-10-26 | 2020-10-30 |  |  |  | Sta 409 | 400(So TX) | 0 | 8k Hour Inspection & Compressor Work | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | PIP | Potential in the path restrictions may be at risk. |  | X20-658546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-121945 |  | 2020-10-08 | 2020-10-08 |  |  |  | Sta 409A | 400(So TX) | 0 | Quarterly Inspections | This project will require unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SIP | Potential in the path restrictions may be at risk. |  | X20-121945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-121624 |  | 2020-10-27 | 2020-10-27 |  |  |  | Sta 409 | 400(So TX) | 0 | 2k Hour Inspection | This project will require unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | PIP | Potential in the path restrictions may be at risk. |  | X20-121624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-121946 |  | 2020-10-08 | 2020-10-17 |  |  |  | Sta 409A | 400(So TX) | 0 | Unit Overhaul | This project will require unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | PIP | Potential in the path restrictions may be at risk. |  | X20-121946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-82218 |  | 2020-10-06 | 2020-10-06 |  |  |  | Sta 500-1 to Sta 823 | 500 | L | Maintenance Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The following meters will be shut-in for the duration of the project. | SOP | Potential out of path restrictions may be at risk. | 420373 TRNSCO/TGP KINDER LA EXCH (BI 1 420708 ELIZ NG/TGP GRANT LA SALES ALLEN 420436 VERNON/TGP PITKIN LA VERNON 420793 ELIZ NG/TGP J R FRANKS 1 VERNON 420388 PROVNCAL/TGP PROVENCAL LA NATCHITOC | X20-82218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-759646 | *** | 2020-09-07 | 2020-09-20 | Completed |  |  | MLVS 530-1 | 500 | L | Anomaly Remediation | This activity will include pipe inspections and repairs, as needed, in specified areas. The following meter will be shut in for the project. | SOP | Potential out of path restrictions may be at risk. | 410723 GULFSTH/TGP KILN MISS EXCH HANCOCK 420383 GULFSTH/TGP KILN MISS EXCHANGE HANC | X20-759646 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-759652 |  | 2020-09-21 | 2020-09-24 |  |  |  | MLVS 533-2 | 500 | L | Anomaly Remediation | This activity will include pipe inspections and repairs, as needed, in specified areas. The following meter may experience lower pressures; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. | 412753 PAR MINL/TGP UDP PISTOL RIDGE: RIP 412758 PETROHRV/TGP HIGHWAY 13 : RIP 533D- 412750 DELPHI/TGP UDP PISTOL RIDGE: RIP 53 | X20-759652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-759656 |  | 2020-09-25 | 2020-10-04 |  |  |  | MLVS 535-1 | 500 | 1 | Anomaly Remediation | This activity will include pipe inspections and repairs, as needed, in specified areas. Customers may experience lower pressures; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | X20-759656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-759660 |  | 2020-10-19 | 2020-10-31 |  |  |  | MLV 538-1 to MLV 541-1 | 500 | 1 | Anomaly Remediation | This activity will include pipe inspections and repairs, as needed, in specified areas. The following meter will be shut in for the project. | SOP | Potential out of path restrictions may be at risk. | 412060 /TGP HEIDELBURG TRANSPORT JASPER | X20-759660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-759663 |  | 2020-10-05 | 2020-10-18 |  |  |  | MLV 539-2 to MLV 541-2 | 500 | 1 | Anomaly Remediation | This activity will include pipe inspections and repairs, as needed, in specified areas. Customers may experience lower pressures; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | X20-759663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X19-1005955 |  | 2020-10-26 | 2020-10-30 |  |  |  | Sta 542 | 500 | 1 | Annual ESD test | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SIP | Potential in the path restrictions may be at risk. |  | X19-1005955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-152344 |  | 2020-10-26 | 2020-10-30 |  |  |  | Sta 542 | 500 | 1 | Filter Change Out | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SIP | Potential in the path restrictions may be at risk. |  | X20-152344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-45324 |  | 2020-09-07 | 2020-10-11 |  |  |  | Sta 542: Units 1B | 500 | 1 | Automation Upgrade | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-45324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X19-1005956 |  | 2020-10-12 | 2020-10-14 |  |  |  | Sta. 546 | 500 | 1 | Annual ESD test | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SIP | Potential in the path restrictions may be at risk. |  | X19-1005956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-433144 |  | 2020-10-28 | 2020-11-05 |  |  |  | MLVS 546G | 500 | 1 | Meter Tube Maintenance | This project will require taking the meter station out of service. The meter listed will be shut in for the duration of the project. |  |  | 421003 CAL GEN/TGP LOWNDES | X20-433144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-450656 | *** | 2020-11-09 | 2020-12-18 | Project Change | 7/27/20 | 9/04/20 | Sta 546: Units 4A | 500 | 1 | Engine Overhaul | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-450656 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
X19-1005957 | *** | 2020-09-29 | 2020-09-29 | Added |  |  | Sta 550 | 500 | 1 | Annual ESD test | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SIP | Potential in the path restrictions may be at risk. |  | X19-1005957 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-859755 | *** | 2020-11-09 | 2020-11-13 | Added |  |  | Sta 550 | 500 | 1 | Install Load Lines | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. The meter listed below will be shut-in during the project. | SIP | Potential in the path restrictions may be at risk. |  | X20-859755 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-433287 |  | 2020-05-11 | 2020-11-30 |  |  |  | Sta 550: Unit 3A | 500 | 1 | Regrout | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-433287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-45328 |  | 2020-08-21 | 2020-10-15 |  |  |  | Sta 555: Units 1A to 3A | 500 | 1 | Automation Upgrade | This project will require unit outages, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-45328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-45327 |  | 2020-10-16 | 2020-11-19 |  |  |  | Sta 555: Unit 1B | 500 | 1 | Automation Upgrade | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-45327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-158409 |  | 2020-09-21 | 2020-10-05 |  |  |  | MLVS 557B-101.1 | 500 | 1 | ECDA | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-158409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-852663 | *** | 2020-09-29 | 2020-09-29 | Added |  |  | Sta 563 | 500 | 1 | Safety System | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-852663 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-273344 | *** | 2020-08-13 | 2020-09-10 | Completed |  |  | MLV 700-1 to 707-1 | 700 | 0 | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-273344 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-255902 |  | 2020-09-29 | 2020-09-29 |  |  |  | MLV 707 to STA 40 | 700 | 0 | Maintenance Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. | SOP | Potential out of path restrictions may be at risk. |  | X20-255902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-116357 | *** | 2020-10-20 | 2020-10-20 | Completed |  |  | MLV 820-1A to MLV 821R-101.1 | 800 | L | Maintenance Pig | This activity This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.will require operating at controlled flow rates. Customers may experience pressure fluctuations. | SIP | Potential in the path restrictions may be at risk. | 49446 CAM IPL/TGP BANKEN RD AT HWY 27 DE 412768 GLDNPASS/TGP STARKS LNG: RIP 820 10 412737 CAM IPL/TGP DEQUINCY GAS STORAGE C 421050 LBERTYGS/TGP DE QUINCY GAS STORAGE 420550 ENTERPRSE/TGP SABINE RIVER 412013 ENTRPRSE/TGP SABINE RIVER TRANS NEW 412690 HPL/TGP SABINE NEWTON 411586 TRNSCO/TGP STARKS LA TRANSPORT CALC | X20-116357 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-43807 |  | 2020-09-23 | 2020-09-23 |  |  |  | STA 823 to Sta 507F | 800 | L | Maintenance Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The following meters will be shut-in for the duration of the project. | SOP | Potential out of path restrictions may be at risk. | 410671 TARGA/TGP UDP LOWRY PLANT DEHY CAME 412002 ANR/TGP CHALKLEY TRANSPORT JEFFERSO 412680 TRUNKLNE/TGP LACASSINE JEFFERSON DA 450302 VAR/TGP CHENIER STRADDLE PLT INLET 450303 TGP/TGP GRAND CHENIER STRADDLE PLAN | X20-43807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X19-1005964 |  | 2020-11-20 | 2020-11-20 |  |  |  | Sta 836A | 800 | 1 | Annual ESD test | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X19-1005964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X19-1005967 |  | 2020-10-22 | 2020-10-22 |  |  |  | Sta 847 | 800 | 1 | Annual ESD test | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X19-1005967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X19-1005969 |  | 2020-11-12 | 2020-11-12 |  |  |  | Sta. 856 | 800 | 1 | Annual ESD test | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X19-1005969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-158395 |  | 2020-08-12 | 2020-09-18 |  |  |  | MLV 857-1 to MLV 860-1 | 800 | 1 | Anomaly Remediation | This project may require taking the pipeline section out of service, which could limit throughput and result in restrictions based on customer nominations. The meter listed may experience pressure fluctuations. | SOP | Potential out of path restrictions may be at risk. | 420706 TEAC/TGP CLIFTON SALES WAYNE | X20-158395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X20-835824 | *** | 2020-09-15 | 2020-09-18 | Project Change | 9/15/20 | 9/17/20 | Sta 871: Unit 1A | 800 | 2 | Anchor Bolts | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | X20-835824 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0