{"text_format":"1","workbook":"xlsx","n_sheets":4,"sheets":["Closed","Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":8,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Closed","index":0,"n_rows":37,"n_cols":22,"rows_kept":37,"cut":false,"hidden":true,"merged":[[1,3,1,15],[2,3,2,15],[3,3,3,15]]}
[null,null,null,"Updated ","2016"]
[null,null,null,"Tennessee Gas Pipeline 2015 Pipeline Outage and Maintenance Summary"]
[null,null,null,"This is a summary of the current status of all TGP Winter 2014-2015 Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  Additionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
[null,null,null,"*** Indicates revision"]
["Date Change","Project New/Completed/Closed","Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","Location","Leg","Zone","Maintenance Activity","Anticipated Impact","Potential Restriction Level","TOS Potential Restrictions","Meter(s) in Impacted Area","Customer Notifications","Loc","Email Text","Posting Text","Completion Text"]
[{"$f":"IF(AND(H6<>\"\",I6<>\"\"), \"Date change. Previously scheduled \" & TEXT(H6,\"m/d/y;@\") &IF(H6=I6,\"\",\" to \" & TEXT(I6,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed",null,{"$f":"IF(G6<>\"\",\"***\",\"\")","v":"***"},"2015-01-11","2016-01-11",{"$f":"IF(AND(A6=\"\",B6=\"\"),\"\",IF(B6=\"\",A6,B6))","v":"Project Completed"},null,null,"MS #412494 DCP Warren","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412494 DCP Warren",401,{"$f":"\"(\"&C6&\") \"&J6&\":  \"&M6&IF(AND(E6=\"\",F6=\"\"),\"\",\" (\")&IF(E6=\"\",\"\",\"\"&TEXT(E6,\"m/d/y;@\"))&IF(OR(F6=E6,E6=\"\",F6=\"\"),\"\",\" to \")&IF(OR(F6=\"\",F6=E6),\"\",TEXT(F6,\"m/d/y;@\"))&IF(AND(E6=\"\",F6=\"\"),\"\",\")\")","v":"() MS #412494 DCP Warren:  Meter Station (1/11/15 to 1/11/16)"},{"$f":"D6&J6&\":  \"&M6&IF(AND(E6=\"\",F6=\"\"),\"\",\"\n\")&IF(E6=\"\",\"\",\"--\"&TEXT(E6,\"m/d/y;@\"))&IF(OR(F6=E6,E6=\"\",F6=\"\"),\"\",\" through \")&IF(OR(F6=\"\",F6=E6),\"\",TEXT(F6,\"m/d/y;@\"))&IF(AND(E6=\"\",F6=\"\"),\"\",\":  \")&N6&\"  \"&P6&IF(Q6=\"\",\"\",\"\n\"&Q6)&IF(G6=\"\",\"\",\"\n***\")&G6&\"\n………………………………\"","v":"***MS #412494 DCP Warren:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412494 DCP Warren\n***Project Completed\n………………………………"},{"$f":"D6&J6&\":  \"&M6&IF(G6=\"\",\"\",\"\n***\")&G6&IF(Q6=\"\",\"\",\"\nThe following meters are available for nominations:\n\")&Q6&\"\n………………………………\"","v":"***MS #412494 DCP Warren:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412494 DCP Warren\n………………………………"}]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412400 King Ranch","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412400 King Ranch",402.1,"() MS #412400 King Ranch:  Meter Station (1/11/15 to 1/11/16)","***MS #412400 King Ranch:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412400 King Ranch\n***Project Completed\n………………………………","***MS #412400 King Ranch:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412400 King Ranch\n………………………………"]
["","Project Completed",null,"***","2015-01-12","2016-01-12","Project Completed",null,null,"MS #410539 Duvak Gas Gathering","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410539 Duvak Gas Gathering",402.1,"() MS #410539 Duvak Gas Gathering:  Meter Station (1/12/15 to 1/12/16)","***MS #410539 Duvak Gas Gathering:  Meter Station\n--1/12/15 through 1/12/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410539 Duvak Gas Gathering\n***Project Completed\n………………………………","***MS #410539 Duvak Gas Gathering:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n410539 Duvak Gas Gathering\n………………………………"]
["","Project Completed",null,"***","2015-01-13","2016-01-13","Project Completed",null,null,"MS #412356 DCP LaGloria","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412356 DCP LaGloria",403.1,"() MS #412356 DCP LaGloria:  Meter Station (1/13/15 to 1/13/16)","***MS #412356 DCP LaGloria:  Meter Station\n--1/13/15 through 1/13/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412356 DCP LaGloria\n***Project Completed\n………………………………","***MS #412356 DCP LaGloria:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412356 DCP LaGloria\n………………………………"]
["","Project Completed",null,"***","2015-01-13","2016-01-13","Project Completed",null,null,"MS #410173 Enterprise LaReforma","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410173 Enterprise LaReforma",406.1,"() MS #410173 Enterprise LaReforma:  Meter Station (1/13/15 to 1/13/16)","***MS #410173 Enterprise LaReforma:  Meter Station\n--1/13/15 through 1/13/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410173 Enterprise LaReforma\n***Project Completed\n………………………………","***MS #410173 Enterprise LaReforma:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n410173 Enterprise LaReforma\n………………………………"]
["","Project Completed",null,"***","2015-01-12","2016-01-12","Project Completed",null,null,"MS #411903 Enterprise El Benito","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","411903 Enterprise El Benito",407.1,"() MS #411903 Enterprise El Benito:  Meter Station (1/12/15 to 1/12/16)","***MS #411903 Enterprise El Benito:  Meter Station\n--1/12/15 through 1/12/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n411903 Enterprise El Benito\n***Project Completed\n………………………………","***MS #411903 Enterprise El Benito:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n411903 Enterprise El Benito\n………………………………"]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412088 Enterprise Sullivan","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412088 Enterprise Sullivan",407.1,"() MS #412088 Enterprise Sullivan:  Meter Station (1/11/15 to 1/11/16)","***MS #412088 Enterprise Sullivan:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412088 Enterprise Sullivan\n***Project Completed\n………………………………","***MS #412088 Enterprise Sullivan:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412088 Enterprise Sullivan\n………………………………"]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412683 HESCO","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412683 HESCO",408.1,"() MS #412683 HESCO:  Meter Station (1/11/15 to 1/11/16)","***MS #412683 HESCO:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412683 HESCO\n***Project Completed\n………………………………","***MS #412683 HESCO:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412683 HESCO\n………………………………"]
[{"$f":"IF(AND(H14<>\"\",I14<>\"\"), \"Date change. Previously scheduled \" & TEXT(H14,\"m/d/y;@\") &IF(H14=I14,\"\",\" to \" & TEXT(I14,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X16-36843",{"$f":"IF(G14<>\"\",\"***\",\"\")","v":"***"},"2016-01-27","2016-01-27","Project Completed",null,null,"Sta. 237",200,5,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,237,"(X16-36843) Sta. 237:  Unit  Maintenance (1/27/16)","***Sta. 237:  Unit  Maintenance\n--1/27/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Sta. 237:  Unit  Maintenance\n***Project Completed\n………………………………"]
[{"$f":"IF(AND(H15<>\"\",I15<>\"\"), \"Date change. Previously scheduled \" & TEXT(H15,\"m/d/y;@\") &IF(H15=I15,\"\",\" to \" & TEXT(I15,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X14-1478563",{"$f":"IF(G15<>\"\",\"***\",\"\")","v":"***"},"2015-11-16","2016-02-12","Project Completed",null,null,"MLV 32-1D to 33-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,32.200000000000003,"(X14-1478563) MLV 32-1D to 33-1:  Hydrotest (11/16/15 to 2/12/16)","***MLV 32-1D to 33-1:  Hydrotest\n--11/16/15 through 2/12/16:  This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***MLV 32-1D to 33-1:  Hydrotest\n***Project Completed\n………………………………"]
[null,"Project Completed","X16-16074",null,"2016-01-18","2016-01-28","Project Completed",null,null,"Station 550","500","1","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,550,"(X16-16074) Station 550:  Station Maintenance (1/18/16 to 1/28/16)","Station 550:  Station Maintenance\n--1/18/16 through 1/28/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","Station 550:  Station Maintenance\n***Project Completed\n………………………………"]
[{"$f":"IF(AND(H17<>\"\",I17<>\"\"), \"Date change. Previously scheduled \" & TEXT(H17,\"m/d/y;@\") &IF(H17=I17,\"\",\" to \" & TEXT(I17,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X16-46202",{"$f":"IF(G17<>\"\",\"***\",\"\")","v":"***"},"2016-02-01","2016-02-07","Project Completed",null,null,"Station 9","100","0","Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.",null,9,"(X16-46202) Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items) (2/1/16 to 2/7/16)","***Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)\n--2/1/16 through 2/7/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\n***Project Completed\n………………………………","***Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)\n***Project Completed\n………………………………"]
["","Project Completed","X15-925633","***","2016-02-09","2016-02-11","Project Completed",null,null,"Sta. 266A",200,6,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,266,"(X15-925633) Sta. 266A:  Unit  Maintenance (2/9/16 to 2/11/16)","***Sta. 266A:  Unit  Maintenance\n--2/9/16 through 2/11/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Sta. 266A:  Unit  Maintenance\n***Project Completed\n………………………………"]
["","Project Completed","X15-929733","***","2016-01-27","2016-02-10","Project Completed",null,null,"MLV 834-1 to 838-1",800,5,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",834.1,"(X15-929733) MLV 834-1 to 838-1:  ILI/Cleaning Pig (1/27/16 to 2/10/16)","***MLV 834-1 to 838-1:  ILI/Cleaning Pig\n--1/27/16 through 2/10/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 834-1 to 838-1:  ILI/Cleaning Pig\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X14-1562506","***","2015-11-02","2016-02-19","Project Completed",null,null,"MLV 5-1 to 6-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410063 ROCHE DEHYDRATION             \n",5.0999999999999996,"(X14-1562506) MLV 5-1 to 6-1:  Hydrotest (11/2/15 to 2/19/16)","***MLV 5-1 to 6-1:  Hydrotest\n--11/2/15 through 2/19/16:  This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410063 ROCHE DEHYDRATION             \n\n***Project Completed\n………………………………","***MLV 5-1 to 6-1:  Hydrotest\n***Project Completed\nThe following meters are available for nominations:\n410063 ROCHE DEHYDRATION             \n\n………………………………"]
["","Project Completed","X14-1562506","***","2015-11-02","2016-02-19","Project Completed",null,null,"MLV 7-1 to 9-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","\n412490 Charro\n421083 Eagle Ford Field Service",5.0999999999999996,"(X14-1562506) MLV 7-1 to 9-1:  Hydrotest (11/2/15 to 2/19/16)","***MLV 7-1 to 9-1:  Hydrotest\n--11/2/15 through 2/19/16:  This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n\n412490 Charro\n421083 Eagle Ford Field Service\n***Project Completed\n………………………………","***MLV 7-1 to 9-1:  Hydrotest\n***Project Completed\nThe following meters are available for nominations:\n\n412490 Charro\n421083 Eagle Ford Field Service\n………………………………"]
["Date change. Previously scheduled 2/18/16 to 2/20/16.","Project Completed","X15-882289","***","2016-02-22","2016-02-24","Project Completed","2016-02-18","2016-02-20","MLV 24-2 to 25-2S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.2,"(X15-882289) MLV 24-2 to 25-2S:  Anomaly Remediation (2/22/16 to 2/24/16)","***MLV 24-2 to 25-2S:  Anomaly Remediation\n--2/22/16 through 2/24/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 24-2 to 25-2S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-925630","***","2016-02-23","2016-02-23","Project Completed",null,null,"WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B)",200,"L","ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,265.10000000000002,"(X15-925630) WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig (2/23/16)","***WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig\n--2/23/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig\n***Project Completed\n………………………………"]
["","Project Completed","X16-23748","***","2016-02-15","2016-02-18","Project Completed",null,null,"MLV 530-3 to 532-3",500,"L","ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,530.29999999999995,"(X16-23748) MLV 530-3 to 532-3:  ILI/Cleaning Pig (2/15/16 to 2/18/16)","***MLV 530-3 to 532-3:  ILI/Cleaning Pig\n--2/15/16 through 2/18/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***MLV 530-3 to 532-3:  ILI/Cleaning Pig\n***Project Completed\n………………………………"]
["","Project Canceled","X16-98720","***","2016-03-06","2016-03-06","Project Canceled",null,null,"Sta. 1",100,0,"Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,1,"(X16-98720) Sta. 1:  Station Maintenance (3/6/16)","***Sta. 1:  Station Maintenance\n--3/6/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Canceled\n………………………………","***Sta. 1:  Station Maintenance\n***Project Canceled\n………………………………"]
["","Project Completed","X14-1562513\nX14-1540661","***","2015-07-01","2016-03-04","Project Completed",null,null,"Station 32","100","0","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,32,"(X14-1562513\nX14-1540661) Station 32:  Station Maintenance (7/1/15 to 3/4/16)","***Station 32:  Station Maintenance\n--7/1/15 through 3/4/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Station 32:  Station Maintenance\n***Project Completed\n………………………………"]
["","Project Canceled","X15-926822","***","2016-06-06","2016-06-11","Project Canceled",null,null,"BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1)",300,6,"Pipe Inspection","This project involves inspecting multiple sites.  We do not anticipate having to do any repairs, however if a repair is needed  there is a potential that the pipe  may require replacement which will require isolation of the pipe.  This may limit throughput and will result in restrictions based on customer nominations.  Customers may experience pressure fluctuations during this timeframe.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",343.1,"(X15-926822) BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection (6/6/16 to 6/11/16)","***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection\n--6/6/16 through 6/11/16:  This project involves inspecting multiple sites.  We do not anticipate having to do any repairs, however if a repair is needed  there is a potential that the pipe  may require replacement which will require isolation of the pipe.  This may limit throughput and will result in restrictions based on customer nominations.  Customers may experience pressure fluctuations during this timeframe.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928271","***","TBD","TBD","Project Canceled",null,null,"MLV 555-1 to 550-1",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.1,"(X15-928271) MLV 555-1 to 550-1:  ILI/Cleaning Pig (TBD)","***MLV 555-1 to 550-1:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-1 to 550-1:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928272","***","TBD","TBD","Project Canceled",null,null,"MLV 555-2 to 550-2",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.20000000000005,"(X15-928272) MLV 555-2 to 550-2:  ILI/Cleaning Pig (TBD)","***MLV 555-2 to 550-2:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-2 to 550-2:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928273","***","TBD","TBD","Project Canceled",null,null,"MLV 555-3 to 552-3",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.29999999999995,"(X15-928273) MLV 555-3 to 552-3:  ILI/Cleaning Pig (TBD)","***MLV 555-3 to 552-3:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-3 to 552-3:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-882281","***","2016-02-24","2016-03-03","Project Completed",null,null,"24-1A to 25-1S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.1,"(X15-882281) 24-1A to 25-1S:  Anomaly Remediation (2/24/16 to 3/3/16)","***24-1A to 25-1S:  Anomaly Remediation\n--2/24/16 through 3/3/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***24-1A to 25-1S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-882291","***","2016-03-03","2016-03-04","Project Completed",null,null,"MLV 24-3 to 25-3S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.3,"(X15-882291) MLV 24-3 to 25-3S:  Anomaly Remediation (3/3/16 to 3/4/16)","***MLV 24-3 to 25-3S:  Anomaly Remediation\n--3/3/16 through 3/4/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 24-3 to 25-3S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X14-1178175","***","2015-06-15","2016-03-31","Project Completed",null,null,"Station 63","100","1","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,63,"(X14-1178175) Station 63:  Station Maintenance (6/15/15 to 3/31/16)","***Station 63:  Station Maintenance\n--6/15/15 through 3/31/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Station 63:  Station Maintenance\n***Project Completed\n………………………………"]
["","Project Cancelled","X15-913224","***","2016-04-16","2016-05-21","Project Cancelled",null,null,"MLV 109-2",100,2,"Pipe Replacement","This project will require taking the pipeline section out of service.   This will limit throughput and will result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",109.2,"(X15-913224) MLV 109-2:  Pipe Replacement (4/16/16 to 5/21/16)","***MLV 109-2:  Pipe Replacement\n--4/16/16 through 5/21/16:  This project will require taking the pipeline section out of service.   This will limit throughput and will result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Cancelled\n………………………………","***MLV 109-2:  Pipe Replacement\n***Project Cancelled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-926830","***","2016-03-07","2016-03-11","Project Completed",null,null,"MLV 400-1 to 408-1",100,0,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.","To Be Determined",400.1,"(X15-926830) MLV 400-1 to 408-1:  ILI/Cleaning Pig (3/7/16 to 3/11/16)","***MLV 400-1 to 408-1:  ILI/Cleaning Pig\n--3/7/16 through 3/11/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 400-1 to 408-1:  ILI/Cleaning Pig\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Cancelled","X16-143836","***","2016-03-28","2016-04-04","Project Cancelled",null,null,"Sta. 409",100,0,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.",null,409,"(X16-143836) Sta. 409:  Unit  Maintenance (3/28/16 to 4/4/16)","***Sta. 409:  Unit  Maintenance\n--3/28/16 through 4/4/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\n***Project Cancelled\n………………………………","***Sta. 409:  Unit  Maintenance\n***Project Cancelled\n………………………………"]
["","Project Cancelled","X15-929680","***","2016-04-18","2016-04-27","Project Cancelled",null,null,"SABINE - KINDER LINE to 822-1",800,"L","Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",822.1,"(X15-929680) SABINE - KINDER LINE to 822-1:  Anomaly Remediation (4/18/16 to 4/27/16)","***SABINE - KINDER LINE to 822-1:  Anomaly Remediation\n--4/18/16 through 4/27/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Cancelled\n………………………………","***SABINE - KINDER LINE to 822-1:  Anomaly Remediation\n***Project Cancelled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]

{"sheet":"Sheet1","index":1,"n_rows":81,"n_cols":33,"rows_kept":81,"cut":false,"hidden":false,"merged":[[2,0,2,14]]}
["Updated ","2020-11-19"]
["Tennessee Gas Pipeline 2020 Pipeline Outage and Maintenance Summary"]
["This is a summary of the current status of all TGP 2020 Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  \nAdditionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
["*** Indicates revision"]
["Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","Location","Leg","Zone","Maintenance Activity","Anticipated Impact","Potential Restriction Level","TOS Potential Restrictions","Meter(s) in Impacted Area",null,null,null,null,null,null,null,null,null,"\\\\houCORP\\TRANS\\TRANSERVICES\\OPPLAN\\COMMON\\Outages\\Outage_DB\\TGP\\Files"]
["X20-957168",null,"2020-12-10","2020-12-12",null,null,null,"MLV 1-2BL to MLV 1-2A","100","0","New Meter TGP Whistle (Pin# 54847)","This project may require reducing the pipeline pressure, which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-957168",0,0,0,0,0,0,0,0]
["X19-761902",null,"2020-12-07","2020-12-18",null,null,null,"MLV 5-2 to MLV 2-2","100","0","Pipe Replacement","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X19-761902",0,0,0,0,0,0,0,0]
["X20-57719",null,"2020-09-08","2020-11-18",null,null,null,"Sta 17: Unit 1C","100","0","Major Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-57719",0,0,0,0,0,0,0,0]
["X19-1003538",null,"2020-12-07","2020-12-11",null,null,null,"Sta. 25","100","0","Annual ESD test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X19-1003538",0,0,0,0,0,0,0,0]
["X20-658542",null,"2020-12-07","2020-12-11",null,null,null,"Sta. 25","100","0","Annual Electrical Inspection","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-658542",0,0,0,0,0,0,0,0]
["X20-939837",null,"2020-12-31","2020-12-31",null,null,null,"Sta 25: Unit 1C","100","0","Electrical Test & Borescope","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-939837",0,0,0,0,0,0,0,0]
["X20-832825","***","2020-09-08","2020-11-20","Project Change","9/08/20","12/11/20","MLV 25-1 to 32-1","100","0","Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","412862 SOCOASTP/TGP COLDSPRING LATERAL: RI",null,null,null,null,null,null,null,null,null,"X20-832825",0,0,1,0,0,0,0,0]
["X20-984287",null,"2020-11-30","2020-12-19",null,null,null,"MLV 36-3 to MLV 36-3A","100","0","Emergent Hydrostatic Pressure Test","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-984287",0,0,0,0,0,0,0,0]
["X20-835661","***","2021-01-12","2021-01-12","Project Change","11/17/20","11/17/20","MLV 40-2 to MLV 32-2","100","0","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.","No meters affected on this maintenance pig run.",null,null,null,null,null,null,null,null,null,"X20-835661",0,1,1,0,0,0,0,0]
["X20-647061","***","2020-09-01","2020-12-07","Project Change","9/01/20","11/17/20","MLV 40-1 and 41-1","100","0","TGP 100-1 & 2 RED RIVER BRIDGE RECOATING","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-647061",0,0,1,0,0,0,0,0]
["X20-950850",null,"2020-11-02","2020-12-31",null,null,null,"MLV 40-3D to MLV 41-3A","100","1","Anomaly Remediation From ILI","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-950850",0,0,0,0,0,0,0,0]
["X20-1015437","***","2020-11-12","2020-11-12","Completed",null,null,"MLVS 47E","100","1","Meter Scrubber Inspection","This project will overlap with the customer’s scheduled plant shutdown.  The meter listed will be shut in for the duration of the project.",null,null,"421062 ENTRGYLA/TGP PERRYVILLE POWER OUACH",null,null,null,null,null,null,null,null,null,"X20-1015437",1,0,0,0,0,0,0,0]
["X20-945751",null,"2020-11-30","2020-12-31",null,null,null,"MLV 47-4D to MLV 49-4","100","1","High Priority Anomaly Digs","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed below may be shut-in during the project. Project dates pending.","SOP","Potential out of path restrictions may be at risk.","421013 BBTMIDLA/TGP FAIRBANKS OUACHITA",null,null,null,null,null,null,null,null,null,"X20-945751",0,0,0,0,0,0,0,0]
["X20-963839",null,"2021-04-20","2021-04-27",null,null,null,"MLV 63-1S to MLV 54-1D","100","1","Pig Run - Cleaning / Gauge 4/20/21, MFL 4/22/21, Hardspot 4/27/21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-963839",0,0,0,0,0,0,0,0]
["X20-963844",null,"2021-03-16","2021-03-23",null,null,null,"MLV 63-4S to MLV 54-4D","100","1","Pig Run - Cleaning / Gauge 3/16/21, MFL 3/18/21, Hardspot 3/23/21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-963844",0,0,0,0,0,0,0,0]
["X20-1036894","***","2020-11-22","2020-11-23","Added",null,null,"Sta 63","100","1","JW Heater 5 year inspection","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-1036894",1,0,0,0,0,0,0,0]
["X20-963850",null,"2021-03-02","2021-03-09",null,null,null,"MLV 71-3S to MLV 63-3D","100","1","Pig Run - Cleaning / Gauge 3/2/21, MFL 3/4/21, Hardspot 3/9/21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-963850",0,0,0,0,0,0,0,0]
["X19-1003556",null,"2020-11-17","2020-11-18",null,null,null,"Sta. 71","100","1","Annual ESD test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X19-1003556",0,0,0,0,0,0,0,0]
["X20-973331",null,"2020-09-29","2020-12-15",null,null,null,"MLV 71-3D to 79-3S","100","1","High Priority Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-973331",0,0,0,0,0,0,0,0]
["X20-939822",null,"2020-11-30","2020-12-11",null,null,null,"Sta 87: Unit 3D","100","2","Exhaust Bolts","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-939822",0,0,0,0,0,0,0,0]
["X20-776714",null,"2020-09-14","2020-12-30",null,null,null,"MLV 87-2 to MLV 96-2","100","2","Anomaly Remediation From ILI","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-776714",0,0,0,0,0,0,0,0]
["X19-703248","***","2019-08-01","2021-12-31","Project Change","8/01/19","12/31/20","MLV 106-1 to MLV 96-1","100","2","Pressure Restriction from ILI","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X19-703248",0,0,1,0,0,0,0,0]
["X20-950668",null,"2020-10-27","2020-12-19",null,null,null,"MLV 96-1 to MLV 106-1","100","2","Anomaly Remediation From ILI","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-950668",0,0,0,0,0,0,0,0]
["X20-1026313",null,"2020-11-16","2020-12-04",null,null,null,"MLV 100-2 to MLV 101-2","100","2","Class Change","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-1026313",0,0,0,0,0,0,0,0]
["X20-877871",null,"2020-12-04","2020-12-13",null,null,null,"Sta 106","100","2","Station Yard Valves Tie In","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-877871",0,0,0,0,0,0,0,0]
["X20-776683",null,"2020-09-08","2020-11-20",null,null,null,"MLV 106-3 to MLV 107-3","100","2","Wrinkle Bend Replacement","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-776683",0,0,0,0,0,0,0,0]
["X20-1031708",null,"2020-11-30","2020-12-04",null,null,null,"Sta 110: Units 6A, 8A, & 9A","100","2","Electrical Inspections","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-1031708",0,0,0,0,0,0,0,0]
["X20-930955","***","2020-10-12","2020-12-04","Project Change","10/12/20","11/16/20","Sta 114: Unit 2C","100","3","Coupling Repair","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-930955",0,0,1,0,0,0,0,0]
["X20-947957",null,"2020-12-14","2020-12-15",null,null,null,"Sta 114: Unit 1D","100","3","4k Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-947957",0,0,0,0,0,0,0,0]
["X20-947958",null,"2020-12-01","2020-12-02",null,null,null,"Sta 119: Unit 1A","100","3","4k Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-947958",0,0,0,0,0,0,0,0]
["X20-848924",null,"2020-11-16","2020-11-20",null,null,null,"Sta 200: Unit 2A","200","4","10k Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-848924",0,0,0,0,0,0,0,0]
["X20-848923",null,"2021-01-11","2021-01-15",null,null,null,"Sta 200: Unit 3A","200","4","10k Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-848923",0,0,0,0,0,0,0,0]
["X20-848918","***","2020-11-09","2020-11-13","Completed",null,null,"Sta 200: Unit 10A","200","4","10k Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-848918",1,0,0,0,0,0,0,0]
["X20-942960",null,"2020-11-30","2020-12-18",null,null,null,"Sta 204: Unit 1A","200","4","Oil Filter Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-942960",0,0,0,0,0,0,0,0]
["X20-143965","***","2020-09-28","2020-11-13","Completed",null,null,"Sta 204: Unit 10A","200","4","Automation Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-143965",1,0,0,0,0,0,0,0]
["X20-942966","***","2021-01-05","2021-01-06","Project Change","11/17/20","11/18/20","Sta 204: Unit 12A","200","4","Air Cleaner Base Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-942966",0,1,1,0,0,0,0,0]
["X20-942967",null,"2020-11-16","2020-11-20",null,null,null,"Sta 209: Unit 6A","200","4","Catwalk Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-942967",0,0,0,0,0,0,0,0]
["X20-494996",null,"2020-06-01","2020-11-20",null,null,null,"Sta 209: Unit 7A","200","4","Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-494996",0,0,0,0,0,0,0,0]
["X20-942968",null,"2020-12-14","2020-12-24",null,null,null,"Sta 209: Unit 9A","200","4","Catwalk Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-942968",0,0,0,0,0,0,0,0]
["X20-942970",null,"2020-11-30","2020-12-10",null,null,null,"Sta 209: Unit 10A","200","4","Catwalk Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-942970",0,0,0,0,0,0,0,0]
["X20-981353","***","2020-11-09","2020-11-13","Completed",null,null,"Sta 219","200","4","GMV Unit work for Inspections","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-981353",1,0,0,0,0,0,0,0]
["X20-802118","***","2020-11-09","2020-11-19","Project Change","11/09/20","11/12/20","Sta 219: Unit 1B","200","4","Protective Devices","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-802118",0,0,1,0,0,0,0,0]
["X20-981354",null,"2020-11-16","2020-11-19",null,null,null,"Sta 219: Unit 1B","200","4","Annual DOT Protective Device Checks, Relief Valve Testing, Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-981354",0,0,0,0,0,0,0,0]
["X20-147829","***","2020-09-10","2020-11-12","Completed",null,null,"MLVS 243-1","200","5","Pipe Replacement","This project may require taking the pipeline section out of service that could limit throughput and result in restrictions based on customer nominations.  The following meter will be shut in on 8/13 and 9/25.","SOP","Potential out of path restrictions may be at risk.","412065 DOMINION/TGP MORRISVILLE TRANSPORT",null,null,null,null,null,null,null,null,null,"X20-147829",1,0,0,0,0,0,0,0]
["X20-57459","***","2020-10-05","2020-11-20","Project Change","10/05/20","11/12/20","Sta 245: Unit 1B","200","5","50k Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-57459",0,0,1,0,0,0,0,0]
["X20-894601","***","2020-11-09","2020-11-13","Completed",null,null,"Sta 249","200","5","Unit 2A - Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-894601",1,0,0,0,0,0,0,0]
["X19-653349",null,"2021-04-01","2021-08-01",null,null,null,"Sta 261: Unit Replacement","200","6","Isolate systems from 1D (air compressor, generator, fuel gas, et al)","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X19-653349",0,0,0,0,0,0,0,0]
["X20-1031954",null,"2021-04-03","2021-04-19",null,null,null,"Sta. 265E","200","6","Spring Shutdown","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-1031954",0,0,0,0,0,0,0,0]
["X20-469001",null,"2021-04-03","2021-04-19",null,null,null,"Sta 265E","200","6","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-469001",0,0,0,0,0,0,0,0]
["X20-1034818",null,"2021-10-16","2021-10-23",null,null,null,"Sta. 265E","200","6","Fall Outage","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-1034818",0,0,0,0,0,0,0,0]
["X20-1031952",null,"2021-04-03","2021-04-19",null,null,null,"Sta 265: Unit 1A","200","6","Controls Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-1031952",0,0,0,0,0,0,0,0]
["X20-647145","***","2020-11-10","2020-11-20","Completed",null,null,"MLV 304-2 to MLV 306-2","300","4","SCCDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-647145",1,0,0,0,0,0,0,0]
["X20-984300","***","2020-11-11","2020-11-13","Completed",null,null,"Sta 307: Unit 1A","300","4","DOT & Non-DOT protective device testing","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-984300",1,0,0,0,0,0,0,0]
["X20-984297",null,"2020-12-07","2020-12-11",null,null,null,"Sta 307: Unit 2A","300","4","DOT & Non-DOT protective device testing, pocket control upgrade project","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-984297",0,0,0,0,0,0,0,0]
["X20-984298",null,"2020-11-16","2020-11-20",null,null,null,"Sta 307: Unit 3A","300","4","DOT & Non-DOT protective device testing, pocket control upgrade project","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-984298",0,0,0,0,0,0,0,0]
["X19-829634",null,"2021-02-15","2021-05-21",null,null,null,"Sta 307: Unit 3A","300","4","Foundation Replacement","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X19-829634",0,0,0,0,0,0,0,0]
["X19-144300",null,"2021-05-01","2021-08-20",null,null,null,"Sta 307: Unit 5A","300","4","Install Fuel Injection System and Fuel Gas Skid","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X19-144300",0,0,0,0,0,0,0,0]
["X20-867155","***","2020-10-26","2020-11-13","Completed",null,null,"MLV 409-1 to MLV 400-1","400(So TX)","0","Anomaly Remediation","This activity will include pipe inspections and repairs, as needed, in specified areas. Customers may experience lower pressures; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-867155",1,0,0,0,0,0,0,0]
["X20-925634","***","2020-11-02","2020-11-15","Completed",null,null,"MLV 541-3 to MLV 542-3","500","1","Anomaly Remediation","This activity will include pipe inspections and repairs, as needed, in specified areas. Customers may experience lower pressures; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-925634",1,0,0,0,0,0,0,0]
["X20-433144","***","2020-11-10","2020-11-14","Completed",null,null,"MLVS 546G","500","1","Meter Tube Maintenance","This project will overlap with the customer’s scheduled plant shutdown.  The meter listed will be shut in for the duration of the project.",null,null,"421003 CAL GEN/TGP LOWNDES",null,null,null,null,null,null,null,null,null,"X20-433144",1,0,0,0,0,0,0,0]
["X20-872302",null,"2020-10-05","2020-11-20",null,null,null,"Sta 546: Units 1A","500","1","Compressor Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-872302",0,0,0,0,0,0,0,0]
["X20-450656",null,"2020-11-09","2020-12-18",null,null,null,"Sta 546: Units 4A","500","1","Engine Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-450656",0,0,0,0,0,0,0,0]
["X20-973239","***","2020-11-02","2020-11-18","Project Change","11/02/20","11/13/20","Sta 546 - Unit 7A","500","1","UCP Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-973239",0,0,1,0,0,0,0,0]
["X20-909069","***","2020-10-26","2020-11-13","Completed",null,null,"MLVS 548-1","500","1","Special Permit Verification Dig","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-909069",1,0,0,0,0,0,0,0]
["X20-859755",null,"2020-11-17","2020-11-20",null,null,null,"Sta 550","500","1","Install Load Lines","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-859755",0,0,0,0,0,0,0,0]
["X20-433287",null,"2020-05-11","2021-01-31",null,null,null,"Sta 550: Unit 3A","500","1","Regrout","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-433287",0,0,0,0,0,0,0,0]
["X20-45327",null,"2020-10-31","2020-11-25",null,null,null,"Sta 555: Unit 1B","500","1","Automation Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-45327",0,0,0,0,0,0,0,0]
["X20-1046760","***","2020-12-14","2020-12-18","Added",null,null,"Sta 563","500","1","Protective Device Checks & Engine Inspections","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-1046760",1,0,0,0,0,0,0,0]
["X19-1005964",null,"2020-11-20","2020-11-20",null,null,null,"Sta 836A","800","1","Annual ESD test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X19-1005964",0,0,0,0,0,0,0,0]
["X20-1036903","***","2020-11-16","2020-11-20","Added",null,null,"Sta 847","800","1","Substation and Switchgear Inspection","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-1036903",1,0,0,0,0,0,0,0]
["X20-963853",null,"2021-02-08","2021-02-11",null,null,null,"MLV 851-1 to MLV 856-1","800","1","Pig Run - Cleaning / Gauge 2/8/21, Caliper 2/9/21, MFL 2/11/21","This activity will require operating at controlled flow rates. The meters listed may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.","420282 NEWALBNY/TGP COTTON PLANT MS UNION\n420276 BLDWYN/TGP BALDWYN MS TIPPAH\n420046 SYMMETRY/TGP RIPLEY MS TIPPAH\n420429 BOONEVIL/TGP BOONEVILLE MS TIPPAH\n420855 CORINTH/TGP CORINTH  3 ALCORN\n420483 CORINTH/TGP CORINTH MS 2 ALCORN\n420705 CORINTH/TGP NORTH CORINTH MS ALCORN\n420058 AMMID AT/TGP CORINTH MS ALCORN\n420802 KIMBERLY/TGP KIMBERLY CLARK SMS ALC",null,null,null,null,null,null,null,null,null,"X20-963853",0,0,0,0,0,0,0,0]
["X19-1005969","***","2020-11-11","2020-11-12","Completed",null,null,"Sta. 856","800","1","Annual ESD test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X19-1005969",1,0,0,0,0,0,0,0]
["X20-877885",null,"2020-12-01","2020-12-22",null,null,null,"MLV 857-1 to MLV 859-1","800","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-877885",0,0,0,0,0,0,0,0]
["X20-939915",null,"2020-02-10","2020-11-30",null,null,null,"Sta 860: Unit 5A","800","1","Crankcase Replacement & Regrout","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-939915",0,0,0,0,0,0,0,0]
["X20-963854",null,"2021-04-05","2021-04-13",null,null,null,"MLV 866-1 to MLV 860-1","800","1","Pig Run - Cleaning / Gauge 4/6/21, MFL 4/8/21, Hardspot 4/13/21","This activity will require operating at controlled flow rates. The meter listed may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.","420210 VAR/TGP WRIGLEY TENNESSEE HICKMAN",null,null,null,null,null,null,null,null,null,"X20-963854",0,0,0,0,0,0,0,0]
["X20-1015652",null,"2020-11-16","2020-12-07",null,null,null,"Sta 871A","800","2","Unit 2A Power Cylinder Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-1015652",0,0,0,0,0,0,0,0]

{"sheet":"Sheet2","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}

{"sheet":"Sheet3","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}