{"text_format":"1","workbook":"xlsx","n_sheets":4,"sheets":["Closed","Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":6,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Closed","index":0,"n_rows":37,"n_cols":22,"rows_kept":37,"cut":false,"hidden":true,"merged":[[1,3,1,15],[2,3,2,15],[3,3,3,15]]}
[null,null,null,"Updated ","2016"]
[null,null,null,"Tennessee Gas Pipeline 2015 Pipeline Outage and Maintenance Summary"]
[null,null,null,"This is a summary of the current status of all TGP Winter 2014-2015 Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  Additionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
[null,null,null,"*** Indicates revision"]
["Date Change","Project New/Completed/Closed","Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","Location","Leg","Zone","Maintenance Activity","Anticipated Impact","Potential Restriction Level","TOS Potential Restrictions","Meter(s) in Impacted Area","Customer Notifications","Loc","Email Text","Posting Text","Completion Text"]
[{"$f":"IF(AND(H6<>\"\",I6<>\"\"), \"Date change. Previously scheduled \" & TEXT(H6,\"m/d/y;@\") &IF(H6=I6,\"\",\" to \" & TEXT(I6,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed",null,{"$f":"IF(G6<>\"\",\"***\",\"\")","v":"***"},"2015-01-11","2016-01-11",{"$f":"IF(AND(A6=\"\",B6=\"\"),\"\",IF(B6=\"\",A6,B6))","v":"Project Completed"},null,null,"MS #412494 DCP Warren","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412494 DCP Warren",401,{"$f":"\"(\"&C6&\") \"&J6&\":  \"&M6&IF(AND(E6=\"\",F6=\"\"),\"\",\" (\")&IF(E6=\"\",\"\",\"\"&TEXT(E6,\"m/d/y;@\"))&IF(OR(F6=E6,E6=\"\",F6=\"\"),\"\",\" to \")&IF(OR(F6=\"\",F6=E6),\"\",TEXT(F6,\"m/d/y;@\"))&IF(AND(E6=\"\",F6=\"\"),\"\",\")\")","v":"() MS #412494 DCP Warren:  Meter Station (1/11/15 to 1/11/16)"},{"$f":"D6&J6&\":  \"&M6&IF(AND(E6=\"\",F6=\"\"),\"\",\"\n\")&IF(E6=\"\",\"\",\"--\"&TEXT(E6,\"m/d/y;@\"))&IF(OR(F6=E6,E6=\"\",F6=\"\"),\"\",\" through \")&IF(OR(F6=\"\",F6=E6),\"\",TEXT(F6,\"m/d/y;@\"))&IF(AND(E6=\"\",F6=\"\"),\"\",\":  \")&N6&\"  \"&P6&IF(Q6=\"\",\"\",\"\n\"&Q6)&IF(G6=\"\",\"\",\"\n***\")&G6&\"\n………………………………\"","v":"***MS #412494 DCP Warren:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412494 DCP Warren\n***Project Completed\n………………………………"},{"$f":"D6&J6&\":  \"&M6&IF(G6=\"\",\"\",\"\n***\")&G6&IF(Q6=\"\",\"\",\"\nThe following meters are available for nominations:\n\")&Q6&\"\n………………………………\"","v":"***MS #412494 DCP Warren:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412494 DCP Warren\n………………………………"}]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412400 King Ranch","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412400 King Ranch",402.1,"() MS #412400 King Ranch:  Meter Station (1/11/15 to 1/11/16)","***MS #412400 King Ranch:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412400 King Ranch\n***Project Completed\n………………………………","***MS #412400 King Ranch:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412400 King Ranch\n………………………………"]
["","Project Completed",null,"***","2015-01-12","2016-01-12","Project Completed",null,null,"MS #410539 Duvak Gas Gathering","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410539 Duvak Gas Gathering",402.1,"() MS #410539 Duvak Gas Gathering:  Meter Station (1/12/15 to 1/12/16)","***MS #410539 Duvak Gas Gathering:  Meter Station\n--1/12/15 through 1/12/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410539 Duvak Gas Gathering\n***Project Completed\n………………………………","***MS #410539 Duvak Gas Gathering:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n410539 Duvak Gas Gathering\n………………………………"]
["","Project Completed",null,"***","2015-01-13","2016-01-13","Project Completed",null,null,"MS #412356 DCP LaGloria","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412356 DCP LaGloria",403.1,"() MS #412356 DCP LaGloria:  Meter Station (1/13/15 to 1/13/16)","***MS #412356 DCP LaGloria:  Meter Station\n--1/13/15 through 1/13/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412356 DCP LaGloria\n***Project Completed\n………………………………","***MS #412356 DCP LaGloria:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412356 DCP LaGloria\n………………………………"]
["","Project Completed",null,"***","2015-01-13","2016-01-13","Project Completed",null,null,"MS #410173 Enterprise LaReforma","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410173 Enterprise LaReforma",406.1,"() MS #410173 Enterprise LaReforma:  Meter Station (1/13/15 to 1/13/16)","***MS #410173 Enterprise LaReforma:  Meter Station\n--1/13/15 through 1/13/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410173 Enterprise LaReforma\n***Project Completed\n………………………………","***MS #410173 Enterprise LaReforma:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n410173 Enterprise LaReforma\n………………………………"]
["","Project Completed",null,"***","2015-01-12","2016-01-12","Project Completed",null,null,"MS #411903 Enterprise El Benito","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","411903 Enterprise El Benito",407.1,"() MS #411903 Enterprise El Benito:  Meter Station (1/12/15 to 1/12/16)","***MS #411903 Enterprise El Benito:  Meter Station\n--1/12/15 through 1/12/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n411903 Enterprise El Benito\n***Project Completed\n………………………………","***MS #411903 Enterprise El Benito:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n411903 Enterprise El Benito\n………………………………"]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412088 Enterprise Sullivan","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412088 Enterprise Sullivan",407.1,"() MS #412088 Enterprise Sullivan:  Meter Station (1/11/15 to 1/11/16)","***MS #412088 Enterprise Sullivan:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412088 Enterprise Sullivan\n***Project Completed\n………………………………","***MS #412088 Enterprise Sullivan:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412088 Enterprise Sullivan\n………………………………"]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412683 HESCO","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412683 HESCO",408.1,"() MS #412683 HESCO:  Meter Station (1/11/15 to 1/11/16)","***MS #412683 HESCO:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412683 HESCO\n***Project Completed\n………………………………","***MS #412683 HESCO:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412683 HESCO\n………………………………"]
[{"$f":"IF(AND(H14<>\"\",I14<>\"\"), \"Date change. Previously scheduled \" & TEXT(H14,\"m/d/y;@\") &IF(H14=I14,\"\",\" to \" & TEXT(I14,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X16-36843",{"$f":"IF(G14<>\"\",\"***\",\"\")","v":"***"},"2016-01-27","2016-01-27","Project Completed",null,null,"Sta. 237",200,5,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,237,"(X16-36843) Sta. 237:  Unit  Maintenance (1/27/16)","***Sta. 237:  Unit  Maintenance\n--1/27/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Sta. 237:  Unit  Maintenance\n***Project Completed\n………………………………"]
[{"$f":"IF(AND(H15<>\"\",I15<>\"\"), \"Date change. Previously scheduled \" & TEXT(H15,\"m/d/y;@\") &IF(H15=I15,\"\",\" to \" & TEXT(I15,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X14-1478563",{"$f":"IF(G15<>\"\",\"***\",\"\")","v":"***"},"2015-11-16","2016-02-12","Project Completed",null,null,"MLV 32-1D to 33-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,32.200000000000003,"(X14-1478563) MLV 32-1D to 33-1:  Hydrotest (11/16/15 to 2/12/16)","***MLV 32-1D to 33-1:  Hydrotest\n--11/16/15 through 2/12/16:  This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***MLV 32-1D to 33-1:  Hydrotest\n***Project Completed\n………………………………"]
[null,"Project Completed","X16-16074",null,"2016-01-18","2016-01-28","Project Completed",null,null,"Station 550","500","1","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,550,"(X16-16074) Station 550:  Station Maintenance (1/18/16 to 1/28/16)","Station 550:  Station Maintenance\n--1/18/16 through 1/28/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","Station 550:  Station Maintenance\n***Project Completed\n………………………………"]
[{"$f":"IF(AND(H17<>\"\",I17<>\"\"), \"Date change. Previously scheduled \" & TEXT(H17,\"m/d/y;@\") &IF(H17=I17,\"\",\" to \" & TEXT(I17,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X16-46202",{"$f":"IF(G17<>\"\",\"***\",\"\")","v":"***"},"2016-02-01","2016-02-07","Project Completed",null,null,"Station 9","100","0","Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.",null,9,"(X16-46202) Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items) (2/1/16 to 2/7/16)","***Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)\n--2/1/16 through 2/7/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\n***Project Completed\n………………………………","***Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)\n***Project Completed\n………………………………"]
["","Project Completed","X15-925633","***","2016-02-09","2016-02-11","Project Completed",null,null,"Sta. 266A",200,6,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,266,"(X15-925633) Sta. 266A:  Unit  Maintenance (2/9/16 to 2/11/16)","***Sta. 266A:  Unit  Maintenance\n--2/9/16 through 2/11/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Sta. 266A:  Unit  Maintenance\n***Project Completed\n………………………………"]
["","Project Completed","X15-929733","***","2016-01-27","2016-02-10","Project Completed",null,null,"MLV 834-1 to 838-1",800,5,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",834.1,"(X15-929733) MLV 834-1 to 838-1:  ILI/Cleaning Pig (1/27/16 to 2/10/16)","***MLV 834-1 to 838-1:  ILI/Cleaning Pig\n--1/27/16 through 2/10/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 834-1 to 838-1:  ILI/Cleaning Pig\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X14-1562506","***","2015-11-02","2016-02-19","Project Completed",null,null,"MLV 5-1 to 6-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410063 ROCHE DEHYDRATION             \n",5.0999999999999996,"(X14-1562506) MLV 5-1 to 6-1:  Hydrotest (11/2/15 to 2/19/16)","***MLV 5-1 to 6-1:  Hydrotest\n--11/2/15 through 2/19/16:  This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410063 ROCHE DEHYDRATION             \n\n***Project Completed\n………………………………","***MLV 5-1 to 6-1:  Hydrotest\n***Project Completed\nThe following meters are available for nominations:\n410063 ROCHE DEHYDRATION             \n\n………………………………"]
["","Project Completed","X14-1562506","***","2015-11-02","2016-02-19","Project Completed",null,null,"MLV 7-1 to 9-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","\n412490 Charro\n421083 Eagle Ford Field Service",5.0999999999999996,"(X14-1562506) MLV 7-1 to 9-1:  Hydrotest (11/2/15 to 2/19/16)","***MLV 7-1 to 9-1:  Hydrotest\n--11/2/15 through 2/19/16:  This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n\n412490 Charro\n421083 Eagle Ford Field Service\n***Project Completed\n………………………………","***MLV 7-1 to 9-1:  Hydrotest\n***Project Completed\nThe following meters are available for nominations:\n\n412490 Charro\n421083 Eagle Ford Field Service\n………………………………"]
["Date change. Previously scheduled 2/18/16 to 2/20/16.","Project Completed","X15-882289","***","2016-02-22","2016-02-24","Project Completed","2016-02-18","2016-02-20","MLV 24-2 to 25-2S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.2,"(X15-882289) MLV 24-2 to 25-2S:  Anomaly Remediation (2/22/16 to 2/24/16)","***MLV 24-2 to 25-2S:  Anomaly Remediation\n--2/22/16 through 2/24/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 24-2 to 25-2S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-925630","***","2016-02-23","2016-02-23","Project Completed",null,null,"WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B)",200,"L","ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,265.10000000000002,"(X15-925630) WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig (2/23/16)","***WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig\n--2/23/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig\n***Project Completed\n………………………………"]
["","Project Completed","X16-23748","***","2016-02-15","2016-02-18","Project Completed",null,null,"MLV 530-3 to 532-3",500,"L","ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,530.29999999999995,"(X16-23748) MLV 530-3 to 532-3:  ILI/Cleaning Pig (2/15/16 to 2/18/16)","***MLV 530-3 to 532-3:  ILI/Cleaning Pig\n--2/15/16 through 2/18/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***MLV 530-3 to 532-3:  ILI/Cleaning Pig\n***Project Completed\n………………………………"]
["","Project Canceled","X16-98720","***","2016-03-06","2016-03-06","Project Canceled",null,null,"Sta. 1",100,0,"Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,1,"(X16-98720) Sta. 1:  Station Maintenance (3/6/16)","***Sta. 1:  Station Maintenance\n--3/6/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Canceled\n………………………………","***Sta. 1:  Station Maintenance\n***Project Canceled\n………………………………"]
["","Project Completed","X14-1562513\nX14-1540661","***","2015-07-01","2016-03-04","Project Completed",null,null,"Station 32","100","0","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,32,"(X14-1562513\nX14-1540661) Station 32:  Station Maintenance (7/1/15 to 3/4/16)","***Station 32:  Station Maintenance\n--7/1/15 through 3/4/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Station 32:  Station Maintenance\n***Project Completed\n………………………………"]
["","Project Canceled","X15-926822","***","2016-06-06","2016-06-11","Project Canceled",null,null,"BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1)",300,6,"Pipe Inspection","This project involves inspecting multiple sites.  We do not anticipate having to do any repairs, however if a repair is needed  there is a potential that the pipe  may require replacement which will require isolation of the pipe.  This may limit throughput and will result in restrictions based on customer nominations.  Customers may experience pressure fluctuations during this timeframe.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",343.1,"(X15-926822) BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection (6/6/16 to 6/11/16)","***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection\n--6/6/16 through 6/11/16:  This project involves inspecting multiple sites.  We do not anticipate having to do any repairs, however if a repair is needed  there is a potential that the pipe  may require replacement which will require isolation of the pipe.  This may limit throughput and will result in restrictions based on customer nominations.  Customers may experience pressure fluctuations during this timeframe.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928271","***","TBD","TBD","Project Canceled",null,null,"MLV 555-1 to 550-1",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.1,"(X15-928271) MLV 555-1 to 550-1:  ILI/Cleaning Pig (TBD)","***MLV 555-1 to 550-1:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-1 to 550-1:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928272","***","TBD","TBD","Project Canceled",null,null,"MLV 555-2 to 550-2",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.20000000000005,"(X15-928272) MLV 555-2 to 550-2:  ILI/Cleaning Pig (TBD)","***MLV 555-2 to 550-2:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-2 to 550-2:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928273","***","TBD","TBD","Project Canceled",null,null,"MLV 555-3 to 552-3",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.29999999999995,"(X15-928273) MLV 555-3 to 552-3:  ILI/Cleaning Pig (TBD)","***MLV 555-3 to 552-3:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-3 to 552-3:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-882281","***","2016-02-24","2016-03-03","Project Completed",null,null,"24-1A to 25-1S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.1,"(X15-882281) 24-1A to 25-1S:  Anomaly Remediation (2/24/16 to 3/3/16)","***24-1A to 25-1S:  Anomaly Remediation\n--2/24/16 through 3/3/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***24-1A to 25-1S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-882291","***","2016-03-03","2016-03-04","Project Completed",null,null,"MLV 24-3 to 25-3S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.3,"(X15-882291) MLV 24-3 to 25-3S:  Anomaly Remediation (3/3/16 to 3/4/16)","***MLV 24-3 to 25-3S:  Anomaly Remediation\n--3/3/16 through 3/4/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 24-3 to 25-3S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X14-1178175","***","2015-06-15","2016-03-31","Project Completed",null,null,"Station 63","100","1","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,63,"(X14-1178175) Station 63:  Station Maintenance (6/15/15 to 3/31/16)","***Station 63:  Station Maintenance\n--6/15/15 through 3/31/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Station 63:  Station Maintenance\n***Project Completed\n………………………………"]
["","Project Cancelled","X15-913224","***","2016-04-16","2016-05-21","Project Cancelled",null,null,"MLV 109-2",100,2,"Pipe Replacement","This project will require taking the pipeline section out of service.   This will limit throughput and will result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",109.2,"(X15-913224) MLV 109-2:  Pipe Replacement (4/16/16 to 5/21/16)","***MLV 109-2:  Pipe Replacement\n--4/16/16 through 5/21/16:  This project will require taking the pipeline section out of service.   This will limit throughput and will result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Cancelled\n………………………………","***MLV 109-2:  Pipe Replacement\n***Project Cancelled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-926830","***","2016-03-07","2016-03-11","Project Completed",null,null,"MLV 400-1 to 408-1",100,0,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.","To Be Determined",400.1,"(X15-926830) MLV 400-1 to 408-1:  ILI/Cleaning Pig (3/7/16 to 3/11/16)","***MLV 400-1 to 408-1:  ILI/Cleaning Pig\n--3/7/16 through 3/11/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 400-1 to 408-1:  ILI/Cleaning Pig\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Cancelled","X16-143836","***","2016-03-28","2016-04-04","Project Cancelled",null,null,"Sta. 409",100,0,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.",null,409,"(X16-143836) Sta. 409:  Unit  Maintenance (3/28/16 to 4/4/16)","***Sta. 409:  Unit  Maintenance\n--3/28/16 through 4/4/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\n***Project Cancelled\n………………………………","***Sta. 409:  Unit  Maintenance\n***Project Cancelled\n………………………………"]
["","Project Cancelled","X15-929680","***","2016-04-18","2016-04-27","Project Cancelled",null,null,"SABINE - KINDER LINE to 822-1",800,"L","Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",822.1,"(X15-929680) SABINE - KINDER LINE to 822-1:  Anomaly Remediation (4/18/16 to 4/27/16)","***SABINE - KINDER LINE to 822-1:  Anomaly Remediation\n--4/18/16 through 4/27/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Cancelled\n………………………………","***SABINE - KINDER LINE to 822-1:  Anomaly Remediation\n***Project Cancelled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]

{"sheet":"Sheet1","index":1,"n_rows":170,"n_cols":33,"rows_kept":170,"cut":false,"hidden":false,"merged":[[2,0,2,14]]}
["Updated ","2021-02-25"]
["Tennessee Gas Pipeline 2021 Pipeline Outage and Maintenance Summary"]
["This is a summary of the current status of all TGP 2021 Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  \nAdditionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
["*** Indicates revision"]
["Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","Location","Leg","Zone","Maintenance Activity","Anticipated Impact","Potential Restriction Level","TOS Potential Restrictions","Meter(s) in Impacted Area",null,null,null,null,null,null,null,null,null,"\\\\houCORP\\TRANS\\TRANSERVICES\\OPPLAN\\COMMON\\Outages\\Outage_DB\\TGP\\Files"]
["X19-761902",null,"2022-02-14","2022-02-25",null,null,null,"MLV 5-2 to MLV 4-2","100","0","Pipe Replacement","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X19-761902",0,0,0,0,0,0,0,0]
["X21-35982",null,"2021-06-01","2021-07-01",null,null,null,"MLV 4-1 to MLV 5-1","100","0","Pressure Weld Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-35982",0,0,0,0,0,0,0,0]
["X21-22691",null,"2021-02-08","2021-04-30",null,null,null,"MLV 5-2 to MLV 7-2","100","0","Spike Test","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-22691",0,0,0,0,0,0,0,0]
["X20-1085778",null,"2020-11-23","2021-05-23",null,null,null,"MLV 8-2 to MLV 9-2","100","0","High Priority Anomaly","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-1085778",0,0,0,0,0,0,0,0]
["X21-35981",null,"2021-06-01","2021-07-01",null,null,null,"MLV 12-1 to MLV 13-1","100","0","Pressure Weld Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-35981",0,0,0,0,0,0,0,0]
["X21-44519",null,"2021-04-07","2021-04-13",null,null,null,"MLV 17-1-1S to MLV 9-1D","100","0","Pig Run - Cleaning 4/7 - 4/9, Gauge 4/9, Combo 4/13","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-44519",0,0,0,0,0,0,0,0]
["X21-22677","***","2021-02-22","2021-06-01","Project Change","2/15/21","6/01/21","MLV 25-1to MLV 27-1A","100","0","Pressure Weld Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SIP","Potential in the path restrictions may be at risk.","412862 SOCOASTP/TGP COLDSPRING LATERAL: RI",null,null,null,null,null,null,null,null,null,"X21-22677",0,1,0,0,0,0,0,0]
["X21-67835",null,"2021-06-01","2021-06-30",null,null,null,"MLV 25-2 to MLV 26-2","100","0","Pressure Weld Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-67835",0,0,0,0,0,0,0,0]
["X21-67836",null,"2021-07-01","2021-07-31",null,null,null,"MLV 25-3 to MLV 26-3","100","0","Pressure Weld Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-67836",0,0,0,0,0,0,0,0]
["X20-835661",null,"2021-04-13","2021-04-13",null,null,null,"MLV 40-2 to MLV 32-2","100","0","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.","No meters affected on this maintenance pig run.",null,null,null,null,null,null,null,null,null,"X20-835661",0,0,0,0,0,0,0,0]
["X21-27120","***","2021-01-19","2021-05-17","Project Change","1/19/21","5/04/21","MLV 40-1D to MLV 47-1S","100","0","Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.   The meter listed below will be shut-in during the project.","SIP","Potential in the path restrictions may be at risk.","412809 CRTXLIG/TGP CLEAR LAKE NO. 1: RIP 4",null,null,null,null,null,null,null,null,null,"X21-27120",0,0,1,0,0,0,0,0]
["X21-44561",null,"2021-10-27","2021-11-04",null,null,null,"MLV 40-2S to MLV 32-2D","100","0","Cleaning 10/27 - 10/29, Gauge 10/29, DEF 11/2, MDS 11/4","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-44561",0,0,0,0,0,0,0,0]
["X21-44682","***","2021-02-10","2021-04-16","Project Change","2/08/21","3/24/21","MLV 40-3S to MLV 32-3D","100","0","Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-44682",0,1,1,0,0,0,0,0]
["X21-55858",null,"2021-10-12","2021-10-14",null,null,null,"MLV 40-3D TO MLV 47-3S","100","1","PIG Run - Cleaning 10/12, Gauge 10/13, MDS 10/14","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-55858",0,0,0,0,0,0,0,0]
["X21-67838",null,"2021-04-20","2021-04-26",null,null,null,"Bear Creek Storage","100","1","Shut-in Test","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","460017 STORAGE – BEAR CREEK",null,null,null,null,null,null,null,null,null,"X21-67838",0,0,0,0,0,0,0,0]
["X21-67839",null,"2021-10-19","2021-10-25",null,null,null,"Bear Creek Storage","100","1","Shut-in Test","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","460017 STORAGE – BEAR CREEK",null,null,null,null,null,null,null,null,null,"X21-67839",0,0,0,0,0,0,0,0]
["X20-1050025",null,"2021-02-01","2021-03-15",null,null,null,"MLV 46-4A to MLV 47-4A","100","1","Pressure Test","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-1050025",0,0,0,0,0,0,0,0]
["X21-131158",null,"2021-09-13","2021-09-18",null,null,null,"MLVS 47-3","100","1","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-131158",0,0,0,0,0,0,0,0]
["X21-31969",null,"2021-03-01","2021-03-31",null,null,null,"MLV 47-4B to MLV 47-4A","100","1","Pressure Test","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-31969",0,0,0,0,0,0,0,0]
["X20-1050028",null,"2021-07-05","2021-08-20",null,null,null,"MLV 53-4 to MLV 53-4B","100","1","Pressure Test","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-1050028",0,0,0,0,0,0,0,0]
["X21-126288",null,"2021-08-02","2021-08-13",null,null,null,"MLV 47-4D to MLV 48-4","100","1","High Priority Anomaly Digs","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-126288",0,0,0,0,0,0,0,0]
["X20-963839",null,"2021-04-20","2021-04-27",null,null,null,"MLV 63-1S to MLV 54-1D","100","1","Pig Run - Cleaning / Gauge 4/20/21, MFL 4/22/21, Hardspot 4/27/21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-963839",0,0,0,0,0,0,0,0]
["X21-55862",null,"2021-08-10","2021-08-12",null,null,null,"MLV 54-1 to 63-1","100","1","Pig Run - Cleaning Gauge 8/10, AFD 8/12","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-55862",0,0,0,0,0,0,0,0]
["X20-963844",null,"2021-03-16","2021-03-23",null,null,null,"MLV 63-4S to MLV 54-4D","100","1","Pig Run - Cleaning / Gauge 3/16/21, MFL 3/18/21, Hardspot 3/23/21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-963844",0,0,0,0,0,0,0,0]
["X20-963850",null,"2021-03-02","2021-03-09",null,null,null,"MLV 71-3S to MLV 63-3D","100","1","Pig Run - Cleaning / Gauge 3/2/21, MFL 3/4/21, Hardspot 3/9/21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-963850",0,0,0,0,0,0,0,0]
["X21-78592",null,"2021-09-07","2021-09-09",null,null,null,"MLV 63-3 to MLV 54-3","100","1","Cleaning & DEF 9/7/21, MDS 9/9/21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-78592",0,0,0,0,0,0,0,0]
["X21-36083",null,"2021-03-01","2021-04-03",null,null,null,"MLV 63-4D to MLV 71-4S","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-36083",0,0,0,0,0,0,0,0]
["X21-171530","***","2021-05-18","2021-05-19","Added",null,null,"Station 71","100","1","Annual ESD test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-171530",1,0,0,0,0,0,0,0]
["X21-113731",null,"2021-07-19","2021-07-25",null,null,null,"MLV 71-1D TO MLV 72-1","100","1","Drip Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-113731",0,0,0,0,0,0,0,0]
["X20-957254",null,"2021-05-18","2021-05-18",null,null,null,"Station 79","100","1","Annual ESD test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-957254",0,0,0,0,0,0,0,0]
["X21-63150",null,"2021-03-17","2021-03-25",null,null,null,"MLV 79-2D TO MLV 82-2","100","1","Pig Runs - Cleaning/Gauge 3/17/21, EMAT 3/25/21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-63150",0,0,0,0,0,0,0,0]
["X21-63146",null,"2021-08-17","2021-08-19",null,null,null,"MLV 79-2D TO MLV 82-2","100","1","Pig Runs - AFD 8/17/21, EMAT 8/19/21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-63146",0,0,0,0,0,0,0,0]
["X21-63152",null,"2021-05-06","2021-05-11",null,null,null,"MLV 79-3D TO MLV 82-3","100","1","Pig Runs - Cleaning/Gauge 5/6/21, EMAT 5/11/21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-63152",0,0,0,0,0,0,0,0]
["X21-63157",null,"2021-04-29","2021-05-04",null,null,null,"MLV 79-4D TO MLV 82-4","100","1","Pig Runs - Cleaning/Gauge 4/29/21, EMAT 5/4/21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-63157",0,0,0,0,0,0,0,0]
["X21-63167",null,"2021-08-12","2021-08-26",null,null,null,"MLV 82-1C TO MLV 87-1S","100","1","Pig Runs - Cleaning/Gauge 8/12/21, Caliper 8/24/21, EMAT 8/26/21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-63167",0,0,0,0,0,0,0,0]
["X21-63169",null,"2021-05-26","2021-05-26",null,null,null,"MLV 82-2C TO MLV 87-2S","100","1","Pig Runs - Caliper 5/26/21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-63169",0,0,0,0,0,0,0,0]
["X21-63163",null,"2021-04-12","2021-04-13",null,null,null,"MLV 82-3 TO MLV 82-3C","100","1","Pig Runs - Cleaning/Gauge 4/12/21, EMAT 4/13/21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-63163",0,0,0,0,0,0,0,0]
["X21-63164",null,"2021-04-14","2021-04-15",null,null,null,"MLV 82-4 TO MLV 82-4C","100","1","Pig Runs - Cleaning/Gauge 4/14/21, EMAT 4/15/21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-63164",0,0,0,0,0,0,0,0]
["X21-63165",null,"2021-04-20","2021-04-27",null,null,null,"MLV 82-4C TO MLV 87-4S","100","1","Pig Runs - Cleaning/Gauge 4/20/21, EMAT 4/22/21, Hardspot 4/27/21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-63165",0,0,0,0,0,0,0,0]
["X20-957255",null,"2021-08-11","2021-08-11",null,null,null,"Station 87","100","2","Annual ESD test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-957255",0,0,0,0,0,0,0,0]
["X21-161554","***","2021-03-08","2021-03-19","Added",null,null,"Sta 87: Unit 1D","100","2","Power Cylinder and Compressor Packing","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-161554",1,0,0,0,0,0,0,0]
["X21-161553","***","2021-03-02","2021-03-04","Added",null,null,"Sta 87: Unit 1E","100","2","AMOT Device","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-161553",1,0,0,0,0,0,0,0]
["X21-131161","***","2021-02-15","2021-02-20","Completed",null,null,"Sta 87: Unit 2E","100","2","Replace Broken Exhaust Bolts and Bellows","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-131161",1,0,0,0,0,0,0,0]
["X21-63161",null,"2021-03-16","2021-03-23",null,null,null,"MLV 82-2C TO MLV 87-2S","100","1","Pig Runs - Cleaning/Gauge 3/16/21, EMAT 3/23/21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-63161",0,0,0,0,0,0,0,0]
["X19-703248",null,"2019-08-01","2021-12-31",null,null,null,"MLV 106-1 to MLV 96-1","100","2","Pressure Restriction from ILI","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X19-703248",0,0,0,0,0,0,0,0]
["X21-31692",null,"2021-02-15","2021-06-17",null,null,null,"MLV 103-1 and MLV 105-1","100","2","Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-31692",0,0,0,0,0,0,0,0]
["X20-957260",null,"2021-04-26","2021-04-30",null,null,null,"Station 106","100","2","Annual ESD test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-957260",0,0,0,0,0,0,0,0]
["X21-29033",null,"2021-01-04","2021-03-01",null,null,null,"Sta 106: Unit 13B","100","2","Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-29033",0,0,0,0,0,0,0,0]
["X21-29038",null,"2021-03-02","2021-07-01",null,null,null,"Sta 106: Unit 14B","100","2","Re-Grout","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-29038",0,0,0,0,0,0,0,0]
["X21-31716","***","2021-02-15","2021-02-17","Completed",null,null,"Sta 106: Unit 1D","100","2","20k Hour Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-31716",1,0,0,0,0,0,0,0]
["X21-171296","***","2021-03-16","2021-03-17","Added",null,null,"Sta 106: Unit 2D","100","2","20k Hour Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-171296",1,0,0,0,0,0,0,0]
["X20-1105768",null,"2021-06-07","2021-08-24",null,null,null,"MLVS 109-3","100","2","Class Change / Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-1105768",0,0,0,0,0,0,0,0]
["X20-957261",null,"2021-06-14","2021-06-18",null,null,null,"Station 110","100","2","Annual ESD test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-957261",0,0,0,0,0,0,0,0]
["X21-63176",null,"2021-03-08","2021-03-29",null,null,null,"MLV 112-3 TO MLV 114-3","100","3","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-63176",0,0,0,0,0,0,0,0]
["X21-40299",null,"2021-06-09","2021-06-11",null,null,null,"Sta 114: Unit 1D","100","3","Turbine Service and Filter Change Out","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-40299",0,0,0,0,0,0,0,0]
["X21-40301",null,"2021-11-08","2021-11-10",null,null,null,"Sta 114: Unit 1D","100","3","Turbine Service and Filter Change Out","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-40301",0,0,0,0,0,0,0,0]
["X21-63143",null,"2021-04-05","2021-04-07",null,null,null,"MLV 117-2 TO MLV 114-2D","100","3","Pig Runs - Cleaning/Gauge 4/5/21, AFD 4/6/21, EMAT 4/7/21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-63143",0,0,0,0,0,0,0,0]
["X21-40275",null,"2021-04-19","2021-04-20",null,null,null,"Sta. 118A","100","3","Annual ESD test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-40275",0,0,0,0,0,0,0,0]
["X21-40271",null,"2021-04-21","2021-04-23",null,null,null,"Sta 118A: Unit 1A","100","3","Turbine Service and Filter Change Out","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-40271",0,0,0,0,0,0,0,0]
["X21-40272",null,"2021-10-04","2021-10-06",null,null,null,"Sta 118A: Unit 1A","100","3","Turbine Service and Filter Change Out","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-40272",0,0,0,0,0,0,0,0]
["X21-40296",null,"2021-05-17","2021-05-18",null,null,null,"Sta. 119A","100","3","Annual ESD test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-40296",0,0,0,0,0,0,0,0]
["X21-40289",null,"2021-05-19","2021-05-21",null,null,null,"Sta 119A: Unit 1A","100","3","Turbine Service and Filter Change Out","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-40289",0,0,0,0,0,0,0,0]
["X21-40293",null,"2021-11-01","2021-11-03",null,null,null,"Sta 119A: Unit 1A","100","3","Turbine Service and Filter Change Out","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-40293",0,0,0,0,0,0,0,0]
["X20-957282",null,"2021-06-08","2021-06-09",null,null,null,"Station 200","200","4","Annual ESD test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-957282",0,0,0,0,0,0,0,0]
["X21-113820",null,"2021-03-29","2021-04-01",null,null,null,"Sta 200: Unit 1A","200","4","Turbo Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-113820",0,0,0,0,0,0,0,0]
["X21-28989",null,"2021-02-22","2021-03-19",null,null,null,"Sta 200: Unit 4A","200","4","Reline Compressors","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-28989",0,0,0,0,0,0,0,0]
["X20-957285","***","2021-05-17","2021-05-21","Added",null,null,"Station 204","200","4","Annual ESD test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-957285",1,0,0,0,0,0,0,0]
["X21-40469",null,"2021-03-08","2021-03-11",null,null,null,"Sta 204: Unit 3A","200","4","Piston Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-40469",0,0,0,0,0,0,0,0]
["X21-40467",null,"2021-02-01","2021-03-04",null,null,null,"Sta 204: Unit 6A","200","4","Replace Gaskets & Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-40467",0,0,0,0,0,0,0,0]
["X21-40499",null,"2021-03-15","2021-03-25",null,null,null,"Sta 204: Unit 10A","200","4","Exhaust System & Gasket Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-40499",0,0,0,0,0,0,0,0]
["X20-957290","***","2021-05-24","2021-05-28","Added",null,null,"Station 209","200","4","Annual ESD test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-957290",1,0,0,0,0,0,0,0]
["X20-942967","***","2021-03-01","2021-03-05","Completed",null,null,"Sta 209: Unit 6A","200","4","Catwalk Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-942967",1,0,0,0,0,0,0,0]
["X21-161572","***","2021-03-08","2021-03-09","Added",null,null,"Sta 209: Unit 7A","200","4","500 hr Foundation Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-161572",1,0,0,0,0,0,0,0]
["X20-942968","***","2021-02-22","2021-03-12","Project Change","2/08/21","2/25/21","Sta 209: Unit 9A","200","4","Catwalk Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-942968",0,1,1,0,0,0,0,0]
["X21-118105","***","2021-03-10","2021-07-09","Project Change","3/08/21","7/09/21","Sta 209: Unit 10A","200","4","Full Foundation Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-118105",0,1,0,0,0,0,0,0]
["X21-31986",null,"2021-06-09","2021-07-08",null,null,null,"MLVS 213-1","200","4","Class Change","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-31986",0,0,0,0,0,0,0,0]
["X21-31987",null,"2021-07-09","2021-08-08",null,null,null,"MLVS 213-4","200","4","Class Change","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-31987",0,0,0,0,0,0,0,0]
["X20-1085756","***","2021-03-03","2021-03-04","Project Change","3/02/21","3/03/21","MLV 217A-101 to MLV 217A-104","200","4","Pig Run - Cleaning / Gauge 3/3/21,  AFD 3/4/21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed may experience flow limitations.","SOP","Potential out of path restrictions may be at risk.","412863 GEOPETRO/TGP LITTLE BEAVER: RIP 217\n420306 COL GAS/TGP PITTSBURGH TERMINAL PA\n450351 TGP/TGP PITTSBURGH TERMINAL PA (COL\n420199 PEOPLES/TGP PITTSBURGH TERMINAL PA\n420078 EQUITRNS/TGP PITTSBURGH TERMINAL PA\n420385 PEPLGAS/TGP PITTSBURG TERMINAL PA A\n420063 COL GAS/TGP UNIONVILLE PA BEAVER\n421075 LINDYPAV/TGP BIG BEAVER: DIP 217A 1\n48939 GENON EM/TGP MT JACKSON SALES LAWRE",null,null,null,null,null,null,null,null,null,"X20-1085756",0,1,1,1,0,0,0,0]
["X21-135972","***","2021-07-19","2021-08-13","Added",null,null,"MLVS 236-1","200","5","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","412856 EMPIREPL/TGP CANANDAIGUA ONTARIO\n420617 DOMINION/TGP HOPEWELL SALES ONTARIO",null,null,null,null,null,null,null,null,null,"X21-135972",1,0,0,0,0,0,0,0]
["X21-36191",null,"2021-05-24","2021-06-02",null,null,null,"MLV 237-2 to MLV 245-2","200","5","Cleaning, Gage, Combo","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-36191",0,0,0,0,0,0,0,0]
["X21-78604",null,"2021-02-28","2021-03-05",null,null,null,"Sta 241: Unit 1B","200","5","Replace Chocks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-78604",0,0,0,0,0,0,0,0]
["X20-957310","***","2021-05-03","2021-05-07","Added",null,null,"Station 245","200","5","Annual ESD test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-957310",1,0,0,0,0,0,0,0]
["X21-78644",null,"2021-04-05","2021-05-08",null,null,null,"Sta 245: Unit 2B","200","5","50k Hr Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-78644",0,0,0,0,0,0,0,0]
["X21-36192","***","2021-05-24","2021-06-04","Project Change","6/21/21","7/02/21","MLV 245-1 to MLV 249-1","200","5","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-36192",0,1,1,0,0,0,0,0]
["X21-36195","***","2021-05-31","2021-06-19","Project Change","6/28/21","7/16/21","MLV 246 Crossover","200","5","ECDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-36195",0,1,1,0,0,0,0,0]
["X21-36188",null,"2021-04-20","2021-04-21",null,null,null,"MLV 249-1 to MLV 254-1","200","5","Cleaning, Gage, Combo","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-36188",0,0,0,0,0,0,0,0]
["X20-957314",null,"2021-05-24","2021-05-24",null,null,null,"Station 254","200","5","Annual ESD test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-957314",0,0,0,0,0,0,0,0]
["X21-78621",null,"2021-05-24","2021-06-04",null,null,null,"Sta 254: Unit 2B","200","5","Turbine Exchange","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-78621",0,0,0,0,0,0,0,0]
["X20-1105640","***","2021-06-07","2021-06-19","Completed",null,null,"MLV 254-2 to MLV 261-2","200","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-1105640",1,0,0,0,0,0,0,0]
["X21-161544","***","2021-04-23","2021-04-25","Added",null,null,"Sta 261: Unit 4A","200","6","Protective Relay","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-161544",1,0,0,0,0,0,0,0]
["X19-653349",null,"2021-04-19","2021-08-30",null,null,null,"Sta 261: Unit Replacement","200","6","Isolate systems from 1D (air compressor, generator, fuel gas, et al)","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X19-653349",0,0,0,0,0,0,0,0]
["X20-1031954",null,"2021-04-03","2021-04-19",null,null,null,"Sta. 265E","200","6","Spring Shutdown","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-1031954",0,0,0,0,0,0,0,0]
["X20-469001",null,"2021-04-03","2021-04-19",null,null,null,"Sta 265E","200","6","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-469001",0,0,0,0,0,0,0,0]
["X21-42702",null,"2021-04-05","2021-04-23",null,null,null,"MLVS 265E-100","200","6","Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-42702",0,0,0,0,0,0,0,0]
["X20-1034818",null,"2021-10-16","2021-10-23",null,null,null,"Sta. 265E","200","6","Fall Outage","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-1034818",0,0,0,0,0,0,0,0]
["X20-1031952",null,"2022-04-02","2022-04-18",null,null,null,"Sta 265: Unit 1A","200","6","Controls Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-1031952",0,0,0,0,0,0,0,0]
["X20-1105637",null,"2021-06-01","2021-06-05",null,null,null,"MLVS 256C-101","200","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-1105637",0,0,0,0,0,0,0,0]
["X20-1105628",null,"2021-04-05","2021-04-23",null,null,null,"MLV 265E-101 to MLV 265E-105","200","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420750 NARNGST/TGP CRANSTON SALES PROVIDEN\n420926 RISEC/TGP FPLE RISE PROVIDENCE",null,null,null,null,null,null,null,null,null,"X20-1105628",0,0,0,0,0,0,0,0]
["X20-1105603",null,"2021-06-15","2021-06-16",null,null,null,"266C-100 Blackstone Lateral No 2","200","6","Pig run: 6/15/21 Cleaning/Gauge, 6/16/21 AFD","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-1105603",0,0,0,0,0,0,0,0]
["X21-161606","***","2021-05-03","2021-05-14","Added",null,null,"Sta 267","200","6","Repair Unit Valves","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-161606",1,0,0,0,0,0,0,0]
["X20-1105605",null,"2021-06-08","2021-06-09",null,null,null,"MLV 270B-101 to MLV 270B-103","200","6","Pig run: 6/8/21 Cleaning/Gauge, 6/9/21 AFD","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-1105605",0,0,0,0,0,0,0,0]
["X20-1105622",null,"2021-07-27","2021-07-28",null,null,null,"270B-300 Haverhill Lateral","200","6","Pig run: 7/27/21 Cleaning/Gauge, 7/28/21 AFD","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-1105622",0,0,0,0,0,0,0,0]
["X20-1105583",null,"2021-03-25","2021-03-25",null,null,null,"270B-400 Lawrence Delivery","200","6","Pig run: 3/25/21 Cleaning/Gauge, 3/25/21 AFD","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-1105583",0,0,0,0,0,0,0,0]
["X20-1111632",null,"2021-03-22","2021-03-23",null,null,null,"270C-500 GLOUCESTER DELIVERY LINE","200","6","Pig Run: 3/22/21 Cleaning / Gauge, 3/23/21 AFD","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-1111632",0,0,0,0,0,0,0,0]
["X19-829634",null,"2021-02-15","2021-06-10",null,null,null,"Sta 307: Unit 3A","300","4","Foundation Replacement","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X19-829634",0,0,0,0,0,0,0,0]
["X21-67804","***","2021-02-08","2021-02-11","Completed",null,null,"Sta 307 Unit 4A","300","4","Replace broken jug stud","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential in the path restrictions during the maintenance overlap.",null,null,null,null,null,null,null,null,null,null,"X21-67804",1,0,0,0,0,0,0,0]
["X19-144300",null,"2021-05-01","2021-09-15",null,null,null,"Sta 307: Unit 5A","300","4","Install Fuel Injection System and Fuel Gas Skid","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential in the path restrictions during the maintenance overlap.",null,null,null,null,null,null,null,null,null,null,"X19-144300",0,0,0,0,0,0,0,0]
["X21-27057",null,"2021-02-01","2021-03-05",null,null,null,"Sta 313: Unit 1B","300","4","50k Hour Overhaul","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-27057",0,0,0,0,0,0,0,0]
["X21-78596","***","2021-02-22","2021-02-26","Project Change","2/15/21","2/19/21","Sta 313: Unit 2B","300","4","Repair Chocks","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-78596",0,1,1,0,0,0,0,0]
["X21-67841",null,"2021-04-12","2021-04-19",null,null,null,"Ellisburg Storage","300","4","Shut-in Test","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","460012 – DOMINION/TGP ELLISBURG INJECTION PO",null,null,null,null,null,null,null,null,null,"X21-67841",0,0,0,0,0,0,0,0]
["X21-67844",null,"2021-03-29","2021-04-05",null,null,null,"Harrison Storage","300","4","Shut-in Test","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","460004 – DOMINION/TGP HARRISON INJECTION POT",null,null,null,null,null,null,null,null,null,"X21-67844",0,0,0,0,0,0,0,0]
["X21-67847",null,"2021-04-12","2021-04-19",null,null,null,"Hebron Storage","300","4","Shut-in Test","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","400485 HEBRON STORAGE INJECTION POTTER\n470001 HEBRON STORAGE WITHDRAWAL POTTER",null,null,null,null,null,null,null,null,null,"X21-67847",0,0,0,0,0,0,0,0]
["X21-28982",null,"2021-05-31","2021-07-24",null,null,null,"Sta 321","300","4","Gas Cooler Installation","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-28982",0,0,0,0,0,0,0,0]
["X21-42714",null,"2021-05-24","2021-05-30",null,null,null,"MLV 325-2 to MLV 329-2","300","5","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-42714",0,0,0,0,0,0,0,0]
["X20-1105599",null,"2021-03-30","2021-03-30",null,null,null,"334A-100 Con Ed Delivery","300","6","Pig run: 3/30/21 Cleaning/Gauge, 3/30/21 Combo","This activity will require operating at controlled flow rates. The meter listed will have limited flow during the pig run.","SOP","Potential out of path restrictions may be at risk.","420093 CON ED/TGP WHITE PLAINS NY WESTCHES",null,null,null,null,null,null,null,null,null,"X20-1105599",0,0,0,0,0,0,0,0]
["X21-26872",null,"2021-05-01","2021-08-01",null,null,null,"MLV 334A","300","6","Meter Station Upgrade (White Plains MN 420093)","This project will require taking the meter station out of service. The meter listed will be shut in during the project.",null,null,"420093 CON ED/TGP WHITE PLAINS NY WESTCHES",null,null,null,null,null,null,null,null,null,"X21-26872",0,0,0,0,0,0,0,0]
["X20-1105623","***","2021-05-17","2021-06-08","Project Change","5/03/21","5/21/21","334A-100 Con Ed Delivery (Meter Station to EOL)","300","6","ILI tools with cable system","This activity will require operating at controlled flow rates. The meter listed will be shut in during the pig run.","SOP","Potential out of path restrictions may be at risk.","420093 CON ED/TGP WHITE PLAINS NY WESTCHES",null,null,null,null,null,null,null,null,null,"X20-1105623",0,1,1,0,0,0,0,0]
["X21-78471",null,"2021-07-15","2021-07-31",null,null,null,"MLVS 404-1","400 (So TX)","0","Class Change","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-78471",0,0,0,0,0,0,0,0]
["X21-78472",null,"2021-08-01","2021-08-15",null,null,null,"MLVS 404-2","400 (So TX)","0","Class Change","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-78472",0,0,0,0,0,0,0,0]
["X21-161622","***","2021-06-28","2021-07-10","Added",null,null,"Sta 409A","400 (So TX)","0","Protective Device Inspection","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-161622",1,0,0,0,0,0,0,0]
["X21-116101","***","2021-02-26","2021-02-26","Project Change","2/19/21","2/19/21","Sta 409A","400 (So TX)","0","Protective Device Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-116101",0,1,1,0,0,0,0,0]
["X21-67881",null,"2021-08-17","2021-08-22",null,null,null,"Sta 409: Unit 1A","400 (So TX)","0","25k Hr Inspection","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-67881",0,0,0,0,0,0,0,0]
["X21-67884",null,"2021-09-14","2021-09-19",null,null,null,"Sta 409: Unit 2A","400 (So TX)","0","25k Hr Inspection","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-67884",0,0,0,0,0,0,0,0]
["X21-116143",null,"2021-04-13","2021-04-14",null,null,null,"Sta 500C1: Unit 1A","500","L","Turbine Inspections","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-116143",0,0,0,0,0,0,0,0]
["X21-55857",null,"2021-06-08","2021-06-16",null,null,null,"MLV 500-1 TO MLV 507-1","500","L","Pig Run - Cleaning Gauge 6/8 - 6/9, Combo 6/10 - 6/11, Hard Spot 6/14, AFD 6/16","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420373 TRNSCO/TGP KINDER LA EXCH (BI 1\n420708 ELIZ NG/TGP GRANT LA SALES ALLEN\n420436 VERNON/TGP PITKIN LA VERNON\n420793 ELIZ NG/TGP J R FRANKS 1 VERNON\n420388 PROVNCAL/TGP PROVENCAL LA NATCHITOC",null,null,null,null,null,null,null,null,null,"X21-55857",0,0,0,0,0,0,0,0]
["X21-68040",null,"2021-06-07","2021-07-03",null,null,null,"MLVS 511-1","500","L","Class Change","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-68040",0,0,0,0,0,0,0,0]
["X21-27158",null,"2021-06-07","2021-06-13",null,null,null,"MLV 513-1 to MLV 514-1","500","L","Line Lowering & Tie In","This project will require taking the pipeline section out of service. The meter listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420915 SYMMETRY/TGP PORT IBERIA SALES IBER",null,null,null,null,null,null,null,null,null,"X21-27158",0,0,0,0,0,0,0,0]
["X21-171320","***","2021-06-07","2021-06-16","Added",null,null,"MLV 527-3 to MLV 529-2","500","L","Pig Runs - Cleaning 6/7 - 6/9, Gauge 6/9, MLF 6/10, Caliper 6/15, EMAT 6/16","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-171320",1,0,0,0,0,0,0,0]
["X21-171325","***","2021-07-07","2021-07-09","Added",null,null,"MLV 534-1 to MLV 535-1A","500","1","Pig Runs - Cleaning 7/7, Gauge 7/7, Caliper 7/8, MFL 7/9","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-171325",1,0,0,0,0,0,0,0]
["X21-69618","***","2021-06-21","2021-06-30","Added",null,null,"MLV 536-2 to MLV 537-2","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-69618",1,0,0,0,0,0,0,0]
["X21-25212","***","2021-03-15","2021-03-29","Project Change","3/01/21","3/21/21","MLV 538-1 to MLV 540-1","500","1","Valve Replacement & Trap Mod","This project will require taking the pipeline section out of service. The meter listed may be shut in during the project.","SIP","Potential in the path restrictions may be at risk.","412060 /TGP HEIDELBURG TRANSPORT JASPER",null,null,null,null,null,null,null,null,null,"X21-25212",0,1,1,0,0,0,0,0]
["X21-69621","***","2021-09-27","2021-10-13","Added",null,null,"MLV 538-2 to MLV 539-2","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412789 LEAF/TGP JASPER COUNTY: RIP 538 2 5\n412066 DCP OPER/TGP INEZ INTERCONNECT DEHY",null,null,null,null,null,null,null,null,null,"X21-69621",1,0,0,0,0,0,0,0]
["X21-25213","***","2021-03-29","2021-04-08","Project Change","3/15/21","4/02/21","MLV 539-1 to MLV 541-1","500","1","Install Valve","This project will require taking the pipeline section out of service. The meter listed may be shut in during the project.","SIP","Potential in the path restrictions may be at risk.","420807 ATMOS-MS/TGP PINE SPRINGS ROAD LEAK",null,null,null,null,null,null,null,null,null,"X21-25213",0,1,1,0,0,0,0,0]
["X21-25214","***","2021-04-08","2021-04-30","Project Change","4/05/21","5/14/21","MLV 540-1 to MLV 542-1","500","1","Install Valve","This project will require taking the pipeline section out of service. The meter listed may be shut in during the project.","SIP","Potential in the path restrictions may be at risk.","420807 ATMOS-MS/TGP PINE SPRINGS ROAD LEAK",null,null,null,null,null,null,null,null,null,"X21-25214",0,1,1,0,0,0,0,0]
["X21-25228",null,"2021-04-05","2021-06-05",null,null,null,"MLV 540-1A to MLV 541-1","500","1","Class Change","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-25228",0,0,0,0,0,0,0,0]
["X21-25225",null,"2021-06-07","2021-08-11",null,null,null,"MLV 540-2A to MLV 541-2","500","1","Class Change","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-25225",0,0,0,0,0,0,0,0]
["X21-69622","***","2021-10-14","2021-10-25","Added",null,null,"MLV 540-2 to MLV 541-2","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-69622",1,0,0,0,0,0,0,0]
["X21-171248","***","2021-02-24","2021-06-30","Added",null,null,"Sta 542: Unit 4A","500","1","Crankshaft Repair","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-171248",1,0,0,0,0,0,0,0]
["X21-171340","***","2021-09-06","2021-09-20","Added",null,null,"MLV 542-1 to MLV 538-1","500","1","Pig Runs - Chem Cleaning 9/6 - 9/14, Gauge 9/15, Caliper 9/16, MFL 9/20","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-171340",1,0,0,0,0,0,0,0]
["X21-25215","***","2021-05-13","2021-06-01","Project Change","5/17/21","5/31/21","MLV 542-2 to MLV 544-2","500","1","Valve & Drip Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-25215",0,1,1,0,0,0,0,0]
["X21-25221","***","2021-06-01","2021-06-15","Project Change","6/01/21","6/25/21","MLV 543-2 to MLV 545-2","500","1","Valve Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-25221",0,0,1,0,0,0,0,0]
["X21-173927","***","2021-02-24","TBD","Added",null,null,"Sta 546: Unit","500","1","Emergent Repair","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-173927",1,0,0,0,0,0,0,0]
["X21-161556","***","2021-03-15","2021-03-26","Added",null,null,"Sta 546: Unit 1B","500","1","Replace Controllers","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-161556",1,0,0,0,0,0,0,0]
["X21-171328","***","2021-07-20","2021-07-22","Added",null,null,"MLV 546-1 to MLV 542-1","500","1","Pig Runs - Cleaning 7/20, Gauge 7/21, MFL 7/22","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-171328",1,0,0,0,0,0,0,0]
["X21-171335","***","2021-07-28","2021-08-02","Added",null,null,"MLV 546-2 to MLV 542-2","500","1","Pig Runs - Cleaning 7/28, Gauge 7/29, Caliper 7/30, MFL 8/2","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-171335",1,0,0,0,0,0,0,0]
["X21-69623","***","2021-08-31","2021-09-24","Added",null,null,"MLV 546-2 to MLV 547-2","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-69623",1,0,0,0,0,0,0,0]
["X21-171339","***","2021-08-09","2021-08-11","Added",null,null,"MLV 546-3 to MLV 544-3","500","1","Pig Runs - Cleaning 8/9, Gauge 8/10, MFL 8/11","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-171339",1,0,0,0,0,0,0,0]
["X21-69624","***","2021-08-23","2021-08-30","Added",null,null,"MLV 547-2 to MLV 548-2","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412134 DUKE/TGP FAYETTE VERNON TRANSPORT L\n48033 BBTBAMA/TGP FAYETTE VERNON LAMAR",null,null,null,null,null,null,null,null,null,"X21-69624",1,0,0,0,0,0,0,0]
["X20-433287",null,"2020-05-11","2021-03-15",null,null,null,"Sta 550: Unit 3A","500","1","Regrout","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-433287",0,0,0,0,0,0,0,0]
["X21-59380",null,"2021-03-23","2021-03-25",null,null,null,"Sta 550: Unit 3A","500","1","Replace Ball Valves","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-59380",0,0,0,0,0,0,0,0]
["X20-1089825",null,"2021-03-29","2021-04-01",null,null,null,"Sta 555","500","1","Safety System Fiber Upgrade","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-1089825",0,0,0,0,0,0,0,0]
["X20-957355",null,"2021-05-05","2021-05-05",null,null,null,"Station 555","500","1","Annual ESD test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-957355",0,0,0,0,0,0,0,0]
["X21-116271",null,"2021-05-17","2021-07-03",null,null,null,"Sta 555: Unit 4A, 5A, 6A","500","1","Automation Upgrade","This project will require unit outages, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-116271",0,0,0,0,0,0,0,0]
["X20-1050037",null,"2021-09-02","2021-09-17",null,null,null,"MLV 560-2 to MLV 562-2","500","1","Pressure Test & New Valve Installation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-1050037",0,0,0,0,0,0,0,0]
["X21-144366","***","2021-08-31","2021-09-01","Project Change",null,null,"MLV 561-1 to MLV 562-1","500","2","Replace Crossover","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-144366",0,0,0,1,1,1,1,0]
["X21-126059",null,"2021-07-13","2021-07-14",null,null,null,"Sta 563","500","2","Annual ESD test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-126059",0,0,0,0,0,0,0,0]
["X20-1050040",null,"2021-09-02","2021-10-22",null,null,null,"MLV 563-2A to MLV 564-2BR","500","1","Pressure Test & New Valve Installation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-1050040",0,0,0,0,0,0,0,0]
["X21-131212",null,"2021-04-05","2021-04-09",null,null,null,"MLV821-1","800","L","HP Filter Separator Maintenance","This activity will require operating at controlled flow rates. The meter listed will be limited to 750,000 mmscf/d during the project.","SOP","Potential out of path restrictions may be at risk.","49446 CAM IPL/TGP BANKEN RD AT  HWY 27 DE",null,null,null,null,null,null,null,null,null,"X21-131212",0,0,0,0,0,0,0,0]
["X21-55855","***","2021-03-08","2021-03-10","Project Change",null,null,"MLV 823-1 to MLV 821-1","800","L","Pig Run - Cleaning 3/8, Gauge 3/9, Combo 3/10","Requires operating at controlled flow rates. Customers may experience pressure fluctuations.  Meter 49446 will be controlled. Meter 420581 will be shut-in as the pig passes, the rest of the meters will be shut-in for the duration of the pig run.","SOP","Potential out of path restrictions may be at risk.","420581 ENTRGYLA/TGP BECKWITH CREEK CALCASI\n49446 CAM IPL/TGP BANKEN RD AT  HWY 27 DE\n412768 GLDNPASS/TGP STARKS LNG: RIP 820 10\n412737 CAM IPL/TGP DEQUINCY GAS STORAGE C\n421050 LBERTYGS/TGP DE QUINCY GAS STORAGE\n420550 ENTERPRSE/TGP SABINE RIVERsoap\n412013 ENTRPRSE/TGP SABINE RIVER TRANS NEW\n412690 HPL/TGP SABINE NEWTON\n411586 TRNSCO/TGP STARKS LA TRANSPORT CALC",null,null,null,null,null,null,null,null,null,"X21-55855",0,0,0,1,0,0,0,0]
["X20-963853",null,"2021-02-22","2021-02-25",null,null,null,"MLV 851-1 to MLV 856-1","800","1","Pig Run - Cleaning / Gauge 2/22/21, Caliper 2/23/21, MFL 2/25/21","This activity will require operating at controlled flow rates. The meters listed may experience pressure fluctuations.  The meters listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420282 NEWALBNY/TGP COTTON PLANT MS UNION\n420276 BLDWYN/TGP BALDWYN MS TIPPAH\n420046 SYMMETRY/TGP RIPLEY MS TIPPAH\n420429 BOONEVIL/TGP BOONEVILLE MS TIPPAH\n420855 CORINTH/TGP CORINTH  3 ALCORN\n420483 CORINTH/TGP CORINTH MS 2 ALCORN\n420705 CORINTH/TGP NORTH CORINTH MS ALCORN\n420058 AMMID AT/TGP CORINTH MS ALCORN\n420802 KIMBERLY/TGP KIMBERLY CLARK SMS ALC",null,null,null,null,null,null,null,null,null,"X20-963853",0,0,0,0,0,0,0,0]
["X21-171531","***","2021-05-20","2021-05-21","Added",null,null,"Station 856","800","1","Annual ESD test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-171531",1,0,0,0,0,0,0,0]
["X20-939915",null,"2020-02-10","2021-02-26",null,null,null,"Sta 860: Unit 5A","800","1","Crankcase Replacement & Regrout","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-939915",0,0,0,0,0,0,0,0]
["X20-963854",null,"2021-03-25","2021-03-31",null,null,null,"MLV 866-1 to MLV 860-1","800","1","Pig Run - Cleaning 3/25/21, Caliper 3/29/21, MFL 3/31/21","This activity will require operating at controlled flow rates. The meter listed may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.","420210 VAR/TGP WRIGLEY TENNESSEE HICKMAN",null,null,null,null,null,null,null,null,null,"X20-963854",0,0,0,0,0,0,0,0]
["X21-159060","***","2021-03-01","2021-03-12","Added",null,null,"Sta 871: Unit 1A","800","2","Replace Power Heads","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-159060",1,0,0,0,0,0,0,0]
["X20-957370",null,"2021-05-03","2021-05-07",null,null,null,"Station 875","800","2","Annual ESD test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-957370",0,0,0,0,0,0,0,0]

{"sheet":"Sheet2","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}

{"sheet":"Sheet3","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}