{"text_format":"1","workbook":"xlsx","n_sheets":4,"sheets":["Closed","Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":8,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Closed","index":0,"n_rows":37,"n_cols":22,"rows_kept":37,"cut":false,"hidden":true,"merged":[[1,3,1,15],[2,3,2,15],[3,3,3,15]]}
[null,null,null,"Updated ","2016"]
[null,null,null,"Tennessee Gas Pipeline 2015 Pipeline Outage and Maintenance Summary"]
[null,null,null,"This is a summary of the current status of all TGP Winter 2014-2015 Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  Additionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
[null,null,null,"*** Indicates revision"]
["Date Change","Project New/Completed/Closed","Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","Location","Leg","Zone","Maintenance Activity","Anticipated Impact","Potential Restriction Level","TOS Potential Restrictions","Meter(s) in Impacted Area","Customer Notifications","Loc","Email Text","Posting Text","Completion Text"]
[{"$f":"IF(AND(H6<>\"\",I6<>\"\"), \"Date change. Previously scheduled \" & TEXT(H6,\"m/d/y;@\") &IF(H6=I6,\"\",\" to \" & TEXT(I6,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed",null,{"$f":"IF(G6<>\"\",\"***\",\"\")","v":"***"},"2015-01-11","2016-01-11",{"$f":"IF(AND(A6=\"\",B6=\"\"),\"\",IF(B6=\"\",A6,B6))","v":"Project Completed"},null,null,"MS #412494 DCP Warren","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412494 DCP Warren",401,{"$f":"\"(\"&C6&\") \"&J6&\":  \"&M6&IF(AND(E6=\"\",F6=\"\"),\"\",\" (\")&IF(E6=\"\",\"\",\"\"&TEXT(E6,\"m/d/y;@\"))&IF(OR(F6=E6,E6=\"\",F6=\"\"),\"\",\" to \")&IF(OR(F6=\"\",F6=E6),\"\",TEXT(F6,\"m/d/y;@\"))&IF(AND(E6=\"\",F6=\"\"),\"\",\")\")","v":"() MS #412494 DCP Warren:  Meter Station (1/11/15 to 1/11/16)"},{"$f":"D6&J6&\":  \"&M6&IF(AND(E6=\"\",F6=\"\"),\"\",\"\n\")&IF(E6=\"\",\"\",\"--\"&TEXT(E6,\"m/d/y;@\"))&IF(OR(F6=E6,E6=\"\",F6=\"\"),\"\",\" through \")&IF(OR(F6=\"\",F6=E6),\"\",TEXT(F6,\"m/d/y;@\"))&IF(AND(E6=\"\",F6=\"\"),\"\",\":  \")&N6&\"  \"&P6&IF(Q6=\"\",\"\",\"\n\"&Q6)&IF(G6=\"\",\"\",\"\n***\")&G6&\"\n………………………………\"","v":"***MS #412494 DCP Warren:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412494 DCP Warren\n***Project Completed\n………………………………"},{"$f":"D6&J6&\":  \"&M6&IF(G6=\"\",\"\",\"\n***\")&G6&IF(Q6=\"\",\"\",\"\nThe following meters are available for nominations:\n\")&Q6&\"\n………………………………\"","v":"***MS #412494 DCP Warren:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412494 DCP Warren\n………………………………"}]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412400 King Ranch","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412400 King Ranch",402.1,"() MS #412400 King Ranch:  Meter Station (1/11/15 to 1/11/16)","***MS #412400 King Ranch:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412400 King Ranch\n***Project Completed\n………………………………","***MS #412400 King Ranch:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412400 King Ranch\n………………………………"]
["","Project Completed",null,"***","2015-01-12","2016-01-12","Project Completed",null,null,"MS #410539 Duvak Gas Gathering","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410539 Duvak Gas Gathering",402.1,"() MS #410539 Duvak Gas Gathering:  Meter Station (1/12/15 to 1/12/16)","***MS #410539 Duvak Gas Gathering:  Meter Station\n--1/12/15 through 1/12/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410539 Duvak Gas Gathering\n***Project Completed\n………………………………","***MS #410539 Duvak Gas Gathering:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n410539 Duvak Gas Gathering\n………………………………"]
["","Project Completed",null,"***","2015-01-13","2016-01-13","Project Completed",null,null,"MS #412356 DCP LaGloria","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412356 DCP LaGloria",403.1,"() MS #412356 DCP LaGloria:  Meter Station (1/13/15 to 1/13/16)","***MS #412356 DCP LaGloria:  Meter Station\n--1/13/15 through 1/13/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412356 DCP LaGloria\n***Project Completed\n………………………………","***MS #412356 DCP LaGloria:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412356 DCP LaGloria\n………………………………"]
["","Project Completed",null,"***","2015-01-13","2016-01-13","Project Completed",null,null,"MS #410173 Enterprise LaReforma","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410173 Enterprise LaReforma",406.1,"() MS #410173 Enterprise LaReforma:  Meter Station (1/13/15 to 1/13/16)","***MS #410173 Enterprise LaReforma:  Meter Station\n--1/13/15 through 1/13/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410173 Enterprise LaReforma\n***Project Completed\n………………………………","***MS #410173 Enterprise LaReforma:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n410173 Enterprise LaReforma\n………………………………"]
["","Project Completed",null,"***","2015-01-12","2016-01-12","Project Completed",null,null,"MS #411903 Enterprise El Benito","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","411903 Enterprise El Benito",407.1,"() MS #411903 Enterprise El Benito:  Meter Station (1/12/15 to 1/12/16)","***MS #411903 Enterprise El Benito:  Meter Station\n--1/12/15 through 1/12/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n411903 Enterprise El Benito\n***Project Completed\n………………………………","***MS #411903 Enterprise El Benito:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n411903 Enterprise El Benito\n………………………………"]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412088 Enterprise Sullivan","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412088 Enterprise Sullivan",407.1,"() MS #412088 Enterprise Sullivan:  Meter Station (1/11/15 to 1/11/16)","***MS #412088 Enterprise Sullivan:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412088 Enterprise Sullivan\n***Project Completed\n………………………………","***MS #412088 Enterprise Sullivan:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412088 Enterprise Sullivan\n………………………………"]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412683 HESCO","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412683 HESCO",408.1,"() MS #412683 HESCO:  Meter Station (1/11/15 to 1/11/16)","***MS #412683 HESCO:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412683 HESCO\n***Project Completed\n………………………………","***MS #412683 HESCO:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412683 HESCO\n………………………………"]
[{"$f":"IF(AND(H14<>\"\",I14<>\"\"), \"Date change. Previously scheduled \" & TEXT(H14,\"m/d/y;@\") &IF(H14=I14,\"\",\" to \" & TEXT(I14,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X16-36843",{"$f":"IF(G14<>\"\",\"***\",\"\")","v":"***"},"2016-01-27","2016-01-27","Project Completed",null,null,"Sta. 237",200,5,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,237,"(X16-36843) Sta. 237:  Unit  Maintenance (1/27/16)","***Sta. 237:  Unit  Maintenance\n--1/27/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Sta. 237:  Unit  Maintenance\n***Project Completed\n………………………………"]
[{"$f":"IF(AND(H15<>\"\",I15<>\"\"), \"Date change. Previously scheduled \" & TEXT(H15,\"m/d/y;@\") &IF(H15=I15,\"\",\" to \" & TEXT(I15,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X14-1478563",{"$f":"IF(G15<>\"\",\"***\",\"\")","v":"***"},"2015-11-16","2016-02-12","Project Completed",null,null,"MLV 32-1D to 33-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,32.200000000000003,"(X14-1478563) MLV 32-1D to 33-1:  Hydrotest (11/16/15 to 2/12/16)","***MLV 32-1D to 33-1:  Hydrotest\n--11/16/15 through 2/12/16:  This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***MLV 32-1D to 33-1:  Hydrotest\n***Project Completed\n………………………………"]
[null,"Project Completed","X16-16074",null,"2016-01-18","2016-01-28","Project Completed",null,null,"Station 550","500","1","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,550,"(X16-16074) Station 550:  Station Maintenance (1/18/16 to 1/28/16)","Station 550:  Station Maintenance\n--1/18/16 through 1/28/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","Station 550:  Station Maintenance\n***Project Completed\n………………………………"]
[{"$f":"IF(AND(H17<>\"\",I17<>\"\"), \"Date change. Previously scheduled \" & TEXT(H17,\"m/d/y;@\") &IF(H17=I17,\"\",\" to \" & TEXT(I17,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X16-46202",{"$f":"IF(G17<>\"\",\"***\",\"\")","v":"***"},"2016-02-01","2016-02-07","Project Completed",null,null,"Station 9","100","0","Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.",null,9,"(X16-46202) Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items) (2/1/16 to 2/7/16)","***Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)\n--2/1/16 through 2/7/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\n***Project Completed\n………………………………","***Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)\n***Project Completed\n………………………………"]
["","Project Completed","X15-925633","***","2016-02-09","2016-02-11","Project Completed",null,null,"Sta. 266A",200,6,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,266,"(X15-925633) Sta. 266A:  Unit  Maintenance (2/9/16 to 2/11/16)","***Sta. 266A:  Unit  Maintenance\n--2/9/16 through 2/11/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Sta. 266A:  Unit  Maintenance\n***Project Completed\n………………………………"]
["","Project Completed","X15-929733","***","2016-01-27","2016-02-10","Project Completed",null,null,"MLV 834-1 to 838-1",800,5,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",834.1,"(X15-929733) MLV 834-1 to 838-1:  ILI/Cleaning Pig (1/27/16 to 2/10/16)","***MLV 834-1 to 838-1:  ILI/Cleaning Pig\n--1/27/16 through 2/10/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 834-1 to 838-1:  ILI/Cleaning Pig\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X14-1562506","***","2015-11-02","2016-02-19","Project Completed",null,null,"MLV 5-1 to 6-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410063 ROCHE DEHYDRATION             \n",5.0999999999999996,"(X14-1562506) MLV 5-1 to 6-1:  Hydrotest (11/2/15 to 2/19/16)","***MLV 5-1 to 6-1:  Hydrotest\n--11/2/15 through 2/19/16:  This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410063 ROCHE DEHYDRATION             \n\n***Project Completed\n………………………………","***MLV 5-1 to 6-1:  Hydrotest\n***Project Completed\nThe following meters are available for nominations:\n410063 ROCHE DEHYDRATION             \n\n………………………………"]
["","Project Completed","X14-1562506","***","2015-11-02","2016-02-19","Project Completed",null,null,"MLV 7-1 to 9-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","\n412490 Charro\n421083 Eagle Ford Field Service",5.0999999999999996,"(X14-1562506) MLV 7-1 to 9-1:  Hydrotest (11/2/15 to 2/19/16)","***MLV 7-1 to 9-1:  Hydrotest\n--11/2/15 through 2/19/16:  This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n\n412490 Charro\n421083 Eagle Ford Field Service\n***Project Completed\n………………………………","***MLV 7-1 to 9-1:  Hydrotest\n***Project Completed\nThe following meters are available for nominations:\n\n412490 Charro\n421083 Eagle Ford Field Service\n………………………………"]
["Date change. Previously scheduled 2/18/16 to 2/20/16.","Project Completed","X15-882289","***","2016-02-22","2016-02-24","Project Completed","2016-02-18","2016-02-20","MLV 24-2 to 25-2S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.2,"(X15-882289) MLV 24-2 to 25-2S:  Anomaly Remediation (2/22/16 to 2/24/16)","***MLV 24-2 to 25-2S:  Anomaly Remediation\n--2/22/16 through 2/24/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 24-2 to 25-2S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-925630","***","2016-02-23","2016-02-23","Project Completed",null,null,"WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B)",200,"L","ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,265.10000000000002,"(X15-925630) WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig (2/23/16)","***WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig\n--2/23/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig\n***Project Completed\n………………………………"]
["","Project Completed","X16-23748","***","2016-02-15","2016-02-18","Project Completed",null,null,"MLV 530-3 to 532-3",500,"L","ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,530.29999999999995,"(X16-23748) MLV 530-3 to 532-3:  ILI/Cleaning Pig (2/15/16 to 2/18/16)","***MLV 530-3 to 532-3:  ILI/Cleaning Pig\n--2/15/16 through 2/18/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***MLV 530-3 to 532-3:  ILI/Cleaning Pig\n***Project Completed\n………………………………"]
["","Project Canceled","X16-98720","***","2016-03-06","2016-03-06","Project Canceled",null,null,"Sta. 1",100,0,"Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,1,"(X16-98720) Sta. 1:  Station Maintenance (3/6/16)","***Sta. 1:  Station Maintenance\n--3/6/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Canceled\n………………………………","***Sta. 1:  Station Maintenance\n***Project Canceled\n………………………………"]
["","Project Completed","X14-1562513\nX14-1540661","***","2015-07-01","2016-03-04","Project Completed",null,null,"Station 32","100","0","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,32,"(X14-1562513\nX14-1540661) Station 32:  Station Maintenance (7/1/15 to 3/4/16)","***Station 32:  Station Maintenance\n--7/1/15 through 3/4/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Station 32:  Station Maintenance\n***Project Completed\n………………………………"]
["","Project Canceled","X15-926822","***","2016-06-06","2016-06-11","Project Canceled",null,null,"BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1)",300,6,"Pipe Inspection","This project involves inspecting multiple sites.  We do not anticipate having to do any repairs, however if a repair is needed  there is a potential that the pipe  may require replacement which will require isolation of the pipe.  This may limit throughput and will result in restrictions based on customer nominations.  Customers may experience pressure fluctuations during this timeframe.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",343.1,"(X15-926822) BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection (6/6/16 to 6/11/16)","***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection\n--6/6/16 through 6/11/16:  This project involves inspecting multiple sites.  We do not anticipate having to do any repairs, however if a repair is needed  there is a potential that the pipe  may require replacement which will require isolation of the pipe.  This may limit throughput and will result in restrictions based on customer nominations.  Customers may experience pressure fluctuations during this timeframe.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928271","***","TBD","TBD","Project Canceled",null,null,"MLV 555-1 to 550-1",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.1,"(X15-928271) MLV 555-1 to 550-1:  ILI/Cleaning Pig (TBD)","***MLV 555-1 to 550-1:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-1 to 550-1:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928272","***","TBD","TBD","Project Canceled",null,null,"MLV 555-2 to 550-2",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.20000000000005,"(X15-928272) MLV 555-2 to 550-2:  ILI/Cleaning Pig (TBD)","***MLV 555-2 to 550-2:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-2 to 550-2:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928273","***","TBD","TBD","Project Canceled",null,null,"MLV 555-3 to 552-3",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.29999999999995,"(X15-928273) MLV 555-3 to 552-3:  ILI/Cleaning Pig (TBD)","***MLV 555-3 to 552-3:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-3 to 552-3:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-882281","***","2016-02-24","2016-03-03","Project Completed",null,null,"24-1A to 25-1S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.1,"(X15-882281) 24-1A to 25-1S:  Anomaly Remediation (2/24/16 to 3/3/16)","***24-1A to 25-1S:  Anomaly Remediation\n--2/24/16 through 3/3/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***24-1A to 25-1S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-882291","***","2016-03-03","2016-03-04","Project Completed",null,null,"MLV 24-3 to 25-3S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.3,"(X15-882291) MLV 24-3 to 25-3S:  Anomaly Remediation (3/3/16 to 3/4/16)","***MLV 24-3 to 25-3S:  Anomaly Remediation\n--3/3/16 through 3/4/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 24-3 to 25-3S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X14-1178175","***","2015-06-15","2016-03-31","Project Completed",null,null,"Station 63","100","1","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,63,"(X14-1178175) Station 63:  Station Maintenance (6/15/15 to 3/31/16)","***Station 63:  Station Maintenance\n--6/15/15 through 3/31/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Station 63:  Station Maintenance\n***Project Completed\n………………………………"]
["","Project Cancelled","X15-913224","***","2016-04-16","2016-05-21","Project Cancelled",null,null,"MLV 109-2",100,2,"Pipe Replacement","This project will require taking the pipeline section out of service.   This will limit throughput and will result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",109.2,"(X15-913224) MLV 109-2:  Pipe Replacement (4/16/16 to 5/21/16)","***MLV 109-2:  Pipe Replacement\n--4/16/16 through 5/21/16:  This project will require taking the pipeline section out of service.   This will limit throughput and will result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Cancelled\n………………………………","***MLV 109-2:  Pipe Replacement\n***Project Cancelled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-926830","***","2016-03-07","2016-03-11","Project Completed",null,null,"MLV 400-1 to 408-1",100,0,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.","To Be Determined",400.1,"(X15-926830) MLV 400-1 to 408-1:  ILI/Cleaning Pig (3/7/16 to 3/11/16)","***MLV 400-1 to 408-1:  ILI/Cleaning Pig\n--3/7/16 through 3/11/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 400-1 to 408-1:  ILI/Cleaning Pig\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Cancelled","X16-143836","***","2016-03-28","2016-04-04","Project Cancelled",null,null,"Sta. 409",100,0,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.",null,409,"(X16-143836) Sta. 409:  Unit  Maintenance (3/28/16 to 4/4/16)","***Sta. 409:  Unit  Maintenance\n--3/28/16 through 4/4/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\n***Project Cancelled\n………………………………","***Sta. 409:  Unit  Maintenance\n***Project Cancelled\n………………………………"]
["","Project Cancelled","X15-929680","***","2016-04-18","2016-04-27","Project Cancelled",null,null,"SABINE - KINDER LINE to 822-1",800,"L","Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",822.1,"(X15-929680) SABINE - KINDER LINE to 822-1:  Anomaly Remediation (4/18/16 to 4/27/16)","***SABINE - KINDER LINE to 822-1:  Anomaly Remediation\n--4/18/16 through 4/27/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Cancelled\n………………………………","***SABINE - KINDER LINE to 822-1:  Anomaly Remediation\n***Project Cancelled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]

{"sheet":"Sheet1","index":1,"n_rows":153,"n_cols":33,"rows_kept":153,"cut":false,"hidden":false,"merged":[[2,0,2,14]]}
["Updated ","2021-10-14"]
["Tennessee Gas Pipeline 2021 Pipeline Outage and Maintenance Summary"]
["This is a summary of the current status of all TGP 2021 Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  \nAdditionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
["*** Indicates revision"]
["Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","Location","Leg","Zone","Maintenance Activity","Anticipated Impact","Potential Restriction Level","TOS Potential Restrictions","Meter(s) in Impacted Area",null,null,null,null,null,null,null,null,null,"\\\\houCORP\\TRANS\\TRANSERVICES\\OPPLAN\\COMMON\\Outages\\Outage_DB\\TGP\\Files"]
["X21-380850",null,"2021-08-02","2021-10-22",null,null,null,"Sta 1: Unit 1A","100","0","Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-380850",0,0,0,0,0,0,0,0]
["X21-380848",null,"2021-07-12","2021-10-19",null,null,null,"Sta 1: Unit 8A","100","0","Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-380848",0,0,0,0,0,0,0,0]
["X19-761902",null,"2022-02-14","2022-02-25",null,null,null,"MLV 5-2 to MLV 4-2","100","0","Pipe Replacement","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X19-761902",0,0,0,0,0,0,0,0]
["X21-35982",null,"2022-09-01","2022-10-01",null,null,null,"MLV 4-1 to MLV 5-1","100","0","Pressure Weld Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-35982",0,0,0,0,0,0,0,0]
["X21-35981",null,"2022-08-01","2022-09-01",null,null,null,"MLV 12-1 to MLV 13-1","100","0","Pressure Weld Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-35981",0,0,0,0,0,0,0,0]
["X21-22722",null,"2021-10-04","2021-11-12",null,null,null,"Sta 17: Unit 2C","100","0","Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-22722",0,0,0,0,0,0,0,0]
["X21-963698",null,"2021-12-13","2021-12-17",null,null,null,"Sta 25","100","0","Annual ESD & Sub-Station Testing","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-963698",0,0,0,0,0,0,0,0]
["X21-295438",null,"2021-12-07","2021-12-17",null,null,null,"Sta 25: Unit 1C","100","0","Stator Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-295438",0,0,0,0,0,0,0,0]
["X21-960459",null,"2021-10-04","2021-12-01",null,null,null,"Sta 25: Unit 1D","100","0","Voith Bearing","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-960459",0,0,0,0,0,0,0,0]
["X21-295442",null,"2021-10-29","2021-10-30",null,null,null,"Sta 25: Unit 1D","100","0","Exciter Panel Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-295442",0,0,0,0,0,0,0,0]
["X21-295452",null,"2021-10-29","2021-10-30",null,null,null,"Sta 25: Unit 1D","100","0","Motor PM","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-295452",0,0,0,0,0,0,0,0]
["X21-718666",null,"2021-07-29","2021-11-01",null,null,null,"Sta 25: Unit 2D","100","0","Voith Bearing","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-718666",0,0,0,0,0,0,0,0]
["X21-900007",null,"2021-10-26","2021-10-28",null,null,null,"Sta 25: Unit 2D","100","0","Exciter Panel Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-900007",0,0,0,0,0,0,0,0]
["X21-558699","***","2021-11-04","2021-11-24","Project Change","11/01/21","11/24/21","MLV 28-1 to MLV 29-1","100","0","Wrinkle Bend Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-558699",0,1,0,0,0,0,0,0]
["X21-551228",null,"2022-02-01","2022-03-31",null,null,null,"MLV 31-2 to MLV 32-2","100","0","Wrinkle Bend Removal & Mod Pig Traps","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-551228",0,0,0,0,0,0,0,0]
["X21-231767","***","2021-07-15","2021-10-15","Project Change","7/15/21","10/13/21","MLV 36-1 to MLV 37-1","100","0","Wrinkle Bend Removal & Mod Pig Traps","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-231767",0,0,1,0,0,0,0,0]
["X21-938955","***","2021-10-04","2021-10-07","Completed",null,null,"Sta 40: Unit 2C","100","1","Jacket Water and Lube Oil System","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-938955",1,0,0,0,0,0,0,0]
["X21-271936",null,"2021-09-07","2021-10-19",null,null,null,"Sta 40: Unit 1C","100","1","Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-271936",0,0,0,0,0,0,0,0]
["X21-44561",null,"2021-10-26","2021-11-04",null,null,null,"MLV 40-2S to MLV 32-2D","100","0","PIG Run - Cleaning 10/26 - 10/29, Gauge 10/29, DEF 11/2, MDS 11/4","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-44561",0,0,0,0,0,0,0,0]
["X21-55858",null,"2021-10-11","2021-10-14",null,null,null,"MLV 40-3D TO MLV 47-3S","100","1","PIG Run - Cleaning 10/11, Caliper 10/12, MDS 10/14","This activity will require operating at controlled flow rates.   The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","49780 GULFSTH/TGP WORTHY ROAD SOUTH OUACH",null,null,null,null,null,null,null,null,null,"X21-55858",0,0,0,0,0,0,0,0]
["X21-67839",null,"2021-10-19","2021-10-25",null,null,null,"Bear Creek Storage","100","1","Shut-in Test","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","460017 STORAGE – BEAR CREEK",null,null,null,null,null,null,null,null,null,"X21-67839",0,0,0,0,0,0,0,0]
["X21-675588",null,"2021-11-01","2021-11-14",null,null,null,"MLV 47-3BL to MLV 47-3A","100","1","D Arbonne Bayou/Ouachita River tie-ins","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-675588",0,0,0,0,0,0,0,0]
["X21-906326",null,"2021-11-06","2021-11-19",null,null,null,"MLV 53-1 to MLV 53-1A","100","1","Shallow Pipe","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-906326",0,0,0,0,0,0,0,0]
["X21-668271",null,"2021-09-20","2021-11-10",null,null,null,"MLV 53-3 to MLV 54-3","100","1","Trap Modification","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-668271",0,0,0,0,0,0,0,0]
["X21-906332",null,"2021-10-18","2021-11-05",null,null,null,"MLV 53-4 to MLV 53-4A","100","1","Shallow Pipe","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-906332",0,0,0,0,0,0,0,0]
["X20-957252","***","2021-10-12","2021-10-12","Completed",null,null,"Station 54","100","1","Annual ESD test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-957252",1,0,0,0,0,0,0,0]
["X21-982199","***","2021-10-18","2021-10-29","Added",null,null,"MLV 56-2 to MLV 57-2","100","1","Shallow Pipe","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-982199",1,0,0,0,0,0,0,0]
["X21-982202","***","2021-11-01","2021-11-19","Added",null,null,"MLV 59-1 to MLV 60-1","100","1","Shallow Pipe","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-982202",1,0,0,0,0,0,0,0]
["X21-692108",null,"2021-09-13","2021-11-24",null,null,null,"MLVS 60-1","100","1","Line Lowering","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-692108",0,0,0,0,0,0,0,0]
["X21-982201","***","2021-10-25","2021-11-19","Added",null,null,"MLV 61-1 to MLV 62-1","100","1","Shallow Pipe","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-982201",1,0,0,0,0,0,0,0]
["X21-893377",null,"2021-10-26","2021-10-27",null,null,null,"Sta. 63","100","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-893377",0,0,0,0,0,0,0,0]
["X21-786200",null,"2021-08-18","2022-02-26",null,null,null,"Sta 71: Unit 2B","100","1","Main Bearing","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-786200",0,0,0,0,0,0,0,0]
["X21-893233",null,"2021-10-21","2021-10-21",null,null,null,"MLV 79-2D TO MLV 82-2","100","1","Pig Re-Runs - AFD 10/21/21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-893233",0,0,0,0,0,0,0,0]
["X21-803509",null,"2021-10-18","2021-10-22",null,null,null,"Sta 87","100","2","Bldg D Valve Replacement","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-803509",0,0,0,0,0,0,0,0]
["X21-960432","***","2021-10-12","2021-10-13","Completed",null,null,"Sta 87: Unit 2E","100","1","Replace Waste Gate Bellows","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-960432",1,0,0,0,0,0,0,0]
["X21-886970","***","2021-09-20","2021-10-07","Completed",null,null,"Sta 96: Unit 7C","100","2","Compressor Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-886970",1,0,0,0,0,0,0,0]
["X19-703248",null,"2019-08-01","2022-12-31",null,null,null,"MLV 106-1 to MLV 96-1","100","2","Pressure Restriction from ILI","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X19-703248",0,0,0,0,0,0,0,0]
["X21-31692",null,"2021-02-15","2021-11-30",null,null,null,"MLV 103-1 and MLV 105-1","100","2","Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-31692",0,0,0,0,0,0,0,0]
["X21-965417",null,"2021-10-18","2021-11-05",null,null,null,"Sta 106: Unit 13B","100","2","Turbo Charger","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-965417",0,0,0,0,0,0,0,0]
["X21-766276",null,"2021-11-01","2021-11-12",null,null,null,"Sta 106","100","2","Unit 1C - MCC Replacement","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-766276",0,0,0,0,0,0,0,0]
["X21-40121",null,"2021-10-15","2021-10-15",null,null,null,"Sta 107A","100","2","Annual ESD test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-40121",0,0,0,0,0,0,0,0]
["X21-929620","***","2021-10-05","2021-10-09","Completed",null,null,"MLV 109-2A to MLV 110-2","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-929620",1,0,0,0,0,0,0,0]
["X21-751549","***","2021-10-04","2021-10-16","Completed",null,null,"MLV 110-2 to MLV 111-2","100","2","Wrinkle Bend Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-751549",1,0,0,0,0,0,0,0]
["X21-751547","***","2021-10-07","2021-10-18","Project Change","10/07/21","10/16/21","MLV 112-2 to MLV 113-2","100","2","Wrinkle Bend Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","412742 BIGSANDY/TGP GLANCY CARTER",null,null,null,null,null,null,null,null,null,"X21-751547",0,0,1,0,0,0,0,0]
["X21-40301",null,"2021-11-01","2021-11-03",null,null,null,"Sta 114: Unit 1D","100","3","Turbine Service and Filter Change Out","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-40301",0,0,0,0,0,0,0,0]
["X21-40272",null,"2021-11-08","2021-11-10",null,null,null,"Sta 118A: Unit 1A","100","3","Turbine Service and Filter Change Out","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-40272",0,0,0,0,0,0,0,0]
["X21-40293",null,"2021-11-04","2021-11-06",null,null,null,"Sta 119A: Unit 1A","100","3","Turbine Service and Filter Change Out","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-40293",0,0,0,0,0,0,0,0]
["X21-751545",null,"2021-11-01","2021-11-07",null,null,null,"MLV 121-2 to MLV 121-2A","100","3","Wrinkle Bend Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-751545",0,0,0,0,0,0,0,0]
["X21-28988","***","2021-07-26","2021-10-08","Completed",null,null,"Sta 200: Unit 8A","200","4","Upper Block Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-28988",1,0,0,0,0,0,0,0]
["X21-982018","***","2021-10-18","2021-10-22","Added",null,null,"Sta 200: Unit 12A","200","4","Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-982018",1,0,0,0,0,0,0,0]
["X21-923966","***","2021-11-10","2021-11-17","Project Change","10/18/21","10/21/21","Sta 204: Unit 1A","200","4","Install Deactivator","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-923966",0,1,1,0,0,0,0,0]
["X21-979601","***","2021-11-29","2021-12-02","Added",null,null,"Sta 204: Unit 2A","200","4","Engine and Compressor Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-979601",1,0,0,0,0,0,0,0]
["X21-923965","***","2021-11-09","2021-11-09","Project Change","10/14/21","10/14/21","Sta 204: Unit 3A","200","4","Install Deactivator","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-923965",0,1,1,0,0,0,0,0]
["X21-923964","***","2021-11-08","2021-11-08","Project Change","10/13/21","10/13/21","Sta 204: Unit 4A","200","4","Install Deactivator","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-923964",0,1,1,0,0,0,0,0]
["X21-846980","***","2021-10-11","2021-11-04","Project Change","10/11/21","10/12/21","Sta 204: Unit 5A","200","4","Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-846980",0,0,1,0,0,0,0,0]
["X21-979599","***","2021-12-08","2021-12-16","Added",null,null,"Sta 204: Unit 10A","200","4","Punching Carbon & Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-979599",1,0,0,0,0,0,0,0]
["X21-292513",null,"2021-10-05","2021-10-31",null,null,null,"MLV 205-1 to MLV 209-1","200","4","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-292513",0,0,0,0,0,0,0,0]
["X21-929698","***","2021-10-04","2021-10-14","Completed",null,null,"Sta 209: Unit 9A","200","4","Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-929698",1,0,0,0,0,0,0,0]
["X21-118105",null,"2021-03-15","2021-11-04",null,null,null,"Sta 209: Unit 10A","200","4","Full Foundation Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-118105",0,0,0,0,0,0,0,0]
["X21-982007","***","2021-10-18","2021-10-21","Added",null,null,"Sta 209: Unit 12A","200","4","Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-982007",1,0,0,0,0,0,0,0]
["X21-850179","***","2021-09-02","2021-10-15","Added",null,null,"Sta 214: Unit 5A","200","4","Line Bore Compressor Cylinders","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-850179",1,0,0,0,0,0,0,0]
["X21-924378",null,"2021-10-25","2021-10-29",null,null,null,"Sta 214: Unit 13A","200","4","Chock Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-924378",0,0,0,0,0,0,0,0]
["X21-963526",null,"2021-11-01","2021-11-06",null,null,null,"MLVS 217-1","200","4","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-963526",0,0,0,0,0,0,0,0]
["X21-943837",null,"2021-10-25","2021-11-01",null,null,null,"Sta 219: Unit 12A","200","4","Engine Chocks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-943837",0,0,0,0,0,0,0,0]
["X21-788176",null,"2021-11-02","2021-11-02",null,null,null,"Sta 224 to Sta 229","200","5","Maintenance Pig Line 1","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-788176",0,0,0,0,0,0,0,0]
["X21-963527",null,"2021-10-25","2021-10-30",null,null,null,"MLVS 228-1","200","5","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-963527",0,0,0,0,0,0,0,0]
["X21-982053","***","2021-10-18","2021-10-22","Added",null,null,"Sta 229: Unit 1A and Unit 6A","200","5","Power Heads","This project will require unit outages, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-982053",1,0,0,0,0,0,0,0]
["X21-718806",null,"2021-07-27","2021-10-31",null,null,null,"MLV 230 to Sta 237","200","5","Force Majeure","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-718806",0,0,0,0,0,0,0,0]
["X21-929821",null,"2021-10-18","2021-10-20",null,null,null,"Sta 237: Unit 1A","200","5","Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-929821",0,0,0,0,0,0,0,0]
["X21-929824",null,"2021-10-21","2021-10-22",null,null,null,"Sta 237: Unit 2A","200","5","Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-929824",0,0,0,0,0,0,0,0]
["X21-929843",null,"2021-10-11","2021-10-15",null,null,null,"Sta 237: Unit 3A","200","5","Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-929843",0,0,0,0,0,0,0,0]
["X21-929848",null,"2021-10-18","2021-10-21",null,null,null,"Sta 241: Unit 1A","200","5","Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-929848",0,0,0,0,0,0,0,0]
["X21-929854",null,"2021-10-25","2021-10-28",null,null,null,"Sta 241: Unit 2A","200","5","Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-929854",0,0,0,0,0,0,0,0]
["X21-982070","***","2021-10-25","2021-11-06","Added",null,null,"MLV 241-2 to MLV 242-2","200","5","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-982070",1,0,0,0,0,0,0,0]
["X21-906348","***","2021-10-15","2021-10-18","Project Change","10/14/21","10/19/21","MLV 248-1 to MLV 249-1","200","5","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-906348",0,1,1,0,0,0,0,0]
["X21-224827","***","2021-09-20","2021-10-08","Completed",null,null,"Sta 249: Unit 1A","200","5","Air Manifold Replacement & Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-224827",1,0,0,0,0,0,0,0]
["X21-803654","***","2021-10-11","2021-10-16","Project Change","10/11/21","10/13/21","MLV 249-1 to MLV 250-1","200","5","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-803654",0,0,1,0,0,0,0,0]
["X21-688416","***","2021-10-18","2021-10-22","Project Change","10/18/21","10/21/21","MLVS 249-2","200","5","Meter Station Upgrade Iroquois Wright (Mtr 412181)","This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations. The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","412181 IROQUOIS/TGP WRIGHT SMS SCHOHARIE",null,null,null,null,null,null,null,null,null,"X21-688416",0,0,1,1,0,0,0,0]
["X21-906349","***","2021-10-04","2021-10-08","Completed",null,null,"MLV 258-1 to MLV 259-1","200","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-906349",1,0,0,0,0,0,0,0]
["X21-760467",null,"2021-08-09","2021-11-03",null,null,null,"Sta 260A","200","6","Station Transformer","This project will require a station outage which will require operating at controlled flow rates.  Customers may experience pressure fluctuations and flow limitations.","SOP","Potential out of path restrictions may be at risk.","420104 WESTFLD/TGP WESTFIELD MA HAMPDEN\n420401 HOLYOKE/TGP HOLYOKE MA 2 HAMPDEN\n420292 BERKSHR/TGP GREENFIELD MA HAMPSHIRE\n420106 EVRSRC/TGP GRANITE NORTHAMPTON MA H",null,null,null,null,null,null,null,null,null,"X21-760467",0,0,0,0,0,0,0,0]
["X21-982274","***","2021-10-14","2021-10-14","Added",null,null,"Sta 261: Unit 2D","200","6","Witches Hat Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-982274",1,0,0,0,0,0,0,0]
["X21-879354",null,"2021-10-20","2021-10-20",null,null,null,"Sta 264","200","6","Annual ESD test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-879354",0,0,0,0,0,0,0,0]
["X20-1034818",null,"2021-10-16","2021-10-24",null,null,null,"Sta. 265E","200","6","Fall Outage","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-1034818",0,0,0,0,0,0,0,0]
["X20-1031952",null,"2022-04-02","2022-04-18",null,null,null,"Sta 265: Unit 1A","200","6","Controls Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-1031952",0,0,0,0,0,0,0,0]
["X21-929691","***","2021-09-29","2021-10-13","Completed",null,null,"Sta. 266A: Unit 1B","200","6","Valve Actuator","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.   The meter listed below may experience low pressure for deliveries during the project.","SOP","Potential out of path restrictions may be at risk.","420285 AGT/TGP MENDON MASS TIE OVER WORCHE",null,null,null,null,null,null,null,null,null,"X21-929691",1,0,0,0,0,0,0,0]
["X21-886952",null,"2021-10-26","2021-10-26",null,null,null,"270B-301 to 270B-302A","200","6","Pig - AFD 10/26/21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-886952",0,0,0,0,0,0,0,0]
["X21-927101","***","2021-10-18","2021-10-20","Completed",null,null,"Sta 303A: Unit 1A","300","4","Water Wash & 4k Borescope Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-927101",1,0,0,0,0,0,0,0]
["X21-960540","***","2021-10-06","2021-10-07","Completed",null,null,"Sta 307: Unit 2A","300","4","Valve Wiring","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-960540",1,0,0,0,0,0,0,0]
["X21-943899","***","2021-10-21","2021-10-23","Completed",null,null,"Sta 307: Unit 5A","300","4","Flywheel Jack","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-943899",1,0,0,0,0,0,0,0]
["X21-986450","***","2021-10-21","2021-10-23","Added",null,null,"Sta 307: Unit 5A","300","4","Flywheel Jack","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-986450",1,0,0,0,0,0,0,0]
["X21-982258","***","2021-10-26","2021-10-26","Added",null,null,"Sta 310: Unit 1A","300","4","Fuel Valve Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-982258",1,0,0,0,0,0,0,0]
["X21-832592",null,"2021-11-01","2021-11-05",null,null,null,"Ellisburg Storage","300","4","Shut-in Test","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","460012 – DOMINION/TGP ELLISBURG INJECTION PO",null,null,null,null,null,null,null,null,null,"X21-832592",0,0,0,0,0,0,0,0]
["X21-250297",null,"2021-06-07","2021-10-29",null,null,null,"Sta 313: Unit 3A, 6A - 9A","300","4","Automation Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-250297",0,0,0,0,0,0,0,0]
["X21-765950",null,"2021-10-25","2021-11-19",null,null,null,"Sta 313: Unit 8A","300","4","Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-765950",0,0,0,0,0,0,0,0]
["X21-832597",null,"2021-11-01","2021-11-05",null,null,null,"Hebron Storage","300","4","Shut-in Test","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meters listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","400485 HEBRON STORAGE INJECTION POTTER\n470001 HEBRON STORAGE WITHDRAWAL POTTER",null,null,null,null,null,null,null,null,null,"X21-832597",0,0,0,0,0,0,0,0]
["X21-879548",null,"2021-11-01","2021-11-08",null,null,null,"MLV 313A-403 to MLV 313A-404","400 (HC)","4","Replace Creek Crossing","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","PIP","Potential in the path restrictions may be at risk.","412803 ARLSTOR/TGP ARLINGTON STORAGE RECEI",null,null,null,null,null,null,null,null,null,"X21-879548",0,0,0,0,0,0,0,0]
["X21-832596",null,"2021-10-25","2021-10-29",null,null,null,"Harrison Storage","300","4","Shut-in Test","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","460004 – DOMINION/TGP HARRISON INJECTION POT",null,null,null,null,null,null,null,null,null,"X21-832596",0,0,0,0,0,0,0,0]
["X21-803710","***","2021-10-04","2021-10-08","Completed",null,null,"Sta. 323A","300","4","Annual ESD test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-803710",1,0,0,0,0,0,0,0]
["X20-957345","***","2021-10-13","2021-10-13","Completed",null,null,"Station 325","300","5","Annual ESD test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-957345",1,0,0,0,0,0,0,0]
["X21-36198","***","2021-09-27","2021-10-22","Project Change","9/27/21","10/16/21","MLV 334A-100","300","6","ECDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-36198",0,0,1,0,0,0,0,0]
["X21-906356",null,"2022-05-20","2022-05-25",null,null,null,"MLV 336 to MLV 261","300","6","Pig Run - Cleaning 5/20/22, AFD 5/23/22, EMAT 5/25/22","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-906356",0,0,0,0,0,0,0,0]
["X21-979587","***","2022-02-01","2022-02-13","Added",null,null,"MLVS 404-1","400 (So TX)","0","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-979587",1,0,0,0,0,0,0,0]
["X21-979592","***","2022-02-14","2022-02-28","Added",null,null,"MLVS 404-2","400 (So TX)","0","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-979592",1,0,0,0,0,0,0,0]
["X21-799941","***","2021-10-12","2021-10-12","Completed",null,null,"Sta 409A","400 (So TX)","0","Station PECO Filters","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-799941",1,0,0,0,0,0,0,0]
["X21-799936",null,"2021-10-12","2021-10-14",null,null,null,"Sta 409A: Unit 1A","400 (So TX)","0","Cooler Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-799936",0,0,0,0,0,0,0,0]
["X21-67884",null,"2021-12-03","2021-12-08",null,null,null,"Sta 409: Unit 2A","400 (So TX)","0","25k Hr Inspection","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-67884",0,0,0,0,0,0,0,0]
["X21-712941","***","2021-08-31","2021-10-29","Project Change","8/31/21","10/21/21","MLV 409A-101.1 to MLV 409A-102","400 (So TX)","0","Class Change","This project will require taking the pipeline section out of service. The meter listed will be shut in during the project.","SIP","Potential in the path restrictions may be at risk.","421067 CALPINE/TGP HIDALGO",null,null,null,null,null,null,null,null,null,"X21-712941",0,0,1,0,0,0,0,0]
["X21-358931","***","2021-10-13","2021-10-13","Completed",null,null,"MLV 401-1 to MLV 409-1","400 (So TX)","0","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-358931",1,0,0,0,0,0,0,0]
["X21-358939",null,"2021-10-14","2021-10-14",null,null,null,"MLV 401-2 to MLV 409-2","400 (So TX)","0","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","PIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-358939",0,0,0,0,0,0,0,0]
["X20-957229",null,"2021-10-26","2021-10-26",null,null,null,"Station 500C1","500","1","Annual ESD test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-957229",0,0,0,0,0,0,0,0]
["X21-447823",null,"2021-10-25","2021-11-20",null,null,null,"Sta 500C1: Unit A1","500","1","Unit Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-447823",0,0,0,0,0,0,0,0]
["X21-963555",null,"2021-11-10","2021-11-10",null,null,null,"MLV 500-1 TO MLV 507-1","500","L","Pig run - AFD 11/10","This activity will require operating at controlled flow rates.   The meters listed below will be shut-in during the project.","PIP","Potential in the path restrictions may be at risk.","420373 TRNSCO/TGP KINDER LA EXCH (BI 1\n420708 ELIZ NG/TGP GRANT LA SALES ALLEN\n420436 VERNON/TGP PITKIN LA VERNON\n420793 ELIZ NG/TGP J R FRANKS 1 VERNON\n420388 PROVNCAL/TGP PROVENCAL LA NATCHITOC",null,null,null,null,null,null,null,null,null,"X21-963555",0,0,0,0,0,0,0,0]
["X21-556565",null,"2021-10-08","2021-10-18",null,null,null,"Sta 504","500","L","Filter Change Out","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-556565",0,0,0,0,0,0,0,0]
["X21-135749",null,"2021-10-08","2021-10-18",null,null,null,"MLV 504-1A and MLV 505-1","500","L","Pipe Replacement Whiskey Chitto River Crossing","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","PIP","Potential in the path restrictions may be at risk.","420708 ELIZ NG/TGP GRANT LA SALES ALLEN",null,null,null,null,null,null,null,null,null,"X21-135749",0,0,0,0,0,0,0,0]
["X20-957349",null,"2021-10-21","2021-10-21",null,null,null,"Station 527","500","L","Annual ESD test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-957349",0,0,0,0,0,0,0,0]
["X20-957352","***","2021-10-13","2021-10-13","Completed",null,null,"Station 538","500","1","Annual ESD test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-957352",1,0,0,0,0,0,0,0]
["X21-471656",null,"2021-10-25","2021-10-29",null,null,null,"Sta 542","500","1","Annual ESD & Electrical Tests","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-471656",0,0,0,0,0,0,0,0]
["X21-171248","***","2021-02-24","2021-10-22","Project Change","2/24/21","10/15/21","Sta 542: Unit 4A","500","1","Crankshaft Repair","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-171248",0,0,1,0,0,0,0,0]
["X21-593931",null,"2021-10-22","2021-11-05",null,null,null,"MLV 545-1","500","1","Valve Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-593931",0,0,0,0,0,0,0,0]
["X21-927219",null,"2021-10-27","2021-11-05",null,null,null,"MLVS 545-1","500","1","High Priority Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-927219",0,0,0,0,0,0,0,0]
["X21-563414","***","2021-11-30","2021-12-02","Project Change","10/19/21","10/21/21","Sta. 546","500","1","Annual ESD Re- test & Starting Gas Valve Replacement","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-563414",0,1,1,0,0,0,0,0]
["X21-903603","***","2021-08-26","2021-10-22","Project Change","8/26/21","10/15/21","Sta 546: Unit 7A","500","1","Starter / Ring-Gear System","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-903603",0,0,1,0,0,0,0,0]
["X20-957353",null,"2021-12-07","2021-12-07",null,null,null,"Station 550","500","1","Annual ESD test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-957353",0,0,0,0,0,0,0,0]
["X21-250310",null,"2021-10-13","2021-11-09",null,null,null,"Sta 550: Unit 1B","500","1","Automation Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-250310",0,0,0,0,0,0,0,0]
["X21-797093",null,"2021-10-11","2021-10-30",null,null,null,"Sta 555: Units 4A, 5A, 6A","500","1","Replace Unloaders","This project will require unit outages, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-797093",0,0,0,0,0,0,0,0]
["X21-943897",null,"2021-11-01","2021-11-05",null,null,null,"Sta 555: Units 5A","500","1","Power Cylinder Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-943897",0,0,0,0,0,0,0,0]
["X20-1050037",null,"2021-10-28","2021-11-15",null,null,null,"MLV 559-2BL to MLV 560-2","500","1","Pressure Test & New Valve Installation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-1050037",0,0,0,0,0,0,0,0]
["X21-957555",null,"2021-10-27","2021-10-30",null,null,null,"Sta 563: Unit 1A","500","1","Water Wash & Strainer Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-957555",0,0,0,0,0,0,0,0]
["X21-957554",null,"2021-10-25","2021-10-26",null,null,null,"Sta 563: Unit 2A","500","1","Water Wash","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-957554",0,0,0,0,0,0,0,0]
["X21-957547",null,"2021-09-07","2021-10-24",null,null,null,"Sta 823: Unit 1A","800","L","Power Cylinder Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-957547",0,0,0,0,0,0,0,0]
["X21-957552",null,"2021-11-15","2021-11-19",null,null,null,"Sta 823: Unit 2A","800","L","Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-957552",0,0,0,0,0,0,0,0]
["X21-850224",null,"2021-09-02","2021-11-12",null,null,null,"Sta 823: Unit 3A","800","L","Turbo Charger Replacement","This project will require a unit outages, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-850224",0,0,0,0,0,0,0,0]
["X21-864679",null,"2021-10-25","2021-11-04",null,null,null,"Sta 823","800","L","Unit 10A","This project will require a unit outages, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-864679",0,0,0,0,0,0,0,0]
["X21-614719",null,"2019-03-01","2021-12-31",null,null,null,"Sta 823: Unit 10A","800","L","Crankshaft Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-614719",0,0,0,0,0,0,0,0]
["X21-957553",null,"2021-11-08","2021-11-12",null,null,null,"Sta 823: Unit 12A","800","L","HP Bottles","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-957553",0,0,0,0,0,0,0,0]
["X21-277608",null,"2021-10-20","2021-10-20",null,null,null,"Sta 827 to Sta 823","800","L","Maintenance Pig","This activity will require operating at controlled flow rates. The meters listed may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.","421043 PINE PRA/TGP PINE PRAIRIE NORTH RAP\n412847 ACADIAN/TGP CHENEYVILLE RAPIDES\n412713 HUGHES E/TGP UDP BLACK STONE13 EVAN\n412844 TEXLA/TGP ROY MARTIN GATHERING: RIP\n420296 FORSTHIL/TGP FOREST HILL LA RAPIDES\n420530 GLNMORA/TGP GLENMORA LA EXCH RAPIDE\n421042 ELIZ NG/TGP EVANGELINE SALES EVANGE\n420629 ELIZ NG/TGP OAKDALE DETENTION SALES\n420687 ELIZ NG/TGP ALLEN PARISH PRISON SAL\n420406 ELIZ NG/TGP ELIZABETH LA EMERGENCY\n53483 AIRLIQAT/TGP TIMBERLANE BIOGAS REC",null,null,null,null,null,null,null,null,null,"X21-277608",0,0,0,0,0,0,0,0]
["X21-277678",null,"2021-10-20","2021-10-20",null,null,null,"Sta 834 to Sta 827","800","L","Maintenance Pig","This activity will require operating at controlled flow rates. The meters listed may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.","420755 ATMOS TL/TGP LASALLE PARISH NEBO SA\n420447 PELICANG/TGP HARRISONBURG LA CATAHO",null,null,null,null,null,null,null,null,null,"X21-277678",0,0,0,0,0,0,0,0]
["X20-957366",null,"2021-12-06","2021-12-10",null,null,null,"Station 836A","800","1","Annual ESD test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-957366",0,0,0,0,0,0,0,0]
["X21-903608",null,"2021-10-25","2021-10-29",null,null,null,"Sta 836A: Unit 1A","800","1","4k inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-903608",0,0,0,0,0,0,0,0]
["X21-893378",null,"2021-10-28","2021-10-28",null,null,null,"Sta. 847","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-893378",0,0,0,0,0,0,0,0]
["X21-979565","***","2021-10-18","2021-10-20","Added",null,null,"Sta 851","800","1","MCC Electrical Inspection","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-979565",1,0,0,0,0,0,0,0]
["X21-461652",null,"2021-09-29","2021-10-27",null,null,null,"MLV 851-1 to MLV 853-1","800","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.","420282 NEWALBNY/TGP COTTON PLANT MS UNION\n420046 SYMMETRY/TGP RIPLEY MS TIPPAH\n420276 BLDWYN/TGP BALDWYN MS TIPPAH\n420429 BOONEVIL/TGP BOONEVILLE MS TIPPAH\n420855 CORINTH/TGP CORINTH 3 ALCORN\n420483 CORINTH/TGP CORINTH MS 2 ALCORN",null,null,null,null,null,null,null,null,null,"X21-461652",0,0,0,0,0,0,0,0]
["X20-957369",null,"2021-10-11","2021-10-21",null,null,null,"Station 860","800","1","Annual ESD test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-957369",0,0,0,0,0,0,0,0]
["X21-670982",null,"2021-10-11","2021-10-21",null,null,null,"Sta 860","800","1","Replace Unit Isolation Valves & Station Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-670982",0,0,0,0,0,0,0,0]
["X21-670986",null,"2021-10-22","2021-10-24",null,null,null,"Sta 860","800","1","Replace 500-1 Jumper","This project will require a partial station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-670986",0,0,0,0,0,0,0,0]
["X20-939915",null,"2020-02-10","2021-10-29",null,null,null,"Sta 860: Unit 5A","800","1","Crankcase Replacement & Regrout","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X20-939915",0,0,0,0,0,0,0,0]
["X21-845876",null,"2021-10-11","2021-10-22",null,null,null,"Sta 860: Unit 8A","800","1","Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-845876",0,0,0,0,0,0,0,0]
["X21-791108",null,"2021-11-02","2021-11-03",null,null,null,"Sta 871","800","2","Sta Outage Replace Unit Valves","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,null,null,null,null,null,null,null,null,null,"X21-791108",0,0,0,0,0,0,0,0]

{"sheet":"Sheet2","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}

{"sheet":"Sheet3","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}