{"text_format":"1","workbook":"xlsx","n_sheets":4,"sheets":["Closed","Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":8,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Closed","index":0,"n_rows":37,"n_cols":22,"rows_kept":37,"cut":false,"hidden":true,"merged":[[1,3,1,15],[2,3,2,15],[3,3,3,15]]}
[null,null,null,"Updated ","2016"]
[null,null,null,"Tennessee Gas Pipeline 2015 Pipeline Outage and Maintenance Summary"]
[null,null,null,"This is a summary of the current status of all TGP Winter 2014-2015 Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  Additionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
[null,null,null,"*** Indicates revision"]
["Date Change","Project New/Completed/Closed","Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","Location","Leg","Zone","Maintenance Activity","Anticipated Impact","Potential Restriction Level","TOS Potential Restrictions","Meter(s) in Impacted Area","Customer Notifications","Loc","Email Text","Posting Text","Completion Text"]
[{"$f":"IF(AND(H6<>\"\",I6<>\"\"), \"Date change. Previously scheduled \" & TEXT(H6,\"m/d/y;@\") &IF(H6=I6,\"\",\" to \" & TEXT(I6,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed",null,{"$f":"IF(G6<>\"\",\"***\",\"\")","v":"***"},"2015-01-11","2016-01-11",{"$f":"IF(AND(A6=\"\",B6=\"\"),\"\",IF(B6=\"\",A6,B6))","v":"Project Completed"},null,null,"MS #412494 DCP Warren","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412494 DCP Warren",401,{"$f":"\"(\"&C6&\") \"&J6&\":  \"&M6&IF(AND(E6=\"\",F6=\"\"),\"\",\" (\")&IF(E6=\"\",\"\",\"\"&TEXT(E6,\"m/d/y;@\"))&IF(OR(F6=E6,E6=\"\",F6=\"\"),\"\",\" to \")&IF(OR(F6=\"\",F6=E6),\"\",TEXT(F6,\"m/d/y;@\"))&IF(AND(E6=\"\",F6=\"\"),\"\",\")\")","v":"() MS #412494 DCP Warren:  Meter Station (1/11/15 to 1/11/16)"},{"$f":"D6&J6&\":  \"&M6&IF(AND(E6=\"\",F6=\"\"),\"\",\"\n\")&IF(E6=\"\",\"\",\"--\"&TEXT(E6,\"m/d/y;@\"))&IF(OR(F6=E6,E6=\"\",F6=\"\"),\"\",\" through \")&IF(OR(F6=\"\",F6=E6),\"\",TEXT(F6,\"m/d/y;@\"))&IF(AND(E6=\"\",F6=\"\"),\"\",\":  \")&N6&\"  \"&P6&IF(Q6=\"\",\"\",\"\n\"&Q6)&IF(G6=\"\",\"\",\"\n***\")&G6&\"\n………………………………\"","v":"***MS #412494 DCP Warren:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412494 DCP Warren\n***Project Completed\n………………………………"},{"$f":"D6&J6&\":  \"&M6&IF(G6=\"\",\"\",\"\n***\")&G6&IF(Q6=\"\",\"\",\"\nThe following meters are available for nominations:\n\")&Q6&\"\n………………………………\"","v":"***MS #412494 DCP Warren:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412494 DCP Warren\n………………………………"}]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412400 King Ranch","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412400 King Ranch",402.1,"() MS #412400 King Ranch:  Meter Station (1/11/15 to 1/11/16)","***MS #412400 King Ranch:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412400 King Ranch\n***Project Completed\n………………………………","***MS #412400 King Ranch:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412400 King Ranch\n………………………………"]
["","Project Completed",null,"***","2015-01-12","2016-01-12","Project Completed",null,null,"MS #410539 Duvak Gas Gathering","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410539 Duvak Gas Gathering",402.1,"() MS #410539 Duvak Gas Gathering:  Meter Station (1/12/15 to 1/12/16)","***MS #410539 Duvak Gas Gathering:  Meter Station\n--1/12/15 through 1/12/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410539 Duvak Gas Gathering\n***Project Completed\n………………………………","***MS #410539 Duvak Gas Gathering:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n410539 Duvak Gas Gathering\n………………………………"]
["","Project Completed",null,"***","2015-01-13","2016-01-13","Project Completed",null,null,"MS #412356 DCP LaGloria","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412356 DCP LaGloria",403.1,"() MS #412356 DCP LaGloria:  Meter Station (1/13/15 to 1/13/16)","***MS #412356 DCP LaGloria:  Meter Station\n--1/13/15 through 1/13/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412356 DCP LaGloria\n***Project Completed\n………………………………","***MS #412356 DCP LaGloria:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412356 DCP LaGloria\n………………………………"]
["","Project Completed",null,"***","2015-01-13","2016-01-13","Project Completed",null,null,"MS #410173 Enterprise LaReforma","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410173 Enterprise LaReforma",406.1,"() MS #410173 Enterprise LaReforma:  Meter Station (1/13/15 to 1/13/16)","***MS #410173 Enterprise LaReforma:  Meter Station\n--1/13/15 through 1/13/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410173 Enterprise LaReforma\n***Project Completed\n………………………………","***MS #410173 Enterprise LaReforma:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n410173 Enterprise LaReforma\n………………………………"]
["","Project Completed",null,"***","2015-01-12","2016-01-12","Project Completed",null,null,"MS #411903 Enterprise El Benito","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","411903 Enterprise El Benito",407.1,"() MS #411903 Enterprise El Benito:  Meter Station (1/12/15 to 1/12/16)","***MS #411903 Enterprise El Benito:  Meter Station\n--1/12/15 through 1/12/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n411903 Enterprise El Benito\n***Project Completed\n………………………………","***MS #411903 Enterprise El Benito:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n411903 Enterprise El Benito\n………………………………"]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412088 Enterprise Sullivan","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412088 Enterprise Sullivan",407.1,"() MS #412088 Enterprise Sullivan:  Meter Station (1/11/15 to 1/11/16)","***MS #412088 Enterprise Sullivan:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412088 Enterprise Sullivan\n***Project Completed\n………………………………","***MS #412088 Enterprise Sullivan:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412088 Enterprise Sullivan\n………………………………"]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412683 HESCO","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412683 HESCO",408.1,"() MS #412683 HESCO:  Meter Station (1/11/15 to 1/11/16)","***MS #412683 HESCO:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412683 HESCO\n***Project Completed\n………………………………","***MS #412683 HESCO:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412683 HESCO\n………………………………"]
[{"$f":"IF(AND(H14<>\"\",I14<>\"\"), \"Date change. Previously scheduled \" & TEXT(H14,\"m/d/y;@\") &IF(H14=I14,\"\",\" to \" & TEXT(I14,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X16-36843",{"$f":"IF(G14<>\"\",\"***\",\"\")","v":"***"},"2016-01-27","2016-01-27","Project Completed",null,null,"Sta. 237",200,5,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,237,"(X16-36843) Sta. 237:  Unit  Maintenance (1/27/16)","***Sta. 237:  Unit  Maintenance\n--1/27/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Sta. 237:  Unit  Maintenance\n***Project Completed\n………………………………"]
[{"$f":"IF(AND(H15<>\"\",I15<>\"\"), \"Date change. Previously scheduled \" & TEXT(H15,\"m/d/y;@\") &IF(H15=I15,\"\",\" to \" & TEXT(I15,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X14-1478563",{"$f":"IF(G15<>\"\",\"***\",\"\")","v":"***"},"2015-11-16","2016-02-12","Project Completed",null,null,"MLV 32-1D to 33-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,32.200000000000003,"(X14-1478563) MLV 32-1D to 33-1:  Hydrotest (11/16/15 to 2/12/16)","***MLV 32-1D to 33-1:  Hydrotest\n--11/16/15 through 2/12/16:  This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***MLV 32-1D to 33-1:  Hydrotest\n***Project Completed\n………………………………"]
[null,"Project Completed","X16-16074",null,"2016-01-18","2016-01-28","Project Completed",null,null,"Station 550","500","1","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,550,"(X16-16074) Station 550:  Station Maintenance (1/18/16 to 1/28/16)","Station 550:  Station Maintenance\n--1/18/16 through 1/28/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","Station 550:  Station Maintenance\n***Project Completed\n………………………………"]
[{"$f":"IF(AND(H17<>\"\",I17<>\"\"), \"Date change. Previously scheduled \" & TEXT(H17,\"m/d/y;@\") &IF(H17=I17,\"\",\" to \" & TEXT(I17,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X16-46202",{"$f":"IF(G17<>\"\",\"***\",\"\")","v":"***"},"2016-02-01","2016-02-07","Project Completed",null,null,"Station 9","100","0","Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.",null,9,"(X16-46202) Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items) (2/1/16 to 2/7/16)","***Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)\n--2/1/16 through 2/7/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\n***Project Completed\n………………………………","***Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)\n***Project Completed\n………………………………"]
["","Project Completed","X15-925633","***","2016-02-09","2016-02-11","Project Completed",null,null,"Sta. 266A",200,6,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,266,"(X15-925633) Sta. 266A:  Unit  Maintenance (2/9/16 to 2/11/16)","***Sta. 266A:  Unit  Maintenance\n--2/9/16 through 2/11/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Sta. 266A:  Unit  Maintenance\n***Project Completed\n………………………………"]
["","Project Completed","X15-929733","***","2016-01-27","2016-02-10","Project Completed",null,null,"MLV 834-1 to 838-1",800,5,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",834.1,"(X15-929733) MLV 834-1 to 838-1:  ILI/Cleaning Pig (1/27/16 to 2/10/16)","***MLV 834-1 to 838-1:  ILI/Cleaning Pig\n--1/27/16 through 2/10/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 834-1 to 838-1:  ILI/Cleaning Pig\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X14-1562506","***","2015-11-02","2016-02-19","Project Completed",null,null,"MLV 5-1 to 6-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410063 ROCHE DEHYDRATION             \n",5.0999999999999996,"(X14-1562506) MLV 5-1 to 6-1:  Hydrotest (11/2/15 to 2/19/16)","***MLV 5-1 to 6-1:  Hydrotest\n--11/2/15 through 2/19/16:  This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410063 ROCHE DEHYDRATION             \n\n***Project Completed\n………………………………","***MLV 5-1 to 6-1:  Hydrotest\n***Project Completed\nThe following meters are available for nominations:\n410063 ROCHE DEHYDRATION             \n\n………………………………"]
["","Project Completed","X14-1562506","***","2015-11-02","2016-02-19","Project Completed",null,null,"MLV 7-1 to 9-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","\n412490 Charro\n421083 Eagle Ford Field Service",5.0999999999999996,"(X14-1562506) MLV 7-1 to 9-1:  Hydrotest (11/2/15 to 2/19/16)","***MLV 7-1 to 9-1:  Hydrotest\n--11/2/15 through 2/19/16:  This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n\n412490 Charro\n421083 Eagle Ford Field Service\n***Project Completed\n………………………………","***MLV 7-1 to 9-1:  Hydrotest\n***Project Completed\nThe following meters are available for nominations:\n\n412490 Charro\n421083 Eagle Ford Field Service\n………………………………"]
["Date change. Previously scheduled 2/18/16 to 2/20/16.","Project Completed","X15-882289","***","2016-02-22","2016-02-24","Project Completed","2016-02-18","2016-02-20","MLV 24-2 to 25-2S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.2,"(X15-882289) MLV 24-2 to 25-2S:  Anomaly Remediation (2/22/16 to 2/24/16)","***MLV 24-2 to 25-2S:  Anomaly Remediation\n--2/22/16 through 2/24/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 24-2 to 25-2S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-925630","***","2016-02-23","2016-02-23","Project Completed",null,null,"WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B)",200,"L","ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,265.10000000000002,"(X15-925630) WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig (2/23/16)","***WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig\n--2/23/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig\n***Project Completed\n………………………………"]
["","Project Completed","X16-23748","***","2016-02-15","2016-02-18","Project Completed",null,null,"MLV 530-3 to 532-3",500,"L","ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,530.29999999999995,"(X16-23748) MLV 530-3 to 532-3:  ILI/Cleaning Pig (2/15/16 to 2/18/16)","***MLV 530-3 to 532-3:  ILI/Cleaning Pig\n--2/15/16 through 2/18/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***MLV 530-3 to 532-3:  ILI/Cleaning Pig\n***Project Completed\n………………………………"]
["","Project Canceled","X16-98720","***","2016-03-06","2016-03-06","Project Canceled",null,null,"Sta. 1",100,0,"Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,1,"(X16-98720) Sta. 1:  Station Maintenance (3/6/16)","***Sta. 1:  Station Maintenance\n--3/6/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Canceled\n………………………………","***Sta. 1:  Station Maintenance\n***Project Canceled\n………………………………"]
["","Project Completed","X14-1562513\nX14-1540661","***","2015-07-01","2016-03-04","Project Completed",null,null,"Station 32","100","0","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,32,"(X14-1562513\nX14-1540661) Station 32:  Station Maintenance (7/1/15 to 3/4/16)","***Station 32:  Station Maintenance\n--7/1/15 through 3/4/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Station 32:  Station Maintenance\n***Project Completed\n………………………………"]
["","Project Canceled","X15-926822","***","2016-06-06","2016-06-11","Project Canceled",null,null,"BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1)",300,6,"Pipe Inspection","This project involves inspecting multiple sites.  We do not anticipate having to do any repairs, however if a repair is needed  there is a potential that the pipe  may require replacement which will require isolation of the pipe.  This may limit throughput and will result in restrictions based on customer nominations.  Customers may experience pressure fluctuations during this timeframe.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",343.1,"(X15-926822) BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection (6/6/16 to 6/11/16)","***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection\n--6/6/16 through 6/11/16:  This project involves inspecting multiple sites.  We do not anticipate having to do any repairs, however if a repair is needed  there is a potential that the pipe  may require replacement which will require isolation of the pipe.  This may limit throughput and will result in restrictions based on customer nominations.  Customers may experience pressure fluctuations during this timeframe.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928271","***","TBD","TBD","Project Canceled",null,null,"MLV 555-1 to 550-1",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.1,"(X15-928271) MLV 555-1 to 550-1:  ILI/Cleaning Pig (TBD)","***MLV 555-1 to 550-1:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-1 to 550-1:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928272","***","TBD","TBD","Project Canceled",null,null,"MLV 555-2 to 550-2",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.20000000000005,"(X15-928272) MLV 555-2 to 550-2:  ILI/Cleaning Pig (TBD)","***MLV 555-2 to 550-2:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-2 to 550-2:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928273","***","TBD","TBD","Project Canceled",null,null,"MLV 555-3 to 552-3",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.29999999999995,"(X15-928273) MLV 555-3 to 552-3:  ILI/Cleaning Pig (TBD)","***MLV 555-3 to 552-3:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-3 to 552-3:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-882281","***","2016-02-24","2016-03-03","Project Completed",null,null,"24-1A to 25-1S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.1,"(X15-882281) 24-1A to 25-1S:  Anomaly Remediation (2/24/16 to 3/3/16)","***24-1A to 25-1S:  Anomaly Remediation\n--2/24/16 through 3/3/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***24-1A to 25-1S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-882291","***","2016-03-03","2016-03-04","Project Completed",null,null,"MLV 24-3 to 25-3S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.3,"(X15-882291) MLV 24-3 to 25-3S:  Anomaly Remediation (3/3/16 to 3/4/16)","***MLV 24-3 to 25-3S:  Anomaly Remediation\n--3/3/16 through 3/4/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 24-3 to 25-3S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X14-1178175","***","2015-06-15","2016-03-31","Project Completed",null,null,"Station 63","100","1","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,63,"(X14-1178175) Station 63:  Station Maintenance (6/15/15 to 3/31/16)","***Station 63:  Station Maintenance\n--6/15/15 through 3/31/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Station 63:  Station Maintenance\n***Project Completed\n………………………………"]
["","Project Cancelled","X15-913224","***","2016-04-16","2016-05-21","Project Cancelled",null,null,"MLV 109-2",100,2,"Pipe Replacement","This project will require taking the pipeline section out of service.   This will limit throughput and will result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",109.2,"(X15-913224) MLV 109-2:  Pipe Replacement (4/16/16 to 5/21/16)","***MLV 109-2:  Pipe Replacement\n--4/16/16 through 5/21/16:  This project will require taking the pipeline section out of service.   This will limit throughput and will result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Cancelled\n………………………………","***MLV 109-2:  Pipe Replacement\n***Project Cancelled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-926830","***","2016-03-07","2016-03-11","Project Completed",null,null,"MLV 400-1 to 408-1",100,0,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.","To Be Determined",400.1,"(X15-926830) MLV 400-1 to 408-1:  ILI/Cleaning Pig (3/7/16 to 3/11/16)","***MLV 400-1 to 408-1:  ILI/Cleaning Pig\n--3/7/16 through 3/11/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 400-1 to 408-1:  ILI/Cleaning Pig\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Cancelled","X16-143836","***","2016-03-28","2016-04-04","Project Cancelled",null,null,"Sta. 409",100,0,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.",null,409,"(X16-143836) Sta. 409:  Unit  Maintenance (3/28/16 to 4/4/16)","***Sta. 409:  Unit  Maintenance\n--3/28/16 through 4/4/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\n***Project Cancelled\n………………………………","***Sta. 409:  Unit  Maintenance\n***Project Cancelled\n………………………………"]
["","Project Cancelled","X15-929680","***","2016-04-18","2016-04-27","Project Cancelled",null,null,"SABINE - KINDER LINE to 822-1",800,"L","Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",822.1,"(X15-929680) SABINE - KINDER LINE to 822-1:  Anomaly Remediation (4/18/16 to 4/27/16)","***SABINE - KINDER LINE to 822-1:  Anomaly Remediation\n--4/18/16 through 4/27/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Cancelled\n………………………………","***SABINE - KINDER LINE to 822-1:  Anomaly Remediation\n***Project Cancelled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]

{"sheet":"Sheet1","index":1,"n_rows":245,"n_cols":24,"rows_kept":245,"cut":false,"hidden":false,"merged":[[2,0,2,14]]}
["Updated ","2022-09-22"]
["Tennessee Gas Pipeline 2022 Pipeline Outage and Maintenance Summary"]
["This is a summary of the current status of all TGP 2022 Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  \nAdditionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
["*** Indicates revision"]
["Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","Location","Leg","Zone","Maintenance Activity","Anticipated Impact","Potential Restriction Level","TOS Potential Restrictions","Meter(s) in Impacted Area","Loc",null,null,null,null,null,null,null,"\\\\houCORP\\TRANS\\TRANSERVICES\\OPPLAN\\COMMON\\Outages\\Outage_DB\\TGP\\Files"]
["X22-925128",null,"2022-10-11","2022-10-12",null,null,null,"Sta 1","100","0","Replace 8\" Blow Off Valves","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,1,null,"Sta 1:  Replace 8\" Blow Off Valves\n--10/11/22 through 10/12/22:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-449826","***","2022-10-08","2022-10-14","Project Change","2022-10-03","2022-10-07","MLV 5-2 and MLV 6-2","100","0","Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,5.2,"--start_date--end_date------------model_loc--","***MLV 5-2 and MLV 6-2:  Anomaly Remediation\n--10/8/22 through 10/14/22:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 10/3/22 to 10/7/22.\n………………………………"]
["X22-449825","***","2022-09-19","2022-10-07","Project Change",null,"2022-09-30","MLV 6-2 and MLV 7-2","100","0","Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,6.2,"----end_date------------model_loc--","***MLV 6-2 and MLV 7-2:  Anomaly Remediation\n--9/19/22 through 10/7/22:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/19/22 to 9/30/22.\n………………………………"]
["X22-449823","***","2022-09-06","2022-09-30","Project Change",null,"2022-09-16","MLV 7-2 and MLV 8-2","100","0","Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,7.2,"----end_date------------model_loc--","***MLV 7-2 and MLV 8-2:  Anomaly Remediation\n--9/6/22 through 9/30/22:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/6/22 to 9/16/22.\n………………………………"]
["X22-843914","***","2022-09-26","2022-10-06","Project Change","2022-09-22","2022-10-01","MLV 8-1 to  MLV 9-1","100","0","High Priority Anomaly - Sleeve","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,8.09,"--start_date--end_date------------model_loc--","***MLV 8-1 to  MLV 9-1:  High Priority Anomaly - Sleeve\n--9/26/22 through 10/6/22:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/22/22 to 10/1/22.\n………………………………"]
["X22-415651","***","2022-07-13","2022-09-23","Project Change",null,"2022-09-21","MLV 8-2 and MLV 9-2S","100","0","Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,8.1999999999999993,"----end_date------------model_loc--","***MLV 8-2 and MLV 9-2S:  Anomaly Remediation\n--7/13/22 through 9/23/22:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 7/13/22 to 9/21/22.\n………………………………"]
["X22-885772",null,"2022-11-01","2022-11-03",null,null,null,"MLV 17-2S to MLV 9-2D","100","0","Cleaning 11/1 - 11/2, MDS 11/3","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed will be shut in as the pig passes.","SOP","Potential out of path restrictions may be at risk.","49803 KMTEJAS/TGP JACKSON (GANADO)",17.2,null,"MLV 17-2S to MLV 9-2D:  Cleaning 11/1 - 11/2, MDS 11/3\n--11/1/22 through 11/3/22:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed will be shut in as the pig passes.  Potential out of path restrictions may be at risk.\n49803 KMTEJAS/TGP JACKSON (GANADO)\n………………………………"]
["X22-571168",null,"2022-11-15","2022-12-31",null,null,null,"MLV 18-3A to MLV 20-3A","100","0","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,18.3,null,"MLV 18-3A to MLV 20-3A:  Pipe Replacement\n--11/15/22 through 12/31/22:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X21-1122071",null,"2022-08-22","2022-11-15",null,null,null,"MLV 18-2A to MLV 20-2A","100","0","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,20.2,null,"MLV 18-2A to MLV 20-2A:  Pipe Replacement\n--8/22/22 through 11/15/22:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-863218",null,"2022-09-19","2022-10-11",null,null,null,"MLVS 24-3","100","0","New Meter Connection - Pinewood TX (PIN 55540)",null,null,null,null,24.3,null,"MLVS 24-3:  New Meter Connection - Pinewood TX (PIN 55540)\n--9/19/22 through 10/11/22:    \n………………………………"]
["X22-595391",null,"2022-11-01","2022-12-01",null,null,null,"MLV 24-3A to MLV 25-3A","100","0","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,24.3,null,"MLV 24-3A to MLV 25-3A:  Pipe Replacement\n--11/1/22 through 12/1/22:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-947470","***","2022-10-17","2022-10-23","Added",null,null,"Sta 25","100","0","Annual Electrical Inspections","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,25,"------","***Sta 25:  Annual Electrical Inspections\n--10/17/22 through 10/23/22:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X22-53703",null,"2022-12-14","2022-12-14",null,null,null,"MLV 25-3 to MLV 24-3","100","0","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,25.3,null,"MLV 25-3 to MLV 24-3:  Maintenance Pig\n--12/14/22:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-621358",null,"2022-12-06","2022-12-23",null,null,null,"MLV 26-1 Relocation","100","0","Highway Widening","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,26.1,null,"MLV 26-1 Relocation:  Highway Widening\n--12/6/22 through 12/23/22:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-815863",null,"2023-01-10","2023-01-27",null,null,null,"MLV 26-2 Relocation","100","0","Highway Widening","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,26.2,null,"MLV 26-2 Relocation:  Highway Widening\n--1/10/23 through 1/27/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-815864",null,"2023-02-14","2023-03-03",null,null,null,"MLV 26-3 Relocation","100","0","Highway Widening","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,26.3,null,"MLV 26-3 Relocation:  Highway Widening\n--2/14/23 through 3/3/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-841249",null,"2022-09-19","2022-09-23",null,null,null,"Sta 32","100","0","Bldg B UPS & Valve Replacements","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,32,null,"Sta 32:  Bldg B UPS & Valve Replacements\n--9/19/22 through 9/23/22:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-28112",null,"2022-04-18","2022-09-30",null,null,null,"Sta 32","100","0","Unit 2B - Foundation grout CAP.","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,32.018000000000001,null,"Sta 32:  Unit 2B - Foundation grout CAP.\n--4/18/22 through 9/30/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-885607",null,"2022-10-25","2022-10-26",null,null,null,"MLV 32-2S to MLV 25-2D","100","0","Mechanical Cleaning 10/26 - 10/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed will be shut in as the pig passes.","SOP","Potential out of path restrictions may be at risk.","47799 NET MEXI/TGP GILLRINA ROAD NUECES\n49861 CCCPL/TGP SINTON SAN PATRICIO\n53608 VCP/TGP VALLEY CROSSING ALLOCATION\n54847 WHISTLEP/TGP WHISTLER RECEIPT NUECE\n411306 ENTRPRSE/TGP AGUA DELCE NUECES\n412062 BANHUB/TGP BANQUETE TRANSPORT NUECE\n412669 ETP/TGP SHOUP NUECES",32.200000000000003,null,"MLV 32-2S to MLV 25-2D:  Mechanical Cleaning 10/26 - 10/26\n--10/25/22 through 10/26/22:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed will be shut in as the pig passes.  Potential out of path restrictions may be at risk.\n47799 NET MEXI/TGP GILLRINA ROAD NUECES\n49861 CCCPL/TGP SINTON SAN PATRICIO\n53608 VCP/TGP VALLEY CROSSING ALLOCATION\n54847 WHISTLEP/TGP WHISTLER RECEIPT NUECE\n411306 ENTRPRSE/TGP AGUA DELCE NUECES\n412062 BANHUB/TGP BANQUETE TRANSPORT NUECE\n412669 ETP/TGP SHOUP NUECES\n………………………………"]
["X22-847398",null,"2022-10-27","2022-10-27",null,null,null,"MLV 32-2S to MLV 25-2D","100","0","AFD re-run 10/27/22","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be limited.","SOP","Potential out of path restrictions may be at risk.","47799 NET MEXI/TGP GILLRINA ROAD NUECES\n49861 CCCPL/TGP SINTON SAN PATRICIO\n53608 VCP/TGP VALLEY CROSSING ALLOCATION\n54847 WHISTLEP/TGP WHISTLER RECEIPT NUECE\n411306 ENTRPRSE/TGP AGUA DELCE NUECES\n412062 BANHUB/TGP BANQUETE TRANSPORT NUECE\n412669 ETP/TGP SHOUP NUECES",32.200000000000003,null,"MLV 32-2S to MLV 25-2D:  AFD re-run 10/27/22\n--10/27/22:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be limited.  Potential out of path restrictions may be at risk.\n47799 NET MEXI/TGP GILLRINA ROAD NUECES\n49861 CCCPL/TGP SINTON SAN PATRICIO\n53608 VCP/TGP VALLEY CROSSING ALLOCATION\n54847 WHISTLEP/TGP WHISTLER RECEIPT NUECE\n411306 ENTRPRSE/TGP AGUA DELCE NUECES\n412062 BANHUB/TGP BANQUETE TRANSPORT NUECE\n412669 ETP/TGP SHOUP NUECES\n………………………………"]
["X22-885674",null,"2022-10-18","2022-10-20",null,null,null,"MLV 36-1TXR to MLV 32-1D","100","0","Mech Cleaning 10/18 - 10/19, MDS 10/20","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,36.1,null,"MLV 36-1TXR to MLV 32-1D:  Mech Cleaning 10/18 - 10/19, MDS 10/20\n--10/18/22 through 10/20/22:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X21-1142115",null,"2022-12-27","2022-12-28",null,null,null,"MLV 36-1LAR to MLV 36-1TXL","100","0","Gauge 12/27/22, Caliper 12/28/22, MFL 12/28/22","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,36.11,null,"MLV 36-1LAR to MLV 36-1TXL:  Gauge 12/27/22, Caliper 12/28/22, MFL 12/28/22\n--12/27/22 through 12/28/22:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-136997","***","2022-06-06","2022-09-17","Completed",null,null,"MLV 41-1A to MLV 42-1","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed below may be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","412809 CRTXLIG/TGP CLEAR LAKE NO. 1: RIP 4",40.1,"------","***MLV 41-1A to MLV 42-1:  Anomaly Remediation\n***Completed\nThe following meters are available for nominations:\n412809 CRTXLIG/TGP CLEAR LAKE NO. 1: RIP 4"]
["X22-825590",null,"2022-08-29","2022-10-07",null,null,null,"MLV 40-4D to MLV 41-4","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,40.4,null,"MLV 40-4D to MLV 41-4:  Anomaly Remediation\n--8/29/22 through 10/7/22:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-581251","***","2022-10-10","2022-10-28","Project Change",null,null,"MLV 41-1 to MLV 41-1A","100","1","Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","412809 CRTXLIG/TGP CLEAR LAKE NO. 1: RIP 4",41.1,"------meters_affected--anticipated_impact--------model_loc--","***MLV 41-1 to MLV 41-1A:  Anomaly Remediation\n--10/10/22 through 10/28/22:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.  Potential out of path restrictions may be at risk.\n412809 CRTXLIG/TGP CLEAR LAKE NO. 1: RIP 4\n***Project Change\n………………………………"]
["X22-581263",null,"2022-10-10","2022-10-20",null,null,null,"MLV 41-3A to MLV 42-3","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,41.3,null,"MLV 41-3A to MLV 42-3:  Anomaly Remediation\n--10/10/22 through 10/20/22:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-825592",null,"2022-08-29","2022-10-07",null,null,null,"MLV 41-4 to MLV 42-4","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,41.4,null,"MLV 41-4 to MLV 42-4:  Anomaly Remediation\n--8/29/22 through 10/7/22:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-825595",null,"2022-10-31","2022-12-09",null,null,null,"MLV 42-4 to MLV 43-4","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,42.4,null,"MLV 42-4 to MLV 43-4:  Anomaly Remediation\n--10/31/22 through 12/9/22:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-114623",null,"2022-10-18","2022-10-24",null,null,null,"Bear Creek Storage","100","1","Shut-in Test","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","460017 STORAGE – BEAR CREEK",43.000999999999998,null,"Bear Creek Storage:  Shut-in Test\n--10/18/22 through 10/24/22:  This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.  Potential out of path restrictions may be at risk.\n460017 STORAGE – BEAR CREEK\n………………………………"]
["X22-825597",null,"2022-10-31","2022-12-09",null,null,null,"MLV 43-4 to MLV 44-4","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,43.4,null,"MLV 43-4 to MLV 44-4:  Anomaly Remediation\n--10/31/22 through 12/9/22:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-581230",null,"2022-09-26","2022-10-07",null,null,null,"MLV 45-3 to MLV 46-3","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,45.3,null,"MLV 45-3 to MLV 46-3:  Anomaly Remediation\n--9/26/22 through 10/7/22:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-790802","***","2022-09-20","2022-09-20","Completed",null,null,"Station 47 West Monroe","100","1","Annual ESD","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,47,"------","***Station 47 West Monroe:  Annual ESD\n***Completed"]
["X22-877922",null,"2022-09-06","2022-10-14",null,null,null,"Sta 47","100","1","Unit 5C - Bearing Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,47.036999999999999,null,"Sta 47:  Unit 5C - Bearing Inspection\n--9/6/22 through 10/14/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-265158",null,"2022-09-26","2022-09-30",null,null,null,"MLV 47-1D TO MLV 54-1S","100","1","Pig Runs - Cleaning/Gauge 9/26, ROSEN Caliper 9/28, ROSEN MFL-A / IMU Tool 9/30","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,47.1,null,"MLV 47-1D TO MLV 54-1S:  Pig Runs - Cleaning/Gauge 9/26, ROSEN Caliper 9/28, ROSEN MFL-A / IMU Tool 9/30\n--9/26/22 through 9/30/22:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-627826",null,"2022-10-03","2022-10-09",null,null,null,"MLV 47-2D to MLV 47-2A","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,47.2,null,"MLV 47-2D to MLV 47-2A:  Anomaly Remediation\n--10/3/22 through 10/9/22:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-623852",null,"2022-10-10","2022-10-16",null,null,null,"MLV 47-2B to MLV 47-2A","100","1","Wrinkle Bend Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,47.2,null,"MLV 47-2B to MLV 47-2A:  Wrinkle Bend Replacement\n--10/10/22 through 10/16/22:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-265156","***","2022-09-12","2022-09-15","Completed",null,null,"MLV 53-3C TO MLV 47-3D","100","1","Pig Runs - Cleaning/Gauge 9/12 - 9/14, BH Combo Tool 9/15","This activity will require operating at controlled flow rates.  Customers may experience pressure fluctuations.  The meter listed will be limited to 125,000 Dths capacity and secondary deliveries are also at risk.","SOP","Potential out of path restrictions may be at risk.",null,47.3,"------","***MLV 53-3C TO MLV 47-3D:  Pig Runs - Cleaning/Gauge 9/12 - 9/14, BH Combo Tool 9/15\n***Completed"]
["X22-158096",null,"2022-11-07","2022-11-13",null,null,null,"MLV 53-1 to MLV 54-1S","100","1","Normal PT","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,53.1,null,"MLV 53-1 to MLV 54-1S:  Normal PT\n--11/7/22 through 11/13/22:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-158098",null,"2022-12-06","2022-12-11",null,null,null,"MLV 53-2 to MLV 54-2S","100","1","Normal PT","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,53.2,null,"MLV 53-2 to MLV 54-2S:  Normal PT\n--12/6/22 through 12/11/22:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-603005",null,"2022-09-19","2022-09-22",null,null,null,"MLV 53-3E TO MLV 54-3S","100","1","Pig Runs - Cleaning/Gauge 9/19 - 9/21, BH Combo Tool 9/22","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,53.3,null,"MLV 53-3E TO MLV 54-3S:  Pig Runs - Cleaning/Gauge 9/19 - 9/21, BH Combo Tool 9/22\n--9/19/22 through 9/22/22:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-792883","***","2022-09-26","2022-10-08","Project Change","2022-10-10","2022-10-22","MLV 53-4 to 53-4A","100","1","Line Lowering","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,53.4,"--start_date--end_date------------model_loc--","***MLV 53-4 to 53-4A:  Line Lowering\n--9/26/22 through 10/8/22:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 10/10/22 to 10/22/22.\n………………………………"]
["X22-134691",null,"2022-10-18","2022-10-20",null,null,null,"Sta 54","100","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,54,null,"Sta 54:  Annual ESD Test\n--10/18/22 through 10/20/22:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-583201",null,"2022-10-19","2022-10-20",null,null,null,"Sta 54","100","1","Unit 1B - GHG Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,54.017000000000003,null,"Sta 54:  Unit 1B - GHG Inspection\n--10/19/22 through 10/20/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-583199",null,"2022-10-10","2022-10-13",null,null,null,"Sta 54","100","1","Unit 4B - GHG Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,54.02,null,"Sta 54:  Unit 4B - GHG Inspection\n--10/10/22 through 10/13/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-583198",null,"2022-10-17","2022-10-18",null,null,null,"Sta 54","100","1","Unit 6B - GHG Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,54.021999999999998,null,"Sta 54:  Unit 6B - GHG Inspection\n--10/17/22 through 10/18/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-198812","***","2022-07-18","2022-10-08","Project Change",null,"2022-10-01","MLV 54-1D to MLV 63-1S","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,54.1,"----end_date------------model_loc--","***MLV 54-1D to MLV 63-1S:  Anomaly Remediation\n--7/18/22 through 10/8/22:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 7/18/22 to 10/1/22.\n………………………………"]
["X22-844101",null,"2022-09-08","2022-10-15",null,null,null,"MLV 67-1 to MLV 68-1","100","1","Wrinkle Bend Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,67.099999999999994,null,"MLV 67-1 to MLV 68-1:  Wrinkle Bend Replacement\n--9/8/22 through 10/15/22:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-332897","***","2022-09-20","2022-09-20","Completed",null,null,"MLV 69-1 to MLV 71-1S","100","1","Pig Run - Cleaning / Gauge 9/20","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,69.099999999999994,"------","***MLV 69-1 to MLV 71-1S:  Pig Run - Cleaning / Gauge 9/20\n***Completed"]
["X22-332989",null,"2022-09-21","2022-09-22",null,null,null,"MLV 69-1 to MLV 71-1S","100","1","Pig Run - Caliper w/mapping 9/21 - 9/22","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,69.099999999999994,null,"MLV 69-1 to MLV 71-1S:  Pig Run - Caliper w/mapping 9/21 - 9/22\n--9/21/22 through 9/22/22:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-333041",null,"2022-09-22","2022-09-23",null,null,null,"MLV 69-1 to MLV 71-1S","100","1","Pig Run - MFL-C 9/22 - 9/23","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,69.099999999999994,null,"MLV 69-1 to MLV 71-1S:  Pig Run - MFL-C 9/22 - 9/23\n--9/22/22 through 9/23/22:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-198847","***","2022-09-30","2022-10-07","Project Change","2022-09-19","2022-09-24","MLVS 69D-100","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,69.099999999999994,"--start_date--end_date------------model_loc--","***MLVS 69D-100:  Anomaly Remediation\n--9/30/22 through 10/7/22:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/19/22 to 9/24/22.\n………………………………"]
["X22-603145",null,"2022-06-15","2022-10-28",null,null,null,"Sta 71","100","1","Unit 4A - Emergent Repair for Base Gasket","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,71.004000000000005,null,"Sta 71:  Unit 4A - Emergent Repair for Base Gasket\n--6/15/22 through 10/28/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X21-1122093",null,"2022-09-01","2022-10-14",null,null,null,"MLV 71-3D to MLV 79-3S","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,71.3,null,"MLV 71-3D to MLV 79-3S:  Anomaly Remediation\n--9/1/22 through 10/14/22:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-409495",null,"2022-10-10","2022-10-21",null,null,null,"MLV 82-3BL","100","1","Make Piggable Trap Modifications","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,82.3,null,"MLV 82-3BL:  Make Piggable Trap Modifications\n--10/10/22 through 10/21/22:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-954556","***","2022-09-26","2022-09-30","Added",null,null,"Sta 87","100","2","Unit 3D - Turbocharger","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,87.052000000000007,"------","***Sta 87:  Unit 3D - Turbocharger\n--9/26/22 through 9/30/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X22-198725","***","2022-06-13","2022-09-30","Project Change",null,"2022-09-20","MLV 87-2 to MLV 96-2","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,87.2,"----end_date------------model_loc--","***MLV 87-2 to MLV 96-2:  Anomaly Remediation\n--6/13/22 through 9/30/22:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 6/13/22 to 9/20/22.\n………………………………"]
["X22-409670",null,"2022-10-24","2022-11-04",null,null,null,"MLV 87-3BR","100","2","Make Piggable Trap Modifications","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,87.3,null,"MLV 87-3BR:  Make Piggable Trap Modifications\n--10/24/22 through 11/4/22:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-703888",null,"2022-11-07","2022-11-18",null,null,null,"MLV 87-3BL","100","2","Make Piggable Trap Modifications","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,87.31,null,"MLV 87-3BL:  Make Piggable Trap Modifications\n--11/7/22 through 11/18/22:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X19-703248",null,"2019-08-01","2022-12-31",null,null,null,"MLV 96-1 to MLV 106-1","100","2","Anomaly Remediation from ILI","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,96.1,null,"MLV 96-1 to MLV 106-1:  Anomaly Remediation from ILI\n--8/1/19 through 12/31/22:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-471443",null,"2022-11-10","2022-11-15",null,null,null,"MLV 96-2 to MLV 97-2","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,96.2,null,"MLV 96-2 to MLV 97-2:  Anomaly Remediation\n--11/10/22 through 11/15/22:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-471441",null,"2022-11-03","2022-12-09",null,null,null,"MLV 97-2 to MLV 98-2","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,97.2,null,"MLV 97-2 to MLV 98-2:  Anomaly Remediation\n--11/3/22 through 12/9/22:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-198829",null,"2022-10-27","2022-11-02",null,null,null,"MLV 101-2D to MLV 102-2R","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,101.2,null,"MLV 101-2D to MLV 102-2R:  Anomaly Remediation\n--10/27/22 through 11/2/22:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-455183",null,"2022-05-04","2022-11-30",null,null,null,"Sta 106","100","2","Unit 8B - Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106.024,null,"Sta 106:  Unit 8B - Overhaul\n--5/4/22 through 11/30/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-309271","***","2022-09-11","2022-09-19","Completed",null,null,"Sta 106","100","2","Unit 1D - Turbine Exchange","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,106.04900000000001,"------","***Sta 106:  Unit 1D - Turbine Exchange\n***Completed"]
["X22-884953","***","2022-09-19","2022-09-21","Completed",null,null,"Sta 106","100","2","Unit 2D - 8k hr Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106.05,"------","***Sta 106:  Unit 2D - 8k hr Inspection\n***Completed"]
["X22-827741","***","2022-09-14","2022-09-14","Completed",null,null,"MLV 106-3 to MLV 96-3","100","2","Pig Runs - MFL 9/14","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,106.32,"------","***MLV 106-3 to MLV 96-3:  Pig Runs - MFL 9/14\n***Completed"]
["X22-258548",null,"2022-09-07","2022-09-28",null,null,null,"MLV 106-4 to MLV 107-4","100","2","Drip Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106.4,null,"MLV 106-4 to MLV 107-4:  Drip Replacement\n--9/7/22 through 9/28/22:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-894741",null,"2022-09-12","2022-09-26",null,null,null,"MLV 107-3 to MLV 109-3","100","2","High Priority Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,107.3,null,"MLV 107-3 to MLV 109-3:  High Priority Anomaly Remediation\n--9/12/22 through 9/26/22:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-894742",null,"2022-09-17","2022-09-30",null,null,null,"MLV 111-3 to MLV 112-3","100","3","High Priority Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,111.3,null,"MLV 111-3 to MLV 112-3:  High Priority Anomaly Remediation\n--9/17/22 through 9/30/22:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-863113","***","2022-09-12","2022-09-23","Project Change",null,"2022-09-17","MLV 112-3A to MLV 113-3","100","2","Class Change","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.","420045 COL GAS/TGP MAVITY KY BOYD",112.3,"----end_date------------model_loc--","***MLV 112-3A to MLV 113-3:  Class Change\n--9/12/22 through 9/23/22:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n420045 COL GAS/TGP MAVITY KY BOYD\n***\nDate Change, Previously scheduled 9/12/22 to 9/17/22.\n………………………………"]
["X22-703725","***","2022-09-12","2022-09-16","Completed",null,null,"Sta 114","100","3","Building C ATS Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,114,"------","***Sta 114:  Building C ATS Maintenance\n***Completed"]
["X22-841039",null,"2022-10-24","2022-10-29",null,null,null,"Sta 114","200","3","Building C BPS Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,114,null,"Sta 114:  Building C BPS Upgrade\n--10/24/22 through 10/29/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X22-603110","***","2022-09-14","2022-09-16","Completed",null,null,"Sta 114","100","3","Building C Substation Maintenance","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,114.033,"------","***Sta 114:  Building C Substation Maintenance\n***Completed"]
["X22-55539",null,"2022-10-25","2022-10-27",null,null,null,"Sta 114","100","3","Unit 1D - Solar 8k Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,114.04949999999999,null,"Sta 114:  Unit 1D - Solar 8k Inspection\n--10/25/22 through 10/27/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X22-55542",null,"2023-01-02","2023-01-04",null,null,null,"Sta 118A","100","3","Solar 8k Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,118.00149999999999,null,"Sta 118A:  Solar 8k Inspection\n--1/2/23 through 1/4/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X22-55554",null,"2022-11-28","2022-11-30",null,null,null,"Sta 119A","100","3","Unit 1A - Solar 8k Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,119.00149999999999,null,"Sta 119A:  Unit 1A - Solar 8k Inspection\n--11/28/22 through 11/30/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X22-788616","***","2022-10-11","2022-10-11","Project Change","2022-09-28","2022-09-28","Sta 200","200","4","UPS Replacement","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,200,"--start_date--end_date------------model_loc--","***Sta 200:  UPS Replacement\n--10/11/22:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/28/22.\n………………………………"]
["X22-863028",null,"2022-09-26","2022-09-30",null,null,null,"Sta 200","200","4","Unit 6A - Annual Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,200.006,null,"Sta 200:  Unit 6A - Annual Inspection\n--9/26/22 through 9/30/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-863047",null,"2022-10-10","2022-10-14",null,null,null,"Sta 200","200","4","Unit 9A - Annual Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,200.00899999999999,null,"Sta 200:  Unit 9A - Annual Inspection\n--10/10/22 through 10/14/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-198885","***","2022-10-08","2022-10-14","Project Change","2022-09-26","2022-09-30","MLV 200-2 to MLV 204-2","200","4","SCCDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,200.2,"--start_date--end_date------------model_loc--","***MLV 200-2 to MLV 204-2:  SCCDA\n--10/8/22 through 10/14/22:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/26/22 to 9/30/22.\n………………………………"]
["X22-198886","***","2022-10-15","2022-10-21","Project Change","2022-10-03","2022-10-07","MLV 200-3 to MLV 200-3A","200","4","SCCDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,200.3,"--start_date--end_date------------model_loc--","***MLV 200-3 to MLV 200-3A:  SCCDA\n--10/15/22 through 10/21/22:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 10/3/22 to 10/7/22.\n………………………………"]
["X22-950495","***","2022-10-03","2022-10-07","Added",null,null,"MLVS 201-3","200","4","Repaint exposed span","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,201.3,"------","***MLVS 201-3:  Repaint exposed span\n--10/3/22 through 10/7/22:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X22-873362",null,"2022-09-19","2022-09-29",null,null,null,"Sta 204","200","4","Unit 4A - Install New Dry Exhaust","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,204.00399999999999,null,"Sta 204:  Unit 4A - Install New Dry Exhaust\n--9/19/22 through 9/29/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-873300","***","2022-09-13","2022-09-15","Completed",null,null,"Sta 204","200","4","Unit 12A - Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,204.012,"------","***Sta 204:  Unit 12A - Crankcase Inspection\n***Completed"]
["X22-455481","***","2022-09-19","2022-09-23","Project Change",null,null,"MLV 208-4 to MLV 209-4","200","4","Install New Meter Tee (REX Big Muskie Guernsey Pin 44423)","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,208.4,"----------mantenance_desc------model_loc--","***MLV 208-4 to MLV 209-4:  Install New Meter Tee (REX Big Muskie Guernsey Pin 44423)\n--9/19/22 through 9/23/22:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***Project Change\n………………………………"]
["X22-706962","***","2022-09-06","2022-09-15","Completed",null,null,"Sta 209","200","4","Unit 7A - Power Cylinder","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209.00700000000001,"------","***Sta 209:  Unit 7A - Power Cylinder\n***Completed"]
["X22-873465",null,"2022-09-19","2022-09-29",null,null,null,"Sta 209","200","4","Unit 12A - Power Cylinder","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209.012,null,"Sta 209:  Unit 12A - Power Cylinder\n--9/19/22 through 9/29/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-894711",null,"2022-10-11","2022-10-11",null,null,null,"MLV 209-1 to MLV 204-1","200","4","Pig Runs - Caliper 10/11","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,209.1,null,"MLV 209-1 to MLV 204-1:  Pig Runs - Caliper 10/11\n--10/11/22:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X22-894713",null,"2022-10-13","2022-10-13",null,null,null,"MLV 209-3 to MLV 204-3","200","4","Pig Runs - Caliper 10/13","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,209.11,null,"MLV 209-3 to MLV 204-3:  Pig Runs - Caliper 10/13\n--10/13/22:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X22-894715","***","2022-10-18","2022-10-18","Project Change",null,null,"MLV 209-4 to MLV 204-4","200","4","Pig Runs - Caliper 10/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be shut in during the project.","SIP","Potential in the path restrictions may be at risk.","44423 REX/TGP BIG MUSKIE GUERNSEY",209.12,"------meters_affected--anticipated_impact--------model_loc--","***MLV 209-4 to MLV 204-4:  Pig Runs - Caliper 10/18\n--10/18/22:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.  Potential in the path restrictions may be at risk.\n44423 REX/TGP BIG MUSKIE GUERNSEY\n***Project Change\n………………………………"]
["X22-286374",null,"2022-08-29","2022-10-15",null,null,null,"MLV 213-1 to MLV 214-1","200","4","SCCDA Investigation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,213.1,null,"MLV 213-1 to MLV 214-1:  SCCDA Investigation\n--8/29/22 through 10/15/22:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-286381",null,"2022-10-10","2022-10-29",null,null,null,"MLV 213-3 to MLV 214-3","200","4","SCCDA Investigation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,213.3,null,"MLV 213-3 to MLV 214-3:  SCCDA Investigation\n--10/10/22 through 10/29/22:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-286383",null,"2022-10-17","2022-10-22",null,null,null,"MLV 213-4 to MLV 214-4","200","4","SCCDA Investigation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,213.4,null,"MLV 213-4 to MLV 214-4:  SCCDA Investigation\n--10/17/22 through 10/22/22:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-950355","***","2022-09-26","2022-09-29","Added",null,null,"Sta 214","200","4","Unit 2A - Head Replacement & Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,214.00200000000001,"------","***Sta 214:  Unit 2A - Head Replacement & Crankcase Inspection\n--9/26/22 through 9/29/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X22-929771",null,"2022-10-03","2022-10-14",null,null,null,"Sta 214","200","4","Unit 13A - Fuel Injection System Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,214.01300000000001,null,"Sta 214:  Unit 13A - Fuel Injection System Upgrade\n--10/3/22 through 10/14/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-790791",null,"2022-10-04","2022-10-04",null,null,null,"MLV 214-1 to MLV 209-1","200","4","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,214.1,null,"MLV 214-1 to MLV 209-1:  Maintenance Pig\n--10/4/22:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-790792","***","2022-09-27","2022-09-27","Project Change",null,null,"MLV 214-4 to MLV 209-4","200","4","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed will be shut-in as the pig passes.","SOP","Potential out of path restrictions may be at risk.","50708 EGTS/TGP PORT WASHINGTON TUSCARAWAS",214.4,"------meters_affected--anticipated_impact--------model_loc--","***MLV 214-4 to MLV 209-4:  Maintenance Pig\n--9/27/22:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed will be shut-in as the pig passes.  Potential out of path restrictions may be at risk.\n50708 EGTS/TGP PORT WASHINGTON TUSCARAWAS\n***Project Change\n………………………………"]
["X22-954683","***","2022-09-26","2022-09-29","Added",null,null,"Sta 219","200","4","Unit 1A - Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,219.001,"------","***Sta 219:  Unit 1A - Engine Inspection\n--9/26/22 through 9/29/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X22-168772",null,"2022-03-14","2022-09-30",null,null,null,"Sta 219","200","4","Unit 13A - Unit Regrout","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,219.00399999999999,null,"Sta 219:  Unit 13A - Unit Regrout\n--3/14/22 through 9/30/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-815774","***","2022-09-12","2022-09-15","Completed",null,null,"Sta 219","200","4","Unit 5A - Crankcase & Anchor Bolt Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,219.005,"------","***Sta 219:  Unit 5A - Crankcase & Anchor Bolt Inspection\n***Completed"]
["X22-698487",null,"2022-10-04","2022-10-04",null,null,null,"MLV 219-1 to MLV 214-1","200","4","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,219.1,null,"MLV 219-1 to MLV 214-1:  Maintenance Pig\n--10/4/22:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-932320","***","2022-09-21","2022-09-21","Completed",null,null,"MLV 219-2 to MLV 220-2","200","4","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,219.2,"------","***MLV 219-2 to MLV 220-2:  Maintenance Pig\n***Completed"]
["X22-698488",null,"2022-10-11","2022-10-11",null,null,null,"MLV 219-2 to MLV 214-2","200","4","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,219.2,null,"MLV 219-2 to MLV 214-2:  Maintenance Pig\n--10/11/22:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-319919",null,"2022-09-19","2022-09-23",null,null,null,"Station 224","200","5","Units 1A - 4A - Protective Device Testing","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,224.001,null,"Station 224:  Units 1A - 4A - Protective Device Testing\n--9/19/22 through 9/23/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-318975",null,"2022-10-10","2022-10-18",null,null,null,"Sta 229","200","5","Unit 1A - 6A - Protective Device Checks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,229.001,null,"Sta 229:  Unit 1A - 6A - Protective Device Checks\n--10/10/22 through 10/18/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-319278","***","2022-09-19","2022-09-20","Completed",null,null,"Station 230C","200","5","Unit 1A - Protective Device Tests","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,230.001,"------","***Station 230C:  Unit 1A - Protective Device Tests\n***Completed"]
["X22-319377","***","2022-09-14","2022-09-15","Completed",null,null,"Station 230C","200","5","Unit 2A - Protective Device Tests","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,230.00200000000001,"------","***Station 230C:  Unit 2A - Protective Device Tests\n***Completed"]
["X22-319493",null,"2022-09-21","2022-09-22",null,null,null,"Station 230C","200","5","Unit 4A - Protective Device Tests","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,230.00399999999999,null,"Station 230C:  Unit 4A - Protective Device Tests\n--9/21/22 through 9/22/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X22-321769",null,"2022-09-19","2022-10-01",null,null,null,"MLV 230B-100","200","5","ECDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,230.1,null,"MLV 230B-100:  ECDA\n--9/19/22 through 10/1/22:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-321676","***","2022-08-22","2022-09-17","Completed",null,null,"MLV 230B-205 to MLV 230B-206","200","5","SCCDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,230.2,"------","***MLV 230B-205 to MLV 230B-206:  SCCDA\n***Completed"]
["X22-126808",null,"2022-09-27","2022-09-27",null,null,null,"Sta 237","200","5","400 Line Filter/Scrubber Change","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,237,null,"Sta 237:  400 Line Filter/Scrubber Change\n--9/27/22:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-126767",null,"2022-10-17","2022-10-17",null,null,null,"Station 237","200","5","Annual Electric Meggering","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,237,null,"Station 237:  Annual Electric Meggering\n--10/17/22:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-224807",null,"2022-10-17","2022-10-21",null,null,null,"Station 237","200","5","Unit 3A - Fuel System Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,237.00299999999999,null,"Station 237:  Unit 3A - Fuel System Upgrade\n--10/17/22 through 10/21/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-224786",null,"2022-10-10","2022-10-14",null,null,null,"Sta 241","200","5","Unit 1A - Fuel System Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,241.001,null,"Sta 241:  Unit 1A - Fuel System Upgrade\n--10/10/22 through 10/14/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-911989",null,"2022-10-04","2022-10-07",null,null,null,"Sta 241","200","5","Unit 2A - Fuel System Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,241.00200000000001,null,"Sta 241:  Unit 2A - Fuel System Upgrade\n--10/4/22 through 10/7/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-305857",null,"2022-10-17","2022-10-21",null,null,null,"Sta 241","200","5","Unit 2A - Alignment","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,241.00200000000001,null,"Sta 241:  Unit 2A - Alignment\n--10/17/22 through 10/21/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-126809",null,"2022-10-17","2022-10-18",null,null,null,"Sta 241","200","5","Unit 1B - 2K Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,241.017,null,"Sta 241:  Unit 1B - 2K Maintenance\n--10/17/22 through 10/18/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-126811",null,"2022-10-19","2022-10-20",null,null,null,"Sta 241","200","5","Unit 2B - 2K Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,241.018,null,"Sta 241:  Unit 2B - 2K Maintenance\n--10/19/22 through 10/20/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-866252","***","2022-08-30","2022-09-30","Project Change",null,"2022-09-16","Sta 245","200","5","Unit 7A - Turbo Charger Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,245.00700000000001,"----end_date------------model_loc--","***Sta 245:  Unit 7A - Turbo Charger Replacement\n--8/30/22 through 9/30/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 8/30/22 to 9/16/22.\n………………………………"]
["X22-940787","***","2022-09-27","2022-09-27","Added",null,null,"MLV 245-1 to MLV 249-1","200","5","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,245.1,"------","***MLV 245-1 to MLV 249-1:  Maintenance Pig\n--9/27/22:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X22-862886",null,"2022-10-17","2022-10-27",null,null,null,"Sta 249","200","5","Unit 1A - Suction/Discharge Bottle Clamp Replacement/Pier","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,249.001,null,"Sta 249:  Unit 1A - Suction/Discharge Bottle Clamp Replacement/Pier\n--10/17/22 through 10/27/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-644078",null,"2022-09-16","2022-09-30",null,null,null,"MLV 249","200","5","Meter Station Maintenance - Wright Meter (Pin 412181)","This project will require the facility outage.  The meter listed below will be shut-in during the project.",null,null,"412181 IROQUOIS/TGP WRIGHT SMS SCHOHARIE",249.2,null,"MLV 249:  Meter Station Maintenance - Wright Meter (Pin 412181)\n--9/16/22 through 9/30/22:  This project will require the facility outage.  The meter listed below will be shut-in during the project.  \n412181 IROQUOIS/TGP WRIGHT SMS SCHOHARIE\n………………………………"]
["X22-574846",null,"2022-10-20","2022-10-20",null,null,null,"Sta 260A Southwick","200","6","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,260,null,"Sta 260A Southwick:  Annual ESD Test\n--10/20/22:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-574817",null,"2022-10-11","2022-10-11",null,null,null,"Station 261 Agawam","200","6","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meters listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420901 BERKPWR/TGP BERKSHIRE POWER SALES H",261,null,"Station 261 Agawam:  Annual ESD Test\n--10/11/22:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meters listed may be shut in during the project.  Potential out of path restrictions may be at risk.\n420901 BERKPWR/TGP BERKSHIRE POWER SALES H\n………………………………"]
["X22-574984",null,"2022-10-12","2022-10-12",null,null,null,"Station 261 Agawam","200","6","EPA Maintenance Repairs","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meters listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420901 BERKPWR/TGP BERKSHIRE POWER SALES H",261,null,"Station 261 Agawam:  EPA Maintenance Repairs\n--10/12/22:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meters listed may be shut in during the project.  Potential out of path restrictions may be at risk.\n420901 BERKPWR/TGP BERKSHIRE POWER SALES H\n………………………………"]
["X22-574824",null,"2022-10-18","2022-10-18",null,null,null,"Sta 264 Charlton","200","6","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,261,null,"Sta 264 Charlton:  Annual ESD Test\n--10/18/22:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-258577",null,"2022-10-04","2022-10-05",null,null,null,"Sta 261","200","6","Unit 4A - Electrical Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be shut in during this project.","SOP","Potential out of path restrictions may be at risk.","420901 BERKPWR/TGP BERKSHIRE POWER SALES H",261.00400000000002,null,"Sta 261:  Unit 4A - Electrical Inspection\n--10/4/22 through 10/5/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be shut in during this project.  Potential out of path restrictions may be at risk.\n420901 BERKPWR/TGP BERKSHIRE POWER SALES H\n………………………………"]
["X22-258582",null,"2022-10-04","2022-10-05",null,null,null,"Sta 264","200","6","Units 1C, 2C - Protective Devices","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,264.03300000000002,null,"Sta 264:  Units 1C, 2C - Protective Devices\n--10/4/22 through 10/5/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-258584",null,"2022-10-06","2022-10-07",null,null,null,"Sta 264","200","6","Units 1C, 2C - Tuning & HMI Installation","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,264.03309999999999,null,"Sta 264:  Units 1C, 2C - Tuning & HMI Installation\n--10/6/22 through 10/7/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-804633",null,"2022-08-22","2022-09-23",null,null,null,"MLV 264-1 to MLV 265-1","200","6","Anomaly Remediation","This project may require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,264.10000000000002,null,"MLV 264-1 to MLV 265-1:  Anomaly Remediation\n--8/22/22 through 9/23/22:  This project may require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-205094",null,"2022-10-01","2022-10-28",null,null,null,"Sta. 265E","200","6","Unit 1A - Turbine Controls Upgrade","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may have lower pressure.","SOP","Potential out of path restrictions may be at risk.","420926 RISEC/TGP FPLE RISE PROVIDENCE",265,null,"Sta. 265E:  Unit 1A - Turbine Controls Upgrade\n--10/1/22 through 10/28/22:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may have lower pressure.  Potential out of path restrictions may be at risk.\n420926 RISEC/TGP FPLE RISE PROVIDENCE\n………………………………"]
["X22-214469","***","2022-09-08","2022-09-17","Completed",null,null,"MLV 265-1 to MLV 266-1","200","6","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,265.10000000000002,"------","***MLV 265-1 to MLV 266-1:  Pipe Replacement\n***Completed"]
["X21-1079446",null,"2022-10-08","2022-10-15",null,null,null,"Sta. 265E","200","6","Fall Shutdown","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may have lower pressure.","SOP","Potential out of path restrictions may be at risk.","420926 RISEC/TGP FPLE RISE PROVIDENCE",265.10000000000002,null,"Sta. 265E:  Fall Shutdown\n--10/8/22 through 10/15/22:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may have lower pressure.  Potential out of path restrictions may be at risk.\n420926 RISEC/TGP FPLE RISE PROVIDENCE\n………………………………"]
["X22-214413","***","2022-09-08","2022-09-17","Completed",null,null,"MLV 266-1 to MLV 267-1","200","6","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,266.10000000000002,"------","***MLV 266-1 to MLV 267-1:  Pipe Replacement\n***Completed"]
["X22-305758","***","2022-09-13","2022-09-16","Completed",null,null,"Sta 307","300","4","Unit 2A - Protective Device Testing","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,307.00200000000001,"------","***Sta 307:  Unit 2A - Protective Device Testing\n***Completed"]
["X22-305756",null,"2022-09-20","2022-09-23",null,null,null,"Sta 307","300","4","Unit 3A - Protective Device Testing","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,307.00299999999999,null,"Sta 307:  Unit 3A - Protective Device Testing\n--9/20/22 through 9/23/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-305755",null,"2022-09-27","2022-09-30",null,null,null,"Sta 307","300","4","Unit 4A - Protective Device Testing","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,307.00400000000002,null,"Sta 307:  Unit 4A - Protective Device Testing\n--9/27/22 through 9/30/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-305754",null,"2022-10-11","2022-10-13",null,null,null,"Sta 307","300","4","Unit 6A - Protective Device Testing","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,307.00599999999997,null,"Sta 307:  Unit 6A - Protective Device Testing\n--10/11/22 through 10/13/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-750865",null,"2022-07-27","2022-12-31",null,null,null,"MLV 307-1 to MLV 313-1","300","4","FORCE MAJEURE - Pressure Reduction","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed below will have capacity limitations.","SIP","Potential in the path restrictions may be at risk.","47743 NFGMIDCL/TGP CLERMONT #2 MC KEAN",309.08999999999997,null,"MLV 307-1 to MLV 313-1:  FORCE MAJEURE - Pressure Reduction\n--7/27/22 through 12/31/22:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed below will have capacity limitations.  Potential in the path restrictions may be at risk.\n47743 NFGMIDCL/TGP CLERMONT #2 MC KEAN\n………………………………"]
["X22-707226",null,"2022-07-13","2022-12-31",null,null,null,"MLV 309-1 to MLV 310-1","300","4","FORCE MAJEURE - Line 1 OOS","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,309.10000000000002,null,"MLV 309-1 to MLV 310-1:  FORCE MAJEURE - Line 1 OOS\n--7/13/22 through 12/31/22:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X22-750827",null,"2022-11-07","2022-11-11",null,null,null,"Ellisburg Storage","300","4","Shut-in Test","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","460012 – DOMINION/TGP ELLISBURG INJECTION PO",312.05,null,"Ellisburg Storage:  Shut-in Test\n--11/7/22 through 11/11/22:  This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.  Potential out of path restrictions may be at risk.\n460012 – DOMINION/TGP ELLISBURG INJECTION PO\n………………………………"]
["X22-837420","***","2022-09-01","2022-09-23","Project Change",null,"2022-09-16","Sta 313","300","4","Ujnit 2B - Automation Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,313.01799999999997,"----end_date------------model_loc--","***Sta 313:  Ujnit 2B - Automation Upgrade\n--9/1/22 through 9/23/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/1/22 to 9/16/22.\n………………………………"]
["X22-847725","***","2022-09-29","2022-09-29","Project Change",null,null,"MLV 313-1 to MLV 307-1","300","4","Cleaning 9/29","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","47743 NFGMIDCL/TGP CLERMONT #2 MC KEAN\n420072 NFG/TGP LAMONT PA ELK\n412808 NFGMIDCL/TGP CLERMONT DEHY: RIP 310\n412805 PA GNRL/TGP WHITE HOLLOW DEHY:RIP 3\n50512 NFG/TGP CROSBY DELIVERY MC KEAN\n420315 UGI UT/TGP PORT ALLEGANY PA MC KEAN\n420831 ARDAGHGR/TGP BALL GLASS SALES MC KE",313.10000000000002,"------meters_affected--anticipated_impact--------model_loc--","***MLV 313-1 to MLV 307-1:  Cleaning 9/29\n--9/29/22:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.  Potential out of path restrictions may be at risk.\n47743 NFGMIDCL/TGP CLERMONT #2 MC KEAN\n420072 NFG/TGP LAMONT PA ELK\n412808 NFGMIDCL/TGP CLERMONT DEHY: RIP 310\n412805 PA GNRL/TGP WHITE HOLLOW DEHY:RIP 3\n50512 NFG/TGP CROSBY DELIVERY MC KEAN\n420315 UGI UT/TGP PORT ALLEGANY PA MC KEAN\n420831 ARDAGHGR/TGP BALL GLASS SALES MC KE\n***Project Change\n………………………………"]
["X22-847726","***","2022-10-04","2022-10-04","Project Change",null,null,"MLV 313-1 to MLV 307-1","300","4","AFD 10/4","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","47743 NFGMIDCL/TGP CLERMONT #2 MC KEAN\n420072 NFG/TGP LAMONT PA ELK\n412808 NFGMIDCL/TGP CLERMONT DEHY: RIP 310\n412805 PA GNRL/TGP WHITE HOLLOW DEHY:RIP 3\n50512 NFG/TGP CROSBY DELIVERY MC KEAN\n420315 UGI UT/TGP PORT ALLEGANY PA MC KEAN\n420831 ARDAGHGR/TGP BALL GLASS SALES MC KE",313.11,"------meters_affected--anticipated_impact--------model_loc--","***MLV 313-1 to MLV 307-1:  AFD 10/4\n--10/4/22:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.  Potential out of path restrictions may be at risk.\n47743 NFGMIDCL/TGP CLERMONT #2 MC KEAN\n420072 NFG/TGP LAMONT PA ELK\n412808 NFGMIDCL/TGP CLERMONT DEHY: RIP 310\n412805 PA GNRL/TGP WHITE HOLLOW DEHY:RIP 3\n50512 NFG/TGP CROSBY DELIVERY MC KEAN\n420315 UGI UT/TGP PORT ALLEGANY PA MC KEAN\n420831 ARDAGHGR/TGP BALL GLASS SALES MC KE\n***Project Change\n………………………………"]
["X22-847727","***","2022-10-06","2022-10-06","Project Change",null,null,"MLV 313-1 to MLV 307-1","300","4","EMAT 10/6","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","47743 NFGMIDCL/TGP CLERMONT #2 MC KEAN\n420072 NFG/TGP LAMONT PA ELK\n412808 NFGMIDCL/TGP CLERMONT DEHY: RIP 310\n412805 PA GNRL/TGP WHITE HOLLOW DEHY:RIP 3\n50512 NFG/TGP CROSBY DELIVERY MC KEAN\n420315 UGI UT/TGP PORT ALLEGANY PA MC KEAN\n420831 ARDAGHGR/TGP BALL GLASS SALES MC KE",313.12,"------meters_affected--anticipated_impact--------model_loc--","***MLV 313-1 to MLV 307-1:  EMAT 10/6\n--10/6/22:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.  Potential out of path restrictions may be at risk.\n47743 NFGMIDCL/TGP CLERMONT #2 MC KEAN\n420072 NFG/TGP LAMONT PA ELK\n412808 NFGMIDCL/TGP CLERMONT DEHY: RIP 310\n412805 PA GNRL/TGP WHITE HOLLOW DEHY:RIP 3\n50512 NFG/TGP CROSBY DELIVERY MC KEAN\n420315 UGI UT/TGP PORT ALLEGANY PA MC KEAN\n420831 ARDAGHGR/TGP BALL GLASS SALES MC KE\n***Project Change\n………………………………"]
["X22-126769","***","2022-09-20","2022-09-20","Completed",null,null,"Sta 405A","300","5","Filter/Scrubber Change","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,313.43,"------","***Sta 405A:  Filter/Scrubber Change\n***Completed"]
["X22-126780","***","2022-09-20","2022-09-20","Completed",null,null,"Sta 313 to Sta 237","300","5","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,313.49,"------","***Sta 313 to Sta 237:  Maintenance Pig\n***Completed"]
["X22-804499","***","2022-10-10","2022-10-11","Project Change","2022-10-03","2022-10-04","Sta 405A","300","5","Unit 1A - Water Wash & 4k Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,313.55,"--start_date--end_date------------model_loc--","***Sta 405A:  Unit 1A - Water Wash & 4k Inspection\n--10/10/22 through 10/11/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 10/3/22 to 10/4/22.\n………………………………"]
["X22-286433",null,"2022-09-13","2022-09-22",null,null,null,"MLVS C313-0611","300","4","Pig Runs (Tethered) - Cleaning / Gauge 9/16, MFL 9/19","This project will require taking the pipeline section out of service which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below may be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","400485 HEBRON STORAGE INJECTION POTTER\n470001 HEBRON STORAGE WITHDRAWAL POTTER",313.61099999999999,null,"MLVS C313-0611:  Pig Runs (Tethered) - Cleaning / Gauge 9/16, MFL 9/19\n--9/13/22 through 9/22/22:  This project will require taking the pipeline section out of service which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below may be shut-in during the project.  Potential out of path restrictions may be at risk.\n400485 HEBRON STORAGE INJECTION POTTER\n470001 HEBRON STORAGE WITHDRAWAL POTTER\n………………………………"]
["X22-286428",null,"2022-09-13","2022-09-23",null,null,null,"MLVS C313-0612","300","4","Pig Runs (Tethered) - Cleaning / Gauge 9/20, MFL 9/21","This project will require taking the pipeline section out of service which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below may be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","400485 HEBRON STORAGE INJECTION POTTER\n470001 HEBRON STORAGE WITHDRAWAL POTTER",313.61200000000002,null,"MLVS C313-0612:  Pig Runs (Tethered) - Cleaning / Gauge 9/20, MFL 9/21\n--9/13/22 through 9/23/22:  This project will require taking the pipeline section out of service which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below may be shut-in during the project.  Potential out of path restrictions may be at risk.\n400485 HEBRON STORAGE INJECTION POTTER\n470001 HEBRON STORAGE WITHDRAWAL POTTER\n………………………………"]
["X22-286396",null,"2022-10-24","2022-11-12",null,null,null,"MLVS C313-0616","300","4","Pipe Replacement","This project will require taking the pipeline section out of service which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below may be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","400485 HEBRON STORAGE INJECTION POTTER\n470001 HEBRON STORAGE WITHDRAWAL POTTER",313.61599999999999,null,"MLVS C313-0616:  Pipe Replacement\n--10/24/22 through 11/12/22:  This project will require taking the pipeline section out of service which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below may be shut-in during the project.  Potential out of path restrictions may be at risk.\n400485 HEBRON STORAGE INJECTION POTTER\n470001 HEBRON STORAGE WITHDRAWAL POTTER\n………………………………"]
["X22-750823",null,"2022-10-31","2022-11-04",null,null,null,"Harrison Storage","300","4","Shut-in Test","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","460004 – DOMINION/TGP HARRISON INJECTION POT",313.8,null,"Harrison Storage:  Shut-in Test\n--10/31/22 through 11/4/22:  This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.  Potential out of path restrictions may be at risk.\n460004 – DOMINION/TGP HARRISON INJECTION POT\n………………………………"]
["X22-305773",null,"2022-09-13","2022-09-22",null,null,null,"Hebron Storage","300","4","Replace Drips","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","400485 HEBRON STORAGE INJECTION POTTER\n470001 HEBRON STORAGE WITHDRAWAL POTTER",313.91000000000003,null,"Hebron Storage:  Replace Drips\n--9/13/22 through 9/22/22:  This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.  Potential out of path restrictions may be at risk.\n400485 HEBRON STORAGE INJECTION POTTER\n470001 HEBRON STORAGE WITHDRAWAL POTTER\n………………………………"]
["X22-685597",null,"2022-09-13","2022-09-22",null,null,null,"Hebron Storage","300","4","313C-100 Valve Replacement","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","400485 HEBRON STORAGE INJECTION POTTER\n470001 HEBRON STORAGE WITHDRAWAL POTTER",313.92,null,"Hebron Storage:  313C-100 Valve Replacement\n--9/13/22 through 9/22/22:  This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.  Potential out of path restrictions may be at risk.\n400485 HEBRON STORAGE INJECTION POTTER\n470001 HEBRON STORAGE WITHDRAWAL POTTER\n………………………………"]
["X22-750826",null,"2022-11-07","2022-11-11",null,null,null,"Hebron Storage","300","4","Shut-in Test","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","400485 HEBRON STORAGE INJECTION POTTER\n470001 HEBRON STORAGE WITHDRAWAL POTTER",313.92,null,"Hebron Storage:  Shut-in Test\n--11/7/22 through 11/11/22:  This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.  Potential out of path restrictions may be at risk.\n400485 HEBRON STORAGE INJECTION POTTER\n470001 HEBRON STORAGE WITHDRAWAL POTTER\n………………………………"]
["X22-305746","***","2022-09-22","2022-09-22","Project Change",null,null,"MLV 319-1 to MLV 321-1","300","4","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412833 REPSOLOG/TGP SILVARA DEHY: RIP 319F\n412835 SEPCO/TGP KATIE DEHY: RIP 319G 101.\n412846 APPLACHA/TGP UDPSHOEMAKER DEHY: RI\n412841 UGI/TGP UDP AUBURN DEHY: RIP 320 1\n412821 ETC NEPL/TGP DIMOCK DEHY: RIP 320J\n412751 WFS/TGP UDP HOP BOTTOM DEHY: RIP 32",319.10000000000002,"------meters_affected--anticipated_impact--------model_loc--","***MLV 319-1 to MLV 321-1:  Maintenance Pig\n--9/22/22:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.  Potential out of path restrictions may be at risk.\n412833 REPSOLOG/TGP SILVARA DEHY: RIP 319F\n412835 SEPCO/TGP KATIE DEHY: RIP 319G 101.\n412846 APPLACHA/TGP UDPSHOEMAKER DEHY: RI\n412841 UGI/TGP UDP AUBURN DEHY: RIP 320 1\n412821 ETC NEPL/TGP DIMOCK DEHY: RIP 320J\n412751 WFS/TGP UDP HOP BOTTOM DEHY: RIP 32\n***Project Change\n………………………………"]
["X22-305745",null,"2022-10-01","2022-10-01",null,null,null,"MLV 319-1 to MLV 317-1","300","4","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,319.10000000000002,null,"MLV 319-1 to MLV 317-1:  Maintenance Pig\n--10/1/22:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-305747","***","2022-09-15","2022-09-15","Completed",null,null,"MLV 319-2 to MLV 321-2","300","4","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,319.2,"------","***MLV 319-2 to MLV 321-2:  Maintenance Pig\n***Completed"]
["X22-305748","***","2022-09-20","2022-09-20","Completed",null,null,"MLV 320-3A to MLV 321-3BR","300","4","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,320.3,"------","***MLV 320-3A to MLV 321-3BR:  Maintenance Pig\n***Completed"]
["X22-404151",null,"2022-10-17","2022-10-24",null,null,null,"Sta 321","300","4","Install New ESD Bottle","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,321,null,"Sta 321:  Install New ESD Bottle\n--10/17/22 through 10/24/22:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-804509",null,"2023-07-24","2023-08-18",null,null,null,"Sta 321","300","4","Turbo Compressor Tie-In","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,321,null,"Sta 321:  Turbo Compressor Tie-In\n--7/24/23 through 8/18/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-815760",null,"2022-10-11","2022-10-12",null,null,null,"Sta. 323A Lackawaxen","300","5","Annual ESD Testing","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,323,null,"Sta. 323A Lackawaxen:  Annual ESD Testing\n--10/11/22 through 10/12/22:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-815761",null,"2022-10-10","2022-10-14",null,null,null,"Sta. 323A","300","5","Unit 1A - 30k Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,323.00099999999998,null,"Sta. 323A:  Unit 1A - 30k Inspection\n--10/10/22 through 10/14/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-485078",null,"2023-09-02","2023-09-12",null,null,null,"MLV 324-1A to MLV 326-1","300","5","Install New Sta 325 Unit","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.",null,324.10000000000002,null,"MLV 324-1A to MLV 326-1:  Install New Sta 325 Unit\n--9/2/23 through 9/12/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be shut in during the project.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-485076",null,"2023-09-02","2023-09-09",null,null,null,"MLV 327-1A to MLV 328-1","300","5","Install New Sta 327","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.",null,327.10000000000002,null,"MLV 327-1A to MLV 328-1:  Install New Sta 327\n--9/2/23 through 9/9/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be shut in during the project.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-485077",null,"2023-09-11","2023-09-18",null,null,null,"MLV 327-2A to MLV 328-2","300","5","Install New Sta 327","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.",null,327.2,null,"MLV 327-2A to MLV 328-2:  Install New Sta 327\n--9/11/23 through 9/18/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be shut in during the project.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-42641",null,"2022-06-01","2022-12-05",null,null,null,"MLVS 332-1","300","6","Meter Station Upgrade (Knollwood Pin 420477)",null,null,null,null,333.1,null,"MLVS 332-1:  Meter Station Upgrade (Knollwood Pin 420477)\n--6/1/22 through 12/5/22:    \n………………………………"]
["X22-866254",null,"2022-09-19","2022-09-23",null,null,null,"MLV 341-1 to MLV 342-1","300","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,341.1,null,"MLV 341-1 to MLV 342-1:  Anomaly Remediation\n--9/19/22 through 9/23/22:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X22-866256",null,"2022-10-10","2022-10-14",null,null,null,"MLV 346-1 to MLV 347-1","300","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,346.1,null,"MLV 346-1 to MLV 347-1:  Anomaly Remediation\n--10/10/22 through 10/14/22:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X22-866258",null,"2022-10-03","2022-10-07",null,null,null,"MLV 347-1 to MLV 348-1","300","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,347.1,null,"MLV 347-1 to MLV 348-1:  Anomaly Remediation\n--10/3/22 through 10/7/22:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X22-866261",null,"2022-10-03","2022-10-07",null,null,null,"MLV 348-1 to MLV 349-1","300","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,348.1,null,"MLV 348-1 to MLV 349-1:  Anomaly Remediation\n--10/3/22 through 10/7/22:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X22-866263",null,"2022-09-26","2022-09-30",null,null,null,"MLV 349-1 to MLV 350-1","300","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,349.1,null,"MLV 349-1 to MLV 350-1:  Anomaly Remediation\n--9/26/22 through 9/30/22:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X22-866264",null,"2022-09-26","2022-09-30",null,null,null,"MLV 350-1 to MLV 351-1","300","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,350.1,null,"MLV 350-1 to MLV 351-1:  Anomaly Remediation\n--9/26/22 through 9/30/22:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X22-771720",null,"2022-10-19","2022-10-19",null,null,null,"MLV 401-1 to MLV 409-1","400","0","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412733 UES/TGP MYRICK BROOKS",401.1,null,"MLV 401-1 to MLV 409-1:  Maintenance Pig\n--10/19/22:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be shut in during the project.  Potential out of path restrictions may be at risk.\n412733 UES/TGP MYRICK BROOKS\n………………………………"]
["X22-771731",null,"2022-10-20","2022-10-20",null,null,null,"MLV 401-2 to MLV 409-2","400","0","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","PIP","Potential in the path restrictions may be at risk.",null,401.2,null,"MLV 401-2 to MLV 409-2:  Maintenance Pig\n--10/20/22:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X22-885455",null,"2022-10-10","2022-10-12",null,null,null,"MLV 406B-101.2 to MLV 406B-102","100","0","Cleaning 10/10, Cleaning/Gauge Run on 10/11, Cleaning 10/12","This activity will require operating at controlled flow rates.  Customers may experience pressure fluctuations.  The meter listed will be limited to 125,000 Dths capacity and secondary deliveries are also at risk.","SOP","Potential out of path restrictions may be at risk.",null,406,null,"MLV 406B-101.2 to MLV 406B-102:  Cleaning 10/10, Cleaning/Gauge Run on 10/11, Cleaning 10/12\n--10/10/22 through 10/12/22:  This activity will require operating at controlled flow rates.  Customers may experience pressure fluctuations.  The meter listed will be limited to 125,000 Dths capacity and secondary deliveries are also at risk.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-843558",null,"2022-10-13","2022-10-13",null,null,null,"MLV 406B-101.2 to MLV 406B-102","400","0","AFD ILI on 10/13","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,406.1,null,"MLV 406B-101.2 to MLV 406B-102:  AFD ILI on 10/13\n--10/13/22:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-404076",null,"2022-09-10","2022-10-18",null,null,null,"MLV-406-2 to MLV-407-2","400","0","Hydro Test","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be shut in during the project.  Meters in this area may experience pressure fluctuations.","PIP","Potential in the path restrictions may be at risk.","412579 TGP/TGP SANTA FE WILDCAT BROOKS",406.2,null,"MLV-406-2 to MLV-407-2:  Hydro Test\n--9/10/22 through 10/18/22:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be shut in during the project.  Meters in this area may experience pressure fluctuations.  Potential in the path restrictions may be at risk.\n412579 TGP/TGP SANTA FE WILDCAT BROOKS\n………………………………"]
["X22-347573",null,"2022-10-05","2022-10-10",null,null,null,"Sta 409A","400","0","Units 1A & 2A - Preventative Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,409.00099999999998,null,"Sta 409A:  Units 1A & 2A - Preventative Maintenance\n--10/5/22 through 10/10/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X22-954554","***","2022-10-10","2022-10-10","Added",null,null,"Sta 409A","400","0","Units 1A & 2A - Unit Inspections","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,409.00110000000001,"------","***Sta 409A:  Units 1A & 2A - Unit Inspections\n--10/10/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X22-603122",null,"2022-12-07","2022-12-20",null,null,null,"Sta 409","100","0","Station Vent Mods & Unit Inspections","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,409.5,null,"Sta 409:  Station Vent Mods & Unit Inspections\n--12/7/22 through 12/20/22:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X22-905691","***","2022-09-20","2022-09-20","Completed",null,null,"Sta. 500C1 Natchitoches","500","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,500,"------","***Sta. 500C1 Natchitoches:  Annual ESD Test\n***Completed"]
["X22-909494",null,"2022-10-24","2022-10-28",null,null,null,"Sta. 500C1 Natchitoches","500","1","Annual Turbine Maintenance & Borescope","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,500,null,"Sta. 500C1 Natchitoches:  Annual Turbine Maintenance & Borescope\n--10/24/22 through 10/28/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-134673",null,"2022-11-08","2022-11-08",null,null,null,"Sta 500-1 to Sta 823 (MLV 507-1)","500","L","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420373 TRNSCO/TGP KINDER LA EXCH (BI 1\n420708 ELIZ NG/TGP GRANT LA SALES ALLEN\n420436 VERNON/TGP PITKIN LA VERNON\n420793 ELIZ NG/TGP J R FRANKS 1 VERNON\n420388 PROVNCAL/TGP PROVENCAL LA NATCHITOC",500.1,null,"Sta 500-1 to Sta 823 (MLV 507-1):  Maintenance Pig\n--11/8/22:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n420373 TRNSCO/TGP KINDER LA EXCH (BI 1\n420708 ELIZ NG/TGP GRANT LA SALES ALLEN\n420436 VERNON/TGP PITKIN LA VERNON\n420793 ELIZ NG/TGP J R FRANKS 1 VERNON\n420388 PROVNCAL/TGP PROVENCAL LA NATCHITOC\n………………………………"]
["X22-134677","***","2022-09-14","2022-09-14","Completed",null,null,"STA 507K to STA 823","800","L","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.","410671 TARGA/TGP UDP LOWRY PLANT DEHY CAME",507,"------","***STA 507K to STA 823:  Maintenance Pig\n***Completed\nThe following meters are available for nominations:\n410671 TARGA/TGP UDP LOWRY PLANT DEHY CAME"]
["X22-134676","***","2022-09-15","2022-09-15","Completed",null,null,"STA 507F to Sta 823","500","L","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.","SOP","Potential out of path restrictions may be at risk.",null,507,"------","***STA 507F to Sta 823:  Maintenance Pig\n***Completed"]
["X22-947451","***","2022-10-03","2022-10-06","Added",null,null,"MLV 507G-1010 MLV 507G-1011","500","L","Pig Runs - Cleaning 10/3, Gauge 10/4, Caliper 10/5, AFD 10/6","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","421080 CABOT/TGP ST MARY CARBON BLACK: DIP\n412594 NAUTILUS/TG GARDEN CITY ST MARY",507,"------","***MLV 507G-1010 MLV 507G-1011:  Pig Runs - Cleaning 10/3, Gauge 10/4, Caliper 10/5, AFD 10/6\n--10/3/22 through 10/6/22:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n421080 CABOT/TGP ST MARY CARBON BLACK: DIP\n412594 NAUTILUS/TG GARDEN CITY ST MARY\n***Added\n………………………………"]
["X22-492555",null,"2022-10-13","2022-10-13",null,null,null,"Sta 823 to MLV 516","500","L","AFD 10/13","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.","SIP","Potential in the path restrictions may be at risk.","412398 JEFFSTOR/TGP JEFFERSON ISLAND IBERI\n420915 CEGS/TGP PORT IBERIA SALES IBERIA\n421056 ACADIAN/TGP INDIAN BAYOU: DIP 510B-\n410907 TRUNKLNE/TGP CENTERVILLE DEHY TRANS\n450105 AMMID SC/TGP QUIVIRA ST MARY\n412594 NAUTILUS/TGP GARDEN CITY ST MARY\n412684 ANR/TGP SHADYSIDE ST MARY\n412889 CONTLRES/TGP LOPEZ ROAD VERMILION",507.2,null,"Sta 823 to MLV 516:  AFD 10/13\n--10/13/22:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.  Potential in the path restrictions may be at risk.\n412398 JEFFSTOR/TGP JEFFERSON ISLAND IBERI\n420915 CEGS/TGP PORT IBERIA SALES IBERIA\n421056 ACADIAN/TGP INDIAN BAYOU: DIP 510B-\n410907 TRUNKLNE/TGP CENTERVILLE DEHY TRANS\n450105 AMMID SC/TGP QUIVIRA ST MARY\n412594 NAUTILUS/TGP GARDEN CITY ST MARY\n412684 ANR/TGP SHADYSIDE ST MARY\n412889 CONTLRES/TGP LOPEZ ROAD VERMILION\n………………………………"]
["X22-703721",null,"2022-11-07","2022-11-16",null,null,null,"MLV 510A-1 to MLV 512-1","500","L","Line Lowering","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","PIP","Potential in the path restrictions may be at risk.","421056 ACADIAN/TGP INDIAN BAYOU: DIP 510B-",510.1,null,"MLV 510A-1 to MLV 512-1:  Line Lowering\n--11/7/22 through 11/16/22:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  Potential in the path restrictions may be at risk.\n421056 ACADIAN/TGP INDIAN BAYOU: DIP 510B-\n………………………………"]
["X22-843618","***","2022-11-07","2022-11-16","Project Change",null,null,"MLV 510-1 to MLV 513-1","500","L","MLV Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed below will be shut-in during the project.","PIP","Potential in the path restrictions may be at risk.","421056  ACADIAN/TGP INDIAN BAYOU: DIP 510B-\n412398  JEFFSTOR/TGP JEFFERSON ISLAND IBERI",510.1,"------meters_affected----------model_loc--","***MLV 510-1 to MLV 513-1:  MLV Replacement\n--11/7/22 through 11/16/22:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed below will be shut-in during the project.  Potential in the path restrictions may be at risk.\n421056  ACADIAN/TGP INDIAN BAYOU: DIP 510B-\n412398  JEFFSTOR/TGP JEFFERSON ISLAND IBERI\n***Project Change\n………………………………"]
["X22-950482","***","2022-10-20","2022-10-20","Added",null,null,"Sta. 527 Port Sulphur","500","L","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,527,"------","***Sta. 527 Port Sulphur:  Annual ESD Test\n--10/20/22:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X22-929648","***","2022-10-11","2022-10-11","Added",null,null,"MLV 527-3 to MLV 529-3","500","L","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,527.29999999999995,"------","***MLV 527-3 to MLV 529-3:  Maintenance Pig\n--10/11/22:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X22-261411",null,"2022-10-18","2022-10-18",null,null,null,"MLV 529-1 to MLV 530-1","500","L","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,529.1,null,"MLV 529-1 to MLV 530-1:  Maintenance Pig\n--10/18/22:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-261413",null,"2022-10-20","2022-10-20",null,null,null,"MLV 529-2 to MLV 530-2","500","L","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,529.20000000000005,null,"MLV 529-2 to MLV 530-2:  Maintenance Pig\n--10/20/22:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-866315",null,"2022-11-15","2022-11-15",null,null,null,"Sta. 534 Purvis","500","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,534,null,"Sta. 534 Purvis:  Annual ESD Test\n--11/15/22:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-806357","***","2022-09-20","2022-09-20","Completed",null,null,"Sta 538 Heidelberg","500","1","Station ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,538,"------","***Sta 538 Heidelberg:  Station ESD Test\n***Completed"]
["X22-863189",null,"2022-10-25","2022-10-26",null,null,null,"MLVS 538-1","500","1","Replace Control Valve & Meter Tube Cleaning","This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","PIP","Potential in the path restrictions may be at risk.","420291 TRNSCO/TGP HEIDELBERG MISSISIPPE JA",538.1,null,"MLVS 538-1:  Replace Control Valve & Meter Tube Cleaning\n--10/25/22 through 10/26/22:  This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.  Potential in the path restrictions may be at risk.\n420291 TRNSCO/TGP HEIDELBERG MISSISIPPE JA\n………………………………"]
["X22-603113",null,"2022-10-18","2022-10-31",null,null,null,"Sta 542","500","1","Vibration / Pipe Mods","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,542,null,"Sta 542:  Vibration / Pipe Mods\n--10/18/22 through 10/31/22:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X22-478168",null,"2022-10-18","2022-10-31",null,null,null,"Sta 542","500","1","Replace Filter Separator Valves and Relief Valves","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,542,null,"Sta 542:  Replace Filter Separator Valves and Relief Valves\n--10/18/22 through 10/31/22:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X22-485553",null,"2022-10-18","2022-10-19",null,null,null,"Sta 542 Dekalb","500","1","2022 Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,542,null,"Sta 542 Dekalb:  2022 Annual ESD Test\n--10/18/22 through 10/19/22:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-477944","***","2022-05-23","2022-12-09","Project Change",null,"2022-10-28","Sta 542","500","1","Unit 2A - Engine and Compressor Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,542.00199999999995,"----end_date------------model_loc--","***Sta 542:  Unit 2A - Engine and Compressor Overhaul\n--5/23/22 through 12/9/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 5/23/22 to 10/28/22.\n………………………………"]
["X22-627723",null,"2022-10-04","2022-10-05",null,null,null,"MLV 542-2 to MLV 543-2","500","1","Casing Removal","This activity will require operating at reduced pressure. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,542.20000000000005,null,"MLV 542-2 to MLV 543-2:  Casing Removal\n--10/4/22 through 10/5/22:  This activity will require operating at reduced pressure. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-478027","***","2022-09-28","2022-10-06","Project Change","2022-09-24","2022-10-02","Sta 546","500","1","Vibration/Pulsation Piping Mods","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,546,"--start_date--end_date------------model_loc--","***Sta 546:  Vibration/Pulsation Piping Mods\n--9/28/22 through 10/6/22:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/24/22 to 10/2/22.\n………………………………"]
["X22-114325",null,"2022-02-01","2022-09-30",null,null,null,"Sta 546","500","1","Unit 7A - Crankshaft","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,546.00699999999995,null,"Sta 546:  Unit 7A - Crankshaft\n--2/1/22 through 9/30/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-929573","***","2022-09-28","2022-10-08","Project Change","2022-09-24","2022-10-04","Sta 546","500","1","Unit 1B - Controls Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,546.01700000000005,"--start_date--end_date------------model_loc--","***Sta 546:  Unit 1B - Controls Upgrade\n--9/28/22 through 10/8/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/24/22 to 10/4/22.\n………………………………"]
["X22-222714",null,"2022-10-08","2022-10-16",null,null,null,"Sta 550","500","1","Vibration / Pipe Mods","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,550,null,"Sta 550:  Vibration / Pipe Mods\n--10/8/22 through 10/16/22:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X22-150480",null,"2022-10-10","2022-10-11",null,null,null,"Sta 550","500","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,550,null,"Sta 550:  Annual ESD Test\n--10/10/22 through 10/11/22:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-829275",null,"2022-10-17","2022-11-19",null,null,null,"Sta 550","500","1","Unit 1A - 4A - Unit Valve Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,550.00099999999998,null,"Sta 550:  Unit 1A - 4A - Unit Valve Replacement\n--10/17/22 through 11/19/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-894744","***","2022-09-13","2022-09-14","Completed",null,null,"Sta 550","500","1","Unit 1B - Building Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,550.01700000000005,"------","***Sta 550:  Unit 1B - Building Upgrade\n***Completed"]
["X22-603151",null,"2022-08-08","2022-12-31",null,null,null,"Sta 555","500","1","Unit 6A - Engine Regrout","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,555.00599999999997,null,"Sta 555:  Unit 6A - Engine Regrout\n--8/8/22 through 12/31/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-238582",null,"2022-10-04","2022-11-07",null,null,null,"MLV 559-1A to MLV 561-1","500","1","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.",null,559.1,null,"MLV 559-1A to MLV 561-1:  Pipe Replacement\n--10/4/22 through 11/7/22:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be shut in during the project.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-238586","***","2022-11-08","2022-12-22","Project Change",null,"2022-12-15","MLV 559-2A to MLV 560-2","500","1","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.",null,559.20000000000005,"----end_date------------model_loc--","***MLV 559-2A to MLV 560-2:  Pipe Replacement\n--11/8/22 through 12/22/22:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be shut in during the project.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 11/8/22 to 12/15/22.\n………………………………"]
["X22-815769",null,"2022-09-19","2022-09-23",null,null,null,"Sta. 563 Joelton","500","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,563,null,"Sta. 563 Joelton:  Annual ESD Test\n--9/19/22 through 9/23/22:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X22-905734",null,"2022-10-17","2022-10-22",null,null,null,"Sta 823","800","L","Automating 500 Line Valve","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,823,null,"Sta 823:  Automating 500 Line Valve\n--10/17/22 through 10/22/22:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-866409",null,"2022-09-06","2022-09-30",null,null,null,"Sta 823","800","L","Unit 4A - Exhaust Manifold & Unloader Valves","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,823.00400000000002,null,"Sta 823:  Unit 4A - Exhaust Manifold & Unloader Valves\n--9/6/22 through 9/30/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-841077","***","2022-10-09","2022-10-19","Project Change","2022-10-10","2022-10-14","Sta 827","800","L","Unit A3 - Unit Exchange","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,827.00300000000004,"--start_date--end_date------------model_loc--","***Sta 827:  Unit A3 - Unit Exchange\n--10/9/22 through 10/19/22:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 10/10/22 to 10/14/22.\n………………………………"]
["X22-137019",null,"2022-10-11","2022-10-11",null,null,null,"Sta 827 to Sta 823","800","L","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","421043 PINE PRA/TGP PINE PRAIRIE NORTH RAP\n412847 ACADIAN/TGP CHENEYVILLE RAPIDES\n412713 HUGHES E/TGP UDP BLACK STONE13 EVAN\n412844 TEXLA/TGP ROY MARTIN GATHERING: RIP\n420296 FORSTHIL/TGP FOREST HILL LA RAPIDES\n420530 GLNMORA/TGP GLENMORA LA EXCH RAPIDE\n421042 ELIZ NG/TGP EVANGELINE SALES EVANGE\n420629 ELIZ NG/TGP OAKDALE DETENTION SALES\n420687 ELIZ NG/TGP ALLEN PARISH PRISON SAL\n420406 ELIZ NG/TGP ELIZABETH LA EMERGENCY\n53483 AIRLIQAT/TGP TIMBERLANE BIOGAS REC",827.1,null,"Sta 827 to Sta 823:  Maintenance Pig\n--10/11/22:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n421043 PINE PRA/TGP PINE PRAIRIE NORTH RAP\n412847 ACADIAN/TGP CHENEYVILLE RAPIDES\n412713 HUGHES E/TGP UDP BLACK STONE13 EVAN\n412844 TEXLA/TGP ROY MARTIN GATHERING: RIP\n420296 FORSTHIL/TGP FOREST HILL LA RAPIDES\n420530 GLNMORA/TGP GLENMORA LA EXCH RAPIDE\n421042 ELIZ NG/TGP EVANGELINE SALES EVANGE\n420629 ELIZ NG/TGP OAKDALE DETENTION SALES\n420687 ELIZ NG/TGP ALLEN PARISH PRISON SAL\n420406 ELIZ NG/TGP ELIZABETH LA EMERGENCY\n53483 AIRLIQAT/TGP TIMBERLANE BIOGAS REC\n………………………………"]
["X22-154269",null,"2023-03-01","2023-03-31",null,null,null,"MLV 828-1 to MLV 829-1","800","L","Make Piggable","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,828.1,null,"MLV 828-1 to MLV 829-1:  Make Piggable\n--3/1/23 through 3/31/23:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-228796",null,"2022-09-19","2022-09-30",null,null,null,"Sta 834","800","1","Unit 3A - Compressor Valves, Poppets, and Springs","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,834.00300000000004,null,"Sta 834:  Unit 3A - Compressor Valves, Poppets, and Springs\n--9/19/22 through 9/30/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-228786",null,"2022-10-03","2022-10-14",null,null,null,"Sta 834","800","1","Unit 6A - Compressor Valves, Poppets, and Springs","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,834.00599999999997,null,"Sta 834:  Unit 6A - Compressor Valves, Poppets, and Springs\n--10/3/22 through 10/14/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-137021",null,"2022-10-11","2022-10-11",null,null,null,"Sta 834 to Sta 827","800","L","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420755 ATMOS TL/TGP LASALLE PARISH NEBO SA\n420447 PELICANG/TGP HARRISONBURG LA CATAHO",834.1,null,"Sta 834 to Sta 827:  Maintenance Pig\n--10/11/22:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n420755 ATMOS TL/TGP LASALLE PARISH NEBO SA\n420447 PELICANG/TGP HARRISONBURG LA CATAHO\n………………………………"]
["X22-415746","***","2022-09-20","2022-09-20","Completed",null,null,"Sta 838 Transylvania","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,838,"------","***Sta 838 Transylvania:  Annual ESD Test\n***Completed"]
["X22-571124",null,"2022-09-08","2022-10-08",null,null,null,"MLV 843-1 to MLV 844-1","800","1","Shallow Pipe Lowering","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed below may be shut-in during the project.","SIP","Potential in the path restrictions may be at risk.","412762 TEX GAS/TGP ISOLA ROAD RIP 834B 101",843.1,null,"MLV 843-1 to MLV 844-1:  Shallow Pipe Lowering\n--9/8/22 through 10/8/22:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed below may be shut-in during the project.  Potential in the path restrictions may be at risk.\n412762 TEX GAS/TGP ISOLA ROAD RIP 834B 101\n………………………………"]
["X22-222600",null,"2022-09-08","2022-10-08",null,null,null,"MLV 844-1 to MLV 845-1","800","1","Shallow Pipe Lowering","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed below may be shut-in during the project.","SIP","Potential in the path restrictions may be at risk.","420211 ATMOS-MS/TGP GREENWOOD MS LEFLORE",844.1,null,"MLV 844-1 to MLV 845-1:  Shallow Pipe Lowering\n--9/8/22 through 10/8/22:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed below may be shut-in during the project.  Potential in the path restrictions may be at risk.\n420211 ATMOS-MS/TGP GREENWOOD MS LEFLORE\n………………………………"]
["X22-150458",null,"2022-10-18","2022-10-19",null,null,null,"Sta 851","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,851,null,"Sta 851:  Annual ESD Test\n--10/18/22 through 10/19/22:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-641035","***","2022-06-24","2022-09-14","Completed",null,null,"Sta 860","800","1","Unit 6A - Turbo Charger","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,860.00599999999997,"------","***Sta 860:  Unit 6A - Turbo Charger\n***Completed"]
["X22-940846","***","2022-06-24","2022-09-23","Added",null,null,"Sta 860","800","1","Unit 6A - Turbo Charger","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,860.00599999999997,"------","***Sta 860:  Unit 6A - Turbo Charger\n--6/24/22 through 9/23/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X22-806319",null,"2022-10-24","2022-10-28",null,null,null,"Sta 860","800","1","Unit 7A - Turbo Charger","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,860.00699999999995,null,"Sta 860:  Unit 7A - Turbo Charger\n--10/24/22 through 10/28/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-750835","***","2022-09-26","2022-09-28","Project Change","2022-09-19","2022-09-21","Sta 860","800","1","Unit 9A - Ignition System","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,860.00900000000001,"--start_date--end_date------------model_loc--","***Sta 860:  Unit 9A - Ignition System\n--9/26/22 through 9/28/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/19/22 to 9/21/22.\n………………………………"]
["X22-750839","***","2022-09-29","2022-10-02","Project Change","2022-09-22","2022-09-25","Sta 860","800","1","Unit 10A - Ignition System","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,860.01,"--start_date--end_date------------model_loc--","***Sta 860:  Unit 10A - Ignition System\n--9/29/22 through 10/2/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/22/22 to 9/25/22.\n………………………………"]
["X22-623818",null,"2022-10-10","2022-10-14",null,null,null,"Sta 860","800","1","Unit 10A - Jacket Water Fan","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,860.01,null,"Sta 860:  Unit 10A - Jacket Water Fan\n--10/10/22 through 10/14/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-623815","***","2022-10-03","2022-11-07","Project Change","2022-09-26","2022-10-31","Sta 860","800","1","Units 1B - Top End Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,860.01700000000005,"--start_date--end_date------------model_loc--","***Sta 860:  Units 1B - Top End Overhaul\n--10/3/22 through 11/7/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/26/22 to 10/31/22.\n………………………………"]
["X22-623820",null,"2022-09-12","2022-09-29",null,null,null,"Sta 860","800","1","Unit 11A - Compressor Rod","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,860.11,null,"Sta 860:  Unit 11A - Compressor Rod\n--9/12/22 through 9/29/22:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-894733",null,"2022-10-11","2022-10-11",null,null,null,"MLV 866-1B to MLV 860-1","800","2","Pig Run - Cleaning / Gauge 10/11","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,866.1,null,"MLV 866-1B to MLV 860-1:  Pig Run - Cleaning / Gauge 10/11\n--10/11/22:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-894734",null,"2022-10-13","2022-10-13",null,null,null,"MLV 866-1B to MLV 860-1","800","2","Pig Run - Hardspot 10/13","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,866.11,null,"MLV 866-1B to MLV 860-1:  Pig Run - Hardspot 10/13\n--10/13/22:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-387850",null,"2022-10-20","2022-10-26",null,null,null,"MLV 871-1 to MLV 872-1","800","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,871.1,null,"MLV 871-1 to MLV 872-1:  Anomaly Remediation\n--10/20/22 through 10/26/22:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X22-404145","***","2022-09-12","2022-10-17","Project Change",null,"2022-09-26","Sta 871A","800","2","Station Automation Upgrade","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meters listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420886 TET/TGP DRY CREEK SALES CASEY",871.5,"----end_date------------model_loc--","***Sta 871A:  Station Automation Upgrade\n--9/12/22 through 10/17/22:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meters listed may be shut in during the project.  Potential out of path restrictions may be at risk.\n420886 TET/TGP DRY CREEK SALES CASEY\n***\nDate Change, Previously scheduled 9/12/22 to 9/26/22.\n………………………………"]
["X22-387848",null,"2022-10-14","2022-10-19",null,null,null,"MLV 872-1 to MLV 873-1","800","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,872.1,null,"MLV 872-1 to MLV 873-1:  Anomaly Remediation\n--10/14/22 through 10/19/22:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X22-387847",null,"2022-10-08","2022-10-13",null,null,null,"MLV 873-1A to MLV 874-1","800","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,873.1,null,"MLV 873-1A to MLV 874-1:  Anomaly Remediation\n--10/8/22 through 10/13/22:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X22-198757",null,"2022-09-21","2022-10-07",null,null,null,"MLV 875-1 to MLV 876-1","800","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,875.1,null,"MLV 875-1 to MLV 876-1:  Anomaly Remediation\n--9/21/22 through 10/7/22:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]

{"sheet":"Sheet2","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}

{"sheet":"Sheet3","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}