{"text_format":"1","workbook":"xlsx","n_sheets":4,"sheets":["Closed","Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":8,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Closed","index":0,"n_rows":37,"n_cols":22,"rows_kept":37,"cut":false,"hidden":true,"merged":[[1,3,1,15],[2,3,2,15],[3,3,3,15]]}
[null,null,null,"Updated ","2016"]
[null,null,null,"Tennessee Gas Pipeline 2015 Pipeline Outage and Maintenance Summary"]
[null,null,null,"This is a summary of the current status of all TGP Winter 2014-2015 Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  Additionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
[null,null,null,"*** Indicates revision"]
["Date Change","Project New/Completed/Closed","Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","Location","Leg","Zone","Maintenance Activity","Anticipated Impact","Potential Restriction Level","TOS Potential Restrictions","Meter(s) in Impacted Area","Customer Notifications","Loc","Email Text","Posting Text","Completion Text"]
[{"$f":"IF(AND(H6<>\"\",I6<>\"\"), \"Date change. Previously scheduled \" & TEXT(H6,\"m/d/y;@\") &IF(H6=I6,\"\",\" to \" & TEXT(I6,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed",null,{"$f":"IF(G6<>\"\",\"***\",\"\")","v":"***"},"2015-01-11","2016-01-11",{"$f":"IF(AND(A6=\"\",B6=\"\"),\"\",IF(B6=\"\",A6,B6))","v":"Project Completed"},null,null,"MS #412494 DCP Warren","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412494 DCP Warren",401,{"$f":"\"(\"&C6&\") \"&J6&\":  \"&M6&IF(AND(E6=\"\",F6=\"\"),\"\",\" (\")&IF(E6=\"\",\"\",\"\"&TEXT(E6,\"m/d/y;@\"))&IF(OR(F6=E6,E6=\"\",F6=\"\"),\"\",\" to \")&IF(OR(F6=\"\",F6=E6),\"\",TEXT(F6,\"m/d/y;@\"))&IF(AND(E6=\"\",F6=\"\"),\"\",\")\")","v":"() MS #412494 DCP Warren:  Meter Station (1/11/15 to 1/11/16)"},{"$f":"D6&J6&\":  \"&M6&IF(AND(E6=\"\",F6=\"\"),\"\",\"\n\")&IF(E6=\"\",\"\",\"--\"&TEXT(E6,\"m/d/y;@\"))&IF(OR(F6=E6,E6=\"\",F6=\"\"),\"\",\" through \")&IF(OR(F6=\"\",F6=E6),\"\",TEXT(F6,\"m/d/y;@\"))&IF(AND(E6=\"\",F6=\"\"),\"\",\":  \")&N6&\"  \"&P6&IF(Q6=\"\",\"\",\"\n\"&Q6)&IF(G6=\"\",\"\",\"\n***\")&G6&\"\n………………………………\"","v":"***MS #412494 DCP Warren:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412494 DCP Warren\n***Project Completed\n………………………………"},{"$f":"D6&J6&\":  \"&M6&IF(G6=\"\",\"\",\"\n***\")&G6&IF(Q6=\"\",\"\",\"\nThe following meters are available for nominations:\n\")&Q6&\"\n………………………………\"","v":"***MS #412494 DCP Warren:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412494 DCP Warren\n………………………………"}]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412400 King Ranch","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412400 King Ranch",402.1,"() MS #412400 King Ranch:  Meter Station (1/11/15 to 1/11/16)","***MS #412400 King Ranch:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412400 King Ranch\n***Project Completed\n………………………………","***MS #412400 King Ranch:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412400 King Ranch\n………………………………"]
["","Project Completed",null,"***","2015-01-12","2016-01-12","Project Completed",null,null,"MS #410539 Duvak Gas Gathering","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410539 Duvak Gas Gathering",402.1,"() MS #410539 Duvak Gas Gathering:  Meter Station (1/12/15 to 1/12/16)","***MS #410539 Duvak Gas Gathering:  Meter Station\n--1/12/15 through 1/12/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410539 Duvak Gas Gathering\n***Project Completed\n………………………………","***MS #410539 Duvak Gas Gathering:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n410539 Duvak Gas Gathering\n………………………………"]
["","Project Completed",null,"***","2015-01-13","2016-01-13","Project Completed",null,null,"MS #412356 DCP LaGloria","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412356 DCP LaGloria",403.1,"() MS #412356 DCP LaGloria:  Meter Station (1/13/15 to 1/13/16)","***MS #412356 DCP LaGloria:  Meter Station\n--1/13/15 through 1/13/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412356 DCP LaGloria\n***Project Completed\n………………………………","***MS #412356 DCP LaGloria:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412356 DCP LaGloria\n………………………………"]
["","Project Completed",null,"***","2015-01-13","2016-01-13","Project Completed",null,null,"MS #410173 Enterprise LaReforma","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410173 Enterprise LaReforma",406.1,"() MS #410173 Enterprise LaReforma:  Meter Station (1/13/15 to 1/13/16)","***MS #410173 Enterprise LaReforma:  Meter Station\n--1/13/15 through 1/13/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410173 Enterprise LaReforma\n***Project Completed\n………………………………","***MS #410173 Enterprise LaReforma:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n410173 Enterprise LaReforma\n………………………………"]
["","Project Completed",null,"***","2015-01-12","2016-01-12","Project Completed",null,null,"MS #411903 Enterprise El Benito","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","411903 Enterprise El Benito",407.1,"() MS #411903 Enterprise El Benito:  Meter Station (1/12/15 to 1/12/16)","***MS #411903 Enterprise El Benito:  Meter Station\n--1/12/15 through 1/12/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n411903 Enterprise El Benito\n***Project Completed\n………………………………","***MS #411903 Enterprise El Benito:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n411903 Enterprise El Benito\n………………………………"]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412088 Enterprise Sullivan","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412088 Enterprise Sullivan",407.1,"() MS #412088 Enterprise Sullivan:  Meter Station (1/11/15 to 1/11/16)","***MS #412088 Enterprise Sullivan:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412088 Enterprise Sullivan\n***Project Completed\n………………………………","***MS #412088 Enterprise Sullivan:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412088 Enterprise Sullivan\n………………………………"]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412683 HESCO","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412683 HESCO",408.1,"() MS #412683 HESCO:  Meter Station (1/11/15 to 1/11/16)","***MS #412683 HESCO:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412683 HESCO\n***Project Completed\n………………………………","***MS #412683 HESCO:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412683 HESCO\n………………………………"]
[{"$f":"IF(AND(H14<>\"\",I14<>\"\"), \"Date change. Previously scheduled \" & TEXT(H14,\"m/d/y;@\") &IF(H14=I14,\"\",\" to \" & TEXT(I14,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X16-36843",{"$f":"IF(G14<>\"\",\"***\",\"\")","v":"***"},"2016-01-27","2016-01-27","Project Completed",null,null,"Sta. 237",200,5,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,237,"(X16-36843) Sta. 237:  Unit  Maintenance (1/27/16)","***Sta. 237:  Unit  Maintenance\n--1/27/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Sta. 237:  Unit  Maintenance\n***Project Completed\n………………………………"]
[{"$f":"IF(AND(H15<>\"\",I15<>\"\"), \"Date change. Previously scheduled \" & TEXT(H15,\"m/d/y;@\") &IF(H15=I15,\"\",\" to \" & TEXT(I15,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X14-1478563",{"$f":"IF(G15<>\"\",\"***\",\"\")","v":"***"},"2015-11-16","2016-02-12","Project Completed",null,null,"MLV 32-1D to 33-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,32.200000000000003,"(X14-1478563) MLV 32-1D to 33-1:  Hydrotest (11/16/15 to 2/12/16)","***MLV 32-1D to 33-1:  Hydrotest\n--11/16/15 through 2/12/16:  This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***MLV 32-1D to 33-1:  Hydrotest\n***Project Completed\n………………………………"]
[null,"Project Completed","X16-16074",null,"2016-01-18","2016-01-28","Project Completed",null,null,"Station 550","500","1","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,550,"(X16-16074) Station 550:  Station Maintenance (1/18/16 to 1/28/16)","Station 550:  Station Maintenance\n--1/18/16 through 1/28/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","Station 550:  Station Maintenance\n***Project Completed\n………………………………"]
[{"$f":"IF(AND(H17<>\"\",I17<>\"\"), \"Date change. Previously scheduled \" & TEXT(H17,\"m/d/y;@\") &IF(H17=I17,\"\",\" to \" & TEXT(I17,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X16-46202",{"$f":"IF(G17<>\"\",\"***\",\"\")","v":"***"},"2016-02-01","2016-02-07","Project Completed",null,null,"Station 9","100","0","Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.",null,9,"(X16-46202) Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items) (2/1/16 to 2/7/16)","***Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)\n--2/1/16 through 2/7/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\n***Project Completed\n………………………………","***Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)\n***Project Completed\n………………………………"]
["","Project Completed","X15-925633","***","2016-02-09","2016-02-11","Project Completed",null,null,"Sta. 266A",200,6,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,266,"(X15-925633) Sta. 266A:  Unit  Maintenance (2/9/16 to 2/11/16)","***Sta. 266A:  Unit  Maintenance\n--2/9/16 through 2/11/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Sta. 266A:  Unit  Maintenance\n***Project Completed\n………………………………"]
["","Project Completed","X15-929733","***","2016-01-27","2016-02-10","Project Completed",null,null,"MLV 834-1 to 838-1",800,5,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",834.1,"(X15-929733) MLV 834-1 to 838-1:  ILI/Cleaning Pig (1/27/16 to 2/10/16)","***MLV 834-1 to 838-1:  ILI/Cleaning Pig\n--1/27/16 through 2/10/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 834-1 to 838-1:  ILI/Cleaning Pig\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X14-1562506","***","2015-11-02","2016-02-19","Project Completed",null,null,"MLV 5-1 to 6-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410063 ROCHE DEHYDRATION             \n",5.0999999999999996,"(X14-1562506) MLV 5-1 to 6-1:  Hydrotest (11/2/15 to 2/19/16)","***MLV 5-1 to 6-1:  Hydrotest\n--11/2/15 through 2/19/16:  This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410063 ROCHE DEHYDRATION             \n\n***Project Completed\n………………………………","***MLV 5-1 to 6-1:  Hydrotest\n***Project Completed\nThe following meters are available for nominations:\n410063 ROCHE DEHYDRATION             \n\n………………………………"]
["","Project Completed","X14-1562506","***","2015-11-02","2016-02-19","Project Completed",null,null,"MLV 7-1 to 9-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","\n412490 Charro\n421083 Eagle Ford Field Service",5.0999999999999996,"(X14-1562506) MLV 7-1 to 9-1:  Hydrotest (11/2/15 to 2/19/16)","***MLV 7-1 to 9-1:  Hydrotest\n--11/2/15 through 2/19/16:  This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n\n412490 Charro\n421083 Eagle Ford Field Service\n***Project Completed\n………………………………","***MLV 7-1 to 9-1:  Hydrotest\n***Project Completed\nThe following meters are available for nominations:\n\n412490 Charro\n421083 Eagle Ford Field Service\n………………………………"]
["Date change. Previously scheduled 2/18/16 to 2/20/16.","Project Completed","X15-882289","***","2016-02-22","2016-02-24","Project Completed","2016-02-18","2016-02-20","MLV 24-2 to 25-2S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.2,"(X15-882289) MLV 24-2 to 25-2S:  Anomaly Remediation (2/22/16 to 2/24/16)","***MLV 24-2 to 25-2S:  Anomaly Remediation\n--2/22/16 through 2/24/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 24-2 to 25-2S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-925630","***","2016-02-23","2016-02-23","Project Completed",null,null,"WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B)",200,"L","ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,265.10000000000002,"(X15-925630) WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig (2/23/16)","***WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig\n--2/23/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig\n***Project Completed\n………………………………"]
["","Project Completed","X16-23748","***","2016-02-15","2016-02-18","Project Completed",null,null,"MLV 530-3 to 532-3",500,"L","ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,530.29999999999995,"(X16-23748) MLV 530-3 to 532-3:  ILI/Cleaning Pig (2/15/16 to 2/18/16)","***MLV 530-3 to 532-3:  ILI/Cleaning Pig\n--2/15/16 through 2/18/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***MLV 530-3 to 532-3:  ILI/Cleaning Pig\n***Project Completed\n………………………………"]
["","Project Canceled","X16-98720","***","2016-03-06","2016-03-06","Project Canceled",null,null,"Sta. 1",100,0,"Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,1,"(X16-98720) Sta. 1:  Station Maintenance (3/6/16)","***Sta. 1:  Station Maintenance\n--3/6/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Canceled\n………………………………","***Sta. 1:  Station Maintenance\n***Project Canceled\n………………………………"]
["","Project Completed","X14-1562513\nX14-1540661","***","2015-07-01","2016-03-04","Project Completed",null,null,"Station 32","100","0","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,32,"(X14-1562513\nX14-1540661) Station 32:  Station Maintenance (7/1/15 to 3/4/16)","***Station 32:  Station Maintenance\n--7/1/15 through 3/4/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Station 32:  Station Maintenance\n***Project Completed\n………………………………"]
["","Project Canceled","X15-926822","***","2016-06-06","2016-06-11","Project Canceled",null,null,"BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1)",300,6,"Pipe Inspection","This project involves inspecting multiple sites.  We do not anticipate having to do any repairs, however if a repair is needed  there is a potential that the pipe  may require replacement which will require isolation of the pipe.  This may limit throughput and will result in restrictions based on customer nominations.  Customers may experience pressure fluctuations during this timeframe.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",343.1,"(X15-926822) BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection (6/6/16 to 6/11/16)","***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection\n--6/6/16 through 6/11/16:  This project involves inspecting multiple sites.  We do not anticipate having to do any repairs, however if a repair is needed  there is a potential that the pipe  may require replacement which will require isolation of the pipe.  This may limit throughput and will result in restrictions based on customer nominations.  Customers may experience pressure fluctuations during this timeframe.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928271","***","TBD","TBD","Project Canceled",null,null,"MLV 555-1 to 550-1",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.1,"(X15-928271) MLV 555-1 to 550-1:  ILI/Cleaning Pig (TBD)","***MLV 555-1 to 550-1:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-1 to 550-1:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928272","***","TBD","TBD","Project Canceled",null,null,"MLV 555-2 to 550-2",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.20000000000005,"(X15-928272) MLV 555-2 to 550-2:  ILI/Cleaning Pig (TBD)","***MLV 555-2 to 550-2:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-2 to 550-2:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928273","***","TBD","TBD","Project Canceled",null,null,"MLV 555-3 to 552-3",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.29999999999995,"(X15-928273) MLV 555-3 to 552-3:  ILI/Cleaning Pig (TBD)","***MLV 555-3 to 552-3:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-3 to 552-3:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-882281","***","2016-02-24","2016-03-03","Project Completed",null,null,"24-1A to 25-1S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.1,"(X15-882281) 24-1A to 25-1S:  Anomaly Remediation (2/24/16 to 3/3/16)","***24-1A to 25-1S:  Anomaly Remediation\n--2/24/16 through 3/3/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***24-1A to 25-1S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-882291","***","2016-03-03","2016-03-04","Project Completed",null,null,"MLV 24-3 to 25-3S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.3,"(X15-882291) MLV 24-3 to 25-3S:  Anomaly Remediation (3/3/16 to 3/4/16)","***MLV 24-3 to 25-3S:  Anomaly Remediation\n--3/3/16 through 3/4/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 24-3 to 25-3S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X14-1178175","***","2015-06-15","2016-03-31","Project Completed",null,null,"Station 63","100","1","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,63,"(X14-1178175) Station 63:  Station Maintenance (6/15/15 to 3/31/16)","***Station 63:  Station Maintenance\n--6/15/15 through 3/31/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Station 63:  Station Maintenance\n***Project Completed\n………………………………"]
["","Project Cancelled","X15-913224","***","2016-04-16","2016-05-21","Project Cancelled",null,null,"MLV 109-2",100,2,"Pipe Replacement","This project will require taking the pipeline section out of service.   This will limit throughput and will result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",109.2,"(X15-913224) MLV 109-2:  Pipe Replacement (4/16/16 to 5/21/16)","***MLV 109-2:  Pipe Replacement\n--4/16/16 through 5/21/16:  This project will require taking the pipeline section out of service.   This will limit throughput and will result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Cancelled\n………………………………","***MLV 109-2:  Pipe Replacement\n***Project Cancelled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-926830","***","2016-03-07","2016-03-11","Project Completed",null,null,"MLV 400-1 to 408-1",100,0,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.","To Be Determined",400.1,"(X15-926830) MLV 400-1 to 408-1:  ILI/Cleaning Pig (3/7/16 to 3/11/16)","***MLV 400-1 to 408-1:  ILI/Cleaning Pig\n--3/7/16 through 3/11/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 400-1 to 408-1:  ILI/Cleaning Pig\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Cancelled","X16-143836","***","2016-03-28","2016-04-04","Project Cancelled",null,null,"Sta. 409",100,0,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.",null,409,"(X16-143836) Sta. 409:  Unit  Maintenance (3/28/16 to 4/4/16)","***Sta. 409:  Unit  Maintenance\n--3/28/16 through 4/4/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\n***Project Cancelled\n………………………………","***Sta. 409:  Unit  Maintenance\n***Project Cancelled\n………………………………"]
["","Project Cancelled","X15-929680","***","2016-04-18","2016-04-27","Project Cancelled",null,null,"SABINE - KINDER LINE to 822-1",800,"L","Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",822.1,"(X15-929680) SABINE - KINDER LINE to 822-1:  Anomaly Remediation (4/18/16 to 4/27/16)","***SABINE - KINDER LINE to 822-1:  Anomaly Remediation\n--4/18/16 through 4/27/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Cancelled\n………………………………","***SABINE - KINDER LINE to 822-1:  Anomaly Remediation\n***Project Cancelled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]

{"sheet":"Sheet1","index":1,"n_rows":355,"n_cols":24,"rows_kept":355,"cut":false,"hidden":false,"merged":[[2,0,2,14]]}
["Updated ","2023-02-02"]
["Tennessee Gas Pipeline 2022 Pipeline Outage and Maintenance Summary"]
["This is a summary of the current status of all TGP 2022 Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  \nAdditionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
["*** Indicates revision"]
["Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","Location","Leg","Zone","Maintenance Activity","Anticipated Impact","Potential Restriction Level","TOS Potential Restrictions","Meter(s) in Impacted Area","Loc",null,null,null,null,null,null,null,"\\\\houCORP\\TRANS\\TRANSERVICES\\OPPLAN\\COMMON\\Outages\\Outage_DB\\TGP\\Files"]
["X23-120798","***","2023-03-29","2023-03-30","Added",null,null,"Sta 1 Agua Dulce","100","0","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,1,"------","***Sta 1 Agua Dulce:  Annual ESD Test\n--3/29/23 through 3/30/23:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***Added\n………………………………"]
["X23-100682","***","2023-02-25","2023-02-26","Added",null,null,"MLV 1-2BL to MLV 1-2A","100","0","Hot Tap Meter (Whistler)","This project will require reducing the pipeline section pressure which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","54847 WHISTLEP/TGP WHISTLER RECEIPT NUECE",1.2,"------","***MLV 1-2BL to MLV 1-2A:  Hot Tap Meter (Whistler)\n--2/25/23 through 2/26/23:  This project will require reducing the pipeline section pressure which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be shut in during the project.  Potential out of path restrictions may be at risk.\n54847 WHISTLEP/TGP WHISTLER RECEIPT NUECE\n***Added\n………………………………"]
["X23-71257",null,"2023-04-24","2023-05-19",null,null,null,"MLV 1-2A to MLV 2-2","100","0","Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in for the duration of the project.","SOP","Potential out of path restrictions may be at risk.","412196 ENLINK/TGP NORTH BRAYTON DEHY NUECE",1.2,null,"MLV 1-2A to MLV 2-2:  Anomaly Remediation\n--4/24/23 through 5/19/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in for the duration of the project.  Potential out of path restrictions may be at risk.\n412196 ENLINK/TGP NORTH BRAYTON DEHY NUECE\n………………………………"]
["X23-60661",null,"2023-05-22","2023-06-02",null,null,null,"MLV 1-2BL to MLV 1-2A","100","0","Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in for the duration of the project.","SOP","Potential out of path restrictions may be at risk.","412196 ENLINK/TGP NORTH BRAYTON DEHY NUECE\n412062 BANHUB/TGP BANQUETE TRANSPORT NUECE\n412669 ETP/TGP SHOUP NUECES\n412270 LOBO/TGP UDP TRANSAMERICAN INTERCON\n54847 WHISTLEP/TGP WHISTLER RECEIPT NUECE",1.2,null,"MLV 1-2BL to MLV 1-2A:  Anomaly Remediation\n--5/22/23 through 6/2/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in for the duration of the project.  Potential out of path restrictions may be at risk.\n412196 ENLINK/TGP NORTH BRAYTON DEHY NUECE\n412062 BANHUB/TGP BANQUETE TRANSPORT NUECE\n412669 ETP/TGP SHOUP NUECES\n412270 LOBO/TGP UDP TRANSAMERICAN INTERCON\n54847 WHISTLEP/TGP WHISTLER RECEIPT NUECE\n………………………………"]
["X23-60660",null,"2023-04-03","2023-04-21",null,null,null,"MLV 2-2 to MLV 3-2","100","0","Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in for the duration of the project.","SOP","Potential out of path restrictions may be at risk.","412603 MAGNUS/TGP WILDCAT WELDER HEIRS 5 S",2.2000000000000002,null,"MLV 2-2 to MLV 3-2:  Anomaly Remediation\n--4/3/23 through 4/21/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in for the duration of the project.  Potential out of path restrictions may be at risk.\n412603 MAGNUS/TGP WILDCAT WELDER HEIRS 5 S\n………………………………"]
["X23-60659",null,"2023-03-20","2023-03-31",null,null,null,"MLV 3-2 to MLV 3-2A","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,3.2,null,"MLV 3-2 to MLV 3-2A:  Anomaly Remediation\n--3/20/23 through 3/31/23:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-40691",null,"2023-01-10","2023-02-03",null,null,null,"MLV 4-2 to MLV 5-2","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,4.2,null,"MLV 4-2 to MLV 5-2:  Anomaly Remediation\n--1/10/23 through 2/3/23:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-60658",null,"2023-02-13","2023-03-17",null,null,null,"MLV 4-2 to MLV 5-2","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,4.2,null,"MLV 4-2 to MLV 5-2:  Anomaly Remediation\n--2/13/23 through 3/17/23:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-113753","***","2023-08-07","2023-08-11","Added",null,null,"MLV 9-1D TO MLV 17-1S","100","0","Pig Runs - Chemical Cleaning 8/07 to 8/11","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412066 DCP OPER/TGP INEX INTERCONNECT DEHY\n420185 COKINOS/TGP OTTIS FARM TX JACKSON\n420159 COKINOS/TGP MCCOLLOCH SPENCER FARM\n412533 CRIMEXPL/TGP RAUN NO 1 WHARTON\n420470 COKINOS/TGP RAS FARM TEXAS WHARTON\n420183 /TGP KRENEK FARM TX WHARTON\n412523 UES/TGP WILDCAT RASMUSSEN 1 R\n412723 PATTERSN/TGP HILL WHARTON\n412795 VAR/TGP WEST CLIFFORD DEHY: RIP 321\n412261 CRIMEXPL/TGP RASMUSSN 1 DEHY WHAR\n420442 COKINOS/TGP RASMUSSEN FARM TX WHART\n412655 GCENGY/TGP MUELLER WHARTON\n420466 COKINOS/TGP HOLT FARM TX WHARTON\n420160 COKINOS/TGP CARRIERE FARM TEXAS WHA\n400454 KEM ENER/TGP EGYPT NORTH WEST DEHY",9.1,"------","***MLV 9-1D TO MLV 17-1S:  Pig Runs - Chemical Cleaning 8/07 to 8/11\n--8/7/23 through 8/11/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n412066 DCP OPER/TGP INEX INTERCONNECT DEHY\n420185 COKINOS/TGP OTTIS FARM TX JACKSON\n420159 COKINOS/TGP MCCOLLOCH SPENCER FARM\n412533 CRIMEXPL/TGP RAUN NO 1 WHARTON\n420470 COKINOS/TGP RAS FARM TEXAS WHARTON\n420183 /TGP KRENEK FARM TX WHARTON\n412523 UES/TGP WILDCAT RASMUSSEN 1 R\n412723 PATTERSN/TGP HILL WHARTON\n412795 VAR/TGP WEST CLIFFORD DEHY: RIP 321\n412261 CRIMEXPL/TGP RASMUSSN 1 DEHY WHAR\n420442 COKINOS/TGP RASMUSSEN FARM TX WHART\n412655 GCENGY/TGP MUELLER WHARTON\n420466 COKINOS/TGP HOLT FARM TX WHARTON\n420160 COKINOS/TGP CARRIERE FARM TEXAS WHA\n400454 KEM ENER/TGP EGYPT NORTH WEST DEHY\n***Added\n………………………………"]
["X23-113754","***","2023-08-11","2023-08-11","Added",null,null,"MLV 9-1D TO MLV 17-1S","100","0","Pig Runs - Gauge 8/11","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412066 DCP OPER/TGP INEX INTERCONNECT DEHY\n420185 COKINOS/TGP OTTIS FARM TX JACKSON\n420159 COKINOS/TGP MCCOLLOCH SPENCER FARM\n412533 CRIMEXPL/TGP RAUN NO 1 WHARTON\n420470 COKINOS/TGP RAS FARM TEXAS WHARTON\n420183 /TGP KRENEK FARM TX WHARTON\n412523 UES/TGP WILDCAT RASMUSSEN 1 R\n412723 PATTERSN/TGP HILL WHARTON\n412795 VAR/TGP WEST CLIFFORD DEHY: RIP 321\n412261 CRIMEXPL/TGP RASMUSSN 1 DEHY WHAR\n420442 COKINOS/TGP RASMUSSEN FARM TX WHART\n412655 GCENGY/TGP MUELLER WHARTON\n420466 COKINOS/TGP HOLT FARM TX WHARTON\n420160 COKINOS/TGP CARRIERE FARM TEXAS WHA\n400454 KEM ENER/TGP EGYPT NORTH WEST DEHY",9.11,"------","***MLV 9-1D TO MLV 17-1S:  Pig Runs - Gauge 8/11\n--8/11/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n412066 DCP OPER/TGP INEX INTERCONNECT DEHY\n420185 COKINOS/TGP OTTIS FARM TX JACKSON\n420159 COKINOS/TGP MCCOLLOCH SPENCER FARM\n412533 CRIMEXPL/TGP RAUN NO 1 WHARTON\n420470 COKINOS/TGP RAS FARM TEXAS WHARTON\n420183 /TGP KRENEK FARM TX WHARTON\n412523 UES/TGP WILDCAT RASMUSSEN 1 R\n412723 PATTERSN/TGP HILL WHARTON\n412795 VAR/TGP WEST CLIFFORD DEHY: RIP 321\n412261 CRIMEXPL/TGP RASMUSSN 1 DEHY WHAR\n420442 COKINOS/TGP RASMUSSEN FARM TX WHART\n412655 GCENGY/TGP MUELLER WHARTON\n420466 COKINOS/TGP HOLT FARM TX WHARTON\n420160 COKINOS/TGP CARRIERE FARM TEXAS WHA\n400454 KEM ENER/TGP EGYPT NORTH WEST DEHY\n***Added\n………………………………"]
["X23-113756","***","2023-08-15","2023-08-15","Added",null,null,"MLV 9-1D TO MLV 17-1S","100","0","Pig Runs - MFL-C 8/15","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412066 DCP OPER/TGP INEX INTERCONNECT DEHY\n420185 COKINOS/TGP OTTIS FARM TX JACKSON\n420159 COKINOS/TGP MCCOLLOCH SPENCER FARM\n412533 CRIMEXPL/TGP RAUN NO 1 WHARTON\n420470 COKINOS/TGP RAS FARM TEXAS WHARTON\n420183 /TGP KRENEK FARM TX WHARTON\n412523 UES/TGP WILDCAT RASMUSSEN 1 R\n412723 PATTERSN/TGP HILL WHARTON\n412795 VAR/TGP WEST CLIFFORD DEHY: RIP 321\n412261 CRIMEXPL/TGP RASMUSSN 1 DEHY WHAR\n420442 COKINOS/TGP RASMUSSEN FARM TX WHART\n412655 GCENGY/TGP MUELLER WHARTON\n420466 COKINOS/TGP HOLT FARM TX WHARTON\n420160 COKINOS/TGP CARRIERE FARM TEXAS WHA\n400454 KEM ENER/TGP EGYPT NORTH WEST DEHY",9.1199999999999992,"------","***MLV 9-1D TO MLV 17-1S:  Pig Runs - MFL-C 8/15\n--8/15/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n412066 DCP OPER/TGP INEX INTERCONNECT DEHY\n420185 COKINOS/TGP OTTIS FARM TX JACKSON\n420159 COKINOS/TGP MCCOLLOCH SPENCER FARM\n412533 CRIMEXPL/TGP RAUN NO 1 WHARTON\n420470 COKINOS/TGP RAS FARM TEXAS WHARTON\n420183 /TGP KRENEK FARM TX WHARTON\n412523 UES/TGP WILDCAT RASMUSSEN 1 R\n412723 PATTERSN/TGP HILL WHARTON\n412795 VAR/TGP WEST CLIFFORD DEHY: RIP 321\n412261 CRIMEXPL/TGP RASMUSSN 1 DEHY WHAR\n420442 COKINOS/TGP RASMUSSEN FARM TX WHART\n412655 GCENGY/TGP MUELLER WHARTON\n420466 COKINOS/TGP HOLT FARM TX WHARTON\n420160 COKINOS/TGP CARRIERE FARM TEXAS WHA\n400454 KEM ENER/TGP EGYPT NORTH WEST DEHY\n***Added\n………………………………"]
["X23-113762","***","2023-08-17","2023-08-17","Added",null,null,"MLV 9-1D TO MLV 17-1S","100","0","Pig Runs - EMAT 8/17","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412066 DCP OPER/TGP INEX INTERCONNECT DEHY\n420185 COKINOS/TGP OTTIS FARM TX JACKSON\n420159 COKINOS/TGP MCCOLLOCH SPENCER FARM\n412533 CRIMEXPL/TGP RAUN NO 1 WHARTON\n420470 COKINOS/TGP RAS FARM TEXAS WHARTON\n420183 /TGP KRENEK FARM TX WHARTON\n412523 UES/TGP WILDCAT RASMUSSEN 1 R\n412723 PATTERSN/TGP HILL WHARTON\n412795 VAR/TGP WEST CLIFFORD DEHY: RIP 321\n412261 CRIMEXPL/TGP RASMUSSN 1 DEHY WHAR\n420442 COKINOS/TGP RASMUSSEN FARM TX WHART\n412655 GCENGY/TGP MUELLER WHARTON\n420466 COKINOS/TGP HOLT FARM TX WHARTON\n420160 COKINOS/TGP CARRIERE FARM TEXAS WHA\n400454 KEM ENER/TGP EGYPT NORTH WEST DEHY",9.1300000000000008,"------","***MLV 9-1D TO MLV 17-1S:  Pig Runs - EMAT 8/17\n--8/17/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n412066 DCP OPER/TGP INEX INTERCONNECT DEHY\n420185 COKINOS/TGP OTTIS FARM TX JACKSON\n420159 COKINOS/TGP MCCOLLOCH SPENCER FARM\n412533 CRIMEXPL/TGP RAUN NO 1 WHARTON\n420470 COKINOS/TGP RAS FARM TEXAS WHARTON\n420183 /TGP KRENEK FARM TX WHARTON\n412523 UES/TGP WILDCAT RASMUSSEN 1 R\n412723 PATTERSN/TGP HILL WHARTON\n412795 VAR/TGP WEST CLIFFORD DEHY: RIP 321\n412261 CRIMEXPL/TGP RASMUSSN 1 DEHY WHAR\n420442 COKINOS/TGP RASMUSSEN FARM TX WHART\n412655 GCENGY/TGP MUELLER WHARTON\n420466 COKINOS/TGP HOLT FARM TX WHARTON\n420160 COKINOS/TGP CARRIERE FARM TEXAS WHA\n400454 KEM ENER/TGP EGYPT NORTH WEST DEHY\n***Added\n………………………………"]
["X23-113764","***","2023-08-22","2023-08-22","Added",null,null,"MLV 9-1D TO MLV 17-1S","100","0","Pig Runs - DEF 8/22","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412066 DCP OPER/TGP INEX INTERCONNECT DEHY\n420185 COKINOS/TGP OTTIS FARM TX JACKSON\n420159 COKINOS/TGP MCCOLLOCH SPENCER FARM\n412533 CRIMEXPL/TGP RAUN NO 1 WHARTON\n420470 COKINOS/TGP RAS FARM TEXAS WHARTON\n420183 /TGP KRENEK FARM TX WHARTON\n412523 UES/TGP WILDCAT RASMUSSEN 1 R\n412723 PATTERSN/TGP HILL WHARTON\n412795 VAR/TGP WEST CLIFFORD DEHY: RIP 321\n412261 CRIMEXPL/TGP RASMUSSN 1 DEHY WHAR\n420442 COKINOS/TGP RASMUSSEN FARM TX WHART\n412655 GCENGY/TGP MUELLER WHARTON\n420466 COKINOS/TGP HOLT FARM TX WHARTON\n420160 COKINOS/TGP CARRIERE FARM TEXAS WHA\n400454 KEM ENER/TGP EGYPT NORTH WEST DEHY",9.14,"------","***MLV 9-1D TO MLV 17-1S:  Pig Runs - DEF 8/22\n--8/22/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n412066 DCP OPER/TGP INEX INTERCONNECT DEHY\n420185 COKINOS/TGP OTTIS FARM TX JACKSON\n420159 COKINOS/TGP MCCOLLOCH SPENCER FARM\n412533 CRIMEXPL/TGP RAUN NO 1 WHARTON\n420470 COKINOS/TGP RAS FARM TEXAS WHARTON\n420183 /TGP KRENEK FARM TX WHARTON\n412523 UES/TGP WILDCAT RASMUSSEN 1 R\n412723 PATTERSN/TGP HILL WHARTON\n412795 VAR/TGP WEST CLIFFORD DEHY: RIP 321\n412261 CRIMEXPL/TGP RASMUSSN 1 DEHY WHAR\n420442 COKINOS/TGP RASMUSSEN FARM TX WHART\n412655 GCENGY/TGP MUELLER WHARTON\n420466 COKINOS/TGP HOLT FARM TX WHARTON\n420160 COKINOS/TGP CARRIERE FARM TEXAS WHA\n400454 KEM ENER/TGP EGYPT NORTH WEST DEHY\n***Added\n………………………………"]
["X23-113765","***","2023-08-24","2023-08-24","Added",null,null,"MLV 9-1D TO MLV 17-1S","100","0","Pig Runs - MFL-S 8/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412066 DCP OPER/TGP INEX INTERCONNECT DEHY\n420185 COKINOS/TGP OTTIS FARM TX JACKSON\n420159 COKINOS/TGP MCCOLLOCH SPENCER FARM\n412533 CRIMEXPL/TGP RAUN NO 1 WHARTON\n420470 COKINOS/TGP RAS FARM TEXAS WHARTON\n420183 /TGP KRENEK FARM TX WHARTON\n412523 UES/TGP WILDCAT RASMUSSEN 1 R\n412723 PATTERSN/TGP HILL WHARTON\n412795 VAR/TGP WEST CLIFFORD DEHY: RIP 321\n412261 CRIMEXPL/TGP RASMUSSN 1 DEHY WHAR\n420442 COKINOS/TGP RASMUSSEN FARM TX WHART\n412655 GCENGY/TGP MUELLER WHARTON\n420466 COKINOS/TGP HOLT FARM TX WHARTON\n420160 COKINOS/TGP CARRIERE FARM TEXAS WHA\n400454 KEM ENER/TGP EGYPT NORTH WEST DEHY",9.15,"------","***MLV 9-1D TO MLV 17-1S:  Pig Runs - MFL-S 8/24\n--8/24/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n412066 DCP OPER/TGP INEX INTERCONNECT DEHY\n420185 COKINOS/TGP OTTIS FARM TX JACKSON\n420159 COKINOS/TGP MCCOLLOCH SPENCER FARM\n412533 CRIMEXPL/TGP RAUN NO 1 WHARTON\n420470 COKINOS/TGP RAS FARM TEXAS WHARTON\n420183 /TGP KRENEK FARM TX WHARTON\n412523 UES/TGP WILDCAT RASMUSSEN 1 R\n412723 PATTERSN/TGP HILL WHARTON\n412795 VAR/TGP WEST CLIFFORD DEHY: RIP 321\n412261 CRIMEXPL/TGP RASMUSSN 1 DEHY WHAR\n420442 COKINOS/TGP RASMUSSEN FARM TX WHART\n412655 GCENGY/TGP MUELLER WHARTON\n420466 COKINOS/TGP HOLT FARM TX WHARTON\n420160 COKINOS/TGP CARRIERE FARM TEXAS WHA\n400454 KEM ENER/TGP EGYPT NORTH WEST DEHY\n***Added\n………………………………"]
["X23-40746",null,"2023-04-11","2023-04-11",null,null,null,"MLV 5-2 to MLV 9-2S","100","0","Pig Run - Cleaning 4/11/23","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,9.1999999999999993,null,"MLV 5-2 to MLV 9-2S:  Pig Run - Cleaning 4/11/23\n--4/11/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-30089",null,"2023-04-13","2023-04-13",null,null,null,"MLV 5-2 to MLV 9-2S","100","0","Pig Run - Caliper 4/13/23","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,9.2100000000000009,null,"MLV 5-2 to MLV 9-2S:  Pig Run - Caliper 4/13/23\n--4/13/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-40750",null,"2023-06-13","2023-06-13",null,null,null,"MLV 9-3S to MLV 4-3","100","0","Pig Run - Cleaning 6/13/23","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,9.3000000000000007,null,"MLV 9-3S to MLV 4-3:  Pig Run - Cleaning 6/13/23\n--6/13/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-30090",null,"2023-06-14","2023-06-14",null,null,null,"MLV 9-3S to MLV 4-3","100","0","Pig Run - AFD 6/14/23","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,9.31,null,"MLV 9-3S to MLV 4-3:  Pig Run - AFD 6/14/23\n--6/14/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-113644","***","2023-02-28","2023-03-02","Added",null,null,"MLV 15N-101.1R TO MLV 15N-102L","100","0","Pig Runs - Cleaning 2/28 to 3/02","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412046 BURLGTON/TGP MCFARLAND DEHY WHARTON\n412099 LASERGTH/TGP UDP JONES CREEK OTELL\n411929 TRNSCO/TGP WHARTON COUNTY TIE IN W",15.1,"------","***MLV 15N-101.1R TO MLV 15N-102L:  Pig Runs - Cleaning 2/28 to 3/02\n--2/28/23 through 3/2/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n412046 BURLGTON/TGP MCFARLAND DEHY WHARTON\n412099 LASERGTH/TGP UDP JONES CREEK OTELL\n411929 TRNSCO/TGP WHARTON COUNTY TIE IN W\n***Added\n………………………………"]
["X23-113646","***","2023-03-03","2023-03-03","Added",null,null,"MLV 15N-101.1R TO MLV 15N-102L","100","0","Pig Runs - Gauge 3/03","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412046 BURLGTON/TGP MCFARLAND DEHY WHARTON\n412099 LASERGTH/TGP UDP JONES CREEK OTELL\n411929 TRNSCO/TGP WHARTON COUNTY TIE IN W",15.11,"------","***MLV 15N-101.1R TO MLV 15N-102L:  Pig Runs - Gauge 3/03\n--3/3/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n412046 BURLGTON/TGP MCFARLAND DEHY WHARTON\n412099 LASERGTH/TGP UDP JONES CREEK OTELL\n411929 TRNSCO/TGP WHARTON COUNTY TIE IN W\n***Added\n………………………………"]
["X23-113647","***","2023-03-09","2023-03-09","Added",null,null,"MLV 15N-101.1R TO MLV 15N-102L","100","0","Pig Runs - CLP / MFL-A / IMU 3/09","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412046 BURLGTON/TGP MCFARLAND DEHY WHARTON\n412099 LASERGTH/TGP UDP JONES CREEK OTELL\n411929 TRNSCO/TGP WHARTON COUNTY TIE IN W",15.12,"------","***MLV 15N-101.1R TO MLV 15N-102L:  Pig Runs - CLP / MFL-A / IMU 3/09\n--3/9/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n412046 BURLGTON/TGP MCFARLAND DEHY WHARTON\n412099 LASERGTH/TGP UDP JONES CREEK OTELL\n411929 TRNSCO/TGP WHARTON COUNTY TIE IN W\n***Added\n………………………………"]
["X23-62075","***","2023-01-19","2023-02-09","Project Change",null,"2023-02-03","Sta 17","100","0","Unit 2C - Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,17.033999999999999,"----end_date------------model_loc--","***Sta 17:  Unit 2C - Engine Inspection\n--1/19/23 through 2/9/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 1/19/23 to 2/3/23.\n………………………………"]
["X23-113649","***","2023-05-22","2023-05-26","Added",null,null,"MLV 17-1D TO MLV 20-1A","100","0","Pig Runs - Chemical Cleaning 5/22 to 5/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420167 COKINOS/TGP WOODS FARM TX FORT BEND",17.100000000000001,"------","***MLV 17-1D TO MLV 20-1A:  Pig Runs - Chemical Cleaning 5/22 to 5/26\n--5/22/23 through 5/26/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n420167 COKINOS/TGP WOODS FARM TX FORT BEND\n***Added\n………………………………"]
["X23-113659","***","2023-05-26","2023-05-26","Added",null,null,"MLV 17-1D TO MLV 20-1A","100","0","Pig Runs - Gauge 5/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420167 COKINOS/TGP WOODS FARM TX FORT BEND",17.11,"------","***MLV 17-1D TO MLV 20-1A:  Pig Runs - Gauge 5/26\n--5/26/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n420167 COKINOS/TGP WOODS FARM TX FORT BEND\n***Added\n………………………………"]
["X23-113660","***","2023-05-30","2023-05-30","Added",null,null,"MLV 17-1D TO MLV 20-1A","100","0","Pig Runs - MFL-C 5/30","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420167 COKINOS/TGP WOODS FARM TX FORT BEND",17.12,"------","***MLV 17-1D TO MLV 20-1A:  Pig Runs - MFL-C 5/30\n--5/30/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n420167 COKINOS/TGP WOODS FARM TX FORT BEND\n***Added\n………………………………"]
["X23-113676","***","2023-06-01","2023-06-01","Added",null,null,"MLV 17-1D TO MLV 20-1A","100","0","Pig Runs - EMAT 6/01","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420167 COKINOS/TGP WOODS FARM TX FORT BEND",17.13,"------","***MLV 17-1D TO MLV 20-1A:  Pig Runs - EMAT 6/01\n--6/1/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n420167 COKINOS/TGP WOODS FARM TX FORT BEND\n***Added\n………………………………"]
["X23-113689","***","2023-06-17","2023-06-17","Added",null,null,"MLV 17-3D TO MLV 20-3A","100","0","Pig Runs - EMAT 6/17","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","421085 SYMMETRY/TGP PEDERSON ROAD WALLER",17.14,"------","***MLV 17-3D TO MLV 20-3A:  Pig Runs - EMAT 6/17\n--6/17/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n421085 SYMMETRY/TGP PEDERSON ROAD WALLER\n***Added\n………………………………"]
["X23-113682","***","2023-05-08","2023-05-12","Added",null,null,"MLV 17-3D TO MLV 20-3A","100","0","Pig Runs - Chemical Cleaning 5/08 to 5/12","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","421085 SYMMETRY/TGP PEDERSON ROAD WALLER",17.3,"------","***MLV 17-3D TO MLV 20-3A:  Pig Runs - Chemical Cleaning 5/08 to 5/12\n--5/8/23 through 5/12/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n421085 SYMMETRY/TGP PEDERSON ROAD WALLER\n***Added\n………………………………"]
["X23-113686","***","2023-05-12","2023-05-12","Added",null,null,"MLV 17-3D TO MLV 20-3A","100","0","Pig Runs - Gauge Pig 5/12","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","421085 SYMMETRY/TGP PEDERSON ROAD WALLER",17.309999999999999,"------","***MLV 17-3D TO MLV 20-3A:  Pig Runs - Gauge Pig 5/12\n--5/12/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n421085 SYMMETRY/TGP PEDERSON ROAD WALLER\n***Added\n………………………………"]
["X23-113687","***","2023-05-16","2023-05-16","Added",null,null,"MLV 17-3D TO MLV 20-3A","100","0","Pig Runs - MFL-C 5/16","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","421085 SYMMETRY/TGP PEDERSON ROAD WALLER",17.32,"------","***MLV 17-3D TO MLV 20-3A:  Pig Runs - MFL-C 5/16\n--5/16/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n421085 SYMMETRY/TGP PEDERSON ROAD WALLER\n***Added\n………………………………"]
["X22-571168","***","2022-11-18","2023-01-26","Completed",null,null,"MLV 18-3A to MLV 20-3A","100","0","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in for the duration of the project.","SOP","Potential out of path restrictions may be at risk.","412271 KTY STTR/TGP KATY INTERCONNECT WALL\n421085 SYMMETRY/TGP PEDERSON ROAD WALLER",18.3,"------","***MLV 18-3A to MLV 20-3A:  Pipe Replacement\n***Completed\nThe following meters are available for nominations:\n412271 KTY STTR/TGP KATY INTERCONNECT WALL\n421085 SYMMETRY/TGP PEDERSON ROAD WALLER"]
["X23-69752",null,"2023-08-01","2023-08-15",null,null,null,"MLV 19-1 TO MLV 19-1A","100","0","Pressure Weld Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,19.100000000000001,null,"MLV 19-1 TO MLV 19-1A:  Pressure Weld Replacement\n--8/1/23 through 8/15/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-69754",null,"2023-08-15","2023-08-31",null,null,null,"MLV 19-2 TO MLV 19-2A","100","6","Pressure Weld Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,19.2,null,"MLV 19-2 TO MLV 19-2A:  Pressure Weld Replacement\n--8/15/23 through 8/31/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-69739",null,"2023-03-01","2023-03-31",null,null,null,"MLV 20-1 TO MLV 20-1A","100","0","Pressure Weld Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,20.100000000000001,null,"MLV 20-1 TO MLV 20-1A:  Pressure Weld Replacement\n--3/1/23 through 3/31/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-113692","***","2023-04-04","2023-04-06","Added",null,null,"MLV 20-1A TO MLV 24-1A","100","0","Pig Runs - Cleaning 4/04 to 4/06","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412009 LASERGTH/TGP UDP JONES CREEK OTELL\n412788 CP-UGC/TGP MOSSY OAKS: RIP 22N 101.\n411584 VAR/TGP NORTH ROTHERWOOD DEHY HARRI \n410320 ATMOS-MS/TGP SHUQUALAK MS NOXUBEE\n412638 WILMAR/TGP IMPERIAL OAKS DEHY MONTG",20.100000000000001,"------","***MLV 20-1A TO MLV 24-1A:  Pig Runs - Cleaning 4/04 to 4/06\n--4/4/23 through 4/6/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n412009 LASERGTH/TGP UDP JONES CREEK OTELL\n412788 CP-UGC/TGP MOSSY OAKS: RIP 22N 101.\n411584 VAR/TGP NORTH ROTHERWOOD DEHY HARRI \n410320 ATMOS-MS/TGP SHUQUALAK MS NOXUBEE\n412638 WILMAR/TGP IMPERIAL OAKS DEHY MONTG\n***Added\n………………………………"]
["X23-113696","***","2023-04-07","2023-04-07","Added",null,null,"MLV 20-1A TO MLV 24-1A","100","0","Pig Runs - Gauge Pig 4/07","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412009 LASERGTH/TGP UDP JONES CREEK OTELL\n412788 CP-UGC/TGP MOSSY OAKS: RIP 22N 101.\n411584 VAR/TGP NORTH ROTHERWOOD DEHY HARRI \n410320 ATMOS-MS/TGP SHUQUALAK MS NOXUBEE\n412638 WILMAR/TGP IMPERIAL OAKS DEHY MONTG",20.11,"------","***MLV 20-1A TO MLV 24-1A:  Pig Runs - Gauge Pig 4/07\n--4/7/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n412009 LASERGTH/TGP UDP JONES CREEK OTELL\n412788 CP-UGC/TGP MOSSY OAKS: RIP 22N 101.\n411584 VAR/TGP NORTH ROTHERWOOD DEHY HARRI \n410320 ATMOS-MS/TGP SHUQUALAK MS NOXUBEE\n412638 WILMAR/TGP IMPERIAL OAKS DEHY MONTG\n***Added\n………………………………"]
["X23-113697","***","2023-04-11","2023-04-11","Added",null,null,"MLV 20-1A TO MLV 24-1A","100","0","Pig Runs - CLP / MFL-A / IMU 4/11","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412009 LASERGTH/TGP UDP JONES CREEK OTELL\n412788 CP-UGC/TGP MOSSY OAKS: RIP 22N 101.\n411584 VAR/TGP NORTH ROTHERWOOD DEHY HARRI \n410320 ATMOS-MS/TGP SHUQUALAK MS NOXUBEE\n412638 WILMAR/TGP IMPERIAL OAKS DEHY MONTG",20.12,"------","***MLV 20-1A TO MLV 24-1A:  Pig Runs - CLP / MFL-A / IMU 4/11\n--4/11/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n412009 LASERGTH/TGP UDP JONES CREEK OTELL\n412788 CP-UGC/TGP MOSSY OAKS: RIP 22N 101.\n411584 VAR/TGP NORTH ROTHERWOOD DEHY HARRI \n410320 ATMOS-MS/TGP SHUQUALAK MS NOXUBEE\n412638 WILMAR/TGP IMPERIAL OAKS DEHY MONTG\n***Added\n………………………………"]
["X23-69749",null,"2023-06-01","2023-07-31",null,null,null,"MLV 20-2 TO MLV 20-2A","100","0","Pressure Weld Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,20.2,null,"MLV 20-2 TO MLV 20-2A:  Pressure Weld Replacement\n--6/1/23 through 7/31/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-69745",null,"2023-04-01","2023-05-31",null,null,null,"MLV 20-3 TO MLV 20-3A","100","0","Pressure Weld Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,20.3,null,"MLV 20-3 TO MLV 20-3A:  Pressure Weld Replacement\n--4/1/23 through 5/31/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-113698","***","2023-03-28","2023-03-30","Added",null,null,"MLV 20-3A TO MLV 24-3A","100","0","Pig Runs - Cleaning 3/28 to 3/30","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412539 JOY RES/TGP JOSEY RANCH HARRIS\n412485 GALLO LS/TGP TOMBALL MARSHALL A\n421082 CEIP/TGP MOORHEAD ROAD: DIP 23B 101\n412327 FAMCORO/TGP SABINE WELL 5 DEHY MON",20.305,"------","***MLV 20-3A TO MLV 24-3A:  Pig Runs - Cleaning 3/28 to 3/30\n--3/28/23 through 3/30/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n412539 JOY RES/TGP JOSEY RANCH HARRIS\n412485 GALLO LS/TGP TOMBALL MARSHALL A\n421082 CEIP/TGP MOORHEAD ROAD: DIP 23B 101\n412327 FAMCORO/TGP SABINE WELL 5 DEHY MON\n***Added\n………………………………"]
["X23-113699","***","2023-03-31","2023-03-31","Added",null,null,"MLV 20-3A TO MLV 24-3A","100","0","Pig Runs - Gauge Pig 3/31","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412539 JOY RES/TGP JOSEY RANCH HARRIS\n412485 GALLO LS/TGP TOMBALL MARSHALL A\n421082 CEIP/TGP MOORHEAD ROAD: DIP 23B 101\n412327 FAMCORO/TGP SABINE WELL 5 DEHY MON",20.309999999999999,"------","***MLV 20-3A TO MLV 24-3A:  Pig Runs - Gauge Pig 3/31\n--3/31/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n412539 JOY RES/TGP JOSEY RANCH HARRIS\n412485 GALLO LS/TGP TOMBALL MARSHALL A\n421082 CEIP/TGP MOORHEAD ROAD: DIP 23B 101\n412327 FAMCORO/TGP SABINE WELL 5 DEHY MON\n***Added\n………………………………"]
["X23-113700","***","2023-04-14","2023-04-14","Added",null,null,"MLV 20-3A TO MLV 24-3A","100","0","Pig Runs - CLP / MFL-A / IMU 4/14","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412539 JOY RES/TGP JOSEY RANCH HARRIS\n412485 GALLO LS/TGP TOMBALL MARSHALL A\n421082 CEIP/TGP MOORHEAD ROAD: DIP 23B 101\n412327 FAMCORO/TGP SABINE WELL 5 DEHY MON",20.32,"------","***MLV 20-3A TO MLV 24-3A:  Pig Runs - CLP / MFL-A / IMU 4/14\n--4/14/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n412539 JOY RES/TGP JOSEY RANCH HARRIS\n412485 GALLO LS/TGP TOMBALL MARSHALL A\n421082 CEIP/TGP MOORHEAD ROAD: DIP 23B 101\n412327 FAMCORO/TGP SABINE WELL 5 DEHY MON\n***Added\n………………………………"]
["X22-973057","***","2023-01-28","2023-02-27","Project Change",null,"2023-02-20","MLV 25-1 TO MLV 26-1","100","0","BNSF RR Line Relocation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,25.1,"----end_date------------model_loc--","***MLV 25-1 TO MLV 26-1:  BNSF RR Line Relocation\n--1/28/23 through 2/27/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 1/28/23 to 2/20/23.\n………………………………"]
["X22-973055","***","2022-11-17","2023-01-27","Completed",null,null,"MLV 25-2 TO MLV 26-2","100","0","BNSF RR Line Relocation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,25.2,"------","***MLV 25-2 TO MLV 26-2:  BNSF RR Line Relocation\n***Completed"]
["X22-973052","***","2023-02-28","2023-03-18","Project Change","2023-02-21",null,"MLV 25-3 TO MLV 26-3","100","0","BNSF RR Line Relocation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut during the project.","SOP","Potential out of path restrictions may be at risk.","400448 CICO/TGP MERCY GU  1 LIBERTY",25.3,"--start_date--------------model_loc--","***MLV 25-3 TO MLV 26-3:  BNSF RR Line Relocation\n--2/28/23 through 3/18/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut during the project.  Potential out of path restrictions may be at risk.\n400448 CICO/TGP MERCY GU  1 LIBERTY\n***\nDate Change, Previously scheduled 2/21/23 to 3/18/23.\n………………………………"]
["X22-621358",null,"2023-03-07","2023-03-24",null,null,null,"MLV 26-1 Relocation","100","0","Highway Widening","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,26.1,null,"MLV 26-1 Relocation:  Highway Widening\n--3/7/23 through 3/24/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-815863",null,"2023-03-28","2023-04-14",null,null,null,"MLV 26-2 Relocation","100","0","Highway Widening","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,26.2,null,"MLV 26-2 Relocation:  Highway Widening\n--3/28/23 through 4/14/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-815864",null,"2023-02-14","2023-03-03",null,null,null,"MLV 26-3 Relocation","100","0","Highway Widening","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,26.3,null,"MLV 26-3 Relocation:  Highway Widening\n--2/14/23 through 3/3/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-113705","***","2023-07-10","2023-07-14","Added",null,null,"MLV 32-2D TO MLV 40-2S","100","0","Pig Runs - Cleaning 7/10 to 7/14","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412277 ETC TX/TGP BORRKELAND FIELD DEHY SA",32.200000000000003,"------","***MLV 32-2D TO MLV 40-2S:  Pig Runs - Cleaning 7/10 to 7/14\n--7/10/23 through 7/14/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n412277 ETC TX/TGP BORRKELAND FIELD DEHY SA\n***Added\n………………………………"]
["X23-113708","***","2023-07-14","2023-07-14","Added",null,null,"MLV 32-2D TO MLV 40-2S","100","0","Pig Runs - Gauge 7/14","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412277 ETC TX/TGP BORRKELAND FIELD DEHY SA",32.21,"------","***MLV 32-2D TO MLV 40-2S:  Pig Runs - Gauge 7/14\n--7/14/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n412277 ETC TX/TGP BORRKELAND FIELD DEHY SA\n***Added\n………………………………"]
["X23-113710","***","2023-07-20","2023-07-20","Added",null,null,"MLV 32-2D TO MLV 40-2S","100","0","Pig Runs - CLP / MFL-A / IMU 7/20","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412277 ETC TX/TGP BORRKELAND FIELD DEHY SA",32.22,"------","***MLV 32-2D TO MLV 40-2S:  Pig Runs - CLP / MFL-A / IMU 7/20\n--7/20/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n412277 ETC TX/TGP BORRKELAND FIELD DEHY SA\n***Added\n………………………………"]
["X23-113721","***","2023-07-25","2023-07-25","Added",null,null,"MLV 32-2D TO MLV 40-2S","800","1","Pig Runs - MFL-C 7/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412277 ETC TX/TGP BORRKELAND FIELD DEHY SA",32.229999999999997,"------","***MLV 32-2D TO MLV 40-2S:  Pig Runs - MFL-C 7/25\n--7/25/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n412277 ETC TX/TGP BORRKELAND FIELD DEHY SA\n***Added\n………………………………"]
["X23-113722","***","2023-07-27","2023-07-27","Added",null,null,"MLV 32-2D TO MLV 40-2S","800","1","Pig Runs - EMAT 7/27","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412277 ETC TX/TGP BORRKELAND FIELD DEHY SA",32.24,"------","***MLV 32-2D TO MLV 40-2S:  Pig Runs - EMAT 7/27\n--7/27/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n412277 ETC TX/TGP BORRKELAND FIELD DEHY SA\n***Added\n………………………………"]
["X23-120648","***","2023-02-22","2023-02-28","Added",null,null,"MLV 41-1 to MLV 42-1","100","1","Pipe Recoat","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,41.1,"------","***MLV 41-1 to MLV 42-1:  Pipe Recoat\n--2/22/23 through 2/28/23:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X23-120650","***","2023-03-01","2023-03-07","Added",null,null,"MLV 41-2 to MLV 42-2","100","1","Pipe Recoat","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,41.2,"------","***MLV 41-2 to MLV 42-2:  Pipe Recoat\n--3/1/23 through 3/7/23:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X23-120640","***","2023-02-15","2023-02-21","Added",null,null,"MLV 41-3 to MLV 42-3","100","1","Pipe Recoat","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,41.3,"------","***MLV 41-3 to MLV 42-3:  Pipe Recoat\n--2/15/23 through 2/21/23:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X23-120652","***","2023-03-08","2023-03-14","Added",null,null,"MLV 41-3 to MLV 42-3","100","1","Pipe Recoat","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,41.3,"------","***MLV 41-3 to MLV 42-3:  Pipe Recoat\n--3/8/23 through 3/14/23:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X23-100955","***","2023-04-18","2023-04-24","Added",null,null,"Bear Creek Storage","100","1","Shut-in Test","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","460017 STORAGE – BEAR CREEK",43,"------","***Bear Creek Storage:  Shut-in Test\n--4/18/23 through 4/24/23:  This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.  Potential out of path restrictions may be at risk.\n460017 STORAGE – BEAR CREEK\n***Added\n………………………………"]
["X23-100958","***","2023-10-17","2023-10-23","Added",null,null,"Bear Creek Storage","100","1","Shut-in Test","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","460017 STORAGE – BEAR CREEK",43.1,"------","***Bear Creek Storage:  Shut-in Test\n--10/17/23 through 10/23/23:  This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.  Potential out of path restrictions may be at risk.\n460017 STORAGE – BEAR CREEK\n***Added\n………………………………"]
["X23-59502","***","2023-01-18","2023-12-31","Project Change",null,"2023-02-28","Sta 47","100","1","Unit 9B - Power Cylinder Investigation","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,47.024999999999999,"----end_date------------model_loc--","***Sta 47:  Unit 9B - Power Cylinder Investigation\n--1/18/23 through 12/31/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 1/18/23 to 2/28/23.\n………………………………"]
["X23-76972",null,"2023-01-30","2023-02-02",null,null,null,"Sta 47","100","1","Unit 1C - Repair Packing","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,47.033000000000001,null,"Sta 47:  Unit 1C - Repair Packing\n--1/30/23 through 2/2/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-118202","***","2023-02-01","2023-02-13","Added",null,null,"Sta 47","100","1","Unit 6C - Water in Crankcase Investigation","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,47.034999999999997,"------","***Sta 47:  Unit 6C - Water in Crankcase Investigation\n--2/1/23 through 2/13/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X23-24595","***","2023-03-17","2023-03-31","Project Change","2023-03-03","2023-03-17","MLV 47-1A thru MLV 48-1","100","1","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,47.1,"--start_date--end_date------------model_loc--","***MLV 47-1A thru MLV 48-1:  Pipe Replacement\n--3/17/23 through 3/31/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 3/3/23 to 3/17/23.\n………………………………"]
["X23-24600","***","2023-04-01","2023-04-15","Project Change","2023-03-18","2023-04-01","MLV 47-2A thru MLV 48-2","100","1","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in for the duration of the project.","SOP","Potential out of path restrictions may be at risk.","47872 ATMOS TL/TGP CHAUVIN OUACHITA",47.2,"--start_date--end_date------------model_loc--","***MLV 47-2A thru MLV 48-2:  Pipe Replacement\n--4/1/23 through 4/15/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in for the duration of the project.  Potential out of path restrictions may be at risk.\n47872 ATMOS TL/TGP CHAUVIN OUACHITA\n***\nDate Change, Previously scheduled 3/18/23 to 4/1/23.\n………………………………"]
["X23-24592","***","2023-02-23","2023-03-16","Project Change","2023-02-16","2023-03-02","MLV 47-4A thru MLV 48-4","100","1","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in for the duration of the project.","SOP","Potential out of path restrictions may be at risk.","421013 BBTMIDLA/TGP FAIRBANKS OUACHITA",47.4,"--start_date--end_date------------model_loc--","***MLV 47-4A thru MLV 48-4:  Pipe Replacement\n--2/23/23 through 3/16/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in for the duration of the project.  Potential out of path restrictions may be at risk.\n421013 BBTMIDLA/TGP FAIRBANKS OUACHITA\n***\nDate Change, Previously scheduled 2/16/23 to 3/2/23.\n………………………………"]
["X23-69503",null,"2023-10-17","2023-10-19",null,null,null,"Sta 54","100","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,54,null,"Sta 54:  Annual ESD Test\n--10/17/23 through 10/19/23:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-583201","***","2023-01-09","2023-02-10","Project Change",null,"2023-01-31","Sta 54","100","1","Unit 1B - GHG Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,54.017000000000003,"----end_date------------model_loc--","***Sta 54:  Unit 1B - GHG Inspection\n--1/9/23 through 2/10/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 1/9/23 to 1/31/23.\n………………………………"]
["X23-113790","***","2023-01-23","2023-02-08","Added",null,null,"Sta 54","100","1","Unit 1B - GHG Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,54.017000000000003,"------","***Sta 54:  Unit 1B - GHG Inspection\n--1/23/23 through 2/8/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X22-583198","***","2023-01-09","2023-02-08","Project Change",null,"2023-01-26","Sta 54","100","1","Unit 6B - GHG Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,54.021999999999998,"----end_date------------model_loc--","***Sta 54:  Unit 6B - GHG Inspection\n--1/9/23 through 2/8/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 1/9/23 to 1/26/23.\n………………………………"]
["X23-57468",null,"2023-08-15","2023-08-15",null,null,null,"MLV 63-2D to 69-2","100","1","Pig Runs - Cleaning / Gauge 8/15","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,63.2,null,"MLV 63-2D to 69-2:  Pig Runs - Cleaning / Gauge 8/15\n--8/15/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-57472",null,"2023-08-17","2023-08-17",null,null,null,"MLV 63-2D to 69-2","100","1","Pig Runs - MFL Combo 8/17","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,63.21,null,"MLV 63-2D to 69-2:  Pig Runs - MFL Combo 8/17\n--8/17/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-1180243",null,"2022-11-28","2023-02-03",null,null,null,"Sta 71","100","1","Re-Wire Unit Compressor Valves","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,71,null,"Sta 71:  Re-Wire Unit Compressor Valves\n--11/28/22 through 2/3/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-603145","***","2022-06-15","2023-01-31","Completed",null,null,"Sta 71","100","1","Unit 4A - Emergent Repair for Base Gasket","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,71.004000000000005,"------","***Sta 71:  Unit 4A - Emergent Repair for Base Gasket\n***Completed"]
["X22-1077575",null,"2022-10-27","2023-04-25",null,null,null,"Sta 860 TO Sta 87","800","1","Emergent Repair","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,87,null,"Sta 860 TO Sta 87:  Emergent Repair\n--10/27/22 through 4/25/23:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-62072",null,"2023-08-08","2023-08-08",null,null,null,"Sta 87 Portland","100","2","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,87,null,"Sta 87 Portland:  Annual ESD Test\n--8/8/23:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-62061",null,"2023-08-01","2023-08-31",null,null,null,"Sta 87","100","2","Unt 5C - Regrout","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,87.037000000000006,null,"Sta 87:  Unt 5C - Regrout\n--8/1/23 through 8/31/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-118199","***","2023-03-06","2023-03-19","Added",null,null,"Sta 87","100","2","Bldg E - Jacket Water System Maintenance","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,87.049000000000007,"------","***Sta 87:  Bldg E - Jacket Water System Maintenance\n--3/6/23 through 3/19/23:  This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***Added\n………………………………"]
["X23-62070",null,"2023-07-17","2023-07-17",null,null,null,"Sta 87","100","2","Bldg D Relief Valves Replacement","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,87.049000000000007,null,"Sta 87:  Bldg D Relief Valves Replacement\n--7/17/23:  This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-62063","***","2023-02-27","2023-03-01","Project Change",null,null,"Sta 87","100","2","Unt 1E - Coupling Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,87.064999999999998,"------------prl----model_loc--","***Sta 87:  Unt 1E - Coupling Replacement\n--2/27/23 through 3/1/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***Project Change\n………………………………"]
["X23-62059",null,"2023-05-15","2023-05-19",null,null,null,"Sta 87","100","2","Building E Scrubber Filter Replacement","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,87.064999999999998,null,"Sta 87:  Building E Scrubber Filter Replacement\n--5/15/23 through 5/19/23:  This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X23-30086","***","2023-01-17","2023-01-26","Completed",null,null,"Sta 96","100","2","Unit 11C - Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,96.010999999999996,"------","***Sta 96:  Unit 11C - Engine Inspection\n***Completed"]
["X23-113767","***","2023-02-06","2023-02-13","Added",null,null,"Sta 96","100","2","Unit 9C - Blower / Supercharger Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,96.040999999999997,"------","***Sta 96:  Unit 9C - Blower / Supercharger Replacement\n--2/6/23 through 2/13/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***Added\n………………………………"]
["X23-60663",null,"2023-07-06","2023-07-06",null,null,null,"MLV 96-1S to MLV 87-1D","100","2","Pig Runs - Cleaning/Gauge 7/6","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,96.1,null,"MLV 96-1S to MLV 87-1D:  Pig Runs - Cleaning/Gauge 7/6\n--7/6/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-60665",null,"2023-07-11","2023-07-11",null,null,null,"MLV 96-1S to MLV 87-1D","100","2","Pig Runs - MFL-C\t7/11","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,96.11,null,"MLV 96-1S to MLV 87-1D:  Pig Runs - MFL-C\t7/11\n--7/11/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-60666",null,"2023-07-13","2023-07-13",null,null,null,"MLV 96-1S to MLV 87-1D","100","2","Pig Runs - EMAT\t7/13","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,96.12,null,"MLV 96-1S to MLV 87-1D:  Pig Runs - EMAT\t7/13\n--7/13/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-40681",null,"2023-01-10","2023-07-09",null,null,null,"MLV 96-3D to MLV 106-3S","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,96.3,null,"MLV 96-3D to MLV 106-3S:  Anomaly Remediation\n--1/10/23 through 7/9/23:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X23-57461",null,"2023-08-01","2023-08-01",null,null,null,"MLV 96-4S to 87-4D","100","2","Pig Runs - Cleaning / Gauge 8/1","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,96.4,null,"MLV 96-4S to 87-4D:  Pig Runs - Cleaning / Gauge 8/1\n--8/1/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-57464",null,"2023-08-03","2023-08-03",null,null,null,"MLV 96-4S to 87-4D","100","2","Pig Runs - MFL Combo 8/3","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,96.41,null,"MLV 96-4S to 87-4D:  Pig Runs - MFL Combo 8/3\n--8/3/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-57466",null,"2023-08-08","2023-08-08",null,null,null,"MLV 96-4S to 87-4D","100","2","Pig Runs - Hard Spot 8/8","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,96.42,null,"MLV 96-4S to 87-4D:  Pig Runs - Hard Spot 8/8\n--8/8/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-57376",null,"2023-06-23","2023-06-23",null,null,null,"MLV 96-5S to MLV 90-5","100","2","Pig Runs - Cleaning/Gauge 6/23","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,96.5,null,"MLV 96-5S to MLV 90-5:  Pig Runs - Cleaning/Gauge 6/23\n--6/23/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-57378",null,"2023-06-27","2023-06-27",null,null,null,"MLV 96-5S to MLV 90-5","100","2","Pig Runs - CAL/IMU/MFL-A 6/27","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,96.51,null,"MLV 96-5S to MLV 90-5:  Pig Runs - CAL/IMU/MFL-A 6/27\n--6/27/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-57381",null,"2023-06-29","2023-06-29",null,null,null,"MLV 96-5S to MLV 90-5","100","2","Pig Runs - Hardspot 6/29","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,96.52,null,"MLV 96-5S to MLV 90-5:  Pig Runs - Hardspot 6/29\n--6/29/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-991294",null,"2023-06-19","2023-09-30",null,null,null,"MLV 100-1A to MLV 102-1A","100","2","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,100.1,null,"MLV 100-1A to MLV 102-1A:  Pipe Replacement\n--6/19/23 through 9/30/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-991207",null,"2023-04-27","2023-06-13",null,null,null,"MLV 102-1A to MLV 103-1","100","2","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,102.1,null,"MLV 102-1A to MLV 103-1:  Pipe Replacement\n--4/27/23 through 6/13/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X23-41072",null,"2023-05-08","2023-05-12",null,null,null,"Sta 106","100","2","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,106,null,"Sta 106:  Annual ESD Test & Maintenance\n--5/8/23 through 5/12/23:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X23-41087","***","2023-02-13","2023-02-17","Project Change",null,null,"Sta 106","100","2","Bldg B - Unit Valve Replacement","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,106.017,"------------prl----model_loc--","***Sta 106:  Bldg B - Unit Valve Replacement\n--2/13/23 through 2/17/23:  This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***Project Change\n………………………………"]
["X23-118158","***","2023-02-20","2023-02-24","Added",null,null,"Sta 106","100","2","Bldg B - Coalescing Filter Replacement","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,106.0171,"------","***Sta 106:  Bldg B - Coalescing Filter Replacement\n--2/20/23 through 2/24/23:  This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***Added\n………………………………"]
["X23-41305","***","2023-01-16","2023-03-17","Project Change",null,null,"Sta 106","100","2","Unit 1B - Manifold Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,106.0175,"------------prl----model_loc--","***Sta 106:  Unit 1B - Manifold Maintenance\n--1/16/23 through 3/17/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***Project Change\n………………………………"]
["X23-113789","***","2023-02-06","2023-02-10","Added",null,null,"Sta 106","200","4","Unit 1C - Power Cylinder Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,106.032,"------","***Sta 106:  Unit 1C - Power Cylinder Inspection\n--2/6/23 through 2/10/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***Added\n………………………………"]
["X23-41289","***","2023-01-23","2023-01-27","Completed",null,null,"Sta 106","100","2","Unit 1C - Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106.033,"------","***Sta 106:  Unit 1C - Engine Inspection\n***Completed"]
["X23-100836","***","2023-02-06","2023-02-10","Added",null,null,"Sta 106","100","2","Unit 1C - Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,106.033,"------","***Sta 106:  Unit 1C - Engine Inspection\n--2/6/23 through 2/10/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***Added\n………………………………"]
["X23-41182","***","2023-03-20","2023-03-22","Project Change",null,null,"Sta 106","100","2","Unit 1D - 4k Hr Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,106.04900000000001,"------------prl----model_loc--","***Sta 106:  Unit 1D - 4k Hr Inspection\n--3/20/23 through 3/22/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***Project Change\n………………………………"]
["X23-41254","***","2023-08-28","2023-08-30","Project Change",null,null,"Sta 106","100","2","Unit 1D - 8k Hr Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,106.04900000000001,"------------prl----model_loc--","***Sta 106:  Unit 1D - 8k Hr Inspection\n--8/28/23 through 8/30/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***Project Change\n………………………………"]
["X23-41223","***","2023-06-12","2023-06-14","Project Change",null,null,"Sta 106","100","2","Unit 2D - 4k Hr Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,106.05,"------------prl----model_loc--","***Sta 106:  Unit 2D - 4k Hr Inspection\n--6/12/23 through 6/14/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***Project Change\n………………………………"]
["X23-41266","***","2023-11-27","2023-11-29","Project Change",null,null,"Sta 106","100","2","Unit 2D - 8k Hr Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,106.05,"------------prl----model_loc--","***Sta 106:  Unit 2D - 8k Hr Inspection\n--11/27/23 through 11/29/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***Project Change\n………………………………"]
["X22-954549",null,"2023-02-14","2023-02-16",null,null,null,"MLV 106-7 to MLV 107-7","100","2","New Meter Tap (Mtr: Rumpke Biogas PIN 55963)","This project will require reducing pressure, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106.7,null,"MLV 106-7 to MLV 107-7:  New Meter Tap (Mtr: Rumpke Biogas PIN 55963)\n--2/14/23 through 2/16/23:  This project will require reducing pressure, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-74364",null,"2023-10-17","2023-10-18",null,null,null,"Sta 107A North Means","100","2","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,107,null,"Sta 107A North Means:  Annual ESD Test\n--10/17/23 through 10/18/23:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-74430","***","2023-01-25","2023-04-01","Project Change",null,null,"Sta 106","100","2","Unit 8B - Foundation Investigation","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,109.02500000000001,"----------mantenance_desc--prl----model_loc--","***Sta 106:  Unit 8B - Foundation Investigation\n--1/25/23 through 4/1/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***Project Change\n………………………………"]
["X23-120777","***","2023-07-10","2023-07-14","Added",null,null,"Sta 110","100","2","Annual ESD Test & Substation Inspection","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,110,"------","***Sta 110:  Annual ESD Test & Substation Inspection\n--7/10/23 through 7/14/23:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X23-74511","***","2023-03-06","2023-03-17","Project Change",null,null,"Sta 110","100","2","Unit 7A - Replace Transmission","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,110.00700000000001,"------------prl----model_loc--","***Sta 110:  Unit 7A - Replace Transmission\n--3/6/23 through 3/17/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***Project Change\n………………………………"]
["X23-118185","***","2023-02-08","2023-02-10","Added",null,null,"MLV 110-5 to 109-5","100","2","High Priority Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,110.5,"------","***MLV 110-5 to 109-5:  High Priority Anomaly Remediation\n--2/8/23 through 2/10/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***Added\n………………………………"]
["X23-113510","***","2023-02-08","2023-03-08","Added",null,null,"MLV 111-5 to 110-5","100","2","High Priority Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,111.5,"------","***MLV 111-5 to 110-5:  High Priority Anomaly Remediation\n--2/8/23 through 3/8/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***Added\n………………………………"]
["X23-57493",null,"2023-04-10","2023-04-14",null,null,null,"Sta 114","100","3","Unit 1C - Compressor Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,114.033,null,"Sta 114:  Unit 1C - Compressor Inspection\n--4/10/23 through 4/14/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X23-57492","***","2023-04-03","2023-04-07","Project Change",null,null,"Sta 114","100","2","Unit 2C - Compressor Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,114.03400000000001,"------------prl----model_loc--","***Sta 114:  Unit 2C - Compressor Inspection\n--4/3/23 through 4/7/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***Project Change\n………………………………"]
["X23-57490",null,"2023-02-20","2023-03-31",null,null,null,"Sta 114","100","3","Unit 3C - Compressor / Coupling Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,114.035,null,"Sta 114:  Unit 3C - Compressor / Coupling Inspection\n--2/20/23 through 3/31/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X23-32114",null,"2023-05-20","2023-05-24",null,null,null,"Sta 114","100","3","Unit 1D - Turbine Exchange","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,114.04900000000001,null,"Sta 114:  Unit 1D - Turbine Exchange\n--5/20/23 through 5/24/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X23-57448",null,"2023-06-06","2023-06-06",null,null,null,"MLV 114-3S to 111-3B","100","2","Pig Runs - Cleaning / Gauge 6/6","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,114.3,null,"MLV 114-3S to 111-3B:  Pig Runs - Cleaning / Gauge 6/6\n--6/6/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-57450",null,"2023-06-08","2023-06-08",null,null,null,"MLV 114-3S to 111-3B","100","2","Pig Runs - MFL Combo 6/8","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,114.31,null,"MLV 114-3S to 111-3B:  Pig Runs - MFL Combo 6/8\n--6/8/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-57424","***","2023-04-25","2023-04-25","Project Change",null,null,"MLV 117-2R to 117-2ABL","100","3","Pig Runs - Cleaning / Gauge 4/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,117.2,"------------prl----model_loc--","***MLV 117-2R to 117-2ABL:  Pig Runs - Cleaning / Gauge 4/25\n--4/25/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n***Project Change\n………………………………"]
["X23-57425","***","2023-04-27","2023-04-27","Project Change",null,null,"MLV 117-2R to 117-2ABL","100","3","Pig Runs - MFL Combo 4/27","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,117.21,"------------prl----model_loc--","***MLV 117-2R to 117-2ABL:  Pig Runs - MFL Combo 4/27\n--4/27/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n***Project Change\n………………………………"]
["X22-55542",null,"2023-04-03","2023-04-05",null,null,null,"Sta 118A","100","3","Solar 8k Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,118.00149999999999,null,"Sta 118A:  Solar 8k Inspection\n--4/3/23 through 4/5/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X23-38750",null,"2023-04-06","2023-04-06",null,null,null,"MLV 118-3 to MLV 114-3D","100","3","Pig Run - Cleaning/Gauge 4/6","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","PIP","Potential in the path restrictions may be at risk.",null,118.3,null,"MLV 118-3 to MLV 114-3D:  Pig Run - Cleaning/Gauge 4/6\n--4/6/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X23-38751",null,"2023-04-11","2023-04-11",null,null,null,"MLV 118-3 to MLV 114-3D","100","3","Pig Run - Cal / IMU 4/11","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","PIP","Potential in the path restrictions may be at risk.",null,118.31,null,"MLV 118-3 to MLV 114-3D:  Pig Run - Cal / IMU 4/11\n--4/11/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X23-38752",null,"2023-04-13","2023-04-13",null,null,null,"MLV 118-3 to MLV 114-3D","100","3","Pig Run - Hardspot 4/13","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","PIP","Potential in the path restrictions may be at risk.",null,118.32,null,"MLV 118-3 to MLV 114-3D:  Pig Run - Hardspot 4/13\n--4/13/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X23-38753",null,"2023-04-17","2023-04-17",null,null,null,"MLV 118-3 to MLV 114-3D","100","3","Pig Run - EMAT 4/17","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","PIP","Potential in the path restrictions may be at risk.",null,118.33,null,"MLV 118-3 to MLV 114-3D:  Pig Run - EMAT 4/17\n--4/17/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X23-38755",null,"2023-04-19","2023-04-19",null,null,null,"MLV 118-3 to MLV 114-3D","100","3","Pig Run - MFL-C 4/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","PIP","Potential in the path restrictions may be at risk.",null,118.34,null,"MLV 118-3 to MLV 114-3D:  Pig Run - MFL-C 4/19\n--4/19/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X23-32117",null,"2023-06-05","2023-06-05",null,null,null,"Sta 119A","100","3","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,119,null,"Sta 119A:  Annual ESD Test\n--6/5/23:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-32116",null,"2023-06-05","2023-06-09",null,null,null,"Sta 119A","100","3","Unit 1A - Turbine 8k Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,119.001,null,"Sta 119A:  Unit 1A - Turbine 8k Inspection\n--6/5/23 through 6/9/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-57422",null,"2023-04-20","2023-04-20",null,null,null,"MLV 119-2 to 118-3","100","3","Pig Runs - Cleaning / Gauge 4/20","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","PIP","Potential in the path restrictions may be at risk.",null,119.2,null,"MLV 119-2 to 118-3:  Pig Runs - Cleaning / Gauge 4/20\n--4/20/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X23-57423",null,"2023-05-02","2023-05-02",null,null,null,"MLV 119-2 to 118-3","100","3","Pig Runs - MFL Combo 5/2","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","PIP","Potential in the path restrictions may be at risk.",null,119.21,null,"MLV 119-2 to 118-3:  Pig Runs - MFL Combo 5/2\n--5/2/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X23-38641",null,"2023-03-20","2023-03-20",null,null,null,"MLV 121-2 to MLV 119-2","100","3","Pig Run - Cleaning/Gauge 3/20","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","PIP","Potential in the path restrictions may be at risk.",null,121.2,null,"MLV 121-2 to MLV 119-2:  Pig Run - Cleaning/Gauge 3/20\n--3/20/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X23-38644",null,"2023-03-22","2023-03-22",null,null,null,"MLV 121-2 to MLV 119-2","100","3","Pig Run - MFL-C 3/22","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","PIP","Potential in the path restrictions may be at risk.",null,121.21,null,"MLV 121-2 to MLV 119-2:  Pig Run - MFL-C 3/22\n--3/22/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X23-38647",null,"2023-03-23","2023-03-23",null,null,null,"MLV 121-2 to MLV 119-2","100","3","Pig Run - Cal/IMU 3/23","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","PIP","Potential in the path restrictions may be at risk.",null,121.22,null,"MLV 121-2 to MLV 119-2:  Pig Run - Cal/IMU 3/23\n--3/23/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X23-38648",null,"2023-03-25","2023-03-25",null,null,null,"MLV 121-2 to MLV 119-2","100","3","Pig Run - MFL-A / Hardspot 3/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","PIP","Potential in the path restrictions may be at risk.",null,121.23,null,"MLV 121-2 to MLV 119-2:  Pig Run - MFL-A / Hardspot 3/25\n--3/25/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X23-118153","***","2023-06-12","2023-06-15","Added",null,null,"Sta 200","200","4","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,200,"------","***Sta 200:  Annual ESD Test\n--6/12/23 through 6/15/23:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X23-38636",null,"2023-01-30","2023-02-03",null,null,null,"Sta 200","200","4","Unit 1A - Punch Carbon","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,200.001,null,"Sta 200:  Unit 1A - Punch Carbon\n--1/30/23 through 2/3/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-57435",null,"2023-02-06","2023-02-10",null,null,null,"Sta 200","200","4","Unit 10A - Turbocharger Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,200.01,null,"Sta 200:  Unit 10A - Turbocharger Replacement\n--2/6/23 through 2/10/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-38635","***","2023-01-23","2023-01-27","Completed",null,null,"Sta 200","200","4","Unit 12A - Punch Carbon","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,200.0121,"------","***Sta 200:  Unit 12A - Punch Carbon\n***Completed"]
["X23-57495",null,"2023-02-13","2023-02-17",null,null,null,"Sta 200","200","4","Unit 1B - WEB deflection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,200.017,null,"Sta 200:  Unit 1B - WEB deflection\n--2/13/23 through 2/17/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-57445",null,"2023-06-01","2023-06-01",null,null,null,"MLV 200-1S to 106-3D","100","2","Pig Runs - Cleaning / Gauge 6/1","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,200.1,null,"MLV 200-1S to 106-3D:  Pig Runs - Cleaning / Gauge 6/1\n--6/1/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-57447",null,"2023-06-13","2023-06-13",null,null,null,"MLV 200-1S to 106-3D","100","2","Pig Runs - MFL Combo 6/13","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,200.11,null,"MLV 200-1S to 106-3D:  Pig Runs - MFL Combo 6/13\n--6/13/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-113785","***","2023-05-15","2023-05-19","Added",null,null,"Sta 204","200","4","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,204,"------","***Sta 204:  Annual ESD Test & Maintenance\n--5/15/23 through 5/19/23:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***Added\n………………………………"]
["X23-71229",null,"2023-04-17","2023-09-01",null,null,null,"Sta 204","200","4","Unit 2A - Foundation Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,204.00200000000001,null,"Sta 204:  Unit 2A - Foundation Replacement\n--4/17/23 through 9/1/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-40638","***","2023-01-17","2023-01-27","Completed",null,null,"Sta 204","200","4","Unit 6A - Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,204.006,"------","***Sta 204:  Unit 6A - Crankcase Inspection\n***Completed"]
["X23-113784","***","2023-05-08","2023-05-19","Added",null,null,"Sta 204","200","4","Unit 9A - Compressor Boring","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,204.00899999999999,"------","***Sta 204:  Unit 9A - Compressor Boring\n--5/8/23 through 5/19/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X22-1029792","***","2023-01-09","2023-01-27","Completed",null,null,"Sta 204","200","4","Unit 10A - Punch Carbon","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,204.01,"------","***Sta 204:  Unit 10A - Punch Carbon\n***Completed"]
["X22-1120779","***","2023-02-13","2023-02-16","Project Change","2023-02-06","2023-02-09","Sta 204","200","4","Unit 11A - Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,204.011,"--start_date--end_date------------model_loc--","***Sta 204:  Unit 11A - Crankcase Inspection\n--2/13/23 through 2/16/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 2/6/23 to 2/9/23.\n………………………………"]
["X23-59375","***","2023-02-01","2023-02-09","Project Change",null,"2023-02-02","Sta 204","200","4","Unit 12A - Turbo Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,204.012,"----end_date------------model_loc--","***Sta 204:  Unit 12A - Turbo Maintenance\n--2/1/23 through 2/9/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 2/1/23 to 2/2/23.\n………………………………"]
["X23-113787","***","2023-05-08","2023-05-12","Added",null,null,"Sta 209","200","4","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,209,"------","***Sta 209:  Annual ESD Test & Maintenance\n--5/8/23 through 5/12/23:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***Added\n………………………………"]
["X23-24430",null,"2023-01-30","2023-02-03",null,null,null,"Sta 209","200","4","Unit 1A - Punch Carbon","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209.001,null,"Sta 209:  Unit 1A - Punch Carbon\n--1/30/23 through 2/3/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-24431","***","2023-01-23","2023-01-27","Completed",null,null,"Sta 209","200","4","Unit 2A - Punch Carbon","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209.00200000000001,"------","***Sta 209:  Unit 2A - Punch Carbon\n***Completed"]
["X23-24432",null,"2023-02-06","2023-02-10",null,null,null,"Sta 209","200","4","Unit 3A - Punch Carbon","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209.00299999999999,null,"Sta 209:  Unit 3A - Punch Carbon\n--2/6/23 through 2/10/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-71237",null,"2023-02-13","2023-02-17",null,null,null,"Sta 209","200","4","Unit 4A - Punch Carbon","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209.00399999999999,null,"Sta 209:  Unit 4A - Punch Carbon\n--2/13/23 through 2/17/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-113786","***","2023-02-02","2023-02-02","Added",null,null,"Sta 209","200","4","Unit 13A - Punch Carbon","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209.01300000000001,"------","***Sta 209:  Unit 13A - Punch Carbon\n--2/2/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X23-40711",null,"2023-04-20","2023-04-20",null,null,null,"MLV 209-2 to MLV 204-2","200","4","Pig run - Cleaning 4/20","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,209.2,null,"MLV 209-2 to MLV 204-2:  Pig run - Cleaning 4/20\n--4/20/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-40712",null,"2023-04-25","2023-04-25",null,null,null,"MLV 209-2 to MLV 204-2","200","4","Pig run - AFD 4/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,209.21,null,"MLV 209-2 to MLV 204-2:  Pig run - AFD 4/25\n--4/25/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-40713",null,"2023-04-27","2023-04-27",null,null,null,"MLV 209-2 to MLV 204-2","200","4","Pig run - EMAT 4/27","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,209.22,null,"MLV 209-2 to MLV 204-2:  Pig run - EMAT 4/27\n--4/27/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-30085","***","2023-01-09","2023-03-30","Project Change",null,"2023-02-09","Sta 214","200","4","Unit 7A - Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,214.00700000000001,"----end_date------------model_loc--","***Sta 214:  Unit 7A - Engine Inspection\n--1/9/23 through 3/30/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 1/9/23 to 2/9/23.\n………………………………"]
["X23-27323","***","2023-02-07","2023-02-09","Project Change",null,null,"Sta 219","200","4","Unit 5A - Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,219.005,"------------prl----model_loc--","***Sta 219:  Unit 5A - Crankcase Inspection\n--2/7/23 through 2/9/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***Project Change\n………………………………"]
["X23-62206","***","2023-01-23","2023-01-26","Completed",null,null,"Sta 219","200","4","Unit 9A - Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,219.00899999999999,"------","***Sta 219:  Unit 9A - Engine Inspection\n***Completed"]
["X23-59556","***","2023-01-18","2023-01-27","Completed",null,null,"Sta 219","200","4","Unit 1B - Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,219.017,"------","***Sta 219:  Unit 1B - Engine Inspection\n***Completed"]
["X23-40733",null,"2023-04-11","2023-04-11",null,null,null,"MLV 229-2 to MLV 232-2","200","5","Pig run - Cleaning 4/11","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,229.2,null,"MLV 229-2 to MLV 232-2:  Pig run - Cleaning 4/11\n--4/11/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X23-40734",null,"2023-04-13","2023-04-13",null,null,null,"MLV 229-2 to MLV 232-2","200","5","Pig run - EMAT 4/13","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,229.22,null,"MLV 229-2 to MLV 232-2:  Pig run - EMAT 4/13\n--4/13/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X23-74188",null,"2023-05-01","2023-05-05",null,null,null,"Station 230C","200","5","Unit 2A - Turbine Exchange","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,230.00200000000001,null,"Station 230C:  Unit 2A - Turbine Exchange\n--5/1/23 through 5/5/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-74189",null,"2023-06-05","2023-06-09",null,null,null,"Station 230C","200","5","Unit 3A - Turbine Exchange","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,230.00299999999999,null,"Station 230C:  Unit 3A - Turbine Exchange\n--6/5/23 through 6/9/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-59426",null,"2023-09-19","2023-09-19",null,null,null,"MLV 237-1 TO MLV 245-1","200","5","Pig Runs - Cleaning/Gauge 9/20","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,237.1,null,"MLV 237-1 TO MLV 245-1:  Pig Runs - Cleaning/Gauge 9/20\n--9/19/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-59427",null,"2023-09-21","2023-09-21",null,null,null,"MLV 237-1 TO MLV 245-1","200","5","Pig Runs - EMAT 9/21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,237.11,null,"MLV 237-1 TO MLV 245-1:  Pig Runs - EMAT 9/21\n--9/21/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-76820","***","2023-04-04","2023-04-05","Project Change","2023-02-07","2023-02-08","Sta 241","200","5","Unit 3A -Engine Investigation","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,241.00299999999999,"--start_date--end_date------------model_loc--","***Sta 241:  Unit 3A -Engine Investigation\n--4/4/23 through 4/5/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 2/7/23 to 2/8/23.\n………………………………"]
["X23-59599",null,"2023-08-07","2023-08-12",null,null,null,"MLV 241-2 to MLV 242-2","200","5","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,241.2,null,"MLV 241-2 to MLV 242-2:  Anomaly Remediation\n--8/7/23 through 8/12/23:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-59605",null,"2023-08-07","2023-08-12",null,null,null,"MLV 244-2 to MLV 245-2","200","5","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,244.2,null,"MLV 244-2 to MLV 245-2:  Anomaly Remediation\n--8/7/23 through 8/12/23:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-866252",null,"2022-08-30","2023-10-31",null,null,null,"Sta 245","200","5","Unit 7A - Turbo Charger Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,245.00700000000001,null,"Sta 245:  Unit 7A - Turbo Charger Replacement\n--8/30/22 through 10/31/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-59582",null,"2023-05-08","2023-05-12",null,null,null,"MLV 249-1 to MLV 250-1","200","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,249.1,null,"MLV 249-1 to MLV 250-1:  Anomaly Remediation\n--5/8/23 through 5/12/23:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-59584",null,"2023-05-13","2023-05-20",null,null,null,"MLV 253-1 to MLV 254-1","200","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,253.1,null,"MLV 253-1 to MLV 254-1:  Anomaly Remediation\n--5/13/23 through 5/20/23:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-62074",null,"2023-02-06","2023-02-08",null,null,null,"Sta 254","200","5","Unit 5A - Replace Turbo","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,254.005,null,"Sta 254:  Unit 5A - Replace Turbo\n--2/6/23 through 2/8/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-59411",null,"2023-04-25","2023-04-25",null,null,null,"MLV 254-1 to MLV 261-1","200","6","Pig Runs - Cleaning / Gauge 4/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,254.1,null,"MLV 254-1 to MLV 261-1:  Pig Runs - Cleaning / Gauge 4/25\n--4/25/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-59413",null,"2023-04-27","2023-04-27",null,null,null,"MLV 254-1 to MLV 261-1","200","6","Pig Runs - MFL-A/Cal/IMU 4/27","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,254.11,null,"MLV 254-1 to MLV 261-1:  Pig Runs - MFL-A/Cal/IMU 4/27\n--4/27/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-59415",null,"2023-05-02","2023-05-02",null,null,null,"MLV 254-1 to MLV 261-1","200","6","Pig Runs - MFL-C 5/2","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,254.12,null,"MLV 254-1 to MLV 261-1:  Pig Runs - MFL-C 5/2\n--5/2/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-59416",null,"2023-09-27","2023-09-27",null,null,null,"MLV 254-1 to MLV 261-1","200","6","Pig Runs - EMAT: 9/27","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,254.13,null,"MLV 254-1 to MLV 261-1:  Pig Runs - EMAT: 9/27\n--9/27/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-59452",null,"2023-03-28","2023-03-28",null,null,null,"MLV 260A-103 to MLV 260A-105","200","6","Pig Runs - Cleaning/Gauge 3/28","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420292 BERKSHR/TGP GREENFIELD MA HAMPSHIRE\n420106 EVRSRC/TGP GRANITE NORTHAMPTON MA H",260.10000000000002,null,"MLV 260A-103 to MLV 260A-105:  Pig Runs - Cleaning/Gauge 3/28\n--3/28/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.  Potential out of path restrictions may be at risk.\n420292 BERKSHR/TGP GREENFIELD MA HAMPSHIRE\n420106 EVRSRC/TGP GRANITE NORTHAMPTON MA H\n………………………………"]
["X23-59498","***","2023-06-21","2023-06-21","Project Change","2023-06-13","2023-06-13","MLV 260A-101.1 TO MLV 260A-103","200","6","Pig Runs - MFL-C 6/21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420104 WESTFLD/TGP WESTFIELD MA HAMPDEN\n420401 HOLYOKE/TGP HOLYOKE MA 2 HAMPDEN",260.10000000000002,"--start_date--end_date------mantenance_desc------model_loc--","***MLV 260A-101.1 TO MLV 260A-103:  Pig Runs - MFL-C 6/21\n--6/21/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.  Potential out of path restrictions may be at risk.\n420104 WESTFLD/TGP WESTFIELD MA HAMPDEN\n420401 HOLYOKE/TGP HOLYOKE MA 2 HAMPDEN\n***\nDate Change, Previously scheduled 6/13/23.\n………………………………"]
["X23-59463",null,"2023-03-29","2023-03-29",null,null,null,"MLV 260A-103 to MLV 260A-105","200","6","Pig Runs - MFL-A/Cal/IMU 3/29","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420292 BERKSHR/TGP GREENFIELD MA HAMPSHIRE\n420106 EVRSRC/TGP GRANITE NORTHAMPTON MA H",260.11,null,"MLV 260A-103 to MLV 260A-105:  Pig Runs - MFL-A/Cal/IMU 3/29\n--3/29/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.  Potential out of path restrictions may be at risk.\n420292 BERKSHR/TGP GREENFIELD MA HAMPSHIRE\n420106 EVRSRC/TGP GRANITE NORTHAMPTON MA H\n………………………………"]
["X23-59496","***","2023-06-20","2023-06-20","Project Change","2023-06-13","2023-06-13","MLV 260A-101.1 TO MLV 260A-103","200","6","Pig Runs - Cleaning/Gauge: 6/20","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420104 WESTFLD/TGP WESTFIELD MA HAMPDEN\n420401 HOLYOKE/TGP HOLYOKE MA 2 HAMPDEN",260.11,"--start_date--end_date------mantenance_desc------model_loc--","***MLV 260A-101.1 TO MLV 260A-103:  Pig Runs - Cleaning/Gauge: 6/20\n--6/20/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.  Potential out of path restrictions may be at risk.\n420104 WESTFLD/TGP WESTFIELD MA HAMPDEN\n420401 HOLYOKE/TGP HOLYOKE MA 2 HAMPDEN\n***\nDate Change, Previously scheduled 6/13/23.\n………………………………"]
["X23-59500","***","2023-06-20","2023-06-20","Project Change","2023-06-14","2023-06-14","MLV 260A-101.1 TO MLV 260A-103","200","6","Pig Runs - MFL-A/Cal/IMU 6/20","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420104 WESTFLD/TGP WESTFIELD MA HAMPDEN\n420401 HOLYOKE/TGP HOLYOKE MA 2 HAMPDEN",260.12,"--start_date--end_date------mantenance_desc------model_loc--","***MLV 260A-101.1 TO MLV 260A-103:  Pig Runs - MFL-A/Cal/IMU 6/20\n--6/20/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.  Potential out of path restrictions may be at risk.\n420104 WESTFLD/TGP WESTFIELD MA HAMPDEN\n420401 HOLYOKE/TGP HOLYOKE MA 2 HAMPDEN\n***\nDate Change, Previously scheduled 6/14/23.\n………………………………"]
["X23-59574",null,"2023-07-17","2023-07-22",null,null,null,"MLV 261-1 to MLV 262-1","200","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,261.10000000000002,null,"MLV 261-1 to MLV 262-1:  Anomaly Remediation\n--7/17/23 through 7/22/23:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-59423","***","2023-06-12","2023-06-12","Project Change","2023-06-16","2023-06-16","MLV 261-2 TO MLV 267-2","200","6","Pig Runs - Cleaning/Gauge 6/12","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,261.2,"--start_date--end_date------mantenance_desc------model_loc--","***MLV 261-2 TO MLV 267-2:  Pig Runs - Cleaning/Gauge 6/12\n--6/12/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 6/16/23.\n………………………………"]
["X23-59424","***","2023-06-13","2023-06-13","Project Change","2023-06-20","2023-06-20","MLV 261-2 TO MLV 267-2","200","6","Pig Runs - Cal/IMU 6/13","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,261.20999999999998,"--start_date--end_date------mantenance_desc------model_loc--","***MLV 261-2 TO MLV 267-2:  Pig Runs - Cal/IMU 6/13\n--6/13/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 6/20/23.\n………………………………"]
["X23-59425","***","2023-06-14","2023-06-14","Project Change","2023-06-21","2023-06-21","MLV 261-2 TO MLV 267-2","200","6","Pig Runs - MFL-A 6/14","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,261.22000000000003,"--start_date--end_date------mantenance_desc------model_loc--","***MLV 261-2 TO MLV 267-2:  Pig Runs - MFL-A 6/14\n--6/14/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 6/21/23.\n………………………………"]
["X23-59576","***","2023-05-08","2023-06-10","Project Change","2023-05-02",null,"MLV 262-1 to MLV 263-1","200","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,262.10000000000002,"--start_date--------------model_loc--","***MLV 262-1 to MLV 263-1:  Anomaly Remediation\n--5/8/23 through 6/10/23:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 5/2/23 to 6/10/23.\n………………………………"]
["X23-59577",null,"2023-07-24","2023-07-29",null,null,null,"MLV 264-1 to MLV 265-1","200","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,264.10000000000002,null,"MLV 264-1 to MLV 265-1:  Anomaly Remediation\n--7/24/23 through 7/29/23:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-59494",null,"2023-06-06","2023-06-06",null,null,null,"MLV 265C-101.1 TO MLV 265C-102A","200","6","Pig Runs - Cleaning/Gauge 6/6","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420109 NSTAR/TGP WORCHESTER MA WORCHESTER",265.10000000000002,null,"MLV 265C-101.1 TO MLV 265C-102A:  Pig Runs - Cleaning/Gauge 6/6\n--6/6/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.  Potential out of path restrictions may be at risk.\n420109 NSTAR/TGP WORCHESTER MA WORCHESTER\n………………………………"]
["X23-59579",null,"2023-07-31","2023-08-05",null,null,null,"MLV 265-1 to MLV 266-1","200","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,265.10000000000002,null,"MLV 265-1 to MLV 266-1:  Anomaly Remediation\n--7/31/23 through 8/5/23:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-59495",null,"2023-06-07","2023-06-07",null,null,null,"MLV 265C-101.1 TO MLV 265C-102A","200","6","Pig Runs - MFL-A/Cal/IMU 6/7","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420109 NSTAR/TGP WORCHESTER MA WORCHESTER",265.11,null,"MLV 265C-101.1 TO MLV 265C-102A:  Pig Runs - MFL-A/Cal/IMU 6/7\n--6/7/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.  Potential out of path restrictions may be at risk.\n420109 NSTAR/TGP WORCHESTER MA WORCHESTER\n………………………………"]
["X23-59581","***","2023-04-24","2023-05-06","Project Change","2023-05-02","2023-05-13","MLV 266-1 to MLV 267-1","200","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,266.10000000000002,"--start_date--end_date------------model_loc--","***MLV 266-1 to MLV 267-1:  Anomaly Remediation\n--4/24/23 through 5/6/23:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 5/2/23 to 5/13/23.\n………………………………"]
["X23-59486",null,"2023-05-23","2023-05-23",null,null,null,"MLV 270C-101B TO MLV 270C-102","200","6","Pig Runs - Cleaning/Gauge 5/23","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420136 BOSTN/TGP READING MA MIDDLESEX\n420808 BOSTN/TGP CAMP CURTIS ESSEX",270.10000000000002,null,"MLV 270C-101B TO MLV 270C-102:  Pig Runs - Cleaning/Gauge 5/23\n--5/23/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.  Potential out of path restrictions may be at risk.\n420136 BOSTN/TGP READING MA MIDDLESEX\n420808 BOSTN/TGP CAMP CURTIS ESSEX\n………………………………"]
["X23-69684",null,"2023-05-31","2023-05-31",null,null,null,"MLV 270C-102 TO MLV 270C-104","200","6","Pig Runs - Cleaning/Gauge 5/31","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420658 BOSTN/TGP PEABODY SALES ESSEX\n420118 BOSTN/TGP BEVERLY SALEM MA ESSEX",270.10000000000002,null,"MLV 270C-102 TO MLV 270C-104:  Pig Runs - Cleaning/Gauge 5/31\n--5/31/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.  Potential out of path restrictions may be at risk.\n420658 BOSTN/TGP PEABODY SALES ESSEX\n420118 BOSTN/TGP BEVERLY SALEM MA ESSEX\n………………………………"]
["X23-59592",null,"2023-07-17","2023-07-29",null,null,null,"MLV 270B-101.1 to MLV 270B-102","200","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,270.10000000000002,null,"MLV 270B-101.1 to MLV 270B-102:  Anomaly Remediation\n--7/17/23 through 7/29/23:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-59489",null,"2023-05-24","2023-05-24",null,null,null,"MLV 270C-101B TO MLV 270C-102","200","6","Pig Runs - MFL-A/Cal/IMU 5/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420136 BOSTN/TGP READING MA MIDDLESEX\n420808 BOSTN/TGP CAMP CURTIS ESSEX",270.11,null,"MLV 270C-101B TO MLV 270C-102:  Pig Runs - MFL-A/Cal/IMU 5/24\n--5/24/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.  Potential out of path restrictions may be at risk.\n420136 BOSTN/TGP READING MA MIDDLESEX\n420808 BOSTN/TGP CAMP CURTIS ESSEX\n………………………………"]
["X23-69685",null,"2023-06-01","2023-06-01",null,null,null,"MLV 270C-102 TO MLV 270C-104","200","6","Pig Runs - MFL-A/Cal/IMU 6/1","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420658 BOSTN/TGP PEABODY SALES ESSEX\n420118 BOSTN/TGP BEVERLY SALEM MA ESSEX",270.11,null,"MLV 270C-102 TO MLV 270C-104:  Pig Runs - MFL-A/Cal/IMU 6/1\n--6/1/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.  Potential out of path restrictions may be at risk.\n420658 BOSTN/TGP PEABODY SALES ESSEX\n420118 BOSTN/TGP BEVERLY SALEM MA ESSEX\n………………………………"]
["X23-59417",null,"2023-05-16","2023-05-16",null,null,null,"MLV 270B-301 TO MLV 270B-302A","200","6","Pig Runs - Cleaning / Gauge 5/16","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,270.3,null,"MLV 270B-301 TO MLV 270B-302A:  Pig Runs - Cleaning / Gauge 5/16\n--5/16/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-59596",null,"2023-07-31","2023-08-05",null,null,null,"MLV 270B-302 to MLV 270B-302BR","200","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,270.3,null,"MLV 270B-302 to MLV 270B-302BR:  Anomaly Remediation\n--7/31/23 through 8/5/23:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-59419",null,"2023-05-17","2023-05-17",null,null,null,"MLV 270B-301 TO MLV 270B-302A","200","6","Pig Runs - Cal/IMU: 5/17","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,270.31,null,"MLV 270B-301 TO MLV 270B-302A:  Pig Runs - Cal/IMU: 5/17\n--5/17/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-59420",null,"2023-05-18","2023-05-18",null,null,null,"MLV 270B-301 TO MLV 270B-302A","200","6","Pig Runs - MFL-A: 5/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,270.32,null,"MLV 270B-301 TO MLV 270B-302A:  Pig Runs - MFL-A: 5/18\n--5/18/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-59591",null,"2023-06-12","2023-07-15",null,null,null,"MLV 270C-401 to MLV 270C-402","200","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420117 BOSTN/TGP LYNN MA ESSEX",270.39999999999998,null,"MLV 270C-401 to MLV 270C-402:  Anomaly Remediation\n--6/12/23 through 7/15/23:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be shut in during the project.  Potential out of path restrictions may be at risk.\n420117 BOSTN/TGP LYNN MA ESSEX\n………………………………"]
["X23-59407",null,"2023-03-21","2023-03-21",null,null,null,"MLV 270C-501 to MLV 270C-502","200","6","Pig Runs - Cleaning / Gauge 3/21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420935 BOSTN/TGP DANVERS ESSES\n420138 BOSTN/TGP WENHAM MA ESSEX\n420323 BOSTN/TGP ESSEX MA ESSEX\n420119 BOSTN/TGP GLOUCHESTER MA ESSEX",270.5,null,"MLV 270C-501 to MLV 270C-502:  Pig Runs - Cleaning / Gauge 3/21\n--3/21/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.  Potential out of path restrictions may be at risk.\n420935 BOSTN/TGP DANVERS ESSES\n420138 BOSTN/TGP WENHAM MA ESSEX\n420323 BOSTN/TGP ESSEX MA ESSEX\n420119 BOSTN/TGP GLOUCHESTER MA ESSEX\n………………………………"]
["X23-59586",null,"2023-05-15","2023-06-17",null,null,null,"MLV 270C-501 to MLV 270C-502","200","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420323 BOSTN/TGP ESSEX MA ESSEX\n420119 BOSTN/TGP GLOUCHESTER MA ESSEX",270.5,null,"MLV 270C-501 to MLV 270C-502:  Anomaly Remediation\n--5/15/23 through 6/17/23:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be shut in during the project.  Potential out of path restrictions may be at risk.\n420323 BOSTN/TGP ESSEX MA ESSEX\n420119 BOSTN/TGP GLOUCHESTER MA ESSEX\n………………………………"]
["X23-59408",null,"2023-03-23","2023-03-23",null,null,null,"MLV 270C-501 to MLV 270C-502","200","6","Pig Runs - MFL-A/Cal/IMU 3/23","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420935 BOSTN/TGP DANVERS ESSES\n420138 BOSTN/TGP WENHAM MA ESSEX\n420323 BOSTN/TGP ESSEX MA ESSEX\n420119 BOSTN/TGP GLOUCHESTER MA ESSEX",270.51,null,"MLV 270C-501 to MLV 270C-502:  Pig Runs - MFL-A/Cal/IMU 3/23\n--3/23/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.  Potential out of path restrictions may be at risk.\n420935 BOSTN/TGP DANVERS ESSES\n420138 BOSTN/TGP WENHAM MA ESSEX\n420323 BOSTN/TGP ESSEX MA ESSEX\n420119 BOSTN/TGP GLOUCHESTER MA ESSEX\n………………………………"]
["X23-59468",null,"2023-04-04","2023-04-04",null,null,null,"MLV 273B-101BL to MLV 273B-105A","200","6","Pig Runs - Cleaning/Gauge 4/4","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420121 EVRSRC/TGP LAWRENCE MA ESSEX\n412510 MARITIME/TGP HAVERHILL PORTLAND ESS\n420206 GRANSTGT/TGP GRANITE MA ESSEX\n420122 BOSTN/TGP HAVERHILL MA ESSEX",273.10000000000002,null,"MLV 273B-101BL to MLV 273B-105A:  Pig Runs - Cleaning/Gauge 4/4\n--4/4/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.  Potential out of path restrictions may be at risk.\n420121 EVRSRC/TGP LAWRENCE MA ESSEX\n412510 MARITIME/TGP HAVERHILL PORTLAND ESS\n420206 GRANSTGT/TGP GRANITE MA ESSEX\n420122 BOSTN/TGP HAVERHILL MA ESSEX\n………………………………"]
["X23-59471",null,"2023-04-05","2023-04-05",null,null,null,"MLV 273B-101BL to MLV 273B-105A","200","6","Pig Runs - MFL-A/Cal/IMU 4/5","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420121 EVRSRC/TGP LAWRENCE MA ESSEX\n412510 MARITIME/TGP HAVERHILL PORTLAND ESS\n420206 GRANSTGT/TGP GRANITE MA ESSEX\n420122 BOSTN/TGP HAVERHILL MA ESSEX",273.11,null,"MLV 273B-101BL to MLV 273B-105A:  Pig Runs - MFL-A/Cal/IMU 4/5\n--4/5/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.  Potential out of path restrictions may be at risk.\n420121 EVRSRC/TGP LAWRENCE MA ESSEX\n412510 MARITIME/TGP HAVERHILL PORTLAND ESS\n420206 GRANSTGT/TGP GRANITE MA ESSEX\n420122 BOSTN/TGP HAVERHILL MA ESSEX\n………………………………"]
["X23-59476",null,"2023-04-11","2023-04-11",null,null,null,"MLV 273C-101BL to MLV 273C-103C","200","6","Pig Runs - Cleaning/Gauge 4/11","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420132 LIBERTYU/TGP NASHUA NH HILLSBOROUGH\n420931 LIBERTYU/TGP GRANITE RIDGE ROCKINGH\n420632 LIBERTYU/TGP LONDONDERRY SALES ROCK\n420133 LIBERTYU/TGP MANCHESTER NH HILLSBOR\n420254 LIBERTYU/TGP HOOKSETT NH MERRIMACK\n49831 NG ADVAN/TGP CNG PEMBROKE RECEIPT M\n420426 LIBERTYU/TGP LACONIA NH MERRIMACK",273.12,null,"MLV 273C-101BL to MLV 273C-103C:  Pig Runs - Cleaning/Gauge 4/11\n--4/11/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.  Potential out of path restrictions may be at risk.\n420132 LIBERTYU/TGP NASHUA NH HILLSBOROUGH\n420931 LIBERTYU/TGP GRANITE RIDGE ROCKINGH\n420632 LIBERTYU/TGP LONDONDERRY SALES ROCK\n420133 LIBERTYU/TGP MANCHESTER NH HILLSBOR\n420254 LIBERTYU/TGP HOOKSETT NH MERRIMACK\n49831 NG ADVAN/TGP CNG PEMBROKE RECEIPT M\n420426 LIBERTYU/TGP LACONIA NH MERRIMACK\n………………………………"]
["X23-59477",null,"2023-04-12","2023-04-12",null,null,null,"MLV 273C-101BL to MLV 273C-103C","200","6","Pig Runs - MFL-A/Cal/IMU 4/12","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420132 LIBERTYU/TGP NASHUA NH HILLSBOROUGH\n420931 LIBERTYU/TGP GRANITE RIDGE ROCKINGH\n420632 LIBERTYU/TGP LONDONDERRY SALES ROCK\n420133 LIBERTYU/TGP MANCHESTER NH HILLSBOR\n420254 LIBERTYU/TGP HOOKSETT NH MERRIMACK\n49831 NG ADVAN/TGP CNG PEMBROKE RECEIPT M\n420426 LIBERTYU/TGP LACONIA NH MERRIMACK",273.13,null,"MLV 273C-101BL to MLV 273C-103C:  Pig Runs - MFL-A/Cal/IMU 4/12\n--4/12/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.  Potential out of path restrictions may be at risk.\n420132 LIBERTYU/TGP NASHUA NH HILLSBOROUGH\n420931 LIBERTYU/TGP GRANITE RIDGE ROCKINGH\n420632 LIBERTYU/TGP LONDONDERRY SALES ROCK\n420133 LIBERTYU/TGP MANCHESTER NH HILLSBOR\n420254 LIBERTYU/TGP HOOKSETT NH MERRIMACK\n49831 NG ADVAN/TGP CNG PEMBROKE RECEIPT M\n420426 LIBERTYU/TGP LACONIA NH MERRIMACK\n………………………………"]
["X23-27232","***","2023-02-06","2023-02-16","Project Change",null,null,"Sta 307","300","4","Unit 2A - Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,307.00200000000001,"------------prl----model_loc--","***Sta 307:  Unit 2A - Engine Inspection\n--2/6/23 through 2/16/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***Project Change\n………………………………"]
["X22-750865",null,"2022-07-27","2023-05-28",null,null,null,"MLV 307-1 to MLV 313-1","300","4","FORCE MAJEURE - Pressure Reduction","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed below will have capacity limitations.","SIP","Potential in the path restrictions may be at risk.","47743 NFGMIDCL/TGP CLERMONT #2 MC KEAN",309.08999999999997,null,"MLV 307-1 to MLV 313-1:  FORCE MAJEURE - Pressure Reduction\n--7/27/22 through 5/28/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed below will have capacity limitations.  Potential in the path restrictions may be at risk.\n47743 NFGMIDCL/TGP CLERMONT #2 MC KEAN\n………………………………"]
["X22-707226",null,"2022-07-13","2023-05-28",null,null,null,"MLV 309-1 to MLV 310-1","300","4","FORCE MAJEURE - Line 1 OOS","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,309.10000000000002,null,"MLV 309-1 to MLV 310-1:  FORCE MAJEURE - Line 1 OOS\n--7/13/22 through 5/28/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X22-1106455","***","2023-04-24","2023-05-01","Project Change",null,"2023-04-30","Ellisburg Storage","300","4","Shut-in Test","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","460012 – DOMINION/TGP ELLISBURG INJECTION PO",312.05500000000001,"----end_date------------model_loc--","***Ellisburg Storage:  Shut-in Test\n--4/24/23 through 5/1/23:  This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.  Potential out of path restrictions may be at risk.\n460012 – DOMINION/TGP ELLISBURG INJECTION PO\n***\nDate Change, Previously scheduled 4/24/23 to 4/30/23.\n………………………………"]
["X23-100956","***","2023-03-20","2023-03-27","Added",null,null,"Harrison Storage","300","4","Shut-in Test","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","460004 – DOMINION/TGP HARRISON INJECTION POT",313.5,"------","***Harrison Storage:  Shut-in Test\n--3/20/23 through 3/27/23:  This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.  Potential out of path restrictions may be at risk.\n460004 – DOMINION/TGP HARRISON INJECTION POT\n***Added\n………………………………"]
["X22-1140991","***","2023-04-24","2023-05-01","Project Change",null,"2023-04-30","Hebron Storage","300","4","Shut-in Test","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","400485 HEBRON STORAGE INJECTION POTTER\n470001 HEBRON STORAGE WITHDRAWAL POTTER",313.5,"----end_date------------model_loc--","***Hebron Storage:  Shut-in Test\n--4/24/23 through 5/1/23:  This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.  Potential out of path restrictions may be at risk.\n400485 HEBRON STORAGE INJECTION POTTER\n470001 HEBRON STORAGE WITHDRAWAL POTTER\n***\nDate Change, Previously scheduled 4/24/23 to 4/30/23.\n………………………………"]
["X23-40821",null,"2023-05-23","2023-05-23",null,null,null,"MLVS 313G-100","300","4","Pig run - Cleaning 5/23","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,313.51,null,"MLVS 313G-100:  Pig run - Cleaning 5/23\n--5/23/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-40825",null,"2023-05-25","2023-05-25",null,null,null,"MLVS 313G-100","300","4","Pig run - MFL 5/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,313.52,null,"MLVS 313G-100:  Pig run - MFL 5/25\n--5/25/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-40826",null,"2023-05-30","2023-05-30",null,null,null,"MLVS 313G-100","300","4","Pig run - Cleaning 5/30","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,313.52999999999997,null,"MLVS 313G-100:  Pig run - Cleaning 5/30\n--5/30/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-40829",null,"2023-06-01","2023-06-01",null,null,null,"MLVS 313G-100","300","4","Pig run - MFL 6/1","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,313.54000000000002,null,"MLVS 313G-100:  Pig run - MFL 6/1\n--6/1/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-40843","***","2023-08-21","2023-09-08","Added",null,null,"MLVS C313-0605","300","4","Pig Runs (Tethered) - Cleaning 8/29","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in for the duration of the project.","SOP","Potential out of path restrictions may be at risk.","400485 HEBRON STORAGE INJECTION POTTER\n470001 HEBRON STORAGE WITHDRAWAL POTTER",313.8,"------","***MLVS C313-0605:  Pig Runs (Tethered) - Cleaning 8/29\n--8/21/23 through 9/8/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in for the duration of the project.  Potential out of path restrictions may be at risk.\n400485 HEBRON STORAGE INJECTION POTTER\n470001 HEBRON STORAGE WITHDRAWAL POTTER\n***Added\n………………………………"]
["X23-40844","***","2023-08-21","2023-09-08","Added",null,null,"MLVS C313-0605","300","4","Pig Runs (Tethered) - MFL 8/31","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in for the duration of the project.","SOP","Potential out of path restrictions may be at risk.","400485 HEBRON STORAGE INJECTION POTTER\n470001 HEBRON STORAGE WITHDRAWAL POTTER",313.81,"------","***MLVS C313-0605:  Pig Runs (Tethered) - MFL 8/31\n--8/21/23 through 9/8/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in for the duration of the project.  Potential out of path restrictions may be at risk.\n400485 HEBRON STORAGE INJECTION POTTER\n470001 HEBRON STORAGE WITHDRAWAL POTTER\n***Added\n………………………………"]
["X23-40839","***","2023-08-21","2023-09-08","Added",null,null,"MLVS C313-0606","300","4","Pig Runs (Tethered) - Cleaning / Gauge 8/29","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in for the duration of the project.","SOP","Potential out of path restrictions may be at risk.","400485 HEBRON STORAGE INJECTION POTTER\n470001 HEBRON STORAGE WITHDRAWAL POTTER",313.85000000000002,"------","***MLVS C313-0606:  Pig Runs (Tethered) - Cleaning / Gauge 8/29\n--8/21/23 through 9/8/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in for the duration of the project.  Potential out of path restrictions may be at risk.\n400485 HEBRON STORAGE INJECTION POTTER\n470001 HEBRON STORAGE WITHDRAWAL POTTER\n***Added\n………………………………"]
["X23-40841","***","2023-08-21","2023-09-08","Added",null,null,"MLVS C313-0606","300","4","Pig Runs (Tethered) - MFL 8/30","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in for the duration of the project.","SOP","Potential out of path restrictions may be at risk.","400485 HEBRON STORAGE INJECTION POTTER\n470001 HEBRON STORAGE WITHDRAWAL POTTER",313.86,"------","***MLVS C313-0606:  Pig Runs (Tethered) - MFL 8/30\n--8/21/23 through 9/8/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in for the duration of the project.  Potential out of path restrictions may be at risk.\n400485 HEBRON STORAGE INJECTION POTTER\n470001 HEBRON STORAGE WITHDRAWAL POTTER\n***Added\n………………………………"]
["X23-40833",null,"2023-06-20","2023-06-20",null,null,null,"MLV 317-1 to MLV 313-1","300","4","Pig run - Cleaning 6/20","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,317.10000000000002,null,"MLV 317-1 to MLV 313-1:  Pig run - Cleaning 6/20\n--6/20/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-40834",null,"2023-06-22","2023-06-22",null,null,null,"MLV 317-1 to MLV 313-1","300","4","Pig run - MFL 6/22","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,317.11,null,"MLV 317-1 to MLV 313-1:  Pig run - MFL 6/22\n--6/22/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-40836",null,"2023-07-11","2023-07-11",null,null,null,"MLV 317-2 to MLV 315-2","300","4","Pig run - Cleaning 7/11","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,317.2,null,"MLV 317-2 to MLV 315-2:  Pig run - Cleaning 7/11\n--7/11/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-40838",null,"2023-07-13","2023-07-13",null,null,null,"MLV 317-2 to MLV 315-2","300","4","Pig run - MFL 7/13","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,317.20999999999998,null,"MLV 317-2 to MLV 315-2:  Pig run - MFL 7/13\n--7/13/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-40810","***","2023-04-04","2023-04-04","Project Change",null,null,"MLV 319-1 to MLV 321-1","300","4","Pig run - Cleaning 4/4","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.","SIP","Potential in the path restrictions may be at risk.","412832 APPLACHA/TGP LATINI DEY: RIP 319C\n412833 REPSOLOG/TGP SILVARA DEHY: RIP 319F\n412835 SEPCO/TGP KATIE DEHY: RIP 319G 101.\n412846 APPLACHA/TGP UDP SHOEMAKER DEHY: RI\n420443 UGI UT/TGP AUBURN PA SUSQUEHANNA\n412841 UGI/TGP UDP AUBURN DEHY: RIP 320 1\n412782 APPLACHA/TGP LOTT DEHY: RIP 320D 10\n412821 ETC NEPL/TGP DIMOCK DEHY: RIP 320J\n412751 WFS/TGP UDP HOP BOTTOM DEHY: RIP 32",319.10000000000002,"------meters_affected----------model_loc--","***MLV 319-1 to MLV 321-1:  Pig run - Cleaning 4/4\n--4/4/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.  Potential in the path restrictions may be at risk.\n412832 APPLACHA/TGP LATINI DEY: RIP 319C\n412833 REPSOLOG/TGP SILVARA DEHY: RIP 319F\n412835 SEPCO/TGP KATIE DEHY: RIP 319G 101.\n412846 APPLACHA/TGP UDP SHOEMAKER DEHY: RI\n420443 UGI UT/TGP AUBURN PA SUSQUEHANNA\n412841 UGI/TGP UDP AUBURN DEHY: RIP 320 1\n412782 APPLACHA/TGP LOTT DEHY: RIP 320D 10\n412821 ETC NEPL/TGP DIMOCK DEHY: RIP 320J\n412751 WFS/TGP UDP HOP BOTTOM DEHY: RIP 32\n***Project Change\n………………………………"]
["X23-40830",null,"2023-06-06","2023-06-06",null,null,null,"MLV 319-1 to MLV 317-1","300","4","Pig run - Cleaning 6/6","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,319.10000000000002,null,"MLV 319-1 to MLV 317-1:  Pig run - Cleaning 6/6\n--6/6/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-40811","***","2023-04-05","2023-04-05","Project Change",null,null,"MLV 319-1 to MLV 321-1","300","4","Pig run - Caliper 4/5","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.","SIP","Potential in the path restrictions may be at risk.","412832 APPLACHA/TGP LATINI DEY: RIP 319C\n412833 REPSOLOG/TGP SILVARA DEHY: RIP 319F\n412835 SEPCO/TGP KATIE DEHY: RIP 319G 101.\n412846 APPLACHA/TGP UDP SHOEMAKER DEHY: RI\n420443 UGI UT/TGP AUBURN PA SUSQUEHANNA\n412841 UGI/TGP UDP AUBURN DEHY: RIP 320 1\n412782 APPLACHA/TGP LOTT DEHY: RIP 320D 10\n412821 ETC NEPL/TGP DIMOCK DEHY: RIP 320J\n412751 WFS/TGP UDP HOP BOTTOM DEHY: RIP 32",319.11,"------meters_affected----------model_loc--","***MLV 319-1 to MLV 321-1:  Pig run - Caliper 4/5\n--4/5/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.  Potential in the path restrictions may be at risk.\n412832 APPLACHA/TGP LATINI DEY: RIP 319C\n412833 REPSOLOG/TGP SILVARA DEHY: RIP 319F\n412835 SEPCO/TGP KATIE DEHY: RIP 319G 101.\n412846 APPLACHA/TGP UDP SHOEMAKER DEHY: RI\n420443 UGI UT/TGP AUBURN PA SUSQUEHANNA\n412841 UGI/TGP UDP AUBURN DEHY: RIP 320 1\n412782 APPLACHA/TGP LOTT DEHY: RIP 320D 10\n412821 ETC NEPL/TGP DIMOCK DEHY: RIP 320J\n412751 WFS/TGP UDP HOP BOTTOM DEHY: RIP 32\n***Project Change\n………………………………"]
["X23-40832",null,"2023-06-08","2023-06-08",null,null,null,"MLV 319-1 to MLV 317-1","300","4","Pig run - MFL 6/8","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,319.11,null,"MLV 319-1 to MLV 317-1:  Pig run - MFL 6/8\n--6/8/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-40813","***","2023-04-06","2023-04-06","Project Change",null,null,"MLV 319-1 to MLV 321-1","300","4","Pig run - MFL 4/6","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.","SIP","Potential in the path restrictions may be at risk.","412832 APPLACHA/TGP LATINI DEY: RIP 319C\n412833 REPSOLOG/TGP SILVARA DEHY: RIP 319F\n412835 SEPCO/TGP KATIE DEHY: RIP 319G 101.\n412846 APPLACHA/TGP UDP SHOEMAKER DEHY: RI\n420443 UGI UT/TGP AUBURN PA SUSQUEHANNA\n412841 UGI/TGP UDP AUBURN DEHY: RIP 320 1\n412782 APPLACHA/TGP LOTT DEHY: RIP 320D 10\n412821 ETC NEPL/TGP DIMOCK DEHY: RIP 320J\n412751 WFS/TGP UDP HOP BOTTOM DEHY: RIP 32",319.12,"------meters_affected----------model_loc--","***MLV 319-1 to MLV 321-1:  Pig run - MFL 4/6\n--4/6/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.  Potential in the path restrictions may be at risk.\n412832 APPLACHA/TGP LATINI DEY: RIP 319C\n412833 REPSOLOG/TGP SILVARA DEHY: RIP 319F\n412835 SEPCO/TGP KATIE DEHY: RIP 319G 101.\n412846 APPLACHA/TGP UDP SHOEMAKER DEHY: RI\n420443 UGI UT/TGP AUBURN PA SUSQUEHANNA\n412841 UGI/TGP UDP AUBURN DEHY: RIP 320 1\n412782 APPLACHA/TGP LOTT DEHY: RIP 320D 10\n412821 ETC NEPL/TGP DIMOCK DEHY: RIP 320J\n412751 WFS/TGP UDP HOP BOTTOM DEHY: RIP 32\n***Project Change\n………………………………"]
["X22-804509",null,"2023-07-18","2023-09-22",null,null,null,"Sta 321","300","4","Turbo Compressor Tie-In","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,321,null,"Sta 321:  Turbo Compressor Tie-In\n--7/18/23 through 9/22/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-40817",null,"2023-05-09","2023-05-09",null,null,null,"MLV 321-1 to MLV 325-1","300","5","Pig run - Cleaning 5/9","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,321.10000000000002,null,"MLV 321-1 to MLV 325-1:  Pig run - Cleaning 5/9\n--5/9/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-40819",null,"2023-05-11","2023-05-11",null,null,null,"MLV 321-1 to MLV 325-1","300","5","Pig run - MFL 5/11","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,321.11,null,"MLV 321-1 to MLV 325-1:  Pig run - MFL 5/11\n--5/11/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-485078",null,"2023-09-02","2023-09-12",null,null,null,"MLV 324-1A to MLV 326-1","300","5","Install New Sta 325 Unit","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.",null,324.10000000000002,null,"MLV 324-1A to MLV 326-1:  Install New Sta 325 Unit\n--9/2/23 through 9/12/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be shut in during the project.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-74557",null,"2023-05-22","2023-05-27",null,null,null,"Sta 325","300","5","Unit 3A - Turbine Exchange","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,325.00299999999999,null,"Sta 325:  Unit 3A - Turbine Exchange\n--5/22/23 through 5/27/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-74559",null,"2023-05-31","2023-06-01",null,null,null,"Sta 325","300","5","Unit 4A - Borescope and Water Wash","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,325.00400000000002,null,"Sta 325:  Unit 4A - Borescope and Water Wash\n--5/31/23 through 6/1/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-59570",null,"2023-05-02","2023-05-06",null,null,null,"MLV 327-1 to MLV 329-1","300","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,327.10000000000002,null,"MLV 327-1 to MLV 329-1:  Anomaly Remediation\n--5/2/23 through 5/6/23:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X22-485076",null,"2023-09-06","2023-09-13",null,null,null,"MLV 327-1A to MLV 328-1","300","5","Install New Sta 327","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.",null,327.10000000000002,null,"MLV 327-1A to MLV 328-1:  Install New Sta 327\n--9/6/23 through 9/13/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be shut in during the project.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-485077",null,"2023-09-15","2023-09-22",null,null,null,"MLV 327-2A to MLV 328-2","300","5","Install New Sta 327","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,327.2,null,"MLV 327-2A to MLV 328-2:  Install New Sta 327\n--9/15/23 through 9/22/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-1161061",null,"2023-06-24","2023-07-15",null,null,null,"MLV 352-1 to MLV 353-1","300","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be shut in during the project.","PIP","Potential in the path restrictions may be at risk.","420123 CONN NG/TGP GREENWICH CT FAIRFIELD\n420217 CONN NG/TGP PUTNAM LAKE CT FAIRFIEL\n420434 YANK GAS/TGP LONG RIDGE CT FAIRFIEL\n420124 YANK GAS/TGP STAMFORD CT FAIRFIELD\n420125 YANK GAS/TGP NORWALK CT FAIRFIELD\n420490 CONN NG/TGP WEST PORT CT FAIRFIELD\n420853 CONN NG/TGP EASTON SMS FAIRFIELD\n420126 COMM NG/TGP BRIDGEPORT CT FAIRFIELD",352.1,null,"MLV 352-1 to MLV 353-1:  Anomaly Remediation\n--6/24/23 through 7/15/23:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be shut in during the project.  Potential in the path restrictions may be at risk.\n420123 CONN NG/TGP GREENWICH CT FAIRFIELD\n420217 CONN NG/TGP PUTNAM LAKE CT FAIRFIEL\n420434 YANK GAS/TGP LONG RIDGE CT FAIRFIEL\n420124 YANK GAS/TGP STAMFORD CT FAIRFIELD\n420125 YANK GAS/TGP NORWALK CT FAIRFIELD\n420490 CONN NG/TGP WEST PORT CT FAIRFIELD\n420853 CONN NG/TGP EASTON SMS FAIRFIELD\n420126 COMM NG/TGP BRIDGEPORT CT FAIRFIELD\n………………………………"]
["X23-108324","***","2023-09-19","2023-09-19","Added",null,null,"MLV 400-1 to MLV 409-1","400","0","Pig Run - Cleaning 9/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,400.1,"------","***MLV 400-1 to MLV 409-1:  Pig Run - Cleaning 9/19\n--9/19/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X23-108455","***","2023-09-21","2023-09-21","Added",null,null,"MLV 400-1 to MLV 409-1","400","0","Pig Run - Cleaning 9/21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,400.11,"------","***MLV 400-1 to MLV 409-1:  Pig Run - Cleaning 9/21\n--9/21/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X23-108500","***","2023-09-23","2023-09-23","Added",null,null,"MLV 400-1 to MLV 409-1","400","0","Pig Run - Cleaning 9/23","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,400.12,"------","***MLV 400-1 to MLV 409-1:  Pig Run - Cleaning 9/23\n--9/23/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X23-108538","***","2023-09-25","2023-09-25","Added",null,null,"MLV 400-1 to MLV 409-1","400","0","Pig Run - Gauge 9/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,400.13,"------","***MLV 400-1 to MLV 409-1:  Pig Run - Gauge 9/25\n--9/25/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X23-108570","***","2023-09-27","2023-09-27","Added",null,null,"MLV 400-1 to MLV 409-1","400","0","Pig Run - CLP/MFL/IMU 9/27","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,400.14,"------","***MLV 400-1 to MLV 409-1:  Pig Run - CLP/MFL/IMU 9/27\n--9/27/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X23-108660","***","2023-08-25","2023-08-25","Added",null,null,"MLV 400-2 to MLV 409-2","400","0","Pig Run - Cleaning 8/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,400.2,"------","***MLV 400-2 to MLV 409-2:  Pig Run - Cleaning 8/25\n--8/25/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X23-108843","***","2023-08-28","2023-08-28","Added",null,null,"MLV 400-2 to MLV 409-2","400","0","Pig Run - Cleaning 8/28","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,400.21,"------","***MLV 400-2 to MLV 409-2:  Pig Run - Cleaning 8/28\n--8/28/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X23-108894","***","2023-08-30","2023-08-30","Added",null,null,"MLV 400-2 to MLV 409-2","400","0","Pig Run - Cleaning 8/30","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,400.22,"------","***MLV 400-2 to MLV 409-2:  Pig Run - Cleaning 8/30\n--8/30/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X23-108923","***","2023-09-01","2023-09-01","Added",null,null,"MLV 400-2 to MLV 409-2","400","0","Pig Run - Gauge 9/01","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,400.23,"------","***MLV 400-2 to MLV 409-2:  Pig Run - Gauge 9/01\n--9/1/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X23-108950","***","2023-09-06","2023-09-06","Added",null,null,"MLV 400-2 to MLV 409-2","400","0","Pig Run - CLP/MFL/IMU 9/06","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,400.24,"------","***MLV 400-2 to MLV 409-2:  Pig Run - CLP/MFL/IMU 9/06\n--9/6/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X23-71193",null,"2023-06-16","2023-06-30",null,null,null,"MLV 407-1 TO MLV 408-1","400","0","Class Change","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,407.1,null,"MLV 407-1 TO MLV 408-1:  Class Change\n--6/16/23 through 6/30/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-71197",null,"2023-07-01","2023-08-31",null,null,null,"MLV 407-2 TO MLV 408-2","400","0","Class Change","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","411725 EXPORT/TGP LOS INDIOS DEHY HIDALGO\n412628 SAMSON/TGP LOS INDIOS 3 HIDALGO",407.2,null,"MLV 407-2 TO MLV 408-2:  Class Change\n--7/1/23 through 8/31/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be shut in during the project.  Potential out of path restrictions may be at risk.\n411725 EXPORT/TGP LOS INDIOS DEHY HIDALGO\n412628 SAMSON/TGP LOS INDIOS 3 HIDALGO\n………………………………"]
["X23-24575",null,"2023-03-12","2023-03-19",null,null,null,"Sta 409","400","0","New Unit Mechanical & Electrical Tie-Ins","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,409,null,"Sta 409:  New Unit Mechanical & Electrical Tie-Ins\n--3/12/23 through 3/19/23:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X23-99669","***","2023-04-19","2023-04-21","Added",null,null,"Sta 409A","400","0","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,409,"------","***Sta 409A:  Annual ESD Test\n--4/19/23 through 4/21/23:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***Added\n………………………………"]
["X23-71192",null,"2023-06-01","2023-06-15",null,null,null,"MLV 409-101 TO MLV 409-101B","400","0","Class Change","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","421067 CALPINE/TGP HIDALGO",409.1,null,"MLV 409-101 TO MLV 409-101B:  Class Change\n--6/1/23 through 6/15/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n421067 CALPINE/TGP HIDALGO\n………………………………"]
["X23-101027","***","2023-03-12","2023-03-19","Added",null,null,"Sta 409","400","0","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,409.5,"------","***Sta 409:  Annual ESD Test & Maintenance\n--3/12/23 through 3/19/23:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X22-134673","***","2023-02-14","2023-02-14","Project Change",null,null,"Sta 500-1 to Sta 823 (MLV 507-1)","500","L","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420373 TRNSCO/TGP KINDER LA EXCH (BI 1420708 ELIZ NG/TGP GRANT LA SALES ALLEN420436 VERNON/TGP PITKIN LA VERNON420793 ELIZ NG/TGP J R FRANKS 1 VERNON420388 PROVNCAL/TGP PROVENCAL LA NATCHITOC",500.1,"------meters_affected----------model_loc--","***Sta 500-1 to Sta 823 (MLV 507-1):  Maintenance Pig\n--2/14/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n420373 TRNSCO/TGP KINDER LA EXCH (BI 1420708 ELIZ NG/TGP GRANT LA SALES ALLEN420436 VERNON/TGP PITKIN LA VERNON420793 ELIZ NG/TGP J R FRANKS 1 VERNON420388 PROVNCAL/TGP PROVENCAL LA NATCHITOC\n***Project Change\n………………………………"]
["X23-101117","***","2023-11-07","2023-11-07","Added",null,null,"Sta 500-1 to Sta 823 (MLV 507-1)","500","1","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420373 TRNSCO/TGP KINDER LA EXCH (BI 1420708 ELIZ NG/TGP GRANT LA SALES ALLEN420436 VERNON/TGP PITKIN LA VERNON420793 ELIZ NG/TGP J R FRANKS 1 VERNON420388 PROVNCAL/TGP PROVENCAL LA NATCHITOC",500.11,"------","***Sta 500-1 to Sta 823 (MLV 507-1):  Maintenance Pig\n--11/7/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n420373 TRNSCO/TGP KINDER LA EXCH (BI 1420708 ELIZ NG/TGP GRANT LA SALES ALLEN420436 VERNON/TGP PITKIN LA VERNON420793 ELIZ NG/TGP J R FRANKS 1 VERNON420388 PROVNCAL/TGP PROVENCAL LA NATCHITOC\n***Added\n………………………………"]
["X23-101118","***","2023-09-13","2023-09-13","Added",null,null,"STA 507F to Sta 823","500","L","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,507,"------","***STA 507F to Sta 823:  Maintenance Pig\n--9/13/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X23-113749","***","2023-05-16","2023-05-18","Added",null,null,"MLV 507K-101 TO MLV 507K-104","500","L","Pig Runs - Cleaning 5/16 to 5/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412716 BRAMMER/TGP HILDA HENRY NO 1 JEFFER\n412680 TRUNKLNE/TGP LACASSINE JEFFERSON DA\n420493 COKINOS/TGP MALLETT FARM LA JEFFERS",507.1,"------","***MLV 507K-101 TO MLV 507K-104:  Pig Runs - Cleaning 5/16 to 5/18\n--5/16/23 through 5/18/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n412716 BRAMMER/TGP HILDA HENRY NO 1 JEFFER\n412680 TRUNKLNE/TGP LACASSINE JEFFERSON DA\n420493 COKINOS/TGP MALLETT FARM LA JEFFERS\n***Added\n………………………………"]
["X23-113750","***","2023-05-19","2023-05-19","Added",null,null,"MLV 507K-101 TO MLV 507K-104","500","L","Pig Runs - Gauge Pig 5/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412716 BRAMMER/TGP HILDA HENRY NO 1 JEFFER\n412680 TRUNKLNE/TGP LACASSINE JEFFERSON DA\n420493 COKINOS/TGP MALLETT FARM LA JEFFERS",507.12,"------","***MLV 507K-101 TO MLV 507K-104:  Pig Runs - Gauge Pig 5/19\n--5/19/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n412716 BRAMMER/TGP HILDA HENRY NO 1 JEFFER\n412680 TRUNKLNE/TGP LACASSINE JEFFERSON DA\n420493 COKINOS/TGP MALLETT FARM LA JEFFERS\n***Added\n………………………………"]
["X23-113751","***","2023-05-25","2023-05-25","Added",null,null,"MLV 507K-101 TO MLV 507K-104","500","L","Pig Runs - CLP / MFL-A / IMU 5/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412716 BRAMMER/TGP HILDA HENRY NO 1 JEFFER\n412680 TRUNKLNE/TGP LACASSINE JEFFERSON DA\n420493 COKINOS/TGP MALLETT FARM LA JEFFERS",507.13,"------","***MLV 507K-101 TO MLV 507K-104:  Pig Runs - CLP / MFL-A / IMU 5/25\n--5/25/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n412716 BRAMMER/TGP HILDA HENRY NO 1 JEFFER\n412680 TRUNKLNE/TGP LACASSINE JEFFERSON DA\n420493 COKINOS/TGP MALLETT FARM LA JEFFERS\n***Added\n………………………………"]
["X22-1102761",null,"2023-04-24","2023-04-24",null,null,null,"MLV 516-1 to MLV 523-1","500","L","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,516.1,null,"MLV 516-1 to MLV 523-1:  Maintenance Pig\n--4/24/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-1102770",null,"2023-04-24","2023-04-24",null,null,null,"MLV 523-1 to MLV 524-1","500","L","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,523.1,null,"MLV 523-1 to MLV 524-1:  Maintenance Pig\n--4/24/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-24537",null,"2023-04-24","2023-05-03",null,null,null,"MLV 523-1R to MLV 516-1","500","L","Pig Runs - Chem Cleaning & Gauge 4/24/23 to 4/29/23, Combo 5/1/23, AFD 5/3/23","'This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,523.1,null,"MLV 523-1R to MLV 516-1:  Pig Runs - Chem Cleaning & Gauge 4/24/23 to 4/29/23, Combo 5/1/23, AFD 5/3/23\n--4/24/23 through 5/3/23:  'This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-24536",null,"2023-04-10","2023-04-17",null,null,null,"MLV 523-2 to MLV 524-2","500","L","Pig Runs - Cleaning & Gauge 4/10/23 to 4/15/23, Combo 4/17/23","'This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,523.20000000000005,null,"MLV 523-2 to MLV 524-2:  Pig Runs - Cleaning & Gauge 4/10/23 to 4/15/23, Combo 4/17/23\n--4/10/23 through 4/17/23:  'This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-24529",null,"2023-02-15","2023-02-28",null,null,null,"MLV 524-2 to MLV 527-2","500","L","Pig Runs - Cleaning & Gauge 2/15/23 to 2/27/23, Combo 2/28/23","'This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,524.20000000000005,null,"MLV 524-2 to MLV 527-2:  Pig Runs - Cleaning & Gauge 2/15/23 to 2/27/23, Combo 2/28/23\n--2/15/23 through 2/28/23:  'This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-1146576",null,"2023-04-10","2023-04-15",null,null,null,"Sta 527","500","L","Station 115 KV Line Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,527.1,null,"Sta 527:  Station 115 KV Line Maintenance\n--4/10/23 through 4/15/23:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-929648","***","2023-02-28","2023-02-28","Project Change","2023-01-31","2023-01-31","MLV 527-3 to MLV 529-3","500","L","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,527.29999999999995,"--start_date--end_date------------model_loc--","***MLV 527-3 to MLV 529-3:  Maintenance Pig\n--2/28/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 1/31/23.\n………………………………"]
["X23-57594",null,"2023-04-27","2023-06-02",null,null,null,"MLV 528-1","500","L","Install New Platform","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,528.1,null,"MLV 528-1:  Install New Platform\n--4/27/23 through 6/2/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-57589",null,"2023-02-14","2023-04-26",null,null,null,"MLV 528-2","500","L","Install New Platform","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412654 ELYSIM/TGP POTASH PLAQUEMINES",528.20000000000005,null,"MLV 528-2:  Install New Platform\n--2/14/23 through 4/26/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n412654 ELYSIM/TGP POTASH PLAQUEMINES\n………………………………"]
["X22-261411","***","2023-02-28","2023-02-28","Project Change","2023-01-31","2023-01-31","MLV 529-1 to MLV 530-1","500","L","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,529.1,"--start_date--end_date------------model_loc--","***MLV 529-1 to MLV 530-1:  Maintenance Pig\n--2/28/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 1/31/23.\n………………………………"]
["X22-261413","***","2023-02-28","2023-02-28","Project Change","2023-01-31","2023-01-31","MLV 529-2 to MLV 530-2","500","L","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,529.20000000000005,"--start_date--end_date------------model_loc--","***MLV 529-2 to MLV 530-2:  Maintenance Pig\n--2/28/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 1/31/23.\n………………………………"]
["X23-120615","***","2023-08-07","2023-08-13","Added",null,null,"MLV 530-1 to MLV 534-1","500","L","Pig Runs - Cleaning 8/7 to 8/13","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,530.1,"------","***MLV 530-1 to MLV 534-1:  Pig Runs - Cleaning 8/7 to 8/13\n--8/7/23 through 8/13/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X23-120616","***","2023-09-19","2023-09-19","Added",null,null,"MLV 530-1 to MLV 534-1","500","L","Pig Runs - Caliper 9/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,530.11,"------","***MLV 530-1 to MLV 534-1:  Pig Runs - Caliper 9/19\n--9/19/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X23-120618","***","2023-09-21","2023-09-21","Added",null,null,"MLV 530-1 to MLV 534-1",null,null,"Pig Runs - MFL-A 9/21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,530.12,"------","***MLV 530-1 to MLV 534-1:  Pig Runs - MFL-A 9/21\n--9/21/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X23-120619","***","2023-09-26","2023-09-26","Added",null,null,"MLV 530-1 to MLV 534-1","500","L","Pig Runs - MFL-C 9/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,530.13,"------","***MLV 530-1 to MLV 534-1:  Pig Runs - MFL-C 9/26\n--9/26/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X23-38761",null,"2023-02-20","2023-02-26",null,null,null,"MLV 530-2 to MLV 531-2","500","L","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,530.20000000000005,null,"MLV 530-2 to MLV 531-2:  Anomaly Remediation\n--2/20/23 through 2/26/23:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-38764",null,"2023-02-27","2023-03-10",null,null,null,"MLV 533-2 to MLV 534-2","500","L","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may experience pressure fluctuations and may be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","412753 PAR MINL/TGP UDP PISTOL RIDGE: RIP\n412758 PETROHRV/TGP HIGHWAY 13: RIP 533D-\n412750 PRP INC/TGP PISTOL RIDGE: RIP 533B-",533.20000000000005,null,"MLV 533-2 to MLV 534-2:  Anomaly Remediation\n--2/27/23 through 3/10/23:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may experience pressure fluctuations and may be shut-in during the project.  Potential out of path restrictions may be at risk.\n412753 PAR MINL/TGP UDP PISTOL RIDGE: RIP\n412758 PETROHRV/TGP HIGHWAY 13: RIP 533D-\n412750 PRP INC/TGP PISTOL RIDGE: RIP 533B-\n………………………………"]
["X22-1207728",null,"2022-12-05","2023-05-31",null,null,null,"Sta 534","500","L","Unit 1A - Main Bearings","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,534.00099999999998,null,"Sta 534:  Unit 1A - Main Bearings\n--12/5/22 through 5/31/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-120624","***","2023-10-16","2023-10-22","Added",null,null,"MLV 534-1A to MLV 538-1","500","L","Pig Runs - Cleaning 10/16 to 10/22","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,534.1,"------","***MLV 534-1A to MLV 538-1:  Pig Runs - Cleaning 10/16 to 10/22\n--10/16/23 through 10/22/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X23-120626","***","2023-10-25","2023-10-25","Added",null,null,"MLV 534-1A to MLV 538-1","500","L","Pig Runs - MFL 10/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,534.11,"------","***MLV 534-1A to MLV 538-1:  Pig Runs - MFL 10/25\n--10/25/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X23-74072","***","2023-01-24","2023-01-27","Completed",null,null,"MLV 538-1 to MLV 539-1","500","1","Emergent Repair","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in for the duration of the project.","SOP","Potential out of path restrictions may be at risk.","412060 /TGP HEIDELBURG TRANSPORT JASPER",538.1,"------","***MLV 538-1 to MLV 539-1:  Emergent Repair\n***Completed\nThe following meters are available for nominations:\n412060 /TGP HEIDELBURG TRANSPORT JASPER"]
["X23-57384",null,"2023-06-08","2023-06-08",null,null,null,"MLV 538-1 to MLV 534-1A","500","1","Pig Runs - Cleaning/Gauge 8/10","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,538.1,null,"MLV 538-1 to MLV 534-1A:  Pig Runs - Cleaning/Gauge 8/10\n--6/8/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-120628","***","2023-10-02","2023-10-08","Added",null,null,"MLV 538-1 to MLV 542-1","500","1","Pig Runs - Cleaning 10/2 to 10/8","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,538.1,"------","***MLV 538-1 to MLV 542-1:  Pig Runs - Cleaning 10/2 to 10/8\n--10/2/23 through 10/8/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X23-57385",null,"2023-06-12","2023-06-12",null,null,null,"MLV 538-1 to MLV 534-1A","500","1","Pig Runs - MFL-C 8/12","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,538.11,null,"MLV 538-1 to MLV 534-1A:  Pig Runs - MFL-C 8/12\n--6/12/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-120630","***","2023-10-10","2023-10-10","Added",null,null,"MLV 538-1 to MLV 542-1","500","1","Pig Runs - MFL 10/10","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,538.12,"------","***MLV 538-1 to MLV 542-1:  Pig Runs - MFL 10/10\n--10/10/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X23-120633","***","2023-10-12","2023-10-12","Added",null,null,"MLV 538-1 to MLV 542-1","500","1","Pig Runs - Hard Spot 10/12","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,538.13,"------","***MLV 538-1 to MLV 542-1:  Pig Runs - Hard Spot 10/12\n--10/12/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X22-477944","***","2022-05-23","2023-01-31","Completed",null,null,"Sta 542","500","1","Unit 2A - Engine and Compressor Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,542.00199999999995,"------","***Sta 542:  Unit 2A - Engine and Compressor Overhaul\n***Completed"]
["X22-1035231","***","2022-10-24","2023-02-14","Project Change",null,"2023-01-31","Sta 546","500","1","Unit 5A - Top End and Compressor Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,546.005,"----end_date------------model_loc--","***Sta 546:  Unit 5A - Top End and Compressor Overhaul\n--10/24/22 through 2/14/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 10/24/22 to 1/31/23.\n………………………………"]
["X23-62265",null,"2023-05-29","2023-07-14",null,null,null,"Sta 550","500","1","Unit 1B - Turbine Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,550.01700000000005,null,"Sta 550:  Unit 1B - Turbine Overhaul\n--5/29/23 through 7/14/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-1014898",null,"2023-03-27","2023-05-01",null,null,null,"Sta 555","500","1","Unit 1B - Turbine Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,555.01700000000005,null,"Sta 555:  Unit 1B - Turbine Overhaul\n--3/27/23 through 5/1/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-238586",null,"2023-01-10","2023-02-27",null,null,null,"MLV 559-2A to MLV 560-2","500","1","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.",null,559.20000000000005,null,"MLV 559-2A to MLV 560-2:  Pipe Replacement\n--1/10/23 through 2/27/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be shut in during the project.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-62073",null,"2023-06-28","2023-06-28",null,null,null,"Sta 563 Joelton","500","2","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,563,null,"Sta 563 Joelton:  Annual ESD Test\n--6/28/23:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-62066",null,"2023-02-27","2023-03-03",null,null,null,"Sta 563","500","2","Unt 1A - Coupling ReplacementFuel Injection Cleaning","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,563.00099999999998,null,"Sta 563:  Unt 1A - Coupling ReplacementFuel Injection Cleaning\n--2/27/23 through 3/3/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-27248",null,"2023-02-13","2023-02-26",null,null,null,"MLV 563-1 to MLV 564-1","500","1","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,563.1,null,"MLV 563-1 to MLV 564-1:  Pipe Replacement\n--2/13/23 through 2/26/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-27247",null,"2023-02-13","2023-02-26",null,null,null,"MLV 564-1 to MLV 564-1BR","500","1","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,564.1,null,"MLV 564-1 to MLV 564-1BR:  Pipe Replacement\n--2/13/23 through 2/26/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-57521","***","2023-05-02","2023-05-02","Project Change","2023-05-01","2023-05-01","MLV 820-1 to MLV 821R-101.1","800","L","Maintenance Pig Run","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SIP","Potential in the path restrictions may be at risk.","412768 GLDNPASS/TGP STARKS LNG: RIP 820 10412737 CAM IPL/TGP DE QUINCY GAS STORAGE C421050 LBERTYGS/TGP DE QUINCY GAS STORAGE420550 ENTRPRSE/TGP SABINE RIVER (1 6179412013 ENTRPRSE/TGP SABINE RIVER TRANS NEW",820.1,"--start_date--end_date--meters_affected----------model_loc--","***MLV 820-1 to MLV 821R-101.1:  Maintenance Pig Run\n--5/2/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential in the path restrictions may be at risk.\n412768 GLDNPASS/TGP STARKS LNG: RIP 820 10412737 CAM IPL/TGP DE QUINCY GAS STORAGE C421050 LBERTYGS/TGP DE QUINCY GAS STORAGE420550 ENTRPRSE/TGP SABINE RIVER (1 6179412013 ENTRPRSE/TGP SABINE RIVER TRANS NEW\n***\nDate Change, Previously scheduled 5/1/23.\n………………………………"]
["X23-57523",null,"2023-03-20","2023-03-20",null,null,null,"Meter Station Filter Srubber Maintenance","800","L","Cameron Banken Rd (Pin 49446)","This activity will center on maintenance on the filter scrubber at the meter listed.  The meter listed may experience pressure fluctuations.","SOP","Potential out of path restrictions may be at risk.","49446 CAM IPL/TGP BANKEN RD AT  HWY 27 DE",821,null,"Meter Station Filter Srubber Maintenance:  Cameron Banken Rd (Pin 49446)\n--3/20/23:  This activity will center on maintenance on the filter scrubber at the meter listed.  The meter listed may experience pressure fluctuations.  Potential out of path restrictions may be at risk.\n49446 CAM IPL/TGP BANKEN RD AT  HWY 27 DE\n………………………………"]
["X23-77003","***","2023-02-13","2023-02-13","Added",null,null,"Sta 47","100","1","Communication Upgrade","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,823,"--------anticipated_impact----prl----model_loc--","***Sta 47:  Communication Upgrade\n--2/13/23:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X23-57518",null,"2023-05-08","2023-05-15",null,null,null,"Sta. 823 (Kinder)","800","L","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,823,null,"Sta. 823 (Kinder):  Annual ESD Test\n--5/8/23 through 5/15/23:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-57520",null,"2023-05-08","2023-05-15",null,null,null,"Sta. 823 (Kinder)","800","L","Unit & Inlet Scrubber Valve Replacements","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,823,null,"Sta. 823 (Kinder):  Unit & Inlet Scrubber Valve Replacements\n--5/8/23 through 5/15/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-57522","***","2023-05-03","2023-05-03","Project Change","2023-05-02","2023-05-02","MLV 823-1 to MLV 821R-101.1","800","L","Maintenance Pig Run","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SIP","Potential in the path restrictions may be at risk.","420581 ENTRGYLA/TGP BECKWITH CREEK CALCASI49446 CAM IPL/TGP BANKEN RD AT  HWY 27 DE412768 GLDNPASS/TGP STARKS LNG: RIP 820 10412737 CAM IPL/TGP DEQUINCY GAS STORAGE C421050 LBERTYGS/TGP DE QUINCY GAS STORAGE420550 ENTERPRSE/TGP SABINE RIVERsoap412013 ENTRPRSE/TGP SABINE RIVER TRANS NEW412690 HPL/TGP SABINE NEWTON411586 TRNSCO/TGP STARKS LA TRANSPORT CALC",823.1,"--start_date--end_date--meters_affected----------model_loc--","***MLV 823-1 to MLV 821R-101.1:  Maintenance Pig Run\n--5/3/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential in the path restrictions may be at risk.\n420581 ENTRGYLA/TGP BECKWITH CREEK CALCASI49446 CAM IPL/TGP BANKEN RD AT  HWY 27 DE412768 GLDNPASS/TGP STARKS LNG: RIP 820 10412737 CAM IPL/TGP DEQUINCY GAS STORAGE C421050 LBERTYGS/TGP DE QUINCY GAS STORAGE420550 ENTERPRSE/TGP SABINE RIVERsoap412013 ENTRPRSE/TGP SABINE RIVER TRANS NEW412690 HPL/TGP SABINE NEWTON411586 TRNSCO/TGP STARKS LA TRANSPORT CALC\n***\nDate Change, Previously scheduled 5/2/23.\n………………………………"]
["X23-101115","***","2023-07-12","2023-07-12","Added",null,null,"Sta 823 to MLV 516","500","L","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412398 JEFFSTOR/TGP JEFFERSON ISLAND IBERI420915 CEGS/TGP PORT IBERIA SALES IBERIA421056 ACADIAN/TGP INDIAN BAYOU: DIP 510B-410907 TRUNKLNE/TGP CENTERVILLE DEHY TRANS450105 AMMID SC/TGP QUIVIRA ST MARY412594 NAUTILUS/TGP GARDEN CITY ST MARY412684 ANR/TGP SHADYSIDE ST MARY",823.5,"------","***Sta 823 to MLV 516:  Maintenance Pig\n--7/12/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be shut in during the project.  Potential out of path restrictions may be at risk.\n412398 JEFFSTOR/TGP JEFFERSON ISLAND IBERI420915 CEGS/TGP PORT IBERIA SALES IBERIA421056 ACADIAN/TGP INDIAN BAYOU: DIP 510B-410907 TRUNKLNE/TGP CENTERVILLE DEHY TRANS450105 AMMID SC/TGP QUIVIRA ST MARY412594 NAUTILUS/TGP GARDEN CITY ST MARY412684 ANR/TGP SHADYSIDE ST MARY\n***Added\n………………………………"]
["X23-41070",null,"2023-02-07","2023-02-07",null,null,null,"Sta 827","800","L","Unit 3A - Water Wash","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,827.00300000000004,null,"Sta 827:  Unit 3A - Water Wash\n--2/7/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-101124","***","2023-04-25","2023-04-25","Added",null,null,"Sta 827 to Sta 823","800","L","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SIP","Potential in the path restrictions may be at risk.","421043 PINE PRA/TGP PINE PRAIRIE NORTH RAP412847 ACADIAN/TGP CHENEYVILLE RAPIDES412713 HUGHES E/TGP UDP BLACK STONE13 EVAN412844 TEXLA/TGP ROY MARTIN GATHERING: RIP420296 FORSTHIL/TGP FOREST HILL LA RAPIDES420530 GLNMORA/TGP GLENMORA LA EXCH RAPIDE421042 ELIZ NG/TGP EVANGELINE SALES EVANGE420629 ELIZ NG/TGP OAKDALE DETENTION SALES420687 ELIZ NG/TGP ALLEN PARISH PRISON SAL420406 ELIZ NG/TGP ELIZABETH LA EMERGENCY53483 AIRLIQAT/TGP TIMBERLANE BIOGAS REC",827.1,"------","***Sta 827 to Sta 823:  Maintenance Pig\n--4/25/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential in the path restrictions may be at risk.\n421043 PINE PRA/TGP PINE PRAIRIE NORTH RAP412847 ACADIAN/TGP CHENEYVILLE RAPIDES412713 HUGHES E/TGP UDP BLACK STONE13 EVAN412844 TEXLA/TGP ROY MARTIN GATHERING: RIP420296 FORSTHIL/TGP FOREST HILL LA RAPIDES420530 GLNMORA/TGP GLENMORA LA EXCH RAPIDE421042 ELIZ NG/TGP EVANGELINE SALES EVANGE420629 ELIZ NG/TGP OAKDALE DETENTION SALES420687 ELIZ NG/TGP ALLEN PARISH PRISON SAL420406 ELIZ NG/TGP ELIZABETH LA EMERGENCY53483 AIRLIQAT/TGP TIMBERLANE BIOGAS REC\n***Added\n………………………………"]
["X23-101126","***","2023-10-11","2023-10-11","Added",null,null,"Sta 827 to Sta 823","800","L","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SIP","Potential in the path restrictions may be at risk.","421043 PINE PRA/TGP PINE PRAIRIE NORTH RAP412847 ACADIAN/TGP CHENEYVILLE RAPIDES412713 HUGHES E/TGP UDP BLACK STONE13 EVAN412844 TEXLA/TGP ROY MARTIN GATHERING: RIP420296 FORSTHIL/TGP FOREST HILL LA RAPIDES420530 GLNMORA/TGP GLENMORA LA EXCH RAPIDE421042 ELIZ NG/TGP EVANGELINE SALES EVANGE420629 ELIZ NG/TGP OAKDALE DETENTION SALES420687 ELIZ NG/TGP ALLEN PARISH PRISON SAL420406 ELIZ NG/TGP ELIZABETH LA EMERGENCY53483 AIRLIQAT/TGP TIMBERLANE BIOGAS REC",827.11,"------","***Sta 827 to Sta 823:  Maintenance Pig\n--10/11/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential in the path restrictions may be at risk.\n421043 PINE PRA/TGP PINE PRAIRIE NORTH RAP412847 ACADIAN/TGP CHENEYVILLE RAPIDES412713 HUGHES E/TGP UDP BLACK STONE13 EVAN412844 TEXLA/TGP ROY MARTIN GATHERING: RIP420296 FORSTHIL/TGP FOREST HILL LA RAPIDES420530 GLNMORA/TGP GLENMORA LA EXCH RAPIDE421042 ELIZ NG/TGP EVANGELINE SALES EVANGE420629 ELIZ NG/TGP OAKDALE DETENTION SALES420687 ELIZ NG/TGP ALLEN PARISH PRISON SAL420406 ELIZ NG/TGP ELIZABETH LA EMERGENCY53483 AIRLIQAT/TGP TIMBERLANE BIOGAS REC\n***Added\n………………………………"]
["X22-154269",null,"2023-03-01","2023-03-31",null,null,null,"MLV 828-1 to MLV 829-1","800","L","Make Piggable","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,828.1,null,"MLV 828-1 to MLV 829-1:  Make Piggable\n--3/1/23 through 3/31/23:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-71369",null,"2023-03-20","2023-03-24",null,null,null,"Sta 834","800","1","Unit 1A - Relocate Unit Valve Controls","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,834.00099999999998,null,"Sta 834:  Unit 1A - Relocate Unit Valve Controls\n--3/20/23 through 3/24/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-1209530",null,"2022-12-06","2023-06-15",null,null,null,"Sta 834","800","1","Unit 2A - Crankshaft Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,834.00199999999995,null,"Sta 834:  Unit 2A - Crankshaft Inspection\n--12/6/22 through 6/15/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-71370",null,"2023-03-23","2023-03-25",null,null,null,"Sta 834","800","1","Unit 2A - Relocate Unit Valve Controls","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,834.00199999999995,null,"Sta 834:  Unit 2A - Relocate Unit Valve Controls\n--3/23/23 through 3/25/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-71292","***","2023-01-30","2023-02-02","Completed",null,null,"Sta 834","800","1","Unit 3A - Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,834.00300000000004,"------","***Sta 834:  Unit 3A - Engine Inspection\n***Completed"]
["X23-71372",null,"2023-03-27","2023-03-29",null,null,null,"Sta 834","800","1","Unit 4A - Relocate Unit Valve Controls","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,834.00400000000002,null,"Sta 834:  Unit 4A - Relocate Unit Valve Controls\n--3/27/23 through 3/29/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-71374",null,"2023-07-17","2023-07-21",null,null,null,"Sta 834","800","1","Unit 6A - Replace Lube System","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,834.00599999999997,null,"Sta 834:  Unit 6A - Replace Lube System\n--7/17/23 through 7/21/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-71375",null,"2023-07-24","2023-07-28",null,null,null,"Sta 834","800","1","Unit 7A - Replace Lube System","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,834.00699999999995,null,"Sta 834:  Unit 7A - Replace Lube System\n--7/24/23 through 7/28/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-71377",null,"2023-08-01","2023-08-31",null,null,null,"Sta 834","800","1","Unit 7A - Compressor Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,834.00710000000004,null,"Sta 834:  Unit 7A - Compressor Overhaul\n--8/1/23 through 8/31/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-101122","***","2023-04-25","2023-04-25","Added",null,null,"Sta 834 to Sta 827","800","L","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SIP","Potential in the path restrictions may be at risk.","420755 ATMOS TL/TGP LASALLE PARISH NEBO SA\n420447 PELICANG/TGP HARRISONBURG LA CATAHO",834.1,"------","***Sta 834 to Sta 827:  Maintenance Pig\n--4/25/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential in the path restrictions may be at risk.\n420755 ATMOS TL/TGP LASALLE PARISH NEBO SA\n420447 PELICANG/TGP HARRISONBURG LA CATAHO\n***Added\n………………………………"]
["X23-113734","***","2023-09-19","2023-09-22","Added",null,null,"MLV 834-1 TO MLV 827-1","800","1","Pig Runs - Chemical Cleaning 9/19 to 9/22","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420447 PELICANG/TGP HARRISONBURG LA CATAHO\n420775 VAR/TGP NORTH GARDEN ISLAND BAY GAS",834.1,"------","***MLV 834-1 TO MLV 827-1:  Pig Runs - Chemical Cleaning 9/19 to 9/22\n--9/19/23 through 9/22/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n420447 PELICANG/TGP HARRISONBURG LA CATAHO\n420775 VAR/TGP NORTH GARDEN ISLAND BAY GAS\n***Added\n………………………………"]
["X23-113737","***","2023-09-22","2023-09-22","Added",null,null,"MLV 834-1 TO MLV 827-1","800","1","Pig Runs - Gauge 9/22","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420447 PELICANG/TGP HARRISONBURG LA CATAHO\n420775 VAR/TGP NORTH GARDEN ISLAND BAY GAS",834.11,"------","***MLV 834-1 TO MLV 827-1:  Pig Runs - Gauge 9/22\n--9/22/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n420447 PELICANG/TGP HARRISONBURG LA CATAHO\n420775 VAR/TGP NORTH GARDEN ISLAND BAY GAS\n***Added\n………………………………"]
["X23-101123","***","2023-10-11","2023-10-11","Added",null,null,"Sta 834 to Sta 827","800","L","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SIP","Potential in the path restrictions may be at risk.","420755 ATMOS TL/TGP LASALLE PARISH NEBO SA\n420447 PELICANG/TGP HARRISONBURG LA CATAHO",834.11,"------","***Sta 834 to Sta 827:  Maintenance Pig\n--10/11/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential in the path restrictions may be at risk.\n420755 ATMOS TL/TGP LASALLE PARISH NEBO SA\n420447 PELICANG/TGP HARRISONBURG LA CATAHO\n***Added\n………………………………"]
["X23-113730","***","2023-09-26","2023-09-26","Added",null,null,"MLV 834-1 TO MLV 827-1","800","1","Pig Runs - MFL-C 9/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420447 PELICANG/TGP HARRISONBURG LA CATAHO\n420775 VAR/TGP NORTH GARDEN ISLAND BAY GAS",834.12,"------","***MLV 834-1 TO MLV 827-1:  Pig Runs - MFL-C 9/26\n--9/26/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n420447 PELICANG/TGP HARRISONBURG LA CATAHO\n420775 VAR/TGP NORTH GARDEN ISLAND BAY GAS\n***Added\n………………………………"]
["X23-113732","***","2023-09-28","2023-09-28","Added",null,null,"MLV 834-1 TO MLV 827-1","800","1","Pig Runs - EMAT 9/28","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420447 PELICANG/TGP HARRISONBURG LA CATAHO\n420775 VAR/TGP NORTH GARDEN ISLAND BAY GAS",834.13,"------","***MLV 834-1 TO MLV 827-1:  Pig Runs - EMAT 9/28\n--9/28/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n420447 PELICANG/TGP HARRISONBURG LA CATAHO\n420775 VAR/TGP NORTH GARDEN ISLAND BAY GAS\n***Added\n………………………………"]
["X23-113745","***","2023-10-03","2023-10-05","Added",null,null,"MLV 834-1 TO MLV 838-1","800","1","Pig Runs - Cleaning 10/03 to 10/05","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412691 REGENCY/TGP PEOPLES ROAD FRANKLIN\n49554 BBTMIDLA/TGP NORTH PEOPLES RD FRANK\n420279 ATMOS TL/TGP CROWVILLE LA FRANKLIN\n49585 GULFRUN/TGP BEARFOOT RICHLAND\n49589 ETC TIG/TGP URSUS FRANKLIN\n49587 GULFSTH/TGP LUPE FRANKLIN\n49583 MEP/TGP PILLAR MADISON\n49643 GULFSTH/TGP SKIPPER MADISON",834.14,"------","***MLV 834-1 TO MLV 838-1:  Pig Runs - Cleaning 10/03 to 10/05\n--10/3/23 through 10/5/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n412691 REGENCY/TGP PEOPLES ROAD FRANKLIN\n49554 BBTMIDLA/TGP NORTH PEOPLES RD FRANK\n420279 ATMOS TL/TGP CROWVILLE LA FRANKLIN\n49585 GULFRUN/TGP BEARFOOT RICHLAND\n49589 ETC TIG/TGP URSUS FRANKLIN\n49587 GULFSTH/TGP LUPE FRANKLIN\n49583 MEP/TGP PILLAR MADISON\n49643 GULFSTH/TGP SKIPPER MADISON\n***Added\n………………………………"]
["X23-113746","***","2023-10-06","2023-10-06","Added",null,null,"MLV 834-1 TO MLV 838-1","800","1","Pig Runs - Gauge 10/06","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412691 REGENCY/TGP PEOPLES ROAD FRANKLIN\n49554 BBTMIDLA/TGP NORTH PEOPLES RD FRANK\n420279 ATMOS TL/TGP CROWVILLE LA FRANKLIN\n49585 GULFRUN/TGP BEARFOOT RICHLAND\n49589 ETC TIG/TGP URSUS FRANKLIN\n49587 GULFSTH/TGP LUPE FRANKLIN\n49583 MEP/TGP PILLAR MADISON\n49643 GULFSTH/TGP SKIPPER MADISON",834.15,"------","***MLV 834-1 TO MLV 838-1:  Pig Runs - Gauge 10/06\n--10/6/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n412691 REGENCY/TGP PEOPLES ROAD FRANKLIN\n49554 BBTMIDLA/TGP NORTH PEOPLES RD FRANK\n420279 ATMOS TL/TGP CROWVILLE LA FRANKLIN\n49585 GULFRUN/TGP BEARFOOT RICHLAND\n49589 ETC TIG/TGP URSUS FRANKLIN\n49587 GULFSTH/TGP LUPE FRANKLIN\n49583 MEP/TGP PILLAR MADISON\n49643 GULFSTH/TGP SKIPPER MADISON\n***Added\n………………………………"]
["X23-113748","***","2023-10-10","2023-10-10","Added",null,null,"MLV 834-1 TO MLV 838-1","800","1","Pig Runs - CLP / MFL-A / IMU 10/10","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412691 REGENCY/TGP PEOPLES ROAD FRANKLIN\n49554 BBTMIDLA/TGP NORTH PEOPLES RD FRANK\n420279 ATMOS TL/TGP CROWVILLE LA FRANKLIN\n49585 GULFRUN/TGP BEARFOOT RICHLAND\n49589 ETC TIG/TGP URSUS FRANKLIN\n49587 GULFSTH/TGP LUPE FRANKLIN\n49583 MEP/TGP PILLAR MADISON\n49643 GULFSTH/TGP SKIPPER MADISON",834.16,"------","***MLV 834-1 TO MLV 838-1:  Pig Runs - CLP / MFL-A / IMU 10/10\n--10/10/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n412691 REGENCY/TGP PEOPLES ROAD FRANKLIN\n49554 BBTMIDLA/TGP NORTH PEOPLES RD FRANK\n420279 ATMOS TL/TGP CROWVILLE LA FRANKLIN\n49585 GULFRUN/TGP BEARFOOT RICHLAND\n49589 ETC TIG/TGP URSUS FRANKLIN\n49587 GULFSTH/TGP LUPE FRANKLIN\n49583 MEP/TGP PILLAR MADISON\n49643 GULFSTH/TGP SKIPPER MADISON\n***Added\n………………………………"]
["X23-69504",null,"2023-07-18","2023-07-19",null,null,null,"Sta 843","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,843,null,"Sta 843:  Annual ESD Test\n--7/18/23 through 7/19/23:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-1120812",null,"2023-01-16","2023-03-03",null,null,null,"Sta 843","800","1","Unit 1A - Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,843.00099999999998,null,"Sta 843:  Unit 1A - Engine Inspection\n--1/16/23 through 3/3/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-1120813","***","2023-01-23","2023-02-17","Project Change",null,"2023-01-27","Sta 843","800","1","Unit 8A - Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,843.00800000000004,"----end_date------------model_loc--","***Sta 843:  Unit 8A - Crankcase Inspection\n--1/23/23 through 2/17/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 1/23/23 to 1/27/23.\n………………………………"]
["X23-113717","***","2023-07-10","2023-07-17","Added",null,null,"Sta 860","800","1","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,860,"------","***Sta 860:  Annual ESD Test & Maintenance\n--7/10/23 through 7/17/23:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X23-118147","***","2023-07-18","2023-08-07","Added",null,null,"Sta 860","800","1","Units 1A, 2A & 4A - Install New 12\" Piping","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,860.00099999999998,"------","***Sta 860:  Units 1A, 2A & 4A - Install New 12\" Piping\n--7/18/23 through 8/7/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X23-30240","***","2023-01-02","2023-02-10","Project Change",null,"2023-01-27","Sta 860","800","1","Unit 7A - Engine Bearings","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,860.00699999999995,"----end_date------------model_loc--","***Sta 860:  Unit 7A - Engine Bearings\n--1/2/23 through 2/10/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 1/2/23 to 1/27/23.\n………………………………"]
["X23-45629","***","2023-01-12","2023-02-02","Project Change",null,"2023-01-27","Sta 860","800","1","Unit 9A - Power Cylinder Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,860.00900000000001,"----end_date------------model_loc--","***Sta 860:  Unit 9A - Power Cylinder Inspection\n--1/12/23 through 2/2/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 1/12/23 to 1/27/23.\n………………………………"]
["X23-71363",null,"2023-01-24","2023-02-03",null,null,null,"Sta 860","800","1","Unit 9A - Jacket Water System","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,860.00909999999999,null,"Sta 860:  Unit 9A - Jacket Water System\n--1/24/23 through 2/3/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-27242",null,"2023-02-28","2023-03-06",null,null,null,"MLV 860-1 to MLV 861-1","800","1","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,860.1,null,"MLV 860-1 to MLV 861-1:  Pipe Replacement\n--2/28/23 through 3/6/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-113718","***","2023-07-10","2023-07-17","Added",null,null,"Sta 860","800","1","Install New 12\" Valve","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,860.1,"------","***Sta 860:  Install New 12\" Valve\n--7/10/23 through 7/17/23:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X23-27245",null,"2023-02-27","2023-03-05",null,null,null,"MLV 865-1 to MLV 865-1BR","800","1","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,865.1,null,"MLV 865-1 to MLV 865-1BR:  Pipe Replacement\n--2/27/23 through 3/5/23:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-57455","***","2023-07-18","2023-07-18","Project Change","2023-07-17","2023-07-17","MLV 871-1 to 866-1D","800","2","Pig Runs - Cleaning / Gauge 7/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,871.1,"--start_date--end_date------mantenance_desc------model_loc--","***MLV 871-1 to 866-1D:  Pig Runs - Cleaning / Gauge 7/18\n--7/18/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 7/17/23.\n………………………………"]
["X23-57458","***","2023-07-20","2023-07-20","Project Change","2023-07-19","2023-07-19","MLV 871-1 to 866-1D","800","2","Pig Runs - MFL Combo 7/20","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,871.11,"--start_date--end_date------mantenance_desc------model_loc--","***MLV 871-1 to 866-1D:  Pig Runs - MFL Combo 7/20\n--7/20/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 7/19/23.\n………………………………"]
["X23-57452",null,"2023-07-11","2023-07-11",null,null,null,"MLV 873-2A to 871-2","800","2","Pig Runs - Cleaning / Gauge 7/11","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,873.2,null,"MLV 873-2A to 871-2:  Pig Runs - Cleaning / Gauge 7/11\n--7/11/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-57453",null,"2023-07-13","2023-07-13",null,null,null,"MLV 873-2A to 871-2","800","2","Pig Runs - MFL Combo 7/13","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,873.21,null,"MLV 873-2A to 871-2:  Pig Runs - MFL Combo 7/13\n--7/13/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-41074",null,"2023-05-16","2023-05-18",null,null,null,"Sta 875","800","2","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,875,null,"Sta 875:  Annual ESD Test & Maintenance\n--5/16/23 through 5/18/23:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X23-41240",null,"2023-06-19","2023-06-21",null,null,null,"Sta 875","800","2","Unit 1A - 4k Hr Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,875.00099999999998,null,"Sta 875:  Unit 1A - 4k Hr Inspection\n--6/19/23 through 6/21/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-41276",null,"2023-12-04","2023-12-06",null,null,null,"Sta 875","800","2","Unit 1A - 8k Hr Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,875.00099999999998,null,"Sta 875:  Unit 1A - 8k Hr Inspection\n--12/4/23 through 12/6/23:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-57443","***","2023-06-12","2023-06-12","Project Change",null,"2023-06-13","MLV 876-1 to 871-1","800","2","Pig Runs - Cleaning / Gauge 6/12","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,876.1,"----end_date------mantenance_desc------model_loc--","***MLV 876-1 to 871-1:  Pig Runs - Cleaning / Gauge 6/12\n--6/12/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 6/12/23 to 6/13/23.\n………………………………"]
["X23-57444","***","2023-06-15","2023-06-15","Project Change",null,null,"MLV 876-1 to 871-1","800","2","Pig Runs - MFL Combo 6/15","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,876.11,"----------mantenance_desc------model_loc--","***MLV 876-1 to 871-1:  Pig Runs - MFL Combo 6/15\n--6/15/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Project Change\n………………………………"]
["X23-57440",null,"2023-05-09","2023-05-09",null,null,null,"MLV 876-2 to 874-2","800","2","Pig Runs - Cleaning / Gauge 5/9","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,876.2,null,"MLV 876-2 to 874-2:  Pig Runs - Cleaning / Gauge 5/9\n--5/9/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X23-57441",null,"2023-05-11","2023-05-11",null,null,null,"MLV 876-2 to 874-2","800","2","Pig Runs - MFL Combo 5/11","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,876.21,null,"MLV 876-2 to 874-2:  Pig Runs - MFL Combo 5/11\n--5/11/23:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]

{"sheet":"Sheet2","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}

{"sheet":"Sheet3","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}