## Closed (hidden)
|  |  | Updated | 2016
Tennessee Gas Pipeline 2015 Pipeline Outage and Maintenance Summary
This is a summary of the current status of all TGP Winter 2014-2015 Pipeline Outages and Maintenance Projects. This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions. Additionally, anticipated impact and restrictions are subject to change. *Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project. *Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time).
*** Indicates revision
Date Change | Project New/Completed/Closed | Outage # | Revised | Start Date | End Date | Reason Changed | Prev. Start Date | Prev. End Date | Location | Leg | Zone | Maintenance Activity | Anticipated Impact | Potential Restriction Level | TOS Potential Restrictions | Meter(s) in Impacted Area | Customer Notifications | Loc | Email Text | Posting Text | Completion Text
| Project Completed |  | *** | 2015-01-11 | 2016-01-11 | Project Completed |  |  | MS #412494 DCP Warren | 400 | 0 | Meter Station | This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | 412494 DCP Warren | 401 | () MS #412494 DCP Warren: Meter Station (1/11/15 to 1/11/16) | ***MS #412494 DCP Warren: Meter Station --1/11/15 through 1/11/16: This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. 412494 DCP Warren ***Project Completed ……………………………… | ***MS #412494 DCP Warren: Meter Station ***Project Completed The following meters are available for nominations: 412494 DCP Warren ………………………………
| Project Completed |  | *** | 2015-01-11 | 2016-01-11 | Project Completed |  |  | MS #412400 King Ranch | 400 | 0 | Meter Station | This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | 412400 King Ranch | 402.1 | () MS #412400 King Ranch: Meter Station (1/11/15 to 1/11/16) | ***MS #412400 King Ranch: Meter Station --1/11/15 through 1/11/16: This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. 412400 King Ranch ***Project Completed ……………………………… | ***MS #412400 King Ranch: Meter Station ***Project Completed The following meters are available for nominations: 412400 King Ranch ………………………………
| Project Completed |  | *** | 2015-01-12 | 2016-01-12 | Project Completed |  |  | MS #410539 Duvak Gas Gathering | 400 | 0 | Meter Station | This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | 410539 Duvak Gas Gathering | 402.1 | () MS #410539 Duvak Gas Gathering: Meter Station (1/12/15 to 1/12/16) | ***MS #410539 Duvak Gas Gathering: Meter Station --1/12/15 through 1/12/16: This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. 410539 Duvak Gas Gathering ***Project Completed ……………………………… | ***MS #410539 Duvak Gas Gathering: Meter Station ***Project Completed The following meters are available for nominations: 410539 Duvak Gas Gathering ………………………………
| Project Completed |  | *** | 2015-01-13 | 2016-01-13 | Project Completed |  |  | MS #412356 DCP LaGloria | 400 | 0 | Meter Station | This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | 412356 DCP LaGloria | 403.1 | () MS #412356 DCP LaGloria: Meter Station (1/13/15 to 1/13/16) | ***MS #412356 DCP LaGloria: Meter Station --1/13/15 through 1/13/16: This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. 412356 DCP LaGloria ***Project Completed ……………………………… | ***MS #412356 DCP LaGloria: Meter Station ***Project Completed The following meters are available for nominations: 412356 DCP LaGloria ………………………………
| Project Completed |  | *** | 2015-01-13 | 2016-01-13 | Project Completed |  |  | MS #410173 Enterprise LaReforma | 400 | 0 | Meter Station | This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | 410173 Enterprise LaReforma | 406.1 | () MS #410173 Enterprise LaReforma: Meter Station (1/13/15 to 1/13/16) | ***MS #410173 Enterprise LaReforma: Meter Station --1/13/15 through 1/13/16: This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. 410173 Enterprise LaReforma ***Project Completed ……………………………… | ***MS #410173 Enterprise LaReforma: Meter Station ***Project Completed The following meters are available for nominations: 410173 Enterprise LaReforma ………………………………
| Project Completed |  | *** | 2015-01-12 | 2016-01-12 | Project Completed |  |  | MS #411903 Enterprise El Benito | 400 | 0 | Meter Station | This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | 411903 Enterprise El Benito | 407.1 | () MS #411903 Enterprise El Benito: Meter Station (1/12/15 to 1/12/16) | ***MS #411903 Enterprise El Benito: Meter Station --1/12/15 through 1/12/16: This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. 411903 Enterprise El Benito ***Project Completed ……………………………… | ***MS #411903 Enterprise El Benito: Meter Station ***Project Completed The following meters are available for nominations: 411903 Enterprise El Benito ………………………………
| Project Completed |  | *** | 2015-01-11 | 2016-01-11 | Project Completed |  |  | MS #412088 Enterprise Sullivan | 400 | 0 | Meter Station | This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | 412088 Enterprise Sullivan | 407.1 | () MS #412088 Enterprise Sullivan: Meter Station (1/11/15 to 1/11/16) | ***MS #412088 Enterprise Sullivan: Meter Station --1/11/15 through 1/11/16: This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. 412088 Enterprise Sullivan ***Project Completed ……………………………… | ***MS #412088 Enterprise Sullivan: Meter Station ***Project Completed The following meters are available for nominations: 412088 Enterprise Sullivan ………………………………
| Project Completed |  | *** | 2015-01-11 | 2016-01-11 | Project Completed |  |  | MS #412683 HESCO | 400 | 0 | Meter Station | This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | 412683 HESCO | 408.1 | () MS #412683 HESCO: Meter Station (1/11/15 to 1/11/16) | ***MS #412683 HESCO: Meter Station --1/11/15 through 1/11/16: This project will require isolating the pipeline section. Physical flow will be suspended. No other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. 412683 HESCO ***Project Completed ……………………………… | ***MS #412683 HESCO: Meter Station ***Project Completed The following meters are available for nominations: 412683 HESCO ………………………………
| Project Completed | X16-36843 | *** | 2016-01-27 | 2016-01-27 | Project Completed |  |  | Sta. 237 | 200 | 5 | Unit Maintenance | This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. |  | 237 | (X16-36843) Sta. 237: Unit Maintenance (1/27/16) | ***Sta. 237: Unit Maintenance --1/27/16: This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. ***Project Completed ……………………………… | ***Sta. 237: Unit Maintenance ***Project Completed ………………………………
| Project Completed | X14-1478563 | *** | 2015-11-16 | 2016-02-12 | Project Completed |  |  | MLV 32-1D to 33-1 | 100 | 0 | Hydrotest | This project will require taking the pipeline section out of service. This will limit throughput and may result in restrictions based on customer nominations. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. |  | 32.2 | (X14-1478563) MLV 32-1D to 33-1: Hydrotest (11/16/15 to 2/12/16) | ***MLV 32-1D to 33-1: Hydrotest --11/16/15 through 2/12/16: This project will require taking the pipeline section out of service. This will limit throughput and may result in restrictions based on customer nominations. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. ***Project Completed ……………………………… | ***MLV 32-1D to 33-1: Hydrotest ***Project Completed ………………………………
| Project Completed | X16-16074 |  | 2016-01-18 | 2016-01-28 | Project Completed |  |  | Station 550 | 500 | 1 | Station Maintenance | This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. |  | 550 | (X16-16074) Station 550: Station Maintenance (1/18/16 to 1/28/16) | Station 550: Station Maintenance --1/18/16 through 1/28/16: This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. ***Project Completed ……………………………… | Station 550: Station Maintenance ***Project Completed ………………………………
| Project Completed | X16-46202 | *** | 2016-02-01 | 2016-02-07 | Project Completed |  |  | Station 9 | 100 | 0 | Station Maintenance (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items) | This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time. | SIP | Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations. |  | 9 | (X16-46202) Station 9: Station Maintenance (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items) (2/1/16 to 2/7/16) | ***Station 9: Station Maintenance (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items) --2/1/16 through 2/7/16: This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time. Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations. ***Project Completed ……………………………… | ***Station 9: Station Maintenance (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items) ***Project Completed ………………………………
| Project Completed | X15-925633 | *** | 2016-02-09 | 2016-02-11 | Project Completed |  |  | Sta. 266A | 200 | 6 | Unit Maintenance | This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. |  | 266 | (X15-925633) Sta. 266A: Unit Maintenance (2/9/16 to 2/11/16) | ***Sta. 266A: Unit Maintenance --2/9/16 through 2/11/16: This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. ***Project Completed ……………………………… | ***Sta. 266A: Unit Maintenance ***Project Completed ………………………………
| Project Completed | X15-929733 | *** | 2016-01-27 | 2016-02-10 | Project Completed |  |  | MLV 834-1 to 838-1 | 800 | 5 | ILI/Cleaning Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | To Be Determined | 834.1 | (X15-929733) MLV 834-1 to 838-1: ILI/Cleaning Pig (1/27/16 to 2/10/16) | ***MLV 834-1 to 838-1: ILI/Cleaning Pig --1/27/16 through 2/10/16: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. To Be Determined ***Project Completed ……………………………… | ***MLV 834-1 to 838-1: ILI/Cleaning Pig ***Project Completed The following meters are available for nominations: To Be Determined ………………………………
| Project Completed | X14-1562506 | *** | 2015-11-02 | 2016-02-19 | Project Completed |  |  | MLV 5-1 to 6-1 | 100 | 0 | Hydrotest | This project will require taking the pipeline section out of service. The listed meters will be shut in during the outage. This will limit throughput and may result in restrictions based on customer nominations. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | 410063 ROCHE DEHYDRATION | 5.1 | (X14-1562506) MLV 5-1 to 6-1: Hydrotest (11/2/15 to 2/19/16) | ***MLV 5-1 to 6-1: Hydrotest --11/2/15 through 2/19/16: This project will require taking the pipeline section out of service. The listed meters will be shut in during the outage. This will limit throughput and may result in restrictions based on customer nominations. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. 410063 ROCHE DEHYDRATION ***Project Completed ……………………………… | ***MLV 5-1 to 6-1: Hydrotest ***Project Completed The following meters are available for nominations: 410063 ROCHE DEHYDRATION ………………………………
| Project Completed | X14-1562506 | *** | 2015-11-02 | 2016-02-19 | Project Completed |  |  | MLV 7-1 to 9-1 | 100 | 0 | Hydrotest | This project will require taking the pipeline section out of service. The listed meters will be shut in during the outage. This will limit throughput and may result in restrictions based on customer nominations. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | 412490 Charro 421083 Eagle Ford Field Service | 5.1 | (X14-1562506) MLV 7-1 to 9-1: Hydrotest (11/2/15 to 2/19/16) | ***MLV 7-1 to 9-1: Hydrotest --11/2/15 through 2/19/16: This project will require taking the pipeline section out of service. The listed meters will be shut in during the outage. This will limit throughput and may result in restrictions based on customer nominations. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. 412490 Charro 421083 Eagle Ford Field Service ***Project Completed ……………………………… | ***MLV 7-1 to 9-1: Hydrotest ***Project Completed The following meters are available for nominations: 412490 Charro 421083 Eagle Ford Field Service ………………………………
Date change. Previously scheduled 2/18/16 to 2/20/16. | Project Completed | X15-882289 | *** | 2016-02-22 | 2016-02-24 | Project Completed | 2016-02-18 | 2016-02-20 | MLV 24-2 to 25-2S | 100 | 0 | Anomaly Remediation | This outage will require pressure reductions and possibly line isolations. However no other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | To Be Determined | 24.2 | (X15-882289) MLV 24-2 to 25-2S: Anomaly Remediation (2/22/16 to 2/24/16) | ***MLV 24-2 to 25-2S: Anomaly Remediation --2/22/16 through 2/24/16: This outage will require pressure reductions and possibly line isolations. However no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. To Be Determined ***Project Completed ……………………………… | ***MLV 24-2 to 25-2S: Anomaly Remediation ***Project Completed The following meters are available for nominations: To Be Determined ………………………………
| Project Completed | X15-925630 | *** | 2016-02-23 | 2016-02-23 | Project Completed |  |  | WORCESTER DELIVERY NO. 2 LINE (265C-101.1 to 265C-101B) | 200 | L | ILI/Cleaning Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. |  | 265.1 | (X15-925630) WORCESTER DELIVERY NO. 2 LINE (265C-101.1 to 265C-101B): ILI/Cleaning Pig (2/23/16) | ***WORCESTER DELIVERY NO. 2 LINE (265C-101.1 to 265C-101B): ILI/Cleaning Pig --2/23/16: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. ***Project Completed ……………………………… | ***WORCESTER DELIVERY NO. 2 LINE (265C-101.1 to 265C-101B): ILI/Cleaning Pig ***Project Completed ………………………………
| Project Completed | X16-23748 | *** | 2016-02-15 | 2016-02-18 | Project Completed |  |  | MLV 530-3 to 532-3 | 500 | L | ILI/Cleaning Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. |  | 530.3 | (X16-23748) MLV 530-3 to 532-3: ILI/Cleaning Pig (2/15/16 to 2/18/16) | ***MLV 530-3 to 532-3: ILI/Cleaning Pig --2/15/16 through 2/18/16: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. ***Project Completed ……………………………… | ***MLV 530-3 to 532-3: ILI/Cleaning Pig ***Project Completed ………………………………
| Project Canceled | X16-98720 | *** | 2016-03-06 | 2016-03-06 | Project Canceled |  |  | Sta. 1 | 100 | 0 | Station Maintenance | This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. |  | 1 | (X16-98720) Sta. 1: Station Maintenance (3/6/16) | ***Sta. 1: Station Maintenance --3/6/16: This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. ***Project Canceled ……………………………… | ***Sta. 1: Station Maintenance ***Project Canceled ………………………………
| Project Completed | X14-1562513 X14-1540661 | *** | 2015-07-01 | 2016-03-04 | Project Completed |  |  | Station 32 | 100 | 0 | Station Maintenance | This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. |  | 32 | (X14-1562513 X14-1540661) Station 32: Station Maintenance (7/1/15 to 3/4/16) | ***Station 32: Station Maintenance --7/1/15 through 3/4/16: This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. ***Project Completed ……………………………… | ***Station 32: Station Maintenance ***Project Completed ………………………………
| Project Canceled | X15-926822 | *** | 2016-06-06 | 2016-06-11 | Project Canceled |  |  | BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1) | 300 | 6 | Pipe Inspection | This project involves inspecting multiple sites. We do not anticipate having to do any repairs, however if a repair is needed there is a potential that the pipe may require replacement which will require isolation of the pipe. This may limit throughput and will result in restrictions based on customer nominations. Customers may experience pressure fluctuations during this timeframe. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | To Be Determined | 343.1 | (X15-926822) BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1): Pipe Inspection (6/6/16 to 6/11/16) | ***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1): Pipe Inspection --6/6/16 through 6/11/16: This project involves inspecting multiple sites. We do not anticipate having to do any repairs, however if a repair is needed there is a potential that the pipe may require replacement which will require isolation of the pipe. This may limit throughput and will result in restrictions based on customer nominations. Customers may experience pressure fluctuations during this timeframe. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. To Be Determined ***Project Canceled ……………………………… | ***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1): Pipe Inspection ***Project Canceled The following meters are available for nominations: To Be Determined ………………………………
| Project Canceled | X15-928271 | *** | TBD | TBD | Project Canceled |  |  | MLV 555-1 to 550-1 | 500 | 1 | ILI/Cleaning Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | To Be Determined | 555.1 | (X15-928271) MLV 555-1 to 550-1: ILI/Cleaning Pig (TBD) | ***MLV 555-1 to 550-1: ILI/Cleaning Pig --TBD: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. To Be Determined ***Project Canceled ……………………………… | ***MLV 555-1 to 550-1: ILI/Cleaning Pig ***Project Canceled The following meters are available for nominations: To Be Determined ………………………………
| Project Canceled | X15-928272 | *** | TBD | TBD | Project Canceled |  |  | MLV 555-2 to 550-2 | 500 | 1 | ILI/Cleaning Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | To Be Determined | 555.2 | (X15-928272) MLV 555-2 to 550-2: ILI/Cleaning Pig (TBD) | ***MLV 555-2 to 550-2: ILI/Cleaning Pig --TBD: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. To Be Determined ***Project Canceled ……………………………… | ***MLV 555-2 to 550-2: ILI/Cleaning Pig ***Project Canceled The following meters are available for nominations: To Be Determined ………………………………
| Project Canceled | X15-928273 | *** | TBD | TBD | Project Canceled |  |  | MLV 555-3 to 552-3 | 500 | 1 | ILI/Cleaning Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | To Be Determined | 555.3 | (X15-928273) MLV 555-3 to 552-3: ILI/Cleaning Pig (TBD) | ***MLV 555-3 to 552-3: ILI/Cleaning Pig --TBD: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. To Be Determined ***Project Canceled ……………………………… | ***MLV 555-3 to 552-3: ILI/Cleaning Pig ***Project Canceled The following meters are available for nominations: To Be Determined ………………………………
| Project Completed | X15-882281 | *** | 2016-02-24 | 2016-03-03 | Project Completed |  |  | 24-1A to 25-1S | 100 | 0 | Anomaly Remediation | This outage will require pressure reductions and possibly line isolations. However no other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | To Be Determined | 24.1 | (X15-882281) 24-1A to 25-1S: Anomaly Remediation (2/24/16 to 3/3/16) | ***24-1A to 25-1S: Anomaly Remediation --2/24/16 through 3/3/16: This outage will require pressure reductions and possibly line isolations. However no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. To Be Determined ***Project Completed ……………………………… | ***24-1A to 25-1S: Anomaly Remediation ***Project Completed The following meters are available for nominations: To Be Determined ………………………………
| Project Completed | X15-882291 | *** | 2016-03-03 | 2016-03-04 | Project Completed |  |  | MLV 24-3 to 25-3S | 100 | 0 | Anomaly Remediation | This outage will require pressure reductions and possibly line isolations. However no other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | To Be Determined | 24.3 | (X15-882291) MLV 24-3 to 25-3S: Anomaly Remediation (3/3/16 to 3/4/16) | ***MLV 24-3 to 25-3S: Anomaly Remediation --3/3/16 through 3/4/16: This outage will require pressure reductions and possibly line isolations. However no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. To Be Determined ***Project Completed ……………………………… | ***MLV 24-3 to 25-3S: Anomaly Remediation ***Project Completed The following meters are available for nominations: To Be Determined ………………………………
| Project Completed | X14-1178175 | *** | 2015-06-15 | 2016-03-31 | Project Completed |  |  | Station 63 | 100 | 1 | Station Maintenance | This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. |  | 63 | (X14-1178175) Station 63: Station Maintenance (6/15/15 to 3/31/16) | ***Station 63: Station Maintenance --6/15/15 through 3/31/16: This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. ***Project Completed ……………………………… | ***Station 63: Station Maintenance ***Project Completed ………………………………
| Project Cancelled | X15-913224 | *** | 2016-04-16 | 2016-05-21 | Project Cancelled |  |  | MLV 109-2 | 100 | 2 | Pipe Replacement | This project will require taking the pipeline section out of service. This will limit throughput and will result in restrictions based on customer nominations. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | To Be Determined | 109.2 | (X15-913224) MLV 109-2: Pipe Replacement (4/16/16 to 5/21/16) | ***MLV 109-2: Pipe Replacement --4/16/16 through 5/21/16: This project will require taking the pipeline section out of service. This will limit throughput and will result in restrictions based on customer nominations. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. To Be Determined ***Project Cancelled ……………………………… | ***MLV 109-2: Pipe Replacement ***Project Cancelled The following meters are available for nominations: To Be Determined ………………………………
| Project Completed | X15-926830 | *** | 2016-03-07 | 2016-03-11 | Project Completed |  |  | MLV 400-1 to 408-1 | 100 | 0 | ILI/Cleaning Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. | SIP | Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations. | To Be Determined | 400.1 | (X15-926830) MLV 400-1 to 408-1: ILI/Cleaning Pig (3/7/16 to 3/11/16) | ***MLV 400-1 to 408-1: ILI/Cleaning Pig --3/7/16 through 3/11/16: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations, however, no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations. To Be Determined ***Project Completed ……………………………… | ***MLV 400-1 to 408-1: ILI/Cleaning Pig ***Project Completed The following meters are available for nominations: To Be Determined ………………………………
| Project Cancelled | X16-143836 | *** | 2016-03-28 | 2016-04-04 | Project Cancelled |  |  | Sta. 409 | 100 | 0 | Unit Maintenance | This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations. | SIP | Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations. |  | 409 | (X16-143836) Sta. 409: Unit Maintenance (3/28/16 to 4/4/16) | ***Sta. 409: Unit Maintenance --3/28/16 through 4/4/16: This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations. Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations. ***Project Cancelled ……………………………… | ***Sta. 409: Unit Maintenance ***Project Cancelled ………………………………
| Project Cancelled | X15-929680 | *** | 2016-04-18 | 2016-04-27 | Project Cancelled |  |  | SABINE - KINDER LINE to 822-1 | 800 | L | Anomaly Remediation | This outage will require pressure reductions and possibly line isolations. However no other service impact is anticipated. | SOP | Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. | To Be Determined | 822.1 | (X15-929680) SABINE - KINDER LINE to 822-1: Anomaly Remediation (4/18/16 to 4/27/16) | ***SABINE - KINDER LINE to 822-1: Anomaly Remediation --4/18/16 through 4/27/16: This outage will require pressure reductions and possibly line isolations. However no other service impact is anticipated. Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations. To Be Determined ***Project Cancelled ……………………………… | ***SABINE - KINDER LINE to 822-1: Anomaly Remediation ***Project Cancelled The following meters are available for nominations: To Be Determined ………………………………

## Sheet1
Updated | 2023-06-08
Tennessee Gas Pipeline 2023 Pipeline Outage and Maintenance Summary
This is a summary of the current status of all TGP 2023 Pipeline Outages and Maintenance Projects. This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions. Additionally, anticipated impact and restrictions are subject to change. *Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project. *Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time).
*** Indicates revision
Outage # | Revised | Start Date | End Date | Reason Changed | Prev. Start Date | Prev. End Date | Location | Leg | Zone | Maintenance Activity | Anticipated Impact | Potential Restriction Level | TOS Potential Restrictions | Meter(s) in Impacted Area | Loc |  |  | \\houCORP\TRANS\TRANSERVICES\OPPLAN\COMMON\Outages\Outage_DB\TGP\Files
X23-157490 |  | 2023-09-26 | 2023-09-26 |  |  |  | MLV 1-1 to MLV 9-1 | 100 | 0 | Pig Run - Maintenance | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 1.1 |  | MLV 1-1 to MLV 9-1: Pig Run - Maintenance --9/26/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-157482 |  | 2023-11-14 | 2023-11-14 |  |  |  | MLV 1-1 to MLV 9-1 | 100 | 0 | Pig Run - Maintenance | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 1.1 |  | MLV 1-1 to MLV 9-1: Pig Run - Maintenance --11/14/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-502214 | *** | 2023-05-20 | 2023-06-23 | Project Change |  |  | MLV 1-2A to MLV 2-2 | 100 | 0 | Line Lowering | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meter listed will be shut in for the duration of the project. | SOP | Potential out of path restrictions may be at risk. | 412196 ENLINK/TGP NORTH BRAYTON DEHY NUECE 412062 BANHUB/TGP BANQUETE TRANSPORT NUECE 412669 ETP/TGP SHOUP NUECES 54847 WHISTLEP/TGP WHISTLER RECEIPT NUECE | 1.2 | ------meters_affected----------model_loc-- | ***MLV 1-2A to MLV 2-2: Line Lowering --5/20/23 through 6/23/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meter listed will be shut in for the duration of the project. Potential out of path restrictions may be at risk. 412196 ENLINK/TGP NORTH BRAYTON DEHY NUECE 412062 BANHUB/TGP BANQUETE TRANSPORT NUECE 412669 ETP/TGP SHOUP NUECES 54847 WHISTLEP/TGP WHISTLER RECEIPT NUECE ***Project Change ………………………………
X23-60661 |  | 2023-05-22 | 2023-06-10 |  |  |  | MLV 1-2BL to MLV 1-2A | 100 | 0 | Anomaly Remediation | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed will be shut in for the duration of the project. | SOP | Potential out of path restrictions may be at risk. | 412062 BANHUB/TGP BANQUETE TRANSPORT NUECE 412669 ETP/TGP SHOUP NUECES 54847 WHISTLEP/TGP WHISTLER RECEIPT NUECE | 1.2 |  | MLV 1-2BL to MLV 1-2A: Anomaly Remediation --5/22/23 through 6/10/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed will be shut in for the duration of the project. Potential out of path restrictions may be at risk. 412062 BANHUB/TGP BANQUETE TRANSPORT NUECE 412669 ETP/TGP SHOUP NUECES 54847 WHISTLEP/TGP WHISTLER RECEIPT NUECE ………………………………
X23-157494 |  | 2023-09-28 | 2023-09-28 |  |  |  | MLV 1-2 to MLV 9-2 | 100 | 0 | Pig Run - Maintenance | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 1.2 |  | MLV 1-2 to MLV 9-2: Pig Run - Maintenance --9/28/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-157484 |  | 2023-11-16 | 2023-11-16 |  |  |  | MLV 1-2 to MLV 9-2 | 100 | 0 | Pig Run - Maintenance | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 1.2 |  | MLV 1-2 to MLV 9-2: Pig Run - Maintenance --11/16/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-308184 |  | 2023-06-09 | 2023-06-09 |  |  |  | MLV 4-3 to MLV 9-3 | 100 | 0 | Pig Run - Cleaning 6/09 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 4.3 |  | MLV 4-3 to MLV 9-3: Pig Run - Cleaning 6/09 --6/9/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-308200 |  | 2023-06-12 | 2023-06-12 |  |  |  | MLV 4-3 to MLV 9-3 | 100 | 0 | Pig Run - Gauge 6/12 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 4.31 |  | MLV 4-3 to MLV 9-3: Pig Run - Gauge 6/12 --6/12/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-157491 |  | 2023-09-27 | 2023-09-27 |  |  |  | MLV 5-3 to MLV 9-3 | 100 | 0 | Pig Run - Maintenance | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 5.3 |  | MLV 5-3 to MLV 9-3: Pig Run - Maintenance --9/27/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-157486 |  | 2023-11-15 | 2023-11-15 |  |  |  | MLV 5-3 to MLV 9-3 | 100 | 0 | Pig Run - Maintenance | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 5.3 |  | MLV 5-3 to MLV 9-3: Pig Run - Maintenance --11/15/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-113753 |  | 2023-08-08 | 2023-08-10 |  |  |  | MLV 9-1D TO MLV 17-1S | 100 | 0 | Pig Runs - Cleaning 8/08 to 8/10 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 412066 DCP OPER/TGP INEX INTERCONNECT DEHY 420185 COKINOS/TGP OTTIS FARM TX JACKSON 420159 COKINOS/TGP MCCOLLOCH SPENCER FARM 412533 CRIMEXPL/TGP RAUN NO 1 WHARTON 420470 COKINOS/TGP RAS FARM TEXAS WHARTON 420183 /TGP KRENEK FARM TX WHARTON 412523 UES/TGP WILDCAT RASMUSSEN 1 R 412723 PATTERSN/TGP HILL WHARTON 412795 VAR/TGP WEST CLIFFORD DEHY: RIP 321 412261 CRIMEXPL/TGP RASMUSSN 1 DEHY WHAR 420442 COKINOS/TGP RASMUSSEN FARM TX WHART 412655 GCENGY/TGP MUELLER WHARTON 420466 COKINOS/TGP HOLT FARM TX WHARTON 420160 COKINOS/TGP CARRIERE FARM TEXAS WHA 400454 KEM ENER/TGP EGYPT NORTH WEST DEHY | 9.1 |  | MLV 9-1D TO MLV 17-1S: Pig Runs - Cleaning 8/08 to 8/10 --8/8/23 through 8/10/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 412066 DCP OPER/TGP INEX INTERCONNECT DEHY 420185 COKINOS/TGP OTTIS FARM TX JACKSON 420159 COKINOS/TGP MCCOLLOCH SPENCER FARM 412533 CRIMEXPL/TGP RAUN NO 1 WHARTON 420470 COKINOS/TGP RAS FARM TEXAS WHARTON 420183 /TGP KRENEK FARM TX WHARTON 412523 UES/TGP WILDCAT RASMUSSEN 1 R 412723 PATTERSN/TGP HILL WHARTON 412795 VAR/TGP WEST CLIFFORD DEHY: RIP 321 412261 CRIMEXPL/TGP RASMUSSN 1 DEHY WHAR 420442 COKINOS/TGP RASMUSSEN FARM TX WHART 412655 GCENGY/TGP MUELLER WHARTON 420466 COKINOS/TGP HOLT FARM TX WHARTON 420160 COKINOS/TGP CARRIERE FARM TEXAS WHA 400454 KEM ENER/TGP EGYPT NORTH WEST DEHY ………………………………
X23-113754 |  | 2023-08-11 | 2023-08-11 |  |  |  | MLV 9-1D TO MLV 17-1S | 100 | 0 | Pig Runs - Gauge 8/11 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 412066 DCP OPER/TGP INEX INTERCONNECT DEHY 420185 COKINOS/TGP OTTIS FARM TX JACKSON 420159 COKINOS/TGP MCCOLLOCH SPENCER FARM 412533 CRIMEXPL/TGP RAUN NO 1 WHARTON 420470 COKINOS/TGP RAS FARM TEXAS WHARTON 420183 /TGP KRENEK FARM TX WHARTON 412523 UES/TGP WILDCAT RASMUSSEN 1 R 412723 PATTERSN/TGP HILL WHARTON 412795 VAR/TGP WEST CLIFFORD DEHY: RIP 321 412261 CRIMEXPL/TGP RASMUSSN 1 DEHY WHAR 420442 COKINOS/TGP RASMUSSEN FARM TX WHART 412655 GCENGY/TGP MUELLER WHARTON 420466 COKINOS/TGP HOLT FARM TX WHARTON 420160 COKINOS/TGP CARRIERE FARM TEXAS WHA 400454 KEM ENER/TGP EGYPT NORTH WEST DEHY | 9.11 |  | MLV 9-1D TO MLV 17-1S: Pig Runs - Gauge 8/11 --8/11/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 412066 DCP OPER/TGP INEX INTERCONNECT DEHY 420185 COKINOS/TGP OTTIS FARM TX JACKSON 420159 COKINOS/TGP MCCOLLOCH SPENCER FARM 412533 CRIMEXPL/TGP RAUN NO 1 WHARTON 420470 COKINOS/TGP RAS FARM TEXAS WHARTON 420183 /TGP KRENEK FARM TX WHARTON 412523 UES/TGP WILDCAT RASMUSSEN 1 R 412723 PATTERSN/TGP HILL WHARTON 412795 VAR/TGP WEST CLIFFORD DEHY: RIP 321 412261 CRIMEXPL/TGP RASMUSSN 1 DEHY WHAR 420442 COKINOS/TGP RASMUSSEN FARM TX WHART 412655 GCENGY/TGP MUELLER WHARTON 420466 COKINOS/TGP HOLT FARM TX WHARTON 420160 COKINOS/TGP CARRIERE FARM TEXAS WHA 400454 KEM ENER/TGP EGYPT NORTH WEST DEHY ………………………………
X23-113756 |  | 2023-08-15 | 2023-08-15 |  |  |  | MLV 9-1D TO MLV 17-1S | 100 | 0 | Pig Runs - MFL-C 8/15 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 412066 DCP OPER/TGP INEX INTERCONNECT DEHY 420185 COKINOS/TGP OTTIS FARM TX JACKSON 420159 COKINOS/TGP MCCOLLOCH SPENCER FARM 412533 CRIMEXPL/TGP RAUN NO 1 WHARTON 420470 COKINOS/TGP RAS FARM TEXAS WHARTON 420183 /TGP KRENEK FARM TX WHARTON 412523 UES/TGP WILDCAT RASMUSSEN 1 R 412723 PATTERSN/TGP HILL WHARTON 412795 VAR/TGP WEST CLIFFORD DEHY: RIP 321 412261 CRIMEXPL/TGP RASMUSSN 1 DEHY WHAR 420442 COKINOS/TGP RASMUSSEN FARM TX WHART 412655 GCENGY/TGP MUELLER WHARTON 420466 COKINOS/TGP HOLT FARM TX WHARTON 420160 COKINOS/TGP CARRIERE FARM TEXAS WHA 400454 KEM ENER/TGP EGYPT NORTH WEST DEHY | 9.12 |  | MLV 9-1D TO MLV 17-1S: Pig Runs - MFL-C 8/15 --8/15/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 412066 DCP OPER/TGP INEX INTERCONNECT DEHY 420185 COKINOS/TGP OTTIS FARM TX JACKSON 420159 COKINOS/TGP MCCOLLOCH SPENCER FARM 412533 CRIMEXPL/TGP RAUN NO 1 WHARTON 420470 COKINOS/TGP RAS FARM TEXAS WHARTON 420183 /TGP KRENEK FARM TX WHARTON 412523 UES/TGP WILDCAT RASMUSSEN 1 R 412723 PATTERSN/TGP HILL WHARTON 412795 VAR/TGP WEST CLIFFORD DEHY: RIP 321 412261 CRIMEXPL/TGP RASMUSSN 1 DEHY WHAR 420442 COKINOS/TGP RASMUSSEN FARM TX WHART 412655 GCENGY/TGP MUELLER WHARTON 420466 COKINOS/TGP HOLT FARM TX WHARTON 420160 COKINOS/TGP CARRIERE FARM TEXAS WHA 400454 KEM ENER/TGP EGYPT NORTH WEST DEHY ………………………………
X23-113765 |  | 2023-08-17 | 2023-08-17 |  |  |  | MLV 9-1D TO MLV 17-1S | 100 | 0 | Pig Runs - MFL-S 8/17 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 412066 DCP OPER/TGP INEX INTERCONNECT DEHY 420185 COKINOS/TGP OTTIS FARM TX JACKSON 420159 COKINOS/TGP MCCOLLOCH SPENCER FARM 412533 CRIMEXPL/TGP RAUN NO 1 WHARTON 420470 COKINOS/TGP RAS FARM TEXAS WHARTON 420183 /TGP KRENEK FARM TX WHARTON 412523 UES/TGP WILDCAT RASMUSSEN 1 R 412723 PATTERSN/TGP HILL WHARTON 412795 VAR/TGP WEST CLIFFORD DEHY: RIP 321 412261 CRIMEXPL/TGP RASMUSSN 1 DEHY WHAR 420442 COKINOS/TGP RASMUSSEN FARM TX WHART 412655 GCENGY/TGP MUELLER WHARTON 420466 COKINOS/TGP HOLT FARM TX WHARTON 420160 COKINOS/TGP CARRIERE FARM TEXAS WHA 400454 KEM ENER/TGP EGYPT NORTH WEST DEHY | 9.15 |  | MLV 9-1D TO MLV 17-1S: Pig Runs - MFL-S 8/17 --8/17/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 412066 DCP OPER/TGP INEX INTERCONNECT DEHY 420185 COKINOS/TGP OTTIS FARM TX JACKSON 420159 COKINOS/TGP MCCOLLOCH SPENCER FARM 412533 CRIMEXPL/TGP RAUN NO 1 WHARTON 420470 COKINOS/TGP RAS FARM TEXAS WHARTON 420183 /TGP KRENEK FARM TX WHARTON 412523 UES/TGP WILDCAT RASMUSSEN 1 R 412723 PATTERSN/TGP HILL WHARTON 412795 VAR/TGP WEST CLIFFORD DEHY: RIP 321 412261 CRIMEXPL/TGP RASMUSSN 1 DEHY WHAR 420442 COKINOS/TGP RASMUSSEN FARM TX WHART 412655 GCENGY/TGP MUELLER WHARTON 420466 COKINOS/TGP HOLT FARM TX WHARTON 420160 COKINOS/TGP CARRIERE FARM TEXAS WHA 400454 KEM ENER/TGP EGYPT NORTH WEST DEHY ………………………………
X23-40750 |  | 2023-06-08 | 2023-06-08 |  |  |  | MLV 4-3 to MLV 9-3 | 100 | 0 | Pig Run - Cleaning 6/08 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 9.3 |  | MLV 4-3 to MLV 9-3: Pig Run - Cleaning 6/08 --6/8/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-30090 |  | 2023-06-14 | 2023-06-14 |  |  |  | MLV 4-3 to MLV 9-3 | 100 | 0 | Pig Run - AFD 6/14 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 9.31 |  | MLV 4-3 to MLV 9-3: Pig Run - AFD 6/14 --6/14/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-396966 |  | 2023-06-14 | 2023-06-14 |  |  |  | Sta 11A | 100 | 0 | Annual ESD Test | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 11 |  | Sta 11A: Annual ESD Test --6/14/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-155982 |  | 2023-05-16 | 2023-08-07 |  |  |  | MLV 11-1 TO MLV 12-1 | 100 | 0 | Pressure Weld Replacement | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. | 412066 DCP OPER/TGP INEZ INTERCONNECT DEHY | 11.1 |  | MLV 11-1 TO MLV 12-1: Pressure Weld Replacement --5/16/23 through 8/7/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. 412066 DCP OPER/TGP INEZ INTERCONNECT DEHY ………………………………
X23-155985 |  | 2023-04-27 | 2023-07-28 |  |  |  | MLV 13-1 TO MLV 17-1 | 100 | 0 | Pressure Weld Replacement | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 420185 COKINOS/TGP OTTIS FARM TX JACKSON 412533 CRIMEXPL/TGP RAUN NO 1 WARTHON 420470 COKINOS/TGP RAS FARM TEXAS WHARTN 420183 COKENRG/TGP KRENEK FARM TX WHARTON 412523 UES/TGP WILDCAT RASMUSSEN 1 R 412723 PATTERSN/TGP HILL WHARTON 412261 CRIMEXPL/TGP RASMUSSEN 1 DEHY WHAR 420442 COKINOS/TGP RASMUSSEN FARM TX WHART 412655 GCENGY/TGP MUELLER WHARTON 420466 COKINOS/TGP HOLT FARM TX WHARTON 420160 COKINOS/TGP CARRIERE FARM TEXAS WHA 400454 KEM ENER/TGP EGYPT NORTH WEST DEHY 412091 WAGNER/TGP GARWOOD TRANSPORT COLORA 54086 TGP/PHP SHERIDAN COLORADO 410144 CPROC/TGP HCP COLORADO 420158 COKINOS/TGP RAUN FARM TX WHARTON 420369 COKINOS/TGP WIGGINTON FARM TX WH 420332 COKINOS/TGP NITSCH FARM TX WHARTON | 13.1 |  | MLV 13-1 TO MLV 17-1: Pressure Weld Replacement --4/27/23 through 7/28/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 420185 COKINOS/TGP OTTIS FARM TX JACKSON 412533 CRIMEXPL/TGP RAUN NO 1 WARTHON 420470 COKINOS/TGP RAS FARM TEXAS WHARTN 420183 COKENRG/TGP KRENEK FARM TX WHARTON 412523 UES/TGP WILDCAT RASMUSSEN 1 R 412723 PATTERSN/TGP HILL WHARTON 412261 CRIMEXPL/TGP RASMUSSEN 1 DEHY WHAR 420442 COKINOS/TGP RASMUSSEN FARM TX WHART 412655 GCENGY/TGP MUELLER WHARTON 420466 COKINOS/TGP HOLT FARM TX WHARTON 420160 COKINOS/TGP CARRIERE FARM TEXAS WHA 400454 KEM ENER/TGP EGYPT NORTH WEST DEHY 412091 WAGNER/TGP GARWOOD TRANSPORT COLORA 54086 TGP/PHP SHERIDAN COLORADO 410144 CPROC/TGP HCP COLORADO 420158 COKINOS/TGP RAUN FARM TX WHARTON 420369 COKINOS/TGP WIGGINTON FARM TX WH 420332 COKINOS/TGP NITSCH FARM TX WHARTON ………………………………
X23-461855 |  | 2023-05-02 | 2023-07-14 |  |  |  | MLV 15-1 to MLV 17-1 | 100 | 0 | Install Two Tees | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 420185 COKINOS/TGP OTTIS FARM TX JACKSON 412533 CRIMEXPL/TGP RAUN NO 1 WARTHON 420470 COKINOS/TGP RAS FARM TEXAS WHARTN 420183 COKENRG/TGP KRENEK FARM TX WHARTON 412523 UES/TGP WILDCAT RASMUSSEN 1 R 412723 PATTERSN/TGP HILL WHARTON 412261 CRIMEXPL/TGP RASMUSSEN 1 DEHY WHAR 420442 COKINOS/TGP RASMUSSEN FARM TX WHART 412655 GCENGY/TGP MUELLER WHARTON 420466 COKINOS/TGP HOLT FARM TX WHARTON 420160 COKINOS/TGP CARRIERE FARM TEXAS WHA 400454 KEM ENER/TGP EGYPT NORTH WEST DEHY 412091 WAGNER/TGP GARWOOD TRANSPORT COLORA 54086 TGP/PHP SHERIDAN COLORADO 410144 CPROC/TGP HCP COLORADO 420158 COKINOS/TGP RAUN FARM TX WHARTON 420369 COKINOS/TGP WIGGINTON FARM TX WH 420332 COKINOS/TGP NITSCH FARM TX WHARTON | 15.1 |  | MLV 15-1 to MLV 17-1: Install Two Tees --5/2/23 through 7/14/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 420185 COKINOS/TGP OTTIS FARM TX JACKSON 412533 CRIMEXPL/TGP RAUN NO 1 WARTHON 420470 COKINOS/TGP RAS FARM TEXAS WHARTN 420183 COKENRG/TGP KRENEK FARM TX WHARTON 412523 UES/TGP WILDCAT RASMUSSEN 1 R 412723 PATTERSN/TGP HILL WHARTON 412261 CRIMEXPL/TGP RASMUSSEN 1 DEHY WHAR 420442 COKINOS/TGP RASMUSSEN FARM TX WHART 412655 GCENGY/TGP MUELLER WHARTON 420466 COKINOS/TGP HOLT FARM TX WHARTON 420160 COKINOS/TGP CARRIERE FARM TEXAS WHA 400454 KEM ENER/TGP EGYPT NORTH WEST DEHY 412091 WAGNER/TGP GARWOOD TRANSPORT COLORA 54086 TGP/PHP SHERIDAN COLORADO 410144 CPROC/TGP HCP COLORADO 420158 COKINOS/TGP RAUN FARM TX WHARTON 420369 COKINOS/TGP WIGGINTON FARM TX WH 420332 COKINOS/TGP NITSCH FARM TX WHARTON ………………………………
X23-461859 |  | 2023-08-01 | 2023-08-01 |  |  |  | MLV 15-1 to MLV 16-1 | 100 | 0 | Meter Station Tie In to Ln 1 (Pin 49525 ) | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 15.1 |  | MLV 15-1 to MLV 16-1: Meter Station Tie In to Ln 1 (Pin 49525 ) --8/1/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-461858 |  | 2023-07-21 | 2023-07-21 |  |  |  | MLV 16-1 to MLV 17-1 | 100 | 0 | Meter Station Tie In to Ln 1 (Pin 49524) | This project will require taking the facility out of service which could limit throughput and result in restrictions based on customer nominations. The meter listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 49524 GULFSTH/TGP COASTAL BEND LNG WHARTO | 16.1 |  | MLV 16-1 to MLV 17-1: Meter Station Tie In to Ln 1 (Pin 49524) --7/21/23: This project will require taking the facility out of service which could limit throughput and result in restrictions based on customer nominations. The meter listed will be shut in during the project. Potential out of path restrictions may be at risk. 49524 GULFSTH/TGP COASTAL BEND LNG WHARTO ………………………………
X23-113649 |  | 2023-10-23 | 2023-10-27 |  |  |  | MLV 17-1D TO MLV 20-1A | 100 | 0 | Pig Runs - Chemical Cleaning 10/23 to 10/27 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meter listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 420167 COKINOS/TGP WOODS FARM TX FORT BEND | 17.1 |  | MLV 17-1D TO MLV 20-1A: Pig Runs - Chemical Cleaning 10/23 to 10/27 --10/23/23 through 10/27/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meter listed will be shut in during the project. Potential out of path restrictions may be at risk. 420167 COKINOS/TGP WOODS FARM TX FORT BEND ………………………………
X23-113659 |  | 2023-10-27 | 2023-10-27 |  |  |  | MLV 17-1D TO MLV 20-1A | 100 | 0 | Pig Runs - Gauge 10/27 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meter listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 420167 COKINOS/TGP WOODS FARM TX FORT BEND | 17.11 |  | MLV 17-1D TO MLV 20-1A: Pig Runs - Gauge 10/27 --10/27/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meter listed will be shut in during the project. Potential out of path restrictions may be at risk. 420167 COKINOS/TGP WOODS FARM TX FORT BEND ………………………………
X23-113660 |  | 2023-10-31 | 2023-10-31 |  |  |  | MLV 17-1D TO MLV 20-1A | 100 | 0 | Pig Runs - MFL-C 10/31 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meter listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 420167 COKINOS/TGP WOODS FARM TX FORT BEND | 17.12 |  | MLV 17-1D TO MLV 20-1A: Pig Runs - MFL-C 10/31 --10/31/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meter listed will be shut in during the project. Potential out of path restrictions may be at risk. 420167 COKINOS/TGP WOODS FARM TX FORT BEND ………………………………
X23-113676 |  | 2023-11-02 | 2023-11-02 |  |  |  | MLV 17-1D TO MLV 20-1A | 100 | 0 | Pig Runs - EMAT 11/02 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meter listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 420167 COKINOS/TGP WOODS FARM TX FORT BEND | 17.13 |  | MLV 17-1D TO MLV 20-1A: Pig Runs - EMAT 11/02 --11/2/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meter listed will be shut in during the project. Potential out of path restrictions may be at risk. 420167 COKINOS/TGP WOODS FARM TX FORT BEND ………………………………
X23-113689 |  | 2023-10-12 | 2023-10-12 |  |  |  | MLV 17-3D TO MLV 20-3A | 100 | 0 | Pig Runs - EMAT 10/12 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meter listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 421085 SYMMETRY/TGP PEDERSON ROAD WALLER | 17.14 |  | MLV 17-3D TO MLV 20-3A: Pig Runs - EMAT 10/12 --10/12/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meter listed will be shut in during the project. Potential out of path restrictions may be at risk. 421085 SYMMETRY/TGP PEDERSON ROAD WALLER ………………………………
X23-150700 |  | 2023-09-15 | 2023-10-31 |  |  |  | MLV 18-2 to MLV 18-2A | 100 | 0 | Make Piggable | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 17.2 |  | MLV 18-2 to MLV 18-2A: Make Piggable --9/15/23 through 10/31/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-113682 |  | 2023-10-03 | 2023-10-06 |  |  |  | MLV 17-3D TO MLV 20-3A | 100 | 0 | Pig Runs - Chemical Cleaning 10/03 to 10/06 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meter listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 421085 SYMMETRY/TGP PEDERSON ROAD WALLER | 17.3 |  | MLV 17-3D TO MLV 20-3A: Pig Runs - Chemical Cleaning 10/03 to 10/06 --10/3/23 through 10/6/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meter listed will be shut in during the project. Potential out of path restrictions may be at risk. 421085 SYMMETRY/TGP PEDERSON ROAD WALLER ………………………………
X23-113686 |  | 2023-10-06 | 2023-10-06 |  |  |  | MLV 17-3D TO MLV 20-3A | 100 | 0 | Pig Runs - Gauge Pig 10/06 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meter listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 421085 SYMMETRY/TGP PEDERSON ROAD WALLER | 17.31 |  | MLV 17-3D TO MLV 20-3A: Pig Runs - Gauge Pig 10/06 --10/6/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meter listed will be shut in during the project. Potential out of path restrictions may be at risk. 421085 SYMMETRY/TGP PEDERSON ROAD WALLER ………………………………
X23-113687 |  | 2023-10-10 | 2023-10-10 |  |  |  | MLV 17-3D TO MLV 20-3A | 100 | 0 | Pig Runs - MFL-C 10/10 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 421085 SYMMETRY/TGP PEDERSON ROAD WALLER | 17.32 |  | MLV 17-3D TO MLV 20-3A: Pig Runs - MFL-C 10/10 --10/10/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 421085 SYMMETRY/TGP PEDERSON ROAD WALLER ………………………………
X23-263357 |  | 2023-04-15 | 2023-07-15 |  |  |  | MLV 18-3A TO MLV 19-3 | 100 | 0 | Class Change | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 18.3 |  | MLV 18-3A TO MLV 19-3: Class Change --4/15/23 through 7/15/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-69749 | *** | 2023-07-07 | 2023-08-19 | Project Change | 2023-07-06 |  | MLV 20-2 TO MLV 20-2A | 100 | 0 | Pressure Weld Replacement | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 20.2 | --start_date--------------model_loc-- | ***MLV 20-2 TO MLV 20-2A: Pressure Weld Replacement --7/7/23 through 8/19/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. *** Date Change, Previously scheduled 7/6/23 to 8/19/23. ………………………………
X23-69745 |  | 2023-04-21 | 2023-07-05 |  |  |  | MLV 20-3 TO MLV 20-3A | 100 | 0 | Pressure Weld Replacement | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 20.3 |  | MLV 20-3 TO MLV 20-3A: Pressure Weld Replacement --4/21/23 through 7/5/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-579316 | *** | 2023-06-02 | 2023-06-09 | Added |  |  | MLV 25-1 to MLV 26-1 | 100 | 0 | Emergent Repair | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 25.1 | ------ | ***MLV 25-1 to MLV 26-1: Emergent Repair --6/2/23 through 6/9/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ***Added ………………………………
X22-621358 |  | 2023-10-10 | 2023-10-29 |  |  |  | MLV 26-1 Relocation | 100 | 0 | Highway Widening | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 26.1 |  | MLV 26-1 Relocation: Highway Widening --10/10/23 through 10/29/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-428676 |  | 2023-08-21 | 2023-09-08 |  |  |  | MLV 26-2 TO MLV 27-2 | 100 | 0 | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed may be shut in for the duration of the project. | SOP | Potential out of path restrictions may be at risk. | 421064 E TX ELE/TGP SAN JACINTO | 26.2 |  | MLV 26-2 TO MLV 27-2: Anomaly Remediation --8/21/23 through 9/8/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed may be shut in for the duration of the project. Potential out of path restrictions may be at risk. 421064 E TX ELE/TGP SAN JACINTO ………………………………
X22-815863 |  | 2023-10-30 | 2023-11-19 |  |  |  | MLV 26-2 Relocation | 100 | 0 | Highway Widening | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 26.2 |  | MLV 26-2 Relocation: Highway Widening --10/30/23 through 11/19/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X22-815864 |  | 2023-09-19 | 2023-10-09 |  |  |  | MLV 26-3 Relocation | 100 | 0 | Highway Widening | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 26.3 |  | MLV 26-3 Relocation: Highway Widening --9/19/23 through 10/9/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-428675 |  | 2023-08-07 | 2023-08-18 |  |  |  | MLV 28-2 TO MLV 29-2 | 100 | 0 | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 28.2 |  | MLV 28-2 TO MLV 29-2: Anomaly Remediation --8/7/23 through 8/18/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-428674 |  | 2023-07-17 | 2023-08-04 |  |  |  | MLV 31-2 TO MLV 32-2 | 100 | 0 | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 31.2 |  | MLV 31-2 TO MLV 32-2: Anomaly Remediation --7/17/23 through 8/4/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-170135 | *** | 2023-06-27 | 2023-06-28 | Project Change | 2023-06-06 | 2023-06-07 | Sta 32 | 100 | 0 | Annual ESD Test & Maintenance | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 32 | --start_date--end_date------------model_loc-- | ***Sta 32: Annual ESD Test & Maintenance --6/27/23 through 6/28/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. *** Date Change, Previously scheduled 6/6/23 to 6/7/23. ………………………………
X23-113705 | *** | 2023-07-10 | 2023-07-14 | Project Change |  |  | MLV 32-2D TO MLV 40-2S | 100 | 0 | Pig Runs - Chemical Cleaning 7/10 to 7/14 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 32.2 | ------meters_affected--anticipated_impact--------model_loc-- | ***MLV 32-2D TO MLV 40-2S: Pig Runs - Chemical Cleaning 7/10 to 7/14 --7/10/23 through 7/14/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ***Project Change ………………………………
X23-113708 | *** | 2023-07-14 | 2023-07-14 | Project Change |  |  | MLV 32-2D TO MLV 40-2S | 100 | 0 | Pig Runs - Gauge 7/14 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 32.21 | ------meters_affected--anticipated_impact--------model_loc-- | ***MLV 32-2D TO MLV 40-2S: Pig Runs - Gauge 7/14 --7/14/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ***Project Change ………………………………
X23-113710 | *** | 2023-07-20 | 2023-07-20 | Project Change |  |  | MLV 32-2D TO MLV 40-2S | 100 | 0 | Pig Runs - CLP / MFL-A / IMU 7/20 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 32.22 | ------meters_affected--anticipated_impact--------model_loc-- | ***MLV 32-2D TO MLV 40-2S: Pig Runs - CLP / MFL-A / IMU 7/20 --7/20/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ***Project Change ………………………………
X23-113721 | *** | 2023-07-25 | 2023-07-25 | Project Change |  |  | MLV 32-2D TO MLV 40-2S | 800 | 1 | Pig Runs - MFL-C 7/25 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 32.23 | ------meters_affected--anticipated_impact--------model_loc-- | ***MLV 32-2D TO MLV 40-2S: Pig Runs - MFL-C 7/25 --7/25/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ***Project Change ………………………………
X23-113722 | *** | 2023-07-27 | 2023-07-27 | Project Change |  |  | MLV 32-2D TO MLV 40-2S | 800 | 1 | Pig Runs - EMAT 7/27 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 32.24 | ------meters_affected--anticipated_impact--------model_loc-- | ***MLV 32-2D TO MLV 40-2S: Pig Runs - EMAT 7/27 --7/27/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ***Project Change ………………………………
X23-159657 | *** | 2023-08-02 | 2023-08-02 | Project Change | 2023-06-06 | 2023-06-06 | MLV 32-3D to MLV 40-3S | 100 | 0 | Maintenance Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 32.3 | --start_date--end_date------------model_loc-- | ***MLV 32-3D to MLV 40-3S: Maintenance Pig --8/2/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. *** Date Change, Previously scheduled 6/6/23. ………………………………
X23-156000 |  | 2023-08-01 | 2023-09-15 |  |  |  | MLV 36-1 TO MLV 37-1 | 100 | 0 | Class Change | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 36.1 |  | MLV 36-1 TO MLV 37-1: Class Change --8/1/23 through 9/15/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-156003 |  | 2023-09-15 | 2023-10-15 |  |  |  | MLV 36-2 TO MLV 37-2 | 100 | 0 | Class Change | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 36.2 |  | MLV 36-2 TO MLV 37-2: Class Change --9/15/23 through 10/15/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-156004 |  | 2023-10-15 | 2023-11-30 |  |  |  | MLV 36-3 TO MLV 37-3 | 100 | 0 | Class Change | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 36.3 |  | MLV 36-3 TO MLV 37-3: Class Change --10/15/23 through 11/30/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-156005 |  | 2023-10-01 | 2023-10-30 |  |  |  | MLV 39-1 TO MLV 40-1 | 100 | 0 | Class Change | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 39.1 |  | MLV 39-1 TO MLV 40-1: Class Change --10/1/23 through 10/30/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-156006 |  | 2023-11-01 | 2023-11-30 |  |  |  | MLV 39-2 TO MLV 40-2 | 100 | 0 | Wrinkle Bend Replacement | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 39.2 |  | MLV 39-2 TO MLV 40-2: Wrinkle Bend Replacement --11/1/23 through 11/30/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-374931 |  | 2023-04-08 | 2023-06-09 |  |  |  | Sta 40 | 100 | 1 | Unit 1C - Emergent Repair | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 40.033 |  | Sta 40: Unit 1C - Emergent Repair --4/8/23 through 6/9/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-374748 |  | 2023-09-12 | 2023-09-15 |  |  |  | MLV 41-2A to MLV 42-2 | 100 | 1 | Pipe Replacement | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 41.2 |  | MLV 41-2A to MLV 42-2: Pipe Replacement --9/12/23 through 9/15/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-135883 | *** | 2023-03-06 | 2023-06-06 | Completed |  |  | MLV 41-4 TO MLV 42-4 | 100 | 1 | Anomaly Remediation | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 41.4 | ------ | ***MLV 41-4 TO MLV 42-4: Anomaly Remediation ***Completed
X23-135887 |  | 2023-06-07 | 2023-06-23 |  |  |  | MLV 42-4 TO MLV 43-4 | 100 | 1 | Anomaly Remediation | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 42.4 |  | MLV 42-4 TO MLV 43-4: Anomaly Remediation --6/7/23 through 6/23/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-100958 |  | 2023-10-17 | 2023-10-23 |  |  |  | Bear Creek Storage | 100 | 1 | Shut-in Test | This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations. The meter listed below will be shut-in during the project. | SOP | Potential out of path restrictions may be at risk. | 460017 STORAGE – BEAR CREEK | 43.1 |  | Bear Creek Storage: Shut-in Test --10/17/23 through 10/23/23: This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations. The meter listed below will be shut-in during the project. Potential out of path restrictions may be at risk. 460017 STORAGE – BEAR CREEK ………………………………
X23-520546 |  | 2023-06-07 | 2023-06-08 |  |  |  | Bear Creek Storage | 100 | 1 | Chemical Clean & Flow Test | This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations. The meter listed below will be shut-in during the project. | SOP | Potential out of path restrictions may be at risk. | 460017 STORAGE – BEAR CREEK | 43.11 |  | Bear Creek Storage: Chemical Clean & Flow Test --6/7/23 through 6/8/23: This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations. The meter listed below will be shut-in during the project. Potential out of path restrictions may be at risk. 460017 STORAGE – BEAR CREEK ………………………………
X23-135888 |  | 2023-06-27 | 2023-08-04 |  |  |  | MLV 43-4 TO MLV 44-4 | 100 | 1 | Anomaly Remediation | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 43.4 |  | MLV 43-4 TO MLV 44-4: Anomaly Remediation --6/27/23 through 8/4/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-135889 |  | 2023-08-08 | 2023-08-11 |  |  |  | MLV 44-4 TO MLV 45-4 | 100 | 1 | Anomaly Remediation | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 44.4 |  | MLV 44-4 TO MLV 45-4: Anomaly Remediation --8/8/23 through 8/11/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-375002 |  | 2023-05-15 | 2023-07-15 |  |  |  | MLV 46-2 thru MLV 46-2BR | 100 | 1 | Pipe Replacement | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. | 47872 ATMOS TL/TGP CHAUVIN OUACHITA | 46.2 |  | MLV 46-2 thru MLV 46-2BR: Pipe Replacement --5/15/23 through 7/15/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. 47872 ATMOS TL/TGP CHAUVIN OUACHITA ………………………………
X23-135890 |  | 2023-08-15 | 2023-09-01 |  |  |  | MLV 46-4 TO MLV 46-4A | 100 | 1 | Anomaly Remediation | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 46.4 |  | MLV 46-4 TO MLV 46-4A: Anomaly Remediation --8/15/23 through 9/1/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-59502 |  | 2023-01-18 | 2023-12-31 |  |  |  | Sta 47 | 100 | 1 | Unit 9B - Power Cylinder Investigation | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 47.025 |  | Sta 47: Unit 9B - Power Cylinder Investigation --1/18/23 through 12/31/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-140712 |  | 2023-05-16 | 2023-06-30 |  |  |  | MLV 47-1BL thru MLV 49-1 | 100 | 1 | Tee Installation | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 47.1 |  | MLV 47-1BL thru MLV 49-1: Tee Installation --5/16/23 through 6/30/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-374732 |  | 2023-09-15 | 2023-09-30 |  |  |  | MLV 47-1D to MLV 48-1 | 100 | 1 | Trap Modification | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 47.1 |  | MLV 47-1D to MLV 48-1: Trap Modification --9/15/23 through 9/30/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-24600 |  | 2023-05-16 | 2023-08-16 |  |  |  | MLV 47-2BL thru MLV 49-2 | 100 | 1 | Pipe Replacement | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meter listed is expected to be shut in from 5/13/23 to 5/29/23. | SOP | Potential out of path restrictions may be at risk. | 47872 ATMOS TL/TGP CHAUVIN OUACHITA | 47.2 |  | MLV 47-2BL thru MLV 49-2: Pipe Replacement --5/16/23 through 8/16/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meter listed is expected to be shut in from 5/13/23 to 5/29/23. Potential out of path restrictions may be at risk. 47872 ATMOS TL/TGP CHAUVIN OUACHITA ………………………………
X23-276279 |  | 2023-08-15 | 2023-08-15 |  |  |  | MLV 47-2D TO MLV 53-2CR | 100 | 1 | Pig Runs - Cleaning 8/15 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 47.2 |  | MLV 47-2D TO MLV 53-2CR: Pig Runs - Cleaning 8/15 --8/15/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-276282 |  | 2023-08-17 | 2023-08-17 |  |  |  | MLV 47-2D TO MLV 53-2CR | 100 | 1 | Pig Runs - Cleaning & Gauge 8/17 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 47.21 |  | MLV 47-2D TO MLV 53-2CR: Pig Runs - Cleaning & Gauge 8/17 --8/17/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-276283 |  | 2023-08-22 | 2023-08-22 |  |  |  | MLV 47-2D TO MLV 53-2CR | 100 | 1 | Pig Runs - AFD 8/22 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 47.22 |  | MLV 47-2D TO MLV 53-2CR: Pig Runs - AFD 8/22 --8/22/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-276284 |  | 2023-08-24 | 2023-08-24 |  |  |  | MLV 47-2D TO MLV 53-2CR | 100 | 1 | Pig Runs - EMAT 8/24 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 47.23 |  | MLV 47-2D TO MLV 53-2CR: Pig Runs - EMAT 8/24 --8/24/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-276271 |  | 2023-09-21 | 2023-09-21 |  |  |  | MLV 47-3D TO MLV 53-3CR | 100 | 1 | Pig Runs - Cleaning & Gauge 9/21 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be temporarily shut in as the pig passes. | SOP | Potential out of path restrictions may be at risk. | 421062 ENTRGYLA/TGP PERRYVILLE POWER OUACH 412352 EGT/TGP GUTHRIE EXCHANGE OUACHITA | 47.31 |  | MLV 47-3D TO MLV 53-3CR: Pig Runs - Cleaning & Gauge 9/21 --9/21/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be temporarily shut in as the pig passes. Potential out of path restrictions may be at risk. 421062 ENTRGYLA/TGP PERRYVILLE POWER OUACH 412352 EGT/TGP GUTHRIE EXCHANGE OUACHITA ………………………………
X23-276276 |  | 2023-10-03 | 2023-10-03 |  |  |  | MLV 47-3D TO MLV 53-3CR | 100 | 1 | Pig Runs - AFD 10/3 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be temporarily shut in as the pig passes. | SOP | Potential out of path restrictions may be at risk. | 421062 ENTRGYLA/TGP PERRYVILLE POWER OUACH 412352 EGT/TGP GUTHRIE EXCHANGE OUACHITA | 47.32 |  | MLV 47-3D TO MLV 53-3CR: Pig Runs - AFD 10/3 --10/3/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be temporarily shut in as the pig passes. Potential out of path restrictions may be at risk. 421062 ENTRGYLA/TGP PERRYVILLE POWER OUACH 412352 EGT/TGP GUTHRIE EXCHANGE OUACHITA ………………………………
X23-276277 |  | 2023-10-05 | 2023-10-05 |  |  |  | MLV 47-3D TO MLV 53-3CR | 100 | 1 | Pig Runs - EMAT 10/5 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be temporarily shut in as the pig passes. | SOP | Potential out of path restrictions may be at risk. | 421062 ENTRGYLA/TGP PERRYVILLE POWER OUACH 412352 EGT/TGP GUTHRIE EXCHANGE OUACHITA | 47.33 |  | MLV 47-3D TO MLV 53-3CR: Pig Runs - EMAT 10/5 --10/5/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be temporarily shut in as the pig passes. Potential out of path restrictions may be at risk. 421062 ENTRGYLA/TGP PERRYVILLE POWER OUACH 412352 EGT/TGP GUTHRIE EXCHANGE OUACHITA ………………………………
X23-276287 |  | 2023-09-26 | 2023-09-26 |  |  |  | MLV 47-3D TO MLV 53-3CR | 100 | 1 | Pig Runs - CLP 9/26 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 47.34 |  | MLV 47-3D TO MLV 53-3CR: Pig Runs - CLP 9/26 --9/26/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-276289 |  | 2023-09-28 | 2023-09-28 |  |  |  | MLV 47-3D TO MLV 53-3CR | 100 | 1 | Pig Runs - MDS 9/28 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 47.35 |  | MLV 47-3D TO MLV 53-3CR: Pig Runs - MDS 9/28 --9/28/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-374734 |  | 2023-09-01 | 2023-09-15 |  |  |  | MLV 52-1 to MLV 54-1S | 100 | 1 | Trap Modification | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 52.1 |  | MLV 52-1 to MLV 54-1S: Trap Modification --9/1/23 through 9/15/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-69503 |  | 2023-10-17 | 2023-10-19 |  |  |  | Sta 54 | 100 | 1 | Annual ESD Test | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 54 |  | Sta 54: Annual ESD Test --10/17/23 through 10/19/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X22-583201 |  | 2023-01-09 | 2023-06-29 |  |  |  | Sta 54 | 100 | 1 | Unit 1B - GHG Inspection | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 54.017 |  | Sta 54: Unit 1B - GHG Inspection --1/9/23 through 6/29/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-170264 |  | 2023-07-17 | 2023-07-28 |  |  |  | Sta 63 | 100 | 1 | Bldg D - Jacket Water System Maintenance | This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 63.049 |  | Sta 63: Bldg D - Jacket Water System Maintenance --7/17/23 through 7/28/23: This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-57468 |  | 2023-08-15 | 2023-08-15 |  |  |  | MLV 63-2D to 69-2 | 100 | 1 | Pig Runs - Cleaning / Gauge 8/15 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 63.2 |  | MLV 63-2D to 69-2: Pig Runs - Cleaning / Gauge 8/15 --8/15/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-57472 |  | 2023-08-17 | 2023-08-17 |  |  |  | MLV 63-2D to 69-2 | 100 | 1 | Pig Runs - MFL Combo 8/17 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 63.21 |  | MLV 63-2D to 69-2: Pig Runs - MFL Combo 8/17 --8/17/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-307641 |  | 2023-03-27 | 2023-10-30 |  |  |  | Sta 71 | 100 | 1 | Unit 3A - Discharge Bottle | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 71.003 |  | Sta 71: Unit 3A - Discharge Bottle --3/27/23 through 10/30/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-307735 |  | 2023-03-27 | 2023-08-04 |  |  |  | Sta 71 | 100 | 1 | Unit 2C - Replacing Unloaders | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 71.034 |  | Sta 71: Unit 2C - Replacing Unloaders --3/27/23 through 8/4/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-307764 |  | 2023-03-27 | 2023-08-04 |  |  |  | Sta 71 | 100 | 1 | Unit 3C - Replacing Unloaders | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 71.035 |  | Sta 71: Unit 3C - Replacing Unloaders --3/27/23 through 8/4/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-307781 |  | 2023-03-27 | 2023-08-04 |  |  |  | Sta 71 | 100 | 1 | Unit 4C - Replacing Unloaders | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 71.036 |  | Sta 71: Unit 4C - Replacing Unloaders --3/27/23 through 8/4/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-514109 |  | 2023-06-12 | 2023-06-22 |  |  |  | MLV 79-2D to MLV 80-2 | 100 | 1 | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 79.2 |  | MLV 79-2D to MLV 80-2: Anomaly Remediation --6/12/23 through 6/22/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-514110 |  | 2023-07-17 | 2023-08-13 |  |  |  | MLV 79-2D to MLV 80-2 | 100 | 1 | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 79.2 |  | MLV 79-2D to MLV 80-2: Anomaly Remediation --7/17/23 through 8/13/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-514112 |  | 2023-08-14 | 2023-08-20 |  |  |  | MLV 80-2 to MLV 81-2 | 100 | 1 | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 80.2 |  | MLV 80-2 to MLV 81-2: Anomaly Remediation --8/14/23 through 8/20/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-514113 |  | 2023-08-21 | 2023-08-27 |  |  |  | MLV 81-2 to MLV 82-2 | 100 | 1 | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 81.2 |  | MLV 81-2 to MLV 82-2: Anomaly Remediation --8/21/23 through 8/27/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-157610 |  | 2023-06-08 | 2023-06-23 |  |  |  | MLV 82-1C to MLV 83-1 | 100 | 1 | Wrinkle Bend Replacement | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 82.1 |  | MLV 82-1C to MLV 83-1: Wrinkle Bend Replacement --6/8/23 through 6/23/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-411449 | *** | 2023-04-24 | 2023-06-02 | Completed |  |  | MLV 82-2 to MLV 87-2 | 100 | 1 | Anomaly Remediation | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 82.2 | ------ | ***MLV 82-2 to MLV 87-2: Anomaly Remediation ***Completed
X23-579422 | *** | 2023-06-06 | 2023-06-09 | Added |  |  | MLV 82-4C to MLV 83-4 | 100 | 1 | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 82.4 | ------ | ***MLV 82-4C to MLV 83-4: Anomaly Remediation --6/6/23 through 6/9/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ***Added ………………………………
X23-157611 |  | 2023-06-26 | 2023-08-22 |  |  |  | MLV 83-1A to MLV 84-1 | 100 | 1 | Wrinkle Bend Replacement | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 83.1 |  | MLV 83-1A to MLV 84-1: Wrinkle Bend Replacement --6/26/23 through 8/22/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-579414 | *** | 2023-06-09 | 2023-06-19 | Added |  |  | MLV 83-4 to MLV 83-4B | 100 | 1 | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 83.4 | ------ | ***MLV 83-4 to MLV 83-4B: Anomaly Remediation --6/9/23 through 6/19/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ***Added ………………………………
X23-579416 | *** | 2023-06-20 | 2023-06-22 | Added |  |  | MLV 83-4B to MLV 84-4 | 100 | 1 | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 83.45 | ------ | ***MLV 83-4B to MLV 84-4: Anomaly Remediation --6/20/23 through 6/22/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ***Added ………………………………
X23-157612 |  | 2023-08-23 | 2023-09-18 |  |  |  | MLV 84-1 to MLV 86-1 | 100 | 1 | Wrinkle Bend Replacement | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 84.1 |  | MLV 84-1 to MLV 86-1: Wrinkle Bend Replacement --8/23/23 through 9/18/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-579419 | *** | 2023-06-23 | 2023-06-26 | Added |  |  | MLV 84-4 to MLV 85-4 | 100 | 1 | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 84.4 | ------ | ***MLV 84-4 to MLV 85-4: Anomaly Remediation --6/23/23 through 6/26/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ***Added ………………………………
X23-579421 | *** | 2023-06-27 | 2023-06-30 | Added |  |  | MLV 85-4 to MLV 86-4 | 100 | 1 | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 85.4 | ------ | ***MLV 85-4 to MLV 86-4: Anomaly Remediation --6/27/23 through 6/30/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ***Added ………………………………
X23-62072 |  | 2023-08-08 | 2023-08-08 |  |  |  | Sta 87 Portland | 100 | 2 | Annual ESD Test | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 87 |  | Sta 87 Portland: Annual ESD Test --8/8/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-62061 |  | 2023-08-01 | 2023-08-31 |  |  |  | Sta 87 | 100 | 2 | Unt 5C - Regrout | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 87.037 |  | Sta 87: Unt 5C - Regrout --8/1/23 through 8/31/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-118199 | *** | 2023-06-06 | 2023-06-10 | Project Change | 2023-06-05 | 2023-06-09 | Sta 87 | 100 | 2 | Bldg E - Jacket Water System Maintenance | This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SIP | Potential in the path restrictions may be at risk. |  | 87.049 | --start_date--end_date------------model_loc-- | ***Sta 87: Bldg E - Jacket Water System Maintenance --6/6/23 through 6/10/23: This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential in the path restrictions may be at risk. *** Date Change, Previously scheduled 6/5/23 to 6/9/23. ………………………………
X23-62070 |  | 2023-07-17 | 2023-07-17 |  |  |  | Sta 87 | 100 | 2 | Bldg D Relief Valves Replacement | This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 87.049 |  | Sta 87: Bldg D Relief Valves Replacement --7/17/23: This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-62059 |  | 2023-07-24 | 2023-07-29 |  |  |  | Sta 87 | 100 | 2 | Building E Scrubber Filter Replacement | This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SIP | Potential in the path restrictions may be at risk. |  | 87.065 |  | Sta 87: Building E Scrubber Filter Replacement --7/24/23 through 7/29/23: This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential in the path restrictions may be at risk. ………………………………
X23-326849 | *** | 2023-06-01 | 2023-06-01 | Completed |  |  | MLV 82-1C to MLV 87-1S | 100 | 1 | Pig Run - MFL-A 6/01 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 87.15 | ------ | ***MLV 82-1C to MLV 87-1S: Pig Run - MFL-A 6/01 ***Completed
X23-327135 |  | 2023-07-18 | 2023-07-18 |  |  |  | MLV 87-3S to MLV 82-3C | 100 | 1 | Pig Run - Cleanng / Gauge 7/18 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 87.3 |  | MLV 87-3S to MLV 82-3C: Pig Run - Cleanng / Gauge 7/18 --7/18/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-327071 |  | 2023-07-19 | 2023-07-19 |  |  |  | MLV 87-3S to MLV 82-3C | 100 | 1 | Pig Run - Caliper 7/19 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 87.31 |  | MLV 87-3S to MLV 82-3C: Pig Run - Caliper 7/19 --7/19/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-327165 |  | 2023-07-21 | 2023-07-21 |  |  |  | MLV 87-3S to MLV 82-3C | 100 | 1 | Pig Run - MFL-A 7/21 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 87.32 |  | MLV 87-3S to MLV 82-3C: Pig Run - MFL-A 7/21 --7/21/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-327214 |  | 2023-07-24 | 2023-07-24 |  |  |  | MLV 87-3S to MLV 82-3C | 100 | 1 | Pig Run - Hard Spot 7/24 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 87.33 |  | MLV 87-3S to MLV 82-3C: Pig Run - Hard Spot 7/24 --7/24/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-326917 | *** | 2023-06-26 | 2023-06-26 | Project Change | 2023-06-15 | 2023-06-15 | MLV 87-4S to MLV 82-4C | 100 | 1 | Pig Run - Cleaning / Gauge 6/26 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 87.4 | --start_date--end_date------mantenance_desc------model_loc-- | ***MLV 87-4S to MLV 82-4C: Pig Run - Cleaning / Gauge 6/26 --6/26/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. *** Date Change, Previously scheduled 6/15/23. ………………………………
X23-326994 | *** | 2023-06-28 | 2023-06-28 | Project Change | 2023-06-27 | 2023-06-27 | MLV 87-4S to MLV 82-4C | 100 | 1 | Pig Run - MFL-C 6/27 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 87.41 | --start_date--end_date------------model_loc-- | ***MLV 87-4S to MLV 82-4C: Pig Run - MFL-C 6/27 --6/28/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. *** Date Change, Previously scheduled 6/27/23. ………………………………
X23-327036 | *** | 2023-06-30 | 2023-06-30 | Project Change | 2023-06-29 | 2023-06-29 | MLV 87-4S to MLV 82-4C | 100 | 1 | Pig Run - EMAT 6/29 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 87.42 | --start_date--end_date------------model_loc-- | ***MLV 87-4S to MLV 82-4C: Pig Run - EMAT 6/29 --6/30/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. *** Date Change, Previously scheduled 6/29/23. ………………………………
X23-513980 |  | 2023-08-15 | 2023-08-18 |  |  |  | MLV 90-3 to MLV 91-3 | 100 | 2 | Pipe Replacement | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 90.3 |  | MLV 90-3 to MLV 91-3: Pipe Replacement --8/15/23 through 8/18/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-513981 |  | 2023-09-19 | 2023-10-03 |  |  |  | MLV 93-3 to MLV 94-3 | 100 | 2 | Pipe Replacement | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 93.3 |  | MLV 93-3 to MLV 94-3: Pipe Replacement --9/19/23 through 10/3/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-170333 |  | 2023-07-13 | 2023-07-14 |  |  |  | Sta 96 | 100 | 2 | Annual ESD Test | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 96 |  | Sta 96: Annual ESD Test --7/13/23 through 7/14/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-170342 |  | 2023-07-10 | 2023-07-12 |  |  |  | Sta 96 | 100 | 2 | Annual Electric Sub Station Inspection | This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 96.0001 |  | Sta 96: Annual Electric Sub Station Inspection --7/10/23 through 7/12/23: This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-173590 |  | 2023-08-14 | 2023-08-17 |  |  |  | Sta 96 | 100 | 2 | Building D Safety System Upgrade | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 96.049 |  | Sta 96: Building D Safety System Upgrade --8/14/23 through 8/17/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-173585 |  | 2023-08-18 | 2023-09-02 |  |  |  | Sta 96 | 100 | 2 | Unit 1D - Automation Upgrade | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 96.0491 |  | Sta 96: Unit 1D - Automation Upgrade --8/18/23 through 9/2/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-173586 |  | 2023-09-04 | 2023-09-16 |  |  |  | Sta 96 | 100 | 2 | Unit 2D - Automation Upgrade | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 96.0492 |  | Sta 96: Unit 2D - Automation Upgrade --9/4/23 through 9/16/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-60663 |  | 2023-07-06 | 2023-07-06 |  |  |  | MLV 96-1S to MLV 87-1D | 100 | 2 | Pig Runs - Cleaning/Gauge 7/6 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 96.1 |  | MLV 96-1S to MLV 87-1D: Pig Runs - Cleaning/Gauge 7/6 --7/6/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-60665 |  | 2023-07-11 | 2023-07-11 |  |  |  | MLV 96-1S to MLV 87-1D | 100 | 2 | Pig Runs - MFL-C 7/11 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 96.11 |  | MLV 96-1S to MLV 87-1D: Pig Runs - MFL-C 7/11 --7/11/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-60666 |  | 2023-07-13 | 2023-07-13 |  |  |  | MLV 96-1S to MLV 87-1D | 100 | 2 | Pig Runs - EMAT 7/13 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 96.12 |  | MLV 96-1S to MLV 87-1D: Pig Runs - EMAT 7/13 --7/13/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-40681 | *** | 2023-01-10 | 2023-06-02 | Completed |  |  | MLV 96-3D to MLV 106-3S | 100 | 2 | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SIP | Potential in the path restrictions may be at risk. |  | 96.3 | ------ | ***MLV 96-3D to MLV 106-3S: Anomaly Remediation ***Completed
X23-57461 |  | 2023-08-01 | 2023-08-01 |  |  |  | MLV 96-4S to 87-4D | 100 | 2 | Pig Runs - Cleaning / Gauge 8/1 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 96.4 |  | MLV 96-4S to 87-4D: Pig Runs - Cleaning / Gauge 8/1 --8/1/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-57464 |  | 2023-08-03 | 2023-08-03 |  |  |  | MLV 96-4S to 87-4D | 100 | 2 | Pig Runs - MFL Combo 8/3 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 96.41 |  | MLV 96-4S to 87-4D: Pig Runs - MFL Combo 8/3 --8/3/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-57466 |  | 2023-08-08 | 2023-08-08 |  |  |  | MLV 96-4S to 87-4D | 100 | 2 | Pig Runs - Hard Spot 8/8 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 96.42 |  | MLV 96-4S to 87-4D: Pig Runs - Hard Spot 8/8 --8/8/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X22-991294 |  | 2023-07-01 | 2023-09-30 |  |  |  | MLV 100-1A to MLV 102-1A | 100 | 2 | Pipe Replacement | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 100.1 |  | MLV 100-1A to MLV 102-1A: Pipe Replacement --7/1/23 through 9/30/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-374760 |  | 2023-08-07 | 2023-08-14 |  |  |  | MLV 100-2 to MLV 101-2 | 100 | 2 | Install Two 26" Tees | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 100.2 |  | MLV 100-2 to MLV 101-2: Install Two 26" Tees --8/7/23 through 8/14/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-517656 |  | 2023-08-22 | 2023-09-05 |  |  |  | MLV 100-3 to MLV 101-3 | 100 | 2 | Class Change and Pipe Replacement | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 100.3 |  | MLV 100-3 to MLV 101-3: Class Change and Pipe Replacement --8/22/23 through 9/5/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-374778 |  | 2023-08-15 | 2023-08-25 |  |  |  | MLV 101-2 to MLV 102-2 | 100 | 2 | Install Two 26" Tees | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 101.2 |  | MLV 101-2 to MLV 102-2: Install Two 26" Tees --8/15/23 through 8/25/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-149083 | *** | 2023-04-28 | 2023-06-02 | Completed |  |  | MLV 105-3 to MLV 106-3 | 100 | 2 | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 105.3 | ------ | ***MLV 105-3 to MLV 106-3: Anomaly Remediation ***Completed
X23-411440 | *** | 2023-05-08 | 2023-06-09 | Project Change |  | 2023-06-02 | Sta 106 | 100 | 2 | Bldg B - Coalescing Filter Replacement | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 106.017 | ----end_date------------model_loc-- | ***Sta 106: Bldg B - Coalescing Filter Replacement --5/8/23 through 6/9/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. *** Date Change, Previously scheduled 5/8/23 to 6/2/23. ………………………………
X23-41305 | *** | 2023-01-16 | 2023-07-31 | Project Change |  | 2023-05-31 | Sta 106 | 100 | 2 | Unit 1B - Manifold Maintenance | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SIP | Potential in the path restrictions may be at risk. |  | 106.0175 | ----end_date------------model_loc-- | ***Sta 106: Unit 1B - Manifold Maintenance --1/16/23 through 7/31/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential in the path restrictions may be at risk. *** Date Change, Previously scheduled 1/16/23 to 5/31/23. ………………………………
X23-41254 |  | 2023-08-28 | 2023-08-30 |  |  |  | Sta 106 | 100 | 2 | Unit 1D - 8k Hr Inspection | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SIP | Potential in the path restrictions may be at risk. |  | 106.049 |  | Sta 106: Unit 1D - 8k Hr Inspection --8/28/23 through 8/30/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential in the path restrictions may be at risk. ………………………………
X23-41223 |  | 2023-07-10 | 2023-07-13 |  |  |  | Sta 106 | 100 | 2 | Unit 2D - 4k Hr Inspection | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SIP | Potential in the path restrictions may be at risk. |  | 106.05 |  | Sta 106: Unit 2D - 4k Hr Inspection --7/10/23 through 7/13/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential in the path restrictions may be at risk. ………………………………
X23-41266 |  | 2023-11-27 | 2023-11-29 |  |  |  | Sta 106 | 100 | 2 | Unit 2D - 8k Hr Inspection | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SIP | Potential in the path restrictions may be at risk. |  | 106.05 |  | Sta 106: Unit 2D - 8k Hr Inspection --11/27/23 through 11/29/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential in the path restrictions may be at risk. ………………………………
X23-390948 |  | 2023-04-17 | 2024-07-01 |  |  |  | MLV 106-3D to MLV 107-3 | 100 | 2 | Class Change | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 106.3 |  | MLV 106-3D to MLV 107-3: Class Change --4/17/23 through 7/1/24: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-354397 |  | 2023-08-27 | 2023-09-05 |  |  |  | MLV 876-1 to 107-5 | 100 | 2 | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 106.5 |  | MLV 876-1 to 107-5: Anomaly Remediation --8/27/23 through 9/5/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X22-954549 | *** | 2023-05-31 | 2023-06-07 | Completed |  |  | MLV 106-7 to MLV 107-7 | 100 | 2 | New Meter Tap (Mtr: Rumpke Biogas PIN 55963) | This project will require reducing pressure, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 106.7 | ------ | ***MLV 106-7 to MLV 107-7: New Meter Tap (Mtr: Rumpke Biogas PIN 55963) ***Completed
X23-74364 |  | 2023-10-17 | 2023-10-18 |  |  |  | Sta 107A North Means | 100 | 2 | Annual ESD Test | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 107 |  | Sta 107A North Means: Annual ESD Test --10/17/23 through 10/18/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-354401 |  | 2023-08-17 | 2023-08-26 |  |  |  | MLV 107-5 to 109-5 | 100 | 2 | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 107.5 |  | MLV 107-5 to 109-5: Anomaly Remediation --8/17/23 through 8/26/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-354406 | *** | 2023-06-12 | 2023-07-17 | Project Change |  | 2023-07-14 | MLV 108-3 to MLV 109-3 | 100 | 2 | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 108.3 | ----end_date------------model_loc-- | ***MLV 108-3 to MLV 109-3: Anomaly Remediation --6/12/23 through 7/17/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. *** Date Change, Previously scheduled 6/12/23 to 7/14/23. ………………………………
X23-354407 | *** | 2023-06-12 | 2023-07-17 | Project Change |  | 2023-07-14 | MLV 109-3 to MLV 110-3 | 100 | 2 | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 109.3 | ----end_date------------model_loc-- | ***MLV 109-3 to MLV 110-3: Anomaly Remediation --6/12/23 through 7/17/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. *** Date Change, Previously scheduled 6/12/23 to 7/14/23. ………………………………
X23-517655 |  | 2023-08-22 | 2023-08-29 |  |  |  | MLV 109-4 to MLV 110-4 | 100 | 2 | Class Change and Pipe Replacement | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 109.4 |  | MLV 109-4 to MLV 110-4: Class Change and Pipe Replacement --8/22/23 through 8/29/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-354404 |  | 2023-08-07 | 2023-08-16 |  |  |  | MLV 109-5 to 110-5 | 100 | 2 | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 109.5 |  | MLV 109-5 to 110-5: Anomaly Remediation --8/7/23 through 8/16/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-120777 |  | 2023-07-10 | 2023-07-14 |  |  |  | Sta 110 | 100 | 2 | Annual ESD Test & Substation Inspection | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 110 |  | Sta 110: Annual ESD Test & Substation Inspection --7/10/23 through 7/14/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-282697 | *** | 2023-05-29 | 2023-06-02 | Completed |  |  | Sta 110 | 100 | 2 | Unit 9A - Motor Maintenance | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 110.009 | ------ | ***Sta 110: Unit 9A - Motor Maintenance ***Completed
X23-514138 |  | 2023-09-12 | 2023-09-12 |  |  |  | MLV 111-3B to MLV 114-3S | 100 | 2 | Pig Run - Cleaning / Gauge 9/12 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 111.3 |  | MLV 111-3B to MLV 114-3S: Pig Run - Cleaning / Gauge 9/12 --9/12/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-514140 |  | 2023-09-14 | 2023-09-14 |  |  |  | MLV 111-3B to MLV 114-3S | 100 | 2 | Pig Run - MDS 9/14 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 111.31 |  | MLV 111-3B to MLV 114-3S: Pig Run - MDS 9/14 --9/14/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-542839 |  | 2023-06-05 | 2023-06-08 |  |  |  | Sta 114 | 100 | 3 | Unit 1C - Engine Inspection | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 114.033 |  | Sta 114: Unit 1C - Engine Inspection --6/5/23 through 6/8/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-57448 | *** | 2023-06-01 | 2023-06-01 | Completed |  |  | MLV 114-3S to MLV 111-3B | 100 | 2 | Pig Runs - Cleaning / Gauge 6/1 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 114.3 | ------ | ***MLV 114-3S to MLV 111-3B: Pig Runs - Cleaning / Gauge 6/1 ***Completed
X23-374735 |  | 2023-07-10 | 2023-07-23 |  |  |  | MLV 114-3A to MLV 115-3 | 100 | 3 | Drip Replacement | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 114.3 |  | MLV 114-3A to MLV 115-3: Drip Replacement --7/10/23 through 7/23/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-57450 |  | 2023-06-13 | 2023-06-13 |  |  |  | MLV 114-3S to MLV 111-3B | 100 | 2 | Pig Runs - MFL Combo 6/13 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 114.31 |  | MLV 114-3S to MLV 111-3B: Pig Runs - MFL Combo 6/13 --6/13/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-354279 |  | 2023-07-24 | 2023-08-07 |  |  |  | MLV 115-2 to 116-2 | 100 | 3 | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 115.2 |  | MLV 115-2 to 116-2: Anomaly Remediation --7/24/23 through 8/7/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-579311 | *** | 2023-07-27 | 2023-07-28 | Added |  |  | Sta 118A | 100 | 3 | Annual ESD Test | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 118 | ------ | ***Sta 118A: Annual ESD Test --7/27/23 through 7/28/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ***Added ………………………………
X22-55542 | *** | 2023-07-24 | 2023-07-26 | Project Change | 2023-06-05 | 2023-06-07 | Sta 118A | 100 | 3 | Solar 8k Inspection | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SIP | Potential in the path restrictions may be at risk. |  | 118.0015 | --start_date--end_date------------model_loc-- | ***Sta 118A: Solar 8k Inspection --7/24/23 through 7/26/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential in the path restrictions may be at risk. *** Date Change, Previously scheduled 6/5/23 to 6/7/23. ………………………………
X23-38751 |  | 2023-06-20 | 2023-06-20 |  |  |  | MLV 118-3 to MLV 114-3D | 100 | 3 | Pig Run - CLP / IMU / MFL-A 6/20 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | PIP | Potential in the path restrictions may be at risk. |  | 118.31 |  | MLV 118-3 to MLV 114-3D: Pig Run - CLP / IMU / MFL-A 6/20 --6/20/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential in the path restrictions may be at risk. ………………………………
X23-38752 |  | 2023-06-22 | 2023-06-22 |  |  |  | MLV 118-3 to MLV 114-3D | 100 | 3 | Pig Run - Hardspot 6/22 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | PIP | Potential in the path restrictions may be at risk. |  | 118.32 |  | MLV 118-3 to MLV 114-3D: Pig Run - Hardspot 6/22 --6/22/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential in the path restrictions may be at risk. ………………………………
X23-32117 |  | 2023-06-12 | 2023-06-16 |  |  |  | Sta 119A | 100 | 3 | Annual ESD Test | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 119 |  | Sta 119A: Annual ESD Test --6/12/23 through 6/16/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-32116 |  | 2023-06-12 | 2023-06-16 |  |  |  | Sta 119A | 100 | 3 | Unit 1A - Turbine 8k Inspection | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 119.001 |  | Sta 119A: Unit 1A - Turbine 8k Inspection --6/12/23 through 6/16/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-377293 |  | 2023-08-01 | 2023-08-31 |  |  |  | MLV 120-1 & MLV 121-1 | 100 | 3 | Installing Actuators & Communications | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 120.1 |  | MLV 120-1 & MLV 121-1: Installing Actuators & Communications --8/1/23 through 8/31/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-118153 |  | 2023-06-12 | 2023-06-15 |  |  |  | Sta 200 | 200 | 4 | Annual ESD Test | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 200 |  | Sta 200: Annual ESD Test --6/12/23 through 6/15/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-581367 | *** | 2023-06-09 | 2023-06-15 | Added |  |  | Sta 200 | 200 | 4 | Unit 4A - Operator on Unit Valve | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 200.004 | ------ | ***Sta 200: Unit 4A - Operator on Unit Valve --6/9/23 through 6/15/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ***Added ………………………………
X23-520604 |  | 2023-06-26 | 2023-06-29 |  |  |  | Sta 200 | 200 | 4 | Unit 11A - Compressor Bolts & Turbo Replacement | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 200.011 |  | Sta 200: Unit 11A - Compressor Bolts & Turbo Replacement --6/26/23 through 6/29/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-520598 |  | 2023-06-05 | 2023-06-09 |  |  |  | MLV 200-1S to MLV 106-3D | 100 | 2 | Pressure Restriction for Pig Operations | This activity will require operating at controlled flow rates and at a reduced pressure. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 200.1 |  | MLV 200-1S to MLV 106-3D: Pressure Restriction for Pig Operations --6/5/23 through 6/9/23: This activity will require operating at controlled flow rates and at a reduced pressure. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-57445 | *** | 2023-06-06 | 2023-06-06 | Completed |  |  | MLV 200-1S to MLV 106-3D | 100 | 2 | Pig Runs - Cleaning / Gauge 6/6 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 200.1 | ------ | ***MLV 200-1S to MLV 106-3D: Pig Runs - Cleaning / Gauge 6/6 ***Completed
X23-57447 |  | 2023-06-08 | 2023-06-08 |  |  |  | MLV 200-1S to MLV 106-3D | 100 | 2 | Pig Runs - MFL Combo 6/8 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 200.11 |  | MLV 200-1S to MLV 106-3D: Pig Runs - MFL Combo 6/8 --6/8/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-327254 |  | 2023-08-08 | 2023-08-08 |  |  |  | MLV 200-2S to MLV 106-4D | 100 | 2 | Pig Run - Cleaning / Gauge 8/8 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 200.2 |  | MLV 200-2S to MLV 106-4D: Pig Run - Cleaning / Gauge 8/8 --8/8/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-327348 |  | 2023-08-10 | 2023-08-10 |  |  |  | MLV 200-2S to MLV 106-4D | 100 | 2 | Pig Run - Caliper 8/10 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 200.21 |  | MLV 200-2S to MLV 106-4D: Pig Run - Caliper 8/10 --8/10/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-327395 |  | 2023-08-14 | 2023-08-14 |  |  |  | MLV 200-2S to MLV 106-4D | 100 | 2 | Pig Run - MFL-A 8/14 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 200.22 |  | MLV 200-2S to MLV 106-4D: Pig Run - MFL-A 8/14 --8/14/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-327428 |  | 2023-08-16 | 2023-08-16 |  |  |  | MLV 200-2S to MLV 106-4D | 100 | 2 | Pig Run - Hard Spot 8/16 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 200.23 |  | MLV 200-2S to MLV 106-4D: Pig Run - Hard Spot 8/16 --8/16/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-514080 | *** | 2023-06-12 | 2023-06-23 | Project Change | 2023-07-10 | 2023-07-28 | MLV 202-1 to MLV 203-1 | 200 | 4 | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 202.1 | --start_date--end_date------------model_loc-- | ***MLV 202-1 to MLV 203-1: Anomaly Remediation --6/12/23 through 6/23/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. *** Date Change, Previously scheduled 7/10/23 to 7/28/23. ………………………………
X23-71229 |  | 2023-04-17 | 2023-09-01 |  |  |  | Sta 204 | 200 | 4 | Unit 2A - Foundation Replacement | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 204.002 |  | Sta 204: Unit 2A - Foundation Replacement --4/17/23 through 9/1/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-113784 | *** | 2023-05-08 | 2023-06-29 | Project Change |  | 2023-06-08 | Sta 204 | 200 | 4 | Unit 9A - Compressor Boring | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 204.009 | ----end_date------------model_loc-- | ***Sta 204: Unit 9A - Compressor Boring --5/8/23 through 6/29/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. *** Date Change, Previously scheduled 5/8/23 to 6/8/23. ………………………………
X23-479687 | *** | 2023-07-17 | 2023-07-20 | Project Change | 2023-06-26 | 2023-06-29 | Sta 204 | 200 | 4 | Unit 10A - Anchor Bolt Inspections | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 204.01 | --start_date--end_date------------model_loc-- | ***Sta 204: Unit 10A - Anchor Bolt Inspections --7/17/23 through 7/20/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. *** Date Change, Previously scheduled 6/26/23 to 6/29/23. ………………………………
X23-520518 | *** | 2023-07-10 | 2023-07-13 | Project Change | 2023-06-12 | 2023-06-15 | Sta 204 | 200 | 4 | Unit 11A - Engine Inspections | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 204.011 | --start_date--end_date------------model_loc-- | ***Sta 204: Unit 11A - Engine Inspections --7/10/23 through 7/13/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. *** Date Change, Previously scheduled 6/12/23 to 6/15/23. ………………………………
X23-445142 |  | 2023-07-10 | 2023-07-13 |  |  |  | Sta 209 | 200 | 4 | Unit 5A - Crankcase Inspection | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 205.005 |  | Sta 209: Unit 5A - Crankcase Inspection --7/10/23 through 7/13/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-517642 |  | 2023-09-12 | 2023-09-19 |  |  |  | MLV 206-3 to MLV 207-3 | 200 | 4 | Landslide Midigation with Pipe Replacement | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 206.3 |  | MLV 206-3 to MLV 207-3: Landslide Midigation with Pipe Replacement --9/12/23 through 9/19/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-517650 |  | 2023-08-15 | 2023-09-30 |  |  |  | MLV 206-4 to MLV 207-4 | 200 | 4 | Landslide Midigation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 206.4 |  | MLV 206-4 to MLV 207-4: Landslide Midigation --8/15/23 through 9/30/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-581336 | *** | 2023-06-12 | 2023-06-15 | Added |  |  | Sta 209 | 200 | 4 | Unit 6A - Replace FW & OP Turbos | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 209.006 | ------ | ***Sta 209: Unit 6A - Replace FW & OP Turbos --6/12/23 through 6/15/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ***Added ………………………………
X23-517482 |  | 2023-06-26 | 2023-06-29 |  |  |  | Sta 209 | 200 | 4 | Unit 7A - Crankcase Inspection | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 209.007 |  | Sta 209: Unit 7A - Crankcase Inspection --6/26/23 through 6/29/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-581338 | *** | 2023-07-17 | 2023-07-20 | Added |  |  | Sta 209 | 200 | 4 | Unit 8A - Crankcase Inspection | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 209.008 | ------ | ***Sta 209: Unit 8A - Crankcase Inspection --7/17/23 through 7/20/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ***Added ………………………………
X23-445145 |  | 2023-06-12 | 2023-06-14 |  |  |  | Sta 209 | 200 | 4 | Unit 11A - Install New Fuel Header | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 209.011 |  | Sta 209: Unit 11A - Install New Fuel Header --6/12/23 through 6/14/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-445144 | *** | 2023-06-07 | 2023-06-09 | Completed |  |  | Sta 209 | 200 | 4 | Unit 12A - Install New Fuel Header | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 209.012 | ------ | ***Sta 209: Unit 12A - Install New Fuel Header ***Completed
X23-445143 | *** | 2023-06-05 | 2023-06-07 | Completed |  |  | Sta 209 | 200 | 4 | Unit 13A - Install New Fuel Header | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 209.013 | ------ | ***Sta 209: Unit 13A - Install New Fuel Header ***Completed
X23-374739 |  | 2023-08-01 | 2023-08-31 |  |  |  | MLV 210-3 to MLV 211-3 | 200 | 4 | Class Change | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 210.3 |  | MLV 210-3 to MLV 211-3: Class Change --8/1/23 through 8/31/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-374737 |  | 2023-09-01 | 2023-09-30 |  |  |  | MLV 213-3A to MLV 214-3 | 200 | 4 | Class Change | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 213.3 |  | MLV 213-3A to MLV 214-3: Class Change --9/1/23 through 9/30/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-170318 | *** | 2023-07-10 | 2023-07-14 | Project Change | 2023-06-26 | 2023-06-30 | Sta 214 | 200 | 4 | Annual ESD Test & Maintenance | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 214 | --start_date--end_date------------model_loc-- | ***Sta 214: Annual ESD Test & Maintenance --7/10/23 through 7/14/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. *** Date Change, Previously scheduled 6/26/23 to 6/30/23. ………………………………
X23-581369 | *** | 2023-06-12 | 2023-06-16 | Added |  |  | MLV 214-1 to MLV 215-1 | 200 | 4 | High Priority Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 214.1 | ------ | ***MLV 214-1 to MLV 215-1: High Priority Anomaly Remediation --6/12/23 through 6/16/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ***Added ………………………………
X23-581373 | *** | 2023-06-19 | 2023-06-30 | Added |  |  | MLV 216-1 to MLV 217-1 | 200 | 4 | High Priority Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 216.1 | ------ | ***MLV 216-1 to MLV 217-1: High Priority Anomaly Remediation --6/19/23 through 6/30/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ***Added ………………………………
X23-374738 |  | 2023-10-01 | 2023-10-31 |  |  |  | MLV 216-2 to MLV 217-2 | 200 | 4 | Class Change | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 216.2 |  | MLV 216-2 to MLV 217-2: Class Change --10/1/23 through 10/31/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-581374 | *** | 2023-07-10 | 2023-07-14 | Added |  |  | MLV 217-1 to MLV 218-1 | 200 | 4 | High Priority Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 217.1 | ------ | ***MLV 217-1 to MLV 218-1: High Priority Anomaly Remediation --7/10/23 through 7/14/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ***Added ………………………………
X23-581375 | *** | 2023-07-17 | 2023-07-21 | Added |  |  | MLV 218-1 to MLV 219-1 | 200 | 4 | High Priority Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 218.1 | ------ | ***MLV 218-1 to MLV 219-1: High Priority Anomaly Remediation --7/17/23 through 7/21/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ***Added ………………………………
X23-513985 | *** | 2023-05-29 | 2023-06-01 | Completed |  |  | Sta 219 | 200 | 4 | Unit 7A - Crankcase and Anchor Bolt Inspection | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 219.007 | ------ | ***Sta 219: Unit 7A - Crankcase and Anchor Bolt Inspection ***Completed
X23-581368 | *** | 2023-06-19 | 2023-06-23 | Added |  |  | Sta 219 | 200 | 4 | Unit 1B - Annual Protective Device Testing | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 219.017 | ------ | ***Sta 219: Unit 1B - Annual Protective Device Testing --6/19/23 through 6/23/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ***Added ………………………………
X23-328612 |  | 2023-08-29 | 2023-08-30 |  |  |  | Station 224 | 200 | 5 | Scrubber Inspections & Filter Change | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 224 |  | Station 224: Scrubber Inspections & Filter Change --8/29/23 through 8/30/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-263269 |  | 2023-07-11 | 2023-07-13 |  |  |  | Station 230C | 200 | 4 | Annual ESD | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. The meters listed may be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 410902 TRANSCAN/TGP UDP NIAGARA RIVER NIAG 421079 TRANSCAN/TGP UDP NIAGARA RIVER DELI | 230 |  | Station 230C: Annual ESD --7/11/23 through 7/13/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. The meters listed may be shut in during the project. Potential out of path restrictions may be at risk. 410902 TRANSCAN/TGP UDP NIAGARA RIVER NIAG 421079 TRANSCAN/TGP UDP NIAGARA RIVER DELI ………………………………
X23-328616 |  | 2023-09-12 | 2023-09-13 |  |  |  | Station 230C | 200 | 5 | Scrubber / Filter Inspection | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. The meters listed may be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 410902 TRANSCAN/TGP UDP NIAGARA RIVER NIAG 421079 TRANSCAN/TGP UDP NIAGARA RIVER DELI | 230 |  | Station 230C: Scrubber / Filter Inspection --9/12/23 through 9/13/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. The meters listed may be shut in during the project. Potential out of path restrictions may be at risk. 410902 TRANSCAN/TGP UDP NIAGARA RIVER NIAG 421079 TRANSCAN/TGP UDP NIAGARA RIVER DELI ………………………………
X23-74189 |  | 2023-06-05 | 2023-06-09 |  |  |  | Sta 230C | 200 | 5 | Unit 3A - Turbine Exchange | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 230.003 |  | Sta 230C: Unit 3A - Turbine Exchange --6/5/23 through 6/9/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-276135 |  | 2023-07-25 | 2023-07-25 |  |  |  | Sta 233 | 200 | 4 | Annual ESD Test | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 233 |  | Sta 233: Annual ESD Test --7/25/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-276140 |  | 2023-07-25 | 2023-07-26 |  |  |  | Sta 233 | 200 | 4 | Scrubber Filter Inspecton A-1 | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 233.001 |  | Sta 233: Scrubber Filter Inspecton A-1 --7/25/23 through 7/26/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-276136 |  | 2023-07-27 | 2023-07-27 |  |  |  | Sta 233 | 200 | 4 | Point to Point and Trans Cals | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 233.001 |  | Sta 233: Point to Point and Trans Cals --7/27/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-276214 |  | 2023-08-08 | 2023-08-08 |  |  |  | Station 237 | 200 | 5 | Annual ESD Test | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 237 |  | Station 237: Annual ESD Test --8/8/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-276225 |  | 2023-09-26 | 2023-09-26 |  |  |  | Sta 237 | 200 | 5 | 400 Line Filter/Scrubber Change | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 237 |  | Sta 237: 400 Line Filter/Scrubber Change --9/26/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-276230 |  | 2023-09-27 | 2023-09-27 |  |  |  | Sta 237 | 200 | 5 | Scrubber Inspection Filter Change | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 237 |  | Sta 237: Scrubber Inspection Filter Change --9/27/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-276217 |  | 2023-08-09 | 2023-08-09 |  |  |  | Sta 237 | 200 | 5 | Point to Point and Trans Cals | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 237.001 |  | Sta 237: Point to Point and Trans Cals --8/9/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-517666 | *** | 2023-05-30 | 2023-06-01 | Completed |  |  | Sta 237 | 200 | 5 | Unit 3A - Compressor Rod Packing | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 237.003 | ------ | ***Sta 237: Unit 3A - Compressor Rod Packing ***Completed
X23-276132 |  | 2023-06-20 | 2023-06-20 |  |  |  | Station 237 | 200 | 4 | Unit 3A - Device Tests | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 237.003 |  | Station 237: Unit 3A - Device Tests --6/20/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-59426 |  | 2023-09-19 | 2023-09-19 |  |  |  | MLV 237-1 TO MLV 245-1 | 200 | 5 | Pig Runs - Cleaning/Gauge 9/19 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 237.1 |  | MLV 237-1 TO MLV 245-1: Pig Runs - Cleaning/Gauge 9/19 --9/19/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-59427 |  | 2023-09-21 | 2023-09-21 |  |  |  | MLV 237-1 TO MLV 245-1 | 200 | 5 | Pig Runs - EMAT 9/21 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 237.11 |  | MLV 237-1 TO MLV 245-1: Pig Runs - EMAT 9/21 --9/21/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-276141 |  | 2023-06-13 | 2023-06-13 |  |  |  | Sta 241 | 200 | 5 | Annual ESD Test | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 241 |  | Sta 241: Annual ESD Test --6/13/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-276146 | *** | 2023-06-15 | 2023-06-15 | Project Change | 2023-06-14 | 2023-06-14 | Sta 241 | 200 | 5 | Point to Point and Trans Cals | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 241.001 | --start_date--end_date------------model_loc-- | ***Sta 241: Point to Point and Trans Cals --6/15/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. *** Date Change, Previously scheduled 6/14/23. ………………………………
X23-517669 |  | 2023-07-17 | 2023-07-20 |  |  |  | Sta 241 | 200 | 5 | Unit 1A - Crankcase Inspection | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 241.001 |  | Sta 241: Unit 1A - Crankcase Inspection --7/17/23 through 7/20/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-276156 |  | 2023-08-21 | 2023-08-21 |  |  |  | Sta 241 | 200 | 5 | Unit 1A Device Tests & Relief VLV | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 241.001 |  | Sta 241: Unit 1A Device Tests & Relief VLV --8/21/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-517670 |  | 2023-07-10 | 2023-07-13 |  |  |  | Sta 241 | 200 | 5 | Unit 2A - Crankcase Inspection | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 241.002 |  | Sta 241: Unit 2A - Crankcase Inspection --7/10/23 through 7/13/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-276188 |  | 2023-08-22 | 2023-08-22 |  |  |  | Sta 241 | 200 | 5 | Unit 2A Device Tests & Relief VLV | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 241.002 |  | Sta 241: Unit 2A Device Tests & Relief VLV --8/22/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-276150 |  | 2023-07-05 | 2023-07-06 |  |  |  | Sta 241 | 200 | 5 | Unit 3A Device Tests & Relief VLV | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 241.003 |  | Sta 241: Unit 3A Device Tests & Relief VLV --7/5/23 through 7/6/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-276208 |  | 2023-08-23 | 2023-08-23 |  |  |  | Sta 241 | 200 | 5 | Unit 1B Device Tests & Relief VLV | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 241.017 |  | Sta 241: Unit 1B Device Tests & Relief VLV --8/23/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-276239 |  | 2023-10-10 | 2023-10-11 |  |  |  | Sta 241 | 200 | 5 | Unit 1B 2K Maintenance | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 241.0171 |  | Sta 241: Unit 1B 2K Maintenance --10/10/23 through 10/11/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-276210 |  | 2023-08-24 | 2023-08-24 |  |  |  | Sta 241 | 200 | 5 | Unit 2B Device Tests & Relief VLV | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 241.018 |  | Sta 241: Unit 2B Device Tests & Relief VLV --8/24/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-276245 |  | 2023-10-11 | 2023-10-12 |  |  |  | Sta 241 | 200 | 5 | Unit 2B 2K Maintenance | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 241.0181 |  | Sta 241: Unit 2B 2K Maintenance --10/11/23 through 10/12/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-59605 |  | 2023-07-24 | 2023-07-29 |  |  |  | MLV 244-2 to MLV 245-2 | 200 | 5 | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 244.2 |  | MLV 244-2 to MLV 245-2: Anomaly Remediation --7/24/23 through 7/29/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X22-866252 |  | 2022-08-30 | 2023-10-31 |  |  |  | Sta 245 | 200 | 5 | Unit 7A - Turbo Charger Replacement | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 245.007 |  | Sta 245: Unit 7A - Turbo Charger Replacement --8/30/22 through 10/31/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-59582 |  | 2023-06-12 | 2023-06-17 |  |  |  | MLV 249-1 to MLV 250-1 | 200 | 6 | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 249.1 |  | MLV 249-1 to MLV 250-1: Anomaly Remediation --6/12/23 through 6/17/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-568970 | *** | 2023-06-05 | 2023-06-09 | Completed |  |  | MLV 253-1 to MLV 254-1 | 200 | 5 | Anomaly Remediation Emergent Repair | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 253.1 | ------ | ***MLV 253-1 to MLV 254-1: Anomaly Remediation Emergent Repair ***Completed
X23-59584 |  | 2023-06-12 | 2023-06-17 |  |  |  | MLV 253-1 to MLV 254-1 | 200 | 6 | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 253.1 |  | MLV 253-1 to MLV 254-1: Anomaly Remediation --6/12/23 through 6/17/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-248857 |  | 2023-09-26 | 2023-09-26 |  |  |  | MLV 254-1 to MLV 261-1 | 200 | 6 | Pig Runs - Cleaning & Gauge: 9/26 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 254.13 |  | MLV 254-1 to MLV 261-1: Pig Runs - Cleaning & Gauge: 9/26 --9/26/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-59416 |  | 2023-09-28 | 2023-09-28 |  |  |  | MLV 254-1 to MLV 261-1 | 200 | 6 | Pig Runs - EMAT: 9/28 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 254.13 |  | MLV 254-1 to MLV 261-1: Pig Runs - EMAT: 9/28 --9/28/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-59496 |  | 2023-06-20 | 2023-06-20 |  |  |  | MLV 260A-101.1 TO MLV 260A-103 | 200 | 6 | Pig Runs - Cleaning/Gauge: 6/20 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed may be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 420104 WESTFLD/TGP WESTFIELD MA HAMPDEN 420401 HOLYOKE/TGP HOLYOKE MA 2 HAMPDEN | 260.11 |  | MLV 260A-101.1 TO MLV 260A-103: Pig Runs - Cleaning/Gauge: 6/20 --6/20/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed may be shut in during the project. Potential out of path restrictions may be at risk. 420104 WESTFLD/TGP WESTFIELD MA HAMPDEN 420401 HOLYOKE/TGP HOLYOKE MA 2 HAMPDEN ………………………………
X23-59500 |  | 2023-06-20 | 2023-06-20 |  |  |  | MLV 260A-101.1 TO MLV 260A-103 | 200 | 6 | Pig Runs - MFL-A/Cal/IMU 6/20 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed may be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 420104 WESTFLD/TGP WESTFIELD MA HAMPDEN 420401 HOLYOKE/TGP HOLYOKE MA 2 HAMPDEN | 260.12 |  | MLV 260A-101.1 TO MLV 260A-103: Pig Runs - MFL-A/Cal/IMU 6/20 --6/20/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed may be shut in during the project. Potential out of path restrictions may be at risk. 420104 WESTFLD/TGP WESTFIELD MA HAMPDEN 420401 HOLYOKE/TGP HOLYOKE MA 2 HAMPDEN ………………………………
X23-526678 | *** | 2023-06-05 | 2023-06-05 | Completed |  |  | Sta 261 | 200 | 6 | Unit 5A - Water Wash | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 261.005 | ------ | ***Sta 261: Unit 5A - Water Wash ***Completed
X23-526682 | *** | 2023-06-06 | 2023-06-06 | Completed |  |  | Sta 261 | 200 | 6 | Unit 2D - Water Wash | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 261.05 | ------ | ***Sta 261: Unit 2D - Water Wash ***Completed
X23-59574 |  | 2023-07-05 | 2023-07-15 |  |  |  | MLV 261-1 to MLV 262-1 | 200 | 6 | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 261.1 |  | MLV 261-1 to MLV 262-1: Anomaly Remediation --7/5/23 through 7/15/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-59423 |  | 2023-06-12 | 2023-06-12 |  |  |  | MLV 261-2 TO MLV 267-2 | 200 | 6 | Pig Runs - Cleaning/Gauge 6/12 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 261.2 |  | MLV 261-2 TO MLV 267-2: Pig Runs - Cleaning/Gauge 6/12 --6/12/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-59424 |  | 2023-06-13 | 2023-06-13 |  |  |  | MLV 261-2 TO MLV 267-2 | 200 | 6 | Pig Runs - Cal/IMU 6/13 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 261.21 |  | MLV 261-2 TO MLV 267-2: Pig Runs - Cal/IMU 6/13 --6/13/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-59425 |  | 2023-06-15 | 2023-06-15 |  |  |  | MLV 261-2 TO MLV 267-2 | 200 | 6 | Pig Runs - MFL-A 6/15 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 261.22 |  | MLV 261-2 TO MLV 267-2: Pig Runs - MFL-A 6/15 --6/15/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-59576 | *** | 2023-05-08 | 2023-06-10 | Completed |  |  | MLV 262-1 to MLV 263-1 | 200 | 6 | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 262.1 | ------ | ***MLV 262-1 to MLV 263-1: Anomaly Remediation ***Completed
X23-59577 |  | 2023-06-19 | 2023-06-24 |  |  |  | MLV 264-1 to MLV 265-1 | 200 | 6 | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 264.1 |  | MLV 264-1 to MLV 265-1: Anomaly Remediation --6/19/23 through 6/24/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-248933 |  | 2023-10-07 | 2023-10-14 |  |  |  | Sta 265E | 200 | 6 | Unit 1A - Turbine Exchange | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. | 420707 OCEAN ST/TGP PROVIDENCE 420758 NARNGST/TGP LINCOLN SMS PROVIDENCE 420910 NARNGST/TGP SMITHFIELD DELIVERY PR 420926 RISEC/TGP FPLE RISE PROVIDENCE 420750 NARNGST/TGP CRANSTON SALES PROVIDEN | 265 |  | Sta 265E: Unit 1A - Turbine Exchange --10/7/23 through 10/14/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. 420707 OCEAN ST/TGP PROVIDENCE 420758 NARNGST/TGP LINCOLN SMS PROVIDENCE 420910 NARNGST/TGP SMITHFIELD DELIVERY PR 420926 RISEC/TGP FPLE RISE PROVIDENCE 420750 NARNGST/TGP CRANSTON SALES PROVIDEN ………………………………
X23-59494 | *** | 2023-06-06 | 2023-06-06 | Completed |  |  | MLV 265C-101.1 TO MLV 265C-102A | 200 | 6 | Pig Runs - Cleaning/Gauge 6/6 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meter listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 420109 NSTAR/TGP WORCHESTER MA WORCHESTER | 265.1 | ------ | ***MLV 265C-101.1 TO MLV 265C-102A: Pig Runs - Cleaning/Gauge 6/6 ***Completed The following meters are available for nominations: 420109 NSTAR/TGP WORCHESTER MA WORCHESTER
X23-59579 |  | 2023-06-26 | 2023-07-01 |  |  |  | MLV 265-1 to MLV 266-1 | 200 | 6 | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 265.1 |  | MLV 265-1 to MLV 266-1: Anomaly Remediation --6/26/23 through 7/1/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X22-573251 | *** | 2023-08-04 | 2023-08-08 | Project Change | 2023-05-31 | 2023-06-02 | MLV 265E-104 | 200 | 6 | Hot Tap for New Meter Station - Anaergia Biogas (Pin: 55784 Receipt / 55785 Delivery) | This project may require reducing the pipeline section pressure. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 265.1 | --start_date--end_date------------model_loc-- | ***MLV 265E-104: Hot Tap for New Meter Station - Anaergia Biogas (Pin: 55784 Receipt / 55785 Delivery) --8/4/23 through 8/8/23: This project may require reducing the pipeline section pressure. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. *** Date Change, Previously scheduled 5/31/23 to 6/2/23. ………………………………
X23-59495 | *** | 2023-06-07 | 2023-06-07 | Completed |  |  | MLV 265C-101.1 TO MLV 265C-102A | 200 | 6 | Pig Runs - MFL-A/Cal/IMU 6/7 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meter listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 420109 NSTAR/TGP WORCHESTER MA WORCHESTER | 265.11 | ------ | ***MLV 265C-101.1 TO MLV 265C-102A: Pig Runs - MFL-A/Cal/IMU 6/7 ***Completed The following meters are available for nominations: 420109 NSTAR/TGP WORCHESTER MA WORCHESTER
X23-248869 |  | 2023-07-31 | 2023-08-12 |  |  |  | MLVS 265E-200 | 200 | 6 | ECDA | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 265.2 |  | MLVS 265E-200: ECDA --7/31/23 through 8/12/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-428547 |  | 2023-06-05 | 2023-06-08 |  |  |  | Sta 266 | 200 | 6 | Unit 1B - 4K inspection & Protective Device | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. | 420285 AGT/TGP MENDON MASS TIE OVER | 266.017 |  | Sta 266: Unit 1B - 4K inspection & Protective Device --6/5/23 through 6/8/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. 420285 AGT/TGP MENDON MASS TIE OVER ………………………………
X23-59592 |  | 2023-07-17 | 2023-07-22 |  |  |  | MLV 270B-101.1 to MLV 270B-102 | 200 | 6 | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 270.1 |  | MLV 270B-101.1 to MLV 270B-102: Anomaly Remediation --7/17/23 through 7/22/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-59596 |  | 2023-07-24 | 2023-07-29 |  |  |  | MLV 270B-302 to MLV 270B-302BR | 200 | 6 | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 270.3 |  | MLV 270B-302 to MLV 270B-302BR: Anomaly Remediation --7/24/23 through 7/29/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-59591 |  | 2023-05-22 | 2023-06-17 |  |  |  | MLV 270C-401 to MLV 270C-402 | 200 | 6 | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meter listed may be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 420117 BOSTN/TGP LYNN MA ESSEX | 270.4 |  | MLV 270C-401 to MLV 270C-402: Anomaly Remediation --5/22/23 through 6/17/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meter listed may be shut in during the project. Potential out of path restrictions may be at risk. 420117 BOSTN/TGP LYNN MA ESSEX ………………………………
X23-59586 |  | 2023-06-19 | 2023-07-22 |  |  |  | MLV 270C-501 to MLV 270C-502 | 200 | 6 | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed may be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 420323 BOSTN/TGP ESSEX MA ESSEX 420119 BOSTN/TGP GLOUCHESTER MA ESSEX | 270.5 |  | MLV 270C-501 to MLV 270C-502: Anomaly Remediation --6/19/23 through 7/22/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed may be shut in during the project. Potential out of path restrictions may be at risk. 420323 BOSTN/TGP ESSEX MA ESSEX 420119 BOSTN/TGP GLOUCHESTER MA ESSEX ………………………………
X23-135863 |  | 2023-07-10 | 2023-07-24 |  |  |  | Sta 307 | 300 | 4 | BPS/Auxillary Automation Upgrade | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 307 |  | Sta 307: BPS/Auxillary Automation Upgrade --7/10/23 through 7/24/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-513983 | *** | 2023-06-12 | 2023-06-15 | Project Change | 2023-05-29 | 2023-06-01 | Sta 307 | 300 | 4 | Unit 1A - Crankcase Inspection | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 307.001 | --start_date--end_date------------model_loc-- | ***Sta 307: Unit 1A - Crankcase Inspection --6/12/23 through 6/15/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. *** Date Change, Previously scheduled 5/29/23 to 6/1/23. ………………………………
X23-513986 |  | 2023-06-05 | 2023-06-08 |  |  |  | Sta 307 | 300 | 4 | Unit 3A - Crankcase and Compressor Inspection | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 307.003 |  | Sta 307: Unit 3A - Crankcase and Compressor Inspection --6/5/23 through 6/8/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-173500 |  | 2023-06-27 | 2023-06-27 |  |  |  | Station 310 Smethport | 300 | 4 | Annual ESD Test | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 310 |  | Station 310 Smethport: Annual ESD Test --6/27/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-411388 | *** | 2023-06-01 | 2023-06-02 | Completed |  |  | Sta 310 | 300 | 4 | Unit 1A - Water Wash & Inspection | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 310.001 | ------ | ***Sta 310: Unit 1A - Water Wash & Inspection ***Completed
X23-173507 |  | 2023-09-05 | 2023-09-06 |  |  |  | Sta 313 Coudersport | 300 | 4 | Annual ESD Test | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 313 |  | Sta 313 Coudersport: Annual ESD Test --9/5/23 through 9/6/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-248870 | *** | 2023-07-05 | 2023-07-22 | Project Change | 2023-06-05 | 2023-06-17 | MLVS 333A-100 | 300 | 6 | ECDA | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 313.1 | --start_date--end_date------------model_loc-- | ***MLVS 333A-100: ECDA --7/5/23 through 7/22/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. *** Date Change, Previously scheduled 6/5/23 to 6/17/23. ………………………………
X23-276220 |  | 2023-09-19 | 2023-09-19 |  |  |  | Sta 313 to Sta 237 | 300 | 4 | Maintenance Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 313.5 |  | Sta 313 to Sta 237: Maintenance Pig --9/19/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-40829 |  | 2023-06-14 | 2023-06-14 |  |  |  | MLVS 313G-100 | 300 | 4 | Pig run - MFL 6/14 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meter listed will be shut in for the duration of the project. | SOP | Potential out of path restrictions may be at risk. | 420527 NFG/TGP ROSE LAKE POTTER | 313.54 |  | MLVS 313G-100: Pig run - MFL 6/14 --6/14/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meter listed will be shut in for the duration of the project. Potential out of path restrictions may be at risk. 420527 NFG/TGP ROSE LAKE POTTER ………………………………
X23-40843 |  | 2023-08-21 | 2023-09-08 |  |  |  | MLVS C313-0605 | 300 | 4 | Pig Runs (Tethered) - Cleaning 8/29 | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed will be shut in for the duration of the project. | SOP | Potential out of path restrictions may be at risk. | 400485 HEBRON STORAGE INJECTION POTTER 470001 HEBRON STORAGE WITHDRAWAL POTTER | 313.8 |  | MLVS C313-0605: Pig Runs (Tethered) - Cleaning 8/29 --8/21/23 through 9/8/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed will be shut in for the duration of the project. Potential out of path restrictions may be at risk. 400485 HEBRON STORAGE INJECTION POTTER 470001 HEBRON STORAGE WITHDRAWAL POTTER ………………………………
X23-40844 |  | 2023-08-21 | 2023-09-08 |  |  |  | MLVS C313-0605 | 300 | 4 | Pig Runs (Tethered) - MFL 8/31 | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed will be shut in for the duration of the project. | SOP | Potential out of path restrictions may be at risk. | 400485 HEBRON STORAGE INJECTION POTTER 470001 HEBRON STORAGE WITHDRAWAL POTTER | 313.81 |  | MLVS C313-0605: Pig Runs (Tethered) - MFL 8/31 --8/21/23 through 9/8/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed will be shut in for the duration of the project. Potential out of path restrictions may be at risk. 400485 HEBRON STORAGE INJECTION POTTER 470001 HEBRON STORAGE WITHDRAWAL POTTER ………………………………
X23-40839 |  | 2023-08-21 | 2023-09-08 |  |  |  | MLVS C313-0606 | 300 | 4 | Pig Runs (Tethered) - Cleaning / Gauge 8/29 | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed will be shut in for the duration of the project. | SOP | Potential out of path restrictions may be at risk. | 400485 HEBRON STORAGE INJECTION POTTER 470001 HEBRON STORAGE WITHDRAWAL POTTER | 313.85 |  | MLVS C313-0606: Pig Runs (Tethered) - Cleaning / Gauge 8/29 --8/21/23 through 9/8/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed will be shut in for the duration of the project. Potential out of path restrictions may be at risk. 400485 HEBRON STORAGE INJECTION POTTER 470001 HEBRON STORAGE WITHDRAWAL POTTER ………………………………
X23-40841 |  | 2023-08-21 | 2023-09-08 |  |  |  | MLVS C313-0606 | 300 | 4 | Pig Runs (Tethered) - MFL 8/30 | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed will be shut in for the duration of the project. | SOP | Potential out of path restrictions may be at risk. | 400485 HEBRON STORAGE INJECTION POTTER 470001 HEBRON STORAGE WITHDRAWAL POTTER | 313.86 |  | MLVS C313-0606: Pig Runs (Tethered) - MFL 8/30 --8/21/23 through 9/8/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed will be shut in for the duration of the project. Potential out of path restrictions may be at risk. 400485 HEBRON STORAGE INJECTION POTTER 470001 HEBRON STORAGE WITHDRAWAL POTTER ………………………………
X23-173509 |  | 2023-07-18 | 2023-07-19 |  |  |  | Sta 315 Wellsboro | 300 | 4 | Annual ESD Test | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 315 |  | Sta 315 Wellsboro: Annual ESD Test --7/18/23 through 7/19/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-526540 |  | 2023-06-14 | 2023-06-14 |  |  |  | Sta 317 | 300 | 4 | Unit 1C - Compressor Seal Flush | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 317.033 |  | Sta 317: Unit 1C - Compressor Seal Flush --6/14/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-40833 |  | 2023-06-20 | 2023-06-20 |  |  |  | MLV 317-1 to MLV 313-1 | 300 | 4 | Pig run - Cleaning 6/20 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in for the duration of the project. | SOP | Potential out of path restrictions may be at risk. | 412858 DIV PROD/TGP MASON DEHY: RIP 315F 1 412781 NFG/TGP HOLLOW ROAD DEHY: RIP 315B 412797 NFG/TGP UDP RICHMOND DEHY:RIP 315E 420213 UGI/TGP MANSFIELD PA TIOGA 412822 MAINESBG/TGP UDP HEMLOCK HILL II DE 412811 NFG/TGP MAINESBURG DEHY: RIP 316G T 412791 REPSOLOG/TGP MOUNTAIN RIDGE DEHY: 412827 REPSOLOG/TGP PUTNAM DEHYD: RIP 316H 412796 UGITX/TGP SWEENEY DEHY: RIP 316E 10 412770 REPSOLOG/TGP SHEDDEN DEHY: RIP 316D 412818 REPSOLOG/TGP SHEDDEN II DEHY: RIP 3 | 317.1 |  | MLV 317-1 to MLV 313-1: Pig run - Cleaning 6/20 --6/20/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in for the duration of the project. Potential out of path restrictions may be at risk. 412858 DIV PROD/TGP MASON DEHY: RIP 315F 1 412781 NFG/TGP HOLLOW ROAD DEHY: RIP 315B 412797 NFG/TGP UDP RICHMOND DEHY:RIP 315E 420213 UGI/TGP MANSFIELD PA TIOGA 412822 MAINESBG/TGP UDP HEMLOCK HILL II DE 412811 NFG/TGP MAINESBURG DEHY: RIP 316G T 412791 REPSOLOG/TGP MOUNTAIN RIDGE DEHY: 412827 REPSOLOG/TGP PUTNAM DEHYD: RIP 316H 412796 UGITX/TGP SWEENEY DEHY: RIP 316E 10 412770 REPSOLOG/TGP SHEDDEN DEHY: RIP 316D 412818 REPSOLOG/TGP SHEDDEN II DEHY: RIP 3 ………………………………
X23-40834 |  | 2023-06-22 | 2023-06-22 |  |  |  | MLV 317-1 to MLV 313-1 | 300 | 4 | Pig run - MFL 6/22 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in for the duration of the project. | SOP | Potential out of path restrictions may be at risk. | 412858 DIV PROD/TGP MASON DEHY: RIP 315F 1 412781 NFG/TGP HOLLOW ROAD DEHY: RIP 315B 412797 NFG/TGP UDP RICHMOND DEHY:RIP 315E 420213 UGI/TGP MANSFIELD PA TIOGA 412822 MAINESBG/TGP UDP HEMLOCK HILL II DE 412811 NFG/TGP MAINESBURG DEHY: RIP 316G T 412791 REPSOLOG/TGP MOUNTAIN RIDGE DEHY: 412827 REPSOLOG/TGP PUTNAM DEHYD: RIP 316H 412796 UGITX/TGP SWEENEY DEHY: RIP 316E 10 412770 REPSOLOG/TGP SHEDDEN DEHY: RIP 316D 412818 REPSOLOG/TGP SHEDDEN II DEHY: RIP 3 | 317.11 |  | MLV 317-1 to MLV 313-1: Pig run - MFL 6/22 --6/22/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in for the duration of the project. Potential out of path restrictions may be at risk. 412858 DIV PROD/TGP MASON DEHY: RIP 315F 1 412781 NFG/TGP HOLLOW ROAD DEHY: RIP 315B 412797 NFG/TGP UDP RICHMOND DEHY:RIP 315E 420213 UGI/TGP MANSFIELD PA TIOGA 412822 MAINESBG/TGP UDP HEMLOCK HILL II DE 412811 NFG/TGP MAINESBURG DEHY: RIP 316G T 412791 REPSOLOG/TGP MOUNTAIN RIDGE DEHY: 412827 REPSOLOG/TGP PUTNAM DEHYD: RIP 316H 412796 UGITX/TGP SWEENEY DEHY: RIP 316E 10 412770 REPSOLOG/TGP SHEDDEN DEHY: RIP 316D 412818 REPSOLOG/TGP SHEDDEN II DEHY: RIP 3 ………………………………
X23-40836 |  | 2023-07-11 | 2023-07-11 |  |  |  | MLV 317-2 to MLV 315-2 | 300 | 4 | Pig run - Cleaning 7/11 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 317.2 |  | MLV 317-2 to MLV 315-2: Pig run - Cleaning 7/11 --7/11/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-40838 |  | 2023-07-13 | 2023-07-13 |  |  |  | MLV 317-2 to MLV 315-2 | 300 | 4 | Pig run - MFL 7/13 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 317.21 |  | MLV 317-2 to MLV 315-2: Pig run - MFL 7/13 --7/13/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-40830 | *** | 2023-06-06 | 2023-06-06 | Completed |  |  | MLV 319-1 to MLV 317-1 | 300 | 4 | Pig run - Cleaning 6/6 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in for the duration of the project. | SOP | Potential out of path restrictions may be at risk. | 412834 APPLACHA/TGP UDP CALKINS DEHY: RIP 412785 BLCKHILL/TGP SWAIN ROAD DEHY: RIP 3 420652 LSTOCKNG/TGP WYALUSING SALES BRADFO | 319.1 | ------ | ***MLV 319-1 to MLV 317-1: Pig run - Cleaning 6/6 ***Completed The following meters are available for nominations: 412834 APPLACHA/TGP UDP CALKINS DEHY: RIP 412785 BLCKHILL/TGP SWAIN ROAD DEHY: RIP 3 420652 LSTOCKNG/TGP WYALUSING SALES BRADFO
X23-40832 |  | 2023-06-08 | 2023-06-08 |  |  |  | MLV 319-1 to MLV 317-1 | 300 | 4 | Pig run - MFL 6/8 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in for the duration of the project. | SOP | Potential out of path restrictions may be at risk. | 412834 APPLACHA/TGP UDP CALKINS DEHY: RIP 412785 BLCKHILL/TGP SWAIN ROAD DEHY: RIP 3 420652 LSTOCKNG/TGP WYALUSING SALES BRADFO | 319.11 |  | MLV 319-1 to MLV 317-1: Pig run - MFL 6/8 --6/8/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in for the duration of the project. Potential out of path restrictions may be at risk. 412834 APPLACHA/TGP UDP CALKINS DEHY: RIP 412785 BLCKHILL/TGP SWAIN ROAD DEHY: RIP 3 420652 LSTOCKNG/TGP WYALUSING SALES BRADFO ………………………………
X22-804509 |  | 2023-07-18 | 2023-08-18 |  |  |  | Sta 321 | 300 | 4 | Turbo Compressor Tie-In | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 321 |  | Sta 321: Turbo Compressor Tie-In --7/18/23 through 8/18/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-461564 |  | 2023-09-04 | 2023-09-10 |  |  |  | Sta 321 | 300 | 5 | Electrical Tie-In | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 321.001 |  | Sta 321: Electrical Tie-In --9/4/23 through 9/10/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-40817 |  | 2023-08-22 | 2023-08-22 |  |  |  | MLV 321-1 to MLV 325-1 | 300 | 5 | Pig run - Cleaning 8/22 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 321.1 |  | MLV 321-1 to MLV 325-1: Pig run - Cleaning 8/22 --8/22/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-40819 |  | 2023-08-24 | 2023-08-24 |  |  |  | MLV 321-1 to MLV 325-1 | 300 | 5 | Pig run - MFL 8/24 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 321.11 |  | MLV 321-1 to MLV 325-1: Pig run - MFL 8/24 --8/24/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X22-485078 |  | 2023-09-05 | 2023-09-09 |  |  |  | MLV 324-1A to MLV 326-1 | 300 | 5 | Install New Sta 325 Unit | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed may be shut in during the project. | SOP | Potential out of path restrictions may be at risk. |  | 324.1 |  | MLV 324-1A to MLV 326-1: Install New Sta 325 Unit --9/5/23 through 9/9/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed may be shut in during the project. Potential out of path restrictions may be at risk. ………………………………
X23-396969 |  | 2023-09-05 | 2023-09-27 |  |  |  | Sta 325 | 300 | 5 | Install New Unit | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 325 |  | Sta 325: Install New Unit --9/5/23 through 9/27/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X22-485076 |  | 2023-09-06 | 2023-09-13 |  |  |  | MLV 327-1A to MLV 328-1 | 300 | 5 | Install New Sta 327 | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed may be shut in during the project. | SOP | Potential out of path restrictions may be at risk. |  | 327.1 |  | MLV 327-1A to MLV 328-1: Install New Sta 327 --9/6/23 through 9/13/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed may be shut in during the project. Potential out of path restrictions may be at risk. ………………………………
X22-485077 |  | 2023-09-15 | 2023-09-22 |  |  |  | MLV 327-2A to MLV 328-2 | 300 | 5 | Install New Sta 327 | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 327.2 |  | MLV 327-2A to MLV 328-2: Install New Sta 327 --9/15/23 through 9/22/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-248873 |  | 2023-08-28 | 2023-09-16 |  |  |  | MLVS 340A-100 | 300 | 6 | ECDA | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 340.1 |  | MLVS 340A-100: ECDA --8/28/23 through 9/16/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-248878 | *** | 2023-06-12 | 2023-07-01 | Project Change | 2023-06-19 | 2023-07-08 | MLVS 343A-100 | 300 | 6 | ECDA | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 343.1 | --start_date--end_date------------model_loc-- | ***MLVS 343A-100: ECDA --6/12/23 through 7/1/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. *** Date Change, Previously scheduled 6/19/23 to 7/8/23. ………………………………
X23-248880 |  | 2023-08-14 | 2023-08-26 |  |  |  | MLVS 345A-100 | 300 | 6 | ECDA | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 345.1 |  | MLVS 345A-100: ECDA --8/14/23 through 8/26/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-108324 |  | 2023-09-19 | 2023-09-19 |  |  |  | MLV 400-1 to MLV 409-1 | 400 | 0 | Pig Run - Cleaning 9/19 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 411884 ENRONCTR/TGP MAGNOLIA PLANT PTR MAK 440236 MAGNOLIA CITY PLANT FUEL NUECES 440279 VAR/TGP MAGNOLIA CITY PLANT FLARE N 410736 VAR/TGP PETRONELLA DEHY NUECES 016347 / 420837 TGP/TGP FALFURRIAS BROOKS 412733 UES/TGP MYRICK BROOKS | 400.1 |  | MLV 400-1 to MLV 409-1: Pig Run - Cleaning 9/19 --9/19/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 411884 ENRONCTR/TGP MAGNOLIA PLANT PTR MAK 440236 MAGNOLIA CITY PLANT FUEL NUECES 440279 VAR/TGP MAGNOLIA CITY PLANT FLARE N 410736 VAR/TGP PETRONELLA DEHY NUECES 016347 / 420837 TGP/TGP FALFURRIAS BROOKS 412733 UES/TGP MYRICK BROOKS ………………………………
X23-108455 |  | 2023-09-21 | 2023-09-21 |  |  |  | MLV 400-1 to MLV 409-1 | 400 | 0 | Pig Run - Cleaning 9/21 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 411884 ENRONCTR/TGP MAGNOLIA PLANT PTR MAK 440236 MAGNOLIA CITY PLANT FUEL NUECES 440279 VAR/TGP MAGNOLIA CITY PLANT FLARE N 410736 VAR/TGP PETRONELLA DEHY NUECES 016347 / 420837 TGP/TGP FALFURRIAS BROOKS 412733 UES/TGP MYRICK BROOKS | 400.11 |  | MLV 400-1 to MLV 409-1: Pig Run - Cleaning 9/21 --9/21/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 411884 ENRONCTR/TGP MAGNOLIA PLANT PTR MAK 440236 MAGNOLIA CITY PLANT FUEL NUECES 440279 VAR/TGP MAGNOLIA CITY PLANT FLARE N 410736 VAR/TGP PETRONELLA DEHY NUECES 016347 / 420837 TGP/TGP FALFURRIAS BROOKS 412733 UES/TGP MYRICK BROOKS ………………………………
X23-108500 |  | 2023-09-23 | 2023-09-23 |  |  |  | MLV 400-1 to MLV 409-1 | 400 | 0 | Pig Run - Cleaning 9/23 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 411884 ENRONCTR/TGP MAGNOLIA PLANT PTR MAK 440236 MAGNOLIA CITY PLANT FUEL NUECES 440279 VAR/TGP MAGNOLIA CITY PLANT FLARE N 410736 VAR/TGP PETRONELLA DEHY NUECES 016347 / 420837 TGP/TGP FALFURRIAS BROOKS 412733 UES/TGP MYRICK BROOKS | 400.12 |  | MLV 400-1 to MLV 409-1: Pig Run - Cleaning 9/23 --9/23/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 411884 ENRONCTR/TGP MAGNOLIA PLANT PTR MAK 440236 MAGNOLIA CITY PLANT FUEL NUECES 440279 VAR/TGP MAGNOLIA CITY PLANT FLARE N 410736 VAR/TGP PETRONELLA DEHY NUECES 016347 / 420837 TGP/TGP FALFURRIAS BROOKS 412733 UES/TGP MYRICK BROOKS ………………………………
X23-108538 |  | 2023-09-25 | 2023-09-25 |  |  |  | MLV 400-1 to MLV 409-1 | 400 | 0 | Pig Run - Gauge 9/25 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 411884 ENRONCTR/TGP MAGNOLIA PLANT PTR MAK 440236 MAGNOLIA CITY PLANT FUEL NUECES 440279 VAR/TGP MAGNOLIA CITY PLANT FLARE N 410736 VAR/TGP PETRONELLA DEHY NUECES 016347 / 420837 TGP/TGP FALFURRIAS BROOKS 412733 UES/TGP MYRICK BROOKS | 400.13 |  | MLV 400-1 to MLV 409-1: Pig Run - Gauge 9/25 --9/25/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 411884 ENRONCTR/TGP MAGNOLIA PLANT PTR MAK 440236 MAGNOLIA CITY PLANT FUEL NUECES 440279 VAR/TGP MAGNOLIA CITY PLANT FLARE N 410736 VAR/TGP PETRONELLA DEHY NUECES 016347 / 420837 TGP/TGP FALFURRIAS BROOKS 412733 UES/TGP MYRICK BROOKS ………………………………
X23-108570 |  | 2023-09-27 | 2023-09-27 |  |  |  | MLV 400-1 to MLV 409-1 | 400 | 0 | Pig Run - CLP/MFL/IMU 9/27 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 411884 ENRONCTR/TGP MAGNOLIA PLANT PTR MAK 440236 MAGNOLIA CITY PLANT FUEL NUECES 440279 VAR/TGP MAGNOLIA CITY PLANT FLARE N 410736 VAR/TGP PETRONELLA DEHY NUECES 016347 / 420837 TGP/TGP FALFURRIAS BROOKS 412733 UES/TGP MYRICK BROOKS | 400.14 |  | MLV 400-1 to MLV 409-1: Pig Run - CLP/MFL/IMU 9/27 --9/27/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 411884 ENRONCTR/TGP MAGNOLIA PLANT PTR MAK 440236 MAGNOLIA CITY PLANT FUEL NUECES 440279 VAR/TGP MAGNOLIA CITY PLANT FLARE N 410736 VAR/TGP PETRONELLA DEHY NUECES 016347 / 420837 TGP/TGP FALFURRIAS BROOKS 412733 UES/TGP MYRICK BROOKS ………………………………
X23-108660 |  | 2023-08-25 | 2023-08-25 |  |  |  | MLV 400-2 to MLV 409-2 | 400 | 0 | Pig Run - Cleaning 8/25 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 410736 VAR/TGP PETRONELLA DEHY NUECES 412197 KMTEJAS/TGP KING RANCH KLEBERG 412579 TGP/TGP SANTA FE WILDCAT BROOKS 411725 EXPORT/TGP LOS INDIOS DEHY HIDALGO 412628 SAMSON/TGP LOS INDIOS 3 HIDALGO | 400.2 |  | MLV 400-2 to MLV 409-2: Pig Run - Cleaning 8/25 --8/25/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 410736 VAR/TGP PETRONELLA DEHY NUECES 412197 KMTEJAS/TGP KING RANCH KLEBERG 412579 TGP/TGP SANTA FE WILDCAT BROOKS 411725 EXPORT/TGP LOS INDIOS DEHY HIDALGO 412628 SAMSON/TGP LOS INDIOS 3 HIDALGO ………………………………
X23-108843 |  | 2023-08-28 | 2023-08-28 |  |  |  | MLV 400-2 to MLV 409-2 | 400 | 0 | Pig Run - Cleaning 8/28 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 410736 VAR/TGP PETRONELLA DEHY NUECES 412197 KMTEJAS/TGP KING RANCH KLEBERG 412579 TGP/TGP SANTA FE WILDCAT BROOKS 411725 EXPORT/TGP LOS INDIOS DEHY HIDALGO 412628 SAMSON/TGP LOS INDIOS 3 HIDALGO | 400.21 |  | MLV 400-2 to MLV 409-2: Pig Run - Cleaning 8/28 --8/28/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 410736 VAR/TGP PETRONELLA DEHY NUECES 412197 KMTEJAS/TGP KING RANCH KLEBERG 412579 TGP/TGP SANTA FE WILDCAT BROOKS 411725 EXPORT/TGP LOS INDIOS DEHY HIDALGO 412628 SAMSON/TGP LOS INDIOS 3 HIDALGO ………………………………
X23-108894 |  | 2023-08-30 | 2023-08-30 |  |  |  | MLV 400-2 to MLV 409-2 | 400 | 0 | Pig Run - Cleaning 8/30 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 410736 VAR/TGP PETRONELLA DEHY NUECES 412197 KMTEJAS/TGP KING RANCH KLEBERG 412579 TGP/TGP SANTA FE WILDCAT BROOKS 411725 EXPORT/TGP LOS INDIOS DEHY HIDALGO 412628 SAMSON/TGP LOS INDIOS 3 HIDALGO | 400.22 |  | MLV 400-2 to MLV 409-2: Pig Run - Cleaning 8/30 --8/30/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 410736 VAR/TGP PETRONELLA DEHY NUECES 412197 KMTEJAS/TGP KING RANCH KLEBERG 412579 TGP/TGP SANTA FE WILDCAT BROOKS 411725 EXPORT/TGP LOS INDIOS DEHY HIDALGO 412628 SAMSON/TGP LOS INDIOS 3 HIDALGO ………………………………
X23-108923 |  | 2023-09-01 | 2023-09-01 |  |  |  | MLV 400-2 to MLV 409-2 | 400 | 0 | Pig Run - Gauge 9/01 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 410736 VAR/TGP PETRONELLA DEHY NUECES 412197 KMTEJAS/TGP KING RANCH KLEBERG 412579 TGP/TGP SANTA FE WILDCAT BROOKS 411725 EXPORT/TGP LOS INDIOS DEHY HIDALGO 412628 SAMSON/TGP LOS INDIOS 3 HIDALGO | 400.23 |  | MLV 400-2 to MLV 409-2: Pig Run - Gauge 9/01 --9/1/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 410736 VAR/TGP PETRONELLA DEHY NUECES 412197 KMTEJAS/TGP KING RANCH KLEBERG 412579 TGP/TGP SANTA FE WILDCAT BROOKS 411725 EXPORT/TGP LOS INDIOS DEHY HIDALGO 412628 SAMSON/TGP LOS INDIOS 3 HIDALGO ………………………………
X23-108950 |  | 2023-09-06 | 2023-09-06 |  |  |  | MLV 400-2 to MLV 409-2 | 400 | 0 | Pig Run - CLP/MFL/IMU 9/06 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 410736 VAR/TGP PETRONELLA DEHY NUECES 412197 KMTEJAS/TGP KING RANCH KLEBERG 412579 TGP/TGP SANTA FE WILDCAT BROOKS 411725 EXPORT/TGP LOS INDIOS DEHY HIDALGO 412628 SAMSON/TGP LOS INDIOS 3 HIDALGO | 400.24 |  | MLV 400-2 to MLV 409-2: Pig Run - CLP/MFL/IMU 9/06 --9/6/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 410736 VAR/TGP PETRONELLA DEHY NUECES 412197 KMTEJAS/TGP KING RANCH KLEBERG 412579 TGP/TGP SANTA FE WILDCAT BROOKS 411725 EXPORT/TGP LOS INDIOS DEHY HIDALGO 412628 SAMSON/TGP LOS INDIOS 3 HIDALGO ………………………………
X23-424018 |  | 2023-09-12 | 2023-09-12 |  |  |  | MLV 400-2 to MLV 409-2 | 100 | 0 | Pig Run - MFL-C 9/12 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 410736 VAR/TGP PETRONELLA DEHY NUECES 412197 KMTEJAS/TGP KING RANCH KLEBERG 412579 TGP/TGP SANTA FE WILDCAT BROOKS 411725 EXPORT/TGP LOS INDIOS DEHY HIDALGO 412628 SAMSON/TGP LOS INDIOS 3 HIDALGO | 400.25 |  | MLV 400-2 to MLV 409-2: Pig Run - MFL-C 9/12 --9/12/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 410736 VAR/TGP PETRONELLA DEHY NUECES 412197 KMTEJAS/TGP KING RANCH KLEBERG 412579 TGP/TGP SANTA FE WILDCAT BROOKS 411725 EXPORT/TGP LOS INDIOS DEHY HIDALGO 412628 SAMSON/TGP LOS INDIOS 3 HIDALGO ………………………………
X23-424020 |  | 2023-09-14 | 2023-09-14 |  |  |  | MLV 400-2 to MLV 409-2 | 100 | 0 | Pig Run - EMAT 9/14 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 410736 VAR/TGP PETRONELLA DEHY NUECES 412197 KMTEJAS/TGP KING RANCH KLEBERG 412579 TGP/TGP SANTA FE WILDCAT BROOKS 411725 EXPORT/TGP LOS INDIOS DEHY HIDALGO 412628 SAMSON/TGP LOS INDIOS 3 HIDALGO | 400.26 |  | MLV 400-2 to MLV 409-2: Pig Run - EMAT 9/14 --9/14/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 410736 VAR/TGP PETRONELLA DEHY NUECES 412197 KMTEJAS/TGP KING RANCH KLEBERG 412579 TGP/TGP SANTA FE WILDCAT BROOKS 411725 EXPORT/TGP LOS INDIOS DEHY HIDALGO 412628 SAMSON/TGP LOS INDIOS 3 HIDALGO ………………………………
X23-276224 |  | 2023-09-20 | 2023-09-20 |  |  |  | Sta 405A | 300 | 4 | Filter/Scrubber Change | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 405 |  | Sta 405A: Filter/Scrubber Change --9/20/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-276247 |  | 2023-10-16 | 2023-10-16 |  |  |  | Sta 405A | 200 | 5 | Unit 1A - Water Wash | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 405.0012 |  | Sta 405A: Unit 1A - Water Wash --10/16/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-276249 |  | 2023-10-17 | 2023-10-17 |  |  |  | Sta 405A | 200 | 5 | Unit 1A - 8K Solar Turbine Borescope Inspection | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 405.0013 |  | Sta 405A: Unit 1A - 8K Solar Turbine Borescope Inspection --10/17/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-428646 |  | 2023-08-15 | 2023-08-15 |  |  |  | MLV 406A-101L to MLV 406A-101.1 | 100 | 0 | Pig Run - Maintenance | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 406.1 |  | MLV 406A-101L to MLV 406A-101.1: Pig Run - Maintenance --8/15/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-71193 |  | 2023-06-22 | 2023-07-17 |  |  |  | MLV 407-1 TO MLV 408-1 | 400 | 0 | Class Change | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 407.1 |  | MLV 407-1 TO MLV 408-1: Class Change --6/22/23 through 7/17/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-71197 |  | 2023-07-18 | 2023-08-07 |  |  |  | MLV 407-2 TO MLV 408-2 | 400 | 0 | Class Change | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed may be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 411725 EXPORT/TGP LOS INDIOS DEHY HIDALGO 412628 SAMSON/TGP LOS INDIOS 3 HIDALGO | 407.2 |  | MLV 407-2 TO MLV 408-2: Class Change --7/18/23 through 8/7/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed may be shut in during the project. Potential out of path restrictions may be at risk. 411725 EXPORT/TGP LOS INDIOS DEHY HIDALGO 412628 SAMSON/TGP LOS INDIOS 3 HIDALGO ………………………………
X23-99669 | *** | 2023-05-30 | 2023-06-01 | Completed |  |  | Sta 409A | 400 | 0 | Annual ESD Test | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. The meters listed may experience pressure fluctuations. | SIP | Potential in the path restrictions may be at risk. | 450261 CENAGAS/TGP PEMEX CHECK DELIV SOUTH 450262 CENAGAS/TGP REC NORTH HIDALGO | 409 | ------ | ***Sta 409A: Annual ESD Test ***Completed The following meters are available for nominations: 450261 CENAGAS/TGP PEMEX CHECK DELIV SOUTH 450262 CENAGAS/TGP REC NORTH HIDALGO
X23-526554 |  | 2023-06-21 | 2023-06-21 |  |  |  | Sta 409 | 100 | 0 | Unit 3A - Vibration Study | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 409.003 |  | Sta 409: Unit 3A - Vibration Study --6/21/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-428658 |  | 2023-07-22 | 2023-07-22 |  |  |  | MLV 409A-901L to MLV 409A-902 | 100 | 0 | Pig Run - Maintenance | This activity will require operating at controlled flow rates which will limit throughput through the station and result in restrictions based on customer nominations. The meters listed may experience pressure fluctuations. | SOP | Potential out of path restrictions may be at risk. | 450261 CENAGAS/TGP PEMEX CHECK DELIV SOUTH 450262 CENAGAS/TGP REC NORTH HIDALGO | 409.09 |  | MLV 409A-901L to MLV 409A-902: Pig Run - Maintenance --7/22/23: This activity will require operating at controlled flow rates which will limit throughput through the station and result in restrictions based on customer nominations. The meters listed may experience pressure fluctuations. Potential out of path restrictions may be at risk. 450261 CENAGAS/TGP PEMEX CHECK DELIV SOUTH 450262 CENAGAS/TGP REC NORTH HIDALGO ………………………………
X23-428655 |  | 2023-06-22 | 2023-06-22 |  |  |  | MLV 409A-101L to MLV 409A-103R | 100 | 0 | Pig Run - Maintenance | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 409.1 |  | MLV 409A-101L to MLV 409A-103R: Pig Run - Maintenance --6/22/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-71192 |  | 2023-07-10 | 2023-09-15 |  |  |  | MLV 409-101 TO MLV 409-101B | 400 | 0 | Class Change | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 421067 CALPINE/TGP HIDALGO 412220 TXINDPT/TGP SAN SALVADOR DEHY HIDAL | 409.1 |  | MLV 409-101 TO MLV 409-101B: Class Change --7/10/23 through 9/15/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 421067 CALPINE/TGP HIDALGO 412220 TXINDPT/TGP SAN SALVADOR DEHY HIDAL ………………………………
X23-428656 |  | 2023-07-20 | 2023-07-20 |  |  |  | MLV 409A-1101L to MLV 409A-1103 | 100 | 0 | Pig Run - Maintenance | This activity will require operating at controlled flow rates which will limit throughput through the station and result in restrictions based on customer nominations. The meters listed may experience pressure fluctuations. | SOP | Potential out of path restrictions may be at risk. | 421017 GDR/TGP RIO BRAVO HIDALGO 412659 DEWBRE/TGP CIMMARRON HIDALGO | 409.11 |  | MLV 409A-1101L to MLV 409A-1103: Pig Run - Maintenance --7/20/23: This activity will require operating at controlled flow rates which will limit throughput through the station and result in restrictions based on customer nominations. The meters listed may experience pressure fluctuations. Potential out of path restrictions may be at risk. 421017 GDR/TGP RIO BRAVO HIDALGO 412659 DEWBRE/TGP CIMMARRON HIDALGO ………………………………
X23-428648 |  | 2023-06-20 | 2023-06-20 |  |  |  | MLV 409A-1200BL to MLV 409A-1202R | 100 | 0 | Pig Run - Maintenance | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 409.12 |  | MLV 409A-1200BL to MLV 409A-1202R: Pig Run - Maintenance --6/20/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-101117 |  | 2023-11-07 | 2023-11-07 |  |  |  | Sta 500-1 to Sta 823 (MLV 507-1) | 500 | 1 | Maintenance Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 420373 TRNSCO/TGP KINDER LA EXCH (BI 1 420708 ELIZ NG/TGP GRANT LA SALES ALLEN 420436 VERNON/TGP PITKIN LA VERNON 420793 ELIZ NG/TGP J R FRANKS 1 VERNON 420388 PROVNCAL/TGP PROVENCAL LA NATCHITOC | 500.11 |  | Sta 500-1 to Sta 823 (MLV 507-1): Maintenance Pig --11/7/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 420373 TRNSCO/TGP KINDER LA EXCH (BI 1 420708 ELIZ NG/TGP GRANT LA SALES ALLEN 420436 VERNON/TGP PITKIN LA VERNON 420793 ELIZ NG/TGP J R FRANKS 1 VERNON 420388 PROVNCAL/TGP PROVENCAL LA NATCHITOC ………………………………
X23-101118 |  | 2023-09-13 | 2023-09-13 |  |  |  | STA 507F to Sta 823 | 500 | L | Maintenance Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 507 |  | STA 507F to Sta 823: Maintenance Pig --9/13/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-113749 |  | 2023-07-12 | 2023-07-14 |  |  |  | MLV 507K-101 TO MLV 507K-104 | 500 | L | Pig Runs - Cleaning 7/12 to 7/14 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 412716 BRAMMER/TGP HILDA HENRY NO 1 JEFFER 412680 TRUNKLNE/TGP LACASSINE JEFFERSON DA 420493 COKINOS/TGP MALLETT FARM LA JEFFERS | 507.1 |  | MLV 507K-101 TO MLV 507K-104: Pig Runs - Cleaning 7/12 to 7/14 --7/12/23 through 7/14/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 412716 BRAMMER/TGP HILDA HENRY NO 1 JEFFER 412680 TRUNKLNE/TGP LACASSINE JEFFERSON DA 420493 COKINOS/TGP MALLETT FARM LA JEFFERS ………………………………
X23-113750 |  | 2023-07-14 | 2023-07-14 |  |  |  | MLV 507K-101 TO MLV 507K-104 | 500 | L | Pig Runs - Gauge Pig 7/14 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 412716 BRAMMER/TGP HILDA HENRY NO 1 JEFFER 412680 TRUNKLNE/TGP LACASSINE JEFFERSON DA 420493 COKINOS/TGP MALLETT FARM LA JEFFERS | 507.12 |  | MLV 507K-101 TO MLV 507K-104: Pig Runs - Gauge Pig 7/14 --7/14/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 412716 BRAMMER/TGP HILDA HENRY NO 1 JEFFER 412680 TRUNKLNE/TGP LACASSINE JEFFERSON DA 420493 COKINOS/TGP MALLETT FARM LA JEFFERS ………………………………
X23-113751 |  | 2023-07-19 | 2023-07-19 |  |  |  | MLV 507K-101 TO MLV 507K-104 | 500 | L | Pig Runs - CLP / MFL-A / IMU 7/19 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 412716 BRAMMER/TGP HILDA HENRY NO 1 JEFFER 412680 TRUNKLNE/TGP LACASSINE JEFFERSON DA 420493 COKINOS/TGP MALLETT FARM LA JEFFERS | 507.13 |  | MLV 507K-101 TO MLV 507K-104: Pig Runs - CLP / MFL-A / IMU 7/19 --7/19/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 412716 BRAMMER/TGP HILDA HENRY NO 1 JEFFER 412680 TRUNKLNE/TGP LACASSINE JEFFERSON DA 420493 COKINOS/TGP MALLETT FARM LA JEFFERS ………………………………
X23-135784 |  | 2023-10-14 | 2023-10-27 |  |  |  | MLV 510A-1 to MLV 511-1 | 500 | L | Line Lowering | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SIP | Potential in the path restrictions may be at risk. | 421056 ACADIAN/TGP INDIAN BAYOU: DIP 510B- | 510 |  | MLV 510A-1 to MLV 511-1: Line Lowering --10/14/23 through 10/27/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential in the path restrictions may be at risk. 421056 ACADIAN/TGP INDIAN BAYOU: DIP 510B- ………………………………
X23-390755 |  | 2023-10-14 | 2023-11-12 |  |  |  | MLV 511-1 to MLV 512-1 | 500 | L | Line Lowering | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 511.1 |  | MLV 511-1 to MLV 512-1: Line Lowering --10/14/23 through 11/12/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-135797 |  | 2023-10-10 | 2023-11-05 |  |  |  | MLV 512-1 to MLV 513-1 | 500 | L | Line Lowering | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed will be shut in for the duration of the project. | SIP | Potential in the path restrictions may be at risk. | 412398 JEFFSTOR/TGP JEFFERSON ISLAND IBERI 412889 CONTLRES/TGP LOPEZ ROAD VERMILION | 512 |  | MLV 512-1 to MLV 513-1: Line Lowering --10/10/23 through 11/5/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed will be shut in for the duration of the project. Potential in the path restrictions may be at risk. 412398 JEFFSTOR/TGP JEFFERSON ISLAND IBERI 412889 CONTLRES/TGP LOPEZ ROAD VERMILION ………………………………
X23-390764 |  | 2023-10-10 | 2023-11-05 |  |  |  | MLV 513-1 to MLV 514-1 | 500 | L | Line Lowering | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed will be shut in for the duration of the project. | SOP | Potential out of path restrictions may be at risk. | 420915 SYMMETRY/TGP PORT IBERIA SALES IBER 54402 SYMMETRY/TGP ADOLPH ROAD IBERIA | 513.1 |  | MLV 513-1 to MLV 514-1: Line Lowering --10/10/23 through 11/5/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed will be shut in for the duration of the project. Potential out of path restrictions may be at risk. 420915 SYMMETRY/TGP PORT IBERIA SALES IBER 54402 SYMMETRY/TGP ADOLPH ROAD IBERIA ………………………………
X23-135800 |  | 2023-10-06 | 2023-10-29 |  |  |  | MLV 514-1 to MLV 515-1 | 500 | L | Line Lowering | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SIP | Potential in the path restrictions may be at risk. |  | 514 |  | MLV 514-1 to MLV 515-1: Line Lowering --10/6/23 through 10/29/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential in the path restrictions may be at risk. ………………………………
X23-390769 |  | 2023-10-06 | 2023-10-29 |  |  |  | MLV 515-1 to MLV 515-1A | 500 | L | Line Lowering | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed will be shut in for the duration of the project. | SOP | Potential out of path restrictions may be at risk. | 410907 TRUNKLNE/TGP CENTERVILLE DEHY TR | 515.1 |  | MLV 515-1 to MLV 515-1A: Line Lowering --10/6/23 through 10/29/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed will be shut in for the duration of the project. Potential out of path restrictions may be at risk. 410907 TRUNKLNE/TGP CENTERVILLE DEHY TR ………………………………
X23-390771 |  | 2023-10-06 | 2023-10-22 |  |  |  | MLV 515-1A to MLV 516-1 | 500 | L | Line Lowering | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed will be shut in for the duration of the project. | SOP | Potential out of path restrictions may be at risk. | 410907 TRUNKLNE/TGP CENTERVILLE DEHY TR | 515.11 |  | MLV 515-1A to MLV 516-1: Line Lowering --10/6/23 through 10/22/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed will be shut in for the duration of the project. Potential out of path restrictions may be at risk. 410907 TRUNKLNE/TGP CENTERVILLE DEHY TR ………………………………
X23-390774 |  | 2023-10-02 | 2023-10-13 |  |  |  | MLV 517-1 to MLV 518-1 | 500 | L | Line Lowering | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 517.1 |  | MLV 517-1 to MLV 518-1: Line Lowering --10/2/23 through 10/13/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-135805 |  | 2023-10-02 | 2023-10-13 |  |  |  | MLV 516-1 to MLV 517-1 | 500 | L | Line Lowering | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed will be shut in for the duration of the project. | SIP | Potential in the path restrictions may be at risk. | 412684 ANR/TGP SHADYSIDE ST MARY 412705 MTBB/TGP MARTIN WELL 1 ST MARY | 518 |  | MLV 516-1 to MLV 517-1: Line Lowering --10/2/23 through 10/13/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed will be shut in for the duration of the project. Potential in the path restrictions may be at risk. 412684 ANR/TGP SHADYSIDE ST MARY 412705 MTBB/TGP MARTIN WELL 1 ST MARY ………………………………
X23-390776 |  | 2023-10-02 | 2023-10-12 |  |  |  | MLV 518-1 to MLV 519-1 | 500 | L | Line Lowering | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 518.1 |  | MLV 518-1 to MLV 519-1: Line Lowering --10/2/23 through 10/12/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X22-1102770 | *** | 2023-06-07 | 2023-06-08 | Project Change | 2023-06-05 | 2023-06-05 | MLV 523-1 to MLV 524-1 | 500 | L | Maintenance Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 523.1 | --start_date--end_date------------model_loc-- | ***MLV 523-1 to MLV 524-1: Maintenance Pig --6/7/23 through 6/8/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. *** Date Change, Previously scheduled 6/5/23. ………………………………
X23-24536 | *** | 2023-06-08 | 2023-06-14 | Project Change | 2023-06-05 | 2023-06-13 | MLV 523-2 to MLV 524-2 | 500 | L | Pig Runs - Chemical Cleaning 6/5 to 6/14 | 'This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 523.2 | --start_date--end_date------mantenance_desc------model_loc-- | ***MLV 523-2 to MLV 524-2: Pig Runs - Chemical Cleaning 6/5 to 6/14 --6/8/23 through 6/14/23: 'This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. *** Date Change, Previously scheduled 6/5/23 to 6/13/23. ………………………………
X23-374918 |  | 2023-06-13 | 2023-06-13 |  |  |  | MLV 523-2 to MLV 524-2 | 500 | L | Pig Runs - Gauge 6/13 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 523.21 |  | MLV 523-2 to MLV 524-2: Pig Runs - Gauge 6/13 --6/13/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-374921 |  | 2023-06-15 | 2023-06-15 |  |  |  | MLV 523-2 to MLV 524-2 | 500 | L | Pig Runs - Combo 6/15 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 523.22 |  | MLV 523-2 to MLV 524-2: Pig Runs - Combo 6/15 --6/15/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-135816 |  | 2023-10-02 | 2023-10-30 |  |  |  | MLV 523 to Sta 527 | 500 | L | Pressure Regulation and OPP | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed will be shut in for the duration of the project. | SOP | Potential out of path restrictions may be at risk. | 411145 OGS/TGP BAY BATISTE TRANSPORT PLAQU 412658 C.W.ENER/TGP FLEUR PLAQUEMINES 412672 TGP/TGP QUEEN BESS JEFFERSON | 524 |  | MLV 523 to Sta 527: Pressure Regulation and OPP --10/2/23 through 10/30/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed will be shut in for the duration of the project. Potential out of path restrictions may be at risk. 411145 OGS/TGP BAY BATISTE TRANSPORT PLAQU 412658 C.W.ENER/TGP FLEUR PLAQUEMINES 412672 TGP/TGP QUEEN BESS JEFFERSON ………………………………
X23-235665 |  | 2023-05-15 | 2023-12-30 |  |  |  | Sta 527 | 500 | L | Station Reversal & Automation Upgrade | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 527 |  | Sta 527: Station Reversal & Automation Upgrade --5/15/23 through 12/30/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X22-1146576 |  | 2023-07-10 | 2023-07-15 |  |  |  | Sta 527 | 500 | L | Station 115 KV Line Maintenance | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 527.1 |  | Sta 527: Station 115 KV Line Maintenance --7/10/23 through 7/15/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-374936 |  | 2023-08-07 | 2023-08-13 |  |  |  | MLV 527-1 to MLV 529-1 | 500 | L | Pig Runs - Cleaning 8/7 to 8/13 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 527.1 |  | MLV 527-1 to MLV 529-1: Pig Runs - Cleaning 8/7 to 8/13 --8/7/23 through 8/13/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-374937 |  | 2023-08-15 | 2023-08-15 |  |  |  | MLV 527-1 to MLV 529-1 | 500 | L | Pig Runs - Combo 8/15 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 527.11 |  | MLV 527-1 to MLV 529-1: Pig Runs - Combo 8/15 --8/15/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-374938 |  | 2023-08-17 | 2023-08-17 |  |  |  | MLV 527-1 to MLV 529-1 | 500 | L | Pig Runs - AFD 8/17 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 527.12 |  | MLV 527-1 to MLV 529-1: Pig Runs - AFD 8/17 --8/17/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-135847 |  | 2023-10-02 | 2023-10-31 |  |  |  | MLV 523 to Sta 527 | 500 | L | Trap Modification | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 527.2 |  | MLV 523 to Sta 527: Trap Modification --10/2/23 through 10/31/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-57594 |  | 2023-10-01 | 2023-11-07 |  |  |  | MLV 528-1 | 500 | L | Install New Platform | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 528.1 |  | MLV 528-1: Install New Platform --10/1/23 through 11/7/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-57589 |  | 2023-07-17 | 2023-09-29 |  |  |  | MLV 528-2 & MLV 528-3 | 500 | L | Install New Platform | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meter listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 412654 ELYSIM/TGP POTASH PLAQUEMINES | 528.2 |  | MLV 528-2 & MLV 528-3: Install New Platform --7/17/23 through 9/29/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meter listed will be shut in during the project. Potential out of path restrictions may be at risk. 412654 ELYSIM/TGP POTASH PLAQUEMINES ………………………………
X22-261411 | *** | 2023-08-07 | 2023-08-07 | Project Change | 2023-06-05 | 2023-06-05 | MLV 529-1 to MLV 530-1 | 500 | L | Maintenance Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 529.1 | --start_date--end_date------------model_loc-- | ***MLV 529-1 to MLV 530-1: Maintenance Pig --8/7/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. *** Date Change, Previously scheduled 6/5/23. ………………………………
X23-374962 |  | 2023-09-13 | 2023-09-20 |  |  |  | MLV 529D-101A | 500 | L | Yscloskey to Toca Pig - Chemical Cleaning 9/13 to 9/20 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 529.1 |  | MLV 529D-101A: Yscloskey to Toca Pig - Chemical Cleaning 9/13 to 9/20 --9/13/23 through 9/20/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-374967 |  | 2023-09-21 | 2023-09-21 |  |  |  | MLV 529D-101A | 500 | L | Yscloskey to Toca Pig - Combo 9/21 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 529.11 |  | MLV 529D-101A: Yscloskey to Toca Pig - Combo 9/21 --9/21/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X22-261413 |  | 2023-07-10 | 2023-07-10 |  |  |  | MLV 529-2 to MLV 530-2 | 500 | L | Maintenance Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 529.2 |  | MLV 529-2 to MLV 530-2: Maintenance Pig --7/10/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-374941 |  | 2023-10-02 | 2023-10-09 |  |  |  | MLV 529-2 to MLV 530-2 | 500 | L | Pig Runs - Cleaning 10/2 to 10/9 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 529.2 |  | MLV 529-2 to MLV 530-2: Pig Runs - Cleaning 10/2 to 10/9 --10/2/23 through 10/9/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-513991 |  | 2023-10-09 | 2023-10-09 |  |  |  | MLV 529-2 to MLV 530-2 | 500 | L | Pig Runs - Gauge 10/9 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 529.2 |  | MLV 529-2 to MLV 530-2: Pig Runs - Gauge 10/9 --10/9/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-374943 |  | 2023-10-11 | 2023-10-11 |  |  |  | MLV 529-2 to MLV 530-2 | 500 | L | Pig Runs - Combo 10/11 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 529.21 |  | MLV 529-2 to MLV 530-2: Pig Runs - Combo 10/11 --10/11/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-374944 |  | 2023-10-13 | 2023-10-13 |  |  |  | MLV 529-2 to MLV 530-2 | 500 | L | Pig Runs - AFD 10/13 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 529.22 |  | MLV 529-2 to MLV 530-2: Pig Runs - AFD 10/13 --10/13/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-120615 |  | 2023-08-07 | 2023-08-13 |  |  |  | MLV 530-1 to MLV 534-1 | 500 | L | Pig Runs - Cleaning 8/7 to 8/13 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 410723 GULFSTH/TGP KILN MISS EXCH HANCOCK 420930 FGT/TGP CARNES COMPRESSOR STONE | 530.1 |  | MLV 530-1 to MLV 534-1: Pig Runs - Cleaning 8/7 to 8/13 --8/7/23 through 8/13/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 410723 GULFSTH/TGP KILN MISS EXCH HANCOCK 420930 FGT/TGP CARNES COMPRESSOR STONE ………………………………
X23-120616 |  | 2023-09-19 | 2023-09-19 |  |  |  | MLV 530-1 to MLV 534-1 | 500 | L | Pig Runs - Caliper 9/19 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 410723 GULFSTH/TGP KILN MISS EXCH HANCOCK 420930 FGT/TGP CARNES COMPRESSOR STONE | 530.11 |  | MLV 530-1 to MLV 534-1: Pig Runs - Caliper 9/19 --9/19/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 410723 GULFSTH/TGP KILN MISS EXCH HANCOCK 420930 FGT/TGP CARNES COMPRESSOR STONE ………………………………
X23-120618 |  | 2023-09-21 | 2023-09-21 |  |  |  | MLV 530-1 to MLV 534-1 |  |  | Pig Runs - MFL-A 9/21 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 410723 GULFSTH/TGP KILN MISS EXCH HANCOCK 420930 FGT/TGP CARNES COMPRESSOR STONE | 530.12 |  | MLV 530-1 to MLV 534-1: Pig Runs - MFL-A 9/21 --9/21/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 410723 GULFSTH/TGP KILN MISS EXCH HANCOCK 420930 FGT/TGP CARNES COMPRESSOR STONE ………………………………
X23-120619 |  | 2023-09-26 | 2023-09-26 |  |  |  | MLV 530-1 to MLV 534-1 | 500 | L | Pig Runs - MFL-C 9/26 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 410723 GULFSTH/TGP KILN MISS EXCH HANCOCK 420930 FGT/TGP CARNES COMPRESSOR STONE | 530.13 |  | MLV 530-1 to MLV 534-1: Pig Runs - MFL-C 9/26 --9/26/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 410723 GULFSTH/TGP KILN MISS EXCH HANCOCK 420930 FGT/TGP CARNES COMPRESSOR STONE ………………………………
X23-38761 |  | 2023-10-02 | 2023-10-08 |  |  |  | MLV 530-2 to MLV 531-2 | 500 | L | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 530.2 |  | MLV 530-2 to MLV 531-2: Anomaly Remediation --10/2/23 through 10/8/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-374945 |  | 2023-06-19 | 2023-06-25 |  |  |  | MLV 530-3 to MLV 532-3 | 500 | L | Pig Runs - Cleaning 6/19 to 6/25 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 530.3 |  | MLV 530-3 to MLV 532-3: Pig Runs - Cleaning 6/19 to 6/25 --6/19/23 through 6/25/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-374946 |  | 2023-06-27 | 2023-06-27 |  |  |  | MLV 530-3 to MLV 532-3 | 500 | L | Pig Runs - Combo 6/27 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 530.31 |  | MLV 530-3 to MLV 532-3: Pig Runs - Combo 6/27 --6/27/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-38764 |  | 2023-10-09 | 2023-10-20 |  |  |  | MLV 533-2 to MLV 534-2 | 500 | L | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed may experience pressure fluctuations and may be shut-in during the project. | SOP | Potential out of path restrictions may be at risk. | 412753 PAR MINL/TGP UDP PISTOL RIDGE: RIP 412758 PETROHRV/TGP HIGHWAY 13: RIP 533D- 412750 PRP INC/TGP PISTOL RIDGE: RIP 533B- | 533.2 |  | MLV 533-2 to MLV 534-2: Anomaly Remediation --10/9/23 through 10/20/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed may experience pressure fluctuations and may be shut-in during the project. Potential out of path restrictions may be at risk. 412753 PAR MINL/TGP UDP PISTOL RIDGE: RIP 412758 PETROHRV/TGP HIGHWAY 13: RIP 533D- 412750 PRP INC/TGP PISTOL RIDGE: RIP 533B- ………………………………
X23-245490 |  | 2023-03-06 | 2024-06-01 |  |  |  | Sta 534 | 500 | 1 | Unit 1A to 7A - Overhaul | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 534.001 |  | Sta 534: Unit 1A to 7A - Overhaul --3/6/23 through 6/1/24: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-120626 |  | 2023-06-13 | 2023-06-13 |  |  |  | MLV 538-1 to MLV 534-1A | 500 | L | Pig Runs - Cleaning 6/13 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 412612 VNTUREOG/TGP BEI WALKER 1-8 JONES 420714 CPTENTEX/TGP LAUREL SALES JONES 420726 CPTENTEX/TGP LAUREL SALES 2 JONES | 534.11 |  | MLV 538-1 to MLV 534-1A: Pig Runs - Cleaning 6/13 --6/13/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 412612 VNTUREOG/TGP BEI WALKER 1-8 JONES 420714 CPTENTEX/TGP LAUREL SALES JONES 420726 CPTENTEX/TGP LAUREL SALES 2 JONES ………………………………
X23-191417 |  | 2023-06-14 | 2023-06-14 |  |  |  | MLV 538-1 to MLV 534-1A | 500 | L | Pig Runs - Cleaning / Gauge 6/14 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 412612 VNTUREOG/TGP BEI WALKER 1-8 JONES 420714 CPTENTEX/TGP LAUREL SALES JONES 420726 CPTENTEX/TGP LAUREL SALES 2 JONES | 534.12 |  | MLV 538-1 to MLV 534-1A: Pig Runs - Cleaning / Gauge 6/14 --6/14/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 412612 VNTUREOG/TGP BEI WALKER 1-8 JONES 420714 CPTENTEX/TGP LAUREL SALES JONES 420726 CPTENTEX/TGP LAUREL SALES 2 JONES ………………………………
X23-191420 |  | 2023-06-20 | 2023-06-20 |  |  |  | MLV 538-1 to MLV 534-1A | 500 | L | Pig Runs - CAL/IMU 6/20 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 412612 VNTUREOG/TGP BEI WALKER 1-8 JONES 420714 CPTENTEX/TGP LAUREL SALES JONES 420726 CPTENTEX/TGP LAUREL SALES 2 JONES | 534.13 |  | MLV 538-1 to MLV 534-1A: Pig Runs - CAL/IMU 6/20 --6/20/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 412612 VNTUREOG/TGP BEI WALKER 1-8 JONES 420714 CPTENTEX/TGP LAUREL SALES JONES 420726 CPTENTEX/TGP LAUREL SALES 2 JONES ………………………………
X23-191421 |  | 2023-06-22 | 2023-06-22 |  |  |  | MLV 538-1 to MLV 534-1A | 500 | L | Pig Runs - MFL-A 6/22 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 412612 VNTUREOG/TGP BEI WALKER 1-8 JONES 420714 CPTENTEX/TGP LAUREL SALES JONES 420726 CPTENTEX/TGP LAUREL SALES 2 JONES | 534.14 |  | MLV 538-1 to MLV 534-1A: Pig Runs - MFL-A 6/22 --6/22/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 412612 VNTUREOG/TGP BEI WALKER 1-8 JONES 420714 CPTENTEX/TGP LAUREL SALES JONES 420726 CPTENTEX/TGP LAUREL SALES 2 JONES ………………………………
X23-155714 |  | 2023-09-09 | 2023-11-15 |  |  |  | MLV 535-1 to MLV 536-1 | 500 | 1 | Pipe Replacement | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 535.1 |  | MLV 535-1 to MLV 536-1: Pipe Replacement --9/9/23 through 11/15/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-155718 |  | 2023-08-14 | 2023-09-09 |  |  |  | MLV 535-2 to MLV 536-2 | 500 | 1 | Pipe Replacement | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 535.2 |  | MLV 535-2 to MLV 536-2: Pipe Replacement --8/14/23 through 9/9/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-155721 |  | 2023-05-26 | 2023-06-29 |  |  |  | MLV 536-2 to MLV 537-2 | 500 | 1 | Hydro Test | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 536.2 |  | MLV 536-2 to MLV 537-2: Hydro Test --5/26/23 through 6/29/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-130800 |  | 2023-09-05 | 2023-09-11 |  |  |  | MLV 536-3 to MLV 538-3 | 500 | 1 | Pig Runs - Cleaning 9/5 to 9/11 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meter listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 412460 VNTUREOG/TGP UDP A FOOTE ESTATE | 536.3 |  | MLV 536-3 to MLV 538-3: Pig Runs - Cleaning 9/5 to 9/11 --9/5/23 through 9/11/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meter listed will be shut in during the project. Potential out of path restrictions may be at risk. 412460 VNTUREOG/TGP UDP A FOOTE ESTATE ………………………………
X23-130803 |  | 2023-10-05 | 2023-10-05 |  |  |  | MLV 536-3 to MLV 538-3 | 500 | 1 | Pig Runs - MFL 10/5 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meter listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 412460 VNTUREOG/TGP UDP A FOOTE ESTATE | 536.31 |  | MLV 536-3 to MLV 538-3: Pig Runs - MFL 10/5 --10/5/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meter listed will be shut in during the project. Potential out of path restrictions may be at risk. 412460 VNTUREOG/TGP UDP A FOOTE ESTATE ………………………………
X23-155722 |  | 2023-05-26 | 2023-07-21 |  |  |  | MLV 537-2 to MLV 538-2 | 500 | 1 | Hydro Test | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 537.2 |  | MLV 537-2 to MLV 538-2: Hydro Test --5/26/23 through 7/21/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-245502 |  | 2023-03-06 | 2024-06-01 |  |  |  | Sta 538 | 500 | 1 | Unit 1A to 9A - Overhaul | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 538.001 |  | Sta 538: Unit 1A to 9A - Overhaul --3/6/23 through 6/1/24: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-514118 |  | 2023-06-15 | 2023-06-15 |  |  |  | MLV 538-1 to MLV 534-1A | 500 | L | Pig Runs - MFL-C 6/15 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 412612 VNTUREOG/TGP BEI WALKER 1-8 JONES 420714 CPTENTEX/TGP LAUREL SALES JONES 420726 CPTENTEX/TGP LAUREL SALES 2 JONES | 538.1 |  | MLV 538-1 to MLV 534-1A: Pig Runs - MFL-C 6/15 --6/15/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 412612 VNTUREOG/TGP BEI WALKER 1-8 JONES 420714 CPTENTEX/TGP LAUREL SALES JONES 420726 CPTENTEX/TGP LAUREL SALES 2 JONES ………………………………
X23-135892 |  | 2023-09-04 | 2023-09-15 |  |  |  | MLV 538-1 TO MLV 539-1 | 500 | 1 | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meter listed may be shut in for the duration of the project. | SOP | Potential out of path restrictions may be at risk. | 412060 /TGP HEIDELBURG TRANSPORT JASPER | 538.1 |  | MLV 538-1 TO MLV 539-1: Anomaly Remediation --9/4/23 through 9/15/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meter listed may be shut in for the duration of the project. Potential out of path restrictions may be at risk. 412060 /TGP HEIDELBURG TRANSPORT JASPER ………………………………
X23-120628 |  | 2023-11-27 | 2023-12-03 |  |  |  | MLV 538-1 to MLV 542-1 | 500 | 1 | Pig Runs - Cleaning 11/27 to 12/3 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 412060 /TGP HEIDELBURG TRANSPORT JASPER 420807 ATMOS-MS/TGP PINE SPRINGS ROAD LEAK | 538.1 |  | MLV 538-1 to MLV 542-1: Pig Runs - Cleaning 11/27 to 12/3 --11/27/23 through 12/3/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 412060 /TGP HEIDELBURG TRANSPORT JASPER 420807 ATMOS-MS/TGP PINE SPRINGS ROAD LEAK ………………………………
X23-120630 |  | 2023-12-05 | 2023-12-05 |  |  |  | MLV 538-1 to MLV 542-1 | 500 | 1 | Pig Runs - MFL 12/5 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 412060 /TGP HEIDELBURG TRANSPORT JASPER 420807 ATMOS-MS/TGP PINE SPRINGS ROAD LEAK | 538.12 |  | MLV 538-1 to MLV 542-1: Pig Runs - MFL 12/5 --12/5/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 412060 /TGP HEIDELBURG TRANSPORT JASPER 420807 ATMOS-MS/TGP PINE SPRINGS ROAD LEAK ………………………………
X23-120633 |  | 2023-12-07 | 2023-12-07 |  |  |  | MLV 538-1 to MLV 542-1 | 500 | 1 | Pig Runs - Hard Spot 12/7 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 412060 /TGP HEIDELBURG TRANSPORT JASPER 420807 ATMOS-MS/TGP PINE SPRINGS ROAD LEAK | 538.13 |  | MLV 538-1 to MLV 542-1: Pig Runs - Hard Spot 12/7 --12/7/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 412060 /TGP HEIDELBURG TRANSPORT JASPER 420807 ATMOS-MS/TGP PINE SPRINGS ROAD LEAK ………………………………
X23-155727 |  | 2023-09-26 | 2023-10-31 |  |  |  | MLV 540-1A to MLV 541-1 | 500 | 1 | Pipe Replacement | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 540.1 |  | MLV 540-1A to MLV 541-1: Pipe Replacement --9/26/23 through 10/31/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-155729 |  | 2023-08-28 | 2023-09-25 |  |  |  | MLV 540-2A to MLV 541-2 | 500 | 1 | Pipe Replacement | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 540.2 |  | MLV 540-2A to MLV 541-2: Pipe Replacement --8/28/23 through 9/25/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-155735 |  | 2023-08-01 | 2023-08-22 |  |  |  | MLV 541-1 to MLV 542-1 | 500 | 1 | Pipe Replacement and Hydro Test | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meter listed will be shut in for the duration of the project. | SOP | Potential out of path restrictions may be at risk. | 420807 ATMOS-MS/TGP PINE SPRINGS ROAD LEAK | 541.1 |  | MLV 541-1 to MLV 542-1: Pipe Replacement and Hydro Test --8/1/23 through 8/22/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meter listed will be shut in for the duration of the project. Potential out of path restrictions may be at risk. 420807 ATMOS-MS/TGP PINE SPRINGS ROAD LEAK ………………………………
X23-155736 |  | 2023-07-06 | 2023-07-31 |  |  |  | MLV 541-2 to MLV 542-2 | 500 | 1 | Pipe Replacement and Hydro Test | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 541.2 |  | MLV 541-2 to MLV 542-2: Pipe Replacement and Hydro Test --7/6/23 through 7/31/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-155740 |  | 2023-04-21 | 2023-06-09 |  |  |  | MLV 541-3 to MLV 542-3 | 500 | 1 | MLV Replacement and Hydro Test | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 541.3 |  | MLV 541-3 to MLV 542-3: MLV Replacement and Hydro Test --4/21/23 through 6/9/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-155978 |  | 2023-02-27 | 2023-11-30 |  |  |  | Sta 542 | 500 | 1 | Unit 1A - Overhaul | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 542.001 |  | Sta 542: Unit 1A - Overhaul --2/27/23 through 11/30/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-394740 | *** | 2023-04-17 | 2023-06-08 | Project Change |  | 2023-06-02 | Sta 542 | 500 | 1 | Unit 2A - Crossheads | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 542.002 | ----end_date------------model_loc-- | ***Sta 542: Unit 2A - Crossheads --4/17/23 through 6/8/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. *** Date Change, Previously scheduled 4/17/23 to 6/2/23. ………………………………
X23-517473 |  | 2023-05-22 | 2023-06-16 |  |  |  | Sta 542 | 500 | 1 | Unit 3A - Emergent Repair | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 542.003 |  | Sta 542: Unit 3A - Emergent Repair --5/22/23 through 6/16/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-467174 |  | 2023-06-26 | 2023-07-02 |  |  |  | Sta. 546 (Columbus) | 500 | 1 | Annual ESD & Maintenance | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 546 |  | Sta. 546 (Columbus): Annual ESD & Maintenance --6/26/23 through 7/2/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-159789 |  | 2023-03-06 | 2023-06-30 |  |  |  | Sta 546 | 500 | 1 | Unit 6A - Overhaul | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 546.006 |  | Sta 546: Unit 6A - Overhaul --3/6/23 through 6/30/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-311727 |  | 2023-03-27 | 2023-06-30 |  |  |  | Sta 546 | 500 | 1 | Unit 7A - Compressor Cylinder | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 546.007 |  | Sta 546: Unit 7A - Compressor Cylinder --3/27/23 through 6/30/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-502130 |  | 2023-07-17 | 2023-07-20 |  |  |  | MLV 547D-101.2 to MLV 547D-102 | 500 | 1 | Pig - Maintenance | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 420879 BBTBAMA/TGP MOUNT ZION LAMAR | 547.1 |  | MLV 547D-101.2 to MLV 547D-102: Pig - Maintenance --7/17/23 through 7/20/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 420879 BBTBAMA/TGP MOUNT ZION LAMAR ………………………………
X23-526784 |  | 2023-05-30 | 2023-06-08 |  |  |  | Sta 550 | 500 | 1 | Unit 1A - Intercooler Gasket Replacement | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 550.001 |  | Sta 550: Unit 1A - Intercooler Gasket Replacement --5/30/23 through 6/8/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-526785 |  | 2023-06-12 | 2023-06-15 |  |  |  | Sta 550 | 500 | 1 | Unit 2A - Intercooler Gasket Replacement | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 550.002 |  | Sta 550: Unit 2A - Intercooler Gasket Replacement --6/12/23 through 6/15/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-526786 |  | 2023-06-26 | 2023-06-29 |  |  |  | Sta 550 | 500 | 1 | Unit 4A - Intercooler Gasket Replacement | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 550.004 |  | Sta 550: Unit 4A - Intercooler Gasket Replacement --6/26/23 through 6/29/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-62265 |  | 2023-10-01 | 2023-10-22 |  |  |  | Sta 550 | 500 | 1 | Unit 1B - Turbine Overhaul | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 550.017 |  | Sta 550: Unit 1B - Turbine Overhaul --10/1/23 through 10/22/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-464696 |  | 2023-06-19 | 2023-06-23 |  |  |  | Sta. 555 | 500 | 1 | Annual ESD Test & Maintenance | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 555 |  | Sta. 555: Annual ESD Test & Maintenance --6/19/23 through 6/23/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-374736 |  | 2023-07-15 | 2023-08-31 |  |  |  | MLV 557-3 to MLV 558-3 | 500 | 1 | Class Change | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 557.3 |  | MLV 557-3 to MLV 558-3: Class Change --7/15/23 through 8/31/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-517654 |  | 2023-09-19 | 2023-10-03 |  |  |  | MLV 560-2 to MLV 561-2 | 500 | 1 | Class Change and Hydrotest | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 560.2 |  | MLV 560-2 to MLV 561-2: Class Change and Hydrotest --9/19/23 through 10/3/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-62073 |  | 2023-06-28 | 2023-06-28 |  |  |  | Sta 563 Joelton | 500 | 2 | Annual ESD Test | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 563 |  | Sta 563 Joelton: Annual ESD Test --6/28/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-411594 |  | 2023-06-26 | 2023-06-30 |  |  |  | Sta 703 Mansfield | 100 | 1 | Annual ESD, Maintenance, & Filter Replacement | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 703 |  | Sta 703 Mansfield: Annual ESD, Maintenance, & Filter Replacement --6/26/23 through 6/30/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-57523 |  | 2023-09-11 | 2023-09-15 |  |  |  | Meter Station Filter Srubber Maintenance | 800 | L | Cameron Banken Rd (Pin 49446) | This activity will center on maintenance on the filter scrubber at the meter listed. The meter listed may experience pressure fluctuations. | SOP | Potential out of path restrictions may be at risk. | 49446 CAM IPL/TGP BANKEN RD AT HWY 27 DE | 821 |  | Meter Station Filter Srubber Maintenance: Cameron Banken Rd (Pin 49446) --9/11/23 through 9/15/23: This activity will center on maintenance on the filter scrubber at the meter listed. The meter listed may experience pressure fluctuations. Potential out of path restrictions may be at risk. 49446 CAM IPL/TGP BANKEN RD AT HWY 27 DE ………………………………
X23-311800 |  | 2023-03-13 | 2023-06-30 |  |  |  | Sta 823 | 800 | L | Unit 2A - Turbo Charger | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 823.002 |  | Sta 823: Unit 2A - Turbo Charger --3/13/23 through 6/30/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-311816 |  | 2023-04-10 | 2023-08-01 |  |  |  | Sta 823 | 800 | L | Unit 6A - Turbo Charger | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 823.006 |  | Sta 823: Unit 6A - Turbo Charger --4/10/23 through 8/1/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-520499 |  | 2023-05-23 | 2023-07-15 |  |  |  | Sta 823 | 800 | L | Unit 11A - Compressor Rods | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 823.011 |  | Sta 823: Unit 11A - Compressor Rods --5/23/23 through 7/15/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-101115 |  | 2023-07-12 | 2023-07-12 |  |  |  | Sta 823 to MLV 516 | 500 | L | Maintenance Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed may be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 412398 JEFFSTOR/TGP JEFFERSON ISLAND IBERI420915 CEGS/TGP PORT IBERIA SALES IBERIA421056 ACADIAN/TGP INDIAN BAYOU: DIP 510B-410907 TRUNKLNE/TGP CENTERVILLE DEHY TRANS450105 AMMID SC/TGP QUIVIRA ST MARY412594 NAUTILUS/TGP GARDEN CITY ST MARY412684 ANR/TGP SHADYSIDE ST MARY | 823.5 |  | Sta 823 to MLV 516: Maintenance Pig --7/12/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed may be shut in during the project. Potential out of path restrictions may be at risk. 412398 JEFFSTOR/TGP JEFFERSON ISLAND IBERI420915 CEGS/TGP PORT IBERIA SALES IBERIA421056 ACADIAN/TGP INDIAN BAYOU: DIP 510B-410907 TRUNKLNE/TGP CENTERVILLE DEHY TRANS450105 AMMID SC/TGP QUIVIRA ST MARY412594 NAUTILUS/TGP GARDEN CITY ST MARY412684 ANR/TGP SHADYSIDE ST MARY ………………………………
X23-377290 |  | 2023-07-10 | 2023-07-14 |  |  |  | Station 827 (Alexandria) | 800 | L | Annual ESD and Maintenance | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 827 |  | Station 827 (Alexandria): Annual ESD and Maintenance --7/10/23 through 7/14/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-101126 |  | 2023-10-11 | 2023-10-11 |  |  |  | Sta 827 to Sta 823 | 800 | L | Maintenance Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 421043 PINE PRA/TGP PINE PRAIRIE NORTH RAP 412847 ACADIAN/TGP CHENEYVILLE RAPIDES 412713 HUGHES E/TGP UDP BLACK STONE13 EVAN 412844 TEXLA/TGP ROY MARTIN GATHERING: RIP 420296 FORSTHIL/TGP FOREST HILL LA RAPIDES 420530 GLNMORA/TGP GLENMORA LA EXCH RAPIDE 421042 ELIZ NG/TGP EVANGELINE SALES EVANGE 420629 ELIZ NG/TGP OAKDALE DETENTION SALES 420687 ELIZ NG/TGP ALLEN PARISH PRISON SAL 420406 ELIZ NG/TGP ELIZABETH LA EMERGENCY 53483 AIRLIQAT/TGP TIMBERLANE BIOGAS REC | 827.11 |  | Sta 827 to Sta 823: Maintenance Pig --10/11/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 421043 PINE PRA/TGP PINE PRAIRIE NORTH RAP 412847 ACADIAN/TGP CHENEYVILLE RAPIDES 412713 HUGHES E/TGP UDP BLACK STONE13 EVAN 412844 TEXLA/TGP ROY MARTIN GATHERING: RIP 420296 FORSTHIL/TGP FOREST HILL LA RAPIDES 420530 GLNMORA/TGP GLENMORA LA EXCH RAPIDE 421042 ELIZ NG/TGP EVANGELINE SALES EVANGE 420629 ELIZ NG/TGP OAKDALE DETENTION SALES 420687 ELIZ NG/TGP ALLEN PARISH PRISON SAL 420406 ELIZ NG/TGP ELIZABETH LA EMERGENCY 53483 AIRLIQAT/TGP TIMBERLANE BIOGAS REC ………………………………
X22-154269 |  | 2023-06-01 | 2023-08-31 |  |  |  | MLV 828-1 to MLV 829-1 | 800 | L | Make Piggable | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 828.1 |  | MLV 828-1 to MLV 829-1: Make Piggable --6/1/23 through 8/31/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X22-1209530 |  | 2022-12-06 | 2023-07-16 |  |  |  | Sta 834 | 800 | 1 | Unit 2A - Crankshaft Inspection | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 834.002 |  | Sta 834: Unit 2A - Crankshaft Inspection --12/6/22 through 7/16/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-502127 | *** | 2023-06-27 | 2023-06-28 | Project Change | 2023-05-30 | 2023-05-31 | Sta 834 | 800 | 1 | Unit 3A - Relocate Unit Valve Controls | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 834.003 | --start_date--end_date------------model_loc-- | ***Sta 834: Unit 3A - Relocate Unit Valve Controls --6/27/23 through 6/28/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. *** Date Change, Previously scheduled 5/30/23 to 5/31/23. ………………………………
X23-71374 |  | 2023-07-17 | 2023-07-21 |  |  |  | Sta 834 | 800 | 1 | Unit 6A - Replace Lube System | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 834.006 |  | Sta 834: Unit 6A - Replace Lube System --7/17/23 through 7/21/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-71375 |  | 2023-07-24 | 2023-07-28 |  |  |  | Sta 834 | 800 | 1 | Unit 7A - Replace Lube System | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 834.007 |  | Sta 834: Unit 7A - Replace Lube System --7/24/23 through 7/28/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-113734 |  | 2023-09-19 | 2023-09-22 |  |  |  | MLV 834-1 TO MLV 827-1 | 800 | 1 | Pig Runs - Chemical Cleaning 9/19 to 9/22 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 420447 PELICANG/TGP HARRISONBURG LA CATAHO 420775 VAR/TGP NORTH GARDEN ISLAND BAY GAS | 834.1 |  | MLV 834-1 TO MLV 827-1: Pig Runs - Chemical Cleaning 9/19 to 9/22 --9/19/23 through 9/22/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 420447 PELICANG/TGP HARRISONBURG LA CATAHO 420775 VAR/TGP NORTH GARDEN ISLAND BAY GAS ………………………………
X23-113737 |  | 2023-09-22 | 2023-09-22 |  |  |  | MLV 834-1 TO MLV 827-1 | 800 | 1 | Pig Runs - Gauge 9/22 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 420447 PELICANG/TGP HARRISONBURG LA CATAHO 420775 VAR/TGP NORTH GARDEN ISLAND BAY GAS | 834.11 |  | MLV 834-1 TO MLV 827-1: Pig Runs - Gauge 9/22 --9/22/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 420447 PELICANG/TGP HARRISONBURG LA CATAHO 420775 VAR/TGP NORTH GARDEN ISLAND BAY GAS ………………………………
X23-101123 |  | 2023-10-11 | 2023-10-11 |  |  |  | Sta 834 to Sta 827 | 800 | L | Maintenance Pig | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 420755 ATMOS TL/TGP LASALLE PARISH NEBO SA 420447 PELICANG/TGP HARRISONBURG LA CATAHO | 834.11 |  | Sta 834 to Sta 827: Maintenance Pig --10/11/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 420755 ATMOS TL/TGP LASALLE PARISH NEBO SA 420447 PELICANG/TGP HARRISONBURG LA CATAHO ………………………………
X23-113730 |  | 2023-09-26 | 2023-09-26 |  |  |  | MLV 834-1 TO MLV 827-1 | 800 | 1 | Pig Runs - MFL-C 9/26 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 420447 PELICANG/TGP HARRISONBURG LA CATAHO 420775 VAR/TGP NORTH GARDEN ISLAND BAY GAS | 834.12 |  | MLV 834-1 TO MLV 827-1: Pig Runs - MFL-C 9/26 --9/26/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 420447 PELICANG/TGP HARRISONBURG LA CATAHO 420775 VAR/TGP NORTH GARDEN ISLAND BAY GAS ………………………………
X23-113732 |  | 2023-09-28 | 2023-09-28 |  |  |  | MLV 834-1 TO MLV 827-1 | 800 | 1 | Pig Runs - EMAT 9/28 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 420447 PELICANG/TGP HARRISONBURG LA CATAHO 420775 VAR/TGP NORTH GARDEN ISLAND BAY GAS | 834.13 |  | MLV 834-1 TO MLV 827-1: Pig Runs - EMAT 9/28 --9/28/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 420447 PELICANG/TGP HARRISONBURG LA CATAHO 420775 VAR/TGP NORTH GARDEN ISLAND BAY GAS ………………………………
X23-113745 |  | 2023-10-03 | 2023-10-06 |  |  |  | MLV 834-1 TO MLV 838-1 | 800 | 1 | Pig Runs - Chemical Cleaning 10/03 to 10/06 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 412691 REGENCY/TGP PEOPLES ROAD FRANKLIN 49554 BBTMIDLA/TGP NORTH PEOPLES RD FRANK 420279 ATMOS TL/TGP CROWVILLE LA FRANKLIN 49585 GULFRUN/TGP BEARFOOT RICHLAND 49589 ETC TIG/TGP URSUS FRANKLIN 49587 GULFSTH/TGP LUPE FRANKLIN 49583 MEP/TGP PILLAR MADISON 49643 GULFSTH/TGP SKIPPER MADISON | 834.14 |  | MLV 834-1 TO MLV 838-1: Pig Runs - Chemical Cleaning 10/03 to 10/06 --10/3/23 through 10/6/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 412691 REGENCY/TGP PEOPLES ROAD FRANKLIN 49554 BBTMIDLA/TGP NORTH PEOPLES RD FRANK 420279 ATMOS TL/TGP CROWVILLE LA FRANKLIN 49585 GULFRUN/TGP BEARFOOT RICHLAND 49589 ETC TIG/TGP URSUS FRANKLIN 49587 GULFSTH/TGP LUPE FRANKLIN 49583 MEP/TGP PILLAR MADISON 49643 GULFSTH/TGP SKIPPER MADISON ………………………………
X23-113746 |  | 2023-10-06 | 2023-10-06 |  |  |  | MLV 834-1 TO MLV 838-1 | 800 | 1 | Pig Runs - Gauge 10/06 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 412691 REGENCY/TGP PEOPLES ROAD FRANKLIN 49554 BBTMIDLA/TGP NORTH PEOPLES RD FRANK 420279 ATMOS TL/TGP CROWVILLE LA FRANKLIN 49585 GULFRUN/TGP BEARFOOT RICHLAND 49589 ETC TIG/TGP URSUS FRANKLIN 49587 GULFSTH/TGP LUPE FRANKLIN 49583 MEP/TGP PILLAR MADISON 49643 GULFSTH/TGP SKIPPER MADISON | 834.15 |  | MLV 834-1 TO MLV 838-1: Pig Runs - Gauge 10/06 --10/6/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 412691 REGENCY/TGP PEOPLES ROAD FRANKLIN 49554 BBTMIDLA/TGP NORTH PEOPLES RD FRANK 420279 ATMOS TL/TGP CROWVILLE LA FRANKLIN 49585 GULFRUN/TGP BEARFOOT RICHLAND 49589 ETC TIG/TGP URSUS FRANKLIN 49587 GULFSTH/TGP LUPE FRANKLIN 49583 MEP/TGP PILLAR MADISON 49643 GULFSTH/TGP SKIPPER MADISON ………………………………
X23-113748 |  | 2023-10-10 | 2023-10-10 |  |  |  | MLV 834-1 TO MLV 838-1 | 800 | 1 | Pig Runs - CLP / MFL-A / IMU 10/10 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. | SOP | Potential out of path restrictions may be at risk. | 412691 REGENCY/TGP PEOPLES ROAD FRANKLIN 49554 BBTMIDLA/TGP NORTH PEOPLES RD FRANK 420279 ATMOS TL/TGP CROWVILLE LA FRANKLIN 49585 GULFRUN/TGP BEARFOOT RICHLAND 49589 ETC TIG/TGP URSUS FRANKLIN 49587 GULFSTH/TGP LUPE FRANKLIN 49583 MEP/TGP PILLAR MADISON 49643 GULFSTH/TGP SKIPPER MADISON | 834.16 |  | MLV 834-1 TO MLV 838-1: Pig Runs - CLP / MFL-A / IMU 10/10 --10/10/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations. The meters listed will be shut in during the project. Potential out of path restrictions may be at risk. 412691 REGENCY/TGP PEOPLES ROAD FRANKLIN 49554 BBTMIDLA/TGP NORTH PEOPLES RD FRANK 420279 ATMOS TL/TGP CROWVILLE LA FRANKLIN 49585 GULFRUN/TGP BEARFOOT RICHLAND 49589 ETC TIG/TGP URSUS FRANKLIN 49587 GULFSTH/TGP LUPE FRANKLIN 49583 MEP/TGP PILLAR MADISON 49643 GULFSTH/TGP SKIPPER MADISON ………………………………
X23-69504 |  | 2023-07-18 | 2023-07-19 |  |  |  | Sta 843 | 800 | 1 | Annual ESD Test | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 843 |  | Sta 843: Annual ESD Test --7/18/23 through 7/19/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X22-1120812 |  | 2023-01-16 | 2023-12-01 |  |  |  | Sta 843 | 800 | 1 | Unit 1A - Engine Inspection | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 843.001 |  | Sta 843: Unit 1A - Engine Inspection --1/16/23 through 12/1/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X22-1120813 |  | 2023-01-23 | 2023-12-01 |  |  |  | Sta 843 | 800 | 1 | Unit 8A - Crankcase Inspection | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 843.008 |  | Sta 843: Unit 8A - Crankcase Inspection --1/23/23 through 12/1/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-354280 |  | 2023-09-05 | 2023-09-22 |  |  |  | MLV 847-1 to 848-1 | 800 | 1 | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 847.1 |  | MLV 847-1 to 848-1: Anomaly Remediation --9/5/23 through 9/22/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-488206 |  | 2023-05-30 | 2023-06-09 |  |  |  | Sta 851 | 800 | 1 | Units: 1A, 2A, 3A, & 4A - Ignition System Upgrade | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 851.001 |  | Sta 851: Units: 1A, 2A, 3A, & 4A - Ignition System Upgrade --5/30/23 through 6/9/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-113717 |  | 2023-07-10 | 2023-07-14 |  |  |  | Sta 860 | 800 | 1 | Annual ESD Test & Maintenance | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 860 |  | Sta 860: Annual ESD Test & Maintenance --7/10/23 through 7/14/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-118147 |  | 2023-07-21 | 2023-08-15 |  |  |  | Sta 860 | 800 | 1 | Units 1A, 2A & 4A - Install New 12" Piping | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 860.001 |  | Sta 860: Units 1A, 2A & 4A - Install New 12" Piping --7/21/23 through 8/15/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-173712 |  | 2023-02-22 | 2023-09-15 |  |  |  | Sta 860 | 800 | 1 | Unit 7A - Bearing Inspection | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 860.007 |  | Sta 860: Unit 7A - Bearing Inspection --2/22/23 through 9/15/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-328599 | *** | 2023-07-05 | 2023-07-28 | Project Change | 2023-05-08 | 2023-06-09 | Sta 860 | 800 | 1 | Unit 9A - Compressor Overhaul | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 860.009 | --start_date--end_date------------model_loc-- | ***Sta 860: Unit 9A - Compressor Overhaul --7/5/23 through 7/28/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. *** Date Change, Previously scheduled 5/8/23 to 6/9/23. ………………………………
X23-572784 | *** | 2023-06-01 | 2023-06-30 | Added |  |  | Sta 860 | 800 | 1 | Unit 10A - Compressor Overhaul | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 860.01 | ------ | ***Sta 860: Unit 10A - Compressor Overhaul --6/1/23 through 6/30/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ***Added ………………………………
X23-423819 | *** | 2023-05-29 | 2023-06-12 | Completed |  |  | MLV 860-1 to MLV 866-1B | 800 | 1 | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 860.1 | ------ | ***MLV 860-1 to MLV 866-1B: Anomaly Remediation ***Completed
X23-113718 |  | 2023-07-10 | 2023-07-20 |  |  |  | Sta 860 | 800 | 1 | Install New 12" Valve | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 860.1 |  | Sta 860: Install New 12" Valve --7/10/23 through 7/20/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-517653 |  | 2023-08-22 | 2023-09-12 |  |  |  | MLV 860-1 to MLV 861-1 | 800 | 4 | Class Change and Hydrotest | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 860.1 |  | MLV 860-1 to MLV 861-1: Class Change and Hydrotest --8/22/23 through 9/12/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-517651 |  | 2023-08-22 | 2023-09-12 |  |  |  | MLV 861-1 to MLV 862-1 | 800 | 2 | Class Change and Hydrotest | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 861.1 |  | MLV 861-1 to MLV 862-1: Class Change and Hydrotest --8/22/23 through 9/12/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-581283 | *** | 2023-05-25 | 2023-06-10 | Added |  |  | MLV 864-1A to MLV 865-1BR | 800 | 1 | Anomaly Remediation | This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 864.1 | ------ | ***MLV 864-1A to MLV 865-1BR: Anomaly Remediation --5/25/23 through 6/10/23: This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ***Added ………………………………
X23-517658 |  | 2023-08-22 | 2023-09-05 |  |  |  | MLV 868-2 to MLV 869-2 | 800 | 2 | Class Change and Pipe Replacement | This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 868.2 |  | MLV 868-2 to MLV 869-2: Class Change and Pipe Replacement --8/22/23 through 9/5/23: This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-170334 |  | 2023-09-12 | 2023-09-12 |  |  |  | Sta 871A | 100 | 2 | Annual ESD Test | This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 871.0001 |  | Sta 871A: Annual ESD Test --9/12/23: This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-488405 |  | 2023-06-05 | 2023-06-16 |  |  |  | Sta 871 | 800 | 2 | Unit 3A - Tubing Replacement | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 871.003 |  | Sta 871: Unit 3A - Tubing Replacement --6/5/23 through 6/16/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-514131 | *** | 2023-06-14 | 2023-06-14 | Project Change | 2023-06-15 | 2023-06-15 | MLV 871-1 to MLV 866-1 | 800 | 1 | Pig Run - Cleaning / Gauge 6/14 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 871.1 | --start_date--end_date------mantenance_desc------model_loc-- | ***MLV 871-1 to MLV 866-1: Pig Run - Cleaning / Gauge 6/14 --6/14/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. *** Date Change, Previously scheduled 6/15/23. ………………………………
X23-57455 |  | 2023-07-18 | 2023-07-18 |  |  |  | MLV 871-1 to MLV 866-1 | 800 | 2 | Pig Runs - Cleaning / Gauge 7/18 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 871.1 |  | MLV 871-1 to MLV 866-1: Pig Runs - Cleaning / Gauge 7/18 --7/18/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-514132 |  | 2023-06-20 | 2023-06-20 |  |  |  | MLV 871-1 to MLV 866-1 | 800 | 1 | Pig Run - MFL-C 6/20 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 871.11 |  | MLV 871-1 to MLV 866-1: Pig Run - MFL-C 6/20 --6/20/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-57458 |  | 2023-07-20 | 2023-07-20 |  |  |  | MLV 871-1 to MLV 866-1 | 800 | 2 | Pig Runs - MFL Combo 7/20 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 871.11 |  | MLV 871-1 to MLV 866-1: Pig Runs - MFL Combo 7/20 --7/20/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-514133 |  | 2023-06-22 | 2023-06-22 |  |  |  | MLV 871-1 to MLV 866-1 | 800 | 1 | Pig Run - EMAT 6/22 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 871.12 |  | MLV 871-1 to MLV 866-1: Pig Run - EMAT 6/22 --6/22/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-57452 |  | 2023-07-11 | 2023-07-11 |  |  |  | MLV 873-2A to 871-2 | 800 | 2 | Pig Runs - Cleaning / Gauge 7/11 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 873.2 |  | MLV 873-2A to 871-2: Pig Runs - Cleaning / Gauge 7/11 --7/11/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-57453 |  | 2023-07-13 | 2023-07-13 |  |  |  | MLV 873-2A to 871-2 | 800 | 2 | Pig Runs - MFL Combo 7/13 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 873.21 |  | MLV 873-2A to 871-2: Pig Runs - MFL Combo 7/13 --7/13/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-41240 |  | 2023-07-17 | 2023-07-19 |  |  |  | Sta 875 | 800 | 2 | Unit 1A - 4k Hr Inspection | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 875.001 |  | Sta 875: Unit 1A - 4k Hr Inspection --7/17/23 through 7/19/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-41276 |  | 2023-12-04 | 2023-12-06 |  |  |  | Sta 875 | 800 | 2 | Unit 1A - 8k Hr Inspection | This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. | SOP | Potential out of path restrictions may be at risk. |  | 875.001 |  | Sta 875: Unit 1A - 8k Hr Inspection --12/4/23 through 12/6/23: This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations. Potential out of path restrictions may be at risk. ………………………………
X23-57443 |  | 2023-06-27 | 2023-06-27 |  |  |  | MLV 876-1 to 871-1 | 800 | 2 | Pig Runs - Cleaning / Gauge 6/27 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 876.1 |  | MLV 876-1 to 871-1: Pig Runs - Cleaning / Gauge 6/27 --6/27/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-57444 |  | 2023-06-29 | 2023-06-29 |  |  |  | MLV 876-1 to 871-1 | 800 | 2 | Pig Runs - MFL Combo 6/29 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SOP | Potential out of path restrictions may be at risk. |  | 876.11 |  | MLV 876-1 to 871-1: Pig Runs - MFL Combo 6/29 --6/29/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential out of path restrictions may be at risk. ………………………………
X23-57441 |  | 2023-07-11 | 2023-07-11 |  |  |  | MLV 876-2 to 874-2 | 800 | 2 | Pig Runs - MFL Combo 7/11 | This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. | SIP | Potential in the path restrictions may be at risk. |  | 876.21 |  | MLV 876-2 to 874-2: Pig Runs - MFL Combo 7/11 --7/11/23: This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated. Potential in the path restrictions may be at risk. ………………………………