{"text_format":"1","workbook":"xlsx","n_sheets":4,"sheets":["Closed","Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":8,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Closed","index":0,"n_rows":37,"n_cols":22,"rows_kept":37,"cut":false,"hidden":true,"merged":[[1,3,1,15],[2,3,2,15],[3,3,3,15]]}
[null,null,null,"Updated ","2016"]
[null,null,null,"Tennessee Gas Pipeline 2015 Pipeline Outage and Maintenance Summary"]
[null,null,null,"This is a summary of the current status of all TGP Winter 2014-2015 Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  Additionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
[null,null,null,"*** Indicates revision"]
["Date Change","Project New/Completed/Closed","Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","Location","Leg","Zone","Maintenance Activity","Anticipated Impact","Potential Restriction Level","TOS Potential Restrictions","Meter(s) in Impacted Area","Customer Notifications","Loc","Email Text","Posting Text","Completion Text"]
[{"$f":"IF(AND(H6<>\"\",I6<>\"\"), \"Date change. Previously scheduled \" & TEXT(H6,\"m/d/y;@\") &IF(H6=I6,\"\",\" to \" & TEXT(I6,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed",null,{"$f":"IF(G6<>\"\",\"***\",\"\")","v":"***"},"2015-01-11","2016-01-11",{"$f":"IF(AND(A6=\"\",B6=\"\"),\"\",IF(B6=\"\",A6,B6))","v":"Project Completed"},null,null,"MS #412494 DCP Warren","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412494 DCP Warren",401,{"$f":"\"(\"&C6&\") \"&J6&\":  \"&M6&IF(AND(E6=\"\",F6=\"\"),\"\",\" (\")&IF(E6=\"\",\"\",\"\"&TEXT(E6,\"m/d/y;@\"))&IF(OR(F6=E6,E6=\"\",F6=\"\"),\"\",\" to \")&IF(OR(F6=\"\",F6=E6),\"\",TEXT(F6,\"m/d/y;@\"))&IF(AND(E6=\"\",F6=\"\"),\"\",\")\")","v":"() MS #412494 DCP Warren:  Meter Station (1/11/15 to 1/11/16)"},{"$f":"D6&J6&\":  \"&M6&IF(AND(E6=\"\",F6=\"\"),\"\",\"\n\")&IF(E6=\"\",\"\",\"--\"&TEXT(E6,\"m/d/y;@\"))&IF(OR(F6=E6,E6=\"\",F6=\"\"),\"\",\" through \")&IF(OR(F6=\"\",F6=E6),\"\",TEXT(F6,\"m/d/y;@\"))&IF(AND(E6=\"\",F6=\"\"),\"\",\":  \")&N6&\"  \"&P6&IF(Q6=\"\",\"\",\"\n\"&Q6)&IF(G6=\"\",\"\",\"\n***\")&G6&\"\n………………………………\"","v":"***MS #412494 DCP Warren:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412494 DCP Warren\n***Project Completed\n………………………………"},{"$f":"D6&J6&\":  \"&M6&IF(G6=\"\",\"\",\"\n***\")&G6&IF(Q6=\"\",\"\",\"\nThe following meters are available for nominations:\n\")&Q6&\"\n………………………………\"","v":"***MS #412494 DCP Warren:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412494 DCP Warren\n………………………………"}]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412400 King Ranch","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412400 King Ranch",402.1,"() MS #412400 King Ranch:  Meter Station (1/11/15 to 1/11/16)","***MS #412400 King Ranch:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412400 King Ranch\n***Project Completed\n………………………………","***MS #412400 King Ranch:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412400 King Ranch\n………………………………"]
["","Project Completed",null,"***","2015-01-12","2016-01-12","Project Completed",null,null,"MS #410539 Duvak Gas Gathering","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410539 Duvak Gas Gathering",402.1,"() MS #410539 Duvak Gas Gathering:  Meter Station (1/12/15 to 1/12/16)","***MS #410539 Duvak Gas Gathering:  Meter Station\n--1/12/15 through 1/12/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410539 Duvak Gas Gathering\n***Project Completed\n………………………………","***MS #410539 Duvak Gas Gathering:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n410539 Duvak Gas Gathering\n………………………………"]
["","Project Completed",null,"***","2015-01-13","2016-01-13","Project Completed",null,null,"MS #412356 DCP LaGloria","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412356 DCP LaGloria",403.1,"() MS #412356 DCP LaGloria:  Meter Station (1/13/15 to 1/13/16)","***MS #412356 DCP LaGloria:  Meter Station\n--1/13/15 through 1/13/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412356 DCP LaGloria\n***Project Completed\n………………………………","***MS #412356 DCP LaGloria:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412356 DCP LaGloria\n………………………………"]
["","Project Completed",null,"***","2015-01-13","2016-01-13","Project Completed",null,null,"MS #410173 Enterprise LaReforma","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410173 Enterprise LaReforma",406.1,"() MS #410173 Enterprise LaReforma:  Meter Station (1/13/15 to 1/13/16)","***MS #410173 Enterprise LaReforma:  Meter Station\n--1/13/15 through 1/13/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410173 Enterprise LaReforma\n***Project Completed\n………………………………","***MS #410173 Enterprise LaReforma:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n410173 Enterprise LaReforma\n………………………………"]
["","Project Completed",null,"***","2015-01-12","2016-01-12","Project Completed",null,null,"MS #411903 Enterprise El Benito","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","411903 Enterprise El Benito",407.1,"() MS #411903 Enterprise El Benito:  Meter Station (1/12/15 to 1/12/16)","***MS #411903 Enterprise El Benito:  Meter Station\n--1/12/15 through 1/12/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n411903 Enterprise El Benito\n***Project Completed\n………………………………","***MS #411903 Enterprise El Benito:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n411903 Enterprise El Benito\n………………………………"]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412088 Enterprise Sullivan","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412088 Enterprise Sullivan",407.1,"() MS #412088 Enterprise Sullivan:  Meter Station (1/11/15 to 1/11/16)","***MS #412088 Enterprise Sullivan:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412088 Enterprise Sullivan\n***Project Completed\n………………………………","***MS #412088 Enterprise Sullivan:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412088 Enterprise Sullivan\n………………………………"]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412683 HESCO","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412683 HESCO",408.1,"() MS #412683 HESCO:  Meter Station (1/11/15 to 1/11/16)","***MS #412683 HESCO:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412683 HESCO\n***Project Completed\n………………………………","***MS #412683 HESCO:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412683 HESCO\n………………………………"]
[{"$f":"IF(AND(H14<>\"\",I14<>\"\"), \"Date change. Previously scheduled \" & TEXT(H14,\"m/d/y;@\") &IF(H14=I14,\"\",\" to \" & TEXT(I14,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X16-36843",{"$f":"IF(G14<>\"\",\"***\",\"\")","v":"***"},"2016-01-27","2016-01-27","Project Completed",null,null,"Sta. 237",200,5,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,237,"(X16-36843) Sta. 237:  Unit  Maintenance (1/27/16)","***Sta. 237:  Unit  Maintenance\n--1/27/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Sta. 237:  Unit  Maintenance\n***Project Completed\n………………………………"]
[{"$f":"IF(AND(H15<>\"\",I15<>\"\"), \"Date change. Previously scheduled \" & TEXT(H15,\"m/d/y;@\") &IF(H15=I15,\"\",\" to \" & TEXT(I15,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X14-1478563",{"$f":"IF(G15<>\"\",\"***\",\"\")","v":"***"},"2015-11-16","2016-02-12","Project Completed",null,null,"MLV 32-1D to 33-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,32.200000000000003,"(X14-1478563) MLV 32-1D to 33-1:  Hydrotest (11/16/15 to 2/12/16)","***MLV 32-1D to 33-1:  Hydrotest\n--11/16/15 through 2/12/16:  This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***MLV 32-1D to 33-1:  Hydrotest\n***Project Completed\n………………………………"]
[null,"Project Completed","X16-16074",null,"2016-01-18","2016-01-28","Project Completed",null,null,"Station 550","500","1","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,550,"(X16-16074) Station 550:  Station Maintenance (1/18/16 to 1/28/16)","Station 550:  Station Maintenance\n--1/18/16 through 1/28/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","Station 550:  Station Maintenance\n***Project Completed\n………………………………"]
[{"$f":"IF(AND(H17<>\"\",I17<>\"\"), \"Date change. Previously scheduled \" & TEXT(H17,\"m/d/y;@\") &IF(H17=I17,\"\",\" to \" & TEXT(I17,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X16-46202",{"$f":"IF(G17<>\"\",\"***\",\"\")","v":"***"},"2016-02-01","2016-02-07","Project Completed",null,null,"Station 9","100","0","Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.",null,9,"(X16-46202) Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items) (2/1/16 to 2/7/16)","***Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)\n--2/1/16 through 2/7/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\n***Project Completed\n………………………………","***Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)\n***Project Completed\n………………………………"]
["","Project Completed","X15-925633","***","2016-02-09","2016-02-11","Project Completed",null,null,"Sta. 266A",200,6,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,266,"(X15-925633) Sta. 266A:  Unit  Maintenance (2/9/16 to 2/11/16)","***Sta. 266A:  Unit  Maintenance\n--2/9/16 through 2/11/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Sta. 266A:  Unit  Maintenance\n***Project Completed\n………………………………"]
["","Project Completed","X15-929733","***","2016-01-27","2016-02-10","Project Completed",null,null,"MLV 834-1 to 838-1",800,5,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",834.1,"(X15-929733) MLV 834-1 to 838-1:  ILI/Cleaning Pig (1/27/16 to 2/10/16)","***MLV 834-1 to 838-1:  ILI/Cleaning Pig\n--1/27/16 through 2/10/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 834-1 to 838-1:  ILI/Cleaning Pig\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X14-1562506","***","2015-11-02","2016-02-19","Project Completed",null,null,"MLV 5-1 to 6-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410063 ROCHE DEHYDRATION             \n",5.0999999999999996,"(X14-1562506) MLV 5-1 to 6-1:  Hydrotest (11/2/15 to 2/19/16)","***MLV 5-1 to 6-1:  Hydrotest\n--11/2/15 through 2/19/16:  This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410063 ROCHE DEHYDRATION             \n\n***Project Completed\n………………………………","***MLV 5-1 to 6-1:  Hydrotest\n***Project Completed\nThe following meters are available for nominations:\n410063 ROCHE DEHYDRATION             \n\n………………………………"]
["","Project Completed","X14-1562506","***","2015-11-02","2016-02-19","Project Completed",null,null,"MLV 7-1 to 9-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","\n412490 Charro\n421083 Eagle Ford Field Service",5.0999999999999996,"(X14-1562506) MLV 7-1 to 9-1:  Hydrotest (11/2/15 to 2/19/16)","***MLV 7-1 to 9-1:  Hydrotest\n--11/2/15 through 2/19/16:  This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n\n412490 Charro\n421083 Eagle Ford Field Service\n***Project Completed\n………………………………","***MLV 7-1 to 9-1:  Hydrotest\n***Project Completed\nThe following meters are available for nominations:\n\n412490 Charro\n421083 Eagle Ford Field Service\n………………………………"]
["Date change. Previously scheduled 2/18/16 to 2/20/16.","Project Completed","X15-882289","***","2016-02-22","2016-02-24","Project Completed","2016-02-18","2016-02-20","MLV 24-2 to 25-2S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.2,"(X15-882289) MLV 24-2 to 25-2S:  Anomaly Remediation (2/22/16 to 2/24/16)","***MLV 24-2 to 25-2S:  Anomaly Remediation\n--2/22/16 through 2/24/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 24-2 to 25-2S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-925630","***","2016-02-23","2016-02-23","Project Completed",null,null,"WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B)",200,"L","ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,265.10000000000002,"(X15-925630) WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig (2/23/16)","***WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig\n--2/23/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig\n***Project Completed\n………………………………"]
["","Project Completed","X16-23748","***","2016-02-15","2016-02-18","Project Completed",null,null,"MLV 530-3 to 532-3",500,"L","ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,530.29999999999995,"(X16-23748) MLV 530-3 to 532-3:  ILI/Cleaning Pig (2/15/16 to 2/18/16)","***MLV 530-3 to 532-3:  ILI/Cleaning Pig\n--2/15/16 through 2/18/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***MLV 530-3 to 532-3:  ILI/Cleaning Pig\n***Project Completed\n………………………………"]
["","Project Canceled","X16-98720","***","2016-03-06","2016-03-06","Project Canceled",null,null,"Sta. 1",100,0,"Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,1,"(X16-98720) Sta. 1:  Station Maintenance (3/6/16)","***Sta. 1:  Station Maintenance\n--3/6/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Canceled\n………………………………","***Sta. 1:  Station Maintenance\n***Project Canceled\n………………………………"]
["","Project Completed","X14-1562513\nX14-1540661","***","2015-07-01","2016-03-04","Project Completed",null,null,"Station 32","100","0","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,32,"(X14-1562513\nX14-1540661) Station 32:  Station Maintenance (7/1/15 to 3/4/16)","***Station 32:  Station Maintenance\n--7/1/15 through 3/4/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Station 32:  Station Maintenance\n***Project Completed\n………………………………"]
["","Project Canceled","X15-926822","***","2016-06-06","2016-06-11","Project Canceled",null,null,"BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1)",300,6,"Pipe Inspection","This project involves inspecting multiple sites.  We do not anticipate having to do any repairs, however if a repair is needed  there is a potential that the pipe  may require replacement which will require isolation of the pipe.  This may limit throughput and will result in restrictions based on customer nominations.  Customers may experience pressure fluctuations during this timeframe.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",343.1,"(X15-926822) BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection (6/6/16 to 6/11/16)","***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection\n--6/6/16 through 6/11/16:  This project involves inspecting multiple sites.  We do not anticipate having to do any repairs, however if a repair is needed  there is a potential that the pipe  may require replacement which will require isolation of the pipe.  This may limit throughput and will result in restrictions based on customer nominations.  Customers may experience pressure fluctuations during this timeframe.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928271","***","TBD","TBD","Project Canceled",null,null,"MLV 555-1 to 550-1",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.1,"(X15-928271) MLV 555-1 to 550-1:  ILI/Cleaning Pig (TBD)","***MLV 555-1 to 550-1:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-1 to 550-1:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928272","***","TBD","TBD","Project Canceled",null,null,"MLV 555-2 to 550-2",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.20000000000005,"(X15-928272) MLV 555-2 to 550-2:  ILI/Cleaning Pig (TBD)","***MLV 555-2 to 550-2:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-2 to 550-2:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928273","***","TBD","TBD","Project Canceled",null,null,"MLV 555-3 to 552-3",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.29999999999995,"(X15-928273) MLV 555-3 to 552-3:  ILI/Cleaning Pig (TBD)","***MLV 555-3 to 552-3:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-3 to 552-3:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-882281","***","2016-02-24","2016-03-03","Project Completed",null,null,"24-1A to 25-1S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.1,"(X15-882281) 24-1A to 25-1S:  Anomaly Remediation (2/24/16 to 3/3/16)","***24-1A to 25-1S:  Anomaly Remediation\n--2/24/16 through 3/3/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***24-1A to 25-1S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-882291","***","2016-03-03","2016-03-04","Project Completed",null,null,"MLV 24-3 to 25-3S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.3,"(X15-882291) MLV 24-3 to 25-3S:  Anomaly Remediation (3/3/16 to 3/4/16)","***MLV 24-3 to 25-3S:  Anomaly Remediation\n--3/3/16 through 3/4/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 24-3 to 25-3S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X14-1178175","***","2015-06-15","2016-03-31","Project Completed",null,null,"Station 63","100","1","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,63,"(X14-1178175) Station 63:  Station Maintenance (6/15/15 to 3/31/16)","***Station 63:  Station Maintenance\n--6/15/15 through 3/31/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Station 63:  Station Maintenance\n***Project Completed\n………………………………"]
["","Project Cancelled","X15-913224","***","2016-04-16","2016-05-21","Project Cancelled",null,null,"MLV 109-2",100,2,"Pipe Replacement","This project will require taking the pipeline section out of service.   This will limit throughput and will result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",109.2,"(X15-913224) MLV 109-2:  Pipe Replacement (4/16/16 to 5/21/16)","***MLV 109-2:  Pipe Replacement\n--4/16/16 through 5/21/16:  This project will require taking the pipeline section out of service.   This will limit throughput and will result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Cancelled\n………………………………","***MLV 109-2:  Pipe Replacement\n***Project Cancelled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-926830","***","2016-03-07","2016-03-11","Project Completed",null,null,"MLV 400-1 to 408-1",100,0,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.","To Be Determined",400.1,"(X15-926830) MLV 400-1 to 408-1:  ILI/Cleaning Pig (3/7/16 to 3/11/16)","***MLV 400-1 to 408-1:  ILI/Cleaning Pig\n--3/7/16 through 3/11/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 400-1 to 408-1:  ILI/Cleaning Pig\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Cancelled","X16-143836","***","2016-03-28","2016-04-04","Project Cancelled",null,null,"Sta. 409",100,0,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.",null,409,"(X16-143836) Sta. 409:  Unit  Maintenance (3/28/16 to 4/4/16)","***Sta. 409:  Unit  Maintenance\n--3/28/16 through 4/4/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\n***Project Cancelled\n………………………………","***Sta. 409:  Unit  Maintenance\n***Project Cancelled\n………………………………"]
["","Project Cancelled","X15-929680","***","2016-04-18","2016-04-27","Project Cancelled",null,null,"SABINE - KINDER LINE to 822-1",800,"L","Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",822.1,"(X15-929680) SABINE - KINDER LINE to 822-1:  Anomaly Remediation (4/18/16 to 4/27/16)","***SABINE - KINDER LINE to 822-1:  Anomaly Remediation\n--4/18/16 through 4/27/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Cancelled\n………………………………","***SABINE - KINDER LINE to 822-1:  Anomaly Remediation\n***Project Cancelled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]

{"sheet":"Sheet1","index":1,"n_rows":384,"n_cols":24,"rows_kept":384,"cut":false,"hidden":false,"merged":[[2,0,2,14]]}
["Updated ","2024-02-08"]
["Tennessee Gas Pipeline 2024 Pipeline Outage and Maintenance Summary"]
["This is a summary of the current status of TGP Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  \nAdditionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
["*** Indicates revision"]
["Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","Location","Leg","Zone","Maintenance Activity","Anticipated Impact","Potential Restriction Level","TOS Potential Restrictions","Meter(s) in Impacted Area","Loc",null,null,null,null,null,null,null,"\\\\houCORP\\TRANS\\TRANSERVICES\\OPPLAN\\COMMON\\Outages\\Outage_DB\\TGP\\Files"]
["X24-56012",null,"2024-03-27","2024-03-27",null,null,null,"Sta 1 Agua Dulce","100","0","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,1,null,"Sta 1 Agua Dulce:  Annual ESD Test\n--3/27/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-157482",null,"2024-03-05","2024-03-05",null,null,null,"MLV 9-1 to MLV 1-1","100","0","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.","SIP","Potential in the path restrictions may be at risk.","54847 WHISTLEP/TGP WHISTLE RECEIPT NUECES\n53608 VCP/TGP VALLEY CROSSING ALLOCATION",1.1000000000000001,null,"MLV 9-1 to MLV 1-1:  Pig Run - Maintenance\n--3/5/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.  Potential in the path restrictions may be at risk.\n54847 WHISTLEP/TGP WHISTLE RECEIPT NUECES\n53608 VCP/TGP VALLEY CROSSING ALLOCATION\n………………………………"]
["X23-157484",null,"2024-03-07","2024-03-07",null,null,null,"MLV 9-2 to MLV 1-2","100","0","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.","SIP","Potential in the path restrictions may be at risk.","54847 WHISTLEP/TGP WHISTLE RECEIPT NUECES\n53608 VCP/TGP VALLEY CROSSING ALLOCATION",1.2,null,"MLV 9-2 to MLV 1-2:  Pig Run - Maintenance\n--3/7/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.  Potential in the path restrictions may be at risk.\n54847 WHISTLEP/TGP WHISTLE RECEIPT NUECES\n53608 VCP/TGP VALLEY CROSSING ALLOCATION\n………………………………"]
["X24-55955",null,"2024-04-15","2024-06-17",null,null,null,"MLV 3-1 TO MLV 4-1","100","0","Class Change / Wrinkle Bend Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,3.1,null,"MLV 3-1 TO MLV 4-1:  Class Change / Wrinkle Bend Replacement\n--4/15/24 through 6/17/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-62229",null,"2024-04-01","2024-04-05",null,null,null,"MLV 4-1 to MLV 5-1","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,4.0999999999999996,null,"MLV 4-1 to MLV 5-1:  Anomaly Remediation\n--4/1/24 through 4/5/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-62242",null,"2024-07-02","2024-07-02",null,null,null,"MLV 5-2 to MLV 1-2D","100","0","Pig Runs - MFL-A 7/2/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,5.2,null,"MLV 5-2 to MLV 1-2D:  Pig Runs - MFL-A 7/2/24\n--7/2/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-76784","***","2024-11-14","2024-11-14","Project Change",null,null,"MLV 5-2 to MLV 1-2D","100","0","Pig Runs - Maintenance Cleaning 11/14","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412603 MAGNUS/TGP WILDCAT WELDER HEIRS 5 S\n412196 ENLINK/TGP NORTH BRAYTON DEHY NUECE\n412062 BANHUB/TGP BANQUETE TRANSPORT NUECE\n412669 ETP/TGP SHOUP NUECES\n412270 LOBO/TGP UDP TRANSAMERICAN INTERCON\n54847 WHISTLEP/TGP WHISTLER RECEIPT NUECE",5.2,"--------anticipated_impact--------model_loc--","***MLV 5-2 to MLV 1-2D:  Pig Runs - Maintenance Cleaning 11/14\n--11/14/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n412603 MAGNUS/TGP WILDCAT WELDER HEIRS 5 S\n412196 ENLINK/TGP NORTH BRAYTON DEHY NUECE\n412062 BANHUB/TGP BANQUETE TRANSPORT NUECE\n412669 ETP/TGP SHOUP NUECES\n412270 LOBO/TGP UDP TRANSAMERICAN INTERCON\n54847 WHISTLEP/TGP WHISTLER RECEIPT NUECE\n***Project Change\n………………………………"]
["X24-62296",null,"2024-07-01","2024-07-01",null,null,null,"MLV 5-2 to MLV 1-2D","100","0","Pig Runs - Cleaning/Gauge 7/1/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,5.21,null,"MLV 5-2 to MLV 1-2D:  Pig Runs - Cleaning/Gauge 7/1/24\n--7/1/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-62245",null,"2024-07-10","2024-07-10",null,null,null,"MLV 5-2 to MLV 9-2S","100","0","Pig Runs - MFL-A 7/10/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,5.22,null,"MLV 5-2 to MLV 9-2S:  Pig Runs - MFL-A 7/10/24\n--7/10/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-62297",null,"2024-07-09","2024-07-09",null,null,null,"MLV 5-2 to MLV 9-2S","100","0","Pig Runs - Cleaning/Gauge 7/9/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,5.23,null,"MLV 5-2 to MLV 9-2S:  Pig Runs - Cleaning/Gauge 7/9/24\n--7/9/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-62227","***","2024-03-01","2024-03-27","Project Change","2024-03-07","2024-03-29","MLV 7-1 to MLV 6-1","100","0","Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,7.1,"--start_date--end_date------------model_loc--","***MLV 7-1 to MLV 6-1:  Anomaly Remediation\n--3/1/24 through 3/27/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 3/7/24 to 3/29/24.\n………………………………"]
["X24-62226","***","2024-04-06","2024-04-12","Project Change","2024-03-01","2024-03-06","MLV 8-1 to MLV 7-1","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,8.1,"--start_date--end_date------------model_loc--","***MLV 8-1 to MLV 7-1:  Anomaly Remediation\n--4/6/24 through 4/12/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 3/1/24 to 3/6/24.\n………………………………"]
["X24-62224",null,"2024-02-26","2024-02-29",null,null,null,"MLV 8-1L to MLV 8-1","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,8.11,null,"MLV 8-1L to MLV 8-1:  Anomaly Remediation\n--2/26/24 through 2/29/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-62240",null,"2024-06-25","2024-06-25",null,null,null,"MLV 9-1D to MLV 17-1S","100","0","Pig Runs - MFL-A 6/25/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,9.1,null,"MLV 9-1D to MLV 17-1S:  Pig Runs - MFL-A 6/25/24\n--6/25/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-76782",null,"2024-11-12","2024-11-12",null,null,null,"MLV 9-1S and MLV 1-1D","100","0","Pig Run - Maintenance Cleaning 11/12","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,9.1,null,"MLV 9-1S and MLV 1-1D:  Pig Run - Maintenance Cleaning 11/12\n--11/12/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-62295",null,"2024-06-24","2024-06-24",null,null,null,"MLV 9-1D to MLV 17-1S","100","0","Pig Runs - Cleaning/Gauge 6/24/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,9.11,null,"MLV 9-1D to MLV 17-1S:  Pig Runs - Cleaning/Gauge 6/24/24\n--6/24/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-76834",null,"2024-11-14","2024-11-14",null,null,null,"MLV 9-2 to MLV 5-2","100","0","Pig Runs - Maintenance Cleaning 11/14","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,9.1999999999999993,null,"MLV 9-2 to MLV 5-2:  Pig Runs - Maintenance Cleaning 11/14\n--11/14/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-157486",null,"2024-03-06","2024-03-06",null,null,null,"MLV 9-3 to MLV 5-3","100","0","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.","SIP","Potential in the path restrictions may be at risk.","54847 WHISTLEP/TGP WHISTLE RECEIPT NUECES\n53608 VCP/TGP VALLEY CROSSING ALLOCATION",9.3000000000000007,null,"MLV 9-3 to MLV 5-3:  Pig Run - Maintenance\n--3/6/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.  Potential in the path restrictions may be at risk.\n54847 WHISTLEP/TGP WHISTLE RECEIPT NUECES\n53608 VCP/TGP VALLEY CROSSING ALLOCATION\n………………………………"]
["X24-76788",null,"2024-05-08","2024-05-08",null,null,null,"MLV 9-3 to MLV 4-3","100","0","Pig Runs - Maintenance Cleaning 5/8","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,9.3000000000000007,null,"MLV 9-3 to MLV 4-3:  Pig Runs - Maintenance Cleaning 5/8\n--5/8/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-76791",null,"2024-11-13","2024-11-13",null,null,null,"MLV 9-3 to MLV 4-3","100","0","Pig Runs - Maintenance Cleaning 11/13","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,9.31,null,"MLV 9-3 to MLV 4-3:  Pig Runs - Maintenance Cleaning 11/13\n--11/13/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-867586",null,"2023-08-26","2024-04-01",null,null,null,"Sta 17","100","0","Unit 2C - Engine Seal Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,17.033999999999999,null,"Sta 17:  Unit 2C - Engine Seal Inspection\n--8/26/23 through 4/1/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-29928",null,"2024-06-11","2024-06-14",null,null,null,"MLV 17-2D TO MLV 20-2A","100","0","Pig Runs - Chem Cleaning 6/11 to 6/14","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420167 COKINOS/TGP WOODS FARM TX FORT BEND\n411788 DCP GLP/TGP KATY TRANSPORT WALLER",17.2,null,"MLV 17-2D TO MLV 20-2A:  Pig Runs - Chem Cleaning 6/11 to 6/14\n--6/11/24 through 6/14/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n420167 COKINOS/TGP WOODS FARM TX FORT BEND\n411788 DCP GLP/TGP KATY TRANSPORT WALLER\n………………………………"]
["X24-29930",null,"2024-06-14","2024-06-14",null,null,null,"MLV 17-2D TO MLV 20-2A","100",null,"Pig Runs - Gauge 6/14","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420167 COKINOS/TGP WOODS FARM TX FORT BEND\n411788 DCP GLP/TGP KATY TRANSPORT WALLER",17.21,null,"MLV 17-2D TO MLV 20-2A:  Pig Runs - Gauge 6/14\n--6/14/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n420167 COKINOS/TGP WOODS FARM TX FORT BEND\n411788 DCP GLP/TGP KATY TRANSPORT WALLER\n………………………………"]
["X24-29932",null,"2024-06-18","2024-06-18",null,null,null,"MLV 17-2D TO MLV 20-2A","100","0","Pig Runs - MFL-C 6/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420167 COKINOS/TGP WOODS FARM TX FORT BEND\n411788 DCP GLP/TGP KATY TRANSPORT WALLER",17.22,null,"MLV 17-2D TO MLV 20-2A:  Pig Runs - MFL-C 6/18\n--6/18/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n420167 COKINOS/TGP WOODS FARM TX FORT BEND\n411788 DCP GLP/TGP KATY TRANSPORT WALLER\n………………………………"]
["X24-29933",null,"2024-06-20","2024-06-20",null,null,null,"MLV 17-2D TO MLV 20-2A","100","0","Pig Runs - EMAT 6/20","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420167 COKINOS/TGP WOODS FARM TX FORT BEND\n411788 DCP GLP/TGP KATY TRANSPORT WALLER",17.23,null,"MLV 17-2D TO MLV 20-2A:  Pig Runs - EMAT 6/20\n--6/20/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n420167 COKINOS/TGP WOODS FARM TX FORT BEND\n411788 DCP GLP/TGP KATY TRANSPORT WALLER\n………………………………"]
["X24-29934",null,"2024-06-25","2024-06-25",null,null,null,"MLV 17-2D TO MLV 20-2A","100","0","Pig Runs - RES 6/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420167 COKINOS/TGP WOODS FARM TX FORT BEND\n411788 DCP GLP/TGP KATY TRANSPORT WALLER",17.239999999999998,null,"MLV 17-2D TO MLV 20-2A:  Pig Runs - RES 6/25\n--6/25/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n420167 COKINOS/TGP WOODS FARM TX FORT BEND\n411788 DCP GLP/TGP KATY TRANSPORT WALLER\n………………………………"]
["X24-29936",null,"2024-06-26","2024-06-26",null,null,null,"MLV 17-2D TO MLV 20-2A","100","0","Pig Runs - MFL-S 6/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420167 COKINOS/TGP WOODS FARM TX FORT BEND\n411788 DCP GLP/TGP KATY TRANSPORT WALLER",17.25,null,"MLV 17-2D TO MLV 20-2A:  Pig Runs - MFL-S 6/26\n--6/26/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n420167 COKINOS/TGP WOODS FARM TX FORT BEND\n411788 DCP GLP/TGP KATY TRANSPORT WALLER\n………………………………"]
["X24-126091","***","2024-01-31","2024-02-29","Added",null,null,"MLV 17-3 TO MLV 18-3","100","0","High Priority Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,17.3,"------","***MLV 17-3 TO MLV 18-3:  High Priority Anomaly Remediation\n--1/31/24 through 2/29/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-29941",null,"2024-05-14","2024-05-14",null,null,null,"MLV 17-3D TO MLV 20-3A","100","0","Pig Runs - Cleaning 5/14","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","421085 SYMMETRY/TGP PEDERSON ROAD WALLER",17.3,null,"MLV 17-3D TO MLV 20-3A:  Pig Runs - Cleaning 5/14\n--5/14/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n421085 SYMMETRY/TGP PEDERSON ROAD WALLER\n………………………………"]
["X24-29950",null,"2024-05-14","2024-05-14",null,null,null,"MLV 17-3D TO MLV 20-3A","100","0","Pig Runs - Gauge 5/14","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","421085 SYMMETRY/TGP PEDERSON ROAD WALLER",17.309999999999999,null,"MLV 17-3D TO MLV 20-3A:  Pig Runs - Gauge 5/14\n--5/14/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n421085 SYMMETRY/TGP PEDERSON ROAD WALLER\n………………………………"]
["X24-29958",null,"2024-05-15","2024-05-15",null,null,null,"MLV 17-3D TO MLV 20-3A","100","0","Pig Runs - MFL-A 5/15","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","421085 SYMMETRY/TGP PEDERSON ROAD WALLER",17.32,null,"MLV 17-3D TO MLV 20-3A:  Pig Runs - MFL-A 5/15\n--5/15/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n421085 SYMMETRY/TGP PEDERSON ROAD WALLER\n………………………………"]
["X24-55950",null,"2024-07-08","2024-08-05",null,null,null,"MLV 18-1A TO MLV 20-1A","100","0","Class Change / Wrinkle Bend Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,18.100000000000001,null,"MLV 18-1A TO MLV 20-1A:  Class Change / Wrinkle Bend Replacement\n--7/8/24 through 8/5/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-62431",null,"2024-04-01","2024-05-04",null,null,null,"MLV 18-2 to MLV 18-2A","100","0","Make Piggable","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,18.2,null,"MLV 18-2 to MLV 18-2A:  Make Piggable\n--4/1/24 through 5/4/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-55954",null,"2024-09-17","2024-10-28",null,null,null,"MLV 18-2A TO MLV 20-2A","100","0","Class Change / Wrinkle Bend Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,18.2,null,"MLV 18-2A TO MLV 20-2A:  Class Change / Wrinkle Bend Replacement\n--9/17/24 through 10/28/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-55953",null,"2024-08-06","2024-09-16",null,null,null,"MLV 18-3A TO MLV 20-3A","100","0","Class Change / Wrinkle Bend Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,18.3,null,"MLV 18-3A TO MLV 20-3A:  Class Change / Wrinkle Bend Replacement\n--8/6/24 through 9/16/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-76928","***","2024-01-24","TBD","Project Change",null,null,"MLV 19-3 to MLV 19-3A","100","0","Emergent Repair   Immediate Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","421085 SYMMETRY/TGP PEDERSON ROAD WALLER",19.3,"--------anticipated_impact--------model_loc--","***MLV 19-3 to MLV 19-3A:  Emergent Repair   Immediate Anomaly Remediation\n--1/24/24 through 2/19/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n421085 SYMMETRY/TGP PEDERSON ROAD WALLER\n***Project Change\n………………………………"]
["X24-76930",null,"2024-01-24","2024-02-26",null,null,null,"MLV 20-3 to MLV 20-3A","100","0","Immediate Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,20.3,null,"MLV 20-3 to MLV 20-3A:  Immediate Anomaly Remediation\n--1/24/24 through 2/26/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-55947",null,"2024-05-14","2024-05-20",null,null,null,"MLV 24-1A TO MLV 25-1","100","0","Class Change / Wrinkle Bend Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,24.1,null,"MLV 24-1A TO MLV 25-1:  Class Change / Wrinkle Bend Replacement\n--5/14/24 through 5/20/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-55945",null,"2024-04-15","2024-05-13",null,null,null,"MLV 24-2 TO MLV 25-2","100","0","Class Change / Wrinkle Bend Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,24.2,null,"MLV 24-2 TO MLV 25-2:  Class Change / Wrinkle Bend Replacement\n--4/15/24 through 5/13/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-55949",null,"2024-05-21","2024-06-17",null,null,null,"MLV 24-3A TO MLV 25-3","100","0","Class Change / Wrinkle Bend Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,24.3,null,"MLV 24-3A TO MLV 25-3:  Class Change / Wrinkle Bend Replacement\n--5/21/24 through 6/17/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-41537",null,"2024-08-13","2024-08-13",null,null,null,"MLV 25-1S to MLV 24-1A","100","0","Pig Runs - Cleaning/Gauge 8/13","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,25.1,null,"MLV 25-1S to MLV 24-1A:  Pig Runs - Cleaning/Gauge 8/13\n--8/13/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-41541",null,"2024-08-15","2024-08-15",null,null,null,"MLV 25-1S to MLV 24-1A","100","0","Pig Runs - AFD 8/15","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,25.11,null,"MLV 25-1S to MLV 24-1A:  Pig Runs - AFD 8/15\n--8/15/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-621358",null,"2024-03-25","2024-04-14",null,null,null,"MLV 26-1 Relocation","100","0","Highway Widening","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,26.1,null,"MLV 26-1 Relocation:  Highway Widening\n--3/25/24 through 4/14/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-815863",null,"2024-04-15","2024-05-05",null,null,null,"MLV 26-2 Relocation","100","0","Highway Widening","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,26.2,null,"MLV 26-2 Relocation:  Highway Widening\n--4/15/24 through 5/5/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-815864",null,"2024-03-04","2024-03-24",null,null,null,"MLV 26-3 Relocation","100","0","Highway Widening","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,26.3,null,"MLV 26-3 Relocation:  Highway Widening\n--3/4/24 through 3/24/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-75005",null,"2024-02-05","2024-02-09",null,null,null,"MLV 27-3 to MLV 27A-101.3","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,27.3,null,"MLV 27-3 to MLV 27A-101.3:  Anomaly Remediation\n--2/5/24 through 2/9/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-75006",null,"2024-02-10","2024-02-14",null,null,null,"MLV 27-3A to MLV 28-3","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,27.31,null,"MLV 27-3A to MLV 28-3:  Anomaly Remediation\n--2/10/24 through 2/14/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-75007","***","2024-02-15","2024-02-19","Project Change",null,null,"MLV 28-3 to MLV 29-3","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412738 TECOGATH/TGP TECO INDIAN SPRINGS PO",28.3,"------meters_affected--anticipated_impact--------model_loc--","***MLV 28-3 to MLV 29-3:  Anomaly Remediation\n--2/15/24 through 2/19/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n412738 TECOGATH/TGP TECO INDIAN SPRINGS PO\n***Project Change\n………………………………"]
["X24-75008",null,"2024-02-20","2024-02-24",null,null,null,"MLV 29-3 to MLV 31-3BR","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,29.3,null,"MLV 29-3 to MLV 31-3BR:  Anomaly Remediation\n--2/20/24 through 2/24/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-75009",null,"2024-02-25","2024-02-29",null,null,null,"MLV 31-3BR to MLV 31-3BR1","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,31.3,null,"MLV 31-3BR to MLV 31-3BR1:  Anomaly Remediation\n--2/25/24 through 2/29/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-75011",null,"2024-02-26","2024-03-07",null,null,null,"MLV 32-1L to MLV 33-1","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,32.1,null,"MLV 32-1L to MLV 33-1:  Anomaly Remediation\n--2/26/24 through 3/7/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-29962",null,"2024-07-23","2024-07-23",null,null,null,"MLV 32-1D to MLV 36-1TX","100","0","Pig Run - Cleaning 7/23","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,32.1,null,"MLV 32-1D to MLV 36-1TX:  Pig Run - Cleaning 7/23\n--7/23/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-29967",null,"2024-07-24","2024-07-24",null,null,null,"MLV 32-1D to MLV 36-1TX","100","0","Pig Run - Gauge 7/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,32.11,null,"MLV 32-1D to MLV 36-1TX:  Pig Run - Gauge 7/24\n--7/24/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-29969",null,"2024-07-25","2024-07-25",null,null,null,"MLV 32-1D to MLV 36-1TX","100","0","Pig Run - DEF 7/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,32.119999999999997,null,"MLV 32-1D to MLV 36-1TX:  Pig Run - DEF 7/25\n--7/25/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-29970",null,"2024-07-26","2024-07-26",null,null,null,"MLV 32-1D to MLV 36-1TX","100","0","Pig Run - MFL-S 7/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,32.130000000000003,null,"MLV 32-1D to MLV 36-1TX:  Pig Run - MFL-S 7/26\n--7/26/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-129495","***","2024-04-02","2024-04-02","Added",null,null,"MLV 32-2D to MLV 40-2S","100","0","Pig Runs - Cleaning 4/2","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,32.200000000000003,"------","***MLV 32-2D to MLV 40-2S:  Pig Runs - Cleaning 4/2\n--4/2/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-129500","***","2024-04-03","2024-04-03","Added",null,null,"MLV 32-2D to MLV 40-2S","100","0","Pig Runs - Gauge 4/3","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,32.21,"------","***MLV 32-2D to MLV 40-2S:  Pig Runs - Gauge 4/3\n--4/3/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-129503","***","2024-04-04","2024-04-04","Added",null,null,"MLV 32-2D to MLV 40-2S","100","0","Pig Runs - EMAT 4/4","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,32.22,"------","***MLV 32-2D to MLV 40-2S:  Pig Runs - EMAT 4/4\n--4/4/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-41542",null,"2024-08-20","2024-08-20",null,null,null,"MLV 32-3S to MLV 25-3D","100","0","Pig Runs - Cleaning/Gauge 8/20","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,32.29,null,"MLV 32-3S to MLV 25-3D:  Pig Runs - Cleaning/Gauge 8/20\n--8/20/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-41545",null,"2024-08-22","2024-08-22",null,null,null,"MLV 32-3S to MLV 25-3D","100","0","Pig Runs - MFL 8/22","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,32.290999999999997,null,"MLV 32-3S to MLV 25-3D:  Pig Runs - MFL 8/22\n--8/22/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-41552",null,"2024-08-27","2024-08-27",null,null,null,"MLV 32-3S to MLV 25-3D","100","0","Pig Runs - Hard Spot 8/27","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,32.292000000000002,null,"MLV 32-3S to MLV 25-3D:  Pig Runs - Hard Spot 8/27\n--8/27/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-29973",null,"2024-05-14","2024-05-16",null,null,null,"MLV 32-3D to MLV 40-3S","100","0","Pig Runs - Cleaning 5/14 to 5/16","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,32.299999999999997,null,"MLV 32-3D to MLV 40-3S:  Pig Runs - Cleaning 5/14 to 5/16\n--5/14/24 through 5/16/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-29975",null,"2024-05-17","2024-05-17",null,null,null,"MLV 32-3D to MLV 40-3S","100","0","Pig Runs - Gauge 5/17","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,32.31,null,"MLV 32-3D to MLV 40-3S:  Pig Runs - Gauge 5/17\n--5/17/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-29976",null,"2024-05-21","2024-05-21",null,null,null,"MLV 32-3D to MLV 40-3S","100","0","Pig Runs - MFL-A 5/21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,32.32,null,"MLV 32-3D to MLV 40-3S:  Pig Runs - MFL-A 5/21\n--5/21/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-29978",null,"2024-05-23","2024-05-23",null,null,null,"MLV 32-3D to MLV 40-3S","100","0","Pig Runs - RES 5/23","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,32.33,null,"MLV 32-3D to MLV 40-3S:  Pig Runs - RES 5/23\n--5/23/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-75013",null,"2024-03-08","2024-03-28",null,null,null,"MLV 35-1 to MLV 36-1","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,35.1,null,"MLV 35-1 to MLV 36-1:  Anomaly Remediation\n--3/8/24 through 3/28/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-32491",null,"2024-02-26","2024-03-01",null,null,null,"MLV 36-1LAL to MLV 37-1","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,36.1,null,"MLV 36-1LAL to MLV 37-1:  Anomaly Remediation\n--2/26/24 through 3/1/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43802",null,"2024-03-12","2024-04-01",null,null,null,"MLV 36-1 TO MLV 37-1","100","0","Class Change / Wrinkle Bend Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,36.11,null,"MLV 36-1 TO MLV 37-1:  Class Change / Wrinkle Bend Replacement\n--3/12/24 through 4/1/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-156003",null,"2024-02-10","2024-03-15",null,null,null,"MLV 36-2 TO MLV 37-2","100","0","Class Change / Wrinkle Bend Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,36.200000000000003,null,"MLV 36-2 TO MLV 37-2:  Class Change / Wrinkle Bend Replacement\n--2/10/24 through 3/15/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-156004",null,"2023-12-13","2024-02-09",null,null,null,"MLV 36-3 TO MLV 37-3","100","0","Class Change / Wrinkle Bend Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,36.299999999999997,null,"MLV 36-3 TO MLV 37-3:  Class Change / Wrinkle Bend Replacement\n--12/13/23 through 2/9/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-32490",null,"2024-03-02","2024-03-06",null,null,null,"MLV 37-1 to MLV 38-1","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,37.1,null,"MLV 37-1 to MLV 38-1:  Anomaly Remediation\n--3/2/24 through 3/6/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-32488",null,"2024-03-07","2024-03-15",null,null,null,"MLV 38-1 to MLV 39-1","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,38.1,null,"MLV 38-1 to MLV 39-1:  Anomaly Remediation\n--3/7/24 through 3/15/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-32484",null,"2024-03-16","2024-03-20",null,null,null,"MLV 39-1 to MLV 40-1","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,39.1,null,"MLV 39-1 to MLV 40-1:  Anomaly Remediation\n--3/16/24 through 3/20/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43803",null,"2024-03-15","2024-04-01",null,null,null,"MLV 39-1 TO MLV 40-1","100","0","Class Change / Wrinkle Bend Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,39.11,null,"MLV 39-1 TO MLV 40-1:  Class Change / Wrinkle Bend Replacement\n--3/15/24 through 4/1/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-156006",null,"2024-02-13","2024-02-23",null,null,null,"MLV 39-2 TO MLV 40-2","100","0","Class Change / Wrinkle Bend Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,39.200000000000003,null,"MLV 39-2 TO MLV 40-2:  Class Change / Wrinkle Bend Replacement\n--2/13/24 through 2/23/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-29983",null,"2024-04-03","2024-04-03",null,null,null,"MLV 40-1D to MLV 47-1S","100","1","Pig Runs - Cleaning 4/3","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412809 CRTXLIG/TGP CLEAR LAKE NO. 1: RIP 4",40.1,null,"MLV 40-1D to MLV 47-1S:  Pig Runs - Cleaning 4/3\n--4/3/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n412809 CRTXLIG/TGP CLEAR LAKE NO. 1: RIP 4\n………………………………"]
["X24-30007",null,"2024-04-05","2024-04-05",null,null,null,"MLV 40-1D to MLV 47-1S","100","1","Pig Runs - Gauge 4/5","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412809 CRTXLIG/TGP CLEAR LAKE NO. 1: RIP 4",40.11,null,"MLV 40-1D to MLV 47-1S:  Pig Runs - Gauge 4/5\n--4/5/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n412809 CRTXLIG/TGP CLEAR LAKE NO. 1: RIP 4\n………………………………"]
["X24-30011",null,"2024-04-08","2024-04-08",null,null,null,"MLV 40-1D to MLV 47-1S","100","1","Pig Runs - MFL-A 4/8","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412809 CRTXLIG/TGP CLEAR LAKE NO. 1: RIP 4",40.119999999999997,null,"MLV 40-1D to MLV 47-1S:  Pig Runs - MFL-A 4/8\n--4/8/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n412809 CRTXLIG/TGP CLEAR LAKE NO. 1: RIP 4\n………………………………"]
["X24-30013",null,"2024-02-13","2024-02-16",null,null,null,"Sta 40-2 to Sta 42-2","100","1","Pig Runs - Cleaning 2/13 to 2/16","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,40.200000000000003,null,"Sta 40-2 to Sta 42-2:  Pig Runs - Cleaning 2/13 to 2/16\n--2/13/24 through 2/16/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-94844",null,"2024-12-11","2024-12-31",null,null,null,"MLV 40-2D to MLV 42-2BR","100","1","Make Piggable","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,40.200000000000003,null,"MLV 40-2D to MLV 42-2BR:  Make Piggable\n--12/11/24 through 12/31/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-30016",null,"2024-02-20","2024-02-20",null,null,null,"Sta 40-2 to Sta 42-2","100","1","Pig Runs - CLP, IMU 2/20","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,40.21,null,"Sta 40-2 to Sta 42-2:  Pig Runs - CLP, IMU 2/20\n--2/20/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-30022",null,"2024-02-21","2024-02-21",null,null,null,"Sta 40-2 to Sta 42-2","100","1","Pig Runs - MFL-A 2/21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,40.22,null,"Sta 40-2 to Sta 42-2:  Pig Runs - MFL-A 2/21\n--2/21/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-30023",null,"2024-02-22","2024-02-22",null,null,null,"Sta 40-2 to Sta 42-2","100","1","Pig Runs - RES 2/22","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,40.229999999999997,null,"Sta 40-2 to Sta 42-2:  Pig Runs - RES 2/22\n--2/22/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-30025",null,"2024-02-29","2024-02-29",null,null,null,"Sta 40-2 to Sta 42-2","100","1","Pig Runs - MFL-S 2/29","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,40.25,null,"Sta 40-2 to Sta 42-2:  Pig Runs - MFL-S 2/29\n--2/29/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-94847",null,"2024-12-11","2024-12-31",null,null,null,"MLV 41-2A to MLV 42-2","100","1","Make Piggable","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,41.2,null,"MLV 41-2A to MLV 42-2:  Make Piggable\n--12/11/24 through 12/31/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-30028",null,"2024-07-30","2024-08-02",null,null,null,"Sta 42-2BL to Sta 47-2S","100","1","Pig Runs - Chem Cleaning 7/30 to 8/2","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,42.2,null,"Sta 42-2BL to Sta 47-2S:  Pig Runs - Chem Cleaning 7/30 to 8/2\n--7/30/24 through 8/2/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-65372",null,"2024-08-02","2024-08-02",null,null,null,"Sta 42-2BL to Sta 47-2S","100","0","Pig Runs - Gauge 8/2","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,42.204999999999998,null,"Sta 42-2BL to Sta 47-2S:  Pig Runs - Gauge 8/2\n--8/2/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-30032",null,"2024-08-06","2024-08-06",null,null,null,"Sta 42-2BL to Sta 47-2S","100","1","Pig Runs - MFL-A 8/6","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,42.21,null,"Sta 42-2BL to Sta 47-2S:  Pig Runs - MFL-A 8/6\n--8/6/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-30035",null,"2024-08-08","2024-08-08",null,null,null,"Sta 42-2BL to Sta 47-2S","100","1","Pig Runs - RES 8/8","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,42.22,null,"Sta 42-2BL to Sta 47-2S:  Pig Runs - RES 8/8\n--8/8/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-30038",null,"2024-08-13","2024-08-13",null,null,null,"Sta 42-2BL to Sta 47-2S","100","1","Pig Runs - MFL-C 8/13","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,42.23,null,"Sta 42-2BL to Sta 47-2S:  Pig Runs - MFL-C 8/13\n--8/13/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-30039",null,"2024-08-15","2024-08-15",null,null,null,"Sta 42-2BL to Sta 47-2S","100","1","Pig Runs - EMAT 8/15","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,42.24,null,"Sta 42-2BL to Sta 47-2S:  Pig Runs - EMAT 8/15\n--8/15/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-1130417",null,"2024-04-16","2024-04-22",null,null,null,"Bear Creek Storage","100","1","Shut-in Test","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","460017 STORAGE – BEAR CREEK",43,null,"Bear Creek Storage:  Shut-in Test\n--4/16/24 through 4/22/24:  This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.  Potential out of path restrictions may be at risk.\n460017 STORAGE – BEAR CREEK\n………………………………"]
["X23-1130419",null,"2024-10-15","2024-10-21",null,null,null,"Bear Creek Storage","100","1","Shut-in Test","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","460017 STORAGE – BEAR CREEK",43.000999999999998,null,"Bear Creek Storage:  Shut-in Test\n--10/15/24 through 10/21/24:  This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.  Potential out of path restrictions may be at risk.\n460017 STORAGE – BEAR CREEK\n………………………………"]
["X23-1120030",null,"2024-04-16","2024-04-22",null,null,null,"MLVS 43A-100","100","1","Replace Valve","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,43.1,null,"MLVS 43A-100:  Replace Valve\n--4/16/24 through 4/22/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-140932","***","2024-09-10","2024-09-10","Added",null,null,"Sta 47 West Monroe","100","1","Annual ESD","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,47,"------","***Sta 47 West Monroe:  Annual ESD\n--9/10/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X23-643018","***","2023-09-04","2024-02-07","Completed",null,null,"Sta 47","100","1","Unit 1C - Power Side Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,47.034999999999997,"------","***Sta 47:  Unit 1C - Power Side Overhaul\n***Completed"]
["X24-43765",null,"2024-03-27","2024-03-27",null,null,null,"MLV 47-1D to MLV 54-1S","100","1","Pig Runs - Cleaning/Gauge 3/27","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,47.1,null,"MLV 47-1D to MLV 54-1S:  Pig Runs - Cleaning/Gauge 3/27\n--3/27/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43767",null,"2024-04-02","2024-04-02",null,null,null,"MLV 47-1D to MLV 54-1S","100","1","Pig Runs - Caliper 4/2","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,47.11,null,"MLV 47-1D to MLV 54-1S:  Pig Runs - Caliper 4/2\n--4/2/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43769",null,"2024-04-04","2024-04-04",null,null,null,"MLV 47-1D to MLV 54-1S","100","1","Pig Runs - MDS 4/4","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,47.12,null,"MLV 47-1D to MLV 54-1S:  Pig Runs - MDS 4/4\n--4/4/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43770",null,"2024-04-09","2024-04-09",null,null,null,"MLV 47-1D to MLV 54-1S","100","1","Pig Runs - AFD (MFL-C) 4/9","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,47.13,null,"MLV 47-1D to MLV 54-1S:  Pig Runs - AFD (MFL-C) 4/9\n--4/9/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43771",null,"2024-04-11","2024-04-11",null,null,null,"MLV 47-1D to MLV 54-1S","100","1","Pig Runs - EMAT 4/11","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,47.14,null,"MLV 47-1D to MLV 54-1S:  Pig Runs - EMAT 4/11\n--4/11/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-27973",null,"2024-03-06","2024-03-15",null,null,null,"MLV 47-3A to MLV 48-3","100","1","Class Change","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,47.3,null,"MLV 47-3A to MLV 48-3:  Class Change\n--3/6/24 through 3/15/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-138238","***","2024-10-08","2024-10-08","Added",null,null,"Sta 54 Greenville","100","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,54,"------","***Sta 54 Greenville:  Annual ESD Test\n--10/8/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X22-583201",null,"2023-01-09","2024-04-26",null,null,null,"Sta 54","100","1","Unit 1B - GHG Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,54.017000000000003,null,"Sta 54:  Unit 1B - GHG Inspection\n--1/9/23 through 4/26/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-138230","***","2024-09-23","2024-09-23","Added",null,null,"Sta 63 Batesville","100","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,63,"------","***Sta 63 Batesville:  Annual ESD Test\n--9/23/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-64059","***","2024-02-12","2024-02-16","Project Change","2024-02-05","2024-02-09","Sta 63","100","1","Unit 2D - Power Cylinder","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,63.05,"--start_date--end_date------------model_loc--","***Sta 63:  Unit 2D - Power Cylinder\n--2/12/24 through 2/16/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 2/5/24 to 2/9/24.\n………………………………"]
["X24-41534",null,"2024-08-01","2024-08-01",null,null,null,"MLV 63-2S to MLV 54-2D","100","1","Pig Runs - Cleaning/Gauge 8/1","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,63.2,null,"MLV 63-2S to MLV 54-2D:  Pig Runs - Cleaning/Gauge 8/1\n--8/1/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-41535",null,"2024-08-06","2024-08-06",null,null,null,"MLV 63-2S to MLV 54-2D","100","1","Pig Runs - AFD 8/6","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,63.21,null,"MLV 63-2S to MLV 54-2D:  Pig Runs - AFD 8/6\n--8/6/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-41536",null,"2024-08-08","2024-08-08",null,null,null,"MLV 63-2S to MLV 54-2D","100","1","Pig Runs - EMAT 8/8","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,63.22,null,"MLV 63-2S to MLV 54-2D:  Pig Runs - EMAT 8/8\n--8/8/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-62404",null,"2024-03-12","2024-03-17",null,null,null,"MLV 69-1 to MLV 70-1","100","1","Meter Filter Seperator (Pin 420948 Magnolia Benton)","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","420948 TVA/TGP MAGNOLIA BENTON",69.099999999999994,null,"MLV 69-1 to MLV 70-1:  Meter Filter Seperator (Pin 420948 Magnolia Benton)\n--3/12/24 through 3/17/24:  This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.  Potential out of path restrictions may be at risk.\n420948 TVA/TGP MAGNOLIA BENTON\n………………………………"]
["X24-140857","***","2024-05-08","2024-05-08","Added",null,null,"Sta 71 Middleton","100","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,71,"------","***Sta 71 Middleton:  Annual ESD Test\n--5/8/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X23-1196655",null,"2023-11-28","2024-03-30",null,null,null,"Sta 71","100","1","Unit 3A - Discharge Bottle Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,71.033000000000001,null,"Sta 71:  Unit 3A - Discharge Bottle Inspection\n--11/28/23 through 3/30/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-140860","***","2024-05-10","2024-05-10","Added",null,null,"Sta 79 Lobelville","100","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,79,"------","***Sta 79 Lobelville:  Annual ESD Test\n--5/10/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-41517",null,"2024-04-02","2024-04-02",null,null,null,"MLV 79-2S to MLV 71-2D","100","1","Pig Runs - Cleaning/Gauge 4/2","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,79.2,null,"MLV 79-2S to MLV 71-2D:  Pig Runs - Cleaning/Gauge 4/2\n--4/2/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-41521",null,"2024-04-04","2024-04-04",null,null,null,"MLV 79-2S to MLV 71-2D","100","1","Pig Runs - MDS 4/4","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,79.209999999999994,null,"MLV 79-2S to MLV 71-2D:  Pig Runs - MDS 4/4\n--4/4/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-140918","***","2024-08-09","2024-08-09","Added",null,null,"Sta 87 Portland","100","2","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,87,"------","***Sta 87 Portland:  Annual ESD Test\n--8/9/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-92818",null,"2024-02-13","2024-02-15",null,null,null,"Sta 87","100","2","Building E - Coupling Alignment","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,87.064999999999998,null,"Sta 87:  Building E - Coupling Alignment\n--2/13/24 through 2/15/24:  This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-126033","***","2024-04-15","2024-05-31","Added",null,null,"MLV 87-1 to MLV 89-1","100","2","High Priority Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,87.1,"------","***MLV 87-1 to MLV 89-1:  High Priority Anomaly Remediation\n--4/15/24 through 5/31/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-56057","***","2024-07-16","2024-07-16","Project Change",null,null,"MLV 87-1S to MLV 82-1C","100","2","Pig Runs - Cleaning 7/16/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,87.1,"------------prl----model_loc--","***MLV 87-1S to MLV 82-1C:  Pig Runs - Cleaning 7/16/24\n--7/16/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Project Change\n………………………………"]
["X24-56058","***","2024-07-18","2024-07-18","Project Change",null,null,"MLV 87-1S to MLV 82-1C","100","1","Pig Runs - Caliper/IMU/Low Field/MFL-A/MFL-S 7/18/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,87.11,"------------prl----model_loc--","***MLV 87-1S to MLV 82-1C:  Pig Runs - Caliper/IMU/Low Field/MFL-A/MFL-S 7/18/24\n--7/18/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Project Change\n………………………………"]
["X24-32416","***","2024-04-15","2024-05-03","Project Change","2024-01-29","2024-02-04","MLV 90-1 to MLV 92-1","100","2","High Priority Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,90.1,"--start_date--end_date------------model_loc--","***MLV 90-1 to MLV 92-1:  High Priority Anomaly Remediation\n--4/15/24 through 5/3/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 1/29/24 to 2/4/24.\n………………………………"]
["X24-32417","***","2024-05-04","2024-05-10","Project Change","2024-02-05","2024-02-11","MLV 93-1 to MLV 94-1","100","2","High Priority Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,93.1,"--start_date--end_date------------model_loc--","***MLV 93-1 to MLV 94-1:  High Priority Anomaly Remediation\n--5/4/24 through 5/10/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 2/5/24 to 2/11/24.\n………………………………"]
["X24-32418","***","2024-05-11","2024-05-17","Project Change","2024-02-12","2024-02-18","MLV 95-1 to MLV 96-1","100","2","High Priority Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,95.1,"--start_date--end_date------------model_loc--","***MLV 95-1 to MLV 96-1:  High Priority Anomaly Remediation\n--5/11/24 through 5/17/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 2/12/24 to 2/18/24.\n………………………………"]
["X24-144118","***","2024-05-06","2024-05-08","Added",null,null,"Sta 96","100","2","Annual Substation Inspection - D Building","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,96,"------","***Sta 96:  Annual Substation Inspection - D Building\n--5/6/24 through 5/8/24:  This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-140915","***","2024-05-09","2024-05-10","Added",null,null,"Sta 96 Campbellsville","100","2","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,96.000100000000003,"------","***Sta 96 Campbellsville:  Annual ESD Test\n--5/9/24 through 5/10/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-95145",null,"2024-02-12","2024-02-16",null,null,null,"Sta 96","100","2","Unit 3C - Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,96.034999999999997,null,"Sta 96:  Unit 3C - Engine Inspection\n--2/12/24 through 2/16/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-75022",null,"2024-04-02","2024-05-31",null,null,null,"MLV 97-5 to MLV 98-5","100","2","Class Change","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,97.5,null,"MLV 97-5 to MLV 98-5:  Class Change\n--4/2/24 through 5/31/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-55873",null,"2024-09-24","2024-09-26",null,null,null,"MLV 101-1 to MLV 96-1","100","2","Pig Runs - Caliper/IMU/MFL-A 9/24 to 9/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,101.1,null,"MLV 101-1 to MLV 96-1:  Pig Runs - Caliper/IMU/MFL-A 9/24 to 9/26\n--9/24/24 through 9/26/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-75021",null,"2024-04-02","2024-04-20",null,null,null,"MLV 103-4 to MLV 104-4","100","2","Class Change","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,103.4,null,"MLV 103-4 to MLV 104-4:  Class Change\n--4/2/24 through 4/20/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-32467",null,"2024-12-03","2024-12-06",null,null,null,"MLV 105-1 to MLV 102-1","100","2","Pig Runs - Cleaning 12/3 to 12/6","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,105.1,null,"MLV 105-1 to MLV 102-1:  Pig Runs - Cleaning 12/3 to 12/6\n--12/3/24 through 12/6/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-32468","***","2024-12-10","2024-12-12","Project Change","2024-09-10",null,"MLV 105-1 to MLV 102-1","100","2","Pig Runs - MFL-A 12/10 to 12/12","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,105.11,"--start_date--------------model_loc--","***MLV 105-1 to MLV 102-1:  Pig Runs - MFL-A 12/10 to 12/12\n--12/10/24 through 12/12/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/10/24 to 12/12/24.\n………………………………"]
["X24-32469",null,"2024-12-19","2024-12-19",null,null,null,"MLV 105-1 to MLV 102-1","100","2","Pig Runs - MFL-S 12/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,105.12,null,"MLV 105-1 to MLV 102-1:  Pig Runs - MFL-S 12/19\n--12/19/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-32470",null,"2024-12-17","2024-12-17",null,null,null,"MLV 105-1 to MLV 102-1","100","2","Pig Runs - AFD 12/17","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,105.13,null,"MLV 105-1 to MLV 102-1:  Pig Runs - AFD 12/17\n--12/17/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-32471",null,"2024-12-20","2024-12-20",null,null,null,"MLV 105-1 to MLV 102-1","100","2","Pig Runs - EMAT 12/20","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,105.14,null,"MLV 105-1 to MLV 102-1:  Pig Runs - EMAT 12/20\n--12/20/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-138188","***","2024-04-01","2024-04-04","Added",null,null,"Sta 106 Clay City","100","2","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106,"------","***Sta 106 Clay City:  Annual ESD Test & Maintenance\n--4/1/24 through 4/4/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-38967",null,"2024-06-04","2024-06-06",null,null,null,"Sta 106","100","2","Unit 1D - 4k Hr Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106.04900000000001,null,"Sta 106:  Unit 1D - 4k Hr Inspection\n--6/4/24 through 6/6/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-38969",null,"2024-12-03","2024-12-05",null,null,null,"Sta 106","100","2","Unit 1D - 4k Hr Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106.0491,null,"Sta 106:  Unit 1D - 4k Hr Inspection\n--12/3/24 through 12/5/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-38963",null,"2024-07-23","2024-07-25",null,null,null,"Sta 106","100","2","Unit 2D - 8k Hr Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106.0501,null,"Sta 106:  Unit 2D - 8k Hr Inspection\n--7/23/24 through 7/25/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-390948","***","2023-02-20","2024-03-29","Completed",null,null,"MLV 106-3C to MLV 107-3","100","2","Class Change","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106.3,"------","***MLV 106-3C to MLV 107-3:  Class Change\n***Completed"]
["X24-138206","***","2024-11-03","2024-11-03","Added",null,null,"Sta 107A North Means","100","2","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,107,"------","***Sta 107A North Means:  Annual ESD Test\n--11/3/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-138191","***","2024-07-15","2024-07-19","Added",null,null,"Sta 110 Morehead","100","2","Annual ESD Test & Substation Inspection","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,110,"------","***Sta 110 Morehead:  Annual ESD Test & Substation Inspection\n--7/15/24 through 7/19/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-138213","***","2024-04-15","2024-04-26","Added",null,null,"Sta 110","100","2","ESD Modification","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,110.0001,"------","***Sta 110:  ESD Modification\n--4/15/24 through 4/26/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-32443",null,"2024-07-18","2024-07-18",null,null,null,"MLV 110-4 to MLV 106-4","100","2","Pig Runs - Cleaning / Gauge 7/18/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,110.4,null,"MLV 110-4 to MLV 106-4:  Pig Runs - Cleaning / Gauge 7/18/24\n--7/18/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-32445",null,"2024-07-23","2024-07-23",null,null,null,"MLV 110-4 to MLV 106-4","100","2","Pig Runs - AFD 7/23/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,110.41,null,"MLV 110-4 to MLV 106-4:  Pig Runs - AFD 7/23/24\n--7/23/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-32446",null,"2024-07-25","2024-07-25",null,null,null,"MLV 110-4 to MLV 106-4","100","2","Pig Runs - EMAT 7/25/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,110.42,null,"MLV 110-4 to MLV 106-4:  Pig Runs - EMAT 7/25/24\n--7/25/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-374735",null,"2024-04-01","2024-04-20",null,null,null,"MLV 114-3A to MLV 115-3","100","3","Drip Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,114.3,null,"MLV 114-3A to MLV 115-3:  Drip Replacement\n--4/1/24 through 4/20/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X23-1155826",null,"2024-03-26","2024-03-26",null,null,null,"MLV 114-6 to MLV 110-6","100","2","Pig Run - Clean/Gauge 3/26/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,114.61,null,"MLV 114-6 to MLV 110-6:  Pig Run - Clean/Gauge 3/26/24\n--3/26/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-1155828",null,"2024-03-28","2024-03-28",null,null,null,"MLV 114-6 to MLV 110-6","100","2","Pig Run - AFD 3/28/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,114.62,null,"MLV 114-6 to MLV 110-6:  Pig Run - AFD 3/28/24\n--3/28/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-1155829",null,"2024-04-02","2024-04-02",null,null,null,"MLV 114-6 to MLV 110-6","100","2","Pig Run - EMAT 4/2/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,114.63,null,"MLV 114-6 to MLV 110-6:  Pig Run - EMAT 4/2/24\n--4/2/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-138211","***","2024-08-26","2024-08-27","Added",null,null,"Sta 118A Tyler Mountain","100","3","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,118,"------","***Sta 118A Tyler Mountain:  Annual ESD Test\n--8/26/24 through 8/27/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-138186","***","2024-08-12","2024-08-13","Added",null,null,"Sta 119A Rocky Fork","100","3","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,119,"------","***Sta 119A Rocky Fork:  Annual ESD Test\n--8/12/24 through 8/13/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-138169","***","2024-05-20","2024-05-24","Added",null,null,"Sta 119","100","3","Unit 1A - Turbine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,119.001,"------","***Sta 119:  Unit 1A - Turbine Inspection\n--5/20/24 through 5/24/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-138202","***","2024-06-11","2024-06-14","Added",null,null,"Sta 200 Greenup","200","4","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,200,"------","***Sta 200 Greenup:  Annual ESD Test\n--6/11/24 through 6/14/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-45836",null,"2024-03-04","2024-03-08",null,null,null,"Sta 200","200","4","Unit 2A - Compressor Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,200.00200000000001,null,"Sta 200:  Unit 2A - Compressor Inspection\n--3/4/24 through 3/8/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-126026","***","2024-02-05","2024-02-09","Completed",null,null,"Sta 200","200","4","Unit 3A - Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,200.00299999999999,"------","***Sta 200:  Unit 3A - Engine Inspection\n***Completed"]
["X24-38949","***","2024-01-29","2024-02-02","Completed",null,null,"Sta 200","200","4","Unit 5A - Turbo Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,200.005,"------","***Sta 200:  Unit 5A - Turbo Replacement\n***Completed"]
["X24-30187",null,"2024-02-19","2024-02-23",null,null,null,"Sta 200","200","4","Unit 6A - Annual Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,200.006,null,"Sta 200:  Unit 6A - Annual Engine Inspection\n--2/19/24 through 2/23/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-30186",null,"2024-02-12","2024-02-16",null,null,null,"Sta 200","200","4","Unit 7A - Annual Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,200.00700000000001,null,"Sta 200:  Unit 7A - Annual Engine Inspection\n--2/12/24 through 2/16/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-30184",null,"2024-02-26","2024-03-01",null,null,null,"Sta 200","200","4","Unit 11A - Annual Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,200.011,null,"Sta 200:  Unit 11A - Annual Engine Inspection\n--2/26/24 through 3/1/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-32448",null,"2024-07-30","2024-07-30",null,null,null,"MLV 200-2 to MLV 110-4","100","2","Pig Runs - Cleaning / Gauge 7/30/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,200.2,null,"MLV 200-2 to MLV 110-4:  Pig Runs - Cleaning / Gauge 7/30/24\n--7/30/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-32450",null,"2024-08-01","2024-08-01",null,null,null,"MLV 200-2 to MLV 110-4","100","2","Pig Runs - AFD 8/1/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,200.21,null,"MLV 200-2 to MLV 110-4:  Pig Runs - AFD 8/1/24\n--8/1/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-32451",null,"2024-08-06","2024-08-06",null,null,null,"MLV 200-2 to MLV 110-4","100","2","Pig Runs - EMAT 8/6/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,200.22,null,"MLV 200-2 to MLV 110-4:  Pig Runs - EMAT 8/6/24\n--8/6/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-74909",null,"2024-04-01","2024-04-04",null,null,null,"Sta 204","200","4","Unit 4A - Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,204.00399999999999,null,"Sta 204:  Unit 4A - Crankcase Inspection\n--4/1/24 through 4/4/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-980173",null,"2024-02-26","2024-02-29",null,null,null,"Sta 204","200","4","Unit 5A - Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,204.005,null,"Sta 204:  Unit 5A - Crankcase Inspection\n--2/26/24 through 2/29/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-928217",null,"2024-03-04","2024-03-07",null,null,null,"Sta 204","200","4","Unit 6A - Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,204.006,null,"Sta 204:  Unit 6A - Crankcase Inspection\n--3/4/24 through 3/7/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-928216",null,"2024-02-19","2024-02-22",null,null,null,"Sta 204","200","4","Unit 7A - Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,204.00700000000001,null,"Sta 204:  Unit 7A - Crankcase Inspection\n--2/19/24 through 2/22/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-1155833",null,"2024-02-12","2024-02-15",null,null,null,"Sta 204","200","4","Unit 8A - Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,204.00800000000001,null,"Sta 204:  Unit 8A - Crankcase Inspection\n--2/12/24 through 2/15/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-25445","***","2024-01-29","2024-02-08","Completed",null,null,"Sta 204","200","4","Unit 9A - Punch Carbon","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,204.00899999999999,"------","***Sta 204:  Unit 9A - Punch Carbon\n***Completed"]
["X24-25447",null,"2024-03-11","2024-03-20",null,null,null,"Sta 204","200","4","Unit 11A - Controls Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,204.011,null,"Sta 204:  Unit 11A - Controls Upgrade\n--3/11/24 through 3/20/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-1167409",null,"2024-02-05","2024-02-14",null,null,null,"Sta 204","200","4","Unit 12A - Controls Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,204.012,null,"Sta 204:  Unit 12A - Controls Upgrade\n--2/5/24 through 2/14/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-1026448",null,"2024-03-19","2024-03-19",null,null,null,"MLV 204-1 to MLV 200-1","200","4","Pig Runs - Cleaning / Gauge 3/19/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,204.1,null,"MLV 204-1 to MLV 200-1:  Pig Runs - Cleaning / Gauge 3/19/24\n--3/19/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-1026449",null,"2024-03-21","2024-03-22",null,null,null,"MLV 204-1 to MLV 200-1","200","4","Pig Runs - EMAT 3/21/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,204.11,null,"MLV 204-1 to MLV 200-1:  Pig Runs - EMAT 3/21/24\n--3/21/24 through 3/22/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-1026453",null,"2024-07-09","2024-07-09",null,null,null,"MLV 204-2 to MLV 200-2","200","4","Pig Runs - Cleaning / Gauge 7/9/23","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,204.2,null,"MLV 204-2 to MLV 200-2:  Pig Runs - Cleaning / Gauge 7/9/23\n--7/9/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-1026454",null,"2024-07-11","2024-07-11",null,null,null,"MLV 204-2 to MLV 200-2","200","4","Pig Runs - AFD 7/11/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,204.21,null,"MLV 204-2 to MLV 200-2:  Pig Runs - AFD 7/11/24\n--7/11/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-1026455",null,"2024-07-16","2024-07-16",null,null,null,"MLV 204-2 to MLV 200-2","200","4","Pig Runs - EMAT 5/16/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,204.22,null,"MLV 204-2 to MLV 200-2:  Pig Runs - EMAT 5/16/24\n--7/16/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-1026450",null,"2024-04-09","2024-04-09",null,null,null,"MLV 204-3 to MLV 200-3B","200","4","Pig Runs - Cleaning / Gauge 4/9/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,204.3,null,"MLV 204-3 to MLV 200-3B:  Pig Runs - Cleaning / Gauge 4/9/24\n--4/9/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-32441",null,"2024-04-16","2024-04-16",null,null,null,"MLV 204-3 to MLV 200-3B","200","4","Pig Runs - RES 4/16/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,204.3,null,"MLV 204-3 to MLV 200-3B:  Pig Runs - RES 4/16/24\n--4/16/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-1026452",null,"2024-04-11","2024-04-11",null,null,null,"MLV 204-3 to MLV 200-3B","200","4","Pig Runs - MFL-A 4/11/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,204.31,null,"MLV 204-3 to MLV 200-3B:  Pig Runs - MFL-A 4/11/24\n--4/11/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-32452",null,"2024-08-13","2024-08-13",null,null,null,"MLV 204-4 to MLV 200-4","200","4","Pig Runs - Cleaning/Gauge 8/13/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,204.4,null,"MLV 204-4 to MLV 200-4:  Pig Runs - Cleaning/Gauge 8/13/24\n--8/13/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-32454",null,"2024-08-14","2024-08-14",null,null,null,"MLV 204-4 to MLV 200-4","200","4","Pig Runs - MFL-A 8/14/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,204.41,null,"MLV 204-4 to MLV 200-4:  Pig Runs - MFL-A 8/14/24\n--8/14/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43861",null,"2024-06-10","2024-06-18",null,null,null,"MLV 205-2 to MLV 206-2","200","4","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,205.2,null,"MLV 205-2 to MLV 206-2:  Anomaly Remediation\n--6/10/24 through 6/18/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-129299","***","2024-05-06","2024-05-09","Added",null,null,"Sta 209 Cambridge","200","4","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209,"------","***Sta 209 Cambridge:  Annual ESD Test & Maintenance\n--5/6/24 through 5/9/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-25504","***","2024-02-19","2024-02-22","Project Change","2024-02-05","2024-02-08","Sta 209","200","4","Unit 1A - Punch Carbon","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209.001,"--start_date--end_date------------model_loc--","***Sta 209:  Unit 1A - Punch Carbon\n--2/19/24 through 2/22/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 2/5/24 to 2/8/24.\n………………………………"]
["X24-25505","***","2024-02-26","2024-02-29","Project Change","2024-02-12","2024-02-15","Sta 209","200","4","Unit 2A - Punch Carbon","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209.00200000000001,"--start_date--end_date------------model_loc--","***Sta 209:  Unit 2A - Punch Carbon\n--2/26/24 through 2/29/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 2/12/24 to 2/15/24.\n………………………………"]
["X24-25506","***","2024-03-04","2024-03-07","Project Change","2024-02-19","2024-02-22","Sta 209","200","4","Unit 3A - Punch Carbon","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209.00299999999999,"--start_date--end_date------------model_loc--","***Sta 209:  Unit 3A - Punch Carbon\n--3/4/24 through 3/7/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 2/19/24 to 2/22/24.\n………………………………"]
["X24-38822","***","2024-03-18","2024-03-21","Project Change","2024-02-26","2024-02-29","Sta 209","200","4","Unit 5A - Punch Carbon","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209.005,"--start_date--end_date------------model_loc--","***Sta 209:  Unit 5A - Punch Carbon\n--3/18/24 through 3/21/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 2/26/24 to 2/29/24.\n………………………………"]
["X24-74910","***","2024-03-25","2024-03-28","Project Change","2024-03-04","2024-03-07","Sta 209","200","4","Unit 6A - Punch Carbon","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209.006,"--start_date--end_date------------model_loc--","***Sta 209:  Unit 6A - Punch Carbon\n--3/25/24 through 3/28/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 3/4/24 to 3/7/24.\n………………………………"]
["X23-910728","***","2024-03-11","2024-03-14","Project Change","2024-03-04","2024-03-07","Sta 209","200","4","Unit 8A - Replace OP Turbo & Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209.00800000000001,"--start_date--end_date------------model_loc--","***Sta 209:  Unit 8A - Replace OP Turbo & Crankcase Inspection\n--3/11/24 through 3/14/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 3/4/24 to 3/7/24.\n………………………………"]
["X24-25502","***","2024-01-29","2024-02-15","Project Change",null,"2024-02-08","Sta 209","200","4","Unit 11A - Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209.011,"----end_date------------model_loc--","***Sta 209:  Unit 11A - Crankcase Inspection\n--1/29/24 through 2/15/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 1/29/24 to 2/8/24.\n………………………………"]
["X23-961737",null,"2023-09-21","2024-03-29",null,null,null,"Sta 214","200","4","Unit 8A - Oil System","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,214.00800000000001,null,"Sta 214:  Unit 8A - Oil System\n--9/21/23 through 3/29/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43774",null,"2023-12-13","2024-03-30",null,null,null,"Sta 214","200","4","Unit 10A - Compressor Liner Retaining Ring","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,214.01,null,"Sta 214:  Unit 10A - Compressor Liner Retaining Ring\n--12/13/23 through 3/30/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-76730","***","2024-01-29","2024-02-01","Completed",null,null,"Sta 214","200","4","Unit 11A - Power Side WO","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,214.011,"------","***Sta 214:  Unit 11A - Power Side WO\n***Completed"]
["X24-144191","***","2024-02-06","2024-02-29","Added",null,null,"Sta 214","200","4","Unit 13A - Fuel Control Module","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,214.01300000000001,"------","***Sta 214:  Unit 13A - Fuel Control Module\n--2/6/24 through 2/29/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X23-642933",null,"2024-04-08","2024-04-12",null,null,null,"MLV 216-3 to MLV 217-3","200","4","Hot Tap for New Meter Station - Petersburgh Mahoning Meter","This project may require reducing the pipeline section pressure.  Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,216.3,null,"MLV 216-3 to MLV 217-3:  Hot Tap for New Meter Station - Petersburgh Mahoning Meter\n--4/8/24 through 4/12/24:  This project may require reducing the pipeline section pressure.  Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-642934",null,"2024-04-15","2024-04-19",null,null,null,"MLV 216-4 to MLV 217-4","200","4","Hot Tap for New Meter Station - Petersburgh Mahoning Meter","This project may require reducing the pipeline section pressure.  Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,216.4,null,"MLV 216-4 to MLV 217-4:  Hot Tap for New Meter Station - Petersburgh Mahoning Meter\n--4/15/24 through 4/19/24:  This project may require reducing the pipeline section pressure.  Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43866",null,"2024-04-11","2024-04-11",null,null,null,"MLV 219-3 to MLV 214-3","200","4","Pig Runs - Cleaning 4/11","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,219.3,null,"MLV 219-3 to MLV 214-3:  Pig Runs - Cleaning 4/11\n--4/11/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43868",null,"2024-04-16","2024-04-16",null,null,null,"MLV 219-3 to MLV 214-3","200","4","Pig Runs - AFD 4/16","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,219.31,null,"MLV 219-3 to MLV 214-3:  Pig Runs - AFD 4/16\n--4/16/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43872",null,"2024-04-18","2024-04-18",null,null,null,"MLV 219-3 to MLV 214-3","200","4","Pig Runs - EMAT 4/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,219.32,null,"MLV 219-3 to MLV 214-3:  Pig Runs - EMAT 4/18\n--4/18/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-27517",null,"2024-07-08","2024-07-26",null,null,null,"MLV 226-1 TO MLV 227-1","200","4","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,226.1,null,"MLV 226-1 TO MLV 227-1:  Pipe Replacement\n--7/8/24 through 7/26/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-92834",null,"2024-02-12","2024-02-14",null,null,null,"Sta 233","200","5","Unit 1B - Valve Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,233.017,null,"Sta 233:  Unit 1B - Valve Replacement\n--2/12/24 through 2/14/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-95144","***","2024-04-16","2024-04-16","Completed",null,null,"Sta 254","200","5","Unit 2B - Emissions Testing","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,254.018,"------","***Sta 254:  Unit 2B - Emissions Testing\n***Completed"]
["X24-27502",null,"2024-06-04","2024-06-04",null,null,null,"MLV 260A-101.1 TO MLV 260A-103","200","6","Pig Runs - Cleaning/Gauge: 6/4","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,260.10000000000002,null,"MLV 260A-101.1 TO MLV 260A-103:  Pig Runs - Cleaning/Gauge: 6/4\n--6/4/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-27505",null,"2024-06-05","2024-06-05",null,null,null,"MLV 260A-101.1 TO MLV 260A-103","200","6","Pig Runs - MFL-C: 6/5","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,260.11,null,"MLV 260A-101.1 TO MLV 260A-103:  Pig Runs - MFL-C: 6/5\n--6/5/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-95132","***","2024-02-01","2024-02-01","Completed",null,null,"Sta 261","200","6","Unit 1C - BAM Commissioning","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,261.03300000000002,"------","***Sta 261:  Unit 1C - BAM Commissioning\n***Completed"]
["X24-27460",null,"2024-03-20","2024-03-20",null,null,null,"MLV 264B-101.2 to MLV 264B-101.2BR","200","6","Pig Run - Cleaning/Gauge 3/20","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,264.10000000000002,null,"MLV 264B-101.2 to MLV 264B-101.2BR:  Pig Run - Cleaning/Gauge 3/20\n--3/20/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-27465",null,"2024-03-20","2024-03-20",null,null,null,"MLV 264B-101.2 to MLV 264B-101.2BR","200","6","Pig Run - MFL-A 3/20","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,264.11,null,"MLV 264B-101.2 to MLV 264B-101.2BR:  Pig Run - MFL-A 3/20\n--3/20/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-27477",null,"2024-04-02","2024-04-02",null,null,null,"MLV 267-1 to 270C-101","200","6","Pig Run - Cleaning/Gauge 4/2/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,267.10000000000002,null,"MLV 267-1 to 270C-101:  Pig Run - Cleaning/Gauge 4/2/24\n--4/2/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-27479",null,"2024-04-09","2024-04-09",null,null,null,"MLV 267-1 to 270C-101",null,null,"Pig Run - MFL-C 4/9/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,267.11,null,"MLV 267-1 to 270C-101:  Pig Run - MFL-C 4/9/24\n--4/9/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-27480",null,"2024-09-17","2024-09-17",null,null,null,"MLV 267-1 to 270C-101","200","6","Pig Run - EMAT 9/17/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,267.12,null,"MLV 267-1 to 270C-101:  Pig Run - EMAT 9/17/24\n--9/17/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-746426",null,"2024-04-16","2024-04-17",null,null,null,"MLVS 268A-100","200","6","Meter Station Upgrade - Hudson Gate (Pin: 420204)","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","420204\tNSTAR/TGP HUDSON MA MIDDLESEX",268.10000000000002,null,"MLVS 268A-100:  Meter Station Upgrade - Hudson Gate (Pin: 420204)\n--4/16/24 through 4/17/24:  This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.  Potential out of path restrictions may be at risk.\n420204\tNSTAR/TGP HUDSON MA MIDDLESEX\n………………………………"]
["X24-27473",null,"2024-03-25","2024-03-25",null,null,null,"MLV 268A-101 to 268A-103","200","6","Pig Run - Cleaning/Gauge 3/25/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,268.11,null,"MLV 268A-101 to 268A-103:  Pig Run - Cleaning/Gauge 3/25/24\n--3/25/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-27474",null,"2024-03-26","2024-03-26",null,null,null,"MLV 268A-101 to 268A-103","200","6","Pig Run - Cal/IMU 3/26/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,268.12,null,"MLV 268A-101 to 268A-103:  Pig Run - Cal/IMU 3/26/24\n--3/26/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-27475",null,"2024-03-28","2024-03-28",null,null,null,"MLV 268A-101 to 268A-103","200","6","Pig Run - MFL-A 3/28/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,268.13,null,"MLV 268A-101 to 268A-103:  Pig Run - MFL-A 3/28/24\n--3/28/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-27487",null,"2024-04-23","2024-04-23",null,null,null,"MLV 270C-102 TO MLV 270C-104","200","6","Pig Runs - Cleaning/Gauge 4/23","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.","420658 BOSTN/TGP PEABODY SALES ESSEX\n420118 BOSTN/TGP BEVERLY SALEM MA ESSEX",270.10000000000002,null,"MLV 270C-102 TO MLV 270C-104:  Pig Runs - Cleaning/Gauge 4/23\n--4/23/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n420658 BOSTN/TGP PEABODY SALES ESSEX\n420118 BOSTN/TGP BEVERLY SALEM MA ESSEX\n………………………………"]
["X23-913466",null,"2024-04-24","2024-04-24",null,null,null,"MLV 270C-102 TO MLV 270C-104","200","6","Pig Re-Runs - MFL-A/Cal/IMU 4/24/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420658 BOSTN/TGP PEABODY SALES ESSEX\n420118 BOSTN/TGP BEVERLY SALEM MA ESSEX",270.10000000000002,null,"MLV 270C-102 TO MLV 270C-104:  Pig Re-Runs - MFL-A/Cal/IMU 4/24/24\n--4/24/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n420658 BOSTN/TGP PEABODY SALES ESSEX\n420118 BOSTN/TGP BEVERLY SALEM MA ESSEX\n………………………………"]
["X24-27509",null,"2024-07-15","2024-07-15",null,null,null,"MLV 270C-101 TO MLV 270C-102","200","6","Pig Runs - Cleaning/Gauge 7/15","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420118 BOSTN/TGP BEVERLY SALEM MA ESSEX",270.10000000000002,null,"MLV 270C-101 TO MLV 270C-102:  Pig Runs - Cleaning/Gauge 7/15\n--7/15/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n420118 BOSTN/TGP BEVERLY SALEM MA ESSEX\n………………………………"]
["X24-27552",null,"2024-07-15","2024-07-15",null,null,null,"MLV 270C-101 TO MLV 270C-102","200","6","Pig Runs - MFL-A 7/15","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420118 BOSTN/TGP BEVERLY SALEM MA ESSEX",270.12,null,"MLV 270C-101 TO MLV 270C-102:  Pig Runs - MFL-A 7/15\n--7/15/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n420118 BOSTN/TGP BEVERLY SALEM MA ESSEX\n………………………………"]
["X24-27554",null,"2024-07-15","2024-07-15",null,null,null,"MLV 270C-101 TO MLV 270C-102","200","6","Pig Runs - Cal 7/15","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420118 BOSTN/TGP BEVERLY SALEM MA ESSEX",270.13,null,"MLV 270C-101 TO MLV 270C-102:  Pig Runs - Cal 7/15\n--7/15/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n420118 BOSTN/TGP BEVERLY SALEM MA ESSEX\n………………………………"]
["X24-27484",null,"2024-04-16","2024-04-16",null,null,null,"MLV 270B-401 to 270B-402","200","6","Pig Run - Cleaning/Gauge 4/16/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,270.39999999999998,null,"MLV 270B-401 to 270B-402:  Pig Run - Cleaning/Gauge 4/16/24\n--4/16/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-27486",null,"2024-04-16","2024-04-16",null,null,null,"MLV 270B-401 to 270B-402","200","6","Pig Run - MFL-A 4/16/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,270.41000000000003,null,"MLV 270B-401 to 270B-402:  Pig Run - MFL-A 4/16/24\n--4/16/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-27495",null,"2024-05-21","2024-05-21",null,null,null,"MLV 270C-1101 TO MLV 270C-1103","200","6","Pig Runs - Cleaning/Gauge 5/21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,270.5,null,"MLV 270C-1101 TO MLV 270C-1103:  Pig Runs - Cleaning/Gauge 5/21\n--5/21/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-27499",null,"2024-05-21","2024-05-21",null,null,null,"MLV 270C-1101 TO MLV 270C-1103","200","6","Pig Runs - MFL-A 5/21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,270.51,null,"MLV 270C-1101 TO MLV 270C-1103:  Pig Runs - MFL-A 5/21\n--5/21/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-126037",null,"2024-02-12","2024-02-15",null,null,null,"Sta 307","300","4","Unit 2A - Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,307.00200000000001,null,"Sta 307:  Unit 2A - Engine Inspection\n--2/12/24 through 2/15/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43887",null,"2024-06-04","2024-06-04",null,null,null,"MLV 307-1 to MLV 219-2","300","4","Pig Runs - Cleaning 6/4","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,307.10000000000002,null,"MLV 307-1 to MLV 219-2:  Pig Runs - Cleaning 6/4\n--6/4/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43889",null,"2024-06-06","2024-06-06",null,null,null,"MLV 307-1 to MLV 219-2","300","4","Pig Runs - MFL 6/6","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,307.11,null,"MLV 307-1 to MLV 219-2:  Pig Runs - MFL 6/6\n--6/6/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43895",null,"2024-09-12","2024-09-12",null,null,null,"MLV 307-1 to MLV 219-2","300","4","Pig Runs - Cleaning 9/12","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,307.12,null,"MLV 307-1 to MLV 219-2:  Pig Runs - Cleaning 9/12\n--9/12/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43894",null,"2024-09-17","2024-09-17",null,null,null,"MLV 307-1 to MLV 219-2","300","4","Pig Runs - MFL 9/17","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,307.13,null,"MLV 307-1 to MLV 219-2:  Pig Runs - MFL 9/17\n--9/17/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43896",null,"2024-09-19","2024-09-19",null,null,null,"MLV 307-1 to MLV 219-2","300","4","Pig Runs - EMAT 9/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,307.14,null,"MLV 307-1 to MLV 219-2:  Pig Runs - EMAT 9/19\n--9/19/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43883",null,"2024-05-08","2024-05-08",null,null,null,"MLV 307-2 to MLV 219-3","300","4","Pig Runs - Cleaning 5/8","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,307.2,null,"MLV 307-2 to MLV 219-3:  Pig Runs - Cleaning 5/8\n--5/8/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43885",null,"2024-05-14","2024-05-14",null,null,null,"MLV 307-2 to MLV 219-3","300","4","Pig Runs - MFL 5/14","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,307.20999999999998,null,"MLV 307-2 to MLV 219-3:  Pig Runs - MFL 5/14\n--5/14/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43880",null,"2024-05-16","2024-05-16",null,null,null,"MLV 307-2 to MLV 219-3","300","4","Pig Runs - EMAT 5/16","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,307.22000000000003,null,"MLV 307-2 to MLV 219-3:  Pig Runs - EMAT 5/16\n--5/16/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43890",null,"2024-07-09","2024-07-09",null,null,null,"MLV 307-2 to MLV 219-3","300","4","Pig Runs - Cleaning 7/9","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,307.23,null,"MLV 307-2 to MLV 219-3:  Pig Runs - Cleaning 7/9\n--7/9/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43893",null,"2024-07-11","2024-07-11",null,null,null,"MLV 307-2 to MLV 219-3","300","4","Pig Runs - MFL 7/11","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,307.24,null,"MLV 307-2 to MLV 219-3:  Pig Runs - MFL 7/11\n--7/11/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-640122",null,"2024-04-08","2024-04-12",null,null,null,"MLV 313-1 to MLV 314-1","300","4","Hot Tap for New Meter Station - Greylock Potter Meter","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,313.10000000000002,null,"MLV 313-1 to MLV 314-1:  Hot Tap for New Meter Station - Greylock Potter Meter\n--4/8/24 through 4/12/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43965",null,"2024-06-19","2024-06-19",null,null,null,"MLVS 313A-100 Recovery Line","300","4","Pig Runs - Cleaning 6/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,313.10000000000002,null,"MLVS 313A-100 Recovery Line:  Pig Runs - Cleaning 6/19\n--6/19/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43967",null,"2024-06-20","2024-06-20",null,null,null,"MLVS 313A-100 Recovery Line","300","4","Pig Runs - MFL 6/20","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,313.11,null,"MLVS 313A-100 Recovery Line:  Pig Runs - MFL 6/20\n--6/20/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-640124",null,"2024-04-15","2024-04-19",null,null,null,"MLV 313-2 to MLV 314-2","300","4","Hot Tap for New Meter Station - Greylock Potter Meter","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,313.2,null,"MLV 313-2 to MLV 314-2:  Hot Tap for New Meter Station - Greylock Potter Meter\n--4/15/24 through 4/19/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43901",null,"2024-07-23","2024-07-23",null,null,null,"MLV 313-2 to MLV 307-2","300","4","Pig Runs - Cleaning 7/23","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,313.2,null,"MLV 313-2 to MLV 307-2:  Pig Runs - Cleaning 7/23\n--7/23/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43903",null,"2024-07-25","2024-07-25",null,null,null,"MLV 313-2 to MLV 307-2","300","4","Pig Runs - MFL 7/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,313.20999999999998,null,"MLV 313-2 to MLV 307-2:  Pig Runs - MFL 7/25\n--7/25/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43925",null,"2024-04-23","2024-04-23",null,null,null,"Sta 313 to Sta 237","300","4","Pig Runs - Cleaning 4/23","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,313.49,null,"Sta 313 to Sta 237:  Pig Runs - Cleaning 4/23\n--4/23/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43929",null,"2024-04-25","2024-04-25",null,null,null,"Sta 313 to Sta 237","300","4","Pig Runs - MFL 4/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,313.49099999999999,null,"Sta 313 to Sta 237:  Pig Runs - MFL 4/25\n--4/25/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43938",null,"2024-04-30","2024-04-30",null,null,null,"Sta 313 to Sta 237","300","4","Pig Runs - EMAT 4/30","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,313.49200000000002,null,"Sta 313 to Sta 237:  Pig Runs - EMAT 4/30\n--4/30/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43910",null,"2024-06-25","2024-06-25",null,null,null,"Sta 313 to Sta 237","300","4","Pig Runs - Cleaning 6/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,313.5,null,"Sta 313 to Sta 237:  Pig Runs - Cleaning 6/25\n--6/25/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43912",null,"2024-06-27","2024-06-27",null,null,null,"Sta 313 to Sta 237","300","4","Pig Runs - MFL 6/27","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,313.51,null,"Sta 313 to Sta 237:  Pig Runs - MFL 6/27\n--6/27/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43914",null,"2024-08-12","2024-08-28",null,null,null,"MLVS C313-0608","300","4","Pig Runs (Tethered) - Cleaning 8/20","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,313.60000000000002,null,"MLVS C313-0608:  Pig Runs (Tethered) - Cleaning 8/20\n--8/12/24 through 8/28/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43917",null,"2024-08-12","2024-08-28",null,null,null,"MLVS C313-0608","300","4","Pig Runs (Tethered) - MFL 8/21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,313.61,null,"MLVS C313-0608:  Pig Runs (Tethered) - MFL 8/21\n--8/12/24 through 8/28/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-25467",null,"2024-02-14","2024-02-14",null,null,null,"Sta. 321","300","4","Low Voltage Motor Control Centers","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,321,null,"Sta. 321:  Low Voltage Motor Control Centers\n--2/14/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-25473",null,"2024-05-14","2024-06-26",null,null,null,"Sta. 323A Lackawaxen","300","5","Gas Coolers Piping, Testing, Automation Upgrade","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,321,null,"Sta. 323A Lackawaxen:  Gas Coolers Piping, Testing, Automation Upgrade\n--5/14/24 through 6/26/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-56063","***","2024-06-10","2024-06-10","Project Change",null,null,"MLV 321-1 to MLV 325-1","300","4","Pig Runs - Cleaning/Gauge 6/10/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,321.10000000000002,"------------prl----model_loc--","***MLV 321-1 to MLV 325-1:  Pig Runs - Cleaning/Gauge 6/10/24\n--6/10/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Project Change\n………………………………"]
["X24-56068","***","2024-06-12","2024-06-12","Project Change",null,null,"MLV 321-1 to MLV 325-1","300","4","Pig Runs - MFL-C 6/12/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,321.12,"------------prl----model_loc--","***MLV 321-1 to MLV 325-1:  Pig Runs - MFL-C 6/12/24\n--6/12/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Project Change\n………………………………"]
["X24-56067","***","2024-09-09","2024-09-09","Project Change",null,null,"MLV 321-1 to MLV 325-1","300","4","Pig Runs - Cleaning/Gauge 9/9/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,321.14999999999998,"------------prl----model_loc--","***MLV 321-1 to MLV 325-1:  Pig Runs - Cleaning/Gauge 9/9/24\n--9/9/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Project Change\n………………………………"]
["X24-56070","***","2024-09-11","2024-09-11","Project Change",null,null,"MLV 321-1 to MLV 325-1","300","4","Pig Runs - EMAT 9/11/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,321.16000000000003,"------------prl----model_loc--","***MLV 321-1 to MLV 325-1:  Pig Runs - EMAT 9/11/24\n--9/11/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Project Change\n………………………………"]
["X24-25471",null,"2024-02-13","2024-02-14",null,null,null,"Sta. 325","300","5","Low Voltage Motor Control Centers","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,325,null,"Sta. 325:  Low Voltage Motor Control Centers\n--2/13/24 through 2/14/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-141006","***","2024-02-12","2024-02-12","Added",null,null,"Sta 325","300","5","Unit 1B - Remove Commissioning Screens","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,325.017,"------","***Sta 325:  Unit 1B - Remove Commissioning Screens\n--2/12/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-56071","***","2024-06-25","2024-06-25","Project Change",null,null,"MLV 325-2 to MLV 328-2","300","5","Pig Runs - Cleaning/Gauge 6/25/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,325.2,"------------prl----model_loc--","***MLV 325-2 to MLV 328-2:  Pig Runs - Cleaning/Gauge 6/25/24\n--6/25/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Project Change\n………………………………"]
["X24-56073","***","2024-06-26","2024-06-26","Project Change",null,null,"MLV 325-2 to MLV 328-2","300","5","Pig Runs - Caliper/MFL-A 6/26/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,325.20999999999998,"------------prl----model_loc--","***MLV 325-2 to MLV 328-2:  Pig Runs - Caliper/MFL-A 6/26/24\n--6/26/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Project Change\n………………………………"]
["X24-65368","***","2024-07-22","2024-08-01","Project Change",null,"2024-07-31","MLV 331-1R2 to MLV 332-1R2","300","5","Pig Runs - Tethered Tools 7/22 to 7/31","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,331.2,"----end_date------------model_loc--","***MLV 331-1R2 to MLV 332-1R2:  Pig Runs - Tethered Tools 7/22 to 7/31\n--7/22/24 through 8/1/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 7/22/24 to 7/31/24.\n………………………………"]
["X24-27490",null,"2024-05-06","2024-05-07",null,null,null,"MLV 336-1 TO MLV 356-1","300","6","Pig Runs - Cleaning/Gauge 5/6 to 5/7","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,336.1,null,"MLV 336-1 TO MLV 356-1:  Pig Runs - Cleaning/Gauge 5/6 to 5/7\n--5/6/24 through 5/7/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-27492",null,"2024-05-09","2024-05-10",null,null,null,"MLV 336-1 TO MLV 356-1","300","6","Pig Runs - MFL-A 5/9 to 5/10","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,336.11,null,"MLV 336-1 TO MLV 356-1:  Pig Runs - MFL-A 5/9 to 5/10\n--5/9/24 through 5/10/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-56074","***","2024-04-30","2024-04-30","Project Change",null,null,"MLV 347A-201.1A to MLV 347A-201.1R","300","5","Pig Runs - Cleaning/Gauge 4/30/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,347.2,"------------prl----model_loc--","***MLV 347A-201.1A to MLV 347A-201.1R:  Pig Runs - Cleaning/Gauge 4/30/24\n--4/30/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Project Change\n………………………………"]
["X24-56076","***","2024-04-30","2024-04-30","Project Change",null,null,"MLV 347A-201.1A to MLV 347A-201.1R","300","5","Pig Runs - Caliper/MFL-A 4/30/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,347.21,"------------prl----model_loc--","***MLV 347A-201.1A to MLV 347A-201.1R:  Pig Runs - Caliper/MFL-A 4/30/24\n--4/30/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Project Change\n………………………………"]
["X24-56077","***","2024-05-01","2024-05-01","Project Change",null,null,"MLV 347A-201.1K to MLV 347A-201A.1","300","5","Pig Runs - Cleaning/Gauge 5/1/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,347.22,"------------prl----model_loc--","***MLV 347A-201.1K to MLV 347A-201A.1:  Pig Runs - Cleaning/Gauge 5/1/24\n--5/1/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Project Change\n………………………………"]
["X24-56078","***","2024-05-01","2024-05-01","Project Change",null,null,"MLV 347A-201.1K to MLV 347A-201A.1","300","5","Pig Runs - MFL-C 5/1/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,347.23,"------------prl----model_loc--","***MLV 347A-201.1K to MLV 347A-201A.1:  Pig Runs - MFL-C 5/1/24\n--5/1/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Project Change\n………………………………"]
["X24-56079","***","2024-05-02","2024-05-02","Project Change",null,null,"MLV 347A-201.1K to MLV 347A-201A.1","300","5","Pig Runs - Caliper/MFL-A 5/2/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,347.24,"------------prl----model_loc--","***MLV 347A-201.1K to MLV 347A-201A.1:  Pig Runs - Caliper/MFL-A 5/2/24\n--5/2/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Project Change\n………………………………"]
["X23-1259545",null,"2023-12-18","2024-03-15",null,null,null,"MLV 400-2 (Sta 1)","100","0","Emergent Repair","This project may require reducing the pipeline section pressure.  Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.","421017 - RIO BRAVO DEL\n450261 - CENEGAS DEL",400.00200000000001,null,"MLV 400-2 (Sta 1):  Emergent Repair\n--12/18/23 through 3/15/24:  This project may require reducing the pipeline section pressure.  Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n421017 - RIO BRAVO DEL\n450261 - CENEGAS DEL\n………………………………"]
["X24-76751","***","2024-03-26","2024-03-26","Project Change",null,null,"MLV 400-1 to MLV 409-1","400","0","Pig Run - Maintenance Cleaning 3/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","411884 ENRONCTR/TGP MAGNOLIA PLANT PTR MAK\n440236 MAGNOLIA CITY PLANT FUEL NUECES\n440279 VAR/TGP MAGNOLIA CITY PLANT FLARE N\n410736 VAR/TGP PETRONELLA DEHY NUECES\n016347 / 420837 TGP/TGP FALFURRIAS BROOKS\n412733 UES/TGP MYRICK BROOKS",400.1,"------------prl----model_loc--","***MLV 400-1 to MLV 409-1:  Pig Run - Maintenance Cleaning 3/26\n--3/26/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n411884 ENRONCTR/TGP MAGNOLIA PLANT PTR MAK\n440236 MAGNOLIA CITY PLANT FUEL NUECES\n440279 VAR/TGP MAGNOLIA CITY PLANT FLARE N\n410736 VAR/TGP PETRONELLA DEHY NUECES\n016347 / 420837 TGP/TGP FALFURRIAS BROOKS\n412733 UES/TGP MYRICK BROOKS\n***Project Change\n………………………………"]
["X24-76754","***","2024-05-14","2024-05-14","Project Change",null,null,"MLV 400-1 to MLV 409-1","400","0","Pig Run - Maintenance Cleaning 5/14","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","411884 ENRONCTR/TGP MAGNOLIA PLANT PTR MAK\n440236 MAGNOLIA CITY PLANT FUEL NUECES\n440279 VAR/TGP MAGNOLIA CITY PLANT FLARE N\n410736 VAR/TGP PETRONELLA DEHY NUECES\n016347 / 420837 TGP/TGP FALFURRIAS BROOKS\n412733 UES/TGP MYRICK BROOKS",400.11,"------------prl----model_loc--","***MLV 400-1 to MLV 409-1:  Pig Run - Maintenance Cleaning 5/14\n--5/14/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n411884 ENRONCTR/TGP MAGNOLIA PLANT PTR MAK\n440236 MAGNOLIA CITY PLANT FUEL NUECES\n440279 VAR/TGP MAGNOLIA CITY PLANT FLARE N\n410736 VAR/TGP PETRONELLA DEHY NUECES\n016347 / 420837 TGP/TGP FALFURRIAS BROOKS\n412733 UES/TGP MYRICK BROOKS\n***Project Change\n………………………………"]
["X24-76755","***","2024-09-17","2024-09-17","Project Change",null,null,"MLV 400-1 to MLV 409-1","400","0","Pig Run - Maintenance Cleaning 9/17","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","411884 ENRONCTR/TGP MAGNOLIA PLANT PTR MAK\n440236 MAGNOLIA CITY PLANT FUEL NUECES\n440279 VAR/TGP MAGNOLIA CITY PLANT FLARE N\n410736 VAR/TGP PETRONELLA DEHY NUECES\n016347 / 420837 TGP/TGP FALFURRIAS BROOKS\n412733 UES/TGP MYRICK BROOKS",400.12,"------------prl----model_loc--","***MLV 400-1 to MLV 409-1:  Pig Run - Maintenance Cleaning 9/17\n--9/17/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n411884 ENRONCTR/TGP MAGNOLIA PLANT PTR MAK\n440236 MAGNOLIA CITY PLANT FUEL NUECES\n440279 VAR/TGP MAGNOLIA CITY PLANT FLARE N\n410736 VAR/TGP PETRONELLA DEHY NUECES\n016347 / 420837 TGP/TGP FALFURRIAS BROOKS\n412733 UES/TGP MYRICK BROOKS\n***Project Change\n………………………………"]
["X24-76758","***","2024-11-05","2024-11-05","Project Change",null,null,"MLV 400-1 to MLV 409-1","400","0","Pig Run - Maintenance Cleaning 11/5","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","411884 ENRONCTR/TGP MAGNOLIA PLANT PTR MAK\n440236 MAGNOLIA CITY PLANT FUEL NUECES\n440279 VAR/TGP MAGNOLIA CITY PLANT FLARE N\n410736 VAR/TGP PETRONELLA DEHY NUECES\n016347 / 420837 TGP/TGP FALFURRIAS BROOKS\n412733 UES/TGP MYRICK BROOKS",400.13,"------------prl----model_loc--","***MLV 400-1 to MLV 409-1:  Pig Run - Maintenance Cleaning 11/5\n--11/5/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n411884 ENRONCTR/TGP MAGNOLIA PLANT PTR MAK\n440236 MAGNOLIA CITY PLANT FUEL NUECES\n440279 VAR/TGP MAGNOLIA CITY PLANT FLARE N\n410736 VAR/TGP PETRONELLA DEHY NUECES\n016347 / 420837 TGP/TGP FALFURRIAS BROOKS\n412733 UES/TGP MYRICK BROOKS\n***Project Change\n………………………………"]
["X24-76760","***","2024-03-28","2024-03-28","Project Change",null,null,"MLV 400-2 to MLV 409-2","400","0","Pig Run - Maintenance Cleaning 3/28","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","410736 VAR/TGP PETRONELLA DEHY NUECES\n412197 KMTEJAS/TGP KING RANCH KLEBERG\n412579 TGP/TGP SANTA FE WILDCAT BROOKS\n411725 EXPORT/TGP LOS INDIOS DEHY HIDALGO\n412628 SAMSON/TGP LOS INDIOS 3 HIDALGO",400.2,"------------prl----model_loc--","***MLV 400-2 to MLV 409-2:  Pig Run - Maintenance Cleaning 3/28\n--3/28/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n410736 VAR/TGP PETRONELLA DEHY NUECES\n412197 KMTEJAS/TGP KING RANCH KLEBERG\n412579 TGP/TGP SANTA FE WILDCAT BROOKS\n411725 EXPORT/TGP LOS INDIOS DEHY HIDALGO\n412628 SAMSON/TGP LOS INDIOS 3 HIDALGO\n***Project Change\n………………………………"]
["X24-76762","***","2024-05-15","2024-05-15","Project Change",null,null,"MLV 400-2 to MLV 409-2","400","0","Pig Run - Maintenance Cleaning 5/15","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","410736 VAR/TGP PETRONELLA DEHY NUECES\n412197 KMTEJAS/TGP KING RANCH KLEBERG\n412579 TGP/TGP SANTA FE WILDCAT BROOKS\n411725 EXPORT/TGP LOS INDIOS DEHY HIDALGO\n412628 SAMSON/TGP LOS INDIOS 3 HIDALGO",400.21,"------------prl----model_loc--","***MLV 400-2 to MLV 409-2:  Pig Run - Maintenance Cleaning 5/15\n--5/15/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n410736 VAR/TGP PETRONELLA DEHY NUECES\n412197 KMTEJAS/TGP KING RANCH KLEBERG\n412579 TGP/TGP SANTA FE WILDCAT BROOKS\n411725 EXPORT/TGP LOS INDIOS DEHY HIDALGO\n412628 SAMSON/TGP LOS INDIOS 3 HIDALGO\n***Project Change\n………………………………"]
["X24-76768","***","2024-08-20","2024-08-20","Project Change",null,null,"MLV 400-2 to MLV 409-2","400","0","Pig Run - Maintenance Cleaning 8/20","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","410736 VAR/TGP PETRONELLA DEHY NUECES\n412197 KMTEJAS/TGP KING RANCH KLEBERG\n412579 TGP/TGP SANTA FE WILDCAT BROOKS\n411725 EXPORT/TGP LOS INDIOS DEHY HIDALGO\n412628 SAMSON/TGP LOS INDIOS 3 HIDALGO",400.22,"------------prl----model_loc--","***MLV 400-2 to MLV 409-2:  Pig Run - Maintenance Cleaning 8/20\n--8/20/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n410736 VAR/TGP PETRONELLA DEHY NUECES\n412197 KMTEJAS/TGP KING RANCH KLEBERG\n412579 TGP/TGP SANTA FE WILDCAT BROOKS\n411725 EXPORT/TGP LOS INDIOS DEHY HIDALGO\n412628 SAMSON/TGP LOS INDIOS 3 HIDALGO\n***Project Change\n………………………………"]
["X24-76772","***","2024-11-06","2024-11-06","Project Change",null,null,"MLV 400-2 to MLV 409-2","400","0","Pig Run - Maintenance Cleaning 11/6","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","410736 VAR/TGP PETRONELLA DEHY NUECES\n412197 KMTEJAS/TGP KING RANCH KLEBERG\n412579 TGP/TGP SANTA FE WILDCAT BROOKS\n411725 EXPORT/TGP LOS INDIOS DEHY HIDALGO\n412628 SAMSON/TGP LOS INDIOS 3 HIDALGO",400.23,"------------prl----model_loc--","***MLV 400-2 to MLV 409-2:  Pig Run - Maintenance Cleaning 11/6\n--11/6/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n410736 VAR/TGP PETRONELLA DEHY NUECES\n412197 KMTEJAS/TGP KING RANCH KLEBERG\n412579 TGP/TGP SANTA FE WILDCAT BROOKS\n411725 EXPORT/TGP LOS INDIOS DEHY HIDALGO\n412628 SAMSON/TGP LOS INDIOS 3 HIDALGO\n***Project Change\n………………………………"]
["X24-25559",null,"2023-12-18","2024-03-15",null,null,null,"MLV 406-2","100","0","Emergent Repair","This project may require reducing the pipeline section pressure.  Customers may experience pressure fluctuations; however, no other service impact is anticipated.","PIP","Potential in the path restrictions may be at risk.","421017 - RIO BRAVO DEL\n450261 - CENEGAS DEL",406.2,null,"MLV 406-2:  Emergent Repair\n--12/18/23 through 3/15/24:  This project may require reducing the pipeline section pressure.  Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n421017 - RIO BRAVO DEL\n450261 - CENEGAS DEL\n………………………………"]
["X23-428658",null,"2024-02-22","2024-02-22",null,null,null,"MLV 409A-901L to MLV 409A-902","100","0","Pig Run - Maintenance","This activity will require operating at controlled flow rates which will limit throughput through the station and result in restrictions based on customer nominations.  The meters listed may experience pressure fluctuations.","SOP","Potential out of path restrictions may be at risk.","450261\tCENAGAS/TGP PEMEX CHECK DELIV SOUTH\n450262\tCENAGAS/TGP REC NORTH HIDALGO",409.09,null,"MLV 409A-901L to MLV 409A-902:  Pig Run - Maintenance\n--2/22/24:  This activity will require operating at controlled flow rates which will limit throughput through the station and result in restrictions based on customer nominations.  The meters listed may experience pressure fluctuations.  Potential out of path restrictions may be at risk.\n450261\tCENAGAS/TGP PEMEX CHECK DELIV SOUTH\n450262\tCENAGAS/TGP REC NORTH HIDALGO\n………………………………"]
["X24-39036","***","2024-02-12","2024-02-14","Project Change",null,null,"MLV 409A-101.1 to MLV 409A-103","400","0","Pig Runs - Cleaning 2/12 to 2/14","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  During the pig run, Cenagas will be shut in and RIO will flow at a controlled rate.","SOP","Potential out of path restrictions may be at risk.","450261 CENAGAS/TGP PEMEX\n421017 GDR/TGP RIO BRAVO HIDALGO",409.1,"------meters_affected--anticipated_impact--------model_loc--","***MLV 409A-101.1 to MLV 409A-103:  Pig Runs - Cleaning 2/12 to 2/14\n--2/12/24 through 2/14/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  During the pig run, Cenagas will be shut in and RIO will flow at a controlled rate.  Potential out of path restrictions may be at risk.\n450261 CENAGAS/TGP PEMEX\n421017 GDR/TGP RIO BRAVO HIDALGO\n***Project Change\n………………………………"]
["X24-39039","***","2024-02-14","2024-02-14","Project Change",null,null,"MLV 409A-101.1 to MLV 409A-103","400","0","Pig Runs - Gauge 2/14","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  During the pig run, Cenagas will be shut in and RIO will flow at a controlled rate.","SOP","Potential out of path restrictions may be at risk.","450261 CENAGAS/TGP PEMEX\n421017 GDR/TGP RIO BRAVO HIDALGO",409.11,"------meters_affected--anticipated_impact--------model_loc--","***MLV 409A-101.1 to MLV 409A-103:  Pig Runs - Gauge 2/14\n--2/14/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  During the pig run, Cenagas will be shut in and RIO will flow at a controlled rate.  Potential out of path restrictions may be at risk.\n450261 CENAGAS/TGP PEMEX\n421017 GDR/TGP RIO BRAVO HIDALGO\n***Project Change\n………………………………"]
["X24-39040","***","2024-02-15","2024-02-15","Project Change",null,null,"MLV 409A-101.1 to MLV 409A-103","400","0","Pig Runs - MFL 2/15","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  During the pig run, Cenagas will be shut in and RIO will flow at a controlled rate.","SOP","Potential out of path restrictions may be at risk.","450261 CENAGAS/TGP PEMEX\n421017 GDR/TGP RIO BRAVO HIDALGO",409.11099999999999,"------meters_affected--anticipated_impact--------model_loc--","***MLV 409A-101.1 to MLV 409A-103:  Pig Runs - MFL 2/15\n--2/15/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  During the pig run, Cenagas will be shut in and RIO will flow at a controlled rate.  Potential out of path restrictions may be at risk.\n450261 CENAGAS/TGP PEMEX\n421017 GDR/TGP RIO BRAVO HIDALGO\n***Project Change\n………………………………"]
["X24-39041","***","2024-02-16","2024-02-16","Project Change",null,null,"MLV 409A-101.1 to MLV 409A-103","400","0","Pig Runs - AFD 2/16","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  During the pig run, Cenagas will be shut in and RIO will flow at a controlled rate.","SOP","Potential out of path restrictions may be at risk.","450261 CENAGAS/TGP PEMEX\n421017 GDR/TGP RIO BRAVO HIDALGO",409.11200000000002,"------meters_affected--anticipated_impact--------model_loc--","***MLV 409A-101.1 to MLV 409A-103:  Pig Runs - AFD 2/16\n--2/16/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  During the pig run, Cenagas will be shut in and RIO will flow at a controlled rate.  Potential out of path restrictions may be at risk.\n450261 CENAGAS/TGP PEMEX\n421017 GDR/TGP RIO BRAVO HIDALGO\n***Project Change\n………………………………"]
["X24-39044","***","2024-02-05","2024-02-07","Completed",null,null,"MLV 409A-1200BL to MLV 409A-1202R","400","0","Pig Run - Cleaning 2/5 to 2/7","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,409.12,"------","***MLV 409A-1200BL to MLV 409A-1202R:  Pig Run - Cleaning 2/5 to 2/7\n***Completed"]
["X24-39047",null,"2024-02-08","2024-02-08",null,null,null,"MLV 409A-1200BL to MLV 409A-1202R","400","0","Pig Run - Gauge 2/8","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,409.12099999999998,null,"MLV 409A-1200BL to MLV 409A-1202R:  Pig Run - Gauge 2/8\n--2/8/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-39048",null,"2024-02-09","2024-02-09",null,null,null,"MLV 409A-1200BL to MLV 409A-1202R","400","0","Pig Run - MFL 2/9","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,409.12200000000001,null,"MLV 409A-1200BL to MLV 409A-1202R:  Pig Run - MFL 2/9\n--2/9/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-114205",null,"2024-03-11","2024-03-11",null,null,null,"Sta 500C1","500","1","Unit 1A - Suction Valve Operator","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,500.00099999999998,null,"Sta 500C1:  Unit 1A - Suction Valve Operator\n--3/11/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-27854",null,"2024-02-28","2024-02-28",null,null,null,"Sta 500-1 to Sta 823 (MLV 507-1)","500","L","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420373 TRNSCO/TGP KINDER LA EXCH (BI 1\n420708 ELIZ NG/TGP GRANT LA SALES ALLEN\n420436 VERNON/TGP PITKIN LA VERNON\n420793 ELIZ NG/TGP J R FRANKS 1 VERNON\n420388 PROVNCAL/TGP PROVENCAL LA NATCHITOC",500.1,null,"Sta 500-1 to Sta 823 (MLV 507-1):  Pig Run - Maintenance\n--2/28/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n420373 TRNSCO/TGP KINDER LA EXCH (BI 1\n420708 ELIZ NG/TGP GRANT LA SALES ALLEN\n420436 VERNON/TGP PITKIN LA VERNON\n420793 ELIZ NG/TGP J R FRANKS 1 VERNON\n420388 PROVNCAL/TGP PROVENCAL LA NATCHITOC\n………………………………"]
["X24-27873",null,"2024-11-12","2024-11-12",null,null,null,"Sta 500-1 to Sta 823 (MLV 507-1)","500","L","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420373 TRNSCO/TGP KINDER LA EXCH (BI 1\n420708 ELIZ NG/TGP GRANT LA SALES ALLEN\n420436 VERNON/TGP PITKIN LA VERNON\n420793 ELIZ NG/TGP J R FRANKS 1 VERNON\n420388 PROVNCAL/TGP PROVENCAL LA NATCHITOC",500.1,null,"Sta 500-1 to Sta 823 (MLV 507-1):  Pig Run - Maintenance\n--11/12/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n420373 TRNSCO/TGP KINDER LA EXCH (BI 1\n420708 ELIZ NG/TGP GRANT LA SALES ALLEN\n420436 VERNON/TGP PITKIN LA VERNON\n420793 ELIZ NG/TGP J R FRANKS 1 VERNON\n420388 PROVNCAL/TGP PROVENCAL LA NATCHITOC\n………………………………"]
["X24-56013","***","2024-07-09","2024-07-09","Project Change",null,null,"STA 507F to Sta 823","500","L","Pig Run - Cleaning/Gauge 7/9/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter(s) listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","410671 TARGA/TGP UDP LOWRY PLANT DEHY CAME\n412002 ANR/TGP CHALKLEY TRANSPORT JEFFERSO\n412680 TRUNKLNE/TGP LACASSINE JEFFERSON DA\n450302 VAR/TGP CHENIER STRADDLE PLT INLET\n450303 TGP/TGP GRAND CHENIER STRADDLE PLAN",507.1,"------------prl----model_loc--","***STA 507F to Sta 823:  Pig Run - Cleaning/Gauge 7/9/24\n--7/9/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter(s) listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n410671 TARGA/TGP UDP LOWRY PLANT DEHY CAME\n412002 ANR/TGP CHALKLEY TRANSPORT JEFFERSO\n412680 TRUNKLNE/TGP LACASSINE JEFFERSON DA\n450302 VAR/TGP CHENIER STRADDLE PLT INLET\n450303 TGP/TGP GRAND CHENIER STRADDLE PLAN\n***Project Change\n………………………………"]
["X24-27891",null,"2024-08-07","2024-08-07",null,null,null,"STA 507F to Sta 823","500","L","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","410671 TARGA/TGP UDP LOWRY PLANT DEHY CAME\n412002 ANR/TGP CHALKLEY TRANSPORT JEFFERSO\n412680 TRUNKLNE/TGP LACASSINE JEFFERSON DA\n450302 VAR/TGP CHENIER STRADDLE PLT INLET\n450303 TGP/TGP GRAND CHENIER STRADDLE PLAN",507.1,null,"STA 507F to Sta 823:  Pig Run - Maintenance\n--8/7/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n410671 TARGA/TGP UDP LOWRY PLANT DEHY CAME\n412002 ANR/TGP CHALKLEY TRANSPORT JEFFERSO\n412680 TRUNKLNE/TGP LACASSINE JEFFERSON DA\n450302 VAR/TGP CHENIER STRADDLE PLT INLET\n450303 TGP/TGP GRAND CHENIER STRADDLE PLAN\n………………………………"]
["X24-56015","***","2024-07-10","2024-07-10","Project Change",null,null,"STA 507F to Sta 823","500","L","Pig Run - AFD 7/10/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter(s) listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","410671 TARGA/TGP UDP LOWRY PLANT DEHY CAME\n412002 ANR/TGP CHALKLEY TRANSPORT JEFFERSO\n412680 TRUNKLNE/TGP LACASSINE JEFFERSON DA\n450302 VAR/TGP CHENIER STRADDLE PLT INLET\n450303 TGP/TGP GRAND CHENIER STRADDLE PLAN",507.12,"------------prl----model_loc--","***STA 507F to Sta 823:  Pig Run - AFD 7/10/24\n--7/10/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter(s) listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n410671 TARGA/TGP UDP LOWRY PLANT DEHY CAME\n412002 ANR/TGP CHALKLEY TRANSPORT JEFFERSO\n412680 TRUNKLNE/TGP LACASSINE JEFFERSON DA\n450302 VAR/TGP CHENIER STRADDLE PLT INLET\n450303 TGP/TGP GRAND CHENIER STRADDLE PLAN\n***Project Change\n………………………………"]
["X24-56016","***","2024-07-11","2024-07-11","Project Change",null,null,"STA 507F to Sta 823","500","L","Pig Run - EMAT 7/11/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter(s) listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","410671 TARGA/TGP UDP LOWRY PLANT DEHY CAME\n412002 ANR/TGP CHALKLEY TRANSPORT JEFFERSO\n412680 TRUNKLNE/TGP LACASSINE JEFFERSON DA\n450302 VAR/TGP CHENIER STRADDLE PLT INLET\n450303 TGP/TGP GRAND CHENIER STRADDLE PLAN",507.13,"------------prl----model_loc--","***STA 507F to Sta 823:  Pig Run - EMAT 7/11/24\n--7/11/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter(s) listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n410671 TARGA/TGP UDP LOWRY PLANT DEHY CAME\n412002 ANR/TGP CHALKLEY TRANSPORT JEFFERSO\n412680 TRUNKLNE/TGP LACASSINE JEFFERSON DA\n450302 VAR/TGP CHENIER STRADDLE PLT INLET\n450303 TGP/TGP GRAND CHENIER STRADDLE PLAN\n***Project Change\n………………………………"]
["X24-56017","***","2024-07-16","2024-07-16","Project Change",null,null,"STA 823 to STA 507K","500","L","Pig Run - Cleaning/Gauge 7/16/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter(s) listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420493\tCOKINOS/TGP MALLETT FARM LA JEFFERS",507.14,"------------prl----model_loc--","***STA 823 to STA 507K:  Pig Run - Cleaning/Gauge 7/16/24\n--7/16/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter(s) listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n420493\tCOKINOS/TGP MALLETT FARM LA JEFFERS\n***Project Change\n………………………………"]
["X24-56018","***","2024-07-17","2024-07-17","Project Change",null,null,"STA 823 to STA 507K","500","L","Pig Run - AFD 7/17/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter(s) listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420493\tCOKINOS/TGP MALLETT FARM LA JEFFERS",507.15,"------------prl----model_loc--","***STA 823 to STA 507K:  Pig Run - AFD 7/17/24\n--7/17/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter(s) listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n420493\tCOKINOS/TGP MALLETT FARM LA JEFFERS\n***Project Change\n………………………………"]
["X24-56019","***","2024-07-18","2024-07-18","Project Change",null,null,"STA 823 to STA 507K","500","L","Pig Run - EMAT 7/18/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter(s) listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420493\tCOKINOS/TGP MALLETT FARM LA JEFFERS",507.16,"------------prl----model_loc--","***STA 823 to STA 507K:  Pig Run - EMAT 7/18/24\n--7/18/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter(s) listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n420493\tCOKINOS/TGP MALLETT FARM LA JEFFERS\n***Project Change\n………………………………"]
["X23-1086955","***","2024-03-26","2024-04-02","Project Change","2024-01-29","2024-02-01","MLV 525-2 to MLV 527-2","500","L","New Meter Hot Tap","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,525.20000000000005,"--start_date--end_date------------model_loc--","***MLV 525-2 to MLV 527-2:  New Meter Hot Tap\n--3/26/24 through 4/2/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 1/29/24 to 2/1/24.\n………………………………"]
["X24-55879",null,"2024-02-12","2024-02-17",null,null,null,"Sta 527","500","L","Substation - Electrical Inspection","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,527,null,"Sta 527:  Substation - Electrical Inspection\n--2/12/24 through 2/17/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-374936",null,"2024-06-03","2024-06-07",null,null,null,"MLV 527-1 to MLV 529-1","500","L","Pig Runs - Cleaning 6/3/24 to 6/7/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,527.1,null,"MLV 527-1 to MLV 529-1:  Pig Runs - Cleaning 6/3/24 to 6/7/24\n--6/3/24 through 6/7/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-374937",null,"2024-06-10","2024-06-10",null,null,null,"MLV 527-1 to MLV 529-1","500","L","Pig Runs - Combo 6/10/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,527.11,null,"MLV 527-1 to MLV 529-1:  Pig Runs - Combo 6/10/24\n--6/10/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-374938",null,"2024-06-12","2024-06-12",null,null,null,"MLV 527-1 to MLV 529-1","500","L","Pig Runs - AFD 6/12/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,527.12,null,"MLV 527-1 to MLV 529-1:  Pig Runs - AFD 6/12/24\n--6/12/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-57594",null,"2023-08-14","2024-02-14",null,null,null,"MLV 528-1","500","L","Install New Platform","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420361 BBTSIGCO/TGP YSCLOSKEY LA ST BERNAR",528.1,null,"MLV 528-1:  Install New Platform\n--8/14/23 through 2/14/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n420361 BBTSIGCO/TGP YSCLOSKEY LA ST BERNAR\n………………………………"]
["X23-846763",null,"2024-05-13","2024-05-24",null,null,null,"MLV 528-1","500","L","Install New Platform Tie-In","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420361 BBTSIGCO/TGP YSCLOSKEY LA ST BERNAR",528.11,null,"MLV 528-1:  Install New Platform Tie-In\n--5/13/24 through 5/24/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n420361 BBTSIGCO/TGP YSCLOSKEY LA ST BERNAR\n………………………………"]
["X23-57589",null,"2024-02-19","2024-05-09",null,null,null,"MLV 528-2 & MLV 528-3","500","L","Install New Platform","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412654 ELYSIM/TGP POTASH PLAQUEMINES",528.20000000000005,null,"MLV 528-2 & MLV 528-3:  Install New Platform\n--2/19/24 through 5/9/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n412654 ELYSIM/TGP POTASH PLAQUEMINES\n………………………………"]
["X23-917779",null,"2023-09-25","2024-02-14",null,null,null,"MLV 529-1 to MLV 530-1","500","L","Install New Platform/Hydrotest","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420361 BBTSIGCO/TGP YSCLOSKEY LA ST BERNAR",529.1,null,"MLV 529-1 to MLV 530-1:  Install New Platform/Hydrotest\n--9/25/23 through 2/14/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n420361 BBTSIGCO/TGP YSCLOSKEY LA ST BERNAR\n………………………………"]
["X23-587635",null,"2023-06-01","2024-08-01",null,null,null,"Sta 530","500","L","Units 2A, 4A & 8A - Automation Upgrade","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,530,null,"Sta 530:  Units 2A, 4A & 8A - Automation Upgrade\n--6/1/23 through 8/1/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-617569",null,"2023-06-01","2024-06-01",null,null,null,"Sta 530","500","L","Unit, 2A, 4A & 8A - Overhaul / Reversal","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,530.00199999999995,null,"Sta 530:  Unit, 2A, 4A & 8A - Overhaul / Reversal\n--6/1/23 through 6/1/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-27798","***","2024-01-03","2024-04-13","Project Change",null,null,"MLV 530-1 to MLV 531-1","500","L","High Priority Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","410723 GULFSTH/TGP KILN MISS EXCH HANCOCK",530.1,"------------prl----model_loc--","***MLV 530-1 to MLV 531-1:  High Priority Anomaly Remediation\n--1/3/24 through 4/13/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n410723 GULFSTH/TGP KILN MISS EXCH HANCOCK\n***Project Change\n………………………………"]
["X23-1164310","***","2024-04-04","2024-05-15","Project Change","2024-04-06",null,"MLV 530-1 to MLV 531-1","500","L","Pipe Replacement, Meter Tie-In, Replace MLV 531-1, Tap Removal","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,530.1,"--start_date--------------model_loc--","***MLV 530-1 to MLV 531-1:  Pipe Replacement, Meter Tie-In, Replace MLV 531-1, Tap Removal\n--4/4/24 through 5/15/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 4/6/24 to 5/15/24.\n………………………………"]
["X23-1164302","***","2024-03-05","2024-04-15","Project Change","2024-03-01","2024-04-05","MLV 530-2 to MLV 531-2","500","L","Pipe Replacement, Meter tie-in, Tap Removal","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,530.20000000000005,"--start_date--end_date------------model_loc--","***MLV 530-2 to MLV 531-2:  Pipe Replacement, Meter tie-in, Tap Removal\n--3/5/24 through 4/15/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 3/1/24 to 4/5/24.\n………………………………"]
["X23-1164300","***","2024-01-20","2024-03-04","Project Change",null,"2024-02-27","MLV 530-3 to MLV 532-3","500","L","Pipe Replacement and Meter Tap","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,530.29999999999995,"----end_date------------model_loc--","***MLV 530-3 to MLV 532-3:  Pipe Replacement and Meter Tap\n--1/20/24 through 3/4/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 1/20/24 to 2/27/24.\n………………………………"]
["X24-27804","***","2024-01-03","2024-04-20","Project Change",null,null,"MLV 531-1 to MLV 532-1","500","L","High Priority Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,531.1,"------------prl----model_loc--","***MLV 531-1 to MLV 532-1:  High Priority Anomaly Remediation\n--1/3/24 through 4/20/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Project Change\n………………………………"]
["X23-1164312","***","2024-04-04","2024-05-23","Project Change","2024-04-06",null,"MLV 531-1 to MLV 532-1","500","L","Replace MLV 531-1 & MLV 532-1","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,531.1,"--start_date--------------model_loc--","***MLV 531-1 to MLV 532-1:  Replace MLV 531-1 & MLV 532-1\n--4/4/24 through 5/23/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 4/6/24 to 5/23/24.\n………………………………"]
["X23-1164306","***","2024-03-05","2024-03-28","Project Change","2024-03-01","2024-03-29","MLV 531-2 to MLV 533-2","500","L","Pipe Replacement, Meter tie-in, Tap Removal","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,531.20000000000005,"--start_date--end_date------------model_loc--","***MLV 531-2 to MLV 533-2:  Pipe Replacement, Meter tie-in, Tap Removal\n--3/5/24 through 3/28/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 3/1/24 to 3/29/24.\n………………………………"]
["X23-1164314","***","2024-04-04","2024-06-15","Project Change","2024-04-06",null,"MLV 532-1 to MLV 533-1","500","L","Replace MLV 532-1 & MLV 533-1, Hydrotest Line 1 532 to 534","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,532.1,"--start_date--------------model_loc--","***MLV 532-1 to MLV 533-1:  Replace MLV 532-1 & MLV 533-1, Hydrotest Line 1 532 to 534\n--4/4/24 through 6/15/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 4/6/24 to 6/15/24.\n………………………………"]
["X24-27805","***","2024-01-03","2024-04-27","Project Change",null,null,"MLV 533-1 to MLV 534-1","500","L","High Priority Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420930 FGT/TGP CARNES COMPRESSOR STONE\n420366 FGT/TGP CARNES MISSISSIPPE STONE",533.1,"------------prl----model_loc--","***MLV 533-1 to MLV 534-1:  High Priority Anomaly Remediation\n--1/3/24 through 4/27/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n420930 FGT/TGP CARNES COMPRESSOR STONE\n420366 FGT/TGP CARNES MISSISSIPPE STONE\n***Project Change\n………………………………"]
["X23-1164316","***","2024-04-09","2024-06-15","Project Change","2024-04-11",null,"MLV 533-1 to CS 534-1","500","L","Replace MLV 533-1, tie-in FGT Tap,  Hydrotest Line 1 532 to 534","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,533.1,"--start_date--------------model_loc--","***MLV 533-1 to CS 534-1:  Replace MLV 533-1, tie-in FGT Tap,  Hydrotest Line 1 532 to 534\n--4/9/24 through 6/15/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 4/11/24 to 6/15/24.\n………………………………"]
["X23-1164307","***","2024-03-02","2024-03-15","Project Change","2024-02-27","2024-03-09","MLV 533-2 to CS 534","500","L","MLV 533 Crossover, New tap at FGT Meter, Reversal work at CS 534","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,533.20000000000005,"--start_date--end_date------------model_loc--","***MLV 533-2 to CS 534:  MLV 533 Crossover, New tap at FGT Meter, Reversal work at CS 534\n--3/2/24 through 3/15/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 2/27/24 to 3/9/24.\n………………………………"]
["X23-245490",null,"2023-03-06","2024-05-01",null,null,null,"Sta 534","500","1","Unit 1A to 7A - Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,534.00099999999998,null,"Sta 534:  Unit 1A to 7A - Overhaul\n--3/6/23 through 5/1/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-1078699",null,"2023-10-25","2025-01-19",null,null,null,"MLV 535-1A to MLV 536-1","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,535.1,null,"MLV 535-1A to MLV 536-1:  Anomaly Remediation\n--10/25/23 through 1/19/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-245502",null,"2023-03-06","2024-06-01",null,null,null,"Sta 538","500","1","Unit 1A to 9A - Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,538.00099999999998,null,"Sta 538:  Unit 1A to 9A - Overhaul\n--3/6/23 through 6/1/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-41546",null,"2024-09-10","2024-09-10",null,null,null,"MLV 538-2 to MLV 534-2","500","1","Pig Runs - Cleaning/Gauge 9/10","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,538.20000000000005,null,"MLV 538-2 to MLV 534-2:  Pig Runs - Cleaning/Gauge 9/10\n--9/10/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-41547",null,"2024-09-12","2024-09-12",null,null,null,"MLV 538-2 to MLV 534-2","500","1","Pig Runs - MFL 9/12","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,538.21,null,"MLV 538-2 to MLV 534-2:  Pig Runs - MFL 9/12\n--9/12/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-936962",null,"2024-05-01","2024-05-31",null,null,null,"MLV 539 to MLV 540","500","1","Install tee Ln 1 & 2 (Rose Hill PIN 420546)","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","420546  TGP/SNG ROSE HILL MISS CLARKE",539,null,"MLV 539 to MLV 540:  Install tee Ln 1 & 2 (Rose Hill PIN 420546)\n--5/1/24 through 5/31/24:  This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.  Potential out of path restrictions may be at risk.\n420546  TGP/SNG ROSE HILL MISS CLARKE\n………………………………"]
["X24-94907",null,"2024-03-01","2024-08-31",null,null,null,"Sta 542","500","1","Unit 3A - Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,542.00300000000004,null,"Sta 542:  Unit 3A - Overhaul\n--3/1/24 through 8/31/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-38912",null,"2023-11-30","2024-02-29",null,null,null,"Sta 542","200","1","Unit 4A - Replace Compressor Heads","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,542.00400000000002,null,"Sta 542:  Unit 4A - Replace Compressor Heads\n--11/30/23 through 2/29/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-41548",null,"2024-09-17","2024-09-17",null,null,null,"MLV 542-2 to MLV 538-2","500","1","Pig Runs - Cleaning/Gauge 9/17","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,542.20000000000005,null,"MLV 542-2 to MLV 538-2:  Pig Runs - Cleaning/Gauge 9/17\n--9/17/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-41549",null,"2024-09-19","2024-09-19",null,null,null,"MLV 542-2 to MLV 538-2","500","1","Pig Runs - MFL 9/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,542.21,null,"MLV 542-2 to MLV 538-2:  Pig Runs - MFL 9/19\n--9/19/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-38915",null,"2024-04-30","2024-04-30",null,null,null,"Sta 546","500","1","Unit 3A - Discharge Valve","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,546.00300000000004,null,"Sta 546:  Unit 3A - Discharge Valve\n--4/30/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-27642",null,"2024-04-08","2024-04-19",null,null,null,"MLV 546-1 MLV 546-1A","500","1","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,546.1,null,"MLV 546-1 MLV 546-1A:  Pipe Replacement\n--4/8/24 through 4/19/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-41531",null,"2024-05-21","2024-05-21",null,null,null,"MLV 547J-101.1 to MLV 547J-102","500","1","Pig Runs - Cleaning/Gauge 5/21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,547.1,null,"MLV 547J-101.1 to MLV 547J-102:  Pig Runs - Cleaning/Gauge 5/21\n--5/21/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-41532",null,"2024-05-23","2024-05-23",null,null,null,"MLV 547J-101.1 to MLV 547J-102","500","1","Pig Runs - MFL 5/23","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,547.11,null,"MLV 547J-101.1 to MLV 547J-102:  Pig Runs - MFL 5/23\n--5/23/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-138233","***","2024-09-30","2024-09-30","Added",null,null,"Sta 550 Hamilton","500","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,550,"------","***Sta 550 Hamilton:  Annual ESD Test\n--9/30/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X23-754448",null,"2024-03-01","2024-04-30",null,null,null,"Sta 550","500","1","Unit 4A - Compressor Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,550.00400000000002,null,"Sta 550:  Unit 4A - Compressor Overhaul\n--3/1/24 through 4/30/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-62265","***","2023-09-18","2024-02-09","Project Change",null,"2024-02-07","Sta 550","500","1","Unit 1B - Turbine Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,550.01700000000005,"----end_date------------model_loc--","***Sta 550:  Unit 1B - Turbine Overhaul\n--9/18/23 through 2/9/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/18/23 to 2/7/24.\n………………………………"]
["X24-140863","***","2024-06-17","2024-06-21","Added",null,null,"Sta 555 Collinwood","500",null,"Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,555,"------","***Sta 555 Collinwood:  Annual ESD Test & Maintenance\n--6/17/24 through 6/21/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X23-1138147",null,"2024-02-26","2024-02-29",null,null,null,"Sta 555","500","1","Unit 3A - Replace Base Core Seals","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,555.00300000000004,null,"Sta 555:  Unit 3A - Replace Base Core Seals\n--2/26/24 through 2/29/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-64058",null,"2024-08-05","2024-08-09",null,null,null,"Sta 555","500","1","Unit 1B - Combustion Liner Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,555.01700000000005,null,"Sta 555:  Unit 1B - Combustion Liner Inspection\n--8/5/24 through 8/9/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-56043","***","2024-04-15","2024-04-15","Project Change",null,null,"MLV 555-1 to MLV 550-1","500","1","Pig Runs - Cleaning 4/15/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,555.1,"------------prl----model_loc--","***MLV 555-1 to MLV 550-1:  Pig Runs - Cleaning 4/15/24\n--4/15/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Project Change\n………………………………"]
["X24-56055","***","2024-06-18","2024-06-18","Project Change",null,null,"MLV 555-1 to MLV 550-1","500","1","Pig Runs - Cleaning 6/18/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,555.1,"------------prl----model_loc--","***MLV 555-1 to MLV 550-1:  Pig Runs - Cleaning 6/18/24\n--6/18/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Project Change\n………………………………"]
["X24-56044","***","2024-04-16","2024-04-16","Project Change",null,null,"MLV 555-1 to MLV 550-1","500","1","Pig Runs - MFL-C 4/16/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,555.11,"------------prl----model_loc--","***MLV 555-1 to MLV 550-1:  Pig Runs - MFL-C 4/16/24\n--4/16/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Project Change\n………………………………"]
["X24-56046","***","2024-04-18","2024-04-18","Project Change",null,null,"MLV 555-1 to MLV 550-1","500","1","Pig Runs - EMAT 4/18/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,555.12,"------------prl----model_loc--","***MLV 555-1 to MLV 550-1:  Pig Runs - EMAT 4/18/24\n--4/18/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Project Change\n………………………………"]
["X24-56056","***","2024-06-20","2024-06-20","Project Change",null,null,"MLV 555-1 to MLV 550-1","500","1","Pig Runs - Caliper/IMU/MFL-A 6/20/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,555.12,"------------prl----model_loc--","***MLV 555-1 to MLV 550-1:  Pig Runs - Caliper/IMU/MFL-A 6/20/24\n--6/20/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Project Change\n………………………………"]
["X24-56039","***","2024-04-09","2024-04-09","Project Change",null,null,"MLV 555-2 to MLV 550-2","500","1","Pig Runs - Cleaning 4/9/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,555.20000000000005,"------------prl----model_loc--","***MLV 555-2 to MLV 550-2:  Pig Runs - Cleaning 4/9/24\n--4/9/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Project Change\n………………………………"]
["X24-56052","***","2024-06-06","2024-06-06","Project Change",null,null,"MLV 555-2 to MLV 550-2","500","1","Pig Runs - Cleaning 6/6/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,555.20000000000005,"------------prl----model_loc--","***MLV 555-2 to MLV 550-2:  Pig Runs - Cleaning 6/6/24\n--6/6/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Project Change\n………………………………"]
["X24-56042","***","2024-04-11","2024-04-11","Project Change",null,null,"MLV 555-2 to MLV 550-2","500","1","Pig Runs - Caliper/IMU/MFL-A 4/11/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,555.21,"------------prl----model_loc--","***MLV 555-2 to MLV 550-2:  Pig Runs - Caliper/IMU/MFL-A 4/11/24\n--4/11/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Project Change\n………………………………"]
["X24-56053","***","2024-06-11","2024-06-11","Project Change",null,null,"MLV 555-2 to MLV 550-2","500","1","Pig Runs - MFL-C 6/11/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,555.21,"------------prl----model_loc--","***MLV 555-2 to MLV 550-2:  Pig Runs - MFL-C 6/11/24\n--6/11/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Project Change\n………………………………"]
["X24-56054","***","2024-06-13","2024-06-13","Project Change",null,null,"MLV 555-2 to MLV 550-2","500","1","Pig Runs - EMAT 6/13/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,555.22,"------------prl----model_loc--","***MLV 555-2 to MLV 550-2:  Pig Runs - EMAT 6/13/24\n--6/13/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Project Change\n………………………………"]
["X24-56036","***","2024-03-19","2024-03-19","Project Change",null,null,"MLV 555-3 to MLV 552-3","500","1","Pig Runs - Cleaning 3/19/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,555.29999999999995,"------------prl----model_loc--","***MLV 555-3 to MLV 552-3:  Pig Runs - Cleaning 3/19/24\n--3/19/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Project Change\n………………………………"]
["X24-56037","***","2024-03-21","2024-03-21","Project Change",null,null,"MLV 555-3 to MLV 552-3","500","1","Pig Runs - Caliper/IMU/MFL-A 3/21/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,555.30999999999995,"------------prl----model_loc--","***MLV 555-3 to MLV 552-3:  Pig Runs - Caliper/IMU/MFL-A 3/21/24\n--3/21/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Project Change\n………………………………"]
["X24-56028","***","2024-03-12","2024-03-12","Project Change",null,null,"MLV 558-1R to MLV 555-1L","500","1","Pig Runs - Cleaning 3/12/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter(s) listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420905 ETNG/TGP ETN 500 LINE INTERCONNECT",558.1,"------------prl----model_loc--","***MLV 558-1R to MLV 555-1L:  Pig Runs - Cleaning 3/12/24\n--3/12/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter(s) listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n420905 ETNG/TGP ETN 500 LINE INTERCONNECT\n***Project Change\n………………………………"]
["X24-56049","***","2024-05-23","2024-05-23","Project Change",null,null,"MLV 558-1R to MLV 555-1R","500","1","Pig Runs - Cleaning 5/23/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter(s) listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420905 ETNG/TGP ETN 500 LINE INTERCONNECT",558.1,"------------prl----model_loc--","***MLV 558-1R to MLV 555-1R:  Pig Runs - Cleaning 5/23/24\n--5/23/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter(s) listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n420905 ETNG/TGP ETN 500 LINE INTERCONNECT\n***Project Change\n………………………………"]
["X24-56035","***","2024-03-14","2024-03-14","Project Change",null,null,"MLV 558-1R to MLV 555-1L","500","1","Pig Runs - Caliper/IMU/MFL-A 3/14/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter(s) listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420905 ETNG/TGP ETN 500 LINE INTERCONNECT",558.11,"------------prl----model_loc--","***MLV 558-1R to MLV 555-1L:  Pig Runs - Caliper/IMU/MFL-A 3/14/24\n--3/14/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter(s) listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n420905 ETNG/TGP ETN 500 LINE INTERCONNECT\n***Project Change\n………………………………"]
["X24-56050","***","2024-05-28","2024-05-28","Project Change",null,null,"MLV 558-1R to MLV 555-1R","500","1","Pig Runs - MFL-C 5/28/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter(s) listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420905 ETNG/TGP ETN 500 LINE INTERCONNECT",558.11,"------------prl----model_loc--","***MLV 558-1R to MLV 555-1R:  Pig Runs - MFL-C 5/28/24\n--5/28/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter(s) listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n420905 ETNG/TGP ETN 500 LINE INTERCONNECT\n***Project Change\n………………………………"]
["X24-56051","***","2024-05-30","2024-05-30","Project Change",null,null,"MLV 558-1R to MLV 555-1R","500","1","Pig Runs - EMAT 5/30/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter(s) listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420905 ETNG/TGP ETN 500 LINE INTERCONNECT",558.12,"------------prl----model_loc--","***MLV 558-1R to MLV 555-1R:  Pig Runs - EMAT 5/30/24\n--5/30/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter(s) listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n420905 ETNG/TGP ETN 500 LINE INTERCONNECT\n***Project Change\n………………………………"]
["X24-140920","***","2024-06-27","2024-06-27","Added",null,null,"Sta 563 Joelton","500","2","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,563,"------","***Sta 563 Joelton:  Annual ESD Test\n--6/27/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-74995",null,"2024-09-16","2024-10-14",null,null,null,"Sta 563","500","1","Unit 1A - Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,563.00099999999998,null,"Sta 563:  Unit 1A - Overhaul\n--9/16/24 through 10/14/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-27942",null,"2024-05-02","2024-05-02",null,null,null,"MLV 820-1 to MLV 821R-101.1","800","L","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412690\tHPL/TGP SABINE NEWTON\n412013\tENTRPRSE/TGP SABINE RIVER TRANS NEW\n412839\tDUNCAN/TGP LABOKAY NO. 1: RIP 820P \n412015\tHEC/TGP STARKS HANKAMER  1 CALCASIE\n420988\tTGP/TGP SABINE PASS PLANT STRANGERS\n401366\tTRNSCO/TGP UTOS EXCH\n400580\tFGT/TGP SABINE EXCH CALCASIEU\n411586\tTRNSCO/TGP STARKS LA TRANSPORT CALC\n412588\tCSVHOLDG/TGP STARKS CALCASIEU\n412768\tGLDNPASS/TGP STARKS LNG: RIP 820 10\n412737\tCAM IPL/TGP DE QUINCY GAS STORAGE C\n49446\tCAM IPL/TGP BANKEN RD AT  HWY 27 DE\n412717\tMAYNE/TGP BURLINGTON CALCASIEU\n412461\tOLIPDPII/TGP DEHYDRATION CALCASIEU\n420581\tBDWKLAGT/TGP BECKWITH CREEK CALCASI\n412653\tPAR MINL/TGP INDIAN VILLAGE JEFFERS\n420473\tTRUNKLNE/TGP KINDER LA EXCH JEFFERS\n420227\tCOKINOS/TGP KING FARM LA JEFFERSON",820.1,null,"MLV 820-1 to MLV 821R-101.1:  Pig Run - Maintenance\n--5/2/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n412690\tHPL/TGP SABINE NEWTON\n412013\tENTRPRSE/TGP SABINE RIVER TRANS NEW\n412839\tDUNCAN/TGP LABOKAY NO. 1: RIP 820P \n412015\tHEC/TGP STARKS HANKAMER  1 CALCASIE\n420988\tTGP/TGP SABINE PASS PLANT STRANGERS\n401366\tTRNSCO/TGP UTOS EXCH\n400580\tFGT/TGP SABINE EXCH CALCASIEU\n411586\tTRNSCO/TGP STARKS LA TRANSPORT CALC\n412588\tCSVHOLDG/TGP STARKS CALCASIEU\n412768\tGLDNPASS/TGP STARKS LNG: RIP 820 10\n412737\tCAM IPL/TGP DE QUINCY GAS STORAGE C\n49446\tCAM IPL/TGP BANKEN RD AT  HWY 27 DE\n412717\tMAYNE/TGP BURLINGTON CALCASIEU\n412461\tOLIPDPII/TGP DEHYDRATION CALCASIEU\n420581\tBDWKLAGT/TGP BECKWITH CREEK CALCASI\n412653\tPAR MINL/TGP INDIAN VILLAGE JEFFERS\n420473\tTRUNKLNE/TGP KINDER LA EXCH JEFFERS\n420227\tCOKINOS/TGP KING FARM LA JEFFERSON\n………………………………"]
["X24-27941",null,"2024-05-03","2024-05-03",null,null,null,"MLV 823-1 to MLV 821R-101.1","800","L","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412690\tHPL/TGP SABINE NEWTON\n412013\tENTRPRSE/TGP SABINE RIVER TRANS NEW\n412839\tDUNCAN/TGP LABOKAY NO. 1: RIP 820P \n412015\tHEC/TGP STARKS HANKAMER  1 CALCASIE\n420988\tTGP/TGP SABINE PASS PLANT STRANGERS\n401366\tTRNSCO/TGP UTOS EXCH\n400580\tFGT/TGP SABINE EXCH CALCASIEU\n411586\tTRNSCO/TGP STARKS LA TRANSPORT CALC\n412588\tCSVHOLDG/TGP STARKS CALCASIEU\n412768\tGLDNPASS/TGP STARKS LNG: RIP 820 10\n412737\tCAM IPL/TGP DE QUINCY GAS STORAGE C\n49446\tCAM IPL/TGP BANKEN RD AT  HWY 27 DE\n412717\tMAYNE/TGP BURLINGTON CALCASIEU\n412461\tOLIPDPII/TGP DEHYDRATION CALCASIEU\n420581\tBDWKLAGT/TGP BECKWITH CREEK CALCASI\n412653\tPAR MINL/TGP INDIAN VILLAGE JEFFERS\n420473\tTRUNKLNE/TGP KINDER LA EXCH JEFFERS\n420227\tCOKINOS/TGP KING FARM LA JEFFERSON",823.1,null,"MLV 823-1 to MLV 821R-101.1:  Pig Run - Maintenance\n--5/3/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n412690\tHPL/TGP SABINE NEWTON\n412013\tENTRPRSE/TGP SABINE RIVER TRANS NEW\n412839\tDUNCAN/TGP LABOKAY NO. 1: RIP 820P \n412015\tHEC/TGP STARKS HANKAMER  1 CALCASIE\n420988\tTGP/TGP SABINE PASS PLANT STRANGERS\n401366\tTRNSCO/TGP UTOS EXCH\n400580\tFGT/TGP SABINE EXCH CALCASIEU\n411586\tTRNSCO/TGP STARKS LA TRANSPORT CALC\n412588\tCSVHOLDG/TGP STARKS CALCASIEU\n412768\tGLDNPASS/TGP STARKS LNG: RIP 820 10\n412737\tCAM IPL/TGP DE QUINCY GAS STORAGE C\n49446\tCAM IPL/TGP BANKEN RD AT  HWY 27 DE\n412717\tMAYNE/TGP BURLINGTON CALCASIEU\n412461\tOLIPDPII/TGP DEHYDRATION CALCASIEU\n420581\tBDWKLAGT/TGP BECKWITH CREEK CALCASI\n412653\tPAR MINL/TGP INDIAN VILLAGE JEFFERS\n420473\tTRUNKLNE/TGP KINDER LA EXCH JEFFERS\n420227\tCOKINOS/TGP KING FARM LA JEFFERSON\n………………………………"]
["X24-27930",null,"2024-08-08","2024-08-08",null,null,null,"STA 823 to STA 507K","500","L","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420493\tCOKINOS/TGP MALLETT FARM LA JEFFERS",823.1,null,"STA 823 to STA 507K:  Pig Run - Maintenance\n--8/8/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n420493\tCOKINOS/TGP MALLETT FARM LA JEFFERS\n………………………………"]
["X24-27837",null,"2024-09-11","2024-09-11",null,null,null,"Sta 823 to MLV 516","500","L","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412398 JEFFSTOR/TGP JEFFERSON ISLAND IBERI\n420915 CEGS/TGP PORT IBERIA SALES IBERIA\n421056 ACADIAN/TGP INDIAN BAYOU: DIP 510B-\n410907 TRUNKLNE/TGP CENTERVILLE DEHY TRANS\n450105 AMMID SC/TGP QUIVIRA ST MARY\n412594 NAUTILUS/TGP GARDEN CITY ST MARY\n412684 ANR/TGP SHADYSIDE ST MARY",823.1,null,"Sta 823 to MLV 516:  Pig Run - Maintenance\n--9/11/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n412398 JEFFSTOR/TGP JEFFERSON ISLAND IBERI\n420915 CEGS/TGP PORT IBERIA SALES IBERIA\n421056 ACADIAN/TGP INDIAN BAYOU: DIP 510B-\n410907 TRUNKLNE/TGP CENTERVILLE DEHY TRANS\n450105 AMMID SC/TGP QUIVIRA ST MARY\n412594 NAUTILUS/TGP GARDEN CITY ST MARY\n412684 ANR/TGP SHADYSIDE ST MARY\n………………………………"]
["X24-27940",null,"2024-04-17","2024-04-17",null,null,null,"Sta 827 to Sta 823","800","L","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","421043 PINE PRA/TGP PINE PRAIRIE NORTH RAP\n412847 ACADIAN/TGP CHENEYVILLE RAPIDES\n412713 HUGHES E/TGP UDP BLACK STONE13 EVAN \n412844 TEXLA/TGP ROY MARTIN GATHERING: RIP\n420296 FORSTHIL/TGP FOREST HILL LA RAPIDES\n420530 GLNMORA/TGP GLENMORA LA EXCH RAPIDE\n421042 ELIZ NG/TGP EVANGELINE SALES EVANGE\n420629 ELIZ NG/TGP OAKDALE DETENTION SALES\n420687 ELIZ NG/TGP ALLEN PARISH PRISON SAL\n420406 ELIZ NG/TGP ELIZABETH LA EMERGENCY\n53483 AIRLIQAT/TGP TIMBERLANE BIOGAS REC",827.1,null,"Sta 827 to Sta 823:  Pig Run - Maintenance\n--4/17/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n421043 PINE PRA/TGP PINE PRAIRIE NORTH RAP\n412847 ACADIAN/TGP CHENEYVILLE RAPIDES\n412713 HUGHES E/TGP UDP BLACK STONE13 EVAN \n412844 TEXLA/TGP ROY MARTIN GATHERING: RIP\n420296 FORSTHIL/TGP FOREST HILL LA RAPIDES\n420530 GLNMORA/TGP GLENMORA LA EXCH RAPIDE\n421042 ELIZ NG/TGP EVANGELINE SALES EVANGE\n420629 ELIZ NG/TGP OAKDALE DETENTION SALES\n420687 ELIZ NG/TGP ALLEN PARISH PRISON SAL\n420406 ELIZ NG/TGP ELIZABETH LA EMERGENCY\n53483 AIRLIQAT/TGP TIMBERLANE BIOGAS REC\n………………………………"]
["X24-27939",null,"2024-10-16","2024-10-16",null,null,null,"Sta 827 to Sta 823","800","L","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","421043 PINE PRA/TGP PINE PRAIRIE NORTH RAP\n412847 ACADIAN/TGP CHENEYVILLE RAPIDES\n412713 HUGHES E/TGP UDP BLACK STONE13 EVAN \n412844 TEXLA/TGP ROY MARTIN GATHERING: RIP\n420296 FORSTHIL/TGP FOREST HILL LA RAPIDES\n420530 GLNMORA/TGP GLENMORA LA EXCH RAPIDE\n421042 ELIZ NG/TGP EVANGELINE SALES EVANGE\n420629 ELIZ NG/TGP OAKDALE DETENTION SALES\n420687 ELIZ NG/TGP ALLEN PARISH PRISON SAL\n420406 ELIZ NG/TGP ELIZABETH LA EMERGENCY\n53483 AIRLIQAT/TGP TIMBERLANE BIOGAS REC",827.1,null,"Sta 827 to Sta 823:  Pig Run - Maintenance\n--10/16/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n421043 PINE PRA/TGP PINE PRAIRIE NORTH RAP\n412847 ACADIAN/TGP CHENEYVILLE RAPIDES\n412713 HUGHES E/TGP UDP BLACK STONE13 EVAN \n412844 TEXLA/TGP ROY MARTIN GATHERING: RIP\n420296 FORSTHIL/TGP FOREST HILL LA RAPIDES\n420530 GLNMORA/TGP GLENMORA LA EXCH RAPIDE\n421042 ELIZ NG/TGP EVANGELINE SALES EVANGE\n420629 ELIZ NG/TGP OAKDALE DETENTION SALES\n420687 ELIZ NG/TGP ALLEN PARISH PRISON SAL\n420406 ELIZ NG/TGP ELIZABETH LA EMERGENCY\n53483 AIRLIQAT/TGP TIMBERLANE BIOGAS REC\n………………………………"]
["X24-140937","***","2024-09-04","2024-09-04","Added",null,null,"Sta 834 Winnsboro","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,834,"------","***Sta 834 Winnsboro:  Annual ESD Test\n--9/4/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X22-1209530",null,"2022-12-06","2024-03-30",null,null,null,"Sta 834","800","1","Unit 2A - Top-End Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,834.00199999999995,null,"Sta 834:  Unit 2A - Top-End Overhaul\n--12/6/22 through 3/30/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-140946","***","2024-09-10","2024-09-10","Added",null,null,"Sta 836A Delhi","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,836,"------","***Sta 836A Delhi:  Annual ESD Test\n--9/10/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-140939","***","2024-09-12","2024-09-12","Added",null,null,"Sta 838 Transylvania","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,838,"------","***Sta 838 Transylvania:  Annual ESD Test\n--9/12/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-41528",null,"2024-05-30","2024-05-30",null,null,null,"MLV 838-1 to MLV 843-1","800","1","Pig Runs - Cleaning/Gauge 5/30","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,838.1,null,"MLV 838-1 to MLV 843-1:  Pig Runs - Cleaning/Gauge 5/30\n--5/30/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-41529",null,"2024-06-04","2024-06-04",null,null,null,"MLV 838-1 to MLV 843-1","800","1","Pig Runs - AFD 6/4","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,838.11,null,"MLV 838-1 to MLV 843-1:  Pig Runs - AFD 6/4\n--6/4/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-41530",null,"2024-06-06","2024-06-06",null,null,null,"MLV 838-1 to MLV 843-1","800","1","Pig Runs - EMAT 6/6","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,838.12,null,"MLV 838-1 to MLV 843-1:  Pig Runs - EMAT 6/6\n--6/6/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-138221","***","2024-06-18","2024-06-18","Added",null,null,"Sta 843 Isola","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,843,"------","***Sta 843 Isola:  Annual ESD Test\n--6/18/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-138225","***","2024-08-20","2024-08-20","Added",null,null,"Sta 847 Coffeeville","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,847,"------","***Sta 847 Coffeeville:  Annual ESD Test\n--8/20/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-138240","***","2024-10-08","2024-10-08","Added",null,null,"Sta 851 New Albany","500","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,851,"------","***Sta 851 New Albany:  Annual ESD Test\n--10/8/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-140859","***","2024-05-10","2024-05-10","Added",null,null,"Sta 856 Savannah","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,856,"------","***Sta 856 Savannah:  Annual ESD Test\n--5/10/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X23-841261",null,"2023-08-18","TBD",null,null,null,"Sta 860","800","1","Force Majeure","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,860,null,"Sta 860:  Force Majeure\n--8/18/23 through 6/2/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-75020",null,"2024-06-04","2024-08-16",null,null,null,"MLV 868-1 to MLV 869-1","800","2","Class Change","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,868.1,null,"MLV 868-1 to MLV 869-1:  Class Change\n--6/4/24 through 8/16/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-140914","***","2024-06-04","2024-06-06","Added",null,null,"Sta 871 Campbellsville","800","2","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,871,"------","***Sta 871 Campbellsville:  Annual ESD Test\n--6/4/24 through 6/6/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-140917","***","2024-08-06","2024-08-06","Added",null,null,"Sta 871A Campbellsville","100","2","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,871.00009999999997,"------","***Sta 871A Campbellsville:  Annual ESD Test\n--8/6/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-56059","***","2024-07-30","2024-07-30","Project Change",null,null,"MLV 871-2 to MLV 867-2","800","2","Pig Runs - Cleaning 7/30/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter(s) listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420885 NATGASKY/TGP UDP ALLEN CNTY SALES A",871.2,"------------prl----model_loc--","***MLV 871-2 to MLV 867-2:  Pig Runs - Cleaning 7/30/24\n--7/30/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter(s) listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n420885 NATGASKY/TGP UDP ALLEN CNTY SALES A\n***Project Change\n………………………………"]
["X24-56061","***","2024-08-01","2024-08-01","Project Change",null,null,"MLV 871-2 to MLV 867-2","800","2","Pig Runs - Caliper/IMU/MFL-A 8/1/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter(s) listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420885 NATGASKY/TGP UDP ALLEN CNTY SALES A",871.21,"------------prl----model_loc--","***MLV 871-2 to MLV 867-2:  Pig Runs - Caliper/IMU/MFL-A 8/1/24\n--8/1/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter(s) listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n420885 NATGASKY/TGP UDP ALLEN CNTY SALES A\n***Project Change\n………………………………"]
["X24-138184","***","2024-04-30","2024-05-01","Added",null,null,"Sta 875 Richmond","800","2","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,875,"------","***Sta 875 Richmond:  Annual ESD Test & Maintenance\n--4/30/24 through 5/1/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-126189","***","2024-02-20","2024-02-20","Added",null,null,"Sta 875","800","2","Unit 1A - 8k Hr Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,875.00099999999998,"------","***Sta 875:  Unit 1A - 8k Hr Inspection\n--2/20/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-138168","***","2024-04-08","2024-04-12","Added",null,null,"Sta 875","800","2","Unit 1A - Turbine Exchange","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,875.00099999999998,"------","***Sta 875:  Unit 1A - Turbine Exchange\n--4/8/24 through 4/12/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]

{"sheet":"Sheet2","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}

{"sheet":"Sheet3","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}