{"text_format":"1","workbook":"xlsx","n_sheets":4,"sheets":["Closed","Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":8,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Closed","index":0,"n_rows":37,"n_cols":22,"rows_kept":37,"cut":false,"hidden":true,"merged":[[1,3,1,15],[2,3,2,15],[3,3,3,15]]}
[null,null,null,"Updated ","2016"]
[null,null,null,"Tennessee Gas Pipeline 2015 Pipeline Outage and Maintenance Summary"]
[null,null,null,"This is a summary of the current status of all TGP Winter 2014-2015 Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  Additionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
[null,null,null,"*** Indicates revision"]
["Date Change","Project New/Completed/Closed","Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","Location","Leg","Zone","Maintenance Activity","Anticipated Impact","Potential Restriction Level","TOS Potential Restrictions","Meter(s) in Impacted Area","Customer Notifications","Loc","Email Text","Posting Text","Completion Text"]
[{"$f":"IF(AND(H6<>\"\",I6<>\"\"), \"Date change. Previously scheduled \" & TEXT(H6,\"m/d/y;@\") &IF(H6=I6,\"\",\" to \" & TEXT(I6,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed",null,{"$f":"IF(G6<>\"\",\"***\",\"\")","v":"***"},"2015-01-11","2016-01-11",{"$f":"IF(AND(A6=\"\",B6=\"\"),\"\",IF(B6=\"\",A6,B6))","v":"Project Completed"},null,null,"MS #412494 DCP Warren","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412494 DCP Warren",401,{"$f":"\"(\"&C6&\") \"&J6&\":  \"&M6&IF(AND(E6=\"\",F6=\"\"),\"\",\" (\")&IF(E6=\"\",\"\",\"\"&TEXT(E6,\"m/d/y;@\"))&IF(OR(F6=E6,E6=\"\",F6=\"\"),\"\",\" to \")&IF(OR(F6=\"\",F6=E6),\"\",TEXT(F6,\"m/d/y;@\"))&IF(AND(E6=\"\",F6=\"\"),\"\",\")\")","v":"() MS #412494 DCP Warren:  Meter Station (1/11/15 to 1/11/16)"},{"$f":"D6&J6&\":  \"&M6&IF(AND(E6=\"\",F6=\"\"),\"\",\"\n\")&IF(E6=\"\",\"\",\"--\"&TEXT(E6,\"m/d/y;@\"))&IF(OR(F6=E6,E6=\"\",F6=\"\"),\"\",\" through \")&IF(OR(F6=\"\",F6=E6),\"\",TEXT(F6,\"m/d/y;@\"))&IF(AND(E6=\"\",F6=\"\"),\"\",\":  \")&N6&\"  \"&P6&IF(Q6=\"\",\"\",\"\n\"&Q6)&IF(G6=\"\",\"\",\"\n***\")&G6&\"\n………………………………\"","v":"***MS #412494 DCP Warren:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412494 DCP Warren\n***Project Completed\n………………………………"},{"$f":"D6&J6&\":  \"&M6&IF(G6=\"\",\"\",\"\n***\")&G6&IF(Q6=\"\",\"\",\"\nThe following meters are available for nominations:\n\")&Q6&\"\n………………………………\"","v":"***MS #412494 DCP Warren:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412494 DCP Warren\n………………………………"}]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412400 King Ranch","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412400 King Ranch",402.1,"() MS #412400 King Ranch:  Meter Station (1/11/15 to 1/11/16)","***MS #412400 King Ranch:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412400 King Ranch\n***Project Completed\n………………………………","***MS #412400 King Ranch:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412400 King Ranch\n………………………………"]
["","Project Completed",null,"***","2015-01-12","2016-01-12","Project Completed",null,null,"MS #410539 Duvak Gas Gathering","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410539 Duvak Gas Gathering",402.1,"() MS #410539 Duvak Gas Gathering:  Meter Station (1/12/15 to 1/12/16)","***MS #410539 Duvak Gas Gathering:  Meter Station\n--1/12/15 through 1/12/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410539 Duvak Gas Gathering\n***Project Completed\n………………………………","***MS #410539 Duvak Gas Gathering:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n410539 Duvak Gas Gathering\n………………………………"]
["","Project Completed",null,"***","2015-01-13","2016-01-13","Project Completed",null,null,"MS #412356 DCP LaGloria","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412356 DCP LaGloria",403.1,"() MS #412356 DCP LaGloria:  Meter Station (1/13/15 to 1/13/16)","***MS #412356 DCP LaGloria:  Meter Station\n--1/13/15 through 1/13/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412356 DCP LaGloria\n***Project Completed\n………………………………","***MS #412356 DCP LaGloria:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412356 DCP LaGloria\n………………………………"]
["","Project Completed",null,"***","2015-01-13","2016-01-13","Project Completed",null,null,"MS #410173 Enterprise LaReforma","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410173 Enterprise LaReforma",406.1,"() MS #410173 Enterprise LaReforma:  Meter Station (1/13/15 to 1/13/16)","***MS #410173 Enterprise LaReforma:  Meter Station\n--1/13/15 through 1/13/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410173 Enterprise LaReforma\n***Project Completed\n………………………………","***MS #410173 Enterprise LaReforma:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n410173 Enterprise LaReforma\n………………………………"]
["","Project Completed",null,"***","2015-01-12","2016-01-12","Project Completed",null,null,"MS #411903 Enterprise El Benito","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","411903 Enterprise El Benito",407.1,"() MS #411903 Enterprise El Benito:  Meter Station (1/12/15 to 1/12/16)","***MS #411903 Enterprise El Benito:  Meter Station\n--1/12/15 through 1/12/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n411903 Enterprise El Benito\n***Project Completed\n………………………………","***MS #411903 Enterprise El Benito:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n411903 Enterprise El Benito\n………………………………"]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412088 Enterprise Sullivan","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412088 Enterprise Sullivan",407.1,"() MS #412088 Enterprise Sullivan:  Meter Station (1/11/15 to 1/11/16)","***MS #412088 Enterprise Sullivan:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412088 Enterprise Sullivan\n***Project Completed\n………………………………","***MS #412088 Enterprise Sullivan:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412088 Enterprise Sullivan\n………………………………"]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412683 HESCO","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412683 HESCO",408.1,"() MS #412683 HESCO:  Meter Station (1/11/15 to 1/11/16)","***MS #412683 HESCO:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412683 HESCO\n***Project Completed\n………………………………","***MS #412683 HESCO:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412683 HESCO\n………………………………"]
[{"$f":"IF(AND(H14<>\"\",I14<>\"\"), \"Date change. Previously scheduled \" & TEXT(H14,\"m/d/y;@\") &IF(H14=I14,\"\",\" to \" & TEXT(I14,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X16-36843",{"$f":"IF(G14<>\"\",\"***\",\"\")","v":"***"},"2016-01-27","2016-01-27","Project Completed",null,null,"Sta. 237",200,5,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,237,"(X16-36843) Sta. 237:  Unit  Maintenance (1/27/16)","***Sta. 237:  Unit  Maintenance\n--1/27/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Sta. 237:  Unit  Maintenance\n***Project Completed\n………………………………"]
[{"$f":"IF(AND(H15<>\"\",I15<>\"\"), \"Date change. Previously scheduled \" & TEXT(H15,\"m/d/y;@\") &IF(H15=I15,\"\",\" to \" & TEXT(I15,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X14-1478563",{"$f":"IF(G15<>\"\",\"***\",\"\")","v":"***"},"2015-11-16","2016-02-12","Project Completed",null,null,"MLV 32-1D to 33-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,32.200000000000003,"(X14-1478563) MLV 32-1D to 33-1:  Hydrotest (11/16/15 to 2/12/16)","***MLV 32-1D to 33-1:  Hydrotest\n--11/16/15 through 2/12/16:  This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***MLV 32-1D to 33-1:  Hydrotest\n***Project Completed\n………………………………"]
[null,"Project Completed","X16-16074",null,"2016-01-18","2016-01-28","Project Completed",null,null,"Station 550","500","1","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,550,"(X16-16074) Station 550:  Station Maintenance (1/18/16 to 1/28/16)","Station 550:  Station Maintenance\n--1/18/16 through 1/28/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","Station 550:  Station Maintenance\n***Project Completed\n………………………………"]
[{"$f":"IF(AND(H17<>\"\",I17<>\"\"), \"Date change. Previously scheduled \" & TEXT(H17,\"m/d/y;@\") &IF(H17=I17,\"\",\" to \" & TEXT(I17,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X16-46202",{"$f":"IF(G17<>\"\",\"***\",\"\")","v":"***"},"2016-02-01","2016-02-07","Project Completed",null,null,"Station 9","100","0","Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.",null,9,"(X16-46202) Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items) (2/1/16 to 2/7/16)","***Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)\n--2/1/16 through 2/7/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\n***Project Completed\n………………………………","***Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)\n***Project Completed\n………………………………"]
["","Project Completed","X15-925633","***","2016-02-09","2016-02-11","Project Completed",null,null,"Sta. 266A",200,6,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,266,"(X15-925633) Sta. 266A:  Unit  Maintenance (2/9/16 to 2/11/16)","***Sta. 266A:  Unit  Maintenance\n--2/9/16 through 2/11/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Sta. 266A:  Unit  Maintenance\n***Project Completed\n………………………………"]
["","Project Completed","X15-929733","***","2016-01-27","2016-02-10","Project Completed",null,null,"MLV 834-1 to 838-1",800,5,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",834.1,"(X15-929733) MLV 834-1 to 838-1:  ILI/Cleaning Pig (1/27/16 to 2/10/16)","***MLV 834-1 to 838-1:  ILI/Cleaning Pig\n--1/27/16 through 2/10/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 834-1 to 838-1:  ILI/Cleaning Pig\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X14-1562506","***","2015-11-02","2016-02-19","Project Completed",null,null,"MLV 5-1 to 6-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410063 ROCHE DEHYDRATION             \n",5.0999999999999996,"(X14-1562506) MLV 5-1 to 6-1:  Hydrotest (11/2/15 to 2/19/16)","***MLV 5-1 to 6-1:  Hydrotest\n--11/2/15 through 2/19/16:  This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410063 ROCHE DEHYDRATION             \n\n***Project Completed\n………………………………","***MLV 5-1 to 6-1:  Hydrotest\n***Project Completed\nThe following meters are available for nominations:\n410063 ROCHE DEHYDRATION             \n\n………………………………"]
["","Project Completed","X14-1562506","***","2015-11-02","2016-02-19","Project Completed",null,null,"MLV 7-1 to 9-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","\n412490 Charro\n421083 Eagle Ford Field Service",5.0999999999999996,"(X14-1562506) MLV 7-1 to 9-1:  Hydrotest (11/2/15 to 2/19/16)","***MLV 7-1 to 9-1:  Hydrotest\n--11/2/15 through 2/19/16:  This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n\n412490 Charro\n421083 Eagle Ford Field Service\n***Project Completed\n………………………………","***MLV 7-1 to 9-1:  Hydrotest\n***Project Completed\nThe following meters are available for nominations:\n\n412490 Charro\n421083 Eagle Ford Field Service\n………………………………"]
["Date change. Previously scheduled 2/18/16 to 2/20/16.","Project Completed","X15-882289","***","2016-02-22","2016-02-24","Project Completed","2016-02-18","2016-02-20","MLV 24-2 to 25-2S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.2,"(X15-882289) MLV 24-2 to 25-2S:  Anomaly Remediation (2/22/16 to 2/24/16)","***MLV 24-2 to 25-2S:  Anomaly Remediation\n--2/22/16 through 2/24/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 24-2 to 25-2S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-925630","***","2016-02-23","2016-02-23","Project Completed",null,null,"WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B)",200,"L","ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,265.10000000000002,"(X15-925630) WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig (2/23/16)","***WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig\n--2/23/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig\n***Project Completed\n………………………………"]
["","Project Completed","X16-23748","***","2016-02-15","2016-02-18","Project Completed",null,null,"MLV 530-3 to 532-3",500,"L","ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,530.29999999999995,"(X16-23748) MLV 530-3 to 532-3:  ILI/Cleaning Pig (2/15/16 to 2/18/16)","***MLV 530-3 to 532-3:  ILI/Cleaning Pig\n--2/15/16 through 2/18/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***MLV 530-3 to 532-3:  ILI/Cleaning Pig\n***Project Completed\n………………………………"]
["","Project Canceled","X16-98720","***","2016-03-06","2016-03-06","Project Canceled",null,null,"Sta. 1",100,0,"Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,1,"(X16-98720) Sta. 1:  Station Maintenance (3/6/16)","***Sta. 1:  Station Maintenance\n--3/6/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Canceled\n………………………………","***Sta. 1:  Station Maintenance\n***Project Canceled\n………………………………"]
["","Project Completed","X14-1562513\nX14-1540661","***","2015-07-01","2016-03-04","Project Completed",null,null,"Station 32","100","0","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,32,"(X14-1562513\nX14-1540661) Station 32:  Station Maintenance (7/1/15 to 3/4/16)","***Station 32:  Station Maintenance\n--7/1/15 through 3/4/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Station 32:  Station Maintenance\n***Project Completed\n………………………………"]
["","Project Canceled","X15-926822","***","2016-06-06","2016-06-11","Project Canceled",null,null,"BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1)",300,6,"Pipe Inspection","This project involves inspecting multiple sites.  We do not anticipate having to do any repairs, however if a repair is needed  there is a potential that the pipe  may require replacement which will require isolation of the pipe.  This may limit throughput and will result in restrictions based on customer nominations.  Customers may experience pressure fluctuations during this timeframe.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",343.1,"(X15-926822) BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection (6/6/16 to 6/11/16)","***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection\n--6/6/16 through 6/11/16:  This project involves inspecting multiple sites.  We do not anticipate having to do any repairs, however if a repair is needed  there is a potential that the pipe  may require replacement which will require isolation of the pipe.  This may limit throughput and will result in restrictions based on customer nominations.  Customers may experience pressure fluctuations during this timeframe.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928271","***","TBD","TBD","Project Canceled",null,null,"MLV 555-1 to 550-1",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.1,"(X15-928271) MLV 555-1 to 550-1:  ILI/Cleaning Pig (TBD)","***MLV 555-1 to 550-1:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-1 to 550-1:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928272","***","TBD","TBD","Project Canceled",null,null,"MLV 555-2 to 550-2",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.20000000000005,"(X15-928272) MLV 555-2 to 550-2:  ILI/Cleaning Pig (TBD)","***MLV 555-2 to 550-2:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-2 to 550-2:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928273","***","TBD","TBD","Project Canceled",null,null,"MLV 555-3 to 552-3",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.29999999999995,"(X15-928273) MLV 555-3 to 552-3:  ILI/Cleaning Pig (TBD)","***MLV 555-3 to 552-3:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-3 to 552-3:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-882281","***","2016-02-24","2016-03-03","Project Completed",null,null,"24-1A to 25-1S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.1,"(X15-882281) 24-1A to 25-1S:  Anomaly Remediation (2/24/16 to 3/3/16)","***24-1A to 25-1S:  Anomaly Remediation\n--2/24/16 through 3/3/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***24-1A to 25-1S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-882291","***","2016-03-03","2016-03-04","Project Completed",null,null,"MLV 24-3 to 25-3S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.3,"(X15-882291) MLV 24-3 to 25-3S:  Anomaly Remediation (3/3/16 to 3/4/16)","***MLV 24-3 to 25-3S:  Anomaly Remediation\n--3/3/16 through 3/4/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 24-3 to 25-3S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X14-1178175","***","2015-06-15","2016-03-31","Project Completed",null,null,"Station 63","100","1","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,63,"(X14-1178175) Station 63:  Station Maintenance (6/15/15 to 3/31/16)","***Station 63:  Station Maintenance\n--6/15/15 through 3/31/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Station 63:  Station Maintenance\n***Project Completed\n………………………………"]
["","Project Cancelled","X15-913224","***","2016-04-16","2016-05-21","Project Cancelled",null,null,"MLV 109-2",100,2,"Pipe Replacement","This project will require taking the pipeline section out of service.   This will limit throughput and will result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",109.2,"(X15-913224) MLV 109-2:  Pipe Replacement (4/16/16 to 5/21/16)","***MLV 109-2:  Pipe Replacement\n--4/16/16 through 5/21/16:  This project will require taking the pipeline section out of service.   This will limit throughput and will result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Cancelled\n………………………………","***MLV 109-2:  Pipe Replacement\n***Project Cancelled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-926830","***","2016-03-07","2016-03-11","Project Completed",null,null,"MLV 400-1 to 408-1",100,0,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.","To Be Determined",400.1,"(X15-926830) MLV 400-1 to 408-1:  ILI/Cleaning Pig (3/7/16 to 3/11/16)","***MLV 400-1 to 408-1:  ILI/Cleaning Pig\n--3/7/16 through 3/11/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 400-1 to 408-1:  ILI/Cleaning Pig\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Cancelled","X16-143836","***","2016-03-28","2016-04-04","Project Cancelled",null,null,"Sta. 409",100,0,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.",null,409,"(X16-143836) Sta. 409:  Unit  Maintenance (3/28/16 to 4/4/16)","***Sta. 409:  Unit  Maintenance\n--3/28/16 through 4/4/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\n***Project Cancelled\n………………………………","***Sta. 409:  Unit  Maintenance\n***Project Cancelled\n………………………………"]
["","Project Cancelled","X15-929680","***","2016-04-18","2016-04-27","Project Cancelled",null,null,"SABINE - KINDER LINE to 822-1",800,"L","Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",822.1,"(X15-929680) SABINE - KINDER LINE to 822-1:  Anomaly Remediation (4/18/16 to 4/27/16)","***SABINE - KINDER LINE to 822-1:  Anomaly Remediation\n--4/18/16 through 4/27/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Cancelled\n………………………………","***SABINE - KINDER LINE to 822-1:  Anomaly Remediation\n***Project Cancelled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]

{"sheet":"Sheet1","index":1,"n_rows":396,"n_cols":24,"rows_kept":396,"cut":false,"hidden":false,"merged":[[2,0,2,14]]}
["Updated ","2024-07-18"]
["Tennessee Gas Pipeline 2024 Pipeline Outage and Maintenance Summary"]
["This is a summary of the current status of TGP Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  \nAdditionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
["*** Indicates revision"]
["Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","Location","Leg","Zone","Maintenance Activity","Anticipated Impact","Potential Restriction Level","TOS Potential Restrictions","Meter(s) in Impacted Area","Loc",null,null,null,null,null,null,null,"\\\\houCORP\\TRANS\\TRANSERVICES\\OPPLAN\\COMMON\\Outages\\Outage_DB\\TGP\\Files"]
["X24-55955","***","2024-07-23","2024-09-15","Project Change",null,null,"MLV 3-1 TO MLV 4-1","100","0","Class Change / Wrinkle Bend Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412693 GCENGY/TGP MORGAN SAN PATRICIO",3.1,"--------anticipated_impact--------model_loc--","***MLV 3-1 TO MLV 4-1:  Class Change / Wrinkle Bend Replacement\n--7/23/24 through 9/15/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n412693 GCENGY/TGP MORGAN SAN PATRICIO\n***Project Change\n………………………………"]
["X24-760173","***","2024-08-26","2024-08-26","Added",null,null,"MLV 5-2 to MLV 1-2D","100","0","Pig Runs - Cleaning 8/26/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412603 MAGNUS/TGP WILDCAT WELDER HEIRS 5 S\n412196 ENLINK/TGP NORTH BRAYTON DEHY NUECE\n412062 BANHUB/TGP BANQUETE TRANSPORT NUECE\n412669 ETP/TGP SHOUP NUECES\n412270 LOBO/TGP UDP TRANSAMERICAN INTERCON\n54847 WHISTLEP/TGP WHISTLER RECEIPT NUECE",5.2,"------","***MLV 5-2 to MLV 1-2D:  Pig Runs - Cleaning 8/26/24\n--8/26/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n412603 MAGNUS/TGP WILDCAT WELDER HEIRS 5 S\n412196 ENLINK/TGP NORTH BRAYTON DEHY NUECE\n412062 BANHUB/TGP BANQUETE TRANSPORT NUECE\n412669 ETP/TGP SHOUP NUECES\n412270 LOBO/TGP UDP TRANSAMERICAN INTERCON\n54847 WHISTLEP/TGP WHISTLER RECEIPT NUECE\n***Added\n………………………………"]
["X24-62242","***","2024-08-28","2024-08-28","Project Change","2024-08-27","2024-08-27","MLV 5-2 to MLV 1-2D","100","0","Pig Runs - MFL-A 8/28/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SIP","Potential in the path restrictions may be at risk.","412603 MAGNUS/TGP WILDCAT WELDER HEIRS 5 S\n412196 ENLINK/TGP NORTH BRAYTON DEHY NUECE\n412062 BANHUB/TGP BANQUETE TRANSPORT NUECE\n412669 ETP/TGP SHOUP NUECES\n412270 LOBO/TGP UDP TRANSAMERICAN INTERCON\n54847 WHISTLEP/TGP WHISTLER RECEIPT NUECE",5.2,"--start_date--end_date------mantenance_desc------model_loc--","***MLV 5-2 to MLV 1-2D:  Pig Runs - MFL-A 8/28/24\n--8/28/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential in the path restrictions may be at risk.\n412603 MAGNUS/TGP WILDCAT WELDER HEIRS 5 S\n412196 ENLINK/TGP NORTH BRAYTON DEHY NUECE\n412062 BANHUB/TGP BANQUETE TRANSPORT NUECE\n412669 ETP/TGP SHOUP NUECES\n412270 LOBO/TGP UDP TRANSAMERICAN INTERCON\n54847 WHISTLEP/TGP WHISTLER RECEIPT NUECE\n***\nDate Change, Previously scheduled 8/27/24.\n………………………………"]
["X24-76784",null,"2024-11-14","2024-11-14",null,null,null,"MLV 5-2 to MLV 1-2D","100","0","Pig Runs - Maintenance Cleaning 11/14","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SIP","Potential in the path restrictions may be at risk.","412603 MAGNUS/TGP WILDCAT WELDER HEIRS 5 S\n412196 ENLINK/TGP NORTH BRAYTON DEHY NUECE\n412062 BANHUB/TGP BANQUETE TRANSPORT NUECE\n412669 ETP/TGP SHOUP NUECES\n412270 LOBO/TGP UDP TRANSAMERICAN INTERCON\n54847 WHISTLEP/TGP WHISTLER RECEIPT NUECE",5.2,null,"MLV 5-2 to MLV 1-2D:  Pig Runs - Maintenance Cleaning 11/14\n--11/14/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential in the path restrictions may be at risk.\n412603 MAGNUS/TGP WILDCAT WELDER HEIRS 5 S\n412196 ENLINK/TGP NORTH BRAYTON DEHY NUECE\n412062 BANHUB/TGP BANQUETE TRANSPORT NUECE\n412669 ETP/TGP SHOUP NUECES\n412270 LOBO/TGP UDP TRANSAMERICAN INTERCON\n54847 WHISTLEP/TGP WHISTLER RECEIPT NUECE\n………………………………"]
["X24-760176","***","2024-08-27","2024-08-27","Added",null,null,"MLV 5-2 to MLV 1-2D","100","0","Pig Runs - Cleaning 8/27/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412603 MAGNUS/TGP WILDCAT WELDER HEIRS 5 S\n412196 ENLINK/TGP NORTH BRAYTON DEHY NUECE\n412062 BANHUB/TGP BANQUETE TRANSPORT NUECE\n412669 ETP/TGP SHOUP NUECES\n412270 LOBO/TGP UDP TRANSAMERICAN INTERCON\n54847 WHISTLEP/TGP WHISTLER RECEIPT NUECE",5.21,"------","***MLV 5-2 to MLV 1-2D:  Pig Runs - Cleaning 8/27/24\n--8/27/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n412603 MAGNUS/TGP WILDCAT WELDER HEIRS 5 S\n412196 ENLINK/TGP NORTH BRAYTON DEHY NUECE\n412062 BANHUB/TGP BANQUETE TRANSPORT NUECE\n412669 ETP/TGP SHOUP NUECES\n412270 LOBO/TGP UDP TRANSAMERICAN INTERCON\n54847 WHISTLEP/TGP WHISTLER RECEIPT NUECE\n***Added\n………………………………"]
["X24-62245","***","2024-07-12","2024-07-12","Completed",null,null,"MLV 5-2 to MLV 9-2S","100","0","Pig Runs - MFL-A 7/12/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","54847 WHISTLEP/TGP WHISTLE RECEIPT NUECES\n53608 VCP/TGP VALLEY CROSSING ALLOCATION",5.22,"------","***MLV 5-2 to MLV 9-2S:  Pig Runs - MFL-A 7/12/24\n***Completed\nThe following meters are available for nominations:\n54847 WHISTLEP/TGP WHISTLE RECEIPT NUECES\n53608 VCP/TGP VALLEY CROSSING ALLOCATION"]
["X24-62297","***","2024-07-11","2024-07-11","Completed",null,null,"MLV 5-2 to MLV 9-2S","100","0","Pig Runs - Cleaning/Gauge 7/11/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","54847 WHISTLEP/TGP WHISTLE RECEIPT NUECES\n53608 VCP/TGP VALLEY CROSSING ALLOCATION",5.23,"------","***MLV 5-2 to MLV 9-2S:  Pig Runs - Cleaning/Gauge 7/11/24\n***Completed\nThe following meters are available for nominations:\n54847 WHISTLEP/TGP WHISTLE RECEIPT NUECES\n53608 VCP/TGP VALLEY CROSSING ALLOCATION"]
["X24-633724",null,"2024-07-23","2024-08-23",null,null,null,"MLV 6-1 to MLV 7-1","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,6.1,null,"MLV 6-1 to MLV 7-1:  Anomaly Remediation\n--7/23/24 through 8/23/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-383729",null,"2024-06-15","2024-07-21",null,null,null,"MLV 8-3 to MLV 8-3BR","100","0","Hot Tap for New Meter Station - Invista Meter","This project may require reducing the pipeline section pressure.  Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,8.3000000000000007,null,"MLV 8-3 to MLV 8-3BR:  Hot Tap for New Meter Station - Invista Meter\n--6/15/24 through 7/21/24:  This project may require reducing the pipeline section pressure.  Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-76782",null,"2024-11-12","2024-11-12",null,null,null,"MLV 9-1S and MLV 1-1D","100","0","Pig Run - Maintenance Cleaning 11/12","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SIP","Potential in the path restrictions may be at risk.","54847 WHISTLEP/TGP WHISTLE RECEIPT NUECES\n53608 VCP/TGP VALLEY CROSSING ALLOCATION",9.0500000000000007,null,"MLV 9-1S and MLV 1-1D:  Pig Run - Maintenance Cleaning 11/12\n--11/12/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential in the path restrictions may be at risk.\n54847 WHISTLEP/TGP WHISTLE RECEIPT NUECES\n53608 VCP/TGP VALLEY CROSSING ALLOCATION\n………………………………"]
["X24-62295",null,"2024-09-16","2024-09-16",null,null,null,"MLV 9-1D to MLV 17-1S","100","0","Pig Runs - Cleaning/Gauge 9/16/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420185 COKINOS/TGP OTTIS FARM TX JACKSON\n420158 COKINOS/TGP RAUN FARM TX WHARTON\n420183 COKENRG/TGP KRENEK FARM TX WHARTON\n412523 UES/TGP WILDCAT RASMUSSEN 1 R\n420442 COKINOS/TGP RASMUSSEN FARM TX WHART\n420466 COKINOS/TGP HOLT FARM TX WHARTON\n400454 KEM ENER/TGP EGYPT NORTH WEST DEHY\n420369 COKINOS/TGP WIGGINTON FARM TX WHART",9.11,null,"MLV 9-1D to MLV 17-1S:  Pig Runs - Cleaning/Gauge 9/16/24\n--9/16/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n420185 COKINOS/TGP OTTIS FARM TX JACKSON\n420158 COKINOS/TGP RAUN FARM TX WHARTON\n420183 COKENRG/TGP KRENEK FARM TX WHARTON\n412523 UES/TGP WILDCAT RASMUSSEN 1 R\n420442 COKINOS/TGP RASMUSSEN FARM TX WHART\n420466 COKINOS/TGP HOLT FARM TX WHARTON\n400454 KEM ENER/TGP EGYPT NORTH WEST DEHY\n420369 COKINOS/TGP WIGGINTON FARM TX WHART\n………………………………"]
["X24-62240",null,"2024-09-17","2024-09-17",null,null,null,"MLV 9-1D to MLV 17-1S","100","0","Pig Runs - MFL-A 9/17/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420185 COKINOS/TGP OTTIS FARM TX JACKSON\n420158 COKINOS/TGP RAUN FARM TX WHARTON\n420183 COKENRG/TGP KRENEK FARM TX WHARTON\n412523 UES/TGP WILDCAT RASMUSSEN 1 R\n420442 COKINOS/TGP RASMUSSEN FARM TX WHART\n420466 COKINOS/TGP HOLT FARM TX WHARTON\n400454 KEM ENER/TGP EGYPT NORTH WEST DEHY\n420369 COKINOS/TGP WIGGINTON FARM TX WHART",9.1199999999999992,null,"MLV 9-1D to MLV 17-1S:  Pig Runs - MFL-A 9/17/24\n--9/17/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n420185 COKINOS/TGP OTTIS FARM TX JACKSON\n420158 COKINOS/TGP RAUN FARM TX WHARTON\n420183 COKENRG/TGP KRENEK FARM TX WHARTON\n412523 UES/TGP WILDCAT RASMUSSEN 1 R\n420442 COKINOS/TGP RASMUSSEN FARM TX WHART\n420466 COKINOS/TGP HOLT FARM TX WHARTON\n400454 KEM ENER/TGP EGYPT NORTH WEST DEHY\n420369 COKINOS/TGP WIGGINTON FARM TX WHART\n………………………………"]
["X24-277894",null,"2024-09-19","2024-09-19",null,null,null,"MLV 9-1D to MLV 17-1S","100","0","Pig Runs - MFL-C 9/19/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420185 COKINOS/TGP OTTIS FARM TX JACKSON\n420158 COKINOS/TGP RAUN FARM TX WHARTON\n420183 COKENRG/TGP KRENEK FARM TX WHARTON\n412523 UES/TGP WILDCAT RASMUSSEN 1 R\n420442 COKINOS/TGP RASMUSSEN FARM TX WHART\n420466 COKINOS/TGP HOLT FARM TX WHARTON\n400454 KEM ENER/TGP EGYPT NORTH WEST DEHY\n420369 COKINOS/TGP WIGGINTON FARM TX WHART",9.1300000000000008,null,"MLV 9-1D to MLV 17-1S:  Pig Runs - MFL-C 9/19/24\n--9/19/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n420185 COKINOS/TGP OTTIS FARM TX JACKSON\n420158 COKINOS/TGP RAUN FARM TX WHARTON\n420183 COKENRG/TGP KRENEK FARM TX WHARTON\n412523 UES/TGP WILDCAT RASMUSSEN 1 R\n420442 COKINOS/TGP RASMUSSEN FARM TX WHART\n420466 COKINOS/TGP HOLT FARM TX WHARTON\n400454 KEM ENER/TGP EGYPT NORTH WEST DEHY\n420369 COKINOS/TGP WIGGINTON FARM TX WHART\n………………………………"]
["X24-76834",null,"2024-11-14","2024-11-14",null,null,null,"MLV 9-2 to MLV 5-2","100","0","Pig Runs - Maintenance Cleaning 11/14","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SIP","Potential in the path restrictions may be at risk.","54847 WHISTLEP/TGP WHISTLE RECEIPT NUECES\n53608 VCP/TGP VALLEY CROSSING ALLOCATION",9.1999999999999993,null,"MLV 9-2 to MLV 5-2:  Pig Runs - Maintenance Cleaning 11/14\n--11/14/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential in the path restrictions may be at risk.\n54847 WHISTLEP/TGP WHISTLE RECEIPT NUECES\n53608 VCP/TGP VALLEY CROSSING ALLOCATION\n………………………………"]
["X24-76791",null,"2024-11-13","2024-11-13",null,null,null,"MLV 9-3 to MLV 4-3","100","0","Pig Runs - Maintenance Cleaning 11/13","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SIP","Potential in the path restrictions may be at risk.","54847 WHISTLEP/TGP WHISTLE RECEIPT NUECES\n53608 VCP/TGP VALLEY CROSSING ALLOCATION",9.31,null,"MLV 9-3 to MLV 4-3:  Pig Runs - Maintenance Cleaning 11/13\n--11/13/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential in the path restrictions may be at risk.\n54847 WHISTLEP/TGP WHISTLE RECEIPT NUECES\n53608 VCP/TGP VALLEY CROSSING ALLOCATION\n………………………………"]
["X23-867586",null,"2023-08-26","2024-11-15",null,null,null,"Sta 17","100","0","Unit 2C - Engine Seal Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,17.033999999999999,null,"Sta 17:  Unit 2C - Engine Seal Inspection\n--8/26/23 through 11/15/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-411200",null,"2024-07-08","2024-08-31",null,null,null,"MLV 17-3 TO MLV 18-3","100","1","High Priority Anomaly Remediation / Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,17.3,null,"MLV 17-3 TO MLV 18-3:  High Priority Anomaly Remediation / Pipe Replacement\n--7/8/24 through 8/31/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-29941",null,"2024-11-05","2024-11-05",null,null,null,"MLV 17-3D TO MLV 20-3A","100","0","Pig Runs - Cleaning 11/5","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","421085 SYMMETRY/TGP PEDERSON ROAD WALLER",17.3,null,"MLV 17-3D TO MLV 20-3A:  Pig Runs - Cleaning 11/5\n--11/5/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n421085 SYMMETRY/TGP PEDERSON ROAD WALLER\n………………………………"]
["X24-29950",null,"2024-11-06","2024-11-06",null,null,null,"MLV 17-3D TO MLV 20-3A","100","0","Pig Runs - Gauge 11/6","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","421085 SYMMETRY/TGP PEDERSON ROAD WALLER",17.309999999999999,null,"MLV 17-3D TO MLV 20-3A:  Pig Runs - Gauge 11/6\n--11/6/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n421085 SYMMETRY/TGP PEDERSON ROAD WALLER\n………………………………"]
["X24-29958",null,"2024-11-07","2024-11-07",null,null,null,"MLV 17-3D TO MLV 20-3A","100","0","Pig Runs - MFL-A 11/7","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","421085 SYMMETRY/TGP PEDERSON ROAD WALLER",17.32,null,"MLV 17-3D TO MLV 20-3A:  Pig Runs - MFL-A 11/7\n--11/7/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n421085 SYMMETRY/TGP PEDERSON ROAD WALLER\n………………………………"]
["X24-55954",null,"2024-09-01","2024-10-31",null,null,null,"MLV 18-2A TO MLV 20-2A","100","0","Class Change / Wrinkle Bend Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420167 COKINOS/TGP WOODS FARM TX FORT BEND\n411788 DCP GLP/TGP KATY TRANSPORT WALLER",18.2,null,"MLV 18-2A TO MLV 20-2A:  Class Change / Wrinkle Bend Replacement\n--9/1/24 through 10/31/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n420167 COKINOS/TGP WOODS FARM TX FORT BEND\n411788 DCP GLP/TGP KATY TRANSPORT WALLER\n………………………………"]
["X24-55953",null,"2024-07-01","2024-08-31",null,null,null,"MLV 18-3A TO MLV 20-3A","100","0","Class Change / Wrinkle Bend Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","421085 SYMMETRY/TGP PEDERSON ROAD WALLER\n412271  ENSTOR/KATY INTERCONNECT\n412100  ATMOS-TX/TGP KATY EXCH",18.3,null,"MLV 18-3A TO MLV 20-3A:  Class Change / Wrinkle Bend Replacement\n--7/1/24 through 8/31/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n421085 SYMMETRY/TGP PEDERSON ROAD WALLER\n412271  ENSTOR/KATY INTERCONNECT\n412100  ATMOS-TX/TGP KATY EXCH\n………………………………"]
["X24-411203",null,"2024-07-08","2024-08-31",null,null,null,"MLV 18-3 TO MLV 19-3","100","0","High Priority Anomaly Remediation / Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,18.3,null,"MLV 18-3 TO MLV 19-3:  High Priority Anomaly Remediation / Pipe Replacement\n--7/8/24 through 8/31/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-411204",null,"2024-07-08","2024-08-31",null,null,null,"MLV 19-3 TO MLV 20-3","100","0","High Priority Anomaly Remediation / Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","421085 SYMMETRY/TGP PEDERSON ROAD WALLER",19.3,null,"MLV 19-3 TO MLV 20-3:  High Priority Anomaly Remediation / Pipe Replacement\n--7/8/24 through 8/31/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n421085 SYMMETRY/TGP PEDERSON ROAD WALLER\n………………………………"]
["X24-671080",null,"2024-08-05","2024-08-09",null,null,null,"Sta 25","100","0","Electrical Inspection","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,25,null,"Sta 25:  Electrical Inspection\n--8/5/24 through 8/9/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-572335","***","2024-07-30","2024-07-30","Project Change","2024-07-16","2024-07-16","Sta 25","100","0","Unit 1C - Compressor/Unit Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,25.033000000000001,"--start_date--end_date------------model_loc--","***Sta 25:  Unit 1C - Compressor/Unit Inspection\n--7/30/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 7/16/24.\n………………………………"]
["X24-41537",null,"2024-08-13","2024-08-13",null,null,null,"MLV 25-1S to MLV 24-1A","100","0","Pig Runs - Cleaning/Gauge 8/13","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,25.1,null,"MLV 25-1S to MLV 24-1A:  Pig Runs - Cleaning/Gauge 8/13\n--8/13/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-671169",null,"2024-10-28","2024-11-17",null,null,null,"MLV 25-1 to MLV 26-1 Relocation","100","0","Highway 105 Widening","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,25.1,null,"MLV 25-1 to MLV 26-1 Relocation:  Highway 105 Widening\n--10/28/24 through 11/17/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-41541",null,"2024-08-15","2024-08-15",null,null,null,"MLV 25-1S to MLV 24-1A","100","0","Pig Runs - AFD 8/15","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,25.11,null,"MLV 25-1S to MLV 24-1A:  Pig Runs - AFD 8/15\n--8/15/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-671172",null,"2024-10-28","2024-11-17",null,null,null,"MLV 25A-101 to MLV 25A-102 Relocation","100","0","Highway 105 Widening","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","411559 HEC/TGP UDP 1 CENTRAL COAL & COKE D",25.11,null,"MLV 25A-101 to MLV 25A-102 Relocation:  Highway 105 Widening\n--10/28/24 through 11/17/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n411559 HEC/TGP UDP 1 CENTRAL COAL & COKE D\n………………………………"]
["X24-609070","***","2024-08-27","2024-08-27","Project Change","2024-07-16","2024-07-16","MLV 25-2 to MLV 32-2","100","0","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,25.2,"--start_date--end_date------------model_loc--","***MLV 25-2 to MLV 32-2:  Pig Run - Maintenance\n--8/27/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 7/16/24.\n………………………………"]
["X22-621358",null,"2024-10-28","2024-11-17",null,null,null,"MLV 26-1 Relocation","100","0","Highway 59 Widening","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,26.1,null,"MLV 26-1 Relocation:  Highway 59 Widening\n--10/28/24 through 11/17/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-815863",null,"2024-11-18","2024-12-15",null,null,null,"MLV 26-2 Relocation","100","0","Highway 59 Widening","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,26.2,null,"MLV 26-2 Relocation:  Highway 59 Widening\n--11/18/24 through 12/15/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-815864",null,"2024-10-07","2024-10-27",null,null,null,"MLV 26-3 Relocation","100","0","Highway 59 Widening","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","400448 CICO/TGP MERCY GU 1 LIBERTY",26.3,null,"MLV 26-3 Relocation:  Highway 59 Widening\n--10/7/24 through 10/27/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n400448 CICO/TGP MERCY GU 1 LIBERTY\n………………………………"]
["X24-29962","***","2024-07-19","2024-07-23","Project Change","2024-07-23",null,"MLV 32-1D to MLV 36-1TX","100","0","Pig Run - Chem Cleaning 7/19 to 7/23","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,32.1,"--start_date--------mantenance_desc------model_loc--","***MLV 32-1D to MLV 36-1TX:  Pig Run - Chem Cleaning 7/19 to 7/23\n--7/19/24 through 7/23/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 7/23/24 to 7/23/24.\n………………………………"]
["X24-29967","***","2024-07-24","2024-07-24","Project Change",null,null,"MLV 32-1D to MLV 36-1TX","100","0","Pig Run - Chem Cleaning 7/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,32.11,"----------mantenance_desc------model_loc--","***MLV 32-1D to MLV 36-1TX:  Pig Run - Chem Cleaning 7/24\n--7/24/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Project Change\n………………………………"]
["X24-29969",null,"2024-07-25","2024-07-25",null,null,null,"MLV 32-1D to MLV 36-1TX","100","0","Pig Run - DEF 7/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,32.119999999999997,null,"MLV 32-1D to MLV 36-1TX:  Pig Run - DEF 7/25\n--7/25/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-29970",null,"2024-07-26","2024-07-26",null,null,null,"MLV 32-1D to MLV 36-1TX","100","0","Pig Run - MFL-S 7/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,32.130000000000003,null,"MLV 32-1D to MLV 36-1TX:  Pig Run - MFL-S 7/26\n--7/26/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-41542",null,"2024-08-27","2024-08-27",null,null,null,"MLV 32-3S to MLV 25-3D","100","0","Pig Runs - Cleaning/Gauge 8/27","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,32.29,null,"MLV 32-3S to MLV 25-3D:  Pig Runs - Cleaning/Gauge 8/27\n--8/27/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-41552",null,"2024-08-29","2024-08-29",null,null,null,"MLV 32-3S to MLV 25-3D","100","0","Pig Runs - MFL Combo / Hard Spot 8/29","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,32.292000000000002,null,"MLV 32-3S to MLV 25-3D:  Pig Runs - MFL Combo / Hard Spot 8/29\n--8/29/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-497996","***","2024-07-01","2024-07-24","Project Change",null,"2024-07-15","MLV 35-3 to MLV 36-3","100","0","Pipe Relocation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,35.299999999999997,"----end_date------------model_loc--","***MLV 35-3 to MLV 36-3:  Pipe Relocation\n--7/1/24 through 7/24/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 7/1/24 to 7/15/24.\n………………………………"]
["X24-626387",null,"2024-07-24","2024-07-24",null,null,null,"MLV 36-1TX to MLV 36-1LA","100","0","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,36.1,null,"MLV 36-1TX to MLV 36-1LA:  Pig Run - Maintenance\n--7/24/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-626391",null,"2024-07-24","2024-07-24",null,null,null,"MLV 36-1LA to MLV 40-1S","100","0","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,36.11,null,"MLV 36-1LA to MLV 40-1S:  Pig Run - Maintenance\n--7/24/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-616103",null,"2024-07-30","2024-07-30",null,null,null,"MLV 39A-101.1","100","0","Adding 2\" Tap (Meter Robeline  PIN 420150)","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","420150 ATMOS TL/TGP ROBLINE LA NATCHITOCHE",39.1,null,"MLV 39A-101.1:  Adding 2\" Tap (Meter Robeline  PIN 420150)\n--7/30/24:  This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.  Potential out of path restrictions may be at risk.\n420150 ATMOS TL/TGP ROBLINE LA NATCHITOCHE\n………………………………"]
["X24-94844","***","2024-11-18","2024-11-26","Project Change","2024-10-18","2024-10-26","MLV 40-2D to MLV 42-2BR","100","1","Make Piggable","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,40.200000000000003,"--start_date--end_date------------model_loc--","***MLV 40-2D to MLV 42-2BR:  Make Piggable\n--11/18/24 through 11/26/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 10/18/24 to 10/26/24.\n………………………………"]
["X24-642657","***","2024-12-03","2024-12-04","Project Change","2024-10-08","2024-10-09","Sta 40-2 to Sta 42-2","100","1","Pig Runs - Cleaning 12/3 to 12/4","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,40.200000000000003,"--start_date--end_date------mantenance_desc------model_loc--","***Sta 40-2 to Sta 42-2:  Pig Runs - Cleaning 12/3 to 12/4\n--12/3/24 through 12/4/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 10/8/24 to 10/9/24.\n………………………………"]
["X24-159396","***","2024-12-10","2024-12-10","Project Change","2024-10-15","2024-10-15","Sta 40-2 to Sta 42-2","100","1","Pig Runs - MFL-C 12/10","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,40.200000000000003,"--start_date--end_date------mantenance_desc------model_loc--","***Sta 40-2 to Sta 42-2:  Pig Runs - MFL-C 12/10\n--12/10/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 10/15/24.\n………………………………"]
["X24-159397","***","2024-12-12","2024-12-12","Project Change","2024-10-17","2024-10-17","Sta 40-2 to Sta 42-2","100","1","Pig Runs - EMAT 12/12","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,40.21,"--start_date--end_date------mantenance_desc------model_loc--","***Sta 40-2 to Sta 42-2:  Pig Runs - EMAT 12/12\n--12/12/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 10/17/24.\n………………………………"]
["X24-30025","***","2024-12-05","2024-12-05","Project Change","2024-10-10","2024-10-10","Sta 40-2 to Sta 42-2","100","1","Pig Runs - MFL-S 12/5","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,40.25,"--start_date--end_date------mantenance_desc------model_loc--","***Sta 40-2 to Sta 42-2:  Pig Runs - MFL-S 12/5\n--12/5/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 10/10/24.\n………………………………"]
["X24-741213",null,"2024-08-27","2024-08-27",null,null,null,"MLV 40-3 to MLV 47-3","100","1","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,40.299999999999997,null,"MLV 40-3 to MLV 47-3:  Pig Run - Maintenance\n--8/27/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-741216",null,"2024-08-29","2024-08-29",null,null,null,"MLV 40-4 to MLV 47-4","100","1","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,40.4,null,"MLV 40-4 to MLV 47-4:  Pig Run - Maintenance\n--8/29/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-94847",null,"2024-09-07","2024-09-14",null,null,null,"MLV 41-2A to MLV 42-2","100","1","Make Piggable","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,41.2,null,"MLV 41-2A to MLV 42-2:  Make Piggable\n--9/7/24 through 9/14/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-30028",null,"2024-07-30","2024-08-02",null,null,null,"Sta 42-2BL to Sta 47-2S","100","1","Pig Runs - Chem Cleaning 7/30 to 8/2","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,42.2,null,"Sta 42-2BL to Sta 47-2S:  Pig Runs - Chem Cleaning 7/30 to 8/2\n--7/30/24 through 8/2/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-65372",null,"2024-08-02","2024-08-02",null,null,null,"Sta 42-2BL to Sta 47-2S","100","0","Pig Runs - Gauge 8/2","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,42.204999999999998,null,"Sta 42-2BL to Sta 47-2S:  Pig Runs - Gauge 8/2\n--8/2/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-30032",null,"2024-08-06","2024-08-06",null,null,null,"Sta 42-2BL to Sta 47-2S","100","1","Pig Runs - MFL-A 8/6","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,42.21,null,"Sta 42-2BL to Sta 47-2S:  Pig Runs - MFL-A 8/6\n--8/6/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-30035",null,"2024-08-08","2024-08-08",null,null,null,"Sta 42-2BL to Sta 47-2S","100","1","Pig Runs - RES 8/8","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,42.22,null,"Sta 42-2BL to Sta 47-2S:  Pig Runs - RES 8/8\n--8/8/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-30038",null,"2024-08-13","2024-08-13",null,null,null,"Sta 42-2BL to Sta 47-2S","100","1","Pig Runs - MFL-C 8/13","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,42.23,null,"Sta 42-2BL to Sta 47-2S:  Pig Runs - MFL-C 8/13\n--8/13/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-30039",null,"2024-08-15","2024-08-15",null,null,null,"Sta 42-2BL to Sta 47-2S","100","1","Pig Runs - EMAT 8/15","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,42.24,null,"Sta 42-2BL to Sta 47-2S:  Pig Runs - EMAT 8/15\n--8/15/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-1130419",null,"2024-10-15","2024-10-21",null,null,null,"Bear Creek Storage","100","1","Shut-in Test","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","460017 STORAGE – BEAR CREEK",43.000999999999998,null,"Bear Creek Storage:  Shut-in Test\n--10/15/24 through 10/21/24:  This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.  Potential out of path restrictions may be at risk.\n460017 STORAGE – BEAR CREEK\n………………………………"]
["X24-293323",null,"2024-08-20","2024-08-20",null,null,null,"MLVS 46A","100","1","Meter Station Maintenance Scrubber/Filter Service (Goodhope PIN 48813)","This project may require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below may be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","48813 ATTMOS TL/TGP GOODHOPE OUACHITA",46,null,"MLVS 46A:  Meter Station Maintenance Scrubber/Filter Service (Goodhope PIN 48813)\n--8/20/24:  This project may require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below may be shut-in during the project.  Potential out of path restrictions may be at risk.\n48813 ATTMOS TL/TGP GOODHOPE OUACHITA\n………………………………"]
["X24-449146",null,"2024-08-01","2024-09-30",null,null,null,"MLV 46-1 to MLV 46-1BR","100","1","Class Change","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,46.1,null,"MLV 46-1 to MLV 46-1BR:  Class Change\n--8/1/24 through 9/30/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-449147",null,"2024-10-01","2024-11-30",null,null,null,"MLV 46-4 to MLV 46-4BR","100","1","Class Change","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,46.4,null,"MLV 46-4 to MLV 46-4BR:  Class Change\n--10/1/24 through 11/30/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-140932",null,"2024-09-10","2024-09-10",null,null,null,"Sta 47 West Monroe","100","1","Annual ESD","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,47,null,"Sta 47 West Monroe:  Annual ESD\n--9/10/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-640589",null,"2024-07-29","2024-08-30",null,null,null,"Sta 47","100","1","Unit 1D - 16K Top End Overhaul and Turbocharger Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,47.048999999999999,null,"Sta 47:  Unit 1D - 16K Top End Overhaul and Turbocharger Overhaul\n--7/29/24 through 8/30/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-262252",null,"2024-07-22","2024-07-24",null,null,null,"Sta 47","100","1","Unit 2D - Replace Geislinger Coupling on Unit 2D","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,47.05,null,"Sta 47:  Unit 2D - Replace Geislinger Coupling on Unit 2D\n--7/22/24 through 7/24/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-428703",null,"2024-08-19","2024-08-19",null,null,null,"MLV 47-1D to MLV 54-1S","100","1","Pig Runs - Cleaning/Gauge 8/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,47.1,null,"MLV 47-1D to MLV 54-1S:  Pig Runs - Cleaning/Gauge 8/19\n--8/19/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43770",null,"2024-08-21","2024-08-21",null,null,null,"MLV 47-1D to MLV 54-1S","100","1","Pig Runs - AFD (MFL-C) 8/21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,47.13,null,"MLV 47-1D to MLV 54-1S:  Pig Runs - AFD (MFL-C) 8/21\n--8/21/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43771",null,"2024-08-23","2024-08-23",null,null,null,"MLV 47-1D to MLV 54-1S","100","1","Pig Runs - EMAT 8/23","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,47.14,null,"MLV 47-1D to MLV 54-1S:  Pig Runs - EMAT 8/23\n--8/23/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-658509",null,"2024-07-15","2024-07-26",null,null,null,"MLV 47-2C TO MLV 48-2","100","1","Wrinkle Bend / Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,47.2,null,"MLV 47-2C TO MLV 48-2:  Wrinkle Bend / Pipe Replacement\n--7/15/24 through 7/26/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-766739","***","2024-07-26","2024-08-16","Added",null,null,"MLV 48-3 to MLV 49-3","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,48.3,"------","***MLV 48-3 to MLV 49-3:  Anomaly Remediation\n--7/26/24 through 8/16/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-766744","***","2024-07-24","2024-08-09","Added",null,null,"MLV 51-3 to MLV 52-3","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,51.3,"------","***MLV 51-3 to MLV 52-3:  Anomaly Remediation\n--7/24/24 through 8/9/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-609062","***","2024-07-08","2024-07-12","Completed",null,null,"MLV 53-2C TO MLV 53-2","100","1","High Priority Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,53.2,"------","***MLV 53-2C TO MLV 53-2:  High Priority Anomaly Remediation\n***Completed"]
["X24-609065","***","2024-07-08","2024-07-12","Completed",null,null,"MLV 53-2 TO MLV 52-2","100","1","High Priority Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,53.21,"------","***MLV 53-2 TO MLV 52-2:  High Priority Anomaly Remediation\n***Completed"]
["X24-415098",null,"2024-09-03","2024-09-27",null,null,null,"Sta 54","100","1","Station PLC - Controls Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,54,null,"Sta 54:  Station PLC - Controls Upgrade\n--9/3/24 through 9/27/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-138238",null,"2024-10-08","2024-10-10",null,null,null,"Sta 54 Greenville","100","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,54,null,"Sta 54 Greenville:  Annual ESD Test\n--10/8/24 through 10/10/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-633576",null,"2024-07-15","2024-07-31",null,null,null,"Sta 54 Greenville","100","1","Units 9B - Ignition System Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,54.024999999999999,null,"Sta 54 Greenville:  Units 9B - Ignition System Replacement\n--7/15/24 through 7/31/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-415095",null,"2024-09-03","2024-09-20",null,null,null,"Sta 54","100","1","Unit 1D - Controls Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,54.048999999999999,null,"Sta 54:  Unit 1D - Controls Upgrade\n--9/3/24 through 9/20/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-640584",null,"2024-07-22","2024-07-27",null,null,null,"Sta 54","100","1","Unit 2D - Ariel Compressor Packing Case Change Out & Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,54.05,null,"Sta 54:  Unit 2D - Ariel Compressor Packing Case Change Out & Maintenance\n--7/22/24 through 7/27/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-415096",null,"2024-09-23","2024-10-11",null,null,null,"Sta 54","100","1","Unit 2D - Controls Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,54.05,null,"Sta 54:  Unit 2D - Controls Upgrade\n--9/23/24 through 10/11/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-198176",null,"2024-02-26","TBD",null,null,null,"MLV 54-1 to MLV 69-1","100","1","Force Majeure","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,54.1,null,"MLV 54-1 to MLV 69-1:  Force Majeure\n--2/26/24 through 12/31/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-760072","***","2024-08-12","2024-08-30","Added",null,null,"MLV 58-3 to MLV 59-3","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,58.3,"------","***MLV 58-3 to MLV 59-3:  Anomaly Remediation\n--8/12/24 through 8/30/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-293500",null,"2024-09-09","2024-09-15",null,null,null,"Sta 63","100","1","Inspect & Replace Gas Scrubber Filters","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,63,null,"Sta 63:  Inspect & Replace Gas Scrubber Filters\n--9/9/24 through 9/15/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-138230",null,"2024-09-23","2024-09-24",null,null,null,"Sta 63 Batesville","100","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,63,null,"Sta 63 Batesville:  Annual ESD Test\n--9/23/24 through 9/24/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-293515","***","2024-07-09","2024-07-12","Completed",null,null,"Sta 63","100","1","A Building - Unit Valve Replacements","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,63.000999999999998,"------","***Sta 63:  A Building - Unit Valve Replacements\n***Completed"]
["X24-293475",null,"2024-08-20","2024-08-23",null,null,null,"Sta 63 Batesville","100","1","Unit 1D - Safety Device Checks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,63.048999999999999,null,"Sta 63 Batesville:  Unit 1D - Safety Device Checks\n--8/20/24 through 8/23/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-569123",null,"2024-08-26","2024-10-11",null,null,null,"Sta 63","100","1","Unit 2D - 60K hour inspections","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,63.05,null,"Sta 63:  Unit 2D - 60K hour inspections\n--8/26/24 through 10/11/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-293478",null,"2024-08-27","2024-08-29",null,null,null,"Sta 63 Batesville","100","1","Unit 2D - Safety Device Checks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,63.05,null,"Sta 63 Batesville:  Unit 2D - Safety Device Checks\n--8/27/24 through 8/29/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-41534",null,"2024-08-01","2024-08-01",null,null,null,"MLV 63-2S to MLV 54-2D","100","1","Pig Runs - Cleaning/Gauge 8/1","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,63.2,null,"MLV 63-2S to MLV 54-2D:  Pig Runs - Cleaning/Gauge 8/1\n--8/1/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-41535",null,"2024-08-06","2024-08-06",null,null,null,"MLV 63-2S to MLV 54-2D","100","1","Pig Runs - AFD 8/6","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,63.21,null,"MLV 63-2S to MLV 54-2D:  Pig Runs - AFD 8/6\n--8/6/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-41536",null,"2024-08-08","2024-08-08",null,null,null,"MLV 63-2S to MLV 54-2D","100","1","Pig Runs - EMAT 8/8","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,63.22,null,"MLV 63-2S to MLV 54-2D:  Pig Runs - EMAT 8/8\n--8/8/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-760070","***","2024-08-05","2024-08-09","Added",null,null,"MLV 69-1 to MLV 70-1","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,69.099999999999994,"------","***MLV 69-1 to MLV 70-1:  Anomaly Remediation\n--8/5/24 through 8/9/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-760069","***","2024-07-22","2024-08-02","Added",null,null,"MLV 70-2R to MLV 70-2","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,70.2,"------","***MLV 70-2R to MLV 70-2:  Anomaly Remediation\n--7/22/24 through 8/2/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X23-1196655",null,"2023-11-28","2024-11-22",null,null,null,"Sta 71","100","1","Unit 3A - Discharge Bottle Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,71.003,null,"Sta 71:  Unit 3A - Discharge Bottle Inspection\n--11/28/23 through 11/22/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-262275",null,"2024-04-08","2024-08-31",null,null,null,"Sta 71","100","1","Unit 7A Replace Crank End Compressor Gasket","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,71.007000000000005,null,"Sta 71:  Unit 7A Replace Crank End Compressor Gasket\n--4/8/24 through 8/31/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-517361",null,"2024-07-22","2024-07-28",null,null,null,"MLV 75-1 to MLV 76-1","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,75.099999999999994,null,"MLV 75-1 to MLV 76-1:  Anomaly Remediation\n--7/22/24 through 7/28/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-316210",null,"2024-08-05","2024-09-15",null,null,null,"MLV 77-2 to MLV 77-2A","100","1","Class Change / Pipe Replacement","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,77.2,null,"MLV 77-2 to MLV 77-2A:  Class Change / Pipe Replacement\n--8/5/24 through 9/15/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-520739",null,"2024-07-29","2024-08-24",null,null,null,"MLV 78-1 to MLV 79-1SR","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,78.099999999999994,null,"MLV 78-1 to MLV 79-1SR:  Anomaly Remediation\n--7/29/24 through 8/24/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-181527",null,"2024-08-19","2024-08-26",null,null,null,"MLV 79-1D to MLV 81-1","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,79.099999999999994,null,"MLV 79-1D to MLV 81-1:  Anomaly Remediation\n--8/19/24 through 8/26/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-296256",null,"2024-05-23","2024-07-20",null,null,null,"MLV 84-1A to MLV 85-1","100","1","Class Change","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,84.1,null,"MLV 84-1A to MLV 85-1:  Class Change\n--5/23/24 through 7/20/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-520732",null,"2024-07-28","2024-08-10",null,null,null,"MLV 84-1 to MLV 86-1","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,84.1,null,"MLV 84-1 to MLV 86-1:  Anomaly Remediation\n--7/28/24 through 8/10/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-296273",null,"2024-07-22","2024-09-07",null,null,null,"MLV 84-3 to MLV 85-3","100","1","Class Change","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,84.3,null,"MLV 84-3 to MLV 85-3:  Class Change\n--7/22/24 through 9/7/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-140918",null,"2024-08-07","2024-08-08",null,null,null,"Sta 87 Portland","100","2","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,87,null,"Sta 87 Portland:  Annual ESD Test\n--8/7/24 through 8/8/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-326855",null,"2024-09-02","2024-11-29",null,null,null,"Sta 87","100","2","Unit 5C - Foundation Regrout","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,87.037000000000006,null,"Sta 87:  Unit 5C - Foundation Regrout\n--9/2/24 through 11/29/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-664526",null,"2024-08-19","2024-08-20",null,null,null,"Sta 87","100","2","Building D - Scrubber Filter Inspection/Change Out","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,87.049000000000007,null,"Sta 87:  Building D - Scrubber Filter Inspection/Change Out\n--8/19/24 through 8/20/24:  This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-633552",null,"2024-08-12","2024-08-17",null,null,null,"Sta 87","100","1","Unit 3D - Install New Air Distributor","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,87.051000000000002,null,"Sta 87:  Unit 3D - Install New Air Distributor\n--8/12/24 through 8/17/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-633583",null,"2024-09-16","2024-09-27",null,null,null,"St 87","100","2","Unit 1E - Replace Engine Heads","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,87.064999999999998,null,"St 87:  Unit 1E - Replace Engine Heads\n--9/16/24 through 9/27/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-633584",null,"2024-07-22","2024-08-02",null,null,null,"St 87","100","2","Unit 2E - Replace Engine Heads","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,87.066000000000003,null,"St 87:  Unit 2E - Replace Engine Heads\n--7/22/24 through 8/2/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-56057",null,"2024-08-13","2024-08-13",null,null,null,"MLV 87-1S to MLV 82-1C","100","2","Pig Runs - Cleaning 8/13/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,87.1,null,"MLV 87-1S to MLV 82-1C:  Pig Runs - Cleaning 8/13/24\n--8/13/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-56058",null,"2024-08-15","2024-08-15",null,null,null,"MLV 87-1S to MLV 82-1C","100","1","Pig Runs - Caliper/IMU/Low Field/MFL-A/MFL-S 8/15/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,87.11,null,"MLV 87-1S to MLV 82-1C:  Pig Runs - Caliper/IMU/Low Field/MFL-A/MFL-S 8/15/24\n--8/15/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-664529","***","2024-07-16","2024-07-17","Completed",null,null,"Sta 96","100","2","Building C - Scrubber Filter Inspection/Change Out","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,96.033000000000001,"------","***Sta 96:  Building C - Scrubber Filter Inspection/Change Out\n***Completed"]
["X24-326860",null,"2024-09-09","2024-09-12",null,null,null,"Sta 96","100","2","Unit 5C - Torque Engine Base Frame Anchor Bolts","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,96.037000000000006,null,"Sta 96:  Unit 5C - Torque Engine Base Frame Anchor Bolts\n--9/9/24 through 9/12/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-326854",null,"2024-07-08","2024-10-05",null,null,null,"Sta 96","100","2","Unit 7C - Foundation Regrout","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,96.039000000000001,null,"Sta 96:  Unit 7C - Foundation Regrout\n--7/8/24 through 10/5/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-664528","***","2024-07-15","2024-07-15","Completed",null,null,"Sta 96","100","2","Building D - Scrubber Filter Inspection/Change Out","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,96.049000000000007,"------","***Sta 96:  Building D - Scrubber Filter Inspection/Change Out\n***Completed"]
["X24-633738",null,"2024-08-26","2024-08-31",null,null,null,"MLV 96-3D to MLV 97-3","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,96.3,null,"MLV 96-3D to MLV 97-3:  Anomaly Remediation\n--8/26/24 through 8/31/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-633775",null,"2024-08-27","2024-09-08",null,null,null,"MLV 97-3 to MLV 98-3","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,97.3,null,"MLV 97-3 to MLV 98-3:  Anomaly Remediation\n--8/27/24 through 9/8/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-633742",null,"2024-09-09","2024-09-22",null,null,null,"MLV 98-3 to MLV 99-3","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,98.3,null,"MLV 98-3 to MLV 99-3:  Anomaly Remediation\n--9/9/24 through 9/22/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-633743",null,"2024-09-23","2024-09-29",null,null,null,"MLV 100-3 to MLV 101-3","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,100.3,null,"MLV 100-3 to MLV 101-3:  Anomaly Remediation\n--9/23/24 through 9/29/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-443123",null,"2024-09-24","2024-09-24",null,null,null,"MLV 101-1 to MLV 96-1","100","2","Pig Runs - Cleaning 9/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,101.1,null,"MLV 101-1 to MLV 96-1:  Pig Runs - Cleaning 9/24\n--9/24/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-55873",null,"2024-09-26","2024-09-26",null,null,null,"MLV 101-1 to MLV 96-1","100","2","Pig Runs - Caliper/IMU/MFL-A 9/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,101.11,null,"MLV 101-1 to MLV 96-1:  Pig Runs - Caliper/IMU/MFL-A 9/26\n--9/26/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-633744",null,"2024-09-30","2024-10-06",null,null,null,"MLV 101-3 to MLV 102-3","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,101.3,null,"MLV 101-3 to MLV 102-3:  Anomaly Remediation\n--9/30/24 through 10/6/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-262116",null,"2024-07-26","2024-08-02",null,null,null,"MLV 101-5 to MLV 102-5","100","2","Tie-In to Line 5","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,101.5,null,"MLV 101-5 to MLV 102-5:  Tie-In to Line 5\n--7/26/24 through 8/2/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-174231",null,"2024-06-04","2024-09-05",null,null,null,"MLV 102-1 to MLV 102-1A","100","2","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,102.1,null,"MLV 102-1 to MLV 102-1A:  Pipe Replacement\n--6/4/24 through 9/5/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-174233",null,"2024-09-06","2024-11-06",null,null,null,"MLV 102-1A to MLV 103-1","100","2","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,102.11,null,"MLV 102-1A to MLV 103-1:  Pipe Replacement\n--9/6/24 through 11/6/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-633746",null,"2024-10-07","2024-10-13",null,null,null,"MLV 103-3 to MLV 104-3","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,103.3,null,"MLV 103-3 to MLV 104-3:  Anomaly Remediation\n--10/7/24 through 10/13/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-32467",null,"2024-12-03","2024-12-03",null,null,null,"MLV 105-1 to MLV 102-1","100","2","Pig Runs - Cleaning 12/3","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,105.1,null,"MLV 105-1 to MLV 102-1:  Pig Runs - Cleaning 12/3\n--12/3/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-32468",null,"2024-12-05","2024-12-05",null,null,null,"MLV 105-1 to MLV 102-1","100","2","Pig Runs - MFL-A 12/5","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,105.11,null,"MLV 105-1 to MLV 102-1:  Pig Runs - MFL-A 12/5\n--12/5/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-32469",null,"2024-12-10","2024-12-10",null,null,null,"MLV 105-1 to MLV 102-1","100","2","Pig Runs - MFL-S 12/10","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,105.12,null,"MLV 105-1 to MLV 102-1:  Pig Runs - MFL-S 12/10\n--12/10/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-32470",null,"2024-12-17","2024-12-17",null,null,null,"MLV 105-1 to MLV 102-1","100","2","Pig Runs - AFD 12/17","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,105.13,null,"MLV 105-1 to MLV 102-1:  Pig Runs - AFD 12/17\n--12/17/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-32471",null,"2024-12-19","2024-12-19",null,null,null,"MLV 105-1 to MLV 102-1","100","2","Pig Runs - EMAT 12/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,105.14,null,"MLV 105-1 to MLV 102-1:  Pig Runs - EMAT 12/19\n--12/19/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-633749",null,"2024-10-14","2024-11-16",null,null,null,"MLV 105-3 to MLV 106-3","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,105.3,null,"MLV 105-3 to MLV 106-3:  Anomaly Remediation\n--10/14/24 through 11/16/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-425778",null,"2024-07-29","2024-08-02",null,null,null,"Sta 106","100","2","Unit 1B - Inspect Scavenging Air Cylinder & Valves","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106.017,null,"Sta 106:  Unit 1B - Inspect Scavenging Air Cylinder & Valves\n--7/29/24 through 8/2/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-425785",null,"2024-08-05","2024-08-09",null,null,null,"Sta 106","100","2","Unit 3B - Inspect Scavenging Air Cylinder & Valves","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106.01900000000001,null,"Sta 106:  Unit 3B - Inspect Scavenging Air Cylinder & Valves\n--8/5/24 through 8/9/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-425786",null,"2024-08-12","2024-08-16",null,null,null,"Sta 106","100","2","Unit 4B - Inspect Scavenging Air Cylinder & Valves","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106.02,null,"Sta 106:  Unit 4B - Inspect Scavenging Air Cylinder & Valves\n--8/12/24 through 8/16/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-425787",null,"2024-08-19","2024-08-23",null,null,null,"Sta 106","100","2","Unit 5B - Inspect Scavenging Air Cylinder & Valves","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106.021,null,"Sta 106:  Unit 5B - Inspect Scavenging Air Cylinder & Valves\n--8/19/24 through 8/23/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-425773","***","2024-07-15","2024-07-17","Completed",null,null,"Sta 106","100","2","Unit 9B - Replace #3 Power Cylinder Base Gasket","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106.02500000000001,"------","***Sta 106:  Unit 9B - Replace #3 Power Cylinder Base Gasket\n***Completed"]
["X24-626627",null,"2024-06-10","2024-07-26",null,null,null,"Sta 106","100","2","Unit 1C - Water Leak","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106.033,null,"Sta 106:  Unit 1C - Water Leak\n--6/10/24 through 7/26/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-618203",null,"2024-07-15","2024-07-26",null,null,null,"Sta 106","100","2","Unit 1C - Engine Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106.033,null,"Sta 106:  Unit 1C - Engine Maintenance\n--7/15/24 through 7/26/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-425776",null,"2024-07-22","2024-07-25",null,null,null,"Sta 106","100","2","Unit 1C - Replace Power Cylinder Head Gasket / Packing Case","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106.033,null,"Sta 106:  Unit 1C - Replace Power Cylinder Head Gasket / Packing Case\n--7/22/24 through 7/25/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-428363",null,"2024-09-01","2024-09-15",null,null,null,"Sta 106","100","2","C Building - Install 4 Jacket Water Fan VFD's","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106.033,null,"Sta 106:  C Building - Install 4 Jacket Water Fan VFD's\n--9/1/24 through 9/15/24:  This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-38969",null,"2024-12-03","2024-12-05",null,null,null,"Sta 106","100","2","Unit 1D - 4k Hr Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106.0491,null,"Sta 106:  Unit 1D - 4k Hr Inspection\n--12/3/24 through 12/5/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-38963",null,"2024-08-13","2024-08-15",null,null,null,"Sta 106","100","2","Unit 2D - 8k Hr Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106.0501,null,"Sta 106:  Unit 2D - 8k Hr Inspection\n--8/13/24 through 8/15/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-396025","***","2024-06-23","2024-07-25","Project Change",null,"2024-07-18","MLV 106-5L to MLV 107-5","100","2","Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106.5,"----end_date------------model_loc--","***MLV 106-5L to MLV 107-5:  Anomaly Remediation\n--6/23/24 through 7/25/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 6/23/24 to 7/18/24.\n………………………………"]
["X24-138206",null,"2024-11-03","2024-11-03",null,null,null,"Sta 107A North Means","100","2","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,107,null,"Sta 107A North Means:  Annual ESD Test\n--11/3/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-686814",null,"2024-07-29","2024-08-02",null,null,null,"MLV 107-3 to MLV 108-3","100","2","Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,107.3,null,"MLV 107-3 to MLV 108-3:  Anomaly Remediation\n--7/29/24 through 8/2/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-396029","***","2024-06-18","2024-07-25","Project Change",null,"2024-07-18","MLV 107-5 to MLV 109-5A","100","2","Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,107.5,"----end_date------------model_loc--","***MLV 107-5 to MLV 109-5A:  Anomaly Remediation\n--6/18/24 through 7/25/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 6/18/24 to 7/18/24.\n………………………………"]
["X24-396034",null,"2024-06-23","2024-07-18",null,null,null,"MLV 109-5 to MLV 109-5A","100","2","Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,109.3,null,"MLV 109-5 to MLV 109-5A:  Anomaly Remediation\n--6/23/24 through 7/18/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-633752",null,"2024-08-05","2024-08-10",null,null,null,"MLV 109-3 to MLV 109-3A","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,109.3,null,"MLV 109-3 to MLV 109-3A:  Anomaly Remediation\n--8/5/24 through 8/10/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-138191",null,"2024-07-15","2024-07-19",null,null,null,"Sta 110 Morehead","100","2","Annual ESD Test & Substation Inspection","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,110,null,"Sta 110 Morehead:  Annual ESD Test & Substation Inspection\n--7/15/24 through 7/19/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-396035",null,"2024-06-23","2024-07-18",null,null,null,"MLV 110-5 to MLV 111-5A","100","2","Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,110.3,null,"MLV 110-5 to MLV 111-5A:  Anomaly Remediation\n--6/23/24 through 7/18/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-633754",null,"2024-08-12","2024-08-17",null,null,null,"MLV 110-3 to MLV 111-3","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,110.3,null,"MLV 110-3 to MLV 111-3:  Anomaly Remediation\n--8/12/24 through 8/17/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-32443",null,"2024-10-29","2024-10-29",null,null,null,"MLV 110-4 to MLV 106-4","100","2","Pig Runs - Cleaning / Gauge 10/29/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,110.4,null,"MLV 110-4 to MLV 106-4:  Pig Runs - Cleaning / Gauge 10/29/24\n--10/29/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-32445",null,"2024-10-31","2024-10-31",null,null,null,"MLV 110-4 to MLV 106-4","100","2","Pig Runs - AFD 10/31/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,110.41,null,"MLV 110-4 to MLV 106-4:  Pig Runs - AFD 10/31/24\n--10/31/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-32446",null,"2024-11-05","2024-11-05",null,null,null,"MLV 110-4 to MLV 106-4","100","2","Pig Runs - EMAT 11/5/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,110.42,null,"MLV 110-4 to MLV 106-4:  Pig Runs - EMAT 11/5/24\n--11/5/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-144302",null,"2024-10-21","2024-10-23",null,null,null,"Sta 114","100",null,"Unit 1D - 8K hour inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,114.0491,null,"Sta 114:  Unit 1D - 8K hour inspection\n--10/21/24 through 10/23/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-494970",null,"2024-08-20","2024-08-20",null,null,null,"MLV 117-2 to MLV 114-2","100","2","Pig Runs - Cleaning/Gauge 8/20","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,117.2,null,"MLV 117-2 to MLV 114-2:  Pig Runs - Cleaning/Gauge 8/20\n--8/20/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-383617",null,"2024-08-22","2024-08-22",null,null,null,"MLV 117-2 to MLV 114-2","100","3","Pig Runs - MFL-S 8/22","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","PIP","Potential in the path restrictions may be at risk.",null,117.2,null,"MLV 117-2 to MLV 114-2:  Pig Runs - MFL-S 8/22\n--8/22/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-138211",null,"2024-08-26","2024-08-27",null,null,null,"Sta 118A Tyler Mountain","100","3","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,118,null,"Sta 118A Tyler Mountain:  Annual ESD Test\n--8/26/24 through 8/27/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-144237",null,"2024-12-16","2024-12-18",null,null,null,"Sta 118A","100","3","Unit 1A - 8K Turbine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,118.001,null,"Sta 118A:  Unit 1A - 8K Turbine Inspection\n--12/16/24 through 12/18/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-138186",null,"2024-08-12","2024-08-13",null,null,null,"Sta 119A Rocky Fork","100","3","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,119,null,"Sta 119A Rocky Fork:  Annual ESD Test\n--8/12/24 through 8/13/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-361794",null,"2024-09-23","2024-09-27",null,null,null,"Sta 119","100","3","Unit 1A - Add Upstream Filtration to Turbine Fuel Skid","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,119.001,null,"Sta 119:  Unit 1A - Add Upstream Filtration to Turbine Fuel Skid\n--9/23/24 through 9/27/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-144244",null,"2024-11-18","2024-11-20",null,null,null,"Sta 119","100","3","Unit 1A - Turbine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,119.001,null,"Sta 119:  Unit 1A - Turbine Inspection\n--11/18/24 through 11/20/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-741160",null,"2024-07-17","2024-07-19",null,null,null,"Sta 200","200","4","Unit  5A - Turbo Exhaust Leak","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,200.005,null,"Sta 200:  Unit  5A - Turbo Exhaust Leak\n--7/17/24 through 7/19/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-770742","***","2024-07-29","2024-08-02","Added",null,null,"Sta 200","200","4","Unit 5A - Replace bad gasket","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,200.005,"------","***Sta 200:  Unit 5A - Replace bad gasket\n--7/29/24 through 8/2/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-501372","***","2024-07-08","2024-07-12","Completed",null,null,"Sta 200","200","4","Unit 9A - Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,200.00899999999999,"------","***Sta 200:  Unit 9A - Engine Inspection\n***Completed"]
["X24-741162",null,"2024-07-22","2024-07-26",null,null,null,"Sta 200","200","4","Unit 10A - Replace Alignment Chocks/Retorque to Specs","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,200.01,null,"Sta 200:  Unit 10A - Replace Alignment Chocks/Retorque to Specs\n--7/22/24 through 7/26/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-741158","***","2024-07-15","2024-07-16","Completed",null,null,"Sta 200","200","4","Unit 11A - Torquing Power Cylinders","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,200.011,"------","***Sta 200:  Unit 11A - Torquing Power Cylinders\n***Completed"]
["X24-520752",null,"2024-07-29","2024-08-08",null,null,null,"MLV 200-1SL to MLV 201-1","200","4","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,200.1,null,"MLV 200-1SL to MLV 201-1:  Anomaly Remediation\n--7/29/24 through 8/8/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-520759",null,"2024-08-12","2024-08-16",null,null,null,"MLV 202-1 to MLV 203-1R","200","4","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,200.1,null,"MLV 202-1 to MLV 203-1R:  Anomaly Remediation\n--8/12/24 through 8/16/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-487698",null,"2024-08-19","2024-08-29",null,null,null,"MLV 200-2DBL to MLV 200-2A","200","4","Make Piggable / Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","421018 TET/TGP HANGING ROCK SCIOTO",200.2,null,"MLV 200-2DBL to MLV 200-2A:  Make Piggable / Replacement\n--8/19/24 through 8/29/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n421018 TET/TGP HANGING ROCK SCIOTO\n………………………………"]
["X24-32448",null,"2024-11-07","2024-11-07",null,null,null,"MLV 200-2 to MLV 110-4","100","2","Pig Runs - Cleaning / Gauge 11/7/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,200.2,null,"MLV 200-2 to MLV 110-4:  Pig Runs - Cleaning / Gauge 11/7/24\n--11/7/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-32450",null,"2024-11-12","2024-11-12",null,null,null,"MLV 200-2 to MLV 110-4","100","2","Pig Runs - AFD 11/12/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,200.21,null,"MLV 200-2 to MLV 110-4:  Pig Runs - AFD 11/12/24\n--11/12/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-32451",null,"2024-11-14","2024-11-14",null,null,null,"MLV 200-2 to MLV 110-4","100","2","Pig Runs - EMAT 11/14/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,200.22,null,"MLV 200-2 to MLV 110-4:  Pig Runs - EMAT 11/14/24\n--11/14/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-520722","***","2024-07-23","2024-07-27","Project Change","2024-07-15","2024-07-20","MLV 201-4 to MLV 202-4","200","4","Emergent Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,201.4,"--start_date--end_date------mantenance_desc------model_loc--","***MLV 201-4 to MLV 202-4:  Emergent Anomaly Remediation\n--7/23/24 through 7/27/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 7/15/24 to 7/20/24.\n………………………………"]
["X24-520724","***","2024-07-29","2024-08-02","Project Change","2024-07-22","2024-07-26","MLV 202-4 to MLV 203-4","200","4","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,202.4,"--start_date--end_date------------model_loc--","***MLV 202-4 to MLV 203-4:  Anomaly Remediation\n--7/29/24 through 8/2/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***\nDate Change, Previously scheduled 7/22/24 to 7/26/24.\n………………………………"]
["X24-674850",null,"2024-07-01","2024-10-31",null,null,null,"Sta 204","200","4","Operational Conditions","This project will limit capacity thru the pipeline section which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,204,null,"Sta 204:  Operational Conditions\n--7/1/24 through 10/31/24:  This project will limit capacity thru the pipeline section which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-744508",null,"2024-08-26","2024-08-27",null,null,null,"Sta 204","200","4","Scrubber Filter Change","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,204,null,"Sta 204:  Scrubber Filter Change\n--8/26/24 through 8/27/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-756128","***","2024-08-19","2024-08-22","Added",null,null,"Sta 204","200","4","Unit 3A - Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,204.00299999999999,"------","***Sta 204:  Unit 3A - Crankcase Inspection\n--8/19/24 through 8/22/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-655566",null,"2024-07-08","2024-08-15",null,null,null,"Sta 204","200","4","Unit 4A - Compressor Piston","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,204.00399999999999,null,"Sta 204:  Unit 4A - Compressor Piston\n--7/8/24 through 8/15/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-756130","***","2024-08-26","2024-08-29","Added",null,null,"Sta 204","200","4","Unit 7A - Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,204.00700000000001,"------","***Sta 204:  Unit 7A - Crankcase Inspection\n--8/26/24 through 8/29/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-756123","***","2024-07-22","2024-07-25","Added",null,null,"Sta 204","200","4","Unit 10A - Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,204.01,"------","***Sta 204:  Unit 10A - Crankcase Inspection\n--7/22/24 through 7/25/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-671282","***","2024-07-11","2024-07-11","Completed",null,null,"MLV 204-1 to MLV 200-1","200","4","Pig Runs - AFD 7/11/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,204.1,"------","***MLV 204-1 to MLV 200-1:  Pig Runs - AFD 7/11/24\n***Completed"]
["X23-1026449","***","2024-07-16","2024-07-16","Completed",null,null,"MLV 204-1 to MLV 200-1","200","4","Pig Runs - EMAT 7/16/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,204.11,"------","***MLV 204-1 to MLV 200-1:  Pig Runs - EMAT 7/16/24\n***Completed"]
["X23-1026453",null,"2024-11-19","2024-11-19",null,null,null,"MLV 204-2 to MLV 200-2","200","4","Pig Runs - Cleaning / Gauge 11/19/23","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,204.2,null,"MLV 204-2 to MLV 200-2:  Pig Runs - Cleaning / Gauge 11/19/23\n--11/19/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-1026454",null,"2024-11-21","2024-11-21",null,null,null,"MLV 204-2 to MLV 200-2","200","4","Pig Runs - AFD 11/21/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,204.21,null,"MLV 204-2 to MLV 200-2:  Pig Runs - AFD 11/21/24\n--11/21/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-1026455",null,"2024-11-26","2024-11-26",null,null,null,"MLV 204-2 to MLV 200-2","200","4","Pig Runs - EMAT 11/26/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,204.22,null,"MLV 204-2 to MLV 200-2:  Pig Runs - EMAT 11/26/24\n--11/26/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-32452",null,"2024-07-18","2024-07-18",null,null,null,"MLV 200-4A to MLV 200-4","200","4","Pig Runs - Cleaning/Gauge 7/18/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,204.4,null,"MLV 200-4A to MLV 200-4:  Pig Runs - Cleaning/Gauge 7/18/24\n--7/18/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-32454",null,"2024-07-19","2024-07-19",null,null,null,"MLV 200-4A to MLV 200-4","200","4","Pig Runs - MFL-A 7/19/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,204.41,null,"MLV 200-4A to MLV 200-4:  Pig Runs - MFL-A 7/19/24\n--7/19/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-744510",null,"2024-08-28","2024-08-29",null,null,null,"Sta 209","200","4","Scrubber Filter Change","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209,null,"Sta 209:  Scrubber Filter Change\n--8/28/24 through 8/29/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-756135","***","2024-07-22","2024-07-25","Added",null,null,"Sta 209","200","4","Unit 2A - Compressor Pressure Packing","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209.00200000000001,"------","***Sta 209:  Unit 2A - Compressor Pressure Packing\n--7/22/24 through 7/25/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-74910","***","2024-04-09","2024-07-18","Project Change",null,"2024-08-30","Sta 209","200","4","Unit 6A - Turbo Charger","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209.006,"----end_date------------model_loc--","***Sta 209:  Unit 6A - Turbo Charger\n--4/9/24 through 7/18/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 4/9/24 to 8/30/24.\n………………………………"]
["X23-910728","***","2024-08-05","2024-08-08","Project Change","2024-07-15","2024-07-18","Sta 209","200","4","Unit 8A - Replace OP Turbo & Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209.00800000000001,"--start_date--end_date------------model_loc--","***Sta 209:  Unit 8A - Replace OP Turbo & Crankcase Inspection\n--8/5/24 through 8/8/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 7/15/24 to 7/18/24.\n………………………………"]
["X24-756136","***","2024-07-29","2024-08-01","Added",null,null,"Sta 209","200","4","Unit 9A - Compressor Clearance & Piston Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209.00899999999999,"------","***Sta 209:  Unit 9A - Compressor Clearance & Piston Inspection\n--7/29/24 through 8/1/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-674766","***","2024-07-08","2024-07-11","Completed",null,null,"Sta 209","200","4","Unit 10A - Replace OP Turbo & Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209.01,"------","***Sta 209:  Unit 10A - Replace OP Turbo & Crankcase Inspection\n***Completed"]
["X24-652774",null,"2024-07-29","2024-08-31",null,null,null,"MLV 213-2 to MLV 214-2","200","4","Class Change / Pipe Replacement","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,213.2,null,"MLV 213-2 to MLV 214-2:  Class Change / Pipe Replacement\n--7/29/24 through 8/31/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-961737",null,"2023-09-21","2024-08-16",null,null,null,"Sta 214","200","4","Unit 8A - Oil System","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,214.00800000000001,null,"Sta 214:  Unit 8A - Oil System\n--9/21/23 through 8/16/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-744500",null,"2024-07-08","2024-08-31",null,null,null,"Sta 214","200","4","Unit 10A - Compressor Cylinder","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,214.01,null,"Sta 214:  Unit 10A - Compressor Cylinder\n--7/8/24 through 8/31/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-642934",null,"2024-07-18","2024-07-19",null,null,null,"MLV 216-4 to MLV 217-4","200","4","Hot Tap for New Meter Station - Petersburgh Mahoning Meter","This project may require reducing the pipeline section pressure.  Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,216.4,null,"MLV 216-4 to MLV 217-4:  Hot Tap for New Meter Station - Petersburgh Mahoning Meter\n--7/18/24 through 7/19/24:  This project may require reducing the pipeline section pressure.  Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-201663",null,"2024-07-24","2024-07-31",null,null,null,"Sta 219","200","4","Station Upgrade","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,219,null,"Sta 219:  Station Upgrade\n--7/24/24 through 7/31/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-201661",null,"2024-06-10","2024-09-14",null,null,null,"Sta 219","200","4","Unit 1B - Engine Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,219.017,null,"Sta 219:  Unit 1B - Engine Upgrade\n--6/10/24 through 9/14/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-282419",null,"2024-07-15","2024-07-26",null,null,null,"MLV 226-1 to MLV 227-1","200","5","Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,226.1,null,"MLV 226-1 to MLV 227-1:  Anomaly Remediation\n--7/15/24 through 7/26/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-183164",null,"2024-07-30","2024-07-31",null,null,null,"Station 230C","200","5","Annual ESD","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.","410902 TRANSCAN/TGP UDP NIAGARA RIVER NIAG\n421079 TRANSCAN/TGP UDP NIAGARA RIVER DELI",230,null,"Station 230C:  Annual ESD\n--7/30/24 through 7/31/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n410902 TRANSCAN/TGP UDP NIAGARA RIVER NIAG\n421079 TRANSCAN/TGP UDP NIAGARA RIVER DELI\n………………………………"]
["X24-183166",null,"2024-09-12","2024-09-12",null,null,null,"Station 230C","200","5","Unit 1A - Protective Device Tests","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,230.001,null,"Station 230C:  Unit 1A - Protective Device Tests\n--9/12/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-183167",null,"2024-09-19","2024-09-19",null,null,null,"Station 230C","200","5","Unit 2A - Protective Device Tests","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,230.00200000000001,null,"Station 230C:  Unit 2A - Protective Device Tests\n--9/19/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-183168",null,"2024-09-26","2024-09-26",null,null,null,"Station 230C","200","5","Unit 3A - Protective Device Tests","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,230.00299999999999,null,"Station 230C:  Unit 3A - Protective Device Tests\n--9/26/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-183169",null,"2024-10-03","2024-10-03",null,null,null,"Station 230C","200","5","Unit 4A - Protective Device Tests","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,230.00399999999999,null,"Station 230C:  Unit 4A - Protective Device Tests\n--10/3/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-609053",null,"2024-09-30","2024-10-12",null,null,null,"MLV 230B-101 TO MLV 230B-105","200","5","SCCDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,230.1,null,"MLV 230B-101 TO MLV 230B-105:  SCCDA\n--9/30/24 through 10/12/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-168770",null,"2024-08-06","2024-08-06",null,null,null,"Station 237","200","5","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,237,null,"Station 237:  Annual ESD Test\n--8/6/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-168757",null,"2024-07-23","2024-07-23",null,null,null,"Sta 237","200","5","400 Line Filter/Scrubber Change","This project may require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,237.00020000000001,null,"Sta 237:  400 Line Filter/Scrubber Change\n--7/23/24:  This project may require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-168771",null,"2024-08-07","2024-08-07",null,null,null,"Station 237","200","5","Point to Point and Trans Cals","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,237.001,null,"Station 237:  Point to Point and Trans Cals\n--8/7/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-609052",null,"2024-09-16","2024-09-28",null,null,null,"MLV 237-2 TO MLV 245-2","200","5","SCCDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,237.2,null,"MLV 237-2 TO MLV 245-2:  SCCDA\n--9/16/24 through 9/28/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-542003",null,"2024-09-17","2024-09-17",null,null,null,"MLV 237-2 TO MLV 245-2","200","5","Pig Runs - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,237.2,null,"MLV 237-2 TO MLV 245-2:  Pig Runs - Maintenance\n--9/17/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-168759",null,"2024-07-08","2024-07-26",null,null,null,"Sta 241","200","5","Unit 1A - Main Bearing Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,241.001,null,"Sta 241:  Unit 1A - Main Bearing Replacement\n--7/8/24 through 7/26/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-168760",null,"2024-08-12","2024-08-12",null,null,null,"Sta 241","200","5","Unit 1A - Device and Relief Valve Tests","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,241.001,null,"Sta 241:  Unit 1A - Device and Relief Valve Tests\n--8/12/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-168764",null,"2024-08-13","2024-08-13",null,null,null,"Sta 241","200","5","Unit 2A - Device and Relief Valve Tests","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,241.00200000000001,null,"Sta 241:  Unit 2A - Device and Relief Valve Tests\n--8/13/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-168756",null,"2024-07-31","2024-07-31",null,null,null,"Sta 241","300","5","Unit 3A - Device and Relief Valve Tests","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,241.00299999999999,null,"Sta 241:  Unit 3A - Device and Relief Valve Tests\n--7/31/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-168765",null,"2024-08-14","2024-08-14",null,null,null,"Sta 241","200","5","Unit 1B - Device and Relief Valve Tests","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,241.017,null,"Sta 241:  Unit 1B - Device and Relief Valve Tests\n--8/14/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-168772",null,"2024-10-07","2024-10-08",null,null,null,"Sta 241","200","5","Unit 1B - 2K Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,241.017,null,"Sta 241:  Unit 1B - 2K Maintenance\n--10/7/24 through 10/8/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-168767",null,"2024-08-15","2024-08-15",null,null,null,"Sta 241","200","5","Unit 2B - Device and Relief Valve Tests","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,241.018,null,"Sta 241:  Unit 2B - Device and Relief Valve Tests\n--8/15/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-168773",null,"2024-10-09","2024-10-10",null,null,null,"Sta 241","200","5","Unit 2B - 2K Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,241.018,null,"Sta 241:  Unit 2B - 2K Maintenance\n--10/9/24 through 10/10/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-255248",null,"2024-09-04","2024-10-02",null,null,null,"Sta 245","200","5","Unit 7A - Controls Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,245.00700000000001,null,"Sta 245:  Unit 7A - Controls Upgrade\n--9/4/24 through 10/2/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-744488",null,"2024-07-29","2024-08-02",null,null,null,"Sta 249","200","5","Unit 1A - Anchor Bolts and Chock Inspections","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,249.001,null,"Sta 249:  Unit 1A - Anchor Bolts and Chock Inspections\n--7/29/24 through 8/2/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-756167","***","2024-07-18","2024-07-18","Added",null,null,"Sta 249","200","5","Unit 2B - Compressor Valve","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,249.018,"------","***Sta 249:  Unit 2B - Compressor Valve\n--7/18/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-186378",null,"2024-09-24","2024-09-24",null,null,null,"MLV 249-1 TO MLV 254-1","200","5","Pig Runs - EMAT 9/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,249.12,null,"MLV 249-1 TO MLV 254-1:  Pig Runs - EMAT 9/24\n--9/24/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-609049",null,"2024-08-05","2024-08-15",null,null,null,"MLV 252A-100","200","5","Direct Assessment","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,252.1,null,"MLV 252A-100:  Direct Assessment\n--8/5/24 through 8/15/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-633590",null,"2024-10-15","2024-10-15",null,null,null,"Sta 260A Southwick","200","6","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,260,null,"Sta 260A Southwick:  Annual ESD Test\n--10/15/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-27502","***","2024-07-18","2024-07-18","Completed",null,null,"MLV 260A-101.1 TO MLV 260A-103","200","6","Pig Runs - Cleaning/Gauge: 7/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,260.10000000000002,"------","***MLV 260A-101.1 TO MLV 260A-103:  Pig Runs - Cleaning/Gauge: 7/18\n***Completed"]
["X24-27505","***","2024-07-18","2024-07-18","Completed",null,null,"MLV 260A-101.1 TO MLV 260A-103","200","6","Pig Runs - MFL-C: 7/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,260.11,"------","***MLV 260A-101.1 TO MLV 260A-103:  Pig Runs - MFL-C: 7/18\n***Completed"]
["X24-633591",null,"2024-10-16","2024-10-17",null,null,null,"Station 261 Agawam","200","6","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420901 BERKPWR/TGP BERKSHIRE POWER SALES H",261,null,"Station 261 Agawam:  Annual ESD Test\n--10/16/24 through 10/17/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n420901 BERKPWR/TGP BERKSHIRE POWER SALES H\n………………………………"]
["X24-609050",null,"2024-08-16","2024-08-31",null,null,null,"MLV 263A-100","200","6","Direct Assessment","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,263.10000000000002,null,"MLV 263A-100:  Direct Assessment\n--8/16/24 through 8/31/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-174294",null,"2024-08-26","2024-09-20",null,null,null,"Sta 264","200","6","Unit 1C & 2C Overhauls and Control System Upgrades","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,264,null,"Sta 264:  Unit 1C & 2C Overhauls and Control System Upgrades\n--8/26/24 through 9/20/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-633592",null,"2024-10-22","2024-10-22",null,null,null,"Sta 264 Charlton","200","6","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,264,null,"Sta 264 Charlton:  Annual ESD Test\n--10/22/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-282417",null,"2024-07-15","2024-08-03",null,null,null,"MLV 265A-101.1 to MLV 265A-102","200","6","Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,265.10000000000002,null,"MLV 265A-101.1 to MLV 265A-102:  Anomaly Remediation\n--7/15/24 through 8/3/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-520791",null,"2025-07-07","2025-07-25",null,null,null,"MLV 265E-103 to MLV 265E-104","200","6","Regulator Installation & Pipe replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420750 NARNGST/TGP CRANSTON SALES PROVIDEN\n420926 RISEC/TGP FPLE RISE PROVIDENCE\n55784 RHOBIO/TGP SCITUATE RNG REC PROVIDE\n55785 RHOBIO/TGP SCITUATE RNG BUYBACK PR\n420910 NARNGST/TGP SMITHFIELD DELIVERY PRO\n420758 NARNGST/TGP LINCOLN SMS PROVIDENCE",265.10000000000002,null,"MLV 265E-103 to MLV 265E-104:  Regulator Installation & Pipe replacement\n--7/7/25 through 7/25/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n420750 NARNGST/TGP CRANSTON SALES PROVIDEN\n420926 RISEC/TGP FPLE RISE PROVIDENCE\n55784 RHOBIO/TGP SCITUATE RNG REC PROVIDE\n55785 RHOBIO/TGP SCITUATE RNG BUYBACK PR\n420910 NARNGST/TGP SMITHFIELD DELIVERY PRO\n420758 NARNGST/TGP LINCOLN SMS PROVIDENCE\n………………………………"]
["X24-159539",null,"2024-09-18","2024-10-15",null,null,null,"Sta. 267 Hopkinton","200","6","Station Controls Upgrade","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,267,null,"Sta. 267 Hopkinton:  Station Controls Upgrade\n--9/18/24 through 10/15/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-159540",null,"2024-09-18","2024-10-11",null,null,null,"Sta. 267","200","6","Unit 1B Controls Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,267.017,null,"Sta. 267:  Unit 1B Controls Upgrade\n--9/18/24 through 10/11/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-159542",null,"2024-09-22","2024-10-15",null,null,null,"Sta. 267","200","6","Unit 2B Controls Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,267.01799999999997,null,"Sta. 267:  Unit 2B Controls Upgrade\n--9/22/24 through 10/15/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-642659",null,"2024-07-23","2024-07-23",null,null,null,"MLV 267-1 to 270C-101","200","6","Pig Run - MFL-C 7/23/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,267.10000000000002,null,"MLV 267-1 to 270C-101:  Pig Run - MFL-C 7/23/24\n--7/23/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-27480",null,"2024-09-17","2024-09-17",null,null,null,"MLV 267-1 to 270C-101","200","6","Pig Run - EMAT 9/17/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,267.12,null,"MLV 267-1 to 270C-101:  Pig Run - EMAT 9/17/24\n--9/17/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-609051",null,"2024-09-02","2024-09-14",null,null,null,"MLV 268A-200","200","6","Direct Assessment","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,268.2,null,"MLV 268A-200:  Direct Assessment\n--9/2/24 through 9/14/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-407225",null,"2024-07-10","2024-07-20",null,null,null,"MLV 270C-103 TO MLV 270C-104","200","6","Beverly-Salem Lateral Cable Log","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420118 BOSTN/TGP BEVERLY SALEM MA ESSEX (CDP 47861)\n420658 MMWEC/TGP PEABODY SALES ESSES",270.10000000000002,null,"MLV 270C-103 TO MLV 270C-104:  Beverly-Salem Lateral Cable Log\n--7/10/24 through 7/20/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n420118 BOSTN/TGP BEVERLY SALEM MA ESSEX (CDP 47861)\n420658 MMWEC/TGP PEABODY SALES ESSES\n………………………………"]
["X24-27509","***","2024-07-15","2024-07-15","Completed",null,null,"MLV 270C-103 TO MLV 270C-104","200","6","Pig Runs - Cleaning/Gauge 7/15","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420118 BOSTN/TGP BEVERLY SALEM MA ESSEX (CDP 47861)\n420658 MMWEC/TGP PEABODY SALES ESSES",270.10000000000002,"------","***MLV 270C-103 TO MLV 270C-104:  Pig Runs - Cleaning/Gauge 7/15\n***Completed\nThe following meters are available for nominations:\n420118 BOSTN/TGP BEVERLY SALEM MA ESSEX (CDP 47861)\n420658 MMWEC/TGP PEABODY SALES ESSES"]
["X24-27552","***","2024-07-15","2024-07-15","Completed",null,null,"MLV 270C-103 TO MLV 270C-104","200","6","Pig Runs - MFL-A 7/15","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420118 BOSTN/TGP BEVERLY SALEM MA ESSEX (CDP 47861)\n420658 MMWEC/TGP PEABODY SALES ESSES",270.12,"------","***MLV 270C-103 TO MLV 270C-104:  Pig Runs - MFL-A 7/15\n***Completed\nThe following meters are available for nominations:\n420118 BOSTN/TGP BEVERLY SALEM MA ESSEX (CDP 47861)\n420658 MMWEC/TGP PEABODY SALES ESSES"]
["X24-27554","***","2024-07-15","2024-07-15","Completed",null,null,"MLV 270C-103 TO MLV 270C-104","200","6","Pig Runs - Cal 7/15","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420118 BOSTN/TGP BEVERLY SALEM MA ESSEX (CDP 47861)\n420658 MMWEC/TGP PEABODY SALES ESSES",270.13,"------","***MLV 270C-103 TO MLV 270C-104:  Pig Runs - Cal 7/15\n***Completed\nThe following meters are available for nominations:\n420118 BOSTN/TGP BEVERLY SALEM MA ESSEX (CDP 47861)\n420658 MMWEC/TGP PEABODY SALES ESSES"]
["X24-275161","***","2024-07-08","2024-07-13","Completed",null,null,"MLV 270C-301L to MLV 270C-302R","200","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,270.3,"------","***MLV 270C-301L to MLV 270C-302R:  Anomaly Remediation\n***Completed"]
["X24-27495",null,"2024-08-07","2024-08-07",null,null,null,"MLV 270C-1101 TO MLV 270C-1103","200","6","Pig Re-Runs - Cleaning/Gauge 8/7","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,270.5,null,"MLV 270C-1101 TO MLV 270C-1103:  Pig Re-Runs - Cleaning/Gauge 8/7\n--8/7/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-27499",null,"2024-08-07","2024-08-07",null,null,null,"MLV 270C-1101 TO MLV 270C-1103","200","6","Pig Re-Runs - MFL-A 8/7","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,270.51,null,"MLV 270C-1101 TO MLV 270C-1103:  Pig Re-Runs - MFL-A 8/7\n--8/7/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-201666",null,"2024-09-23","2024-09-30",null,null,null,"Sta 307","300","4","Station Upgrade","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,307,null,"Sta 307:  Station Upgrade\n--9/23/24 through 9/30/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-201664",null,"2024-07-11","2024-10-26",null,null,null,"Sta 307","300","4","Unit 6A - Engine Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,307.00599999999997,null,"Sta 307:  Unit 6A - Engine Upgrade\n--7/11/24 through 10/26/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-275175",null,"2024-09-09","2024-09-27",null,null,null,"MLV 307-1L to MLV 308-1","300","4","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,307.10000000000002,null,"MLV 307-1L to MLV 308-1:  Anomaly Remediation\n--9/9/24 through 9/27/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43880","***","2024-07-11","2024-07-11","Completed",null,null,"MLV 307-2 to MLV 219-3","300","4","Pig Runs - EMAT 7/11","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SIP","Potential in the path restrictions may be at risk.","412464 PINOAK/TGP JACKSON CENTER DEHY MERC\n412871 PINOAK/TGP TIONESTA: RIP 304E 101.2",307.22000000000003,"------","***MLV 307-2 to MLV 219-3:  Pig Runs - EMAT 7/11\n***Completed\nThe following meters are available for nominations:\n412464 PINOAK/TGP JACKSON CENTER DEHY MERC\n412871 PINOAK/TGP TIONESTA: RIP 304E 101.2"]
["X24-275174",null,"2024-08-05","2024-09-06",null,null,null,"MLV 308-1 to MLV 309-1","300","4","Anomaly Remediation","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412872 PINOAK/TGP MT.JEWETT:RIP 308C 101",308.10000000000002,null,"MLV 308-1 to MLV 309-1:  Anomaly Remediation\n--8/5/24 through 9/6/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n412872 PINOAK/TGP MT.JEWETT:RIP 308C 101\n………………………………"]
["X24-275172",null,"2024-07-29","2024-08-03",null,null,null,"MLV 310-1A to MLV 311-1","300","4","Anomaly Remediation","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412805 PA GNRL/TGP WHITE HOLLOW DEHY:RIP 3",310.10000000000002,null,"MLV 310-1A to MLV 311-1:  Anomaly Remediation\n--7/29/24 through 8/3/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n412805 PA GNRL/TGP WHITE HOLLOW DEHY:RIP 3\n………………………………"]
["X24-373549",null,"2024-09-16","2024-09-20",null,null,null,"Sta 313 Coudersport","300","4","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,313,null,"Sta 313 Coudersport:  Annual ESD Test\n--9/16/24 through 9/20/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43965",null,"2024-08-27","2024-08-27",null,null,null,"MLVS 313C-100 Recovery Line","300","4","Pig Runs - Cleaning 8/27","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,313.10000000000002,null,"MLVS 313C-100 Recovery Line:  Pig Runs - Cleaning 8/27\n--8/27/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-640122",null,"2024-09-02","2024-09-06",null,null,null,"MLV 313-1 to MLV 314-1","300","4","Hot Tap for New Meter Station - Greylock Potter Meter","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,313.10000000000002,null,"MLV 313-1 to MLV 314-1:  Hot Tap for New Meter Station - Greylock Potter Meter\n--9/2/24 through 9/6/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43967",null,"2024-08-28","2024-08-28",null,null,null,"MLVS 313C-100 Recovery Line","300","4","Pig Runs - MFL 8/28","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,313.11,null,"MLVS 313C-100 Recovery Line:  Pig Runs - MFL 8/28\n--8/28/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-640124",null,"2024-09-09","2024-09-13",null,null,null,"MLV 313-2 to MLV 314-2","300","4","Hot Tap for New Meter Station - Greylock Potter Meter","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,313.2,null,"MLV 313-2 to MLV 314-2:  Hot Tap for New Meter Station - Greylock Potter Meter\n--9/9/24 through 9/13/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-572316",null,"2024-10-15","2024-10-15",null,null,null,"MLV 313-2 to MLV 307-2","300","4","Pig Runs - Cleaning 10/15","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,313.2,null,"MLV 313-2 to MLV 307-2:  Pig Runs - Cleaning 10/15\n--10/15/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-168776",null,"2024-10-14","2024-10-14",null,null,null,"Sta 405A","300","5","Unit 1A - 4k Water Wash","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,313.52,null,"Sta 405A:  Unit 1A - 4k Water Wash\n--10/14/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-168778",null,"2024-10-16","2024-10-16",null,null,null,"Sta 405A","300","5","Unit 1A - 4K - 8K Solar Turbine Borescope Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,313.52999999999997,null,"Sta 405A:  Unit 1A - 4K - 8K Solar Turbine Borescope Inspection\n--10/16/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43914",null,"2024-08-12","2024-08-28",null,null,null,"MLVS C313-0608","300","4","Pig Runs (Tethered) - Cleaning 8/20","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,313.60000000000002,null,"MLVS C313-0608:  Pig Runs (Tethered) - Cleaning 8/20\n--8/12/24 through 8/28/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43917",null,"2024-08-12","2024-08-28",null,null,null,"MLVS C313-0608","300","4","Pig Runs (Tethered) - MFL 8/21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,313.61,null,"MLVS C313-0608:  Pig Runs (Tethered) - MFL 8/21\n--8/12/24 through 8/28/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-313369",null,"2024-07-22","2024-07-23",null,null,null,"Sta 315","300","4","Unit 1B - Power Supply and Unit Updates","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,315.017,null,"Sta 315:  Unit 1B - Power Supply and Unit Updates\n--7/22/24 through 7/23/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-25473","***","2024-05-14","2024-07-19","Project Change",null,"2024-07-16","Sta. 323A Lackawaxen","300","5","Gas Coolers Piping, Testing, Automation Upgrade","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,321,"----end_date------------model_loc--","***Sta. 323A Lackawaxen:  Gas Coolers Piping, Testing, Automation Upgrade\n--5/14/24 through 7/19/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 5/14/24 to 7/16/24.\n………………………………"]
["X24-744689","***","2024-08-06","2024-08-07","Added",null,null,"Sta. 321","300","4","Unit 6B - Performance Testing","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,321.02300000000002,"------","***Sta. 321:  Unit 6B - Performance Testing\n--8/6/24 through 8/7/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-56067",null,"2024-09-10","2024-09-10",null,null,null,"MLV 321-1 to MLV 325-1","300","4","Pig Runs - Cleaning/Gauge 9/10/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.","420277 UGI UT/TGP HONESDALE PA SALES WAYNE\n420319 UGI UT/TGP MILFORD PA PIKE",321.14999999999998,null,"MLV 321-1 to MLV 325-1:  Pig Runs - Cleaning/Gauge 9/10/24\n--9/10/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n420277 UGI UT/TGP HONESDALE PA SALES WAYNE\n420319 UGI UT/TGP MILFORD PA PIKE\n………………………………"]
["X24-56070",null,"2024-09-12","2024-09-12",null,null,null,"MLV 321-1 to MLV 325-1","300","4","Pig Runs - EMAT 9/12/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.","420277 UGI UT/TGP HONESDALE PA SALES WAYNE\n420319 UGI UT/TGP MILFORD PA PIKE",321.16000000000003,null,"MLV 321-1 to MLV 325-1:  Pig Runs - EMAT 9/12/24\n--9/12/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n420277 UGI UT/TGP HONESDALE PA SALES WAYNE\n420319 UGI UT/TGP MILFORD PA PIKE\n………………………………"]
["X24-741357",null,"2024-07-25","2024-07-25",null,null,null,"Sta 325","300","5","Low Voltage Motor Control Centers","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,325,null,"Sta 325:  Low Voltage Motor Control Centers\n--7/25/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-664583","***","2024-07-10","2024-07-12","Completed",null,null,"Sta 325","300","5","Unit 1B - Turbine Fuel Skid Piping Mods","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,325.017,"------","***Sta 325:  Unit 1B - Turbine Fuel Skid Piping Mods\n***Completed"]
["X24-275177",null,"2024-09-30","2024-10-25",null,null,null,"MLV 326-1 to MLV 327-1","300","5","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,326.10000000000002,null,"MLV 326-1 to MLV 327-1:  Anomaly Remediation\n--9/30/24 through 10/25/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-275178",null,"2024-10-28","2024-11-02",null,null,null,"MLV 328-1 to MLV 328-1R","300","5","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,328.1,null,"MLV 328-1 to MLV 328-1R:  Anomaly Remediation\n--10/28/24 through 11/2/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-269269",null,"2024-07-22","2024-08-01",null,null,null,"MLV 331-2 to MLV 332-2","300","6","Cable Pig Runs - Cleaning/Gauge 7/29/24","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,331.2,null,"MLV 331-2 to MLV 332-2:  Cable Pig Runs - Cleaning/Gauge 7/29/24\n--7/22/24 through 8/1/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-269273",null,"2024-07-22","2024-08-01",null,null,null,"MLV 331-2 to MLV 332-2","300","6","Cable Pig Runs - Caliper 7/30/24","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,331.21,null,"MLV 331-2 to MLV 332-2:  Cable Pig Runs - Caliper 7/30/24\n--7/22/24 through 8/1/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-269276",null,"2024-07-22","2024-08-01",null,null,null,"MLV 331-2 to MLV 332-2","300","6","Cable Pig Runs - MFL 7/30/24","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,331.22,null,"MLV 331-2 to MLV 332-2:  Cable Pig Runs - MFL 7/30/24\n--7/22/24 through 8/1/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-76758",null,"2024-11-05","2024-11-05",null,null,null,"MLV 400-1 to MLV 409-1","400","0","Pig Run - Maintenance Cleaning 11/5","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412733 UES/TGP MYRICK BROOKS",400.13,null,"MLV 400-1 to MLV 409-1:  Pig Run - Maintenance Cleaning 11/5\n--11/5/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n412733 UES/TGP MYRICK BROOKS\n………………………………"]
["X24-76772",null,"2024-11-06","2024-11-06",null,null,null,"MLV 400-2 to MLV 409-2","400","0","Pig Run - Maintenance Cleaning 11/6","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,400.23,null,"MLV 400-2 to MLV 409-2:  Pig Run - Maintenance Cleaning 11/6\n--11/6/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-741321",null,"2024-07-29","2024-08-03",null,null,null,"Sta 405A","300","5","Unit 1A - PLC & HMI Updates","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,405.00099999999998,null,"Sta 405A:  Unit 1A - PLC & HMI Updates\n--7/29/24 through 8/3/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-744489",null,"2024-07-23","2024-07-23",null,null,null,"Sta 409","400","0","Unit 1A - Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,409.00099999999998,null,"Sta 409:  Unit 1A - Engine Inspection\n--7/23/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-609072",null,"2024-07-15","2024-07-20",null,null,null,"Sta 409","400","0","Unit 3A - Engine 8k hr Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,409.00299999999999,null,"Sta 409:  Unit 3A - Engine 8k hr Inspection\n--7/15/24 through 7/20/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-760256","***","2024-08-14","2024-08-15","Added",null,null,"Sta 500C1","500","1","Suction Basket Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,500.00099999999998,"------","***Sta 500C1:  Suction Basket Maintenance\n--8/14/24 through 8/15/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-27873",null,"2024-11-12","2024-11-12",null,null,null,"Sta 500-1 to Sta 823 (MLV 507-1)","500","L","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420373 TRNSCO/TGP KINDER LA EXCH (BI 1\n420708 ELIZ NG/TGP GRANT LA SALES ALLEN\n420436 VERNON/TGP PITKIN LA VERNON\n420793 ELIZ NG/TGP J R FRANKS 1 VERNON\n420388 PROVNCAL/TGP PROVENCAL LA NATCHITOC",500.1,null,"Sta 500-1 to Sta 823 (MLV 507-1):  Pig Run - Maintenance\n--11/12/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n420373 TRNSCO/TGP KINDER LA EXCH (BI 1\n420708 ELIZ NG/TGP GRANT LA SALES ALLEN\n420436 VERNON/TGP PITKIN LA VERNON\n420793 ELIZ NG/TGP J R FRANKS 1 VERNON\n420388 PROVNCAL/TGP PROVENCAL LA NATCHITOC\n………………………………"]
["X24-505572","***","2024-05-28","2024-07-12","Completed",null,null,"MLV 507F-101 to MLV 507F-102","800","L","Make Piggable","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,507,"------","***MLV 507F-101 to MLV 507F-102:  Make Piggable\n***Completed"]
["X24-56013","***","2024-07-16","2024-07-16","Completed",null,null,"STA 507F to Sta 823","500","L","Pig Run - Cleaning/Gauge 7/16/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","410671 TARGA/TGP UDP LOWRY PLANT DEHY CAME",507.1,"------","***STA 507F to Sta 823:  Pig Run - Cleaning/Gauge 7/16/24\n***Completed\nThe following meters are available for nominations:\n410671 TARGA/TGP UDP LOWRY PLANT DEHY CAME"]
["X24-27891",null,"2024-08-07","2024-08-07",null,null,null,"STA 507F to Sta 823","500","L","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","410671 TARGA/TGP UDP LOWRY PLANT DEHY CAME",507.1,null,"STA 507F to Sta 823:  Pig Run - Maintenance\n--8/7/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n410671 TARGA/TGP UDP LOWRY PLANT DEHY CAME\n………………………………"]
["X24-56015","***","2024-07-17","2024-07-17","Completed",null,null,"STA 507F to Sta 823","500","L","Pig Run - AFD 7/17/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","410671 TARGA/TGP UDP LOWRY PLANT DEHY CAME",507.12,"------","***STA 507F to Sta 823:  Pig Run - AFD 7/17/24\n***Completed\nThe following meters are available for nominations:\n410671 TARGA/TGP UDP LOWRY PLANT DEHY CAME"]
["X24-56016",null,"2024-07-18","2024-07-18",null,null,null,"STA 507F to Sta 823","500","L","Pig Run - EMAT 7/18/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","410671 TARGA/TGP UDP LOWRY PLANT DEHY CAME",507.13,null,"STA 507F to Sta 823:  Pig Run - EMAT 7/18/24\n--7/18/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n410671 TARGA/TGP UDP LOWRY PLANT DEHY CAME\n………………………………"]
["X24-637599",null,"2024-07-22","2024-07-27",null,null,null,"MLV 511-1 to MLV 512-1","500","L","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,511.1,null,"MLV 511-1 to MLV 512-1:  Anomaly Remediation\n--7/22/24 through 7/27/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-637601",null,"2024-07-08","2024-07-20",null,null,null,"MLV 513-1 to MLV 514-1","500","L","Anomaly Remediation","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.","PIP","Potential in the path restrictions may be at risk.","420915 SYMMETRY/TGP PORT IBERIA SALES IBER",513.1,null,"MLV 513-1 to MLV 514-1:  Anomaly Remediation\n--7/8/24 through 7/20/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.  Potential in the path restrictions may be at risk.\n420915 SYMMETRY/TGP PORT IBERIA SALES IBER\n………………………………"]
["X23-374936",null,"2024-09-16","2024-09-17",null,null,null,"MLV 527-1 to MLV 529-1","500","L","Pig Runs - Cleaning/Gauge 9/16/24 to 9/17//24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,527.1,null,"MLV 527-1 to MLV 529-1:  Pig Runs - Cleaning/Gauge 9/16/24 to 9/17//24\n--9/16/24 through 9/17/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X23-374937",null,"2024-09-18","2024-09-18",null,null,null,"MLV 527-1 to MLV 529-1","500","L","Pig Runs - Caliper/IMU 9/18/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,527.11,null,"MLV 527-1 to MLV 529-1:  Pig Runs - Caliper/IMU 9/18/24\n--9/18/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X23-374938",null,"2024-09-19","2024-09-20",null,null,null,"MLV 527-1 to MLV 529-1","500","L","Pig Runs - MFL-C 9/19/24 to 9/20/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,527.12,null,"MLV 527-1 to MLV 529-1:  Pig Runs - MFL-C 9/19/24 to 9/20/24\n--9/19/24 through 9/20/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X23-57594",null,"2023-08-14","2024-08-16",null,null,null,"MLV 527-1 to MLV 528-1","500","L","Platform Installation","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,527.15,null,"MLV 527-1 to MLV 528-1:  Platform Installation\n--8/14/23 through 8/16/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-159481","***","2024-06-14","2024-07-11","Completed",null,null,"MLV 527-2 to MLV 528-2","500","L","Restore Piping at MLV 528","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","SIP","Potential in the path restrictions may be at risk.","412654 ELYSIM/TGP POTASH PLAQUEMINES",527.20000000000005,"------","***MLV 527-2 to MLV 528-2:  Restore Piping at MLV 528\n***Completed\nThe following meters are available for nominations:\n412654 ELYSIM/TGP POTASH PLAQUEMINES"]
["X24-159471",null,"2024-06-14","2024-08-16",null,null,null,"MLV 528-1 to MLV 529-1","500","L","Tie-in 500-1 to Platform","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,528.11,null,"MLV 528-1 to MLV 529-1:  Tie-in 500-1 to Platform\n--6/14/24 through 8/16/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X23-587635",null,"2023-06-01","2024-08-01",null,null,null,"Sta 530","500","L","Units 2A, 4A & 8A - Automation Upgrade","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,530,null,"Sta 530:  Units 2A, 4A & 8A - Automation Upgrade\n--6/1/23 through 8/1/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-1164310","***","2024-05-13","2024-07-23","Project Change",null,"2024-07-18","MLV 530-1 to MLV 531-1","500","L","Pipe Replacement, Meter Tie-In, Replace MLV 531-1, Tap Removal","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,530.1,"----end_date------------model_loc--","***MLV 530-1 to MLV 531-1:  Pipe Replacement, Meter Tie-In, Replace MLV 531-1, Tap Removal\n--5/13/24 through 7/23/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***\nDate Change, Previously scheduled 5/13/24 to 7/18/24.\n………………………………"]
["X24-741377",null,"2024-07-29","2024-07-31",null,null,null,"MLV 530-2 to MLV 531-2","500","L","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,530.20000000000005,null,"MLV 530-2 to MLV 531-2:  Anomaly Remediation\n--7/29/24 through 7/31/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-27804",null,"2024-08-31","2024-09-30",null,null,null,"MLV 531-1 to MLV 532-1","500","L","High Priority Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,531.1,null,"MLV 531-1 to MLV 532-1:  High Priority Anomaly Remediation\n--8/31/24 through 9/30/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-1164314","***","2024-04-30","2024-07-11","Completed",null,null,"MLV 532-1 to MLV 534-1","500","L","Replace MLV 532-1 & MLV 533-1, Hydrotest Line 1 532 to 534","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,532.1,"------","***MLV 532-1 to MLV 534-1:  Replace MLV 532-1 & MLV 533-1, Hydrotest Line 1 532 to 534\n***Completed"]
["X24-741374",null,"2024-07-15","2024-07-19",null,null,null,"MLV 532-2 to MLV 533-2","500","L","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,532.20000000000005,null,"MLV 532-2 to MLV 533-2:  Anomaly Remediation\n--7/15/24 through 7/19/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-1164316","***","2024-05-02","2024-07-23","Project Change",null,"2024-07-20","MLV 533-1 to CS 534-1","500","L","Replace MLV 533-1A, tie-in FGT Tap,  Hydrotest Line 1 532 to 534","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420366 FGT/TGP CARNES MISSISSIPPE STONE",533.1,"----end_date------------model_loc--","***MLV 533-1 to CS 534-1:  Replace MLV 533-1A, tie-in FGT Tap,  Hydrotest Line 1 532 to 534\n--5/2/24 through 7/23/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n420366 FGT/TGP CARNES MISSISSIPPE STONE\n***\nDate Change, Previously scheduled 5/2/24 to 7/20/24.\n………………………………"]
["X24-741376","***","2024-07-24","2024-07-28","Project Change","2024-07-22","2024-07-26","MLV 533-2 to MLV 534-2","500","L","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,533.20000000000005,"--start_date--end_date------------model_loc--","***MLV 533-2 to MLV 534-2:  Anomaly Remediation\n--7/24/24 through 7/28/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 7/22/24 to 7/26/24.\n………………………………"]
["X23-1078699",null,"2023-10-25","2025-01-19",null,null,null,"MLV 535-1A to MLV 536-1","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,535.1,null,"MLV 535-1A to MLV 536-1:  Anomaly Remediation\n--10/25/23 through 1/19/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-383750","***","2024-05-01","2024-07-12","Completed",null,null,"MLV 538-1 to MLV 538-1","500","1","New Meter Hot Tap MEP PIN 44577","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","44577 TGP/MEP JASPER",538.1,"------","***MLV 538-1 to MLV 538-1:  New Meter Hot Tap MEP PIN 44577\n***Completed\nThe following meters are available for nominations:\n44577 TGP/MEP JASPER"]
["X24-383752","***","2024-05-01","2024-07-12","Completed",null,null,"MLV 538-2 to MLV 538-2","500","1","New Meter Hot Tap MEP PIN 44577","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","44577 TGP/MEP JASPER",538.20000000000005,"------","***MLV 538-2 to MLV 538-2:  New Meter Hot Tap MEP PIN 44577\n***Completed\nThe following meters are available for nominations:\n44577 TGP/MEP JASPER"]
["X24-41546",null,"2024-09-10","2024-09-10",null,null,null,"MLV 538-2 to MLV 534-2","500","1","Pig Runs - Cleaning/Gauge 9/10","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,538.20000000000005,null,"MLV 538-2 to MLV 534-2:  Pig Runs - Cleaning/Gauge 9/10\n--9/10/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-41547",null,"2024-09-12","2024-09-12",null,null,null,"MLV 538-2 to MLV 534-2","500","1","Pig Runs - MFL 9/12","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,538.21,null,"MLV 538-2 to MLV 534-2:  Pig Runs - MFL 9/12\n--9/12/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-760111","***","2024-07-15","2024-07-18","Added",null,null,"Sta 542","500","1","Unit 2A - Compressor","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,542.00199999999995,"------","***Sta 542:  Unit 2A - Compressor\n--7/15/24 through 7/18/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-94907",null,"2024-02-12","2024-09-30",null,null,null,"Sta 542","500","1","Unit 3A - Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,542.00300000000004,null,"Sta 542:  Unit 3A - Overhaul\n--2/12/24 through 9/30/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-38912",null,"2023-11-30","2024-08-31",null,null,null,"Sta 542","200","1","Unit 4A - Replace Compressor Heads & Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,542.00400000000002,null,"Sta 542:  Unit 4A - Replace Compressor Heads & Engine Inspection\n--11/30/23 through 8/31/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-41548",null,"2024-09-17","2024-09-17",null,null,null,"MLV 542-2 to MLV 538-2","500","1","Pig Runs - Cleaning/Gauge 9/17","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","PIP","Potential in the path restrictions may be at risk.",null,542.20000000000005,null,"MLV 542-2 to MLV 538-2:  Pig Runs - Cleaning/Gauge 9/17\n--9/17/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-41549",null,"2024-09-19","2024-09-19",null,null,null,"MLV 542-2 to MLV 538-2","500","1","Pig Runs - MFL 9/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","PIP","Potential in the path restrictions may be at risk.",null,542.21,null,"MLV 542-2 to MLV 538-2:  Pig Runs - MFL 9/19\n--9/19/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-166994",null,"2024-02-15","2024-09-30",null,null,null,"Sta 546","500","1","Unit 3A - Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,546.00300000000004,null,"Sta 546:  Unit 3A - Overhaul\n--2/15/24 through 9/30/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-38915",null,"2024-04-30","2024-09-30",null,null,null,"Sta 546","500","1","Unit 3A - Discharge Valve","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,546.00300000000004,null,"Sta 546:  Unit 3A - Discharge Valve\n--4/30/24 through 9/30/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-760185","***","2024-07-09","2024-07-31","Added",null,null,"Sta 546","500","1","Unit 7A - Oil System","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,546.00699999999995,"------","***Sta 546:  Unit 7A - Oil System\n--7/9/24 through 7/31/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-568884",null,"2024-05-27","2024-07-19",null,null,null,"Sta 546","500","1","Unit 1B - Compressor Seal","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,546.01700000000005,null,"Sta 546:  Unit 1B - Compressor Seal\n--5/27/24 through 7/19/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-517419",null,"2024-08-08","2024-09-04",null,null,null,"MLV 546-1 to MLV 546-1A","500","1","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,546.1,null,"MLV 546-1 to MLV 546-1A:  Pipe Replacement\n--8/8/24 through 9/4/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-138233",null,"2024-09-30","2024-10-04",null,null,null,"Sta 550 Hamilton","500","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,550,null,"Sta 550 Hamilton:  Annual ESD Test\n--9/30/24 through 10/4/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-293538",null,"2024-10-01","2024-10-05",null,null,null,"Sta 550","500","1","Fuel Coalescer","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,550,null,"Sta 550:  Fuel Coalescer\n--10/1/24 through 10/5/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-293542",null,"2024-10-01","2024-10-05",null,null,null,"Sta 550","500","1","UPS Upgrade for Sta1 & Hyper Fuel System","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,550,null,"Sta 550:  UPS Upgrade for Sta1 & Hyper Fuel System\n--10/1/24 through 10/5/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-293543",null,"2024-10-01","2024-10-05",null,null,null,"Sta 550","500","2","480V Feed to 550-2 Vlave","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,550,null,"Sta 550:  480V Feed to 550-2 Vlave\n--10/1/24 through 10/5/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-262272",null,"2024-07-22","2024-07-27",null,null,null,"Sta 550","500","1","Unit 2A Turbocharger Replacement 30K OEM","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,550.00199999999995,null,"Sta 550:  Unit 2A Turbocharger Replacement 30K OEM\n--7/22/24 through 7/27/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-326894",null,"2024-09-30","2024-10-04",null,null,null,"Sta 550","500","1","Unit 2A - Lube System Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,550.00199999999995,null,"Sta 550:  Unit 2A - Lube System Replacement\n--9/30/24 through 10/4/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-293537",null,"2024-08-26","2024-08-30",null,null,null,"Sta 550","500","1","Unit 1B Safety Device Checks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,550.01700000000005,null,"Sta 550:  Unit 1B Safety Device Checks\n--8/26/24 through 8/30/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-746842","***","2024-08-02","2024-08-06","Added",null,null,"MLV 552-1 to MLV 553-1","500","1","Anomaly Remediation / Replacement","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,552.1,"------","***MLV 552-1 to MLV 553-1:  Anomaly Remediation / Replacement\n--8/2/24 through 8/6/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-140863",null,"2024-08-12","2024-08-16",null,null,null,"Sta 555 Collinwood","500","1","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,555,null,"Sta 555 Collinwood:  Annual ESD Test & Maintenance\n--8/12/24 through 8/16/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-327003",null,"2024-09-02","2024-09-20",null,null,null,"Sta 555","500","1","Unit 3A - Exhaust System","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,555.00300000000004,null,"Sta 555:  Unit 3A - Exhaust System\n--9/2/24 through 9/20/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-484573",null,"2024-05-01","2025-05-30",null,null,null,"Sta 555","500","1","Unit 4A - Foundation Regrout","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,555.00400000000002,null,"Sta 555:  Unit 4A - Foundation Regrout\n--5/1/24 through 5/30/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-64058",null,"2024-08-05","2024-08-09",null,null,null,"Sta 555","500","1","Unit 1B - Combustion Liner Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,555.01700000000005,null,"Sta 555:  Unit 1B - Combustion Liner Inspection\n--8/5/24 through 8/9/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-671156",null,"2024-09-17","2024-09-17",null,null,null,"MLV 555-1 to MLV 550-1","500","1","Pig Runs - Cleaning 9/17","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,555.1,null,"MLV 555-1 to MLV 550-1:  Pig Runs - Cleaning 9/17\n--9/17/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-56044",null,"2024-09-23","2024-09-23",null,null,null,"MLV 555-1 to MLV 550-1","500","1","Pig Runs - MFL-C 9/23","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,555.11,null,"MLV 555-1 to MLV 550-1:  Pig Runs - MFL-C 9/23\n--9/23/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-56046",null,"2024-09-25","2024-09-25",null,null,null,"MLV 555-1 to MLV 550-1","500","1","Pig Runs - EMAT 9/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,555.12,null,"MLV 555-1 to MLV 550-1:  Pig Runs - EMAT 9/25\n--9/25/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-56052",null,"2024-12-03","2024-12-03",null,null,null,"MLV 555-2 to MLV 550-2","500","1","Pig Runs - Cleaning 12/3","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,555.20000000000005,null,"MLV 555-2 to MLV 550-2:  Pig Runs - Cleaning 12/3\n--12/3/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-56042",null,"2024-12-05","2024-12-05",null,null,null,"MLV 555-2 to MLV 550-2","500","1","Pig Runs - Caliper/IMU 12/5","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,555.21,null,"MLV 555-2 to MLV 550-2:  Pig Runs - Caliper/IMU 12/5\n--12/5/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-56053",null,"2024-12-09","2024-12-09",null,null,null,"MLV 555-2 to MLV 550-2","500","1","Pig Runs - MFL-C 12/9","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,555.21,null,"MLV 555-2 to MLV 550-2:  Pig Runs - MFL-C 12/9\n--12/9/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-56054",null,"2024-12-11","2024-12-11",null,null,null,"MLV 555-2 to MLV 550-2","500","1","Pig Runs - EMAT 12/11","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,555.22,null,"MLV 555-2 to MLV 550-2:  Pig Runs - EMAT 12/11\n--12/11/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-56049",null,"2024-08-22","2024-08-22",null,null,null,"MLV 558-1R to MLV 555-1R","500","1","Pig Runs - Cleaning 8/22/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420905 ETNG/TGP ETN 500 LINE INTERCONNECT",558.1,null,"MLV 558-1R to MLV 555-1R:  Pig Runs - Cleaning 8/22/24\n--8/22/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n420905 ETNG/TGP ETN 500 LINE INTERCONNECT\n………………………………"]
["X24-56050",null,"2024-08-26","2024-08-26",null,null,null,"MLV 558-1R to MLV 555-1R","500","1","Pig Runs - MFL-C 8/26/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420905 ETNG/TGP ETN 500 LINE INTERCONNECT",558.11,null,"MLV 558-1R to MLV 555-1R:  Pig Runs - MFL-C 8/26/24\n--8/26/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n420905 ETNG/TGP ETN 500 LINE INTERCONNECT\n………………………………"]
["X24-56051",null,"2024-08-28","2024-08-28",null,null,null,"MLV 558-1R to MLV 555-1R","500","1","Pig Runs - EMAT 8/28/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420905 ETNG/TGP ETN 500 LINE INTERCONNECT",558.12,null,"MLV 558-1R to MLV 555-1R:  Pig Runs - EMAT 8/28/24\n--8/28/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n420905 ETNG/TGP ETN 500 LINE INTERCONNECT\n………………………………"]
["X24-296276",null,"2024-09-23","2024-12-02",null,null,null,"MLV 560-1 to MLV 561-1","500","1","Class Change","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,560.1,null,"MLV 560-1 to MLV 561-1:  Class Change\n--9/23/24 through 12/2/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-296275",null,"2024-09-05","2024-09-19",null,null,null,"MLV 562-1 to MLV 563-1","500","1","Class Change","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,562.1,null,"MLV 562-1 to MLV 563-1:  Class Change\n--9/5/24 through 9/19/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-324449","***","2024-07-08","2024-07-19","Project Change",null,"2024-07-15","Sta 563","500","1","Hydronic Heater Inspection","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,563,"----end_date------------model_loc--","***Sta 563:  Hydronic Heater Inspection\n--7/8/24 through 7/19/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***\nDate Change, Previously scheduled 7/8/24 to 7/15/24.\n………………………………"]
["X24-324509","***","2024-07-15","2024-07-16","Completed",null,null,"Sta 563","500","1","Scrubber Filter Inspection/Change Out","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,563,"------","***Sta 563:  Scrubber Filter Inspection/Change Out\n***Completed"]
["X24-324440",null,"2024-08-06","2024-08-08",null,null,null,"Sta 563 Joelton","500","1","Solar Annual Safety Checks","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,563,null,"Sta 563 Joelton:  Solar Annual Safety Checks\n--8/6/24 through 8/8/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-324515",null,"2024-09-09","2024-09-12",null,null,null,"Sta 563","500","1","Quarterly Safety Checks","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,563,null,"Sta 563:  Quarterly Safety Checks\n--9/9/24 through 9/12/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-324518",null,"2024-11-04","2024-11-08",null,null,null,"Sta 563","500","1","Quarterly Safety Checks","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,563,null,"Sta 563:  Quarterly Safety Checks\n--11/4/24 through 11/8/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-74995",null,"2024-09-16","2024-10-14",null,null,null,"Sta 563","500","1","Unit 1A - Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,563.00099999999998,null,"Sta 563:  Unit 1A - Overhaul\n--9/16/24 through 10/14/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-296259",null,"2024-06-26","2024-08-16",null,null,null,"MLV 564-1 to MLV 565-1","500","1","Class Change","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,564,null,"MLV 564-1 to MLV 565-1:  Class Change\n--6/26/24 through 8/16/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-658715",null,"2024-08-19","2024-08-30",null,null,null,"MLV 564-2","500","2","Valve Repair","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,564.20000000000005,null,"MLV 564-2:  Valve Repair\n--8/19/24 through 8/30/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-760254","***","2024-08-12","2024-08-13","Added",null,null,"Sta 703","100","0","Unit 1A - Water Wash & Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,703.00099999999998,"------","***Sta 703:  Unit 1A - Water Wash & Inspection\n--8/12/24 through 8/13/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-626384",null,"2024-11-07","2024-11-07",null,null,null,"MLV 706-1 to MLV 700-1","100","0","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412819 LOUISMID/TGP CONVERSE CENTRAL: RIP\n410031 ETX GAS/TGP EAST TX PLANT DEHY PANO",706.1,null,"MLV 706-1 to MLV 700-1:  Pig Run - Maintenance\n--11/7/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n412819 LOUISMID/TGP CONVERSE CENTRAL: RIP\n410031 ETX GAS/TGP EAST TX PLANT DEHY PANO\n………………………………"]
["X24-255276",null,"2024-08-05","2024-08-15",null,null,null,"MLV 821-1 to MLV 823-1","800","L","SCCDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,821.1,null,"MLV 821-1 to MLV 823-1:  SCCDA\n--8/5/24 through 8/15/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-741385",null,"2024-07-08","2024-07-31",null,null,null,"Sta 823","800","L","Unit 1A - Turbo Charger Exchange","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,823.00099999999998,null,"Sta 823:  Unit 1A - Turbo Charger Exchange\n--7/8/24 through 7/31/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-741384",null,"2024-07-08","2024-07-22",null,null,null,"Sta 823","800","L","Unit 2A - Compressor Rod and Packing","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,823.00199999999995,null,"Sta 823:  Unit 2A - Compressor Rod and Packing\n--7/8/24 through 7/22/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-431936",null,"2024-04-29","2024-07-29",null,null,null,"Sta 823","800","L","Unit 12A - Turbo Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,823.01199999999994,null,"Sta 823:  Unit 12A - Turbo Overhaul\n--4/29/24 through 7/29/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-27930",null,"2024-08-08","2024-08-08",null,null,null,"STA 823 to STA 507K","500","L","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420493\tCOKINOS/TGP MALLETT FARM LA JEFFERS",823.1,null,"STA 823 to STA 507K:  Pig Run - Maintenance\n--8/8/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n420493\tCOKINOS/TGP MALLETT FARM LA JEFFERS\n………………………………"]
["X24-27837",null,"2024-09-11","2024-09-11",null,null,null,"Sta 823 to MLV 516","500","L","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412398 JEFFSTOR/TGP JEFFERSON ISLAND IBERI\n420915 CEGS/TGP PORT IBERIA SALES IBERIA\n421056 ACADIAN/TGP INDIAN BAYOU: DIP 510B-\n412594 NAUTILUS/TGP GARDEN CITY ST MARY\n412684 ANR/TGP SHADYSIDE ST MARY",823.1,null,"Sta 823 to MLV 516:  Pig Run - Maintenance\n--9/11/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n412398 JEFFSTOR/TGP JEFFERSON ISLAND IBERI\n420915 CEGS/TGP PORT IBERIA SALES IBERIA\n421056 ACADIAN/TGP INDIAN BAYOU: DIP 510B-\n412594 NAUTILUS/TGP GARDEN CITY ST MARY\n412684 ANR/TGP SHADYSIDE ST MARY\n………………………………"]
["X24-27939",null,"2024-10-16","2024-10-16",null,null,null,"Sta 827 to Sta 823","800","L","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","421043 PINE PRA/TGP PINE PRAIRIE NORTH RAP\n412847 ACADIAN/TGP CHENEYVILLE RAPIDES\n412713 HUGHES E/TGP UDP BLACK STONE13 EVAN \n412844 TEXLA/TGP ROY MARTIN GATHERING: RIP\n420296 FORSTHIL/TGP FOREST HILL LA RAPIDES\n420530 GLNMORA/TGP GLENMORA LA EXCH RAPIDE\n421042 ELIZ NG/TGP EVANGELINE SALES EVANGE\n420629 ELIZ NG/TGP OAKDALE DETENTION SALES\n420687 ELIZ NG/TGP ALLEN PARISH PRISON SAL\n420406 ELIZ NG/TGP ELIZABETH LA EMERGENCY\n53483 AIRLIQAT/TGP TIMBERLANE BIOGAS REC",827.1,null,"Sta 827 to Sta 823:  Pig Run - Maintenance\n--10/16/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n421043 PINE PRA/TGP PINE PRAIRIE NORTH RAP\n412847 ACADIAN/TGP CHENEYVILLE RAPIDES\n412713 HUGHES E/TGP UDP BLACK STONE13 EVAN \n412844 TEXLA/TGP ROY MARTIN GATHERING: RIP\n420296 FORSTHIL/TGP FOREST HILL LA RAPIDES\n420530 GLNMORA/TGP GLENMORA LA EXCH RAPIDE\n421042 ELIZ NG/TGP EVANGELINE SALES EVANGE\n420629 ELIZ NG/TGP OAKDALE DETENTION SALES\n420687 ELIZ NG/TGP ALLEN PARISH PRISON SAL\n420406 ELIZ NG/TGP ELIZABETH LA EMERGENCY\n53483 AIRLIQAT/TGP TIMBERLANE BIOGAS REC\n………………………………"]
["X24-140937",null,"2024-09-04","2024-09-04",null,null,null,"Sta 834 Winnsboro","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,834,null,"Sta 834 Winnsboro:  Annual ESD Test\n--9/4/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-293337",null,"2024-08-05","2024-08-09",null,null,null,"Sta 834","100","1","Unit 1A - Replace Lubrication System","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,834.00099999999998,null,"Sta 834:  Unit 1A - Replace Lubrication System\n--8/5/24 through 8/9/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-640608",null,"2024-09-02","2024-09-06",null,null,null,"Sta 834","100","1","Unit 1A - 12K Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,834.00099999999998,null,"Sta 834:  Unit 1A - 12K Engine Inspection\n--9/2/24 through 9/6/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-293339",null,"2024-08-05","2024-08-09",null,null,null,"Sta 834",null,null,"Unit 2A- Replace Lubrication System","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,834.00199999999995,null,"Sta 834:  Unit 2A- Replace Lubrication System\n--8/5/24 through 8/9/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-640612",null,"2024-08-26","2024-08-30",null,null,null,"Sta 834","800","1","Unit 2A - 12K Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,834.00199999999995,null,"Sta 834:  Unit 2A - 12K Engine Inspection\n--8/26/24 through 8/30/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-449272",null,"2024-04-29","2024-07-31",null,null,null,"Sta 834","800","1","Unit 5A - Full Main Bearing Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,834.005,null,"Sta 834:  Unit 5A - Full Main Bearing Replacement\n--4/29/24 through 7/31/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-262253",null,"2024-04-29","2024-07-31",null,null,null,"Sta 834","800","1","Unit 5A - 30K OEM Turbocharger Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,834.005,null,"Sta 834:  Unit 5A - 30K OEM Turbocharger Replacement\n--4/29/24 through 7/31/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-741368",null,"2024-06-01","2024-07-31",null,null,null,"Sta 834","800","1","Unit 7A - Hyper Fuel","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,834.00699999999995,null,"Sta 834:  Unit 7A - Hyper Fuel\n--6/1/24 through 7/31/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-255333",null,"2024-10-16","2024-10-16",null,null,null,"Sta 834 to Sta 827","800","L","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420755 ATMOS TL/TGP LASALLE PARISH NEBO SA\n420447 PELICANG/TGP HARRISONBURG LA CATAHO",834.11,null,"Sta 834 to Sta 827:  Maintenance Pig\n--10/16/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n420755 ATMOS TL/TGP LASALLE PARISH NEBO SA\n420447 PELICANG/TGP HARRISONBURG LA CATAHO\n………………………………"]
["X24-140946",null,"2024-09-10","2024-09-10",null,null,null,"Sta 836A Delhi","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,836,null,"Sta 836A Delhi:  Annual ESD Test\n--9/10/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-140939",null,"2024-09-12","2024-09-12",null,null,null,"Sta 838 Transylvania","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,838,null,"Sta 838 Transylvania:  Annual ESD Test\n--9/12/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-293576",null,"2024-08-12","2024-08-16",null,null,null,"Sta 847","800","1","Sub-Station Transformer Inspection and Motor Cleaning","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,847,null,"Sta 847:  Sub-Station Transformer Inspection and Motor Cleaning\n--8/12/24 through 8/16/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-138225",null,"2024-08-20","2024-08-21",null,null,null,"Sta 847 Coffeeville","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,847,null,"Sta 847 Coffeeville:  Annual ESD Test\n--8/20/24 through 8/21/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-293581",null,"2024-08-20","2024-08-21",null,null,null,"Sta 851","800","1","UPS Upgrade for STA1","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,851,null,"Sta 851:  UPS Upgrade for STA1\n--8/20/24 through 8/21/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-138240",null,"2024-10-08","2024-10-08",null,null,null,"Sta 851 New Albany","500","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,851,null,"Sta 851 New Albany:  Annual ESD Test\n--10/8/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-293578",null,"2024-09-09","2024-09-14",null,null,null,"Sta 851","800","1","Unit 1A - Air Intake Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,851.00099999999998,null,"Sta 851:  Unit 1A - Air Intake Replacement\n--9/9/24 through 9/14/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-293579",null,"2024-09-09","2024-09-14",null,null,null,"Sta 851","800","1","Unit 2A - Air Intake Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,851.00199999999995,null,"Sta 851:  Unit 2A - Air Intake Replacement\n--9/9/24 through 9/14/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-293580",null,"2024-09-09","2024-09-14",null,null,null,"Sta 851","800","1","Unit 2A - Exhaust Silencer Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,851.00199999999995,null,"Sta 851:  Unit 2A - Exhaust Silencer Replacement\n--9/9/24 through 9/14/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-282537",null,"2024-09-01","2024-09-30",null,null,null,"MLV 853-1 to MLV 854-1","800","1","Make Piggable","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meterS listed may be restricted or shut in during the project.","PIP","Potential in the path restrictions may be at risk.","420705 CORINTH/TGP NORTH CORINTH MS ALCORN\n420058 BBT ALTN/TGP CORINTH MS ALCORN\n420802 KIMBERLY/TGP KIMBERLY CLARK SMS ALC",853.1,null,"MLV 853-1 to MLV 854-1:  Make Piggable\n--9/1/24 through 9/30/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meterS listed may be restricted or shut in during the project.  Potential in the path restrictions may be at risk.\n420705 CORINTH/TGP NORTH CORINTH MS ALCORN\n420058 BBT ALTN/TGP CORINTH MS ALCORN\n420802 KIMBERLY/TGP KIMBERLY CLARK SMS ALC\n………………………………"]
["X23-841261",null,"2023-08-18","TBD",null,null,null,"Sta 860","800","1","Force Majeure","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,860,null,"Sta 860:  Force Majeure\n--8/18/23 through 12/31/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-386317",null,"2024-09-16","2024-09-27",null,null,null,"Sta 860","800","1","HP Replacement","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,860,null,"Sta 860:  HP Replacement\n--9/16/24 through 9/27/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-501214",null,"2024-09-16","2024-09-17",null,null,null,"Sta 860","800",null,"Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,860,null,"Sta 860:  Annual ESD Test\n--9/16/24 through 9/17/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-640564",null,"2024-06-17","2024-07-31",null,null,null,"Sta 860","800","1","Unit 1A - After Cooler","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,860.00099999999998,null,"Sta 860:  Unit 1A - After Cooler\n--6/17/24 through 7/31/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-640558",null,"2024-06-17","2024-08-23",null,null,null,"Sta 860","800","1","Unit 5A - Crank-end Head Gasket","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,860.005,null,"Sta 860:  Unit 5A - Crank-end Head Gasket\n--6/17/24 through 8/23/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-671281",null,"2024-07-15","2024-07-19",null,null,null,"Sta 860","800","1","Unit 1B - Engine Fuel Valve Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,860.01700000000005,null,"Sta 860:  Unit 1B - Engine Fuel Valve Replacement\n--7/15/24 through 7/19/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-296274",null,"2024-08-21","2024-09-02",null,null,null,"MLV 863-1 to MLV 864-1","800","1","Class Change","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,863.1,null,"MLV 863-1 to MLV 864-1:  Class Change\n--8/21/24 through 9/2/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-616019","***","2024-07-08","2024-07-12","Completed",null,null,"MLV 864A-101.1","800","1","Adding 2\" Tap","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,864.1,"------","***MLV 864A-101.1:  Adding 2\" Tap\n***Completed"]
["X24-75020",null,"2024-06-11","2024-07-29",null,null,null,"MLV 868-1 to MLV 869-1","800","2","Class Change","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,868.1,null,"MLV 868-1 to MLV 869-1:  Class Change\n--6/11/24 through 7/29/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-140917",null,"2024-08-06","2024-08-06",null,null,null,"Sta 871A Campbellsville","100","2","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,871.00009999999997,null,"Sta 871A Campbellsville:  Annual ESD Test\n--8/6/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-56059",null,"2024-07-30","2024-07-30",null,null,null,"MLV 871-2 to MLV 867-2","800","2","Pig Runs - Cleaning 7/30/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420885 NATGASKY/TGP UDP ALLEN CNTY SALES A",871.2,null,"MLV 871-2 to MLV 867-2:  Pig Runs - Cleaning 7/30/24\n--7/30/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n420885 NATGASKY/TGP UDP ALLEN CNTY SALES A\n………………………………"]
["X24-56061",null,"2024-08-01","2024-08-01",null,null,null,"MLV 871-2 to MLV 867-2","800","2","Pig Runs - Caliper/IMU/MFL-A 8/1/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420885 NATGASKY/TGP UDP ALLEN CNTY SALES A",871.21,null,"MLV 871-2 to MLV 867-2:  Pig Runs - Caliper/IMU/MFL-A 8/1/24\n--8/1/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n420885 NATGASKY/TGP UDP ALLEN CNTY SALES A\n………………………………"]
["X24-307538",null,"2024-08-19","2024-08-30",null,null,null,"MLV 872-2 to MLV 873-2","800","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,873.2,null,"MLV 872-2 to MLV 873-2:  Anomaly Remediation\n--8/19/24 through 8/30/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-684295","***","2024-07-16","2024-07-17","Completed",null,null,"Sta 875","800","2","Unit 1A - Fuel Skid Filter System","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,875.00099999999998,"------","***Sta 875:  Unit 1A - Fuel Skid Filter System\n***Completed"]

{"sheet":"Sheet2","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}

{"sheet":"Sheet3","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}