{"text_format":"1","workbook":"xlsx","n_sheets":4,"sheets":["Closed","Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":8,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Closed","index":0,"n_rows":37,"n_cols":22,"rows_kept":37,"cut":false,"hidden":true,"merged":[[1,3,1,15],[2,3,2,15],[3,3,3,15]]}
[null,null,null,"Updated ","2016"]
[null,null,null,"Tennessee Gas Pipeline 2015 Pipeline Outage and Maintenance Summary"]
[null,null,null,"This is a summary of the current status of all TGP Winter 2014-2015 Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  Additionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
[null,null,null,"*** Indicates revision"]
["Date Change","Project New/Completed/Closed","Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","Location","Leg","Zone","Maintenance Activity","Anticipated Impact","Potential Restriction Level","TOS Potential Restrictions","Meter(s) in Impacted Area","Customer Notifications","Loc","Email Text","Posting Text","Completion Text"]
[{"$f":"IF(AND(H6<>\"\",I6<>\"\"), \"Date change. Previously scheduled \" & TEXT(H6,\"m/d/y;@\") &IF(H6=I6,\"\",\" to \" & TEXT(I6,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed",null,{"$f":"IF(G6<>\"\",\"***\",\"\")","v":"***"},"2015-01-11","2016-01-11",{"$f":"IF(AND(A6=\"\",B6=\"\"),\"\",IF(B6=\"\",A6,B6))","v":"Project Completed"},null,null,"MS #412494 DCP Warren","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412494 DCP Warren",401,{"$f":"\"(\"&C6&\") \"&J6&\":  \"&M6&IF(AND(E6=\"\",F6=\"\"),\"\",\" (\")&IF(E6=\"\",\"\",\"\"&TEXT(E6,\"m/d/y;@\"))&IF(OR(F6=E6,E6=\"\",F6=\"\"),\"\",\" to \")&IF(OR(F6=\"\",F6=E6),\"\",TEXT(F6,\"m/d/y;@\"))&IF(AND(E6=\"\",F6=\"\"),\"\",\")\")","v":"() MS #412494 DCP Warren:  Meter Station (1/11/15 to 1/11/16)"},{"$f":"D6&J6&\":  \"&M6&IF(AND(E6=\"\",F6=\"\"),\"\",\"\n\")&IF(E6=\"\",\"\",\"--\"&TEXT(E6,\"m/d/y;@\"))&IF(OR(F6=E6,E6=\"\",F6=\"\"),\"\",\" through \")&IF(OR(F6=\"\",F6=E6),\"\",TEXT(F6,\"m/d/y;@\"))&IF(AND(E6=\"\",F6=\"\"),\"\",\":  \")&N6&\"  \"&P6&IF(Q6=\"\",\"\",\"\n\"&Q6)&IF(G6=\"\",\"\",\"\n***\")&G6&\"\n………………………………\"","v":"***MS #412494 DCP Warren:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412494 DCP Warren\n***Project Completed\n………………………………"},{"$f":"D6&J6&\":  \"&M6&IF(G6=\"\",\"\",\"\n***\")&G6&IF(Q6=\"\",\"\",\"\nThe following meters are available for nominations:\n\")&Q6&\"\n………………………………\"","v":"***MS #412494 DCP Warren:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412494 DCP Warren\n………………………………"}]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412400 King Ranch","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412400 King Ranch",402.1,"() MS #412400 King Ranch:  Meter Station (1/11/15 to 1/11/16)","***MS #412400 King Ranch:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412400 King Ranch\n***Project Completed\n………………………………","***MS #412400 King Ranch:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412400 King Ranch\n………………………………"]
["","Project Completed",null,"***","2015-01-12","2016-01-12","Project Completed",null,null,"MS #410539 Duvak Gas Gathering","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410539 Duvak Gas Gathering",402.1,"() MS #410539 Duvak Gas Gathering:  Meter Station (1/12/15 to 1/12/16)","***MS #410539 Duvak Gas Gathering:  Meter Station\n--1/12/15 through 1/12/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410539 Duvak Gas Gathering\n***Project Completed\n………………………………","***MS #410539 Duvak Gas Gathering:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n410539 Duvak Gas Gathering\n………………………………"]
["","Project Completed",null,"***","2015-01-13","2016-01-13","Project Completed",null,null,"MS #412356 DCP LaGloria","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412356 DCP LaGloria",403.1,"() MS #412356 DCP LaGloria:  Meter Station (1/13/15 to 1/13/16)","***MS #412356 DCP LaGloria:  Meter Station\n--1/13/15 through 1/13/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412356 DCP LaGloria\n***Project Completed\n………………………………","***MS #412356 DCP LaGloria:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412356 DCP LaGloria\n………………………………"]
["","Project Completed",null,"***","2015-01-13","2016-01-13","Project Completed",null,null,"MS #410173 Enterprise LaReforma","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410173 Enterprise LaReforma",406.1,"() MS #410173 Enterprise LaReforma:  Meter Station (1/13/15 to 1/13/16)","***MS #410173 Enterprise LaReforma:  Meter Station\n--1/13/15 through 1/13/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410173 Enterprise LaReforma\n***Project Completed\n………………………………","***MS #410173 Enterprise LaReforma:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n410173 Enterprise LaReforma\n………………………………"]
["","Project Completed",null,"***","2015-01-12","2016-01-12","Project Completed",null,null,"MS #411903 Enterprise El Benito","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","411903 Enterprise El Benito",407.1,"() MS #411903 Enterprise El Benito:  Meter Station (1/12/15 to 1/12/16)","***MS #411903 Enterprise El Benito:  Meter Station\n--1/12/15 through 1/12/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n411903 Enterprise El Benito\n***Project Completed\n………………………………","***MS #411903 Enterprise El Benito:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n411903 Enterprise El Benito\n………………………………"]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412088 Enterprise Sullivan","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412088 Enterprise Sullivan",407.1,"() MS #412088 Enterprise Sullivan:  Meter Station (1/11/15 to 1/11/16)","***MS #412088 Enterprise Sullivan:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412088 Enterprise Sullivan\n***Project Completed\n………………………………","***MS #412088 Enterprise Sullivan:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412088 Enterprise Sullivan\n………………………………"]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412683 HESCO","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412683 HESCO",408.1,"() MS #412683 HESCO:  Meter Station (1/11/15 to 1/11/16)","***MS #412683 HESCO:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412683 HESCO\n***Project Completed\n………………………………","***MS #412683 HESCO:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412683 HESCO\n………………………………"]
[{"$f":"IF(AND(H14<>\"\",I14<>\"\"), \"Date change. Previously scheduled \" & TEXT(H14,\"m/d/y;@\") &IF(H14=I14,\"\",\" to \" & TEXT(I14,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X16-36843",{"$f":"IF(G14<>\"\",\"***\",\"\")","v":"***"},"2016-01-27","2016-01-27","Project Completed",null,null,"Sta. 237",200,5,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,237,"(X16-36843) Sta. 237:  Unit  Maintenance (1/27/16)","***Sta. 237:  Unit  Maintenance\n--1/27/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Sta. 237:  Unit  Maintenance\n***Project Completed\n………………………………"]
[{"$f":"IF(AND(H15<>\"\",I15<>\"\"), \"Date change. Previously scheduled \" & TEXT(H15,\"m/d/y;@\") &IF(H15=I15,\"\",\" to \" & TEXT(I15,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X14-1478563",{"$f":"IF(G15<>\"\",\"***\",\"\")","v":"***"},"2015-11-16","2016-02-12","Project Completed",null,null,"MLV 32-1D to 33-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,32.200000000000003,"(X14-1478563) MLV 32-1D to 33-1:  Hydrotest (11/16/15 to 2/12/16)","***MLV 32-1D to 33-1:  Hydrotest\n--11/16/15 through 2/12/16:  This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***MLV 32-1D to 33-1:  Hydrotest\n***Project Completed\n………………………………"]
[null,"Project Completed","X16-16074",null,"2016-01-18","2016-01-28","Project Completed",null,null,"Station 550","500","1","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,550,"(X16-16074) Station 550:  Station Maintenance (1/18/16 to 1/28/16)","Station 550:  Station Maintenance\n--1/18/16 through 1/28/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","Station 550:  Station Maintenance\n***Project Completed\n………………………………"]
[{"$f":"IF(AND(H17<>\"\",I17<>\"\"), \"Date change. Previously scheduled \" & TEXT(H17,\"m/d/y;@\") &IF(H17=I17,\"\",\" to \" & TEXT(I17,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X16-46202",{"$f":"IF(G17<>\"\",\"***\",\"\")","v":"***"},"2016-02-01","2016-02-07","Project Completed",null,null,"Station 9","100","0","Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.",null,9,"(X16-46202) Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items) (2/1/16 to 2/7/16)","***Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)\n--2/1/16 through 2/7/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\n***Project Completed\n………………………………","***Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)\n***Project Completed\n………………………………"]
["","Project Completed","X15-925633","***","2016-02-09","2016-02-11","Project Completed",null,null,"Sta. 266A",200,6,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,266,"(X15-925633) Sta. 266A:  Unit  Maintenance (2/9/16 to 2/11/16)","***Sta. 266A:  Unit  Maintenance\n--2/9/16 through 2/11/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Sta. 266A:  Unit  Maintenance\n***Project Completed\n………………………………"]
["","Project Completed","X15-929733","***","2016-01-27","2016-02-10","Project Completed",null,null,"MLV 834-1 to 838-1",800,5,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",834.1,"(X15-929733) MLV 834-1 to 838-1:  ILI/Cleaning Pig (1/27/16 to 2/10/16)","***MLV 834-1 to 838-1:  ILI/Cleaning Pig\n--1/27/16 through 2/10/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 834-1 to 838-1:  ILI/Cleaning Pig\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X14-1562506","***","2015-11-02","2016-02-19","Project Completed",null,null,"MLV 5-1 to 6-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410063 ROCHE DEHYDRATION             \n",5.0999999999999996,"(X14-1562506) MLV 5-1 to 6-1:  Hydrotest (11/2/15 to 2/19/16)","***MLV 5-1 to 6-1:  Hydrotest\n--11/2/15 through 2/19/16:  This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410063 ROCHE DEHYDRATION             \n\n***Project Completed\n………………………………","***MLV 5-1 to 6-1:  Hydrotest\n***Project Completed\nThe following meters are available for nominations:\n410063 ROCHE DEHYDRATION             \n\n………………………………"]
["","Project Completed","X14-1562506","***","2015-11-02","2016-02-19","Project Completed",null,null,"MLV 7-1 to 9-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","\n412490 Charro\n421083 Eagle Ford Field Service",5.0999999999999996,"(X14-1562506) MLV 7-1 to 9-1:  Hydrotest (11/2/15 to 2/19/16)","***MLV 7-1 to 9-1:  Hydrotest\n--11/2/15 through 2/19/16:  This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n\n412490 Charro\n421083 Eagle Ford Field Service\n***Project Completed\n………………………………","***MLV 7-1 to 9-1:  Hydrotest\n***Project Completed\nThe following meters are available for nominations:\n\n412490 Charro\n421083 Eagle Ford Field Service\n………………………………"]
["Date change. Previously scheduled 2/18/16 to 2/20/16.","Project Completed","X15-882289","***","2016-02-22","2016-02-24","Project Completed","2016-02-18","2016-02-20","MLV 24-2 to 25-2S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.2,"(X15-882289) MLV 24-2 to 25-2S:  Anomaly Remediation (2/22/16 to 2/24/16)","***MLV 24-2 to 25-2S:  Anomaly Remediation\n--2/22/16 through 2/24/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 24-2 to 25-2S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-925630","***","2016-02-23","2016-02-23","Project Completed",null,null,"WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B)",200,"L","ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,265.10000000000002,"(X15-925630) WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig (2/23/16)","***WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig\n--2/23/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig\n***Project Completed\n………………………………"]
["","Project Completed","X16-23748","***","2016-02-15","2016-02-18","Project Completed",null,null,"MLV 530-3 to 532-3",500,"L","ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,530.29999999999995,"(X16-23748) MLV 530-3 to 532-3:  ILI/Cleaning Pig (2/15/16 to 2/18/16)","***MLV 530-3 to 532-3:  ILI/Cleaning Pig\n--2/15/16 through 2/18/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***MLV 530-3 to 532-3:  ILI/Cleaning Pig\n***Project Completed\n………………………………"]
["","Project Canceled","X16-98720","***","2016-03-06","2016-03-06","Project Canceled",null,null,"Sta. 1",100,0,"Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,1,"(X16-98720) Sta. 1:  Station Maintenance (3/6/16)","***Sta. 1:  Station Maintenance\n--3/6/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Canceled\n………………………………","***Sta. 1:  Station Maintenance\n***Project Canceled\n………………………………"]
["","Project Completed","X14-1562513\nX14-1540661","***","2015-07-01","2016-03-04","Project Completed",null,null,"Station 32","100","0","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,32,"(X14-1562513\nX14-1540661) Station 32:  Station Maintenance (7/1/15 to 3/4/16)","***Station 32:  Station Maintenance\n--7/1/15 through 3/4/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Station 32:  Station Maintenance\n***Project Completed\n………………………………"]
["","Project Canceled","X15-926822","***","2016-06-06","2016-06-11","Project Canceled",null,null,"BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1)",300,6,"Pipe Inspection","This project involves inspecting multiple sites.  We do not anticipate having to do any repairs, however if a repair is needed  there is a potential that the pipe  may require replacement which will require isolation of the pipe.  This may limit throughput and will result in restrictions based on customer nominations.  Customers may experience pressure fluctuations during this timeframe.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",343.1,"(X15-926822) BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection (6/6/16 to 6/11/16)","***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection\n--6/6/16 through 6/11/16:  This project involves inspecting multiple sites.  We do not anticipate having to do any repairs, however if a repair is needed  there is a potential that the pipe  may require replacement which will require isolation of the pipe.  This may limit throughput and will result in restrictions based on customer nominations.  Customers may experience pressure fluctuations during this timeframe.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928271","***","TBD","TBD","Project Canceled",null,null,"MLV 555-1 to 550-1",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.1,"(X15-928271) MLV 555-1 to 550-1:  ILI/Cleaning Pig (TBD)","***MLV 555-1 to 550-1:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-1 to 550-1:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928272","***","TBD","TBD","Project Canceled",null,null,"MLV 555-2 to 550-2",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.20000000000005,"(X15-928272) MLV 555-2 to 550-2:  ILI/Cleaning Pig (TBD)","***MLV 555-2 to 550-2:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-2 to 550-2:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928273","***","TBD","TBD","Project Canceled",null,null,"MLV 555-3 to 552-3",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.29999999999995,"(X15-928273) MLV 555-3 to 552-3:  ILI/Cleaning Pig (TBD)","***MLV 555-3 to 552-3:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-3 to 552-3:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-882281","***","2016-02-24","2016-03-03","Project Completed",null,null,"24-1A to 25-1S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.1,"(X15-882281) 24-1A to 25-1S:  Anomaly Remediation (2/24/16 to 3/3/16)","***24-1A to 25-1S:  Anomaly Remediation\n--2/24/16 through 3/3/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***24-1A to 25-1S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-882291","***","2016-03-03","2016-03-04","Project Completed",null,null,"MLV 24-3 to 25-3S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.3,"(X15-882291) MLV 24-3 to 25-3S:  Anomaly Remediation (3/3/16 to 3/4/16)","***MLV 24-3 to 25-3S:  Anomaly Remediation\n--3/3/16 through 3/4/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 24-3 to 25-3S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X14-1178175","***","2015-06-15","2016-03-31","Project Completed",null,null,"Station 63","100","1","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,63,"(X14-1178175) Station 63:  Station Maintenance (6/15/15 to 3/31/16)","***Station 63:  Station Maintenance\n--6/15/15 through 3/31/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Station 63:  Station Maintenance\n***Project Completed\n………………………………"]
["","Project Cancelled","X15-913224","***","2016-04-16","2016-05-21","Project Cancelled",null,null,"MLV 109-2",100,2,"Pipe Replacement","This project will require taking the pipeline section out of service.   This will limit throughput and will result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",109.2,"(X15-913224) MLV 109-2:  Pipe Replacement (4/16/16 to 5/21/16)","***MLV 109-2:  Pipe Replacement\n--4/16/16 through 5/21/16:  This project will require taking the pipeline section out of service.   This will limit throughput and will result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Cancelled\n………………………………","***MLV 109-2:  Pipe Replacement\n***Project Cancelled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-926830","***","2016-03-07","2016-03-11","Project Completed",null,null,"MLV 400-1 to 408-1",100,0,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.","To Be Determined",400.1,"(X15-926830) MLV 400-1 to 408-1:  ILI/Cleaning Pig (3/7/16 to 3/11/16)","***MLV 400-1 to 408-1:  ILI/Cleaning Pig\n--3/7/16 through 3/11/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 400-1 to 408-1:  ILI/Cleaning Pig\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Cancelled","X16-143836","***","2016-03-28","2016-04-04","Project Cancelled",null,null,"Sta. 409",100,0,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.",null,409,"(X16-143836) Sta. 409:  Unit  Maintenance (3/28/16 to 4/4/16)","***Sta. 409:  Unit  Maintenance\n--3/28/16 through 4/4/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\n***Project Cancelled\n………………………………","***Sta. 409:  Unit  Maintenance\n***Project Cancelled\n………………………………"]
["","Project Cancelled","X15-929680","***","2016-04-18","2016-04-27","Project Cancelled",null,null,"SABINE - KINDER LINE to 822-1",800,"L","Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",822.1,"(X15-929680) SABINE - KINDER LINE to 822-1:  Anomaly Remediation (4/18/16 to 4/27/16)","***SABINE - KINDER LINE to 822-1:  Anomaly Remediation\n--4/18/16 through 4/27/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Cancelled\n………………………………","***SABINE - KINDER LINE to 822-1:  Anomaly Remediation\n***Project Cancelled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]

{"sheet":"Sheet1","index":1,"n_rows":299,"n_cols":24,"rows_kept":299,"cut":false,"hidden":false,"merged":[[2,0,2,14]]}
["Updated ","2024-09-19"]
["Tennessee Gas Pipeline 2024 Pipeline Outage and Maintenance Summary"]
["This is a summary of the current status of TGP Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  \nAdditionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
["*** Indicates revision"]
["Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","Location","Leg","Zone","Maintenance Activity","Anticipated Impact","Potential Restriction Level","TOS Potential Restrictions","Meter(s) in Impacted Area","Loc",null,null,null,null,null,null,null,"\\\\houCORP\\TRANS\\TRANSERVICES\\OPPLAN\\COMMON\\Outages\\Outage_DB\\TGP\\Files"]
["X24-55955","***","2024-07-23","2024-09-25","Project Change",null,"2024-09-23","MLV 3-1 TO MLV 4-1","100","0","Class Change / Wrinkle Bend Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412693 GCENGY/TGP MORGAN SAN PATRICIO",3.1,"----end_date------------model_loc--","***MLV 3-1 TO MLV 4-1:  Class Change / Wrinkle Bend Replacement\n--7/23/24 through 9/25/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n412693 GCENGY/TGP MORGAN SAN PATRICIO\n***\nDate Change, Previously scheduled 7/23/24 to 9/23/24.\n………………………………"]
["X24-760176","***","2024-09-12","2024-09-12","Completed",null,null,"MLV 5-2 to MLV 1-2D","100","0","Pig Runs - Cleaning 9/12/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412196 ENLINK/TGP NORTH BRAYTON DEHY NUECE\n412062 BANHUB/TGP BANQUETE TRANSPORT NUECE\n412669 ETP/TGP SHOUP NUECES\n412270 LOBO/TGP UDP TRANSAMERICAN INTERCON\n54847 WHISTLEP/TGP WHISTLER RECEIPT NUECE",5.21,"------","***MLV 5-2 to MLV 1-2D:  Pig Runs - Cleaning 9/12/24\n***Completed\nThe following meters are available for nominations:\n412196 ENLINK/TGP NORTH BRAYTON DEHY NUECE\n412062 BANHUB/TGP BANQUETE TRANSPORT NUECE\n412669 ETP/TGP SHOUP NUECES\n412270 LOBO/TGP UDP TRANSAMERICAN INTERCON\n54847 WHISTLEP/TGP WHISTLER RECEIPT NUECE"]
["X24-62242","***","2024-09-13","2024-09-13","Completed",null,null,"MLV 5-2 to MLV 1-2D","100","0","Pig Runs - MFL-A 9/13/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412196 ENLINK/TGP NORTH BRAYTON DEHY NUECE\n412062 BANHUB/TGP BANQUETE TRANSPORT NUECE\n412669 ETP/TGP SHOUP NUECES\n412270 LOBO/TGP UDP TRANSAMERICAN INTERCON\n54847 WHISTLEP/TGP WHISTLER RECEIPT NUECE",5.22,"------","***MLV 5-2 to MLV 1-2D:  Pig Runs - MFL-A 9/13/24\n***Completed\nThe following meters are available for nominations:\n412196 ENLINK/TGP NORTH BRAYTON DEHY NUECE\n412062 BANHUB/TGP BANQUETE TRANSPORT NUECE\n412669 ETP/TGP SHOUP NUECES\n412270 LOBO/TGP UDP TRANSAMERICAN INTERCON\n54847 WHISTLEP/TGP WHISTLER RECEIPT NUECE"]
["X24-76784",null,"2024-11-14","2024-11-14",null,null,null,"MLV 5-2 to MLV 1-2D","100","0","Pig Runs - Maintenance Cleaning 11/14","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SIP","Potential in the path restrictions may be at risk.","412196 ENLINK/TGP NORTH BRAYTON DEHY NUECE\n412062 BANHUB/TGP BANQUETE TRANSPORT NUECE\n412669 ETP/TGP SHOUP NUECES\n412270 LOBO/TGP UDP TRANSAMERICAN INTERCON\n54847 WHISTLEP/TGP WHISTLER RECEIPT NUECE",5.23,null,"MLV 5-2 to MLV 1-2D:  Pig Runs - Maintenance Cleaning 11/14\n--11/14/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential in the path restrictions may be at risk.\n412196 ENLINK/TGP NORTH BRAYTON DEHY NUECE\n412062 BANHUB/TGP BANQUETE TRANSPORT NUECE\n412669 ETP/TGP SHOUP NUECES\n412270 LOBO/TGP UDP TRANSAMERICAN INTERCON\n54847 WHISTLEP/TGP WHISTLER RECEIPT NUECE\n………………………………"]
["X24-633724","***","2024-09-23","2024-10-25","Project Change","2024-08-06","2024-09-15","MLV 6-1 to MLV 7-1","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,6.1,"--start_date--end_date------------model_loc--","***MLV 6-1 to MLV 7-1:  Anomaly Remediation\n--9/23/24 through 10/25/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 8/6/24 to 9/15/24.\n………………………………"]
["X24-76782",null,"2024-11-12","2024-11-12",null,null,null,"MLV 9-1S and MLV 1-1D","100","0","Pig Run - Maintenance Cleaning 11/12","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SIP","Potential in the path restrictions may be at risk.","54847 WHISTLEP/TGP WHISTLE RECEIPT NUECES\n53608 VCP/TGP VALLEY CROSSING ALLOCATION",9.0500000000000007,null,"MLV 9-1S and MLV 1-1D:  Pig Run - Maintenance Cleaning 11/12\n--11/12/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential in the path restrictions may be at risk.\n54847 WHISTLEP/TGP WHISTLE RECEIPT NUECES\n53608 VCP/TGP VALLEY CROSSING ALLOCATION\n………………………………"]
["X24-62295","***","2024-09-16","2024-09-16","Completed",null,null,"MLV 9-1D to MLV 17-1S","100","0","Pig Runs - Cleaning/Gauge 9/16/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","49524\tGULFSTH/TGP COASTAL BEND LNG WHARTO\n49803\tKMTEJAS/TGP JACKSON       (GANADO) \n54086\tTGP/PHP SHERIDAN COLORADO\n56689\tKMTEJAS/TGP EGYPT PHPE RB WHARTON\n400454\tKEM ENER/TGP EGYPT NORTH WEST DEHY \n410144\tCPROC/TGP HCP COLORADO\n411911\tETP/TGP WHARTON COUNTY TRANSPORT EX\n411938\tLASERGTH/TGP UDP NORTH LOUISE DEHY \n412023\tHGI/TGP UDP ENGLEHARDT COLORADO\n412523\tUES/TGP WILDCAT   RASMUSSEN   1  R \n412860\tET G&P/TGP GANADO PLANT JACKSON\n412878\tBWALKTX/TGP FLAG CITY: RIP 11J 101.\n420158\tCOKINOS/TGP RAUN FARM TX WHARTON\n420159\tCOKINOS/TGP MCCOLLOCH SPENCER FARM \n420162\tCOKINOS/TGP RAUN FARM  2 TX COLORAD\n420183\tCOKENRG/TGP KRENEK FARM TX WHARTON\n420185\tCOKINOS/TGP OTTIS FARM TX JACKSON\n420190\tCOKINOS/TGP SULAK FARM TX WHARTON\n420332\tCOKINOS/TGP NITSCH FARM TX WHARTON\n420369\tCOKINOS/TGP WIGGINTON FARM TX WHART\n420442\tCOKINOS/TGP RASMUSSEN FARM TX WHART\n420466\tCOKINOS/TGP HOLT FARM TX WHARTON\n420479\tCOKINOS/TGP CATTLE TX FARM WHARTON\n421055\tTRES PAL/TGP TRES PALACIOS STORAGE:",9.11,"------","***MLV 9-1D to MLV 17-1S:  Pig Runs - Cleaning/Gauge 9/16/24\n***Completed\nThe following meters are available for nominations:\n49524\tGULFSTH/TGP COASTAL BEND LNG WHARTO\n49803\tKMTEJAS/TGP JACKSON       (GANADO) \n54086\tTGP/PHP SHERIDAN COLORADO\n56689\tKMTEJAS/TGP EGYPT PHPE RB WHARTON\n400454\tKEM ENER/TGP EGYPT NORTH WEST DEHY \n410144\tCPROC/TGP HCP COLORADO\n411911\tETP/TGP WHARTON COUNTY TRANSPORT EX\n411938\tLASERGTH/TGP UDP NORTH LOUISE DEHY \n412023\tHGI/TGP UDP ENGLEHARDT COLORADO\n412523\tUES/TGP WILDCAT   RASMUSSEN   1  R \n412860\tET G&P/TGP GANADO PLANT JACKSON\n412878\tBWALKTX/TGP FLAG CITY: RIP 11J 101.\n420158\tCOKINOS/TGP RAUN FARM TX WHARTON\n420159\tCOKINOS/TGP MCCOLLOCH SPENCER FARM \n420162\tCOKINOS/TGP RAUN FARM  2 TX COLORAD\n420183\tCOKENRG/TGP KRENEK FARM TX WHARTON\n420185\tCOKINOS/TGP OTTIS FARM TX JACKSON\n420190\tCOKINOS/TGP SULAK FARM TX WHARTON\n420332\tCOKINOS/TGP NITSCH FARM TX WHARTON\n420369\tCOKINOS/TGP WIGGINTON FARM TX WHART\n420442\tCOKINOS/TGP RASMUSSEN FARM TX WHART\n420466\tCOKINOS/TGP HOLT FARM TX WHARTON\n420479\tCOKINOS/TGP CATTLE TX FARM WHARTON\n421055\tTRES PAL/TGP TRES PALACIOS STORAGE:"]
["X24-62240","***","2024-09-17","2024-09-17","Completed",null,null,"MLV 9-1D to MLV 17-1S","100","0","Pig Runs - Cleaning 9/17/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","49524\tGULFSTH/TGP COASTAL BEND LNG WHARTO\n49803\tKMTEJAS/TGP JACKSON       (GANADO) \n54086\tTGP/PHP SHERIDAN COLORADO\n56689\tKMTEJAS/TGP EGYPT PHPE RB WHARTON\n400454\tKEM ENER/TGP EGYPT NORTH WEST DEHY \n410144\tCPROC/TGP HCP COLORADO\n411911\tETP/TGP WHARTON COUNTY TRANSPORT EX\n411938\tLASERGTH/TGP UDP NORTH LOUISE DEHY \n412023\tHGI/TGP UDP ENGLEHARDT COLORADO\n412523\tUES/TGP WILDCAT   RASMUSSEN   1  R \n412860\tET G&P/TGP GANADO PLANT JACKSON\n412878\tBWALKTX/TGP FLAG CITY: RIP 11J 101.\n420158\tCOKINOS/TGP RAUN FARM TX WHARTON\n420159\tCOKINOS/TGP MCCOLLOCH SPENCER FARM \n420162\tCOKINOS/TGP RAUN FARM  2 TX COLORAD\n420183\tCOKENRG/TGP KRENEK FARM TX WHARTON\n420185\tCOKINOS/TGP OTTIS FARM TX JACKSON\n420190\tCOKINOS/TGP SULAK FARM TX WHARTON\n420332\tCOKINOS/TGP NITSCH FARM TX WHARTON\n420369\tCOKINOS/TGP WIGGINTON FARM TX WHART\n420442\tCOKINOS/TGP RASMUSSEN FARM TX WHART\n420466\tCOKINOS/TGP HOLT FARM TX WHARTON\n420479\tCOKINOS/TGP CATTLE TX FARM WHARTON\n421055\tTRES PAL/TGP TRES PALACIOS STORAGE:",9.1199999999999992,"------","***MLV 9-1D to MLV 17-1S:  Pig Runs - Cleaning 9/17/24\n***Completed\nThe following meters are available for nominations:\n49524\tGULFSTH/TGP COASTAL BEND LNG WHARTO\n49803\tKMTEJAS/TGP JACKSON       (GANADO) \n54086\tTGP/PHP SHERIDAN COLORADO\n56689\tKMTEJAS/TGP EGYPT PHPE RB WHARTON\n400454\tKEM ENER/TGP EGYPT NORTH WEST DEHY \n410144\tCPROC/TGP HCP COLORADO\n411911\tETP/TGP WHARTON COUNTY TRANSPORT EX\n411938\tLASERGTH/TGP UDP NORTH LOUISE DEHY \n412023\tHGI/TGP UDP ENGLEHARDT COLORADO\n412523\tUES/TGP WILDCAT   RASMUSSEN   1  R \n412860\tET G&P/TGP GANADO PLANT JACKSON\n412878\tBWALKTX/TGP FLAG CITY: RIP 11J 101.\n420158\tCOKINOS/TGP RAUN FARM TX WHARTON\n420159\tCOKINOS/TGP MCCOLLOCH SPENCER FARM \n420162\tCOKINOS/TGP RAUN FARM  2 TX COLORAD\n420183\tCOKENRG/TGP KRENEK FARM TX WHARTON\n420185\tCOKINOS/TGP OTTIS FARM TX JACKSON\n420190\tCOKINOS/TGP SULAK FARM TX WHARTON\n420332\tCOKINOS/TGP NITSCH FARM TX WHARTON\n420369\tCOKINOS/TGP WIGGINTON FARM TX WHART\n420442\tCOKINOS/TGP RASMUSSEN FARM TX WHART\n420466\tCOKINOS/TGP HOLT FARM TX WHARTON\n420479\tCOKINOS/TGP CATTLE TX FARM WHARTON\n421055\tTRES PAL/TGP TRES PALACIOS STORAGE:"]
["X24-277894",null,"2024-09-19","2024-09-19",null,null,null,"MLV 9-1D to MLV 17-1S","100","0","Pig Runs - MDS Tool with IMU/XYZ  9/19/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","49524\tGULFSTH/TGP COASTAL BEND LNG WHARTO\n49803\tKMTEJAS/TGP JACKSON       (GANADO) \n54086\tTGP/PHP SHERIDAN COLORADO\n56689\tKMTEJAS/TGP EGYPT PHPE RB WHARTON\n400454\tKEM ENER/TGP EGYPT NORTH WEST DEHY \n410144\tCPROC/TGP HCP COLORADO\n411911\tETP/TGP WHARTON COUNTY TRANSPORT EX\n411938\tLASERGTH/TGP UDP NORTH LOUISE DEHY \n412023\tHGI/TGP UDP ENGLEHARDT COLORADO\n412523\tUES/TGP WILDCAT   RASMUSSEN   1  R \n412860\tET G&P/TGP GANADO PLANT JACKSON\n412878\tBWALKTX/TGP FLAG CITY: RIP 11J 101.\n420158\tCOKINOS/TGP RAUN FARM TX WHARTON\n420159\tCOKINOS/TGP MCCOLLOCH SPENCER FARM \n420162\tCOKINOS/TGP RAUN FARM  2 TX COLORAD\n420183\tCOKENRG/TGP KRENEK FARM TX WHARTON\n420185\tCOKINOS/TGP OTTIS FARM TX JACKSON\n420190\tCOKINOS/TGP SULAK FARM TX WHARTON\n420332\tCOKINOS/TGP NITSCH FARM TX WHARTON\n420369\tCOKINOS/TGP WIGGINTON FARM TX WHART\n420442\tCOKINOS/TGP RASMUSSEN FARM TX WHART\n420466\tCOKINOS/TGP HOLT FARM TX WHARTON\n420479\tCOKINOS/TGP CATTLE TX FARM WHARTON\n421055\tTRES PAL/TGP TRES PALACIOS STORAGE:",9.1300000000000008,null,"MLV 9-1D to MLV 17-1S:  Pig Runs - MDS Tool with IMU/XYZ  9/19/24\n--9/19/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n49524\tGULFSTH/TGP COASTAL BEND LNG WHARTO\n49803\tKMTEJAS/TGP JACKSON       (GANADO) \n54086\tTGP/PHP SHERIDAN COLORADO\n56689\tKMTEJAS/TGP EGYPT PHPE RB WHARTON\n400454\tKEM ENER/TGP EGYPT NORTH WEST DEHY \n410144\tCPROC/TGP HCP COLORADO\n411911\tETP/TGP WHARTON COUNTY TRANSPORT EX\n411938\tLASERGTH/TGP UDP NORTH LOUISE DEHY \n412023\tHGI/TGP UDP ENGLEHARDT COLORADO\n412523\tUES/TGP WILDCAT   RASMUSSEN   1  R \n412860\tET G&P/TGP GANADO PLANT JACKSON\n412878\tBWALKTX/TGP FLAG CITY: RIP 11J 101.\n420158\tCOKINOS/TGP RAUN FARM TX WHARTON\n420159\tCOKINOS/TGP MCCOLLOCH SPENCER FARM \n420162\tCOKINOS/TGP RAUN FARM  2 TX COLORAD\n420183\tCOKENRG/TGP KRENEK FARM TX WHARTON\n420185\tCOKINOS/TGP OTTIS FARM TX JACKSON\n420190\tCOKINOS/TGP SULAK FARM TX WHARTON\n420332\tCOKINOS/TGP NITSCH FARM TX WHARTON\n420369\tCOKINOS/TGP WIGGINTON FARM TX WHART\n420442\tCOKINOS/TGP RASMUSSEN FARM TX WHART\n420466\tCOKINOS/TGP HOLT FARM TX WHARTON\n420479\tCOKINOS/TGP CATTLE TX FARM WHARTON\n421055\tTRES PAL/TGP TRES PALACIOS STORAGE:\n………………………………"]
["X24-76834",null,"2024-11-14","2024-11-14",null,null,null,"MLV 9-2 to MLV 5-2","100","0","Pig Runs - Maintenance Cleaning 11/14","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SIP","Potential in the path restrictions may be at risk.","54847 WHISTLEP/TGP WHISTLE RECEIPT NUECES\n53608 VCP/TGP VALLEY CROSSING ALLOCATION",9.1999999999999993,null,"MLV 9-2 to MLV 5-2:  Pig Runs - Maintenance Cleaning 11/14\n--11/14/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential in the path restrictions may be at risk.\n54847 WHISTLEP/TGP WHISTLE RECEIPT NUECES\n53608 VCP/TGP VALLEY CROSSING ALLOCATION\n………………………………"]
["X24-76791",null,"2024-11-13","2024-11-13",null,null,null,"MLV 9-3 to MLV 4-3","100","0","Pig Runs - Maintenance Cleaning 11/13","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SIP","Potential in the path restrictions may be at risk.","54847 WHISTLEP/TGP WHISTLE RECEIPT NUECES\n53608 VCP/TGP VALLEY CROSSING ALLOCATION",9.31,null,"MLV 9-3 to MLV 4-3:  Pig Runs - Maintenance Cleaning 11/13\n--11/13/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential in the path restrictions may be at risk.\n54847 WHISTLEP/TGP WHISTLE RECEIPT NUECES\n53608 VCP/TGP VALLEY CROSSING ALLOCATION\n………………………………"]
["X24-973194",null,"2024-09-24","2024-09-25",null,null,null,"Sta 11A","100","0","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,11,null,"Sta 11A:  Annual ESD Test\n--9/24/24 through 9/25/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-973229",null,"2024-09-28","2024-09-30",null,null,null,"MLV 16-3 to MLV 18-3","100","0","Hot Tap for New Meter Bernard Creek (PIN 56009)","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.","56009 MATTEXPR/TGP BERNARD CREEK RECEIPT",16.3,null,"MLV 16-3 to MLV 18-3:  Hot Tap for New Meter Bernard Creek (PIN 56009)\n--9/28/24 through 9/30/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n56009 MATTEXPR/TGP BERNARD CREEK RECEIPT\n………………………………"]
["X24-770910",null,"2024-10-09","2024-10-09",null,null,null,"Sta 17","100","0","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","49524 GULFSTH/TGP COASTAL BEND LNG WHARTO",17,null,"Sta 17:  Annual ESD Test\n--10/9/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n49524 GULFSTH/TGP COASTAL BEND LNG WHARTO\n………………………………"]
["X23-867586",null,"2023-08-26","2024-11-15",null,null,null,"Sta 17","100","0","Unit 2C - Engine Seal Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,17.033999999999999,null,"Sta 17:  Unit 2C - Engine Seal Inspection\n--8/26/23 through 11/15/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-29941",null,"2024-11-05","2024-11-05",null,null,null,"MLV 17-3D TO MLV 20-3A","100","0","Pig Runs - Cleaning 11/5","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","421085 SYMMETRY/TGP PEDERSON ROAD WALLER",17.3,null,"MLV 17-3D TO MLV 20-3A:  Pig Runs - Cleaning 11/5\n--11/5/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n421085 SYMMETRY/TGP PEDERSON ROAD WALLER\n………………………………"]
["X24-29950",null,"2024-11-06","2024-11-06",null,null,null,"MLV 17-3D TO MLV 20-3A","100","0","Pig Runs - Gauge 11/6","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","421085 SYMMETRY/TGP PEDERSON ROAD WALLER",17.309999999999999,null,"MLV 17-3D TO MLV 20-3A:  Pig Runs - Gauge 11/6\n--11/6/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n421085 SYMMETRY/TGP PEDERSON ROAD WALLER\n………………………………"]
["X24-29958",null,"2024-11-07","2024-11-07",null,null,null,"MLV 17-3D TO MLV 20-3A","100","0","Pig Runs - MFL-A 11/7","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","421085 SYMMETRY/TGP PEDERSON ROAD WALLER",17.32,null,"MLV 17-3D TO MLV 20-3A:  Pig Runs - MFL-A 11/7\n--11/7/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n421085 SYMMETRY/TGP PEDERSON ROAD WALLER\n………………………………"]
["X24-55954",null,"2024-08-27","2024-10-31",null,null,null,"MLV 18-2A TO MLV 20-2A","100","0","Class Change / Wrinkle Bend Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be restricted or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420167 COKINOS/TGP WOODS FARM TX FORT BEND\n411788 DCP GLP/TGP KATY TRANSPORT WALLER",18.2,null,"MLV 18-2A TO MLV 20-2A:  Class Change / Wrinkle Bend Replacement\n--8/27/24 through 10/31/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be restricted or shut in during the project.  Potential out of path restrictions may be at risk.\n420167 COKINOS/TGP WOODS FARM TX FORT BEND\n411788 DCP GLP/TGP KATY TRANSPORT WALLER\n………………………………"]
["X24-652796",null,"2024-09-16","2024-09-20",null,null,null,"MLV 19H-101.1","100","0","Valve Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412271 KTY STTR/TGP KATY INTERCONNECT WALL",19.100000000000001,null,"MLV 19H-101.1:  Valve Replacement\n--9/16/24 through 9/20/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n412271 KTY STTR/TGP KATY INTERCONNECT WALL\n………………………………"]
["X24-850659",null,"2024-11-11","2024-11-16",null,null,null,"MLV 20-1 to MLV 20-1R","100","0","Anomaly Remediation / Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,20.100000000000001,null,"MLV 20-1 to MLV 20-1R:  Anomaly Remediation / Replacement\n--11/11/24 through 11/16/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-671169",null,"2025-03-10","2025-03-24",null,null,null,"MLV 25-1 to MLV 26-1 Relocation","100","0","Highway 105 Widening","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,25.1,null,"MLV 25-1 to MLV 26-1 Relocation:  Highway 105 Widening\n--3/10/25 through 3/24/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-671172",null,"2025-03-10","2025-03-24",null,null,null,"MLV 25A-101 to MLV 25A-102 Relocation","100","0","Highway 105 Widening","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","411559 HEC/TGP UDP 1 CENTRAL COAL & COKE D",25.11,null,"MLV 25A-101 to MLV 25A-102 Relocation:  Highway 105 Widening\n--3/10/25 through 3/24/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n411559 HEC/TGP UDP 1 CENTRAL COAL & COKE D\n………………………………"]
["X22-621358",null,"2025-03-10","2025-04-06",null,null,null,"MLV 26-1 Relocation","100","0","Highway 59 Widening","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,26.1,null,"MLV 26-1 Relocation:  Highway 59 Widening\n--3/10/25 through 4/6/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-815863",null,"2025-04-07","2025-05-04",null,null,null,"MLV 26-2 Relocation","100","0","Highway 59 Widening","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,26.2,null,"MLV 26-2 Relocation:  Highway 59 Widening\n--4/7/25 through 5/4/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-815864",null,"2025-05-05","2025-06-01",null,null,null,"MLV 26-3 Relocation","100","0","Highway 59 Widening","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","SOP","Potential out of path restrictions may be at risk.","400448 CICO/TGP MERCY GU 1 LIBERTY",26.3,null,"MLV 26-3 Relocation:  Highway 59 Widening\n--5/5/25 through 6/1/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  Potential out of path restrictions may be at risk.\n400448 CICO/TGP MERCY GU 1 LIBERTY\n………………………………"]
["X24-894768","***","2024-09-09","2024-09-13","Completed",null,null,"Sta 32","100","0","Annual ESD Test & Electrical Inspection","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,32,"------","***Sta 32:  Annual ESD Test & Electrical Inspection\n***Completed"]
["X24-976573","***","2024-09-12","2024-09-19","Project Change",null,"2024-09-17","MLV 34-2 to MLV 35-2","100","0","PHMSA Immediate Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,34.200000000000003,"----end_date------------model_loc--","***MLV 34-2 to MLV 35-2:  PHMSA Immediate Anomaly Remediation\n--9/12/24 through 9/19/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/12/24 to 9/17/24.\n………………………………"]
["X24-976575","***","2024-09-12","2024-09-19","Project Change",null,"2024-09-17","MLV 35-2 to MLV 36-2","100","0","PHMSA Immediate Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,35.200000000000003,"----end_date------------model_loc--","***MLV 35-2 to MLV 36-2:  PHMSA Immediate Anomaly Remediation\n--9/12/24 through 9/19/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/12/24 to 9/17/24.\n………………………………"]
["X24-907892","***","2024-09-25","2024-10-12","Project Change","2024-10-05","2024-10-23","MLV 36-1A TO MLV 37-1","100","0","Hydrotest","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,36.1,"--start_date--end_date------------model_loc--","***MLV 36-1A TO MLV 37-1:  Hydrotest\n--9/25/24 through 10/12/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 10/5/24 to 10/23/24.\n………………………………"]
["X24-976577","***","2024-09-12","2024-09-17","Completed",null,null,"MLV 36-2A to MLV 37-2","100","0","PHMSA Immediate Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,36.200000000000003,"------","***MLV 36-2A to MLV 37-2:  PHMSA Immediate Anomaly Remediation\n***Completed"]
["X24-907894","***","2024-09-24","2024-09-28","Project Change","2024-09-18","2024-09-23","MLV 36-2 TO MLV 36-2A","100","0","Special Permit / Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,36.200000000000003,"--start_date--end_date------------model_loc--","***MLV 36-2 TO MLV 36-2A:  Special Permit / Pipe Replacement\n--9/24/24 through 9/28/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/18/24 to 9/23/24.\n………………………………"]
["X24-907895","***","2024-09-10","2024-09-23","Project Change",null,"2024-09-17","MLV 36-3 TO MLV 36-3A","100","0","Special Permit / Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,36.299999999999997,"----end_date------------model_loc--","***MLV 36-3 TO MLV 36-3A:  Special Permit / Pipe Replacement\n--9/10/24 through 9/23/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/10/24 to 9/17/24.\n………………………………"]
["X24-976578","***","2024-09-12","2024-09-17","Completed",null,null,"MLV 38-2 to MLV 39-2","100","0","PHMSA Immediate Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,38.200000000000003,"------","***MLV 38-2 to MLV 39-2:  PHMSA Immediate Anomaly Remediation\n***Completed"]
["X24-94844",null,"2024-11-18","2024-11-26",null,null,null,"MLV 40-2D to MLV 42-2BR","100","1","Make Piggable","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,40.200000000000003,null,"MLV 40-2D to MLV 42-2BR:  Make Piggable\n--11/18/24 through 11/26/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-642657",null,"2024-12-03","2024-12-04",null,null,null,"Sta 40-2 to Sta 42-2","100","1","Pig Runs - Cleaning 12/3 to 12/4","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,40.200000000000003,null,"Sta 40-2 to Sta 42-2:  Pig Runs - Cleaning 12/3 to 12/4\n--12/3/24 through 12/4/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-159396",null,"2024-12-10","2024-12-10",null,null,null,"Sta 40-2 to Sta 42-2","100","1","Pig Runs - MFL-C 12/10","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,40.200000000000003,null,"Sta 40-2 to Sta 42-2:  Pig Runs - MFL-C 12/10\n--12/10/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-159397",null,"2024-12-12","2024-12-12",null,null,null,"Sta 40-2 to Sta 42-2","100","1","Pig Runs - EMAT 12/12","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,40.21,null,"Sta 40-2 to Sta 42-2:  Pig Runs - EMAT 12/12\n--12/12/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-30025",null,"2024-12-05","2024-12-05",null,null,null,"Sta 40-2 to Sta 42-2","100","1","Pig Runs - MFL-S 12/5","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,40.25,null,"Sta 40-2 to Sta 42-2:  Pig Runs - MFL-S 12/5\n--12/5/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-94847","***","2024-09-07","2024-10-19","Project Change",null,"2024-09-14","MLV 41-2A to MLV 42-2","100","1","Make Piggable","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,41.2,"----end_date------------model_loc--","***MLV 41-2A to MLV 42-2:  Make Piggable\n--9/7/24 through 10/19/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/7/24 to 9/14/24.\n………………………………"]
["X23-1130419",null,"2024-10-15","2024-10-21",null,null,null,"Bear Creek Storage","100","1","Shut-in Test","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","460017 STORAGE – BEAR CREEK",43.000999999999998,null,"Bear Creek Storage:  Shut-in Test\n--10/15/24 through 10/21/24:  This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.  Potential out of path restrictions may be at risk.\n460017 STORAGE – BEAR CREEK\n………………………………"]
["X24-293323","***","2024-09-16","2024-09-16","Completed",null,null,"MLVS 46A","100","1","Meter Station Maintenance Scrubber/Filter Service (Goodhope PIN 48813)","This project may require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below may be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","48813 ATTMOS TL/TGP GOODHOPE OUACHITA",46,"------","***MLVS 46A:  Meter Station Maintenance Scrubber/Filter Service (Goodhope PIN 48813)\n***Completed\nThe following meters are available for nominations:\n48813 ATTMOS TL/TGP GOODHOPE OUACHITA"]
["X24-449146",null,"2024-11-04","2024-11-30",null,null,null,"MLV 46-1 to MLV 46-1BR","100","1","Class Change","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,46.1,null,"MLV 46-1 to MLV 46-1BR:  Class Change\n--11/4/24 through 11/30/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-449147",null,"2024-09-27","2024-11-01",null,null,null,"MLV 46-4 to MLV 46-4BR","100","1","Class Change","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,46.4,null,"MLV 46-4 to MLV 46-4BR:  Class Change\n--9/27/24 through 11/1/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-140932",null,"2024-09-25","2024-09-25",null,null,null,"Sta 47 West Monroe","100","1","Annual ESD","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,47,null,"Sta 47 West Monroe:  Annual ESD\n--9/25/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-785011",null,"2024-07-23","2024-12-31",null,null,null,"Sta 47","100","1","Unit 3C - Engine Deferred Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,47.033999999999999,null,"Sta 47:  Unit 3C - Engine Deferred Maintenance\n--7/23/24 through 12/31/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-920091","***","2024-09-09","2024-09-22","Project Change",null,"2024-09-20","MLV 50-2 to MLV 51-2","100","1","Crossover Valve Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,50.2,"----end_date------------model_loc--","***MLV 50-2 to MLV 51-2:  Crossover Valve Replacement\n--9/9/24 through 9/22/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/9/24 to 9/20/24.\n………………………………"]
["X24-853908","***","2024-09-04","2024-09-13","Completed",null,null,"MLV 50-3 to MLV 51-3","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,50.3,"------","***MLV 50-3 to MLV 51-3:  Anomaly Remediation\n***Completed"]
["X24-853909","***","2024-09-04","2024-09-13","Completed",null,null,"MLV 53-3 to MLV 53-3CR","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,53.3,"------","***MLV 53-3 to MLV 53-3CR:  Anomaly Remediation\n***Completed"]
["X24-415098",null,"2024-09-03","2024-09-27",null,null,null,"Sta 54","100","1","Station PLC - Controls Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,54,null,"Sta 54:  Station PLC - Controls Upgrade\n--9/3/24 through 9/27/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-138238",null,"2024-10-08","2024-10-10",null,null,null,"Sta 54 Greenville","100","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,54,null,"Sta 54 Greenville:  Annual ESD Test\n--10/8/24 through 10/10/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-415095",null,"2024-09-03","2024-09-20",null,null,null,"Sta 54","100","1","Unit 1D - Controls Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,54.048999999999999,null,"Sta 54:  Unit 1D - Controls Upgrade\n--9/3/24 through 9/20/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-415096",null,"2024-09-23","2024-10-11",null,null,null,"Sta 54","100","1","Unit 2D - Controls Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,54.05,null,"Sta 54:  Unit 2D - Controls Upgrade\n--9/23/24 through 10/11/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-640584",null,"2024-09-30","2024-10-04",null,null,null,"Sta 54","100","1","Unit 2D - Ariel Compressor Packing Case Change Out & Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,54.05,null,"Sta 54:  Unit 2D - Ariel Compressor Packing Case Change Out & Maintenance\n--9/30/24 through 10/4/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-198176",null,"2024-02-26","2024-12-31",null,null,null,"MLV 54-1 to MLV 69-1","100","1","Force Majeure","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,54.1,null,"MLV 54-1 to MLV 69-1:  Force Majeure\n--2/26/24 through 12/31/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-888867",null,"2024-09-03","2024-10-31",null,null,null,"MLV 58-1 to MLV 60-1","100","1","Shallow Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,58.1,null,"MLV 58-1 to MLV 60-1:  Shallow Pipe Replacement\n--9/3/24 through 10/31/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-293500","***","2024-09-09","2024-09-15","Completed",null,null,"Sta 63","100","1","Inspect & Replace Gas Scrubber Filters","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,63,"------","***Sta 63:  Inspect & Replace Gas Scrubber Filters\n***Completed"]
["X24-138230",null,"2024-09-23","2024-09-24",null,null,null,"Sta 63 Batesville","100","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,63,null,"Sta 63 Batesville:  Annual ESD Test\n--9/23/24 through 9/24/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-860383",null,"2024-08-26","2024-09-20",null,null,null,"Sta 63","100","1","A Building - Unit Valve Replacements","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,63.000999999999998,null,"Sta 63:  A Building - Unit Valve Replacements\n--8/26/24 through 9/20/24:  This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-569123","***","2024-08-26","2024-11-18","Project Change",null,"2024-10-11","Sta 63","100","1","Unit 2D - 60K hour inspections","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,63.05,"----end_date------------model_loc--","***Sta 63:  Unit 2D - 60K hour inspections\n--8/26/24 through 11/18/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 8/26/24 to 10/11/24.\n………………………………"]
["X23-1196655","***","2023-11-28","2024-12-21","Project Change",null,"2024-11-22","Sta 71","100","1","Unit 3A - Discharge Bottle Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,71.003,"----end_date------------model_loc--","***Sta 71:  Unit 3A - Discharge Bottle Inspection\n--11/28/23 through 12/21/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 11/28/23 to 11/22/24.\n………………………………"]
["X24-262275","***","2024-04-08","2024-10-31","Project Change",null,"2024-09-15","Sta 71","100","1","Unit 7A Replace Crank End Compressor Gasket","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,71.007000000000005,"----end_date------------model_loc--","***Sta 71:  Unit 7A Replace Crank End Compressor Gasket\n--4/8/24 through 10/31/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 4/8/24 to 9/15/24.\n………………………………"]
["X24-316210","***","2024-08-12","2024-10-04","Project Change",null,"2024-10-01","MLV 77-2 to MLV 77-2A","100","1","Class Change / Pipe Replacement","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,77.2,"----end_date------------model_loc--","***MLV 77-2 to MLV 77-2A:  Class Change / Pipe Replacement\n--8/12/24 through 10/4/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 8/12/24 to 10/1/24.\n………………………………"]
["X24-957388","***","2024-09-03","2024-09-23","Project Change",null,"2024-09-14","MLV 79-1D to MLV 81-1","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,79.099999999999994,"----end_date------------model_loc--","***MLV 79-1D to MLV 81-1:  Anomaly Remediation\n--9/3/24 through 9/23/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/3/24 to 9/14/24.\n………………………………"]
["X24-296273","***","2024-10-10","2024-11-27","Project Change","2024-09-26","2024-11-14","MLV 84-3 to MLV 85-3","100","1","Class Change","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,84.3,"--start_date--end_date------------model_loc--","***MLV 84-3 to MLV 85-3:  Class Change\n--10/10/24 through 11/27/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/26/24 to 11/14/24.\n………………………………"]
["X24-140918","***","2024-10-15","2024-10-16","Project Change","2024-09-24","2024-09-25","Sta 87 Portland","100","2","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,87,"--start_date--end_date------------model_loc--","***Sta 87 Portland:  Annual ESD Test\n--10/15/24 through 10/16/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/24/24 to 9/25/24.\n………………………………"]
["X24-326855",null,"2024-08-26","2024-11-29",null,null,null,"Sta 87","100","2","Unit 5C - Foundation Regrout","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,87.037000000000006,null,"Sta 87:  Unit 5C - Foundation Regrout\n--8/26/24 through 11/29/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-664526","***","2024-10-15","2024-10-16","Project Change","2024-09-24","2024-09-25","Sta 87","100","2","Building D - Scrubber Filter Inspection/Change Out","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,87.049000000000007,"--start_date--end_date------------model_loc--","***Sta 87:  Building D - Scrubber Filter Inspection/Change Out\n--10/15/24 through 10/16/24:  This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/24/24 to 9/25/24.\n………………………………"]
["X24-633552","***","2024-10-21","2024-10-26","Project Change","2024-10-14","2024-10-19","Sta 87","100","1","Unit 3D - Install New Air Distributor","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,87.051000000000002,"--start_date--end_date------------model_loc--","***Sta 87:  Unit 3D - Install New Air Distributor\n--10/21/24 through 10/26/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 10/14/24 to 10/19/24.\n………………………………"]
["X24-633583","***","2024-10-07","2024-12-09","Project Change","2024-09-16","2024-09-27","St 87","100","2","Unit 1E - Replace Engine Heads","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,87.064999999999998,"--start_date--end_date------------model_loc--","***St 87:  Unit 1E - Replace Engine Heads\n--10/7/24 through 12/9/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/16/24 to 9/27/24.\n………………………………"]
["X24-633584","***","2024-07-22","2024-09-20","Project Change",null,"2024-09-16","St 87","100","2","Unit 2E - Replace Engine Heads","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,87.066000000000003,"----end_date------------model_loc--","***St 87:  Unit 2E - Replace Engine Heads\n--7/22/24 through 9/20/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 7/22/24 to 9/16/24.\n………………………………"]
["X24-326860","***","2024-10-28","2024-11-01","Project Change","2024-09-09","2024-09-12","Sta 96","100","2","Unit 5C - Torque Engine Base Frame Anchor Bolts","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,96.037000000000006,"--start_date--end_date------------model_loc--","***Sta 96:  Unit 5C - Torque Engine Base Frame Anchor Bolts\n--10/28/24 through 11/1/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/9/24 to 9/12/24.\n………………………………"]
["X24-326854",null,"2024-07-08","2024-10-05",null,null,null,"Sta 96","100","2","Unit 7C - Foundation Regrout","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,96.039000000000001,null,"Sta 96:  Unit 7C - Foundation Regrout\n--7/8/24 through 10/5/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-633738",null,"2024-11-06","2024-11-17",null,null,null,"MLV 96-3D to MLV 97-3","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,96.3,null,"MLV 96-3D to MLV 97-3:  Anomaly Remediation\n--11/6/24 through 11/17/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-633775",null,"2024-10-25","2024-11-05",null,null,null,"MLV 97-3 to MLV 98-3","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,97.3,null,"MLV 97-3 to MLV 98-3:  Anomaly Remediation\n--10/25/24 through 11/5/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-633742",null,"2024-10-13","2024-10-24",null,null,null,"MLV 98-3 to MLV 99-3","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,98.3,null,"MLV 98-3 to MLV 99-3:  Anomaly Remediation\n--10/13/24 through 10/24/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-633743",null,"2024-10-01","2024-10-12",null,null,null,"MLV 100-3 to MLV 101-3","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,100.3,null,"MLV 100-3 to MLV 101-3:  Anomaly Remediation\n--10/1/24 through 10/12/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-443123","***","2024-09-24","2024-09-24","Project Change",null,null,"MLV 101-1 to MLV 96-1","100","2","Pig Runs - Cleaning 9/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","400462 ATMOS KY/TGP DANVILLE KY BOYLE",101.1,"------meters_affected--anticipated_impact--------model_loc--","***MLV 101-1 to MLV 96-1:  Pig Runs - Cleaning 9/24\n--9/24/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n400462 ATMOS KY/TGP DANVILLE KY BOYLE\n***Project Change\n………………………………"]
["X24-55873","***","2024-09-26","2024-09-26","Project Change",null,null,"MLV 101-1 to MLV 96-1","100","2","Pig Runs - Caliper/IMU/MFL-A 9/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","400462 ATMOS KY/TGP DANVILLE KY BOYLE",101.11,"------meters_affected--anticipated_impact--------model_loc--","***MLV 101-1 to MLV 96-1:  Pig Runs - Caliper/IMU/MFL-A 9/26\n--9/26/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n400462 ATMOS KY/TGP DANVILLE KY BOYLE\n***Project Change\n………………………………"]
["X24-633744",null,"2024-09-27","2024-10-12",null,null,null,"MLV 101-3 to MLV 102-3","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,101.3,null,"MLV 101-3 to MLV 102-3:  Anomaly Remediation\n--9/27/24 through 10/12/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-174231","***","2024-06-04","2024-09-25","Project Change",null,"2024-09-17","MLV 102-1 to MLV 102-1A","100","2","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,102.1,"----end_date------------model_loc--","***MLV 102-1 to MLV 102-1A:  Pipe Replacement\n--6/4/24 through 9/25/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 6/4/24 to 9/17/24.\n………………………………"]
["X24-174233","***","2024-09-26","2024-11-07","Project Change","2024-09-18",null,"MLV 102-1A to MLV 103-1","100","2","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,102.11,"--start_date--------------model_loc--","***MLV 102-1A to MLV 103-1:  Pipe Replacement\n--9/26/24 through 11/7/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/18/24 to 11/7/24.\n………………………………"]
["X24-633746","***","2024-09-19","2024-09-27","Project Change","2024-09-14",null,"MLV 102-3 to MLV 104-3","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,103.3,"--start_date--------------model_loc--","***MLV 102-3 to MLV 104-3:  Anomaly Remediation\n--9/19/24 through 9/27/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/14/24 to 9/27/24.\n………………………………"]
["X24-32467",null,"2024-12-03","2024-12-03",null,null,null,"MLV 105-1 to MLV 102-1","100","2","Pig Runs - Cleaning 12/3","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,105.1,null,"MLV 105-1 to MLV 102-1:  Pig Runs - Cleaning 12/3\n--12/3/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-32468",null,"2024-12-05","2024-12-05",null,null,null,"MLV 105-1 to MLV 102-1","100","2","Pig Runs - MFL-A 12/5","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,105.11,null,"MLV 105-1 to MLV 102-1:  Pig Runs - MFL-A 12/5\n--12/5/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-32469",null,"2024-12-10","2024-12-10",null,null,null,"MLV 105-1 to MLV 102-1","100","2","Pig Runs - MFL-S 12/10","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,105.12,null,"MLV 105-1 to MLV 102-1:  Pig Runs - MFL-S 12/10\n--12/10/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-32470",null,"2024-12-17","2024-12-17",null,null,null,"MLV 105-1 to MLV 102-1","100","2","Pig Runs - AFD 12/17","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,105.13,null,"MLV 105-1 to MLV 102-1:  Pig Runs - AFD 12/17\n--12/17/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-32471",null,"2024-12-19","2024-12-19",null,null,null,"MLV 105-1 to MLV 102-1","100","2","Pig Runs - EMAT 12/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,105.14,null,"MLV 105-1 to MLV 102-1:  Pig Runs - EMAT 12/19\n--12/19/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-633749","***","2024-08-26","2024-09-14","Completed",null,null,"MLV 104-3 to MLV 106-3","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,105.3,"------","***MLV 104-3 to MLV 106-3:  Anomaly Remediation\n***Completed"]
["X24-425778",null,"2024-10-21","2024-10-25",null,null,null,"Sta 106","100","2","Unit 1B - Inspect Scavenging Air Cylinder & Valves","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106.017,null,"Sta 106:  Unit 1B - Inspect Scavenging Air Cylinder & Valves\n--10/21/24 through 10/25/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-850671",null,"2024-08-06","2024-10-31",null,null,null,"Sta 106","100","2","Unit 2B - Zero Base Engine Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106.018,null,"Sta 106:  Unit 2B - Zero Base Engine Overhaul\n--8/6/24 through 10/31/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-425785",null,"2024-10-28","2024-11-01",null,null,null,"Sta 106","100","2","Unit 3B - Inspect Scavenging Air Cylinder & Valves","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106.01900000000001,null,"Sta 106:  Unit 3B - Inspect Scavenging Air Cylinder & Valves\n--10/28/24 through 11/1/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-425786",null,"2024-11-04","2024-11-08",null,null,null,"Sta 106","100","2","Unit 4B - Inspect Scavenging Air Cylinder & Valves","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106.02,null,"Sta 106:  Unit 4B - Inspect Scavenging Air Cylinder & Valves\n--11/4/24 through 11/8/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-425787",null,"2024-11-11","2024-11-15",null,null,null,"Sta 106","100","2","Unit 5B - Inspect Scavenging Air Cylinder & Valves","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106.021,null,"Sta 106:  Unit 5B - Inspect Scavenging Air Cylinder & Valves\n--11/11/24 through 11/15/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-626627",null,"2024-06-10","2024-12-31",null,null,null,"Sta 106","100","2","Unit 1C - Water Leak","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106.033,null,"Sta 106:  Unit 1C - Water Leak\n--6/10/24 through 12/31/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-618203",null,"2024-07-15","2024-12-31",null,null,null,"Sta 106","100","2","Unit 1C - Engine Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106.033,null,"Sta 106:  Unit 1C - Engine Maintenance\n--7/15/24 through 12/31/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-38969",null,"2024-12-03","2024-12-05",null,null,null,"Sta 106","100","2","Unit 1D - 4k Hr Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106.0491,null,"Sta 106:  Unit 1D - 4k Hr Inspection\n--12/3/24 through 12/5/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-138206",null,"2024-11-03","2024-11-03",null,null,null,"Sta 107A North Means","100","2","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,107,null,"Sta 107A North Means:  Annual ESD Test\n--11/3/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-396029",null,"2024-10-07","2024-10-19",null,null,null,"MLV 107-5 to MLV 109-5A","100","2","Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,107.5,null,"MLV 107-5 to MLV 109-5A:  Anomaly Remediation\n--10/7/24 through 10/19/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-788668",null,"2024-09-10","2024-09-27",null,null,null,"MLV 110-4 to MLV 111-4","100","2","Make Piggable","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,110.4,null,"MLV 110-4 to MLV 111-4:  Make Piggable\n--9/10/24 through 9/27/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-32443",null,"2024-10-29","2024-10-29",null,null,null,"MLV 110-4 to MLV 106-4","100","2","Pig Runs - Cleaning / Gauge 10/29/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,110.4,null,"MLV 110-4 to MLV 106-4:  Pig Runs - Cleaning / Gauge 10/29/24\n--10/29/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-32445",null,"2024-10-31","2024-10-31",null,null,null,"MLV 110-4 to MLV 106-4","100","2","Pig Runs - AFD 10/31/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,110.41,null,"MLV 110-4 to MLV 106-4:  Pig Runs - AFD 10/31/24\n--10/31/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-32446",null,"2024-11-05","2024-11-05",null,null,null,"MLV 110-4 to MLV 106-4","100","2","Pig Runs - EMAT 11/5/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,110.42,null,"MLV 110-4 to MLV 106-4:  Pig Runs - EMAT 11/5/24\n--11/5/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-788669","***","2024-09-23","2024-10-04","Project Change","2024-09-28","2024-10-11","MLV 111-4A to MLV 200-2S","100","2","Make Piggable","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,111.4,"--start_date--end_date------------model_loc--","***MLV 111-4A to MLV 200-2S:  Make Piggable\n--9/23/24 through 10/4/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/28/24 to 10/11/24.\n………………………………"]
["X24-925502",null,"2024-10-15","2024-10-16",null,null,null,"Sta 114","100","3","Building C Unit Valves","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,114,null,"Sta 114:  Building C Unit Valves\n--10/15/24 through 10/16/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-925503",null,"2024-10-17","2024-10-18",null,null,null,"Sta 114","100","3","Unit 3C - Unit Valves","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,114.033,null,"Sta 114:  Unit 3C - Unit Valves\n--10/17/24 through 10/18/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-144302",null,"2024-10-21","2024-10-23",null,null,null,"Sta 114","100",null,"Unit 1D - 8K hour inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,114.0491,null,"Sta 114:  Unit 1D - 8K hour inspection\n--10/21/24 through 10/23/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-144237",null,"2024-12-16","2024-12-18",null,null,null,"Sta 118A","100","3","Unit 1A - 8K Turbine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,118.001,null,"Sta 118A:  Unit 1A - 8K Turbine Inspection\n--12/16/24 through 12/18/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-925504","***","2024-09-17","2024-09-19","Project Change",null,null,"Sta 119","100","3","Unit 1A - Gas Service Cooler Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,119.001,"----------mantenance_desc------model_loc--","***Sta 119:  Unit 1A - Gas Service Cooler Inspection\n--9/17/24 through 9/19/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***Project Change\n………………………………"]
["X24-144244",null,"2024-11-18","2024-11-20",null,null,null,"Sta 119","100","3","Unit 1A - Turbine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,119.001,null,"Sta 119:  Unit 1A - Turbine Inspection\n--11/18/24 through 11/20/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-894651","***","2024-09-16","2024-09-20","Project Change","2024-09-09","2024-09-13","Sta 200","200","4","Unit 2A - Turbo","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,200.00200000000001,"--start_date--end_date------------model_loc--","***Sta 200:  Unit 2A - Turbo\n--9/16/24 through 9/20/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/9/24 to 9/13/24.\n………………………………"]
["X24-867878",null,"2024-09-30","2024-10-04",null,null,null,"Sta 200","200","4","Unit 1B - Annual Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,200.017,null,"Sta 200:  Unit 1B - Annual Engine Inspection\n--9/30/24 through 10/4/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-487698","***","2024-09-04","2024-09-14","Completed",null,null,"MLV 200-2DBL to MLV 200-2A","200","4","Make Piggable / Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","421018 TET/TGP HANGING ROCK SCIOTO",200.2,"------","***MLV 200-2DBL to MLV 200-2A:  Make Piggable / Replacement\n***Completed\nThe following meters are available for nominations:\n421018 TET/TGP HANGING ROCK SCIOTO"]
["X24-32448",null,"2024-11-07","2024-11-07",null,null,null,"MLV 200-2 to MLV 110-4","100","2","Pig Runs - Cleaning / Gauge 11/7/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,200.2,null,"MLV 200-2 to MLV 110-4:  Pig Runs - Cleaning / Gauge 11/7/24\n--11/7/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-32450",null,"2024-11-12","2024-11-12",null,null,null,"MLV 200-2 to MLV 110-4","100","2","Pig Runs - AFD 11/12/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,200.21,null,"MLV 200-2 to MLV 110-4:  Pig Runs - AFD 11/12/24\n--11/12/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-32451",null,"2024-11-14","2024-11-14",null,null,null,"MLV 200-2 to MLV 110-4","100","2","Pig Runs - EMAT 11/14/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,200.22,null,"MLV 200-2 to MLV 110-4:  Pig Runs - EMAT 11/14/24\n--11/14/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-961508","***","2024-09-17","2024-09-18","Completed",null,null,"MLV 203-2 to MLV 204-2","200","4","Hot Tap for Proposed New Meter Beech Hollow Biogas","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,203.2,"------","***MLV 203-2 to MLV 204-2:  Hot Tap for Proposed New Meter Beech Hollow Biogas\n***Completed"]
["X24-674850",null,"2024-07-01","2024-09-30",null,null,null,"Sta 204","200","4","Operational Conditions","This project will limit capacity thru the pipeline section which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,204,null,"Sta 204:  Operational Conditions\n--7/1/24 through 9/30/24:  This project will limit capacity thru the pipeline section which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-744508",null,"2024-09-25","2024-09-26",null,null,null,"Sta 204","200","4","Scrubber Filter Change","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,204,null,"Sta 204:  Scrubber Filter Change\n--9/25/24 through 9/26/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-806755",null,"2024-09-23","2024-09-26",null,null,null,"Sta 204","200","4","Unit 11A - Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,204.011,null,"Sta 204:  Unit 11A - Crankcase Inspection\n--9/23/24 through 9/26/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-806757","***","2024-09-10","2024-09-22","Project Change",null,"2024-09-19","Sta 204","200","4","Unit 12A - Turbo Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,204.012,"----end_date------------model_loc--","***Sta 204:  Unit 12A - Turbo Replacement\n--9/10/24 through 9/22/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/10/24 to 9/19/24.\n………………………………"]
["X23-1026453",null,"2024-11-19","2024-11-19",null,null,null,"MLV 204-2 to MLV 200-2","200","4","Pig Runs - Cleaning / Gauge 11/19/23","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,204.2,null,"MLV 204-2 to MLV 200-2:  Pig Runs - Cleaning / Gauge 11/19/23\n--11/19/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-1026454",null,"2024-11-21","2024-11-21",null,null,null,"MLV 204-2 to MLV 200-2","200","4","Pig Runs - AFD 11/21/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,204.21,null,"MLV 204-2 to MLV 200-2:  Pig Runs - AFD 11/21/24\n--11/21/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-1026455",null,"2024-11-26","2024-11-26",null,null,null,"MLV 204-2 to MLV 200-2","200","4","Pig Runs - EMAT 11/26/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,204.22,null,"MLV 204-2 to MLV 200-2:  Pig Runs - EMAT 11/26/24\n--11/26/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-867852",null,"2024-09-16","2024-12-06",null,null,null,"MLV 205-1 to MLV 205-1A","200","4","Class Change / Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,205.1,null,"MLV 205-1 to MLV 205-1A:  Class Change / Pipe Replacement\n--9/16/24 through 12/6/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-744510",null,"2024-09-23","2024-09-24",null,null,null,"Sta 209","200","4","Scrubber Filter Change","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209,null,"Sta 209:  Scrubber Filter Change\n--9/23/24 through 9/24/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-987533","***","2024-09-16","2024-09-19","Added",null,null,"Sta 209","200","4","Unit 3A - Replace OP Turbo","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209.00299999999999,"------","***Sta 209:  Unit 3A - Replace OP Turbo\n--9/16/24 through 9/19/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X23-910728",null,"2024-09-23","2024-09-26",null,null,null,"Sta 209","200","4","Unit 8A - Replace OP Turbo & Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209.00800000000001,null,"Sta 209:  Unit 8A - Replace OP Turbo & Crankcase Inspection\n--9/23/24 through 9/26/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-961737",null,"2023-09-21","2024-09-27",null,null,null,"Sta 214","200","4","Unit 8A - Oil System","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,214.00800000000001,null,"Sta 214:  Unit 8A - Oil System\n--9/21/23 through 9/27/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-744500",null,"2024-07-08","2024-09-28",null,null,null,"Sta 214","200","4","Unit 10A - Compressor Cylinder","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,214.01,null,"Sta 214:  Unit 10A - Compressor Cylinder\n--7/8/24 through 9/28/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-877138",null,"2024-08-15","2024-10-04",null,null,null,"MLV 214-3L to MLV 215-3","200","4","PHMSA Immediate Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,214.3,null,"MLV 214-3L to MLV 215-3:  PHMSA Immediate Anomaly Remediation\n--8/15/24 through 10/4/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-877140",null,"2024-08-15","2024-10-04",null,null,null,"MLV 215-3 to MLV 216-3","200","4","PHMSA Immediate Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,215.3,null,"MLV 215-3 to MLV 216-3:  PHMSA Immediate Anomaly Remediation\n--8/15/24 through 10/4/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-201661",null,"2024-06-10","2024-10-01",null,null,null,"Sta 219","200","4","Unit 1B - Engine Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,219.017,null,"Sta 219:  Unit 1B - Engine Upgrade\n--6/10/24 through 10/1/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-183166","***","2024-09-12","2024-09-12","Completed",null,null,"Station 230C","200","5","Unit 1A - Protective Device Tests","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,230.001,"------","***Station 230C:  Unit 1A - Protective Device Tests\n***Completed"]
["X24-183167",null,"2024-09-19","2024-09-19",null,null,null,"Station 230C","200","5","Unit 2A - Protective Device Tests","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,230.00200000000001,null,"Station 230C:  Unit 2A - Protective Device Tests\n--9/19/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-183168",null,"2024-09-26","2024-09-26",null,null,null,"Station 230C","200","5","Unit 3A - Protective Device Tests","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,230.00299999999999,null,"Station 230C:  Unit 3A - Protective Device Tests\n--9/26/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-183169",null,"2024-10-03","2024-10-03",null,null,null,"Station 230C","200","5","Unit 4A - Protective Device Tests","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,230.00399999999999,null,"Station 230C:  Unit 4A - Protective Device Tests\n--10/3/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-609053",null,"2024-10-14","2024-10-26",null,null,null,"MLV 230B-101 TO MLV 230B-105","200","5","SCCDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,230.1,null,"MLV 230B-101 TO MLV 230B-105:  SCCDA\n--10/14/24 through 10/26/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-609052","***","2024-09-30","2024-10-12","Project Change","2024-10-14","2024-10-26","MLV 241-2 TO MLV 242-2","200","5","SCCDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,237.2,"--start_date--end_date------------model_loc--","***MLV 241-2 TO MLV 242-2:  SCCDA\n--9/30/24 through 10/12/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 10/14/24 to 10/26/24.\n………………………………"]
["X24-542003",null,"2024-10-15","2024-10-15",null,null,null,"MLV 237-2 TO MLV 245-2","200","5","Pig Runs - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,237.2,null,"MLV 237-2 TO MLV 245-2:  Pig Runs - Maintenance\n--10/15/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-976524",null,"2024-09-30","2024-10-03",null,null,null,"Sta 241","200","5","Unit 2A - Compressor Valves","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,241.00200000000001,null,"Sta 241:  Unit 2A - Compressor Valves\n--9/30/24 through 10/3/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-957358",null,"2024-09-23","2024-09-27",null,null,null,"Sta 241","200","5","Unit 3A - Max Run Hrs & 203 Leaks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,241.00299999999999,null,"Sta 241:  Unit 3A - Max Run Hrs & 203 Leaks\n--9/23/24 through 9/27/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-168772",null,"2024-10-07","2024-10-08",null,null,null,"Sta 241","200","5","Unit 1B - 2K Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,241.017,null,"Sta 241:  Unit 1B - 2K Maintenance\n--10/7/24 through 10/8/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-168773",null,"2024-10-09","2024-10-10",null,null,null,"Sta 241","200","5","Unit 2B - 2K Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,241.018,null,"Sta 241:  Unit 2B - 2K Maintenance\n--10/9/24 through 10/10/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-839015",null,"2024-09-12","2024-09-30",null,null,null,"Sta 245 West Winfield","200","5","Building A & B Safety System Upgrade","This project will require building outages, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,245,null,"Sta 245 West Winfield:  Building A & B Safety System Upgrade\n--9/12/24 through 9/30/24:  This project will require building outages, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-255248",null,"2024-09-11","2024-10-10",null,null,null,"Sta 245","200","5","Unit 7A - Controls Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,245.00700000000001,null,"Sta 245:  Unit 7A - Controls Upgrade\n--9/11/24 through 10/10/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-960999",null,"2024-10-07","2024-10-10",null,null,null,"Sta 249","200","5","Unit 1B - Compressor Rods","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,249.017,null,"Sta 249:  Unit 1B - Compressor Rods\n--10/7/24 through 10/10/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-186378","***","2024-10-23","2024-10-23","Project Change",null,null,"MLV 249-1 TO MLV 254-1","200","5","Pig Runs - EMAT 10/23","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,249.12,"----------mantenance_desc------model_loc--","***MLV 249-1 TO MLV 254-1:  Pig Runs - EMAT 10/23\n--10/23/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Project Change\n………………………………"]
["X24-633590",null,"2024-10-15","2024-10-15",null,null,null,"Sta 260A Southwick","200","6","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,260,null,"Sta 260A Southwick:  Annual ESD Test\n--10/15/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-957284","***","2024-09-17","2024-09-17","Completed",null,null,"MLV 260A-101.1 TO MLV 260A-103","200","6","Pig Runs - MFL-A/Cal/IMU 9/17","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420104 WESTFLD/TGP WESTFIELD MA HAMPDEN\n420401 HOLYOKE/TGP HOLYOKE MA 2 HAMPDEN",260.10000000000002,"------","***MLV 260A-101.1 TO MLV 260A-103:  Pig Runs - MFL-A/Cal/IMU 9/17\n***Completed\nThe following meters are available for nominations:\n420104 WESTFLD/TGP WESTFIELD MA HAMPDEN\n420401 HOLYOKE/TGP HOLYOKE MA 2 HAMPDEN"]
["X24-957285","***","2024-09-17","2024-09-17","Completed",null,null,"MLV 260A-101.1 TO MLV 260A-103","200","6","Pig Runs - EMAT 9/17","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420104 WESTFLD/TGP WESTFIELD MA HAMPDEN\n420401 HOLYOKE/TGP HOLYOKE MA 2 HAMPDEN",260.11,"------","***MLV 260A-101.1 TO MLV 260A-103:  Pig Runs - EMAT 9/17\n***Completed\nThe following meters are available for nominations:\n420104 WESTFLD/TGP WESTFIELD MA HAMPDEN\n420401 HOLYOKE/TGP HOLYOKE MA 2 HAMPDEN"]
["X24-633591",null,"2024-10-16","2024-10-17",null,null,null,"Station 261 Agawam","200","6","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420901 BERKPWR/TGP BERKSHIRE POWER SALES H",261,null,"Station 261 Agawam:  Annual ESD Test\n--10/16/24 through 10/17/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n420901 BERKPWR/TGP BERKSHIRE POWER SALES H\n………………………………"]
["X24-609050","***","2024-10-16","2024-10-31","Project Change","2024-10-30","2024-11-14","MLV 263A-100","200","6","Direct Assessment","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,263.10000000000002,"--start_date--end_date------------model_loc--","***MLV 263A-100:  Direct Assessment\n--10/16/24 through 10/31/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 10/30/24 to 11/14/24.\n………………………………"]
["X24-174294",null,"2024-08-26","2024-09-20",null,null,null,"Sta 264","200","6","Unit 1C & 2C Overhauls and Control System Upgrades","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,264,null,"Sta 264:  Unit 1C & 2C Overhauls and Control System Upgrades\n--8/26/24 through 9/20/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-520791",null,"2025-07-07","2025-07-25",null,null,null,"MLV 265E-103 to MLV 265E-104","200","6","Regulator Installation & Pipe replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420750 NARNGST/TGP CRANSTON SALES PROVIDEN\n420926 RISEC/TGP FPLE RISE PROVIDENCE\n55784 RHOBIO/TGP SCITUATE RNG REC PROVIDE\n55785 RHOBIO/TGP SCITUATE RNG BUYBACK PR\n420910 NARNGST/TGP SMITHFIELD DELIVERY PRO\n420758 NARNGST/TGP LINCOLN SMS PROVIDENCE",265.10000000000002,null,"MLV 265E-103 to MLV 265E-104:  Regulator Installation & Pipe replacement\n--7/7/25 through 7/25/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n420750 NARNGST/TGP CRANSTON SALES PROVIDEN\n420926 RISEC/TGP FPLE RISE PROVIDENCE\n55784 RHOBIO/TGP SCITUATE RNG REC PROVIDE\n55785 RHOBIO/TGP SCITUATE RNG BUYBACK PR\n420910 NARNGST/TGP SMITHFIELD DELIVERY PRO\n420758 NARNGST/TGP LINCOLN SMS PROVIDENCE\n………………………………"]
["X24-159539",null,"2024-09-18","2024-10-15",null,null,null,"Sta. 267 Hopkinton","200","6","Station Controls Upgrade","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,267,null,"Sta. 267 Hopkinton:  Station Controls Upgrade\n--9/18/24 through 10/15/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-159540",null,"2024-09-18","2024-10-11",null,null,null,"Sta. 267","200","6","Unit 1B Controls Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,267.017,null,"Sta. 267:  Unit 1B Controls Upgrade\n--9/18/24 through 10/11/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-159542",null,"2024-09-22","2024-10-15",null,null,null,"Sta. 267","200","6","Unit 2B Controls Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,267.01799999999997,null,"Sta. 267:  Unit 2B Controls Upgrade\n--9/22/24 through 10/15/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-27480","***","2024-11-13","2024-11-13","Project Change",null,null,"MLV 267-1 to 270C-101","200","6","Pig Run - EMAT 11/13/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,267.12,"----------mantenance_desc------model_loc--","***MLV 267-1 to 270C-101:  Pig Run - EMAT 11/13/24\n--11/13/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Project Change\n………………………………"]
["X24-609051","***","2024-10-16","2024-10-30","Project Change","2024-10-30","2024-11-13","MLV 268A-200","200","6","Direct Assessment","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,268.2,"--start_date--end_date------------model_loc--","***MLV 268A-200:  Direct Assessment\n--10/16/24 through 10/30/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 10/30/24 to 11/13/24.\n………………………………"]
["X24-847658",null,"2024-10-07","2024-10-11",null,null,null,"MLV 270C-103 to MLV 270C-104","200","6","Meter Station Upgrade (Meter Peabody PIN 420658)","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","420658 MMWEC/TGP PEABODY SALES ESSEX",270.10000000000002,null,"MLV 270C-103 to MLV 270C-104:  Meter Station Upgrade (Meter Peabody PIN 420658)\n--10/7/24 through 10/11/24:  This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.  Potential out of path restrictions may be at risk.\n420658 MMWEC/TGP PEABODY SALES ESSEX\n………………………………"]
["X24-894724",null,"2024-11-12","2024-11-12",null,null,null,"Sta 303","300","4","Unit 1A - Solar Software Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,303.00099999999998,null,"Sta 303:  Unit 1A - Solar Software Upgrade\n--11/12/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-201666",null,"2024-09-23","2024-09-30",null,null,null,"Sta 307","300","4","Station Upgrade","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,307,null,"Sta 307:  Station Upgrade\n--9/23/24 through 9/30/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-201664",null,"2024-07-11","2024-10-26",null,null,null,"Sta 307","300","4","Unit 6A - Engine Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,307.00599999999997,null,"Sta 307:  Unit 6A - Engine Upgrade\n--7/11/24 through 10/26/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1000466","***","2024-10-15","2024-10-15","Added",null,null,"Sta 310","300","4","Unit 1A - Water Wash","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,310.00099999999998,"------","***Sta 310:  Unit 1A - Water Wash\n--10/15/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-782049","***","2024-10-29","2024-10-30","Project Change",null,null,"Sta 310","300","4","Unit 1A - Solar Inspection & Borescope","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,310.00099999999998,"----------mantenance_desc------model_loc--","***Sta 310:  Unit 1A - Solar Inspection & Borescope\n--10/29/24 through 10/30/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Project Change\n………………………………"]
["X24-850748",null,"2024-11-04","2024-11-08",null,null,null,"Ellisburg Storage","300","4","Shut-in Test","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","460012 – DOMINION/TGP ELLISBURG INJECTION PO",312.75,null,"Ellisburg Storage:  Shut-in Test\n--11/4/24 through 11/8/24:  This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.  Potential out of path restrictions may be at risk.\n460012 – DOMINION/TGP ELLISBURG INJECTION PO\n………………………………"]
["X24-373549",null,"2024-09-16","2024-09-20",null,null,null,"Sta 313 Coudersport","300","4","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,313,null,"Sta 313 Coudersport:  Annual ESD Test\n--9/16/24 through 9/20/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-640122","***","2024-09-09","2024-09-12","Completed",null,null,"MLV 313-1 to MLV 314-1","300","4","Hot Tap for New Meter Station - Greylock Potter Meter","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,313.10000000000002,"------","***MLV 313-1 to MLV 314-1:  Hot Tap for New Meter Station - Greylock Potter Meter\n***Completed"]
["X23-640124","***","2024-09-09","2024-09-12","Completed",null,null,"MLV 313-2 to MLV 314-2","300","4","Hot Tap for New Meter Station - Greylock Potter Meter","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,313.2,"------","***MLV 313-2 to MLV 314-2:  Hot Tap for New Meter Station - Greylock Potter Meter\n***Completed"]
["X24-572316",null,"2024-10-15","2024-10-15",null,null,null,"MLV 313-2 to MLV 307-2","300","4","Pig Runs - Cleaning 10/15","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,313.2,null,"MLV 313-2 to MLV 307-2:  Pig Runs - Cleaning 10/15\n--10/15/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-850750",null,"2024-10-21","2024-11-04",null,null,null,"Harrison Storage","300","4","Shut-in Test","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","460004 – DOMINION/TGP HARRISON INJECTION POT",313.5,null,"Harrison Storage:  Shut-in Test\n--10/21/24 through 11/4/24:  This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.  Potential out of path restrictions may be at risk.\n460004 – DOMINION/TGP HARRISON INJECTION POT\n………………………………"]
["X24-168776",null,"2024-10-14","2024-10-14",null,null,null,"Sta 405A","300","5","Unit 1A - 4k Water Wash","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,313.52,null,"Sta 405A:  Unit 1A - 4k Water Wash\n--10/14/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-168778",null,"2024-10-16","2024-10-16",null,null,null,"Sta 405A","300","5","Unit 1A - 4K - 8K Solar Turbine Borescope Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,313.52999999999997,null,"Sta 405A:  Unit 1A - 4K - 8K Solar Turbine Borescope Inspection\n--10/16/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43914",null,"2024-09-30","2024-10-16",null,null,null,"MLVS C313-0608","300","4","Pig Runs (Tethered) - Cleaning 10/8","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,313.60000000000002,null,"MLVS C313-0608:  Pig Runs (Tethered) - Cleaning 10/8\n--9/30/24 through 10/16/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-43917",null,"2024-09-30","2024-10-16",null,null,null,"MLVS C313-0608","300","4","Pig Runs (Tethered) - MFL 10/9","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,313.61,null,"MLVS C313-0608:  Pig Runs (Tethered) - MFL 10/9\n--9/30/24 through 10/16/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-850666",null,"2024-09-01","2024-10-31",null,null,null,"Hebron Storage","300","4","Blast, Recoat, and Pipe Insulation Replacement","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","400485 HEBRON STORAGE INJECTION POTTER\n470001 HEBRON STORAGE WITHDRAWAL POTTER",313.75,null,"Hebron Storage:  Blast, Recoat, and Pipe Insulation Replacement\n--9/1/24 through 10/31/24:  This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.  Potential out of path restrictions may be at risk.\n400485 HEBRON STORAGE INJECTION POTTER\n470001 HEBRON STORAGE WITHDRAWAL POTTER\n………………………………"]
["X24-850749",null,"2024-11-04","2024-11-08",null,null,null,"Hebron Storage","300","4","Shut-in Test","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential out of path restrictions may be at risk.","400485 HEBRON STORAGE INJECTION POTTER\n470001 HEBRON STORAGE WITHDRAWAL POTTER",313.76,null,"Hebron Storage:  Shut-in Test\n--11/4/24 through 11/8/24:  This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.  Potential out of path restrictions may be at risk.\n400485 HEBRON STORAGE INJECTION POTTER\n470001 HEBRON STORAGE WITHDRAWAL POTTER\n………………………………"]
["X24-888630",null,"2024-10-09","2024-10-09",null,null,null,"Sta 313A Ellisburg","300","4","Annual ESD Testing","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.",null,313.8,null,"Sta 313A Ellisburg:  Annual ESD Testing\n--10/9/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1000465","***","2024-10-16","2024-10-16","Added",null,null,"Sta 315","300","4","Unit 1B - Water Wash","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,315.017,"------","***Sta 315:  Unit 1B - Water Wash\n--10/16/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-782038","***","2024-10-22","2024-10-23","Project Change",null,null,"Sta 315","300","4","Unit 1B - Solar Inspection & Borescope","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,315.017,"----------mantenance_desc------model_loc--","***Sta 315:  Unit 1B - Solar Inspection & Borescope\n--10/22/24 through 10/23/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Project Change\n………………………………"]
["X24-925659",null,"2024-11-05","2024-11-07",null,null,null,"MLV 316-1 to MLV 317-1","300","4","Meter Station Upgrade Monarch Midstream Mainsburg (Pin: 412822)","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,316.10000000000002,null,"MLV 316-1 to MLV 317-1:  Meter Station Upgrade Monarch Midstream Mainsburg (Pin: 412822)\n--11/5/24 through 11/7/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-916893",null,"2024-10-07","2024-10-08",null,null,null,"Sta 317 Troy","300","4","5-year Electric Substation Inspection","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,317,null,"Sta 317 Troy:  5-year Electric Substation Inspection\n--10/7/24 through 10/8/24:  This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-809845",null,"2024-09-16","2024-09-20",null,null,null,"Sta 317","300","4","Unit 1B - 5-Year gearbox inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,317.017,null,"Sta 317:  Unit 1B - 5-Year gearbox inspection\n--9/16/24 through 9/20/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-879135",null,"2024-09-24","2024-09-25",null,null,null,"Sta 321 Clifford","300","5","Annual ESD Testing","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.",null,321,null,"Sta 321 Clifford:  Annual ESD Testing\n--9/24/24 through 9/25/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-985487","***","2024-09-12","2024-09-12","Completed",null,null,"MLV 321-1 to MLV 325-1","300","5","Pig Runs - Cleaning 9/12/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420277 UGI UT/TGP HONESDALE PA SALES WAYNE\n420319 UGI UT/TGP MILFORD PA PIKE",321.08999999999997,"------","***MLV 321-1 to MLV 325-1:  Pig Runs - Cleaning 9/12/24\n***Completed\nThe following meters are available for nominations:\n420277 UGI UT/TGP HONESDALE PA SALES WAYNE\n420319 UGI UT/TGP MILFORD PA PIKE"]
["X24-56070","***","2024-09-13","2024-09-13","Completed",null,null,"MLV 321-1 to MLV 325-1","300","4","Pig Runs - EMAT 9/13/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.","420277 UGI UT/TGP HONESDALE PA SALES WAYNE\n420319 UGI UT/TGP MILFORD PA PIKE",321.16000000000003,"------","***MLV 321-1 to MLV 325-1:  Pig Runs - EMAT 9/13/24\n***Completed\nThe following meters are available for nominations:\n420277 UGI UT/TGP HONESDALE PA SALES WAYNE\n420319 UGI UT/TGP MILFORD PA PIKE"]
["X24-275177",null,"2024-09-30","2024-11-02",null,null,null,"MLV 326-1 to MLV 327-1","300","5","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,326.10000000000002,null,"MLV 326-1 to MLV 327-1:  Anomaly Remediation\n--9/30/24 through 11/2/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-275178",null,"2024-09-16","2024-09-28",null,null,null,"MLV 328-1 to MLV 329-1R","300","5","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420093\tCON ED/TGP WHITE PLAINS NY WESTCHES\n420101\tTRNSCO/TGP RIVERVALE NEW JERSEY BER\n420201\tCON ED/TGP TAPPAN NY ROCKLAND\n420207\tAGT/TGP MAHWAH NEW JERSEY BERGEN\n420226\tPSEG/TGP RAMSEY NJ BERGEN\n420293\tCON ED/TGP PEARL RIVER NY ROCKLAND\n420339\tPSEG/TGP WEST MILFORD NJ PASSAIC\n420344\tCON ED/TGP RYE NY WESTCHESTER\n420410\tELIZTOWN/TGP SUSSEX NJ SUSSEX\n420450\tELIZTOWN/TGP VERNON NJ SUSSEX\n420477\tCON ED/TGP KNOLLWOOD NY WESTCHESTER\n420516\tPSEG/TGP RINGWOOD NJ PASSAIC\n420608\tNJ NATGS/TGP NEW CLINTON ROAD NJ BE",328.1,null,"MLV 328-1 to MLV 329-1R:  Anomaly Remediation\n--9/16/24 through 9/28/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n420093\tCON ED/TGP WHITE PLAINS NY WESTCHES\n420101\tTRNSCO/TGP RIVERVALE NEW JERSEY BER\n420201\tCON ED/TGP TAPPAN NY ROCKLAND\n420207\tAGT/TGP MAHWAH NEW JERSEY BERGEN\n420226\tPSEG/TGP RAMSEY NJ BERGEN\n420293\tCON ED/TGP PEARL RIVER NY ROCKLAND\n420339\tPSEG/TGP WEST MILFORD NJ PASSAIC\n420344\tCON ED/TGP RYE NY WESTCHESTER\n420410\tELIZTOWN/TGP SUSSEX NJ SUSSEX\n420450\tELIZTOWN/TGP VERNON NJ SUSSEX\n420477\tCON ED/TGP KNOLLWOOD NY WESTCHESTER\n420516\tPSEG/TGP RINGWOOD NJ PASSAIC\n420608\tNJ NATGS/TGP NEW CLINTON ROAD NJ BE\n………………………………"]
["X24-781836","***","2024-09-23","2024-10-04","Project Change","2024-09-09","2024-09-20","MLV 329B-100","300","5","Direct Assessment","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420293 CON ED/TGP PEARL RIVER NY ROCKLAND",329.1,"--start_date--end_date------------model_loc--","***MLV 329B-100:  Direct Assessment\n--9/23/24 through 10/4/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n420293 CON ED/TGP PEARL RIVER NY ROCKLAND\n***\nDate Change, Previously scheduled 9/9/24 to 9/20/24.\n………………………………"]
["X24-874860","***","2024-09-30","2024-10-04","Project Change","2024-08-16","2024-11-01","MLV 337-1 to MLV 338-1","300","6","PHMSA Immediate Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,337.1,"--start_date--end_date------------model_loc--","***MLV 337-1 to MLV 338-1:  PHMSA Immediate Anomaly Remediation\n--9/30/24 through 10/4/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***\nDate Change, Previously scheduled 8/16/24 to 11/1/24.\n………………………………"]
["X24-874865","***","2024-10-07","2024-10-11","Project Change","2024-08-16","2024-11-01","MLV 339-1 to MLV 340-1","300","6","PHMSA Immediate Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,339.1,"--start_date--end_date------------model_loc--","***MLV 339-1 to MLV 340-1:  PHMSA Immediate Anomaly Remediation\n--10/7/24 through 10/11/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***\nDate Change, Previously scheduled 8/16/24 to 11/1/24.\n………………………………"]
["X24-874867","***","2024-09-23","2024-10-28","Project Change","2024-08-16","2024-11-01","MLV 340-1 to MLV 341-1","300","6","PHMSA Immediate Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,340.1,"--start_date--end_date------------model_loc--","***MLV 340-1 to MLV 341-1:  PHMSA Immediate Anomaly Remediation\n--9/23/24 through 10/28/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***\nDate Change, Previously scheduled 8/16/24 to 11/1/24.\n………………………………"]
["X24-874868","***","2024-09-16","2024-09-20","Project Change","2024-08-16","2024-11-01","MLV 341-1 to MLV 342-1","300","6","PHMSA Immediate Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,341.1,"--start_date--end_date------------model_loc--","***MLV 341-1 to MLV 342-1:  PHMSA Immediate Anomaly Remediation\n--9/16/24 through 9/20/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***\nDate Change, Previously scheduled 8/16/24 to 11/1/24.\n………………………………"]
["X24-874874","***","2024-09-16","2024-09-27","Project Change","2024-08-16","2024-11-01","MLV 342-1 to MLV 343-1","300","6","PHMSA Immediate Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,342.1,"--start_date--end_date------------model_loc--","***MLV 342-1 to MLV 343-1:  PHMSA Immediate Anomaly Remediation\n--9/16/24 through 9/27/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***\nDate Change, Previously scheduled 8/16/24 to 11/1/24.\n………………………………"]
["X24-874875","***","2024-08-16","2024-11-01","Completed",null,null,"MLV 343-1 to MLV 344-1","300","6","PHMSA Immediate Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,343.1,"------","***MLV 343-1 to MLV 344-1:  PHMSA Immediate Anomaly Remediation\n***Completed"]
["X24-874876","***","2024-08-26","2024-09-20","Project Change","2024-08-16","2024-11-01","MLV 344-1 to MLV 345-1","300","6","PHMSA Immediate Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,344.1,"--start_date--end_date------------model_loc--","***MLV 344-1 to MLV 345-1:  PHMSA Immediate Anomaly Remediation\n--8/26/24 through 9/20/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***\nDate Change, Previously scheduled 8/16/24 to 11/1/24.\n………………………………"]
["X24-874879","***","2024-08-16","2024-11-01","Completed",null,null,"MLV 346-1 to MLV 347-1","300","6","PHMSA Immediate Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,346.1,"------","***MLV 346-1 to MLV 347-1:  PHMSA Immediate Anomaly Remediation\n***Completed"]
["X24-789723",null,"2024-12-03","2024-12-03",null,null,null,"MLV 347A-201A to EOL","300","5","Pig Re-Run - Cleaning / Gauge 12/3","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420128 YANK GAS/TGP WALLINGFORD CT NEW HAV",347.2,null,"MLV 347A-201A to EOL:  Pig Re-Run - Cleaning / Gauge 12/3\n--12/3/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n420128 YANK GAS/TGP WALLINGFORD CT NEW HAV\n………………………………"]
["X24-789724",null,"2024-12-03","2024-12-03",null,null,null,"MLV 347A-201A to EOL","300","5","Pig Re-Run - MFL-C 12/3","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420128 YANK GAS/TGP WALLINGFORD CT NEW HAV",347.21,null,"MLV 347A-201A to EOL:  Pig Re-Run - MFL-C 12/3\n--12/3/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n420128 YANK GAS/TGP WALLINGFORD CT NEW HAV\n………………………………"]
["X24-874881","***","2024-08-16","2024-11-01","Completed",null,null,"MLV 349-1 to MLV 350-1","300","6","PHMSA Immediate Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,349.1,"------","***MLV 349-1 to MLV 350-1:  PHMSA Immediate Anomaly Remediation\n***Completed"]
["X24-76758",null,"2024-11-05","2024-11-05",null,null,null,"MLV 400-1 to MLV 409-1","400","0","Pig Run - Maintenance Cleaning 11/5","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412733 UES/TGP MYRICK BROOKS",400.13,null,"MLV 400-1 to MLV 409-1:  Pig Run - Maintenance Cleaning 11/5\n--11/5/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n412733 UES/TGP MYRICK BROOKS\n………………………………"]
["X24-76772",null,"2024-11-06","2024-11-06",null,null,null,"MLV 400-2 to MLV 409-2","400","0","Pig Run - Maintenance Cleaning 11/6","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,400.23,null,"MLV 400-2 to MLV 409-2:  Pig Run - Maintenance Cleaning 11/6\n--11/6/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-27873",null,"2024-11-12","2024-11-12",null,null,null,"Sta 500-1 to Sta 823 (MLV 507-1)","500","L","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420373 TRNSCO/TGP KINDER LA EXCH (BI 1\n420708 ELIZ NG/TGP GRANT LA SALES ALLEN\n420436 VERNON/TGP PITKIN LA VERNON\n420793 ELIZ NG/TGP J R FRANKS 1 VERNON\n420388 PROVNCAL/TGP PROVENCAL LA NATCHITOC",500.1,null,"Sta 500-1 to Sta 823 (MLV 507-1):  Pig Run - Maintenance\n--11/12/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n420373 TRNSCO/TGP KINDER LA EXCH (BI 1\n420708 ELIZ NG/TGP GRANT LA SALES ALLEN\n420436 VERNON/TGP PITKIN LA VERNON\n420793 ELIZ NG/TGP J R FRANKS 1 VERNON\n420388 PROVNCAL/TGP PROVENCAL LA NATCHITOC\n………………………………"]
["X24-973419",null,"2024-10-16","2024-10-16",null,null,null,"STA 507F to STA 823","800","L","Pig Run - EMAT 9/26/24","This activity will require operating at controlled flow rates.This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,507.1,null,"STA 507F to STA 823:  Pig Run - EMAT 9/26/24\n--10/16/24:  This activity will require operating at controlled flow rates.This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-981801","***","2024-09-15","2024-09-15","Completed",null,null,"MLV 508-1 to MLV 509-1","500","L","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,508.1,"------","***MLV 508-1 to MLV 509-1:  Anomaly Remediation\n***Completed"]
["X23-374936","***","2024-09-15","2024-09-19","Project Change","2024-09-13","2024-09-18","MLV 527-1 to MLV 529-1","500","L","Pig Runs - Cleaning/Gauge 9/13/24 to 9/19/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,527.1,"--start_date--end_date------mantenance_desc------model_loc--","***MLV 527-1 to MLV 529-1:  Pig Runs - Cleaning/Gauge 9/13/24 to 9/19/24\n--9/15/24 through 9/19/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/13/24 to 9/18/24.\n………………………………"]
["X23-374937","***","2024-09-19","2024-09-20","Project Change",null,"2024-09-19","MLV 527-1 to MLV 529-1","500","L","Pig Runs - Caliper/IMU 9/20/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,527.11,"----end_date------mantenance_desc------model_loc--","***MLV 527-1 to MLV 529-1:  Pig Runs - Caliper/IMU 9/20/24\n--9/19/24 through 9/20/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/19/24 to 9/19/24.\n………………………………"]
["X23-374938","***","2024-09-21","2024-09-22","Project Change",null,"2024-09-21","MLV 527-1 to MLV 529-1","500","L","Pig Runs - MFL-C 9/22/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,527.12,"----end_date------mantenance_desc------model_loc--","***MLV 527-1 to MLV 529-1:  Pig Runs - MFL-C 9/22/24\n--9/21/24 through 9/22/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/21/24 to 9/21/24.\n………………………………"]
["X24-976558",null,"2024-11-07","2024-11-20",null,null,null,"MLVS 529D-100","500","L","Install New Tee","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420556 TGP/SNG TOCA EXCHANGE ST BERNARD",529.1,null,"MLVS 529D-100:  Install New Tee\n--11/7/24 through 11/20/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n420556 TGP/SNG TOCA EXCHANGE ST BERNARD\n………………………………"]
["X23-587635",null,"2023-06-01","2024-09-30",null,null,null,"Sta 530","500","L","Units 2A, 4A - Automation Upgrade","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,530,null,"Sta 530:  Units 2A, 4A - Automation Upgrade\n--6/1/23 through 9/30/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-898668","***","2024-08-26","2024-09-20","Project Change",null,"2024-09-13","Sta 530","500","L","MCC Replacement","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,530,"----end_date------------model_loc--","***Sta 530:  MCC Replacement\n--8/26/24 through 9/20/24:  This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 8/26/24 to 9/13/24.\n………………………………"]
["X24-781915","***","2024-09-26","2024-10-09","Project Change","2024-09-23",null,"MLV 532-2 to MLV 533-2","500","L","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,532.20000000000005,"--start_date--------------model_loc--","***MLV 532-2 to MLV 533-2:  Anomaly Remediation\n--9/26/24 through 10/9/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/23/24 to 10/9/24.\n………………………………"]
["X24-741376","***","2024-09-26","2024-10-09","Project Change","2024-09-23",null,"MLV 533-2 to MLV 534-2","500","L","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,533.20000000000005,"--start_date--------------model_loc--","***MLV 533-2 to MLV 534-2:  Anomaly Remediation\n--9/26/24 through 10/9/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/23/24 to 10/9/24.\n………………………………"]
["X23-1078699","***","2023-10-25","2024-11-14","Project Change",null,"2025-01-19","MLV 535-1A to MLV 536-1","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,535.1,"----end_date------------model_loc--","***MLV 535-1A to MLV 536-1:  Anomaly Remediation\n--10/25/23 through 11/14/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 10/25/23 to 1/19/25.\n………………………………"]
["X24-917021",null,"2024-09-25","2024-09-25",null,null,null,"Sta 538 Heidelberg","500","1","Station ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,538,null,"Sta 538 Heidelberg:  Station ESD Test\n--9/25/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-973207",null,"2024-12-02","2024-12-04",null,null,null,"Sta 538","500","1","Unit 1C - 4k hr Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,538.03300000000002,null,"Sta 538:  Unit 1C - 4k hr Inspection\n--12/2/24 through 12/4/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-888594","***","2024-09-16","2024-09-16","Completed",null,null,"Sta 542 Dekalb","500","1","Ground Fault","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.",null,542,"------","***Sta 542 Dekalb:  Ground Fault\n***Completed"]
["X24-891253",null,"2024-09-18","2024-10-01",null,null,null,"Sta 542","500","1","Unit 1A - Orifice and Spacer Plates","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,542.00099999999998,null,"Sta 542:  Unit 1A - Orifice and Spacer Plates\n--9/18/24 through 10/1/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-891252",null,"2024-10-02","2024-10-16",null,null,null,"Sta 542","500","1","Unit 2A - Orifice and Spacer Plates","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,542.00199999999995,null,"Sta 542:  Unit 2A - Orifice and Spacer Plates\n--10/2/24 through 10/16/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-94907",null,"2024-02-12","2024-11-29",null,null,null,"Sta 542","500","1","Unit 3A - Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,542.00300000000004,null,"Sta 542:  Unit 3A - Overhaul\n--2/12/24 through 11/29/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-38912","***","2023-11-30","2024-09-20","Project Change",null,"2024-09-13","Sta 542","200","1","Unit 4A - Replace Compressor Heads & Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,542.00400000000002,"----end_date------------model_loc--","***Sta 542:  Unit 4A - Replace Compressor Heads & Engine Inspection\n--11/30/23 through 9/20/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 11/30/23 to 9/13/24.\n………………………………"]
["X24-41548","***","2024-09-17","2024-09-17","Completed",null,null,"MLV 542-2 to MLV 538-2","500","1","Pig Runs - Cleaning/Gauge 9/17","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,542.20000000000005,"------","***MLV 542-2 to MLV 538-2:  Pig Runs - Cleaning/Gauge 9/17\n***Completed"]
["X24-41549",null,"2024-09-19","2024-09-19",null,null,null,"MLV 542-2 to MLV 538-2","500","1","Pig Runs - MFL 9/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,542.21,null,"MLV 542-2 to MLV 538-2:  Pig Runs - MFL 9/19\n--9/19/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-806571",null,"2024-10-22","2024-10-22",null,null,null,"MLV 542-3 to MLV 541-3","500","1","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,542.29999999999995,null,"MLV 542-3 to MLV 541-3:  Pig Run - Maintenance\n--10/22/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-888602",null,"2024-09-24","2024-09-24",null,null,null,"Sta. 546 (Columbus)","500","1","Annual ESD & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.",null,546,null,"Sta. 546 (Columbus):  Annual ESD & Maintenance\n--9/24/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-166994",null,"2024-02-15","2024-09-30",null,null,null,"Sta 546","500","1","Unit 3A - Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,546.00300000000004,null,"Sta 546:  Unit 3A - Overhaul\n--2/15/24 through 9/30/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-38915",null,"2024-04-30","2024-10-31",null,null,null,"Sta 546","500","1","Unit 3A - Discharge Valve","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,546.00300000000004,null,"Sta 546:  Unit 3A - Discharge Valve\n--4/30/24 through 10/31/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-850681",null,"2025-03-03","2025-04-18",null,null,null,"Sta 546","500","1","Unit 1B - Turbine Exchange","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,546.01700000000005,null,"Sta 546:  Unit 1B - Turbine Exchange\n--3/3/25 through 4/18/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-517419","***","2024-09-10","2024-09-21","Project Change",null,"2024-09-19","MLV 546-1 to MLV 546-1A","500","1","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,546.1,"----end_date------------model_loc--","***MLV 546-1 to MLV 546-1A:  Pipe Replacement\n--9/10/24 through 9/21/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/10/24 to 9/19/24.\n………………………………"]
["X24-850682",null,"2024-10-01","2024-11-01",null,null,null,"MLV 546-1BL and MLV 546-2BL","500","1","Install Actuators","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,546.1,null,"MLV 546-1BL and MLV 546-2BL:  Install Actuators\n--10/1/24 through 11/1/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-850684",null,"2024-10-01","2024-11-01",null,null,null,"MLV 546-1A and MLV 546-2A","500","1","Install Actuators","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,546.1,null,"MLV 546-1A and MLV 546-2A:  Install Actuators\n--10/1/24 through 11/1/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-293538","***","2024-11-11","2024-11-15","Project Change","2024-10-21","2024-10-25","Sta 550","500","1","Fuel Coalescer","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,550,"--start_date--end_date------------model_loc--","***Sta 550:  Fuel Coalescer\n--11/11/24 through 11/15/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 10/21/24 to 10/25/24.\n………………………………"]
["X24-293542","***","2024-11-11","2024-11-15","Project Change","2024-10-21","2024-10-25","Sta 550","500","1","UPS Upgrade for Sta1 & Hyper Fuel System","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,550,"--start_date--end_date------------model_loc--","***Sta 550:  UPS Upgrade for Sta1 & Hyper Fuel System\n--11/11/24 through 11/15/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 10/21/24 to 10/25/24.\n………………………………"]
["X24-293543","***","2024-11-11","2024-11-15","Project Change","2024-10-21","2024-10-25","Sta 550","500","2","480V Feed to 550-2 Valve","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,550,"--start_date--end_date------------model_loc--","***Sta 550:  480V Feed to 550-2 Valve\n--11/11/24 through 11/15/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 10/21/24 to 10/25/24.\n………………………………"]
["X24-138233","***","2024-11-11","2024-11-15","Project Change","2024-10-21","2024-10-25","Sta 550 Hamilton","500","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,550,"--start_date--end_date------------model_loc--","***Sta 550 Hamilton:  Annual ESD Test\n--11/11/24 through 11/15/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 10/21/24 to 10/25/24.\n………………………………"]
["X24-326894","***","2024-12-12","2024-12-14","Project Change","2024-09-30","2024-10-04","Sta 550","500","1","Unit 2A - Lube System Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,550.00199999999995,"--start_date--end_date------------model_loc--","***Sta 550:  Unit 2A - Lube System Replacement\n--12/12/24 through 12/14/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/30/24 to 10/4/24.\n………………………………"]
["X24-293537","***","2024-11-11","2024-11-15","Project Change","2024-09-16","2024-09-20","Sta 550","500","1","Unit 1B Safety Device Checks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,550.01700000000005,"--start_date--end_date------------model_loc--","***Sta 550:  Unit 1B Safety Device Checks\n--11/11/24 through 11/15/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/16/24 to 9/20/24.\n………………………………"]
["X24-920084",null,"2024-10-11","2024-10-11",null,null,null,"MLV 550-1 to MLV 546-1","500","1","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,550.1,null,"MLV 550-1 to MLV 546-1:  Maintenance Pig\n--10/11/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-920086",null,"2024-10-10","2024-10-10",null,null,null,"MLV 550-2 to MLV 546-2","500","1","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,550.20000000000005,null,"MLV 550-2 to MLV 546-2:  Maintenance Pig\n--10/10/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-920085",null,"2024-10-09","2024-10-09",null,null,null,"MLV 550-3 to MLV 549-3","500","1","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,550.29999999999995,null,"MLV 550-3 to MLV 549-3:  Maintenance Pig\n--10/9/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-140863","***","2024-09-09","2024-09-13","Completed",null,null,"Sta 555 Collinwood","500","1","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,555,"------","***Sta 555 Collinwood:  Annual ESD Test & Maintenance\n***Completed"]
["X24-327003",null,"2024-10-07","2024-10-25",null,null,null,"Sta 555","500","1","Unit 3A - Exhaust System","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,555.00300000000004,null,"Sta 555:  Unit 3A - Exhaust System\n--10/7/24 through 10/25/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-484573",null,"2024-09-03","2024-12-21",null,null,null,"Sta 555","500","1","Unit 4A - Foundation Regrout","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,555.00400000000002,null,"Sta 555:  Unit 4A - Foundation Regrout\n--9/3/24 through 12/21/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-916890","***","2024-09-16","2024-09-19","Completed",null,null,"MLV 555-1 to MLV 550-1","500","1","Pig Runs - Chemical Cleaning 9/16 - 9/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,555.1,"------","***MLV 555-1 to MLV 550-1:  Pig Runs - Chemical Cleaning 9/16 - 9/19\n***Completed"]
["X24-671158","***","2024-09-19","2024-09-19","Project Change","2024-09-26","2024-09-26","MLV 555-1 to MLV 550-1","500","1","Pig Runs - Caliper/IMU 9/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,555.1,"--start_date--end_date------mantenance_desc------model_loc--","***MLV 555-1 to MLV 550-1:  Pig Runs - Caliper/IMU 9/19\n--9/19/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/26/24.\n………………………………"]
["X24-671156","***","2024-09-24","2024-09-24","Completed",null,null,"MLV 555-1 to MLV 550-1","500","1","Pig Runs - Cleaning & Gauge 9/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,555.1,"------","***MLV 555-1 to MLV 550-1:  Pig Runs - Cleaning & Gauge 9/24\n***Completed"]
["X24-56044","***","2024-09-23","2024-09-23","Project Change","2024-10-01","2024-10-01","MLV 555-1 to MLV 550-1","500","1","Pig Runs - MFL-C 9/23","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,555.11,"--start_date--end_date------mantenance_desc------model_loc--","***MLV 555-1 to MLV 550-1:  Pig Runs - MFL-C 9/23\n--9/23/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 10/1/24.\n………………………………"]
["X24-56046","***","2024-09-25","2024-09-25","Project Change","2024-10-03","2024-10-03","MLV 555-1 to MLV 550-1","500","1","Pig Runs - EMAT 9/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,555.12,"--start_date--end_date------mantenance_desc------model_loc--","***MLV 555-1 to MLV 550-1:  Pig Runs - EMAT 9/25\n--9/25/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 10/3/24.\n………………………………"]
["X24-56052",null,"2024-12-03","2024-12-03",null,null,null,"MLV 555-2 to MLV 550-2","500","1","Pig Runs - Cleaning 12/3","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,555.20000000000005,null,"MLV 555-2 to MLV 550-2:  Pig Runs - Cleaning 12/3\n--12/3/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-56042",null,"2024-12-05","2024-12-05",null,null,null,"MLV 555-2 to MLV 550-2","500","1","Pig Runs - Caliper/IMU 12/5","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,555.21,null,"MLV 555-2 to MLV 550-2:  Pig Runs - Caliper/IMU 12/5\n--12/5/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-56053",null,"2024-12-09","2024-12-09",null,null,null,"MLV 555-2 to MLV 550-2","500","1","Pig Runs - MFL-C 12/9","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,555.21,null,"MLV 555-2 to MLV 550-2:  Pig Runs - MFL-C 12/9\n--12/9/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-56054",null,"2024-12-11","2024-12-11",null,null,null,"MLV 555-2 to MLV 550-2","500","1","Pig Runs - EMAT 12/11","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,555.22,null,"MLV 555-2 to MLV 550-2:  Pig Runs - EMAT 12/11\n--12/11/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-296276",null,"2024-09-26","2024-11-20",null,null,null,"MLV 560-1 to MLV 561-1","500","1","Class Change","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,560.1,null,"MLV 560-1 to MLV 561-1:  Class Change\n--9/26/24 through 11/20/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-296275",null,"2024-11-21","2024-12-10",null,null,null,"MLV 562-1 to MLV 563-1","500","1","Class Change","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,562.1,null,"MLV 562-1 to MLV 563-1:  Class Change\n--11/21/24 through 12/10/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-324515","***","2024-09-09","2024-09-12","Completed",null,null,"Sta 563","500","1","Annual and Quarterly Safety Checks","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,563,"------","***Sta 563:  Annual and Quarterly Safety Checks\n***Completed"]
["X24-888728",null,"2024-09-30","2024-10-04",null,null,null,"Sta 563","500","1","Inverter Change Out / Battery Plate Replacement","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,563,null,"Sta 563:  Inverter Change Out / Battery Plate Replacement\n--9/30/24 through 10/4/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-324518",null,"2024-11-04","2024-11-08",null,null,null,"Sta 563","500","1","Quarterly Safety Checks","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,563,null,"Sta 563:  Quarterly Safety Checks\n--11/4/24 through 11/8/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-74995",null,"2024-09-22","2024-09-30",null,null,null,"Sta 563","500","1","Unit 1A - Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,563.00099999999998,null,"Sta 563:  Unit 1A - Overhaul\n--9/22/24 through 9/30/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-296259","***","2024-06-26","2024-09-13","Completed",null,null,"MLV 564-1 to MLV 565-1","500","1","Class Change","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,564,"------","***MLV 564-1 to MLV 565-1:  Class Change\n***Completed"]
["X24-658715",null,"2024-10-14","2024-10-25",null,null,null,"MLV 564-2","500","2","Valve Repair","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,564.20000000000005,null,"MLV 564-2:  Valve Repair\n--10/14/24 through 10/25/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-626384",null,"2024-11-07","2024-11-07",null,null,null,"MLV 706-1 to MLV 700-1","100","0","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412819 LOUISMID/TGP CONVERSE CENTRAL: RIP\n410031 ETX GAS/TGP EAST TX PLANT DEHY PANO",706.1,null,"MLV 706-1 to MLV 700-1:  Pig Run - Maintenance\n--11/7/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n412819 LOUISMID/TGP CONVERSE CENTRAL: RIP\n410031 ETX GAS/TGP EAST TX PLANT DEHY PANO\n………………………………"]
["X24-255276","***","2024-10-21","2024-11-06","Project Change","2024-09-23","2024-10-04","MLV 821-1 to MLV 823-1","800","L","SCCDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420581 BDWKLAGT/TGP BECKWITH CREEK CALCASI\n412461 OLIPDPII/TGP DEHYDRATION CALCASIEU\n49446 CAM IPL/TGP BANKEN RD AT HWY 27 DE\n412737 CAM IPL/TGP DE QUINCY GAS STORAGE C",821.1,"--start_date--end_date------------model_loc--","***MLV 821-1 to MLV 823-1:  SCCDA\n--10/21/24 through 11/6/24:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n420581 BDWKLAGT/TGP BECKWITH CREEK CALCASI\n412461 OLIPDPII/TGP DEHYDRATION CALCASIEU\n49446 CAM IPL/TGP BANKEN RD AT HWY 27 DE\n412737 CAM IPL/TGP DE QUINCY GAS STORAGE C\n***\nDate Change, Previously scheduled 9/23/24 to 10/4/24.\n………………………………"]
["X24-973339",null,"2024-09-30","2024-10-07",null,null,null,"Sta 823","800","L","Filter Srubber Maintenance","This project will require a unit outages, which will limit throughput through the station and result in restrictions based on customer nominations.  The meters listed may experience pressure fluctuations.","SOP","Potential out of path restrictions may be at risk.","49446 CAM IPL/TGP BANKEN RD AT  HWY 27 DE",823,null,"Sta 823:  Filter Srubber Maintenance\n--9/30/24 through 10/7/24:  This project will require a unit outages, which will limit throughput through the station and result in restrictions based on customer nominations.  The meters listed may experience pressure fluctuations.  Potential out of path restrictions may be at risk.\n49446 CAM IPL/TGP BANKEN RD AT  HWY 27 DE\n………………………………"]
["X24-27837",null,"2024-10-02","2024-10-02",null,null,null,"Sta 823 to MLV 516","500","L","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","412398 JEFFSTOR/TGP JEFFERSON ISLAND IBERI\n420915 CEGS/TGP PORT IBERIA SALES IBERIA\n421056 ACADIAN/TGP INDIAN BAYOU: DIP 510B-\n412594 NAUTILUS/TGP GARDEN CITY ST MARY\n412684 ANR/TGP SHADYSIDE ST MARY",823.1,null,"Sta 823 to MLV 516:  Pig Run - Maintenance\n--10/2/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n412398 JEFFSTOR/TGP JEFFERSON ISLAND IBERI\n420915 CEGS/TGP PORT IBERIA SALES IBERIA\n421056 ACADIAN/TGP INDIAN BAYOU: DIP 510B-\n412594 NAUTILUS/TGP GARDEN CITY ST MARY\n412684 ANR/TGP SHADYSIDE ST MARY\n………………………………"]
["X24-27930","***","2024-11-06","2024-11-06","Project Change","2024-09-18","2024-09-18","STA 823 to STA 507K","500","L","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420493\tCOKINOS/TGP MALLETT FARM LA JEFFERS",823.1,"--start_date--end_date------------model_loc--","***STA 823 to STA 507K:  Pig Run - Maintenance\n--11/6/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n420493\tCOKINOS/TGP MALLETT FARM LA JEFFERS\n***\nDate Change, Previously scheduled 9/18/24.\n………………………………"]
["X24-27939",null,"2024-10-16","2024-10-16",null,null,null,"Sta 827 to Sta 823","800","L","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","421043 PINE PRA/TGP PINE PRAIRIE NORTH RAP\n412847 ACADIAN/TGP CHENEYVILLE RAPIDES\n412713 HUGHES E/TGP UDP BLACK STONE13 EVAN \n412844 TEXLA/TGP ROY MARTIN GATHERING: RIP\n420296 FORSTHIL/TGP FOREST HILL LA RAPIDES\n420530 GLNMORA/TGP GLENMORA LA EXCH RAPIDE\n421042 ELIZ NG/TGP EVANGELINE SALES EVANGE\n420629 ELIZ NG/TGP OAKDALE DETENTION SALES\n420687 ELIZ NG/TGP ALLEN PARISH PRISON SAL\n420406 ELIZ NG/TGP ELIZABETH LA EMERGENCY\n53483 AIRLIQAT/TGP TIMBERLANE BIOGAS REC",827.1,null,"Sta 827 to Sta 823:  Pig Run - Maintenance\n--10/16/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n421043 PINE PRA/TGP PINE PRAIRIE NORTH RAP\n412847 ACADIAN/TGP CHENEYVILLE RAPIDES\n412713 HUGHES E/TGP UDP BLACK STONE13 EVAN \n412844 TEXLA/TGP ROY MARTIN GATHERING: RIP\n420296 FORSTHIL/TGP FOREST HILL LA RAPIDES\n420530 GLNMORA/TGP GLENMORA LA EXCH RAPIDE\n421042 ELIZ NG/TGP EVANGELINE SALES EVANGE\n420629 ELIZ NG/TGP OAKDALE DETENTION SALES\n420687 ELIZ NG/TGP ALLEN PARISH PRISON SAL\n420406 ELIZ NG/TGP ELIZABETH LA EMERGENCY\n53483 AIRLIQAT/TGP TIMBERLANE BIOGAS REC\n………………………………"]
["X24-140937",null,"2024-10-23","2024-10-23",null,null,null,"Sta 834 Winnsboro","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,834,null,"Sta 834 Winnsboro:  Annual ESD Test\n--10/23/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-293337","***","2024-09-20","2024-09-25","Project Change","2024-09-09","2024-09-12","Sta 834","100","1","Unit 1A - Replace Lubrication System","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,834.00099999999998,"--start_date--end_date------------model_loc--","***Sta 834:  Unit 1A - Replace Lubrication System\n--9/20/24 through 9/25/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/9/24 to 9/12/24.\n………………………………"]
["X24-973179",null,"2024-11-18","2024-11-22",null,null,null,"Sta 834","800","1","Unit 1A - 12K Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,834.00099999999998,null,"Sta 834:  Unit 1A - 12K Engine Inspection\n--11/18/24 through 11/22/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-293339","***","2024-09-16","2024-09-19","Project Change","2024-09-13","2024-09-17","Sta 834",null,null,"Unit 2A- Replace Lubrication System","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,834.00199999999995,"--start_date--end_date------------model_loc--","***Sta 834:  Unit 2A- Replace Lubrication System\n--9/16/24 through 9/19/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/13/24 to 9/17/24.\n………………………………"]
["X24-640612",null,"2024-11-11","2024-11-15",null,null,null,"Sta 834","800","1","Unit 2A - 12K Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,834.00199999999995,null,"Sta 834:  Unit 2A - 12K Engine Inspection\n--11/11/24 through 11/15/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-860310",null,"2024-09-23","2024-09-27",null,null,null,"Sta 834","800","1","Unit 3A - 12K Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,834.00300000000004,null,"Sta 834:  Unit 3A - 12K Engine Inspection\n--9/23/24 through 9/27/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-860316",null,"2024-09-18","2024-09-24",null,null,null,"Sta 834","100","1","Unit 6A - 12K Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,834.00599999999997,null,"Sta 834:  Unit 6A - 12K Engine Inspection\n--9/18/24 through 9/24/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-860318",null,"2024-12-02","2024-12-06",null,null,null,"Sta 834","100","1","Unit 7A - 12K Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,834.00699999999995,null,"Sta 834:  Unit 7A - 12K Engine Inspection\n--12/2/24 through 12/6/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-255333",null,"2024-10-16","2024-10-16",null,null,null,"Sta 834 to Sta 827","800","L","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.","420755 ATMOS TL/TGP LASALLE PARISH NEBO SA\n420447 PELICANG/TGP HARRISONBURG LA CATAHO",834.11,null,"Sta 834 to Sta 827:  Maintenance Pig\n--10/16/24:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n420755 ATMOS TL/TGP LASALLE PARISH NEBO SA\n420447 PELICANG/TGP HARRISONBURG LA CATAHO\n………………………………"]
["X24-140946",null,"2024-09-30","2024-10-04",null,null,null,"Sta 836A Delhi","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,836,null,"Sta 836A Delhi:  Annual ESD Test\n--9/30/24 through 10/4/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-894582",null,"2024-09-30","2024-10-04",null,null,null,"Sta 836A","800","1","Unit 1A - Solar 8K Inspection & Air Filter Changeout","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,836.00099999999998,null,"Sta 836A:  Unit 1A - Solar 8K Inspection & Air Filter Changeout\n--9/30/24 through 10/4/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-140939","***","2024-09-12","2024-09-12","Completed",null,null,"Sta 838 Transylvania","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,838,"------","***Sta 838 Transylvania:  Annual ESD Test\n***Completed"]
["X24-138240",null,"2024-10-08","2024-10-08",null,null,null,"Sta 851 New Albany","500","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,851,null,"Sta 851 New Albany:  Annual ESD Test\n--10/8/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-293581","***","2024-12-17","2024-12-18","Project Change","2024-10-08","2024-10-09","Sta 851","800","1","UPS Upgrade for STA1","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,851,"--start_date--end_date------------model_loc--","***Sta 851:  UPS Upgrade for STA1\n--12/17/24 through 12/18/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 10/8/24 to 10/9/24.\n………………………………"]
["X24-282537",null,"2024-10-04","2024-10-31",null,null,null,"MLV 854-1 to MLV 856-1","800","1","Make Piggable","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,853.1,null,"MLV 854-1 to MLV 856-1:  Make Piggable\n--10/4/24 through 10/31/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X23-841261",null,"2023-08-18","2025-03-02",null,null,null,"Sta 860","800","1","Force Majeure","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,860,null,"Sta 860:  Force Majeure\n--8/18/23 through 3/2/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-501214","***","2024-09-16","2024-09-17","Completed",null,null,"Sta 860","800",null,"Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,860,"------","***Sta 860:  Annual ESD Test\n***Completed"]
["X24-386317",null,"2024-10-14","2024-10-25",null,null,null,"Sta 860","800","1","HP Replacement","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,860,null,"Sta 860:  HP Replacement\n--10/14/24 through 10/25/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-640564","***","2024-06-17","2024-11-30","Project Change",null,"2024-09-30","Sta 860","800","1","Unit 1A - After Cooler","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,860.00099999999998,"----end_date------------model_loc--","***Sta 860:  Unit 1A - After Cooler\n--6/17/24 through 11/30/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 6/17/24 to 9/30/24.\n………………………………"]
["X24-640558","***","2024-06-17","2024-10-31","Project Change",null,"2024-09-13","Sta 860","800","1","Unit 5A - Crank-end Head Gasket","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,860.005,"----end_date------------model_loc--","***Sta 860:  Unit 5A - Crank-end Head Gasket\n--6/17/24 through 10/31/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 6/17/24 to 9/13/24.\n………………………………"]
["X24-296274",null,"2024-12-11","2024-12-23",null,null,null,"MLV 863-1 to MLV 864-1","800","1","Class Change","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,863.1,null,"MLV 863-1 to MLV 864-1:  Class Change\n--12/11/24 through 12/23/24:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-871263","***","2024-09-12","2024-09-12","Completed",null,null,"Sta 871","800","2","Unit 2A - Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,871.00199999999995,"------","***Sta 871:  Unit 2A - Engine Inspection\n***Completed"]
["X24-782061",null,"2024-07-22","2024-10-10",null,null,null,"Sta 871","800","2","Unit 3A - Power Side Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,871.00300000000004,null,"Sta 871:  Unit 3A - Power Side Overhaul\n--7/22/24 through 10/10/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-867849",null,"2024-10-22","2024-10-22",null,null,null,"Sta 871A Dry Creek","100","2","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.",null,871.5,null,"Sta 871A Dry Creek:  Annual ESD Test\n--10/22/24:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-976513",null,"2024-10-21","2024-11-22",null,null,null,"MLV 872-2 to MLV 873-2","800","2","Anomaly Remediation","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,872.2,null,"MLV 872-2 to MLV 873-2:  Anomaly Remediation\n--10/21/24 through 11/22/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-839376","***","2024-09-17","2024-09-18","Completed",null,null,"Sta 875","800","3","Unit 1A - Install BAM 2.0 Material","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,875.00099999999998,"------","***Sta 875:  Unit 1A - Install BAM 2.0 Material\n***Completed"]
["X24-920145",null,"2024-11-19","2024-11-20",null,null,null,"Sta 875","100","2","Unit 1A - 4k Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,875.00099999999998,null,"Sta 875:  Unit 1A - 4k Inspection\n--11/19/24 through 11/20/24:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]

{"sheet":"Sheet2","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}

{"sheet":"Sheet3","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}