{"text_format":"1","workbook":"xlsx","n_sheets":4,"sheets":["Closed","Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":8,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Closed","index":0,"n_rows":37,"n_cols":22,"rows_kept":37,"cut":false,"hidden":true,"merged":[[1,3,1,15],[2,3,2,15],[3,3,3,15]]}
[null,null,null,"Updated ","2016"]
[null,null,null,"Tennessee Gas Pipeline 2015 Pipeline Outage and Maintenance Summary"]
[null,null,null,"This is a summary of the current status of all TGP Winter 2014-2015 Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  Additionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
[null,null,null,"*** Indicates revision"]
["Date Change","Project New/Completed/Closed","Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","Location","Leg","Zone","Maintenance Activity","Anticipated Impact","Potential Restriction Level","TOS Potential Restrictions","Meter(s) in Impacted Area","Customer Notifications","Loc","Email Text","Posting Text","Completion Text"]
[{"$f":"IF(AND(H6<>\"\",I6<>\"\"), \"Date change. Previously scheduled \" & TEXT(H6,\"m/d/y;@\") &IF(H6=I6,\"\",\" to \" & TEXT(I6,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed",null,{"$f":"IF(G6<>\"\",\"***\",\"\")","v":"***"},"2015-01-11","2016-01-11",{"$f":"IF(AND(A6=\"\",B6=\"\"),\"\",IF(B6=\"\",A6,B6))","v":"Project Completed"},null,null,"MS #412494 DCP Warren","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412494 DCP Warren",401,{"$f":"\"(\"&C6&\") \"&J6&\":  \"&M6&IF(AND(E6=\"\",F6=\"\"),\"\",\" (\")&IF(E6=\"\",\"\",\"\"&TEXT(E6,\"m/d/y;@\"))&IF(OR(F6=E6,E6=\"\",F6=\"\"),\"\",\" to \")&IF(OR(F6=\"\",F6=E6),\"\",TEXT(F6,\"m/d/y;@\"))&IF(AND(E6=\"\",F6=\"\"),\"\",\")\")","v":"() MS #412494 DCP Warren:  Meter Station (1/11/15 to 1/11/16)"},{"$f":"D6&J6&\":  \"&M6&IF(AND(E6=\"\",F6=\"\"),\"\",\"\n\")&IF(E6=\"\",\"\",\"--\"&TEXT(E6,\"m/d/y;@\"))&IF(OR(F6=E6,E6=\"\",F6=\"\"),\"\",\" through \")&IF(OR(F6=\"\",F6=E6),\"\",TEXT(F6,\"m/d/y;@\"))&IF(AND(E6=\"\",F6=\"\"),\"\",\":  \")&N6&\"  \"&P6&IF(Q6=\"\",\"\",\"\n\"&Q6)&IF(G6=\"\",\"\",\"\n***\")&G6&\"\n………………………………\"","v":"***MS #412494 DCP Warren:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412494 DCP Warren\n***Project Completed\n………………………………"},{"$f":"D6&J6&\":  \"&M6&IF(G6=\"\",\"\",\"\n***\")&G6&IF(Q6=\"\",\"\",\"\nThe following meters are available for nominations:\n\")&Q6&\"\n………………………………\"","v":"***MS #412494 DCP Warren:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412494 DCP Warren\n………………………………"}]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412400 King Ranch","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412400 King Ranch",402.1,"() MS #412400 King Ranch:  Meter Station (1/11/15 to 1/11/16)","***MS #412400 King Ranch:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412400 King Ranch\n***Project Completed\n………………………………","***MS #412400 King Ranch:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412400 King Ranch\n………………………………"]
["","Project Completed",null,"***","2015-01-12","2016-01-12","Project Completed",null,null,"MS #410539 Duvak Gas Gathering","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410539 Duvak Gas Gathering",402.1,"() MS #410539 Duvak Gas Gathering:  Meter Station (1/12/15 to 1/12/16)","***MS #410539 Duvak Gas Gathering:  Meter Station\n--1/12/15 through 1/12/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410539 Duvak Gas Gathering\n***Project Completed\n………………………………","***MS #410539 Duvak Gas Gathering:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n410539 Duvak Gas Gathering\n………………………………"]
["","Project Completed",null,"***","2015-01-13","2016-01-13","Project Completed",null,null,"MS #412356 DCP LaGloria","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412356 DCP LaGloria",403.1,"() MS #412356 DCP LaGloria:  Meter Station (1/13/15 to 1/13/16)","***MS #412356 DCP LaGloria:  Meter Station\n--1/13/15 through 1/13/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412356 DCP LaGloria\n***Project Completed\n………………………………","***MS #412356 DCP LaGloria:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412356 DCP LaGloria\n………………………………"]
["","Project Completed",null,"***","2015-01-13","2016-01-13","Project Completed",null,null,"MS #410173 Enterprise LaReforma","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410173 Enterprise LaReforma",406.1,"() MS #410173 Enterprise LaReforma:  Meter Station (1/13/15 to 1/13/16)","***MS #410173 Enterprise LaReforma:  Meter Station\n--1/13/15 through 1/13/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410173 Enterprise LaReforma\n***Project Completed\n………………………………","***MS #410173 Enterprise LaReforma:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n410173 Enterprise LaReforma\n………………………………"]
["","Project Completed",null,"***","2015-01-12","2016-01-12","Project Completed",null,null,"MS #411903 Enterprise El Benito","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","411903 Enterprise El Benito",407.1,"() MS #411903 Enterprise El Benito:  Meter Station (1/12/15 to 1/12/16)","***MS #411903 Enterprise El Benito:  Meter Station\n--1/12/15 through 1/12/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n411903 Enterprise El Benito\n***Project Completed\n………………………………","***MS #411903 Enterprise El Benito:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n411903 Enterprise El Benito\n………………………………"]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412088 Enterprise Sullivan","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412088 Enterprise Sullivan",407.1,"() MS #412088 Enterprise Sullivan:  Meter Station (1/11/15 to 1/11/16)","***MS #412088 Enterprise Sullivan:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412088 Enterprise Sullivan\n***Project Completed\n………………………………","***MS #412088 Enterprise Sullivan:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412088 Enterprise Sullivan\n………………………………"]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412683 HESCO","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412683 HESCO",408.1,"() MS #412683 HESCO:  Meter Station (1/11/15 to 1/11/16)","***MS #412683 HESCO:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412683 HESCO\n***Project Completed\n………………………………","***MS #412683 HESCO:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412683 HESCO\n………………………………"]
[{"$f":"IF(AND(H14<>\"\",I14<>\"\"), \"Date change. Previously scheduled \" & TEXT(H14,\"m/d/y;@\") &IF(H14=I14,\"\",\" to \" & TEXT(I14,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X16-36843",{"$f":"IF(G14<>\"\",\"***\",\"\")","v":"***"},"2016-01-27","2016-01-27","Project Completed",null,null,"Sta. 237",200,5,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,237,"(X16-36843) Sta. 237:  Unit  Maintenance (1/27/16)","***Sta. 237:  Unit  Maintenance\n--1/27/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Sta. 237:  Unit  Maintenance\n***Project Completed\n………………………………"]
[{"$f":"IF(AND(H15<>\"\",I15<>\"\"), \"Date change. Previously scheduled \" & TEXT(H15,\"m/d/y;@\") &IF(H15=I15,\"\",\" to \" & TEXT(I15,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X14-1478563",{"$f":"IF(G15<>\"\",\"***\",\"\")","v":"***"},"2015-11-16","2016-02-12","Project Completed",null,null,"MLV 32-1D to 33-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,32.200000000000003,"(X14-1478563) MLV 32-1D to 33-1:  Hydrotest (11/16/15 to 2/12/16)","***MLV 32-1D to 33-1:  Hydrotest\n--11/16/15 through 2/12/16:  This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***MLV 32-1D to 33-1:  Hydrotest\n***Project Completed\n………………………………"]
[null,"Project Completed","X16-16074",null,"2016-01-18","2016-01-28","Project Completed",null,null,"Station 550","500","1","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,550,"(X16-16074) Station 550:  Station Maintenance (1/18/16 to 1/28/16)","Station 550:  Station Maintenance\n--1/18/16 through 1/28/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","Station 550:  Station Maintenance\n***Project Completed\n………………………………"]
[{"$f":"IF(AND(H17<>\"\",I17<>\"\"), \"Date change. Previously scheduled \" & TEXT(H17,\"m/d/y;@\") &IF(H17=I17,\"\",\" to \" & TEXT(I17,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X16-46202",{"$f":"IF(G17<>\"\",\"***\",\"\")","v":"***"},"2016-02-01","2016-02-07","Project Completed",null,null,"Station 9","100","0","Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.",null,9,"(X16-46202) Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items) (2/1/16 to 2/7/16)","***Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)\n--2/1/16 through 2/7/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\n***Project Completed\n………………………………","***Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)\n***Project Completed\n………………………………"]
["","Project Completed","X15-925633","***","2016-02-09","2016-02-11","Project Completed",null,null,"Sta. 266A",200,6,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,266,"(X15-925633) Sta. 266A:  Unit  Maintenance (2/9/16 to 2/11/16)","***Sta. 266A:  Unit  Maintenance\n--2/9/16 through 2/11/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Sta. 266A:  Unit  Maintenance\n***Project Completed\n………………………………"]
["","Project Completed","X15-929733","***","2016-01-27","2016-02-10","Project Completed",null,null,"MLV 834-1 to 838-1",800,5,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",834.1,"(X15-929733) MLV 834-1 to 838-1:  ILI/Cleaning Pig (1/27/16 to 2/10/16)","***MLV 834-1 to 838-1:  ILI/Cleaning Pig\n--1/27/16 through 2/10/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 834-1 to 838-1:  ILI/Cleaning Pig\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X14-1562506","***","2015-11-02","2016-02-19","Project Completed",null,null,"MLV 5-1 to 6-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410063 ROCHE DEHYDRATION             \n",5.0999999999999996,"(X14-1562506) MLV 5-1 to 6-1:  Hydrotest (11/2/15 to 2/19/16)","***MLV 5-1 to 6-1:  Hydrotest\n--11/2/15 through 2/19/16:  This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410063 ROCHE DEHYDRATION             \n\n***Project Completed\n………………………………","***MLV 5-1 to 6-1:  Hydrotest\n***Project Completed\nThe following meters are available for nominations:\n410063 ROCHE DEHYDRATION             \n\n………………………………"]
["","Project Completed","X14-1562506","***","2015-11-02","2016-02-19","Project Completed",null,null,"MLV 7-1 to 9-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","\n412490 Charro\n421083 Eagle Ford Field Service",5.0999999999999996,"(X14-1562506) MLV 7-1 to 9-1:  Hydrotest (11/2/15 to 2/19/16)","***MLV 7-1 to 9-1:  Hydrotest\n--11/2/15 through 2/19/16:  This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n\n412490 Charro\n421083 Eagle Ford Field Service\n***Project Completed\n………………………………","***MLV 7-1 to 9-1:  Hydrotest\n***Project Completed\nThe following meters are available for nominations:\n\n412490 Charro\n421083 Eagle Ford Field Service\n………………………………"]
["Date change. Previously scheduled 2/18/16 to 2/20/16.","Project Completed","X15-882289","***","2016-02-22","2016-02-24","Project Completed","2016-02-18","2016-02-20","MLV 24-2 to 25-2S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.2,"(X15-882289) MLV 24-2 to 25-2S:  Anomaly Remediation (2/22/16 to 2/24/16)","***MLV 24-2 to 25-2S:  Anomaly Remediation\n--2/22/16 through 2/24/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 24-2 to 25-2S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-925630","***","2016-02-23","2016-02-23","Project Completed",null,null,"WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B)",200,"L","ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,265.10000000000002,"(X15-925630) WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig (2/23/16)","***WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig\n--2/23/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig\n***Project Completed\n………………………………"]
["","Project Completed","X16-23748","***","2016-02-15","2016-02-18","Project Completed",null,null,"MLV 530-3 to 532-3",500,"L","ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,530.29999999999995,"(X16-23748) MLV 530-3 to 532-3:  ILI/Cleaning Pig (2/15/16 to 2/18/16)","***MLV 530-3 to 532-3:  ILI/Cleaning Pig\n--2/15/16 through 2/18/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***MLV 530-3 to 532-3:  ILI/Cleaning Pig\n***Project Completed\n………………………………"]
["","Project Canceled","X16-98720","***","2016-03-06","2016-03-06","Project Canceled",null,null,"Sta. 1",100,0,"Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,1,"(X16-98720) Sta. 1:  Station Maintenance (3/6/16)","***Sta. 1:  Station Maintenance\n--3/6/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Canceled\n………………………………","***Sta. 1:  Station Maintenance\n***Project Canceled\n………………………………"]
["","Project Completed","X14-1562513\nX14-1540661","***","2015-07-01","2016-03-04","Project Completed",null,null,"Station 32","100","0","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,32,"(X14-1562513\nX14-1540661) Station 32:  Station Maintenance (7/1/15 to 3/4/16)","***Station 32:  Station Maintenance\n--7/1/15 through 3/4/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Station 32:  Station Maintenance\n***Project Completed\n………………………………"]
["","Project Canceled","X15-926822","***","2016-06-06","2016-06-11","Project Canceled",null,null,"BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1)",300,6,"Pipe Inspection","This project involves inspecting multiple sites.  We do not anticipate having to do any repairs, however if a repair is needed  there is a potential that the pipe  may require replacement which will require isolation of the pipe.  This may limit throughput and will result in restrictions based on customer nominations.  Customers may experience pressure fluctuations during this timeframe.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",343.1,"(X15-926822) BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection (6/6/16 to 6/11/16)","***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection\n--6/6/16 through 6/11/16:  This project involves inspecting multiple sites.  We do not anticipate having to do any repairs, however if a repair is needed  there is a potential that the pipe  may require replacement which will require isolation of the pipe.  This may limit throughput and will result in restrictions based on customer nominations.  Customers may experience pressure fluctuations during this timeframe.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928271","***","TBD","TBD","Project Canceled",null,null,"MLV 555-1 to 550-1",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.1,"(X15-928271) MLV 555-1 to 550-1:  ILI/Cleaning Pig (TBD)","***MLV 555-1 to 550-1:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-1 to 550-1:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928272","***","TBD","TBD","Project Canceled",null,null,"MLV 555-2 to 550-2",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.20000000000005,"(X15-928272) MLV 555-2 to 550-2:  ILI/Cleaning Pig (TBD)","***MLV 555-2 to 550-2:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-2 to 550-2:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928273","***","TBD","TBD","Project Canceled",null,null,"MLV 555-3 to 552-3",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.29999999999995,"(X15-928273) MLV 555-3 to 552-3:  ILI/Cleaning Pig (TBD)","***MLV 555-3 to 552-3:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-3 to 552-3:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-882281","***","2016-02-24","2016-03-03","Project Completed",null,null,"24-1A to 25-1S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.1,"(X15-882281) 24-1A to 25-1S:  Anomaly Remediation (2/24/16 to 3/3/16)","***24-1A to 25-1S:  Anomaly Remediation\n--2/24/16 through 3/3/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***24-1A to 25-1S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-882291","***","2016-03-03","2016-03-04","Project Completed",null,null,"MLV 24-3 to 25-3S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.3,"(X15-882291) MLV 24-3 to 25-3S:  Anomaly Remediation (3/3/16 to 3/4/16)","***MLV 24-3 to 25-3S:  Anomaly Remediation\n--3/3/16 through 3/4/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 24-3 to 25-3S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X14-1178175","***","2015-06-15","2016-03-31","Project Completed",null,null,"Station 63","100","1","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,63,"(X14-1178175) Station 63:  Station Maintenance (6/15/15 to 3/31/16)","***Station 63:  Station Maintenance\n--6/15/15 through 3/31/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Station 63:  Station Maintenance\n***Project Completed\n………………………………"]
["","Project Cancelled","X15-913224","***","2016-04-16","2016-05-21","Project Cancelled",null,null,"MLV 109-2",100,2,"Pipe Replacement","This project will require taking the pipeline section out of service.   This will limit throughput and will result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",109.2,"(X15-913224) MLV 109-2:  Pipe Replacement (4/16/16 to 5/21/16)","***MLV 109-2:  Pipe Replacement\n--4/16/16 through 5/21/16:  This project will require taking the pipeline section out of service.   This will limit throughput and will result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Cancelled\n………………………………","***MLV 109-2:  Pipe Replacement\n***Project Cancelled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-926830","***","2016-03-07","2016-03-11","Project Completed",null,null,"MLV 400-1 to 408-1",100,0,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.","To Be Determined",400.1,"(X15-926830) MLV 400-1 to 408-1:  ILI/Cleaning Pig (3/7/16 to 3/11/16)","***MLV 400-1 to 408-1:  ILI/Cleaning Pig\n--3/7/16 through 3/11/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 400-1 to 408-1:  ILI/Cleaning Pig\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Cancelled","X16-143836","***","2016-03-28","2016-04-04","Project Cancelled",null,null,"Sta. 409",100,0,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.",null,409,"(X16-143836) Sta. 409:  Unit  Maintenance (3/28/16 to 4/4/16)","***Sta. 409:  Unit  Maintenance\n--3/28/16 through 4/4/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\n***Project Cancelled\n………………………………","***Sta. 409:  Unit  Maintenance\n***Project Cancelled\n………………………………"]
["","Project Cancelled","X15-929680","***","2016-04-18","2016-04-27","Project Cancelled",null,null,"SABINE - KINDER LINE to 822-1",800,"L","Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",822.1,"(X15-929680) SABINE - KINDER LINE to 822-1:  Anomaly Remediation (4/18/16 to 4/27/16)","***SABINE - KINDER LINE to 822-1:  Anomaly Remediation\n--4/18/16 through 4/27/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Cancelled\n………………………………","***SABINE - KINDER LINE to 822-1:  Anomaly Remediation\n***Project Cancelled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]

{"sheet":"Sheet1","index":1,"n_rows":307,"n_cols":24,"rows_kept":307,"cut":false,"hidden":false,"merged":[[2,0,2,14]]}
["Updated ","2025-01-30"]
["Tennessee Gas Pipeline 2025 Pipeline Outage and Maintenance Summary"]
["This is a summary of the current status of TGP Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  \nAdditionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
["*** Indicates revision"]
["Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","Location","Leg","Zone","Maintenance Activity","Anticipated Impact","Potential Restriction Level","TOS Potential Restrictions","Meter(s) in Impacted Area","Loc",null,null,null,null,null,null,null,"\\\\houCORP\\TRANS\\TRANSERVICES\\OPPLAN\\COMMON\\Outages\\Outage_DB\\TGP\\Files"]
["X25-82097",null,"2025-07-21","2025-08-08",null,null,null,"MLV 4-3 to MLV 9-3","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,4.3,null,"MLV 4-3 to MLV 9-3:  Anomaly Remediation\n--7/21/25 through 8/8/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-82116",null,"2025-02-25","2025-02-25",null,null,null,"MLV 13-3 to MLV 17-3","100","0","Pig Run - Cleaning 2/25/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,13.3,null,"MLV 13-3 to MLV 17-3:  Pig Run - Cleaning 2/25/25\n--2/25/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-82089",null,"2025-02-27","2025-02-27",null,null,null,"MLV 13-3 to MLV 17-3","100","0","Pig Run - MFL-A 2/27/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,13.31,null,"MLV 13-3 to MLV 17-3:  Pig Run - MFL-A 2/27/25\n--2/27/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-82092",null,"2025-03-04","2025-03-04",null,null,null,"MLV 13-3 to MLV 17-3","100","0","Pig Run - EMAT 3/4/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,13.32,null,"MLV 13-3 to MLV 17-3:  Pig Run - EMAT 3/4/25\n--3/4/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-84445",null,"2025-01-22","2025-03-30",null,null,null,"MLV 17-3 to MLV 18-3","100","0","Emergent Repair","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,16.3,null,"MLV 17-3 to MLV 18-3:  Emergent Repair\n--1/22/25 through 3/30/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-82095",null,"2025-05-20","2025-06-07",null,null,null,"MLV 17-1D to MLV 20-1A","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,17.100000000000001,null,"MLV 17-1D to MLV 20-1A:  Anomaly Remediation\n--5/20/25 through 6/7/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-82096",null,"2025-06-30","2025-07-04",null,null,null,"MLV 17-2D to MLV 20-2A","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,17.2,null,"MLV 17-2D to MLV 20-2A:  Anomaly Remediation\n--6/30/25 through 7/4/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-82094",null,"2025-04-29","2025-05-17",null,null,null,"MLV 20-1A to MLV 24-1A","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,20.100000000000001,null,"MLV 20-1A to MLV 24-1A:  Anomaly Remediation\n--4/29/25 through 5/17/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-82099",null,"2025-08-16","2025-08-26",null,null,null,"MLV 20-1, MLV-20-2, MLV-20-3 Kicker Lines","100","0","ECDA Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,20.100000000000001,null,"MLV 20-1, MLV-20-2, MLV-20-3 Kicker Lines:  ECDA Remediation\n--8/16/25 through 8/26/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-671169",null,"2025-03-10","2025-03-24",null,null,null,"MLV 25-1 to MLV 26-1 Relocation","100","0","Highway 105 Widening","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,25.1,null,"MLV 25-1 to MLV 26-1 Relocation:  Highway 105 Widening\n--3/10/25 through 3/24/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-671172",null,"2025-03-10","2025-03-24",null,null,null,"MLV 25A-101 to MLV 25A-102 Relocation","100","0","Highway 105 Widening","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","411559 HEC/TGP UDP 1 CENTRAL COAL & COKE D",25.11,null,"MLV 25A-101 to MLV 25A-102 Relocation:  Highway 105 Widening\n--3/10/25 through 3/24/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n411559 HEC/TGP UDP 1 CENTRAL COAL & COKE D\n………………………………"]
["X22-621358","***","2025-10-06","2025-11-02","Project Change","2025-03-10","2025-04-06","MLV 26-1 Relocation","100","0","Highway 59 Widening","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,26.1,"--start_date--end_date------------model_loc--","***MLV 26-1 Relocation:  Highway 59 Widening\n--10/6/25 through 11/2/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 3/10/25 to 4/6/25.\n………………………………"]
["X24-1148994","***","2025-12-15","2025-12-20","Project Change","2025-05-19","2025-05-24","MLV 26-1 to MLV 27-1","100","0","Install Road Casing","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,26.1,"--start_date--end_date------------model_loc--","***MLV 26-1 to MLV 27-1:  Install Road Casing\n--12/15/25 through 12/20/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 5/19/25 to 5/24/25.\n………………………………"]
["X22-815863","***","2025-11-03","2025-11-30","Project Change","2025-04-07","2025-05-04","MLV 26-2 Relocation","100","0","Highway 59 Widening","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,26.2,"--start_date--end_date------------model_loc--","***MLV 26-2 Relocation:  Highway 59 Widening\n--11/3/25 through 11/30/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 4/7/25 to 5/4/25.\n………………………………"]
["X22-815864","***","2025-12-01","2025-12-28","Project Change","2025-05-05","2025-06-01","MLV 26-3 Relocation","100","0","Highway 59 Widening","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","400448 CICO/TGP MERCY GU 1 LIBERTY",26.3,"--start_date--end_date------------model_loc--","***MLV 26-3 Relocation:  Highway 59 Widening\n--12/1/25 through 12/28/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n400448 CICO/TGP MERCY GU 1 LIBERTY\n***\nDate Change, Previously scheduled 5/5/25 to 6/1/25.\n………………………………"]
["X24-1230207","***","2025-01-25","2025-01-25","Completed",null,null,"MLV 32-1D to MLV 36-1TXR","100","0","Pig Run - Rosen AFD 1/25/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,32.04,"------","***MLV 32-1D to MLV 36-1TXR:  Pig Run - Rosen AFD 1/25/25\n***Completed"]
["X24-1230208","***","2025-01-27","2025-01-27","Completed",null,null,"MLV 32-1D to MLV 36-1TXR","100","0","Pig Run - Rosen EMAT 1/27/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,32.049999999999997,"------","***MLV 32-1D to MLV 36-1TXR:  Pig Run - Rosen EMAT 1/27/25\n***Completed"]
["X24-1230209","***","2025-01-29","2025-01-29","Completed",null,null,"MLV 32-1D to MLV 36-1TXR","100","0","Pig Run - Pipecare EMAT 1/29/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,32.06,"------","***MLV 32-1D to MLV 36-1TXR:  Pig Run - Pipecare EMAT 1/29/25\n***Completed"]
["X24-1257780",null,"2025-07-21","2025-07-24",null,null,null,"Sta 40","100","1","Carthage Check Meter","This project will require operating at controlled flow rates. Customers \r\nmay experience pressure fluctuations.  The meters listed may be constrained \r\nduring the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","55661\tKHFS/TGP SOUTH COUCHATTA RECEIPT DE\n410031\tETX GAS/TGP EAST TX PLANT DEHY PANO\n411330\tTEXLA/TGP CHEMARD LAKE DEHY DE SOTO\n412610\tMAGNUMPL/TGP WEST MANSFIELD DE SOTO\n412725\tET G&P/TGP  DE SOTO\n412759\tDIV PROD/TGP BURFORD GATHERING: RIP\n412764\tENT GATH/TGP UDP STATE LINE PROCESS\n412807\tET G&P/TGP LOGANSPORT B: RIP 704H 1\n412819\tLOUISMID/TGP CONVERSE CENTRAL: RIP \n420723\tETP/TGP CARTHAGE GAS UNIT 13 PANOLA",40,null,"Sta 40:  Carthage Check Meter\n--7/21/25 through 7/24/25:  This project will require operating at controlled flow rates. Customers \r\nmay experience pressure fluctuations.  The meters listed may be constrained \r\nduring the project.  Potential secondary restrictions at the meter(s) may be at risk.\n55661\tKHFS/TGP SOUTH COUCHATTA RECEIPT DE\n410031\tETX GAS/TGP EAST TX PLANT DEHY PANO\n411330\tTEXLA/TGP CHEMARD LAKE DEHY DE SOTO\n412610\tMAGNUMPL/TGP WEST MANSFIELD DE SOTO\n412725\tET G&P/TGP  DE SOTO\n412759\tDIV PROD/TGP BURFORD GATHERING: RIP\n412764\tENT GATH/TGP UDP STATE LINE PROCESS\n412807\tET G&P/TGP LOGANSPORT B: RIP 704H 1\n412819\tLOUISMID/TGP CONVERSE CENTRAL: RIP \n420723\tETP/TGP CARTHAGE GAS UNIT 13 PANOLA\n………………………………"]
["X24-1257774",null,"2025-08-01","2025-08-30",null,null,null,"Sta 40","100","1","HP Replacement","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations","SOP","Potential out of path restrictions may be at risk.",null,40.000100000000003,null,"Sta 40:  HP Replacement\n--8/1/25 through 8/30/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-86674","***","2025-02-03","2025-02-04","Added",null,null,"Sta 40","100","1","Unit 2C - Chock Inspections","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,40.033999999999999,"------","***Sta 40:  Unit 2C - Chock Inspections\n--2/3/25 through 2/4/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-38375","***","2025-02-11","2025-02-12","Project Change","2025-01-28","2025-01-29","MLV 40-2SH, 40-3SH, 40-2S and 40-3S","100","1","Replace Actuators","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,40.200000000000003,"--start_date--end_date------------model_loc--","***MLV 40-2SH, 40-3SH, 40-2S and 40-3S:  Replace Actuators\n--2/11/25 through 2/12/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 1/28/25 to 1/29/25.\n………………………………"]
["X24-1151836",null,"2025-04-07","2025-04-11",null,null,null,"MLV 40-3 to MLV 47-3","100","0","Pig Run - Chem Cleaning 4/7/25 to 4/11/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,40.299999999999997,null,"MLV 40-3 to MLV 47-3:  Pig Run - Chem Cleaning 4/7/25 to 4/11/25\n--4/7/25 through 4/11/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1151838",null,"2025-04-15","2025-04-15",null,null,null,"MLV 40-3 to MLV 47-3","100","1","Pig Run - MFL-C 4/15/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,40.31,null,"MLV 40-3 to MLV 47-3:  Pig Run - MFL-C 4/15/25\n--4/15/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1151840",null,"2025-04-17","2025-04-17",null,null,null,"MLV 40-3 to MLV 47-3","100","0","Pig Run - EMAT 4/17/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,40.32,null,"MLV 40-3 to MLV 47-3:  Pig Run - EMAT 4/17/25\n--4/17/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-25861",null,"2025-09-10","2025-09-10",null,null,null,"Sta 47","100","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,47,null,"Sta 47:  Annual ESD Test\n--9/10/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-25860",null,"2025-06-02","2025-06-06",null,null,null,"Sta 47","100","1","Scrubber Filter Separator Cleaning & Inspection","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,47.000100000000003,null,"Sta 47:  Scrubber Filter Separator Cleaning & Inspection\n--6/2/25 through 6/6/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-785011","***","2024-07-23","2025-01-24","Completed",null,null,"Sta 47","100","1","Unit 3C - Engine Deferred Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,47.033999999999999,"------","***Sta 47:  Unit 3C - Engine Deferred Maintenance\n***Completed"]
["X25-25859","***","2025-04-14","2025-04-18","Project Change",null,null,"Sta 47","100","1","Unit 1E - Annual Turbine Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,47.064999999999998,"----------mantenance_desc------model_loc--","***Sta 47:  Unit 1E - Annual Turbine Maintenance\n--4/14/25 through 4/18/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Project Change\n………………………………"]
["X25-35040",null,"2025-01-06","2025-10-31",null,null,null,"MLV 47-1AT to MLV 49-1","100","1","Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,47.1,null,"MLV 47-1AT to MLV 49-1:  Anomaly Remediation\n--1/6/25 through 10/31/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-82100","***","2025-06-02","2025-11-30","Added",null,null,"MLV 47-1A to MLV 48-1","100","1","Class Change","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,47.1,"------","***MLV 47-1A to MLV 48-1:  Class Change\n--6/2/25 through 11/30/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-1176600",null,"2025-04-15","2025-04-15",null,null,null,"MLV 47-3D TO MLV 53-3","100","1","Pig Runs - Cleaning / Gauge 4/15/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,47.3,null,"MLV 47-3D TO MLV 53-3:  Pig Runs - Cleaning / Gauge 4/15/25\n--4/15/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1176711",null,"2025-04-17","2025-04-17",null,null,null,"MLV 47-3D TO MLV 53-3","100","1","Pig Runs - MDS 4/17/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,47.31,null,"MLV 47-3D TO MLV 53-3:  Pig Runs - MDS 4/17/25\n--4/17/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1398725",null,"2025-03-04","2025-03-05",null,null,null,"Sta 54","100","1","Replace Insulator Bushing on Siemens Transformer","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,54,null,"Sta 54:  Replace Insulator Bushing on Siemens Transformer\n--3/4/25 through 3/5/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368171",null,"2025-09-08","2025-09-11",null,null,null,"Sta 54 Greenville","100","1","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,54,null,"Sta 54 Greenville:  Annual ESD Test & Maintenance\n--9/8/25 through 9/11/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-86678","***","2025-11-04","2025-11-04","Added",null,null,"MLV 54-1D TO MLV 63-1S","100","1","Pig Runs - Cleaning / Gauge 11/4/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,54.1,"------","***MLV 54-1D TO MLV 63-1S:  Pig Runs - Cleaning / Gauge 11/4/25\n--11/4/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-86679","***","2025-11-06","2025-11-06","Added",null,null,"MLV 54-1D TO MLV 63-1S","100","1","Pig Runs - CLP / IMU 11/6/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,54.11,"------","***MLV 54-1D TO MLV 63-1S:  Pig Runs - CLP / IMU 11/6/25\n--11/6/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-86680","***","2025-11-11","2025-11-11","Added",null,null,"MLV 54-1D TO MLV 63-1S","100","1","Pig Runs - MFL-C 11/11/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,54.12,"------","***MLV 54-1D TO MLV 63-1S:  Pig Runs - MFL-C 11/11/25\n--11/11/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-86681","***","2025-11-13","2025-11-13","Added",null,null,"MLV 54-1D TO MLV 63-1S","100","1","Pig Runs - MFL-C 11/13/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,54.13,"------","***MLV 54-1D TO MLV 63-1S:  Pig Runs - MFL-C 11/13/25\n--11/13/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-108773","***","2025-02-10","2025-03-07","Added",null,null,"MLV 54-2 to MLV 57-2","100","1","PHMSA Immediate Anomaly Remediatio","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,54.2,"------","***MLV 54-2 to MLV 57-2:  PHMSA Immediate Anomaly Remediatio\n--2/10/25 through 3/7/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-1176748",null,"2025-05-06","2025-05-06",null,null,null,"MLV 54-2D TO MLV 63-2S","100","1","Pig Runs - Cleaning / Gauge 5/06/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,54.2,null,"MLV 54-2D TO MLV 63-2S:  Pig Runs - Cleaning / Gauge 5/06/25\n--5/6/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1176812",null,"2025-05-08","2025-05-08",null,null,null,"MLV 54-2D TO MLV 63-2S","100","1","Pig Runs - MFL-A 5/08/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,54.21,null,"MLV 54-2D TO MLV 63-2S:  Pig Runs - MFL-A 5/08/25\n--5/8/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1176845",null,"2025-03-04","2025-03-04",null,null,null,"MLV 54-4D TO MLV 63-4S","100","1","Pig Runs - Cleaning / Gauge 3/4/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,54.4,null,"MLV 54-4D TO MLV 63-4S:  Pig Runs - Cleaning / Gauge 3/4/25\n--3/4/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1176930",null,"2025-03-06","2025-03-06",null,null,null,"MLV 54-4D TO MLV 63-4S","100","1","Pig Runs - Caliper 3/6/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,54.41,null,"MLV 54-4D TO MLV 63-4S:  Pig Runs - Caliper 3/6/25\n--3/6/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1176957",null,"2025-03-11","2025-03-11",null,null,null,"MLV 54-4D TO MLV 63-4S","100","1","Pig Runs - AFD 3/11/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,54.42,null,"MLV 54-4D TO MLV 63-4S:  Pig Runs - AFD 3/11/25\n--3/11/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1176989",null,"2025-03-13","2025-03-13",null,null,null,"MLV 54-4D TO MLV 63-4S","100","1","Pig Runs - EMAT 3/13/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,54.43,null,"MLV 54-4D TO MLV 63-4S:  Pig Runs - EMAT 3/13/25\n--3/13/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-108769","***","2025-01-30","2025-02-08","Added",null,null,"MLV 60-2 to MLV 62-2","100","1","PHMSA Immediate Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,60.2,"------","***MLV 60-2 to MLV 62-2:  PHMSA Immediate Anomaly Remediation\n--1/30/25 through 2/8/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-1368169",null,"2025-08-27","2025-08-27",null,null,null,"Sta 63 Batesville","100","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,63,null,"Sta 63 Batesville:  Annual ESD Test\n--8/27/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-86701","***","2025-04-01","2025-06-20","Added",null,null,"Sta 63","100","1","Unit 1D - Overhaul & Geislinger Coupling Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,63.048999999999999,"------","***Sta 63:  Unit 1D - Overhaul & Geislinger Coupling Inspection\n--4/1/25 through 6/20/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-1082060",null,"2025-04-29","2025-04-29",null,null,null,"MLV 69-2 to MLV 63-2D","100","1","Pig Runs - Cleaning / Gauge 4/29/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,69.2,null,"MLV 69-2 to MLV 63-2D:  Pig Runs - Cleaning / Gauge 4/29/25\n--4/29/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1082062",null,"2025-05-01","2025-05-01",null,null,null,"MLV 69-2 to MLV 63-2D","100","1","Pig Runs - Caliper / UMU 5/1/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,69.209999999999994,null,"MLV 69-2 to MLV 63-2D:  Pig Runs - Caliper / UMU 5/1/25\n--5/1/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1082063",null,"2025-05-06","2025-05-06",null,null,null,"MLV 69-2 to MLV 63-2D","100","1","Pig Runs - MFL-C 5/6/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,69.22,null,"MLV 69-2 to MLV 63-2D:  Pig Runs - MFL-C 5/6/25\n--5/6/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1082065",null,"2025-05-08","2025-05-08",null,null,null,"MLV 69-2 to MLV 63-2D","100","1","Pig Runs - EMAT 5/8/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,69.23,null,"MLV 69-2 to MLV 63-2D:  Pig Runs - EMAT 5/8/25\n--5/8/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368183",null,"2025-05-07","2025-05-08",null,null,null,"Sta 71 Middleton","100","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,71,null,"Sta 71 Middleton:  Annual ESD Test\n--5/7/25 through 5/8/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-1196655",null,"2023-11-28","2025-02-28",null,null,null,"Sta 71","100","1","Unit 3A - Discharge Bottle Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,71.003,null,"Sta 71:  Unit 3A - Discharge Bottle Inspection\n--11/28/23 through 2/28/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-262275",null,"2024-04-08","2025-01-31",null,null,null,"Sta 71","100","1","Unit 7A Replace Crank End Compressor Gasket","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,71.007000000000005,null,"Sta 71:  Unit 7A Replace Crank End Compressor Gasket\n--4/8/24 through 1/31/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1082056",null,"2025-04-15","2025-04-15",null,null,null,"MLV 71-3S to MLV 63-3D","100","1","Pig Runs - Cleaning / Gauge 4/15/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,71.3,null,"MLV 71-3S to MLV 63-3D:  Pig Runs - Cleaning / Gauge 4/15/25\n--4/15/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1082057",null,"2025-04-17","2025-04-17",null,null,null,"MLV 71-3S to MLV 63-3D","100","1","Pig Runs - Caliper / IMU 4/17/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,71.31,null,"MLV 71-3S to MLV 63-3D:  Pig Runs - Caliper / IMU 4/17/25\n--4/17/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1082058",null,"2025-04-22","2025-04-22",null,null,null,"MLV 71-3S to MLV 63-3D","100","1","Pig Runs - MFL-C 4/22/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,71.319999999999993,null,"MLV 71-3S to MLV 63-3D:  Pig Runs - MFL-C 4/22/25\n--4/22/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1082059",null,"2025-04-24","2025-04-24",null,null,null,"MLV 71-3S to MLV 63-3D","100","1","Pig Runs - EMAT 4/24/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,71.33,null,"MLV 71-3S to MLV 63-3D:  Pig Runs - EMAT 4/24/25\n--4/24/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1082041",null,"2025-02-18","2025-02-18",null,null,null,"MLV 71-4S to MLV 63-4D","100","1","Pig Runs - Cleaning / Gauge 2/18/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,71.400000000000006,null,"MLV 71-4S to MLV 63-4D:  Pig Runs - Cleaning / Gauge 2/18/25\n--2/18/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1082043",null,"2025-02-20","2025-02-20",null,null,null,"MLV 71-4S to MLV 63-4D","100","4","Pig Runs - Caliper / IMU 2/20/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,71.41,null,"MLV 71-4S to MLV 63-4D:  Pig Runs - Caliper / IMU 2/20/25\n--2/20/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1082045",null,"2025-02-25","2025-02-25",null,null,null,"MLV 71-4S to MLV 63-4D","100","1","Pig Runs - MFL-C 2/25/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,71.42,null,"MLV 71-4S to MLV 63-4D:  Pig Runs - MFL-C 2/25/25\n--2/25/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1082047",null,"2025-02-27","2025-02-27",null,null,null,"MLV 71-4S to MLV 63-4D","100","1","Pig Runs - EMAT 2/27/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,71.430000000000007,null,"MLV 71-4S to MLV 63-4D:  Pig Runs - EMAT 2/27/25\n--2/27/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368189",null,"2025-05-06","2025-05-06",null,null,null,"Sta 79 Lobelville","100","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,79,null,"Sta 79 Lobelville:  Annual ESD Test\n--5/6/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1082037",null,"2025-02-04","2025-02-04",null,null,null,"MLV 79-2S to MLV 71-2D","100","1","Pig Runs - Cleaning / Gauge 2/4/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,79.2,null,"MLV 79-2S to MLV 71-2D:  Pig Runs - Cleaning / Gauge 2/4/25\n--2/4/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1082038",null,"2025-02-06","2025-02-06",null,null,null,"MLV 79-2S to MLV 71-2D","100","1","Pig Runs - Caliper / IMU 2/6/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,79.209999999999994,null,"MLV 79-2S to MLV 71-2D:  Pig Runs - Caliper / IMU 2/6/25\n--2/6/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1082039",null,"2025-02-11","2025-02-11",null,null,null,"MLV 79-2S to MLV 71-2D","100","1","Pig Runs - MFL-C 2/11/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,79.22,null,"MLV 79-2S to MLV 71-2D:  Pig Runs - MFL-C 2/11/25\n--2/11/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1082040",null,"2025-02-13","2025-02-13",null,null,null,"MLV 79-2S to MLV 71-2D","100","1","Pig Runs - EMAT 2/13/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,79.23,null,"MLV 79-2S to MLV 71-2D:  Pig Runs - EMAT 2/13/25\n--2/13/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-296273",null,"2024-10-31","2025-01-31",null,null,null,"MLV 84-3 to MLV 85-3","100","1","Class Change","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,84.3,null,"MLV 84-3 to MLV 85-3:  Class Change\n--10/31/24 through 1/31/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368208",null,"2025-10-21","2025-10-22",null,null,null,"Sta 87 Portland","100","2","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,87,null,"Sta 87 Portland:  Annual ESD Test\n--10/21/25 through 10/22/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-326855",null,"2024-08-26","2025-02-07",null,null,null,"Sta 87","100","2","Unit 5C - Foundation Regrout","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,87.037000000000006,null,"Sta 87:  Unit 5C - Foundation Regrout\n--8/26/24 through 2/7/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1009116",null,"2025-02-18","2025-02-18",null,null,null,"MLV 87-4 to MLV 96-4","100","2","Pig Runs - Cleaning / Gauge 2/18/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,87.4,null,"MLV 87-4 to MLV 96-4:  Pig Runs - Cleaning / Gauge 2/18/25\n--2/18/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-69508",null,"2025-02-20","2025-02-20",null,null,null,"MLV 87-4 to MLV 96-4","100","2","Pig Runs - Caliper 2/20/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,87.4,null,"MLV 87-4 to MLV 96-4:  Pig Runs - Caliper 2/20/25\n--2/20/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1009137",null,"2025-02-25","2025-02-25",null,null,null,"MLV 87-4 to MLV 96-4","100","2","Pig Runs - AFD Combo 2/25/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,87.41,null,"MLV 87-4 to MLV 96-4:  Pig Runs - AFD Combo 2/25/25\n--2/25/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1009163",null,"2025-02-27","2025-02-27",null,null,null,"MLV 87-4 to MLV 96-4","100","2","Pig Runs - EMAT 2/27/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,87.42,null,"MLV 87-4 to MLV 96-4:  Pig Runs - EMAT 2/27/25\n--2/27/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-82079","***","2025-05-05","2025-07-11","Added",null,null,"MLV 90-3 to MLV 91-3","100","2","HDD River Crossing Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,90.3,"------","***MLV 90-3 to MLV 91-3:  HDD River Crossing Replacement\n--5/5/25 through 7/11/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-82082","***","2025-05-05","2025-07-11","Added",null,null,"MLV 93-3 to MLV 94-3","100","2","HDD River Crossing Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,93.3,"------","***MLV 93-3 to MLV 94-3:  HDD River Crossing Replacement\n--5/5/25 through 7/11/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-1368197",null,"2025-05-28","2025-05-29",null,null,null,"Sta 96 Campbellsville","100","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,96,null,"Sta 96 Campbellsville:  Annual ESD Test\n--5/28/25 through 5/29/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368198",null,"2025-05-28","2025-05-30",null,null,null,"Sta 96 Campbellsville","100","2","Annual Substation Inspection","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,96.000100000000003,null,"Sta 96 Campbellsville:  Annual Substation Inspection\n--5/28/25 through 5/30/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-326854",null,"2024-07-08","2025-02-28",null,null,null,"Sta 96","100","2","Unit 7C - Foundation Regrout","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,96.039000000000001,null,"Sta 96:  Unit 7C - Foundation Regrout\n--7/8/24 through 2/28/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1009068",null,"2025-02-04","2025-02-04",null,null,null,"MLV 96-2 to MLV 102-2","100","2","Pig Runs - Cleaning / Gauge 2/4/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,96.2,null,"MLV 96-2 to MLV 102-2:  Pig Runs - Cleaning / Gauge 2/4/25\n--2/4/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-69507",null,"2025-02-06","2025-02-06",null,null,null,"MLV 96-2 to MLV 102-2","100","2","Pig Runs - Caliper 2/6/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,96.2,null,"MLV 96-2 to MLV 102-2:  Pig Runs - Caliper 2/6/25\n--2/6/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1009092",null,"2025-02-11","2025-02-11",null,null,null,"MLV 96-2 to MLV 102-2","100","2","Pig Runs - AFD Combo 2/11/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,96.21,null,"MLV 96-2 to MLV 102-2:  Pig Runs - AFD Combo 2/11/25\n--2/11/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1009104",null,"2025-02-13","2025-02-13",null,null,null,"MLV 96-2 to MLV 102-2","100","2","Pig Runs - EMAT 2/13/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,96.22,null,"MLV 96-2 to MLV 102-2:  Pig Runs - EMAT 2/13/25\n--2/13/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1009227",null,"2025-03-18","2025-03-18",null,null,null,"MLV 96-4 to MLV 106-4","100","2","Pig Runs - Cleaning / Gauge 3/18/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SiP","Potential in the path restrictions may be at risk.",null,96.4,null,"MLV 96-4 to MLV 106-4:  Pig Runs - Cleaning / Gauge 3/18/25\n--3/18/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-1009255",null,"2025-03-20","2025-03-20",null,null,null,"MLV 96-4 to MLV 106-4","100","2","Pig Runs - AFD Combo 3/20/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SiP","Potential in the path restrictions may be at risk.",null,96.41,null,"MLV 96-4 to MLV 106-4:  Pig Runs - AFD Combo 3/20/25\n--3/20/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-1009272",null,"2025-03-25","2025-03-25",null,null,null,"MLV 96-4 to MLV 106-4","100","2","Pig Runs - EMAT 3/25/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SiP","Potential in the path restrictions may be at risk.",null,96.42,null,"MLV 96-4 to MLV 106-4:  Pig Runs - EMAT 3/25/25\n--3/25/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-1009324",null,"2025-09-25","2025-09-25",null,null,null,"MLV 96-5 to MLV 102-5","100","2","Pig Runs - Cleaning / Gauge 9/25/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,96.5,null,"MLV 96-5 to MLV 102-5:  Pig Runs - Cleaning / Gauge 9/25/25\n--9/25/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1009338",null,"2025-09-30","2025-09-30",null,null,null,"MLV 96-5 to MLV 102-5","100","2","Pig Runs - AFD Combo 9/30/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,96.51,null,"MLV 96-5 to MLV 102-5:  Pig Runs - AFD Combo 9/30/25\n--9/30/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1009343",null,"2025-10-02","2025-10-02",null,null,null,"MLV 96-5 to MLV 102-5","100","2","Pig Runs - EMAT 10/2/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,96.52,null,"MLV 96-5 to MLV 102-5:  Pig Runs - EMAT 10/2/25\n--10/2/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-40773",null,"2025-01-07","2025-02-01",null,null,null,"MLV 97-1 to MLV 100-1","100","2","Emergent Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,97.1,null,"MLV 97-1 to MLV 100-1:  Emergent Anomaly Remediation\n--1/7/25 through 2/1/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-40775",null,"2025-01-07","2025-02-15",null,null,null,"MLV100-1A to MLV 101-1","100","2","Emergent Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,100.1,null,"MLV100-1A to MLV 101-1:  Emergent Anomaly Remediation\n--1/7/25 through 2/15/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368157",null,"2025-06-02","2025-06-06",null,null,null,"Sta 106 Clay City","100","2","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106,null,"Sta 106 Clay City:  Annual ESD Test & Maintenance\n--6/2/25 through 6/6/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1367811","***","2024-12-17","2025-02-02","Project Change",null,"2025-01-22","Sta 106","100","2","Unit 14B - Compressor Packing","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106.03,"----end_date------------model_loc--","***Sta 106:  Unit 14B - Compressor Packing\n--12/17/24 through 2/2/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 12/17/24 to 1/22/25.\n………………………………"]
["X24-1374956",null,"2025-01-13","2025-03-17",null,null,null,"Sta 106","100","2","Unit 1C - Turbocharger Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106.033,null,"Sta 106:  Unit 1C - Turbocharger Replacement\n--1/13/25 through 3/17/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1009349",null,"2025-10-09","2025-10-09",null,null,null,"MLV 106-1 to MLV 111-7","100","2","Pig Runs - Cleaning / Gauge 10/9/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,106.1,null,"MLV 106-1 to MLV 111-7:  Pig Runs - Cleaning / Gauge 10/9/25\n--10/9/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1009358",null,"2025-10-14","2025-10-14",null,null,null,"MLV 106-1 to MLV 111-7","100","2","Pig Runs - AFD Combo 10/14/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,106.11,null,"MLV 106-1 to MLV 111-7:  Pig Runs - AFD Combo 10/14/25\n--10/14/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1009364",null,"2025-10-16","2025-10-16",null,null,null,"MLV 106-1 to MLV 111-7","100","2","Pig Runs - EMAT 10/16/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,106.12,null,"MLV 106-1 to MLV 111-7:  Pig Runs - EMAT 10/16/25\n--10/16/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368164",null,"2025-10-30","2025-10-30",null,null,null,"Sta 107A North Means","100","2","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,107,null,"Sta 107A North Means:  Annual ESD Test\n--10/30/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-38381",null,"2024-12-29","2025-02-28",null,null,null,"MLV 108-4 to MLV 109-4","100","2","Immediate Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,108.4,null,"MLV 108-4 to MLV 109-4:  Immediate Anomaly Remediation\n--12/29/24 through 2/28/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368158",null,"2025-05-27","2025-05-30",null,null,null,"Sta 110 Morehead","100","2","Annual ESD Test & Substation Inspection","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,110,null,"Sta 110 Morehead:  Annual ESD Test & Substation Inspection\n--5/27/25 through 5/30/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1009371",null,"2025-10-23","2025-10-23",null,null,null,"MLV 111-3 to MLV 114-3","100","2","Pig Runs - Cleaning / Gauge 10/23/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,111.3,null,"MLV 111-3 to MLV 114-3:  Pig Runs - Cleaning / Gauge 10/23/25\n--10/23/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1009383",null,"2025-10-28","2025-10-28",null,null,null,"MLV 111-3 to MLV 114-3","100","2","Pig Runs - AFD Combo 10/28/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,111.31,null,"MLV 111-3 to MLV 114-3:  Pig Runs - AFD Combo 10/28/25\n--10/28/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1009386",null,"2025-10-30","2025-10-30",null,null,null,"MLV 111-3 to MLV 114-3","100","2","Pig Runs - EMAT 10/30/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,111.32,null,"MLV 111-3 to MLV 114-3:  Pig Runs - EMAT 10/30/25\n--10/30/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368160",null,"2025-05-20","2025-05-23",null,null,null,"Sta 114 Catlettsburg","100","3","Annual ESD Test & Substation Inspection","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,114,null,"Sta 114 Catlettsburg:  Annual ESD Test & Substation Inspection\n--5/20/25 through 5/23/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-101576","***","2025-04-14","2025-04-17","Added",null,null,"Sta 114","100","3","Unit 1D - 4K Solar Turbine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,114.04900000000001,"------","***Sta 114:  Unit 1D - 4K Solar Turbine Inspection\n--4/14/25 through 4/17/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-1368165",null,"2025-09-16","2025-09-18",null,null,null,"Sta 118A Tyler Mountain","100","3","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,118,null,"Sta 118A Tyler Mountain:  Annual ESD Test\n--9/16/25 through 9/18/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368156",null,"2025-09-09","2025-09-11",null,null,null,"Sta 119A Rocky Fork","100","3","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,119,null,"Sta 119A Rocky Fork:  Annual ESD Test\n--9/9/25 through 9/11/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1009283",null,"2025-04-01","2025-04-01",null,null,null,"MLV 121-1 to MLV 118-1","100","3","Pig Runs - Cleaning / Gauge 4/1/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SiP","Potential in the path restrictions may be at risk.",null,121.1,null,"MLV 121-1 to MLV 118-1:  Pig Runs - Cleaning / Gauge 4/1/25\n--4/1/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-1009307",null,"2025-04-03","2025-04-03",null,null,null,"MLV 121-1 to MLV 118-1","100","3","Pig Runs - AFD Combo 4/3/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SiP","Potential in the path restrictions may be at risk.",null,121.11,null,"MLV 121-1 to MLV 118-1:  Pig Runs - AFD Combo 4/3/25\n--4/3/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-1009317",null,"2025-04-08","2025-04-08",null,null,null,"MLV 121-1 to MLV 118-1","100","3","Pig Runs - EMAT 4/8/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SiP","Potential in the path restrictions may be at risk.",null,121.12,null,"MLV 121-1 to MLV 118-1:  Pig Runs - EMAT 4/8/25\n--4/8/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-1368163",null,"2025-06-24","2025-06-24",null,null,null,"Sta 200 Greenup","200","4","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,200,null,"Sta 200 Greenup:  Annual ESD Test\n--6/24/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-25714","***","2025-01-21","2025-01-24","Completed",null,null,"Sta 200","200","4","Unit 2A - Crankcase Inspections","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,200.00200000000001,"------","***Sta 200:  Unit 2A - Crankcase Inspections\n***Completed"]
["X25-25708",null,"2025-02-03","2025-02-07",null,null,null,"Sta 200","200","4","Unit 4A - Crankcase Inspections","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,200.00399999999999,null,"Sta 200:  Unit 4A - Crankcase Inspections\n--2/3/25 through 2/7/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-25713",null,"2025-01-27","2025-01-31",null,null,null,"Sta 200","200","4","Unit 10A - Crankcase Inspections","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,200.01,null,"Sta 200:  Unit 10A - Crankcase Inspections\n--1/27/25 through 1/31/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-77407",null,"2025-02-10","2025-02-14",null,null,null,"Sta 200","200","4","Unit 12A - Replace Turbo","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,200.012,null,"Sta 200:  Unit 12A - Replace Turbo\n--2/10/25 through 2/14/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-35049",null,"2025-01-01","2025-03-15",null,null,null,"MLV 200-1 to MLV 201-1","200","4","Immediate Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,200.1,null,"MLV 200-1 to MLV 201-1:  Immediate Anomaly Remediation\n--1/1/25 through 3/15/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-35008",null,"2025-02-18","2025-02-18",null,null,null,"MLV 200-2 to MLV 110-4","100","2","Pig Re-Runs - EMAT 2/18/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,200.2,null,"MLV 200-2 to MLV 110-4:  Pig Re-Runs - EMAT 2/18/25\n--2/18/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-38342",null,"2025-05-05","2025-05-09",null,null,null,"Sta 204","200","4","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,204,null,"Sta 204:  Annual ESD Test & Maintenance\n--5/5/25 through 5/9/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-34890","***","2025-01-24","2025-02-04","Project Change","2025-01-27","2025-01-31","Sta 204","200","4","Unit 2A - Inspect P1 & P2 and all inner coolers","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,204.00200000000001,"--start_date--end_date------------model_loc--","***Sta 204:  Unit 2A - Inspect P1 & P2 and all inner coolers\n--1/24/25 through 2/4/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 1/27/25 to 1/31/25.\n………………………………"]
["X25-34889",null,"2025-02-03","2025-02-06",null,null,null,"Sta 204","200","4","Unit 10A - Punch Carbon & Inspect Cylinders","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,204.01,null,"Sta 204:  Unit 10A - Punch Carbon & Inspect Cylinders\n--2/3/25 through 2/6/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1017097",null,"2025-04-15","2025-04-15",null,null,null,"MLV 204-2 to MLV 200-2","200","4","Pig Runs - Cleaning / Gauge 4/15/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","421018 TET/TGP HANGING ROCK SCIOTO",204.2,null,"MLV 204-2 to MLV 200-2:  Pig Runs - Cleaning / Gauge 4/15/25\n--4/15/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n421018 TET/TGP HANGING ROCK SCIOTO\n………………………………"]
["X24-1017099",null,"2025-04-17","2025-04-17",null,null,null,"MLV 204-2 to MLV 200-2","200","4","Pig Runs - MFL-A Combo 4/17/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","421018 TET/TGP HANGING ROCK SCIOTO",204.21,null,"MLV 204-2 to MLV 200-2:  Pig Runs - MFL-A Combo 4/17/25\n--4/17/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n421018 TET/TGP HANGING ROCK SCIOTO\n………………………………"]
["X24-1017102",null,"2025-04-22","2025-04-22",null,null,null,"MLV 204-2 to MLV 200-2","200","4","Pig Runs - Residual 4/22/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","421018 TET/TGP HANGING ROCK SCIOTO",204.22,null,"MLV 204-2 to MLV 200-2:  Pig Runs - Residual 4/22/25\n--4/22/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n421018 TET/TGP HANGING ROCK SCIOTO\n………………………………"]
["X25-35079",null,"2025-04-24","2025-04-24",null,null,null,"MLV 204-2 to MLV 200-2","200","4","Pig Runs - MFL-C 4/24/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","421018 TET/TGP HANGING ROCK SCIOTO",204.23,null,"MLV 204-2 to MLV 200-2:  Pig Runs - MFL-C 4/24/25\n--4/24/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n421018 TET/TGP HANGING ROCK SCIOTO\n………………………………"]
["X25-35083",null,"2025-04-29","2025-04-29",null,null,null,"MLV 204-2 to MLV 200-2","200","4","Pig Runs - EMAT 4/29/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","421018 TET/TGP HANGING ROCK SCIOTO",204.24,null,"MLV 204-2 to MLV 200-2:  Pig Runs - EMAT 4/29/25\n--4/29/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n421018 TET/TGP HANGING ROCK SCIOTO\n………………………………"]
["X25-38343",null,"2025-05-12","2025-05-16",null,null,null,"Sta 209 Cambridge","200","4","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209,null,"Sta 209 Cambridge:  Annual ESD Test & Maintenance\n--5/12/25 through 5/16/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-34894",null,"2025-01-13","2025-01-30",null,null,null,"Sta 209","200","4","Unit 1A - Bob Weight Inspection at #4 & #5 Main & Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209.001,null,"Sta 209:  Unit 1A - Bob Weight Inspection at #4 & #5 Main & Crankcase Inspection\n--1/13/25 through 1/30/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1146365","***","2025-01-22","2025-01-31","Completed",null,null,"Sta 209","200","4","Unit 2A - Compressor Packing","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209.00200000000001,"------","***Sta 209:  Unit 2A - Compressor Packing\n***Completed"]
["X25-104455","***","2025-02-10","2025-02-14","Added",null,null,"Sta 209","200","4","Unit 2A - Punch Carbon","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209.00200000000001,"------","***Sta 209:  Unit 2A - Punch Carbon\n--2/10/25 through 2/14/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-84572","***","2025-01-23","2025-02-09","Added",null,null,"Sta 209","200","4","Unit 3A - Turbo Failure","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209.00299999999999,"------","***Sta 209:  Unit 3A - Turbo Failure\n--1/23/25 through 2/9/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-43686","***","2025-02-10","2025-02-14","Project Change","2025-02-03","2025-02-07","Sta 209","200","4","Unit 3A - Punch Carbon","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209.00299999999999,"--start_date--end_date------------model_loc--","***Sta 209:  Unit 3A - Punch Carbon\n--2/10/25 through 2/14/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 2/3/25 to 2/7/25.\n………………………………"]
["X25-43687","***","2025-02-17","2025-02-21","Project Change","2025-02-10","2025-02-14","Sta 209","200","4","Unit 4A - Punch Carbon","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209.00399999999999,"--start_date--end_date------------model_loc--","***Sta 209:  Unit 4A - Punch Carbon\n--2/17/25 through 2/21/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 2/10/25 to 2/14/25.\n………………………………"]
["X25-43688","***","2025-02-24","2025-02-28","Project Change","2025-02-17","2025-02-21","Sta 209","200","4","Unit 5A - Punch Carbon","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209.005,"--start_date--end_date------------model_loc--","***Sta 209:  Unit 5A - Punch Carbon\n--2/24/25 through 2/28/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 2/17/25 to 2/21/25.\n………………………………"]
["X25-43689","***","2025-03-03","2025-03-07","Project Change","2025-02-24","2025-02-28","Sta 209","200","4","Unit 6A - Punch Carbon","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209.006,"--start_date--end_date------------model_loc--","***Sta 209:  Unit 6A - Punch Carbon\n--3/3/25 through 3/7/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 2/24/25 to 2/28/25.\n………………………………"]
["X25-34895","***","2025-03-10","2025-03-14","Project Change","2025-03-03","2025-03-07","Sta 209","200","4","Unit 7A - Repack #1 Turbo Exhaust outlet flange","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209.00700000000001,"--start_date--end_date------------model_loc--","***Sta 209:  Unit 7A - Repack #1 Turbo Exhaust outlet flange\n--3/10/25 through 3/14/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 3/3/25 to 3/7/25.\n………………………………"]
["X25-43690","***","2025-03-17","2025-03-21","Project Change","2025-03-10","2025-03-14","Sta 209","200","4","Unit 8A - Punch Carbon","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209.00800000000001,"--start_date--end_date------------model_loc--","***Sta 209:  Unit 8A - Punch Carbon\n--3/17/25 through 3/21/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 3/10/25 to 3/14/25.\n………………………………"]
["X25-43691","***","2025-03-24","2025-03-28","Project Change","2025-03-17","2025-03-21","Sta 209","200","4","Unit 9A - Punch Carbon","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209.00899999999999,"--start_date--end_date------------model_loc--","***Sta 209:  Unit 9A - Punch Carbon\n--3/24/25 through 3/28/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 3/17/25 to 3/21/25.\n………………………………"]
["X25-43694","***","2025-03-31","2025-04-04","Project Change","2025-03-24","2025-03-28","Sta 209","200","4","Unit 10A - Punch Carbon","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209.01,"--start_date--end_date------------model_loc--","***Sta 209:  Unit 10A - Punch Carbon\n--3/31/25 through 4/4/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 3/24/25 to 3/28/25.\n………………………………"]
["X24-1016928",null,"2025-07-15","2025-07-15",null,null,null,"MLV 209-2 to MLV 204-2","200","4","Pig Runs - Cleaning Gauge 7/15/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,209.2,null,"MLV 209-2 to MLV 204-2:  Pig Runs - Cleaning Gauge 7/15/25\n--7/15/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1016946",null,"2025-07-17","2025-07-17",null,null,null,"MLV 209-2 to MLV 204-2","200","4","Pig Runs - MFL-A Combo 7/17/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,209.21,null,"MLV 209-2 to MLV 204-2:  Pig Runs - MFL-A Combo 7/17/25\n--7/17/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1017103",null,"2025-07-22","2025-07-22",null,null,null,"MLV 209-2 to MLV 204-2","200","4","Pig Runs - EMAT 7/22/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,209.22,null,"MLV 209-2 to MLV 204-2:  Pig Runs - EMAT 7/22/25\n--7/22/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1017092",null,"2025-04-22","2025-04-22",null,null,null,"MLV 209-3 to MLV 204-3","200","4","Pig Runs - EMAT 1/21/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,209.32,null,"MLV 209-3 to MLV 204-3:  Pig Runs - EMAT 1/21/25\n--4/22/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1017066",null,"2025-11-11","2025-11-11",null,null,null,"MLV 209-4 to MLV 204-4","200","4","Pig Runs - Cleaning / Gauge 11/11/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,209.4,null,"MLV 209-4 to MLV 204-4:  Pig Runs - Cleaning / Gauge 11/11/25\n--11/11/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1017067",null,"2025-11-13","2025-11-13",null,null,null,"MLV 209-4 to MLV 204-4","200","4","Pig Runs - MFL-A Combo 11/13/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,209.41,null,"MLV 209-4 to MLV 204-4:  Pig Runs - MFL-A Combo 11/13/25\n--11/13/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1017070","***","2025-11-18","2025-11-18","Completed",null,null,"MLV 209-4 to MLV 204-4","200","4","Pig Runs - EMAT 11/18/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,209.42,"------","***MLV 209-4 to MLV 204-4:  Pig Runs - EMAT 11/18/25\n***Completed"]
["X25-86675","***","2025-01-21","2025-02-06","Added",null,null,"Sta 214","200","4","Unit 3A - Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,214.00299999999999,"------","***Sta 214:  Unit 3A - Engine Inspection\n--1/21/25 through 2/6/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-1016963",null,"2025-02-04","2025-02-04",null,null,null,"MLV 214-1 to MLV 209-1","200","4","Pig Runs - Cleaning Gauge 2/4/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,214.1,null,"MLV 214-1 to MLV 209-1:  Pig Runs - Cleaning Gauge 2/4/25\n--2/4/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1016976",null,"2025-02-06","2025-02-06",null,null,null,"MLV 214-1 to MLV 209-1","200","4","Pig Runs - MFL-A Combo 2/6/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,214.11,null,"MLV 214-1 to MLV 209-1:  Pig Runs - MFL-A Combo 2/6/25\n--2/6/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1016984",null,"2025-02-11","2025-02-11",null,null,null,"MLV 214-1 to MLV 209-1","200","4","Pig Runs - MFL-C Combo 2/11/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,214.12,null,"MLV 214-1 to MLV 209-1:  Pig Runs - MFL-C Combo 2/11/25\n--2/11/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1016990",null,"2025-02-13","2025-02-13",null,null,null,"MLV 214-1 to MLV 209-1","200","4","Pig Runs - EMAT 2/13/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,214.13,null,"MLV 214-1 to MLV 209-1:  Pig Runs - EMAT 2/13/25\n--2/13/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1017002","***","2025-03-17","2025-03-17","Project Change","2025-03-04","2025-03-04","MLV 217A-201.3 to MLV 217A-202","200","4","Pig Runs - Cleaning Gauge 3/17/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,214.2,"--start_date--end_date------mantenance_desc------model_loc--","***MLV 217A-201.3 to MLV 217A-202:  Pig Runs - Cleaning Gauge 3/17/25\n--3/17/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 3/4/25.\n………………………………"]
["X24-1017045","***","2025-03-04","2025-03-04","Project Change","2025-03-18","2025-03-18","MLV 214-3 to MLV 209-3","200","4","Pig Runs - Cleaning Gauge 3/4/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,214.3,"--start_date--end_date------mantenance_desc------model_loc--","***MLV 214-3 to MLV 209-3:  Pig Runs - Cleaning Gauge 3/4/25\n--3/4/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 3/18/25.\n………………………………"]
["X24-1017058","***","2025-03-06","2025-03-06","Project Change","2025-03-20","2025-03-20","MLV 214-3 to MLV 209-3","200","4","Pig Runs - MFL-A Combo 3/6/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,214.31,"--start_date--end_date------mantenance_desc------model_loc--","***MLV 214-3 to MLV 209-3:  Pig Runs - MFL-A Combo 3/6/25\n--3/6/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 3/20/25.\n………………………………"]
["X24-1017060","***","2025-03-11","2025-03-11","Project Change","2025-03-25","2025-03-25","MLV 214-3 to MLV 209-3","200","4","Pig Runs - EMAT 3/11/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,214.32,"--start_date--end_date------mantenance_desc------model_loc--","***MLV 214-3 to MLV 209-3:  Pig Runs - EMAT 3/11/25\n--3/11/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 3/25/25.\n………………………………"]
["X24-1017013","***","2025-03-18","2025-03-18","Project Change","2025-03-05","2025-03-05","MLV 217A-201.3 to MLV 217A-202","200","4","Pig Runs - MFL-A Combo 3/18/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,217.21,"--start_date--end_date------mantenance_desc------model_loc--","***MLV 217A-201.3 to MLV 217A-202:  Pig Runs - MFL-A Combo 3/18/25\n--3/18/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 3/5/25.\n………………………………"]
["X24-1017018","***","2025-03-19","2025-03-19","Project Change","2025-03-06","2025-03-06","MLV 217A-201.3 to MLV 217A-202","200","4","Pig Runs - EMAT 3/19/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,217.22,"--start_date--end_date------mantenance_desc------model_loc--","***MLV 217A-201.3 to MLV 217A-202:  Pig Runs - EMAT 3/19/25\n--3/19/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 3/6/25.\n………………………………"]
["X24-1017061",null,"2025-10-30","2025-10-30",null,null,null,"MLV 219-2 to MLV 214-2","200","4","Pig Runs - Cleaning / Gauge 10/30/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,219.2,null,"MLV 219-2 to MLV 214-2:  Pig Runs - Cleaning / Gauge 10/30/25\n--10/30/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1017063",null,"2025-11-04","2025-11-04",null,null,null,"MLV 219-2 to MLV 214-2","200","4","Pig Runs - MFL-A Combo 11/4/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,219.21,null,"MLV 219-2 to MLV 214-2:  Pig Runs - MFL-A Combo 11/4/25\n--11/4/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1017065",null,"2025-11-06","2025-11-06",null,null,null,"MLV 219-2 to MLV 214-2","200","4","Pig Runs - EMAT 11/6/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,219.22,null,"MLV 219-2 to MLV 214-2:  Pig Runs - EMAT 11/6/25\n--11/6/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1017104",null,"2025-04-01","2025-04-01",null,null,null,"MLV 219-4 to MLV 214-4","200","4","Pig Runs - Cleaning / Gauge 4/1/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,219.4,null,"MLV 219-4 to MLV 214-4:  Pig Runs - Cleaning / Gauge 4/1/25\n--4/1/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1017105",null,"2025-04-03","2025-04-03",null,null,null,"MLV 219-4 to MLV 214-4","200","4","Pig Runs - MFL-A Combo 4/3/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,219.41,null,"MLV 219-4 to MLV 214-4:  Pig Runs - MFL-A Combo 4/3/25\n--4/3/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1017106",null,"2025-04-08","2025-04-08",null,null,null,"MLV 219-4 to MLV 214-4","200","4","Pig Runs - EMAT 4/8/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,219.42,null,"MLV 219-4 to MLV 214-4:  Pig Runs - EMAT 4/8/25\n--4/8/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-34917",null,"2025-06-10","2025-06-11",null,null,null,"Sta 224","200","5","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,224,null,"Sta 224:  Annual ESD Test\n--6/10/25 through 6/11/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-34918",null,"2025-05-14","2025-05-15",null,null,null,"Sta 229","200","5","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,229,null,"Sta 229:  Annual ESD Test & Maintenance\n--5/14/25 through 5/15/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-34920",null,"2025-07-16","2025-07-17",null,null,null,"Station 230C","200","5","Annual ESD","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.   The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","410902 TRANSCAN/TGP UDP NIAGARA RIVER NIAG\n421079 TRANSCAN/TGP UDP NIAGARA RIVER DELI",230,null,"Station 230C:  Annual ESD\n--7/16/25 through 7/17/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.   The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n410902 TRANSCAN/TGP UDP NIAGARA RIVER NIAG\n421079 TRANSCAN/TGP UDP NIAGARA RIVER DELI\n………………………………"]
["X25-34896",null,"2025-05-20","2025-05-22",null,null,null,"MLV 230B-201 to MLV 230B-207","200","5","Pig Run - Maintenance Cleaning 5/20 - 5/22","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,230.2,null,"MLV 230B-201 to MLV 230B-207:  Pig Run - Maintenance Cleaning 5/20 - 5/22\n--5/20/25 through 5/22/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-53612","***","2025-01-30","2025-01-30","Project Change","2025-01-28","2025-01-28","Sta 241","200","5","Unit 1B - 2k hr Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,241.017,"--start_date--end_date------------model_loc--","***Sta 241:  Unit 1B - 2k hr Maintenance\n--1/30/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 1/28/25.\n………………………………"]
["X25-53614","***","2025-01-29","2025-01-30","Project Change",null,"2025-01-29","Sta 241","200","5","Unit 2B - 2k hr Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,241.018,"----end_date------------model_loc--","***Sta 241:  Unit 2B - 2k hr Maintenance\n--1/29/25 through 1/30/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 1/29/25 to 1/29/25.\n………………………………"]
["X25-101287","***","2025-05-13","2025-05-14","Added",null,null,"Sta 245 West Winfield","200","5","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,245,"------","***Sta 245 West Winfield:  Annual ESD Test\n--5/13/25 through 5/14/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-86691","***","2025-01-20","2025-02-14","Added",null,null,"Sta 245","200","5","Unit 5A - Timing Chain Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,245.005,"------","***Sta 245:  Unit 5A - Timing Chain Replacement\n--1/20/25 through 2/14/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-101258","***","2025-05-12","2025-05-23","Added",null,null,"Sta 245","200","5","Unit 1C - Water Wash & Borescope","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,245.03299999999999,"------","***Sta 245:  Unit 1C - Water Wash & Borescope\n--5/12/25 through 5/23/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-69555",null,"2025-09-08","2025-09-12",null,null,null,"Sta 245","200","5","Unit 1C - Engine Exchange","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,245.03299999999999,null,"Sta 245:  Unit 1C - Engine Exchange\n--9/8/25 through 9/12/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1017344",null,"2025-05-06","2025-05-06",null,null,null,"MLV 245-2 TO MLV 249-2","200","5","Pig Runs - Cleaning / Gauge 5/6/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420897 NYSEG/TGP RICHFIELD SPRINGS HERKIME\n420857 NYSEG/TGP CARLISLE SALES SCHOHARIE",245.2,null,"MLV 245-2 TO MLV 249-2:  Pig Runs - Cleaning / Gauge 5/6/25\n--5/6/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420897 NYSEG/TGP RICHFIELD SPRINGS HERKIME\n420857 NYSEG/TGP CARLISLE SALES SCHOHARIE\n………………………………"]
["X24-1017368",null,"2025-05-07","2025-05-07",null,null,null,"MLV 245-2 TO MLV 249-2","200","5","Pig Runs - MFL-A / Cal / IMU Combo 5/7/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420897 NYSEG/TGP RICHFIELD SPRINGS HERKIME\n420857 NYSEG/TGP CARLISLE SALES SCHOHARIE",245.21,null,"MLV 245-2 TO MLV 249-2:  Pig Runs - MFL-A / Cal / IMU Combo 5/7/25\n--5/7/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420897 NYSEG/TGP RICHFIELD SPRINGS HERKIME\n420857 NYSEG/TGP CARLISLE SALES SCHOHARIE\n………………………………"]
["X25-56507",null,"2025-04-28","2025-04-29",null,null,null,"Sta 249 Carlisle","200","5","Filter Inspection","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,249.00001,null,"Sta 249 Carlisle:  Filter Inspection\n--4/28/25 through 4/29/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-101468","***","2025-04-28","2025-05-02","Added",null,null,"Sta 249","200","5","Unit 1A - Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,249.001,"------","***Sta 249:  Unit 1A - Crankcase Inspection\n--4/28/25 through 5/2/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-101475","***","2025-05-05","2025-05-09","Added",null,null,"Sta 249","200","5","Unit 2A - Engine Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,249.00200000000001,"------","***Sta 249:  Unit 2A - Engine Maintenance\n--5/5/25 through 5/9/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-86707","***","2025-04-22","2025-04-22","Added",null,null,"MLV 249 to MLV 250","200","5","Meter Station Filter Inspection (Wright SMS PIN: 412181)","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","412181 IROQUOIS/TG WRIGHT SMS SCHOHARIE",249.5,"------","***MLV 249 to MLV 250:  Meter Station Filter Inspection (Wright SMS PIN: 412181)\n--4/22/25:  This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n412181 IROQUOIS/TG WRIGHT SMS SCHOHARIE\n***Added\n………………………………"]
["X25-56501",null,"2025-05-01","2025-05-01",null,null,null,"Sta 254 Nassau","200","5","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,254,null,"Sta 254 Nassau:  Annual ESD Test\n--5/1/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-56505",null,"2025-04-30","2025-04-30",null,null,null,"Sta 254 Nassau","200","5","Filter Inspection","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,254.00001,null,"Sta 254 Nassau:  Filter Inspection\n--4/30/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-108566","***","2025-03-03","2025-03-07","Added",null,null,"Sta 254","200","5","Unit 1A - Replace Power Cylinder Heads","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,254.001,"------","***Sta 254:  Unit 1A - Replace Power Cylinder Heads\n--3/3/25 through 3/7/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-1017305","***","2025-01-24","2025-01-24","Completed",null,null,"MLV 259B-101 TO MLV 259B-102","200","6","Pig Runs - Cleaning / Gauge 1/24/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420130 YANK GAS/TGP WINSTED CT LITCHFIELD\n420131 YANK GAS/TGP TORRINGTON CT LITCHFIE",259.10000000000002,"------","***MLV 259B-101 TO MLV 259B-102:  Pig Runs - Cleaning / Gauge 1/24/25\n***Completed\nThe following meters are available for nominations:\n420130 YANK GAS/TGP WINSTED CT LITCHFIELD\n420131 YANK GAS/TGP TORRINGTON CT LITCHFIE"]
["X24-1017311","***","2025-01-25","2025-01-25","Completed",null,null,"MLV 259B-101 TO MLV 259B-102","200","6","Pig Runs - MFL-A / Cal / IMU Combo 1/25/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420130 YANK GAS/TGP WINSTED CT LITCHFIELD\n420131 YANK GAS/TGP TORRINGTON CT LITCHFIE",259.11,"------","***MLV 259B-101 TO MLV 259B-102:  Pig Runs - MFL-A / Cal / IMU Combo 1/25/25\n***Completed\nThe following meters are available for nominations:\n420130 YANK GAS/TGP WINSTED CT LITCHFIELD\n420131 YANK GAS/TGP TORRINGTON CT LITCHFIE"]
["X25-104698","***","2025-02-17","2025-02-18","Added",null,null,"Sta 260A","200","6","Solar Turbines Protective Devices","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,260,"------","***Sta 260A:  Solar Turbines Protective Devices\n--2/17/25 through 2/18/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-104697","***","2025-09-23","2025-09-23","Added",null,null,"Sta 260A Southwick","200","6","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,260,"------","***Sta 260A Southwick:  Annual ESD Test\n--9/23/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-82387","***","2025-04-14","2025-04-16","Added",null,null,"Sta 260A","200","6","Unit 1A - Gear Box Maintenance Activity","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,260.00099999999998,"------","***Sta 260A:  Unit 1A - Gear Box Maintenance Activity\n--4/14/25 through 4/16/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-1020199",null,"2025-07-15","2025-07-15",null,null,null,"MLV 260A-101.1 TO MLV 260A-103","200","6","Pig Runs - MFL-C 7/15/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420104 WESTFLD/TGP WESTFIELD MA HAMPDEN\n420401 HOLYOKE/TGP HOLYOKE MA 2 HAMPDEN\n420292 BERKSHR/TGP GREENFIELD MA HAMPSHIRE\n420106 EVRSRC/TGP GRANITE NORTHAMPTON MA H",260.11,null,"MLV 260A-101.1 TO MLV 260A-103:  Pig Runs - MFL-C 7/15/25\n--7/15/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420104 WESTFLD/TGP WESTFIELD MA HAMPDEN\n420401 HOLYOKE/TGP HOLYOKE MA 2 HAMPDEN\n420292 BERKSHR/TGP GREENFIELD MA HAMPSHIRE\n420106 EVRSRC/TGP GRANITE NORTHAMPTON MA H\n………………………………"]
["X25-104700","***","2025-02-19","2025-02-21","Added",null,null,"Sta 261","200","6","Solar Turbines Protective Devices","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420901 BERKPWR/TGP BERKSHIRE POWER SALES H",261,"------","***Sta 261:  Solar Turbines Protective Devices\n--2/19/25 through 2/21/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420901 BERKPWR/TGP BERKSHIRE POWER SALES H\n***Added\n………………………………"]
["X25-104695","***","2025-09-16","2025-09-18","Added",null,null,"Sta 261 Agawam","200","6","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420901 BERKPWR/TGP BERKSHIRE POWER SALES H",261,"------","***Sta 261 Agawam:  Annual ESD Test\n--9/16/25 through 9/18/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420901 BERKPWR/TGP BERKSHIRE POWER SALES H\n***Added\n………………………………"]
["X25-82384","***","2025-04-08","2025-04-09","Added",null,null,"Sta 261","200","6","Unit 5A - 4K Maintenance Activity and Water Wash","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,261.005,"------","***Sta 261:  Unit 5A - 4K Maintenance Activity and Water Wash\n--4/8/25 through 4/9/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-82379","***","2025-04-07","2025-04-08","Added",null,null,"Sta 261","200","6","Unit 1C - 4K Maintenance Activity and Water Wash","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,261.03300000000002,"------","***Sta 261:  Unit 1C - 4K Maintenance Activity and Water Wash\n--4/7/25 through 4/8/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-104693","***","2025-09-25","2025-09-25","Added",null,null,"Sta 264 Charlton","200","6","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,264,"------","***Sta 264 Charlton:  Annual ESD Test\n--9/25/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-520791",null,"2025-07-07","2025-07-25",null,null,null,"MLV 265E-103 to MLV 265E-104","200","6","Regulator Installation & Pipe replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420750 NARNGST/TGP CRANSTON SALES PROVIDEN\n420926 RISEC/TGP FPLE RISE PROVIDENCE\n55784 RHOBIO/TGP SCITUATE RNG REC PROVIDE\n55785 RHOBIO/TGP SCITUATE RNG BUYBACK PR\n420910 NARNGST/TGP SMITHFIELD DELIVERY PRO\n420758 NARNGST/TGP LINCOLN SMS PROVIDENCE",265.10000000000002,null,"MLV 265E-103 to MLV 265E-104:  Regulator Installation & Pipe replacement\n--7/7/25 through 7/25/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420750 NARNGST/TGP CRANSTON SALES PROVIDEN\n420926 RISEC/TGP FPLE RISE PROVIDENCE\n55784 RHOBIO/TGP SCITUATE RNG REC PROVIDE\n55785 RHOBIO/TGP SCITUATE RNG BUYBACK PR\n420910 NARNGST/TGP SMITHFIELD DELIVERY PRO\n420758 NARNGST/TGP LINCOLN SMS PROVIDENCE\n………………………………"]
["X24-1020284",null,"2025-12-10","2025-12-10",null,null,null,"MLV 265E-201 to MLV 265E-202","200","6","Pig Runs - Cleaning / Gauge 12/10/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420758 NARNGST/TGP LINCOLN SMS PROVIDENCE",265.2,null,"MLV 265E-201 to MLV 265E-202:  Pig Runs - Cleaning / Gauge 12/10/25\n--12/10/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420758 NARNGST/TGP LINCOLN SMS PROVIDENCE\n………………………………"]
["X24-1020336",null,"2025-12-10","2025-12-10",null,null,null,"MLV 265E-201 to MLV 265E-202","200","6","Pig Runs - MFL-A / Cal / IMU Combo 12/10/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420758 NARNGST/TGP LINCOLN SMS PROVIDENCE",265.20999999999998,null,"MLV 265E-201 to MLV 265E-202:  Pig Runs - MFL-A / Cal / IMU Combo 12/10/25\n--12/10/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420758 NARNGST/TGP LINCOLN SMS PROVIDENCE\n………………………………"]
["X24-1017320",null,"2025-03-18","2025-03-18",null,null,null,"MLV 266A-101L TO MLV 266A-101R","200","6","Pig Runs - Cleaning / Gauge 3/18/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420631 EVRSRC/TGP BROCKTON SALES WORCHESTE\n420894 DYNEGY/TGP BLACKSTONE WORCHESTER\n420285 AGT/TGP MENDON MASS TIE OVER WORCHE\n420424 HESS/TGP BELLINGHAM MA NORFOLK\n420135 NARNGST/TGP PAWTUCKET RI PROVIDENCE",266.10000000000002,null,"MLV 266A-101L TO MLV 266A-101R:  Pig Runs - Cleaning / Gauge 3/18/25\n--3/18/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420631 EVRSRC/TGP BROCKTON SALES WORCHESTE\n420894 DYNEGY/TGP BLACKSTONE WORCHESTER\n420285 AGT/TGP MENDON MASS TIE OVER WORCHE\n420424 HESS/TGP BELLINGHAM MA NORFOLK\n420135 NARNGST/TGP PAWTUCKET RI PROVIDENCE\n………………………………"]
["X24-1017325",null,"2025-03-19","2025-03-19",null,null,null,"MLV 266A-101L TO MLV 266A-101R","200","6","Pig Runs - MFL-A / Cal / IMU Combo 3/19/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420631 EVRSRC/TGP BROCKTON SALES WORCHESTE\n420894 DYNEGY/TGP BLACKSTONE WORCHESTER\n420285 AGT/TGP MENDON MASS TIE OVER WORCHE\n420424 HESS/TGP BELLINGHAM MA NORFOLK\n420135 NARNGST/TGP PAWTUCKET RI PROVIDENCE",266.11,null,"MLV 266A-101L TO MLV 266A-101R:  Pig Runs - MFL-A / Cal / IMU Combo 3/19/25\n--3/19/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420631 EVRSRC/TGP BROCKTON SALES WORCHESTE\n420894 DYNEGY/TGP BLACKSTONE WORCHESTER\n420285 AGT/TGP MENDON MASS TIE OVER WORCHE\n420424 HESS/TGP BELLINGHAM MA NORFOLK\n420135 NARNGST/TGP PAWTUCKET RI PROVIDENCE\n………………………………"]
["X24-1020233",null,"2025-07-22","2025-07-22",null,null,null,"MLV 266A-102A TO MLV 266A-104A","200","6","Pig Runs - Cleaning / Gauge 7/22/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420424 HESS/TGP BELLINGHAM MA NORFOLD\n420135 NARNGST/TGP PAWTUCKET RI PROVIDENCE",266.14,null,"MLV 266A-102A TO MLV 266A-104A:  Pig Runs - Cleaning / Gauge 7/22/25\n--7/22/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420424 HESS/TGP BELLINGHAM MA NORFOLD\n420135 NARNGST/TGP PAWTUCKET RI PROVIDENCE\n………………………………"]
["X24-1020268",null,"2025-07-23","2025-07-23",null,null,null,"MLV 266A-102A TO MLV 266A-104A","200","6","Pig Runs - MFL-A / Cal / IMU Combo 7/23/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420424 HESS/TGP BELLINGHAM MA NORFOLD\n420135 NARNGST/TGP PAWTUCKET RI PROVIDENCE",266.14999999999998,null,"MLV 266A-102A TO MLV 266A-104A:  Pig Runs - MFL-A / Cal / IMU Combo 7/23/25\n--7/23/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420424 HESS/TGP BELLINGHAM MA NORFOLD\n420135 NARNGST/TGP PAWTUCKET RI PROVIDENCE\n………………………………"]
["X24-1017329",null,"2025-03-25","2025-03-25",null,null,null,"MLV 266C-101.1 TO MLV 266C-102A","200","6","Pig Runs - Cleaning / Gauge 3/25/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420631 EVRSRC/TGP BROCKTON SALES WORCHESTE\n420894 DYNEGY/TGP BLACKSTONE WORCHESTER\n420285 AGT/TGP MENDON MASS TIE OVER WORCHE\n420424 HESS/TGP BELLINGHAM MA NORFOLK\n420135 NARNGST/TGP PAWTUCKET RI PROVIDENCE",266.2,null,"MLV 266C-101.1 TO MLV 266C-102A:  Pig Runs - Cleaning / Gauge 3/25/25\n--3/25/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420631 EVRSRC/TGP BROCKTON SALES WORCHESTE\n420894 DYNEGY/TGP BLACKSTONE WORCHESTER\n420285 AGT/TGP MENDON MASS TIE OVER WORCHE\n420424 HESS/TGP BELLINGHAM MA NORFOLK\n420135 NARNGST/TGP PAWTUCKET RI PROVIDENCE\n………………………………"]
["X24-1017332",null,"2025-03-26","2025-03-26",null,null,null,"MLV 266C-101.1 TO MLV 266C-102A","200","6","Pig Runs - MFL-A/Cal/IMU Combo 3/26/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420631 EVRSRC/TGP BROCKTON SALES WORCHESTE\n420894 DYNEGY/TGP BLACKSTONE WORCHESTER\n420285 AGT/TGP MENDON MASS TIE OVER WORCHE\n420424 HESS/TGP BELLINGHAM MA NORFOLK\n420135 NARNGST/TGP PAWTUCKET RI PROVIDENCE",266.20999999999998,null,"MLV 266C-101.1 TO MLV 266C-102A:  Pig Runs - MFL-A/Cal/IMU Combo 3/26/25\n--3/26/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420631 EVRSRC/TGP BROCKTON SALES WORCHESTE\n420894 DYNEGY/TGP BLACKSTONE WORCHESTER\n420285 AGT/TGP MENDON MASS TIE OVER WORCHE\n420424 HESS/TGP BELLINGHAM MA NORFOLK\n420135 NARNGST/TGP PAWTUCKET RI PROVIDENCE\n………………………………"]
["X24-1017338",null,"2025-04-01","2025-04-01",null,null,null,"MLV 267-2 TO MLV 273-2A","200","6","Pig Runs - Cleaning / Gauge 4/1/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","421035 NSTAR/TGP ROUTE 9 FRAMINGHAM MIDDLE\n420611 BOSTN/TGP ACTON SALES MIDDLESEX\n412538 MARITIME/TGP DRACUT MIDDLESEX\n420572 BOSTN/TGP DRACUT MA MIDDLESEX",267.2,null,"MLV 267-2 TO MLV 273-2A:  Pig Runs - Cleaning / Gauge 4/1/25\n--4/1/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n421035 NSTAR/TGP ROUTE 9 FRAMINGHAM MIDDLE\n420611 BOSTN/TGP ACTON SALES MIDDLESEX\n412538 MARITIME/TGP DRACUT MIDDLESEX\n420572 BOSTN/TGP DRACUT MA MIDDLESEX\n………………………………"]
["X24-1017342",null,"2025-04-02","2025-04-02",null,null,null,"MLV 267-2 TO MLV 273-2A","200","6","Pig Runs - MFL-A / Cal / IMU Combo 4/2/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","421035 NSTAR/TGP ROUTE 9 FRAMINGHAM MIDDLE\n420611 BOSTN/TGP ACTON SALES MIDDLESEX\n412538 MARITIME/TGP DRACUT MIDDLESEX\n420572 BOSTN/TGP DRACUT MA MIDDLESEX",267.20999999999998,null,"MLV 267-2 TO MLV 273-2A:  Pig Runs - MFL-A / Cal / IMU Combo 4/2/25\n--4/2/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n421035 NSTAR/TGP ROUTE 9 FRAMINGHAM MIDDLE\n420611 BOSTN/TGP ACTON SALES MIDDLESEX\n412538 MARITIME/TGP DRACUT MIDDLESEX\n420572 BOSTN/TGP DRACUT MA MIDDLESEX\n………………………………"]
["X24-1020346",null,"2025-12-18","2025-12-18",null,null,null,"MLV 268A-301A TO MLV 268A-302","200","6","Pig Runs - Cleaning / Gauge 12/18/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420111 BOSTN/TGP LEOMINSTER MA WORCHESTER",268.3,null,"MLV 268A-301A TO MLV 268A-302:  Pig Runs - Cleaning / Gauge 12/18/25\n--12/18/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420111 BOSTN/TGP LEOMINSTER MA WORCHESTER\n………………………………"]
["X24-1020369",null,"2025-12-18","2025-12-18",null,null,null,"MLV 268A-301A TO MLV 268A-302","200","6","Pig Runs - MFL-A / Cal / IMU Combo 12/18/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420111 BOSTN/TGP LEOMINSTER MA WORCHESTER",268.31,null,"MLV 268A-301A TO MLV 268A-302:  Pig Runs - MFL-A / Cal / IMU Combo 12/18/25\n--12/18/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420111 BOSTN/TGP LEOMINSTER MA WORCHESTER\n………………………………"]
["X24-1017314","***","2025-01-28","2025-01-28","Completed",null,null,"MLV 270B-103 TO MLV 270B-104","200","6","Pig Runs - Cleaning / Gauge 1/28/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420132 LIBERTYU/TGP NASHUA NH HILLSBOROUGH\n420931 LIBERTYU/TGP GRANITE RIDGE ROCKINGH\n420632 LIBERTYU/TGP LONDONDERRY SALES ROCK\n420133 LIBERTYU/TGP MANCHESTER NH HILLSBOR\n420254 LIBERTYU/TGP HOOKSETT NH MERRIMACK\n420451 LIBERTYU/TGP SUNCOOK NH MERRIMACK\n47591 CLEANNRG/TGP TOWN OF PEMBROKE MERRI\n49831 NG ADVAN/TGP CNG PEMBROKE RECEIPT M\n420426 LIBERTYU/TGP LACONIA NH MERRIMACK",270.10000000000002,"------","***MLV 270B-103 TO MLV 270B-104:  Pig Runs - Cleaning / Gauge 1/28/25\n***Completed\nThe following meters are available for nominations:\n420132 LIBERTYU/TGP NASHUA NH HILLSBOROUGH\n420931 LIBERTYU/TGP GRANITE RIDGE ROCKINGH\n420632 LIBERTYU/TGP LONDONDERRY SALES ROCK\n420133 LIBERTYU/TGP MANCHESTER NH HILLSBOR\n420254 LIBERTYU/TGP HOOKSETT NH MERRIMACK\n420451 LIBERTYU/TGP SUNCOOK NH MERRIMACK\n47591 CLEANNRG/TGP TOWN OF PEMBROKE MERRI\n49831 NG ADVAN/TGP CNG PEMBROKE RECEIPT M\n420426 LIBERTYU/TGP LACONIA NH MERRIMACK"]
["X24-847658","***","2025-04-07","2025-04-18","Project Change","2025-01-06","2025-01-27","MLV 270C-103 to MLV 270C-104","200","6","Meter Station Upgrade (Meter Peabody PIN 420658)","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420658 MMWEC/TGP PEABODY SALES ESSEX",270.10000000000002,"--start_date--end_date------------model_loc--","***MLV 270C-103 to MLV 270C-104:  Meter Station Upgrade (Meter Peabody PIN 420658)\n--4/7/25 through 4/18/25:  This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420658 MMWEC/TGP PEABODY SALES ESSEX\n***\nDate Change, Previously scheduled 1/6/25 to 1/27/25.\n………………………………"]
["X24-1017318","***","2025-01-29","2025-01-29","Completed",null,null,"MLV 270B-103 TO MLV 270B-104","200","6","Pig Runs - MFL-A / Cal / IMU Combo 1/29/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420132 LIBERTYU/TGP NASHUA NH HILLSBOROUGH\n420931 LIBERTYU/TGP GRANITE RIDGE ROCKINGH\n420632 LIBERTYU/TGP LONDONDERRY SALES ROCK\n420133 LIBERTYU/TGP MANCHESTER NH HILLSBOR\n420254 LIBERTYU/TGP HOOKSETT NH MERRIMACK\n420451 LIBERTYU/TGP SUNCOOK NH MERRIMACK\n47591 CLEANNRG/TGP TOWN OF PEMBROKE MERRI\n49831 NG ADVAN/TGP CNG PEMBROKE RECEIPT M\n420426 LIBERTYU/TGP LACONIA NH MERRIMACK",270.11,"------","***MLV 270B-103 TO MLV 270B-104:  Pig Runs - MFL-A / Cal / IMU Combo 1/29/25\n***Completed\nThe following meters are available for nominations:\n420132 LIBERTYU/TGP NASHUA NH HILLSBOROUGH\n420931 LIBERTYU/TGP GRANITE RIDGE ROCKINGH\n420632 LIBERTYU/TGP LONDONDERRY SALES ROCK\n420133 LIBERTYU/TGP MANCHESTER NH HILLSBOR\n420254 LIBERTYU/TGP HOOKSETT NH MERRIMACK\n420451 LIBERTYU/TGP SUNCOOK NH MERRIMACK\n47591 CLEANNRG/TGP TOWN OF PEMBROKE MERRI\n49831 NG ADVAN/TGP CNG PEMBROKE RECEIPT M\n420426 LIBERTYU/TGP LACONIA NH MERRIMACK"]
["X24-1017379",null,"2025-06-03","2025-06-03",null,null,null,"MLV 270B-101.1 TO MLV 270B-103","200","6","Pig Runs - Cleaning / Gauge 6/3/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","421025 EVRSRC/TG WYETH GII ESSEX",270.14,null,"MLV 270B-101.1 TO MLV 270B-103:  Pig Runs - Cleaning / Gauge 6/3/25\n--6/3/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n421025 EVRSRC/TG WYETH GII ESSEX\n………………………………"]
["X24-1017377",null,"2025-06-04","2025-06-04",null,null,null,"MLV 270B-101.1 TO MLV 270B-103","200","6","Pig Runs - MFL-C / Cal / IMU Combo 6/4/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","421025 EVRSRC/TG WYETH GII ESSEX",270.14999999999998,null,"MLV 270B-101.1 TO MLV 270B-103:  Pig Runs - MFL-C / Cal / IMU Combo 6/4/25\n--6/4/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n421025 EVRSRC/TG WYETH GII ESSEX\n………………………………"]
["X24-1017380",null,"2025-06-10","2025-06-10",null,null,null,"MLV 270B-104B TO MLV 270B-105A","200","6","Pig Runs - Cleaning / Gauge 6/10/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420132 LIBERTYU/TGP NASHUA NH HILLSBOROUGH\n420931 LIBERTYU/GTGP GRANITE RIDGE ROCKINGH\n420632 LIBERTYU/TGP LONDONDERRY SALES ROCK\n420133 LIBERTYU/TGP MANCHESTER NH HILLSBOR\n420254 LIBERTYU/TGP HOOKSETT NH MERRIMACK\n420451 LIBERTYU/TGP SUNCOOK NH MERRIMACK\n47591 CLEANNRG/TGP TOWN OF PEMBROKE MERRI\n49831 NG ADVAN/TGP CNG PEMBROKE RECEIPT M\n420426 LIBERTYU/TGP LACONIA NH MERRIMACK",270.16000000000003,null,"MLV 270B-104B TO MLV 270B-105A:  Pig Runs - Cleaning / Gauge 6/10/25\n--6/10/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420132 LIBERTYU/TGP NASHUA NH HILLSBOROUGH\n420931 LIBERTYU/GTGP GRANITE RIDGE ROCKINGH\n420632 LIBERTYU/TGP LONDONDERRY SALES ROCK\n420133 LIBERTYU/TGP MANCHESTER NH HILLSBOR\n420254 LIBERTYU/TGP HOOKSETT NH MERRIMACK\n420451 LIBERTYU/TGP SUNCOOK NH MERRIMACK\n47591 CLEANNRG/TGP TOWN OF PEMBROKE MERRI\n49831 NG ADVAN/TGP CNG PEMBROKE RECEIPT M\n420426 LIBERTYU/TGP LACONIA NH MERRIMACK\n………………………………"]
["X24-1017381",null,"2025-06-11","2025-06-11",null,null,null,"MLV 270B-104B TO MLV 270B-105A","200","6","Pig Runs - Cal / IMU 6/11/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420132 LIBERTYU/TGP NASHUA NH HILLSBOROUGH\n420931 LIBERTYU/GTGP GRANITE RIDGE ROCKINGH\n420632 LIBERTYU/TGP LONDONDERRY SALES ROCK\n420133 LIBERTYU/TGP MANCHESTER NH HILLSBOR\n420254 LIBERTYU/TGP HOOKSETT NH MERRIMACK\n420451 LIBERTYU/TGP SUNCOOK NH MERRIMACK\n47591 CLEANNRG/TGP TOWN OF PEMBROKE MERRI\n49831 NG ADVAN/TGP CNG PEMBROKE RECEIPT M\n420426 LIBERTYU/TGP LACONIA NH MERRIMACK",270.17,null,"MLV 270B-104B TO MLV 270B-105A:  Pig Runs - Cal / IMU 6/11/25\n--6/11/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420132 LIBERTYU/TGP NASHUA NH HILLSBOROUGH\n420931 LIBERTYU/GTGP GRANITE RIDGE ROCKINGH\n420632 LIBERTYU/TGP LONDONDERRY SALES ROCK\n420133 LIBERTYU/TGP MANCHESTER NH HILLSBOR\n420254 LIBERTYU/TGP HOOKSETT NH MERRIMACK\n420451 LIBERTYU/TGP SUNCOOK NH MERRIMACK\n47591 CLEANNRG/TGP TOWN OF PEMBROKE MERRI\n49831 NG ADVAN/TGP CNG PEMBROKE RECEIPT M\n420426 LIBERTYU/TGP LACONIA NH MERRIMACK\n………………………………"]
["X25-77460",null,"2025-06-11","2025-06-11",null,null,null,"MLV 270B-104B TO MLV 270B-105A","200","6","Pig Runs - MFL-C 6/11/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420132 LIBERTYU/TGP NASHUA NH HILLSBOROUGH\n420931 LIBERTYU/GTGP GRANITE RIDGE ROCKINGH\n420632 LIBERTYU/TGP LONDONDERRY SALES ROCK\n420133 LIBERTYU/TGP MANCHESTER NH HILLSBOR\n420254 LIBERTYU/TGP HOOKSETT NH MERRIMACK\n420451 LIBERTYU/TGP SUNCOOK NH MERRIMACK\n47591 CLEANNRG/TGP TOWN OF PEMBROKE MERRI\n49831 NG ADVAN/TGP CNG PEMBROKE RECEIPT M\n420426 LIBERTYU/TGP LACONIA NH MERRIMACK",270.17500000000001,null,"MLV 270B-104B TO MLV 270B-105A:  Pig Runs - MFL-C 6/11/25\n--6/11/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420132 LIBERTYU/TGP NASHUA NH HILLSBOROUGH\n420931 LIBERTYU/GTGP GRANITE RIDGE ROCKINGH\n420632 LIBERTYU/TGP LONDONDERRY SALES ROCK\n420133 LIBERTYU/TGP MANCHESTER NH HILLSBOR\n420254 LIBERTYU/TGP HOOKSETT NH MERRIMACK\n420451 LIBERTYU/TGP SUNCOOK NH MERRIMACK\n47591 CLEANNRG/TGP TOWN OF PEMBROKE MERRI\n49831 NG ADVAN/TGP CNG PEMBROKE RECEIPT M\n420426 LIBERTYU/TGP LACONIA NH MERRIMACK\n………………………………"]
["X24-1020093",null,"2025-06-17","2025-06-17",null,null,null,"MLV 270B-105B TO MLV 270B-106","200","6","Pig Runs - Cleaning / Gauge 6/17/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420132 LIBERTYU/TGP NASHUA NH HILLSBOROUGH\n420931 LIBERTYU/TGP GRANITE RIDGE ROCKINGH\n420632 LIBERTYU/TGP LONDONDERRY SALES ROCK\n420133 LIBERTYU/TGP MANCHESTER NH HILLSBOR\n420254 LIBERTYU/TGP HOOKSETT NH MERRIMACK\n420451 LIBERTYU/TGP SUNCOOK NH MERRIMACK\n47591 CLEANNRG/TGP TOWN OF PEMBROKE MERRI\n49831 NG ADVAN/TGP CNG PEMBROKE RECEIPT M\n420426 LIBERTYU/TGP LACONIA NH MERRIMACK",270.18,null,"MLV 270B-105B TO MLV 270B-106:  Pig Runs - Cleaning / Gauge 6/17/25\n--6/17/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420132 LIBERTYU/TGP NASHUA NH HILLSBOROUGH\n420931 LIBERTYU/TGP GRANITE RIDGE ROCKINGH\n420632 LIBERTYU/TGP LONDONDERRY SALES ROCK\n420133 LIBERTYU/TGP MANCHESTER NH HILLSBOR\n420254 LIBERTYU/TGP HOOKSETT NH MERRIMACK\n420451 LIBERTYU/TGP SUNCOOK NH MERRIMACK\n47591 CLEANNRG/TGP TOWN OF PEMBROKE MERRI\n49831 NG ADVAN/TGP CNG PEMBROKE RECEIPT M\n420426 LIBERTYU/TGP LACONIA NH MERRIMACK\n………………………………"]
["X24-1020155",null,"2025-06-18","2025-06-18",null,null,null,"MLV 270B-105B TO MLV 270B-106","200","6","Pig Runs - MFL-A / Cal /IMU Combo 6/18/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420132 LIBERTYU/TGP NASHUA NH HILLSBOROUGH\n420931 LIBERTYU/TGP GRANITE RIDGE ROCKINGH\n420632 LIBERTYU/TGP LONDONDERRY SALES ROCK\n420133 LIBERTYU/TGP MANCHESTER NH HILLSBOR\n420254 LIBERTYU/TGP HOOKSETT NH MERRIMACK\n420451 LIBERTYU/TGP SUNCOOK NH MERRIMACK\n47591 CLEANNRG/TGP TOWN OF PEMBROKE MERRI\n49831 NG ADVAN/TGP CNG PEMBROKE RECEIPT M\n420426 LIBERTYU/TGP LACONIA NH MERRIMACK",270.19,null,"MLV 270B-105B TO MLV 270B-106:  Pig Runs - MFL-A / Cal /IMU Combo 6/18/25\n--6/18/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420132 LIBERTYU/TGP NASHUA NH HILLSBOROUGH\n420931 LIBERTYU/TGP GRANITE RIDGE ROCKINGH\n420632 LIBERTYU/TGP LONDONDERRY SALES ROCK\n420133 LIBERTYU/TGP MANCHESTER NH HILLSBOR\n420254 LIBERTYU/TGP HOOKSETT NH MERRIMACK\n420451 LIBERTYU/TGP SUNCOOK NH MERRIMACK\n47591 CLEANNRG/TGP TOWN OF PEMBROKE MERRI\n49831 NG ADVAN/TGP CNG PEMBROKE RECEIPT M\n420426 LIBERTYU/TGP LACONIA NH MERRIMACK\n………………………………"]
["X25-108514","***","2025-03-17","2025-03-29","Added",null,null,"MLV 270C-303","200","6","ECDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,270.3,"------","***MLV 270C-303:  ECDA\n--3/17/25 through 3/29/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-56456","***","2025-01-28","2025-01-28","Completed",null,null,"Sta 307","300","4","Station Generator Swap","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,307,"------","***Sta 307:  Station Generator Swap\n***Completed"]
["X24-1090163",null,"2025-09-15","2025-10-18",null,null,null,"Sta 315 Wellsboro","300","4","Station Blowdown Silencer","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,315,null,"Sta 315 Wellsboro:  Station Blowdown Silencer\n--9/15/25 through 10/18/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-82234","***","2025-04-07","2025-04-07","Project Change","2025-04-14","2025-04-14","MLV 319-2 TO MLV 321-2","300","4","Pig Runs - Cleaning / Gauge 4/7/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,319.2,"--start_date--end_date------mantenance_desc------model_loc--","***MLV 319-2 TO MLV 321-2:  Pig Runs - Cleaning / Gauge 4/7/25\n--4/7/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 4/14/25.\n………………………………"]
["X25-82237","***","2025-04-09","2025-04-09","Project Change","2025-04-16","2025-04-16","MLV 319-2 TO MLV 321-2","300","4","Pig Runs - Caliper & MFL-A Combo 4/9/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,319.20999999999998,"--start_date--end_date------mantenance_desc------model_loc--","***MLV 319-2 TO MLV 321-2:  Pig Runs - Caliper & MFL-A Combo 4/9/25\n--4/9/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 4/16/25.\n………………………………"]
["X24-1151725",null,"2025-04-14","2025-04-16",null,null,null,"Sta 323","300","5","Electric Company Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations","SOP","Potential out of path restrictions may be at risk.",null,323,null,"Sta 323:  Electric Company Maintenance\n--4/14/25 through 4/16/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1135143","***","2025-01-24","2025-01-24","Completed",null,null,"MLV 400-1 to MLV 409-1","400","0","Pig Run - EMAT 1/23/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","412733  UES/TGP MYRICK BROOKS\n55152   TGP/KMTEJAS KING RANCH EXCH #2 ROLL\n412400  LOBO/TGP KING RANCH JIM WELLS\n410633\tGCENGY/TGP EL EBANITO DEHY STARR\n410729\tKMTEJAS/TGP ZIM DEHYDRATION STARR\n412088\tETP/TGP MONTE CHRISTO EXCH HIDALGO\n412683\tHESCO CO/TGP RAYMONDVILLE HIDALGO\n420878\tGGUC/TGP RINCON DEHYD STARR\n412458\tETP/TGP GILMORE PLANT RESIDUE HIDAL",400.14,"------","***MLV 400-1 to MLV 409-1:  Pig Run - EMAT 1/23/25\n***Completed\nThe following meters are available for nominations:\n412733  UES/TGP MYRICK BROOKS\n55152   TGP/KMTEJAS KING RANCH EXCH #2 ROLL\n412400  LOBO/TGP KING RANCH JIM WELLS\n410633\tGCENGY/TGP EL EBANITO DEHY STARR\n410729\tKMTEJAS/TGP ZIM DEHYDRATION STARR\n412088\tETP/TGP MONTE CHRISTO EXCH HIDALGO\n412683\tHESCO CO/TGP RAYMONDVILLE HIDALGO\n420878\tGGUC/TGP RINCON DEHYD STARR\n412458\tETP/TGP GILMORE PLANT RESIDUE HIDAL"]
["X24-1370477",null,"2025-02-24","2025-03-17",null,null,null,"Sta 409","400","0","Unit 1A - Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,409.00099999999998,null,"Sta 409:  Unit 1A - Maintenance\n--2/24/25 through 3/17/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-53659",null,"2025-04-01","2025-04-01",null,null,null,"MLV 409A-901 to MLV 409A-902","400","L","Pig Run - Cleaning 4/1/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,409.1,null,"MLV 409A-901 to MLV 409A-902:  Pig Run - Cleaning 4/1/25\n--4/1/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-82098",null,"2025-09-09","2025-09-26",null,null,null,"MLV 409A-101 to MLV 409A-103","400","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,409.1,null,"MLV 409A-101 to MLV 409A-103:  Anomaly Remediation\n--9/9/25 through 9/26/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-53665",null,"2025-04-02","2025-04-02",null,null,null,"MLV 409A-901 to MLV 409A-902","400","0","Pig Run - Cleaning 4/2/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,409.11,null,"MLV 409A-901 to MLV 409A-902:  Pig Run - Cleaning 4/2/25\n--4/2/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-53666",null,"2025-04-03","2025-04-03",null,null,null,"MLV 409A-901 to MLV 409A-902","400","0","Pig Run - MFL-A 4/3/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,409.12,null,"MLV 409A-901 to MLV 409A-902:  Pig Run - MFL-A 4/3/25\n--4/3/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-59730","***","2025-04-14","2025-04-26","Project Change","2025-06-02","2025-06-13","MLV 525-2 to MLV 527-2","500","L","Pipeline Tie-In (Muskrat)","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","PIP","Potential in the path restrictions may be at risk.","55833     VG GATOR/TGP EVANGELINE PASS DELIVE\n412658   EXTEX/TGP FLEUR PLAQUEMINES",525.20000000000005,"--start_date--end_date------------model_loc--","***MLV 525-2 to MLV 527-2:  Pipeline Tie-In (Muskrat)\n--4/14/25 through 4/26/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential in the path restrictions may be at risk.\n55833     VG GATOR/TGP EVANGELINE PASS DELIVE\n412658   EXTEX/TGP FLEUR PLAQUEMINES\n***\nDate Change, Previously scheduled 6/2/25 to 6/13/25.\n………………………………"]
["X24-1063651","***","2025-04-14","2025-04-26","Project Change","2025-06-02","2025-06-13","MLV 525-2 to MLV 527-2","500","L","Pipeline Tie-In (500 Line)","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","PIP","Potential in the path restrictions may be at risk.","55833     VG GATOR/TGP EVANGELINE PASS DELIVE\n412658   EXTEX/TGP FLEUR PLAQUEMINES",525.21,"--start_date--end_date------------model_loc--","***MLV 525-2 to MLV 527-2:  Pipeline Tie-In (500 Line)\n--4/14/25 through 4/26/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential in the path restrictions may be at risk.\n55833     VG GATOR/TGP EVANGELINE PASS DELIVE\n412658   EXTEX/TGP FLEUR PLAQUEMINES\n***\nDate Change, Previously scheduled 6/2/25 to 6/13/25.\n………………………………"]
["X25-108466","***","2025-04-01","2025-04-06","Added",null,null,"MLV 534-1 to MLV 535-1","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,534.1,"------","***MLV 534-1 to MLV 535-1:  Anomaly Remediation\n--4/1/25 through 4/6/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-40668","***","2025-03-21","2025-03-29","Project Change","2025-03-10","2025-03-21","MLV 535-1 to MLV 536-1","500","1","Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,535.1,"--start_date--end_date------------model_loc--","***MLV 535-1 to MLV 536-1:  Anomaly Remediation\n--3/21/25 through 3/29/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 3/10/25 to 3/21/25.\n………………………………"]
["X25-108467","***","2025-03-14","2025-03-20","Added",null,null,"MLV 536-1 to MLV 537-1","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420714 CPTENTEX/TGP LAUREL SALES JONES\n420726 CPTENTEX/TGP LAUREL SALES 2 JONES",536.1,"------","***MLV 536-1 to MLV 537-1:  Anomaly Remediation\n--3/14/25 through 3/20/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420714 CPTENTEX/TGP LAUREL SALES JONES\n420726 CPTENTEX/TGP LAUREL SALES 2 JONES\n***Added\n………………………………"]
["X25-108468","***","2025-03-11","2025-03-13","Added",null,null,"MLV 537-1 to MLV 538-1","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,537.1,"------","***MLV 537-1 to MLV 538-1:  Anomaly Remediation\n--3/11/25 through 3/13/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-94907",null,"2024-02-12","2025-03-31",null,null,null,"Sta 542","500","1","Unit 3A - Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,542.00300000000004,null,"Sta 542:  Unit 3A - Overhaul\n--2/12/24 through 3/31/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1146507","***","2024-10-22","2025-02-28","Project Change",null,null,"Sta 546","500","1","Unit 7A - Crosshead Bushing / Oil Pump","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,546.00699999999995,"----------mantenance_desc------model_loc--","***Sta 546:  Unit 7A - Crosshead Bushing / Oil Pump\n--10/22/24 through 2/28/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Project Change\n………………………………"]
["X24-850681",null,"2025-03-03","2025-04-18",null,null,null,"Sta 546","500","1","Unit 1B - Turbine Exchange","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,546.01700000000005,null,"Sta 546:  Unit 1B - Turbine Exchange\n--3/3/25 through 4/18/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1034292",null,"2025-03-04","2025-03-04",null,null,null,"MLV 546G-1BL to MLV 546G-102","500","1","Pig Run - Cleaning / Gauge 3/4/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","421003 CAL GEN/TGP LOWNDES",546.1,null,"MLV 546G-1BL to MLV 546G-102:  Pig Run - Cleaning / Gauge 3/4/25\n--3/4/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n421003 CAL GEN/TGP LOWNDES\n………………………………"]
["X24-1034312",null,"2025-03-05","2025-03-05",null,null,null,"MLV 546G-1BL to MLV 546G-102","500","1","Pig Run - MFL-A 3/5/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","421003 CAL GEN/TGP LOWNDES",546.11,null,"MLV 546G-1BL to MLV 546G-102:  Pig Run - MFL-A 3/5/25\n--3/5/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n421003 CAL GEN/TGP LOWNDES\n………………………………"]
["X24-1174317","***","2025-06-16","2025-06-16","Project Change","2025-04-07","2025-04-07","MLV 550-2 TO MLV 546-2","500","1","Pig Runs - Cleaning / Gauge 6/16/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,546.20000000000005,"--start_date--end_date------mantenance_desc------model_loc--","***MLV 550-2 TO MLV 546-2:  Pig Runs - Cleaning / Gauge 6/16/25\n--6/16/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 4/7/25.\n………………………………"]
["X24-1174494","***","2025-06-18","2025-06-18","Project Change","2025-04-09","2025-04-09","MLV 550-2 TO MLV 546-2","500","1","Pig Runs - AFD 6/18/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,546.21,"--start_date--end_date------mantenance_desc------model_loc--","***MLV 550-2 TO MLV 546-2:  Pig Runs - AFD 6/18/25\n--6/18/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 4/9/25.\n………………………………"]
["X24-1174541","***","2025-06-20","2025-06-20","Project Change","2025-04-11","2025-04-11","MLV 550-2 TO MLV 546-2","500","1","Pig Runs - EMAT 6/20/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,546.22,"--start_date--end_date------mantenance_desc------model_loc--","***MLV 550-2 TO MLV 546-2:  Pig Runs - EMAT 6/20/25\n--6/20/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 4/11/25.\n………………………………"]
["X24-1368175",null,"2025-11-11","2025-11-15",null,null,null,"Sta 550 Hamilton","500","1","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,550,null,"Sta 550 Hamilton:  Annual ESD Test & Maintenance\n--11/11/25 through 11/15/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368176",null,"2025-11-10","2025-11-14",null,null,null,"Sta 550","100","1","A building - Replace SLC 500 Remote PLC","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,550.1,null,"Sta 550:  A building - Replace SLC 500 Remote PLC\n--11/10/25 through 11/14/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-123641","***","2025-01-30","TBD","Added",null,null,"MLV 551-1 to 552-1","500","1","PHMSA Immediate Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,551.1,"------","***MLV 551-1 to 552-1:  PHMSA Immediate Anomaly Remediation\n--1/30/25 through 3/2/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-1368191",null,"2025-09-08","2025-09-12",null,null,null,"Sta 555 Collinwood","500","1","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,555,null,"Sta 555 Collinwood:  Annual ESD Test & Maintenance\n--9/8/25 through 9/12/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-484573","***","2024-09-03","2025-01-24","Completed",null,null,"Sta 555","500","1","Unit 4A - Foundation Regrout","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,555.00400000000002,"------","***Sta 555:  Unit 4A - Foundation Regrout\n***Completed"]
["X25-59799","***","2025-01-25","2025-03-18","Project Change",null,"2025-03-07","Sta 555","500","1","Unit 4A - Compressor Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,555.00409999999999,"----end_date------------model_loc--","***Sta 555:  Unit 4A - Compressor Overhaul\n--1/25/25 through 3/18/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 1/25/25 to 3/7/25.\n………………………………"]
["X24-1178877",null,"2025-03-18","2025-03-18",null,null,null,"MLV 560-3 TO MLV 559-3","500","1","Pig Runs - Cleaning / Gauge 3/18/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,559.29999999999995,null,"MLV 560-3 TO MLV 559-3:  Pig Runs - Cleaning / Gauge 3/18/25\n--3/18/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1178947",null,"2025-03-19","2025-03-19",null,null,null,"MLV 560-3 TO MLV 559-3","500","1","Pig Runs - MFL-A 3/19/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,559.30999999999995,null,"MLV 560-3 TO MLV 559-3:  Pig Runs - MFL-A 3/19/25\n--3/19/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-296276","***","2024-11-04","2025-02-17","Project Change",null,"2025-01-31","MLV 560-1 to MLV 561-1","500","1","Class Change","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,560.1,"----end_date------------model_loc--","***MLV 560-1 to MLV 561-1:  Class Change\n--11/4/24 through 2/17/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***\nDate Change, Previously scheduled 11/4/24 to 1/31/25.\n………………………………"]
["X25-101525","***","2025-03-24","2025-03-27","Added",null,null,"Sta 563","500","1","Quarterly Safety Checks","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,563,"------","***Sta 563:  Quarterly Safety Checks\n--3/24/25 through 3/27/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-1368204",null,"2025-06-16","2025-06-16",null,null,null,"Sta 563 Joelton","500","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,563,null,"Sta 563 Joelton:  Annual ESD Test\n--6/16/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368205",null,"2025-06-16","2025-06-19",null,null,null,"Sta 563 Joelton","100","1","Fuel Gas Filter Changeout","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,563.00009999999997,null,"Sta 563 Joelton:  Fuel Gas Filter Changeout\n--6/16/25 through 6/19/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368207",null,"2025-06-16","2025-06-16",null,null,null,"Sta 563 Joelton","500","1","Unit 2A - 4K/8K Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,563.00199999999995,null,"Sta 563 Joelton:  Unit 2A - 4K/8K Inspection\n--6/16/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-658715",null,"2025-03-10","2025-03-17",null,null,null,"MLV 564-2","500","2","Valve Repair","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,564.20000000000005,null,"MLV 564-2:  Valve Repair\n--3/10/25 through 3/17/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-1178739",null,"2025-04-21","2025-04-21",null,null,null,"MLV 565-1 TO MLV 559-1","500","1","Pig Runs - Cleaning / Gauge 4/21/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,565.1,null,"MLV 565-1 TO MLV 559-1:  Pig Runs - Cleaning / Gauge 4/21/25\n--4/21/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1178795",null,"2025-04-23","2025-04-23",null,null,null,"MLV 565-1 TO MLV 559-1","500","1","Pig Runs - Caliper 4/23/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,565.11,null,"MLV 565-1 TO MLV 559-1:  Pig Runs - Caliper 4/23/25\n--4/23/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1178816",null,"2025-04-25","2025-04-25",null,null,null,"MLV 565-1 TO MLV 559-1","500","1","Pig Runs - AFD 4/25/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,565.12,null,"MLV 565-1 TO MLV 559-1:  Pig Runs - AFD 4/25/25\n--4/25/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1178843",null,"2025-04-29","2025-04-29",null,null,null,"MLV 565-1 TO MLV 559-1","500","1","Pig Runs - EMAT 4/29/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,565.13,null,"MLV 565-1 TO MLV 559-1:  Pig Runs - EMAT 4/29/25\n--4/29/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-86682","***","2025-05-01","2025-05-01","Added",null,null,"MLV 565-1 TO MLV 559-1","500","1","Pig Runs - Residual 5/1/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,565.14,"------","***MLV 565-1 TO MLV 559-1:  Pig Runs - Residual 5/1/25\n--5/1/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-1177017","***","2025-02-17","2025-02-17","Project Change","2025-02-12","2025-02-12","MLV 565-2 TO MLV 559-2","500","1","Pig Runs - Cleaning / Gauge 2/17/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,565.20000000000005,"--start_date--end_date------mantenance_desc------model_loc--","***MLV 565-2 TO MLV 559-2:  Pig Runs - Cleaning / Gauge 2/17/25\n--2/17/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 2/12/25.\n………………………………"]
["X24-1177069","***","2025-02-19","2025-02-19","Project Change","2025-02-18","2025-02-18","MLV 565-2 TO MLV 559-2","500","1","Pig Runs - CLP 2/19/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,565.21,"--start_date--end_date------mantenance_desc------model_loc--","***MLV 565-2 TO MLV 559-2:  Pig Runs - CLP 2/19/25\n--2/19/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n***\nDate Change, Previously scheduled 2/18/25.\n………………………………"]
["X24-1177107","***","2025-02-21","2025-02-21","Project Change","2025-02-20","2025-02-20","MLV 565-2 TO MLV 559-2","500","1","Pig Runs - AFD 2/21/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,565.22,"--start_date--end_date------mantenance_desc------model_loc--","***MLV 565-2 TO MLV 559-2:  Pig Runs - AFD 2/21/25\n--2/21/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n***\nDate Change, Previously scheduled 2/20/25.\n………………………………"]
["X25-104537","***","2025-02-05","2025-02-07","Added",null,null,"Station 827 (Alexandria)","800","L","Starter VFD & Program Changes","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,827,"------","***Station 827 (Alexandria):  Starter VFD & Program Changes\n--2/5/25 through 2/7/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-40664",null,"2025-06-02","2025-06-05",null,null,null,"Station 827 (Alexandria)","800","L","Annual ESD and Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,827,null,"Station 827 (Alexandria):  Annual ESD and Maintenance\n--6/2/25 through 6/5/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-56220","***","2025-01-21","2025-01-24","Completed",null,null,"Sta 834","800","1","Unit 2A - Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,834.00199999999995,"------","***Sta 834:  Unit 2A - Engine Inspection\n***Completed"]
["X24-1242580",null,"2024-11-11","2025-02-21",null,null,null,"Sta 834","800","1","Unit 5A - Cracked Main Bearing","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,834.005,null,"Sta 834:  Unit 5A - Cracked Main Bearing\n--11/11/24 through 2/21/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1186067",null,"2025-03-03","2025-11-03",null,null,null,"Sta 834","800","1","Unit 6A - Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,834.00599999999997,null,"Sta 834:  Unit 6A - Overhaul\n--3/3/25 through 11/3/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-56221",null,"2025-01-27","2025-01-31",null,null,null,"Sta 834","800","1","Unit 7A - Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,834.00699999999995,null,"Sta 834:  Unit 7A - Engine Inspection\n--1/27/25 through 1/31/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-25864",null,"2025-09-30","2025-09-30",null,null,null,"Sta 836A","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,836,null,"Sta 836A:  Annual ESD Test\n--9/30/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-25863",null,"2025-09-10","2025-09-10",null,null,null,"Sta 838","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,838,null,"Sta 838:  Annual ESD Test\n--9/10/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368167",null,"2025-06-18","2025-06-18",null,null,null,"Sta 843 Isola","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,843,null,"Sta 843 Isola:  Annual ESD Test\n--6/18/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1179060",null,"2025-05-13","2025-05-13",null,null,null,"MLV 843-1 TO MLV 847-1","800","1","Pig Runs - Cleaning / Gauge 5/13/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,843.1,null,"MLV 843-1 TO MLV 847-1:  Pig Runs - Cleaning / Gauge 5/13/25\n--5/13/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1179091",null,"2025-05-15","2025-05-15",null,null,null,"MLV 843-1 TO MLV 847-1","800","1","Pig Runs - Caliper 5/15/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,843.11,null,"MLV 843-1 TO MLV 847-1:  Pig Runs - Caliper 5/15/25\n--5/15/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1179111",null,"2025-05-20","2025-05-20",null,null,null,"MLV 843-1 TO MLV 847-1","800","1","Pig Runs - AFD 5/20/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,843.12,null,"MLV 843-1 TO MLV 847-1:  Pig Runs - AFD 5/20/25\n--5/20/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1179124",null,"2025-05-22","2025-05-22",null,null,null,"MLV 843-1 TO MLV 847-1","800","1","Pig Runs - EMAT 5/22/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,843.13,null,"MLV 843-1 TO MLV 847-1:  Pig Runs - EMAT 5/22/25\n--5/22/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368168",null,"2025-08-27","2025-08-28",null,null,null,"Sta 847 Coffeeville","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,847,null,"Sta 847 Coffeeville:  Annual ESD Test\n--8/27/25 through 8/28/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368179",null,"2025-10-08","2025-10-08",null,null,null,"Sta 851 New Albany","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,851,null,"Sta 851 New Albany:  Annual ESD Test\n--10/8/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368184",null,"2025-06-10","2025-06-11",null,null,null,"Sta 856 Savannah","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,856,null,"Sta 856 Savannah:  Annual ESD Test\n--6/10/25 through 6/11/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368187",null,"2025-06-10","2025-06-11",null,null,null,"Sta 856 Savannah","800","1","Replace Leaking ESD Valves on Turbines","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,856.00009999999997,null,"Sta 856 Savannah:  Replace Leaking ESD Valves on Turbines\n--6/10/25 through 6/11/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1082048",null,"2025-03-24","2025-03-24",null,null,null,"MLV 856-1 to MLV 851-1","800","2","Pig Runs - Cleaning / Gauge 3/24/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,856.1,null,"MLV 856-1 to MLV 851-1:  Pig Runs - Cleaning / Gauge 3/24/25\n--3/24/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1082054",null,"2025-03-25","2025-03-25",null,null,null,"MLV 856-1 to MLV 851-1","800","2","Pig Runs - MFL-C 3/25/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,856.11,null,"MLV 856-1 to MLV 851-1:  Pig Runs - MFL-C 3/25/25\n--3/25/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1082055",null,"2025-03-27","2025-03-27",null,null,null,"MLV 856-1 to MLV 851-1","800","2","Pig Runs - EMAT 3/27/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,856.12,null,"MLV 856-1 to MLV 851-1:  Pig Runs - EMAT 3/27/25\n--3/27/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-841261",null,"2023-08-18","TBD",null,null,null,"Sta 860","800","1","Force Majeure","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,860,null,"Sta 860:  Force Majeure\n--8/18/23 through 6/1/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368190",null,"2025-09-17","2025-09-17",null,null,null,"Sta 860","800","1","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,860,null,"Sta 860:  Annual ESD Test & Maintenance\n--9/17/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-640564",null,"2024-06-17","2025-02-14",null,null,null,"Sta 860","800","1","Unit 1A - After Cooler/jacket Water leaking into crankcase","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,860.00099999999998,null,"Sta 860:  Unit 1A - After Cooler/jacket Water leaking into crankcase\n--6/17/24 through 2/14/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-104812","***","2025-02-18","2025-02-20","Added",null,null,"Sta 860","800","1","Unit 2A Carbon Punch & Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,860.00199999999995,"------","***Sta 860:  Unit 2A Carbon Punch & Maintenance\n--2/18/25 through 2/20/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-101552","***","2025-02-11","2025-02-13","Added",null,null,"Sta 860","800","1","Unit 3A Carbon Punch & Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,860.00300000000004,"------","***Sta 860:  Unit 3A Carbon Punch & Maintenance\n--2/11/25 through 2/13/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X23-173712",null,"2024-02-05","2025-02-21",null,null,null,"Sta 860","800","1","Unit 7A - Foundation Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,860.00699999999995,null,"Sta 860:  Unit 7A - Foundation Replacement\n--2/5/24 through 2/21/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368196",null,"2025-06-24","2025-06-25",null,null,null,"Sta 871 Campbellsville","800","2","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,871,null,"Sta 871 Campbellsville:  Annual ESD Test\n--6/24/25 through 6/25/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-101521","***","2025-03-12","2025-03-12","Added",null,null,"Sta 871","800","2","Unit 1A - 1Q Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,871.00099999999998,"------","***Sta 871:  Unit 1A - 1Q Engine Inspection\n--3/12/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-1274950",null,"2025-05-13","2025-05-13",null,null,null,"Sta 871","800","2","Unit 1A - Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,871.00099999999998,null,"Sta 871:  Unit 1A - Engine Inspection\n--5/13/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-101517","***","2025-03-11","2025-03-11","Added",null,null,"Sta 871","800","1","Unit 2A - 1Q Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,871.00199999999995,"------","***Sta 871:  Unit 2A - 1Q Engine Inspection\n--3/11/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-1274947",null,"2025-05-05","2025-05-05",null,null,null,"Sta 871","800","2","Unit 2A - Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,871.00199999999995,null,"Sta 871:  Unit 2A - Engine Inspection\n--5/5/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1009526",null,"2025-05-05","2025-05-09",null,null,null,"Sta 871","800","2","Unit 2A -Compressor Unloaders","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,871.00199999999995,null,"Sta 871:  Unit 2A -Compressor Unloaders\n--5/5/25 through 5/9/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368203",null,"2025-09-18","2025-09-18",null,null,null,"Sta 871A Campbellsville","800","2","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,871.5,null,"Sta 871A Campbellsville:  Annual ESD Test\n--9/18/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368155",null,"2025-06-09","2025-06-09",null,null,null,"Sta 875 Richmond","800","2","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,875,null,"Sta 875 Richmond:  Annual ESD Test & Maintenance\n--6/9/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1009178",null,"2025-03-06","2025-03-06",null,null,null,"MLV 876-2 to MLV 874-2","800","2","Pig Runs - Cleaning / Gauge 3/6/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,876.2,null,"MLV 876-2 to MLV 874-2:  Pig Runs - Cleaning / Gauge 3/6/25\n--3/6/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-1009200",null,"2025-03-11","2025-03-11",null,null,null,"MLV 876-2 to MLV 874-2","800","2","Pig Runs - AFD Combo 3/11/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,876.21,null,"MLV 876-2 to MLV 874-2:  Pig Runs - AFD Combo 3/11/25\n--3/11/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-1009216",null,"2025-03-13","2025-03-13",null,null,null,"MLV 876-2 to MLV 874-2","800","2","Pig Runs - EMAT 3/13/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,876.22,null,"MLV 876-2 to MLV 874-2:  Pig Runs - EMAT 3/13/25\n--3/13/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]

{"sheet":"Sheet2","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}

{"sheet":"Sheet3","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}