{"text_format":"1","workbook":"xlsx","n_sheets":4,"sheets":["Closed","Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":8,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Closed","index":0,"n_rows":37,"n_cols":22,"rows_kept":37,"cut":false,"hidden":true,"merged":[[1,3,1,15],[2,3,2,15],[3,3,3,15]]}
[null,null,null,"Updated ","2016"]
[null,null,null,"Tennessee Gas Pipeline 2015 Pipeline Outage and Maintenance Summary"]
[null,null,null,"This is a summary of the current status of all TGP Winter 2014-2015 Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  Additionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
[null,null,null,"*** Indicates revision"]
["Date Change","Project New/Completed/Closed","Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","Location","Leg","Zone","Maintenance Activity","Anticipated Impact","Potential Restriction Level","TOS Potential Restrictions","Meter(s) in Impacted Area","Customer Notifications","Loc","Email Text","Posting Text","Completion Text"]
[{"$f":"IF(AND(H6<>\"\",I6<>\"\"), \"Date change. Previously scheduled \" & TEXT(H6,\"m/d/y;@\") &IF(H6=I6,\"\",\" to \" & TEXT(I6,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed",null,{"$f":"IF(G6<>\"\",\"***\",\"\")","v":"***"},"2015-01-11","2016-01-11",{"$f":"IF(AND(A6=\"\",B6=\"\"),\"\",IF(B6=\"\",A6,B6))","v":"Project Completed"},null,null,"MS #412494 DCP Warren","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412494 DCP Warren",401,{"$f":"\"(\"&C6&\") \"&J6&\":  \"&M6&IF(AND(E6=\"\",F6=\"\"),\"\",\" (\")&IF(E6=\"\",\"\",\"\"&TEXT(E6,\"m/d/y;@\"))&IF(OR(F6=E6,E6=\"\",F6=\"\"),\"\",\" to \")&IF(OR(F6=\"\",F6=E6),\"\",TEXT(F6,\"m/d/y;@\"))&IF(AND(E6=\"\",F6=\"\"),\"\",\")\")","v":"() MS #412494 DCP Warren:  Meter Station (1/11/15 to 1/11/16)"},{"$f":"D6&J6&\":  \"&M6&IF(AND(E6=\"\",F6=\"\"),\"\",\"\n\")&IF(E6=\"\",\"\",\"--\"&TEXT(E6,\"m/d/y;@\"))&IF(OR(F6=E6,E6=\"\",F6=\"\"),\"\",\" through \")&IF(OR(F6=\"\",F6=E6),\"\",TEXT(F6,\"m/d/y;@\"))&IF(AND(E6=\"\",F6=\"\"),\"\",\":  \")&N6&\"  \"&P6&IF(Q6=\"\",\"\",\"\n\"&Q6)&IF(G6=\"\",\"\",\"\n***\")&G6&\"\n………………………………\"","v":"***MS #412494 DCP Warren:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412494 DCP Warren\n***Project Completed\n………………………………"},{"$f":"D6&J6&\":  \"&M6&IF(G6=\"\",\"\",\"\n***\")&G6&IF(Q6=\"\",\"\",\"\nThe following meters are available for nominations:\n\")&Q6&\"\n………………………………\"","v":"***MS #412494 DCP Warren:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412494 DCP Warren\n………………………………"}]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412400 King Ranch","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412400 King Ranch",402.1,"() MS #412400 King Ranch:  Meter Station (1/11/15 to 1/11/16)","***MS #412400 King Ranch:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412400 King Ranch\n***Project Completed\n………………………………","***MS #412400 King Ranch:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412400 King Ranch\n………………………………"]
["","Project Completed",null,"***","2015-01-12","2016-01-12","Project Completed",null,null,"MS #410539 Duvak Gas Gathering","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410539 Duvak Gas Gathering",402.1,"() MS #410539 Duvak Gas Gathering:  Meter Station (1/12/15 to 1/12/16)","***MS #410539 Duvak Gas Gathering:  Meter Station\n--1/12/15 through 1/12/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410539 Duvak Gas Gathering\n***Project Completed\n………………………………","***MS #410539 Duvak Gas Gathering:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n410539 Duvak Gas Gathering\n………………………………"]
["","Project Completed",null,"***","2015-01-13","2016-01-13","Project Completed",null,null,"MS #412356 DCP LaGloria","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412356 DCP LaGloria",403.1,"() MS #412356 DCP LaGloria:  Meter Station (1/13/15 to 1/13/16)","***MS #412356 DCP LaGloria:  Meter Station\n--1/13/15 through 1/13/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412356 DCP LaGloria\n***Project Completed\n………………………………","***MS #412356 DCP LaGloria:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412356 DCP LaGloria\n………………………………"]
["","Project Completed",null,"***","2015-01-13","2016-01-13","Project Completed",null,null,"MS #410173 Enterprise LaReforma","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410173 Enterprise LaReforma",406.1,"() MS #410173 Enterprise LaReforma:  Meter Station (1/13/15 to 1/13/16)","***MS #410173 Enterprise LaReforma:  Meter Station\n--1/13/15 through 1/13/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410173 Enterprise LaReforma\n***Project Completed\n………………………………","***MS #410173 Enterprise LaReforma:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n410173 Enterprise LaReforma\n………………………………"]
["","Project Completed",null,"***","2015-01-12","2016-01-12","Project Completed",null,null,"MS #411903 Enterprise El Benito","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","411903 Enterprise El Benito",407.1,"() MS #411903 Enterprise El Benito:  Meter Station (1/12/15 to 1/12/16)","***MS #411903 Enterprise El Benito:  Meter Station\n--1/12/15 through 1/12/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n411903 Enterprise El Benito\n***Project Completed\n………………………………","***MS #411903 Enterprise El Benito:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n411903 Enterprise El Benito\n………………………………"]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412088 Enterprise Sullivan","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412088 Enterprise Sullivan",407.1,"() MS #412088 Enterprise Sullivan:  Meter Station (1/11/15 to 1/11/16)","***MS #412088 Enterprise Sullivan:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412088 Enterprise Sullivan\n***Project Completed\n………………………………","***MS #412088 Enterprise Sullivan:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412088 Enterprise Sullivan\n………………………………"]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412683 HESCO","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412683 HESCO",408.1,"() MS #412683 HESCO:  Meter Station (1/11/15 to 1/11/16)","***MS #412683 HESCO:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412683 HESCO\n***Project Completed\n………………………………","***MS #412683 HESCO:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412683 HESCO\n………………………………"]
[{"$f":"IF(AND(H14<>\"\",I14<>\"\"), \"Date change. Previously scheduled \" & TEXT(H14,\"m/d/y;@\") &IF(H14=I14,\"\",\" to \" & TEXT(I14,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X16-36843",{"$f":"IF(G14<>\"\",\"***\",\"\")","v":"***"},"2016-01-27","2016-01-27","Project Completed",null,null,"Sta. 237",200,5,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,237,"(X16-36843) Sta. 237:  Unit  Maintenance (1/27/16)","***Sta. 237:  Unit  Maintenance\n--1/27/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Sta. 237:  Unit  Maintenance\n***Project Completed\n………………………………"]
[{"$f":"IF(AND(H15<>\"\",I15<>\"\"), \"Date change. Previously scheduled \" & TEXT(H15,\"m/d/y;@\") &IF(H15=I15,\"\",\" to \" & TEXT(I15,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X14-1478563",{"$f":"IF(G15<>\"\",\"***\",\"\")","v":"***"},"2015-11-16","2016-02-12","Project Completed",null,null,"MLV 32-1D to 33-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,32.200000000000003,"(X14-1478563) MLV 32-1D to 33-1:  Hydrotest (11/16/15 to 2/12/16)","***MLV 32-1D to 33-1:  Hydrotest\n--11/16/15 through 2/12/16:  This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***MLV 32-1D to 33-1:  Hydrotest\n***Project Completed\n………………………………"]
[null,"Project Completed","X16-16074",null,"2016-01-18","2016-01-28","Project Completed",null,null,"Station 550","500","1","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,550,"(X16-16074) Station 550:  Station Maintenance (1/18/16 to 1/28/16)","Station 550:  Station Maintenance\n--1/18/16 through 1/28/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","Station 550:  Station Maintenance\n***Project Completed\n………………………………"]
[{"$f":"IF(AND(H17<>\"\",I17<>\"\"), \"Date change. Previously scheduled \" & TEXT(H17,\"m/d/y;@\") &IF(H17=I17,\"\",\" to \" & TEXT(I17,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X16-46202",{"$f":"IF(G17<>\"\",\"***\",\"\")","v":"***"},"2016-02-01","2016-02-07","Project Completed",null,null,"Station 9","100","0","Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.",null,9,"(X16-46202) Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items) (2/1/16 to 2/7/16)","***Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)\n--2/1/16 through 2/7/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\n***Project Completed\n………………………………","***Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)\n***Project Completed\n………………………………"]
["","Project Completed","X15-925633","***","2016-02-09","2016-02-11","Project Completed",null,null,"Sta. 266A",200,6,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,266,"(X15-925633) Sta. 266A:  Unit  Maintenance (2/9/16 to 2/11/16)","***Sta. 266A:  Unit  Maintenance\n--2/9/16 through 2/11/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Sta. 266A:  Unit  Maintenance\n***Project Completed\n………………………………"]
["","Project Completed","X15-929733","***","2016-01-27","2016-02-10","Project Completed",null,null,"MLV 834-1 to 838-1",800,5,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",834.1,"(X15-929733) MLV 834-1 to 838-1:  ILI/Cleaning Pig (1/27/16 to 2/10/16)","***MLV 834-1 to 838-1:  ILI/Cleaning Pig\n--1/27/16 through 2/10/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 834-1 to 838-1:  ILI/Cleaning Pig\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X14-1562506","***","2015-11-02","2016-02-19","Project Completed",null,null,"MLV 5-1 to 6-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410063 ROCHE DEHYDRATION             \n",5.0999999999999996,"(X14-1562506) MLV 5-1 to 6-1:  Hydrotest (11/2/15 to 2/19/16)","***MLV 5-1 to 6-1:  Hydrotest\n--11/2/15 through 2/19/16:  This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410063 ROCHE DEHYDRATION             \n\n***Project Completed\n………………………………","***MLV 5-1 to 6-1:  Hydrotest\n***Project Completed\nThe following meters are available for nominations:\n410063 ROCHE DEHYDRATION             \n\n………………………………"]
["","Project Completed","X14-1562506","***","2015-11-02","2016-02-19","Project Completed",null,null,"MLV 7-1 to 9-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","\n412490 Charro\n421083 Eagle Ford Field Service",5.0999999999999996,"(X14-1562506) MLV 7-1 to 9-1:  Hydrotest (11/2/15 to 2/19/16)","***MLV 7-1 to 9-1:  Hydrotest\n--11/2/15 through 2/19/16:  This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n\n412490 Charro\n421083 Eagle Ford Field Service\n***Project Completed\n………………………………","***MLV 7-1 to 9-1:  Hydrotest\n***Project Completed\nThe following meters are available for nominations:\n\n412490 Charro\n421083 Eagle Ford Field Service\n………………………………"]
["Date change. Previously scheduled 2/18/16 to 2/20/16.","Project Completed","X15-882289","***","2016-02-22","2016-02-24","Project Completed","2016-02-18","2016-02-20","MLV 24-2 to 25-2S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.2,"(X15-882289) MLV 24-2 to 25-2S:  Anomaly Remediation (2/22/16 to 2/24/16)","***MLV 24-2 to 25-2S:  Anomaly Remediation\n--2/22/16 through 2/24/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 24-2 to 25-2S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-925630","***","2016-02-23","2016-02-23","Project Completed",null,null,"WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B)",200,"L","ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,265.10000000000002,"(X15-925630) WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig (2/23/16)","***WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig\n--2/23/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig\n***Project Completed\n………………………………"]
["","Project Completed","X16-23748","***","2016-02-15","2016-02-18","Project Completed",null,null,"MLV 530-3 to 532-3",500,"L","ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,530.29999999999995,"(X16-23748) MLV 530-3 to 532-3:  ILI/Cleaning Pig (2/15/16 to 2/18/16)","***MLV 530-3 to 532-3:  ILI/Cleaning Pig\n--2/15/16 through 2/18/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***MLV 530-3 to 532-3:  ILI/Cleaning Pig\n***Project Completed\n………………………………"]
["","Project Canceled","X16-98720","***","2016-03-06","2016-03-06","Project Canceled",null,null,"Sta. 1",100,0,"Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,1,"(X16-98720) Sta. 1:  Station Maintenance (3/6/16)","***Sta. 1:  Station Maintenance\n--3/6/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Canceled\n………………………………","***Sta. 1:  Station Maintenance\n***Project Canceled\n………………………………"]
["","Project Completed","X14-1562513\nX14-1540661","***","2015-07-01","2016-03-04","Project Completed",null,null,"Station 32","100","0","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,32,"(X14-1562513\nX14-1540661) Station 32:  Station Maintenance (7/1/15 to 3/4/16)","***Station 32:  Station Maintenance\n--7/1/15 through 3/4/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Station 32:  Station Maintenance\n***Project Completed\n………………………………"]
["","Project Canceled","X15-926822","***","2016-06-06","2016-06-11","Project Canceled",null,null,"BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1)",300,6,"Pipe Inspection","This project involves inspecting multiple sites.  We do not anticipate having to do any repairs, however if a repair is needed  there is a potential that the pipe  may require replacement which will require isolation of the pipe.  This may limit throughput and will result in restrictions based on customer nominations.  Customers may experience pressure fluctuations during this timeframe.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",343.1,"(X15-926822) BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection (6/6/16 to 6/11/16)","***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection\n--6/6/16 through 6/11/16:  This project involves inspecting multiple sites.  We do not anticipate having to do any repairs, however if a repair is needed  there is a potential that the pipe  may require replacement which will require isolation of the pipe.  This may limit throughput and will result in restrictions based on customer nominations.  Customers may experience pressure fluctuations during this timeframe.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928271","***","TBD","TBD","Project Canceled",null,null,"MLV 555-1 to 550-1",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.1,"(X15-928271) MLV 555-1 to 550-1:  ILI/Cleaning Pig (TBD)","***MLV 555-1 to 550-1:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-1 to 550-1:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928272","***","TBD","TBD","Project Canceled",null,null,"MLV 555-2 to 550-2",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.20000000000005,"(X15-928272) MLV 555-2 to 550-2:  ILI/Cleaning Pig (TBD)","***MLV 555-2 to 550-2:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-2 to 550-2:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928273","***","TBD","TBD","Project Canceled",null,null,"MLV 555-3 to 552-3",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.29999999999995,"(X15-928273) MLV 555-3 to 552-3:  ILI/Cleaning Pig (TBD)","***MLV 555-3 to 552-3:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-3 to 552-3:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-882281","***","2016-02-24","2016-03-03","Project Completed",null,null,"24-1A to 25-1S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.1,"(X15-882281) 24-1A to 25-1S:  Anomaly Remediation (2/24/16 to 3/3/16)","***24-1A to 25-1S:  Anomaly Remediation\n--2/24/16 through 3/3/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***24-1A to 25-1S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-882291","***","2016-03-03","2016-03-04","Project Completed",null,null,"MLV 24-3 to 25-3S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.3,"(X15-882291) MLV 24-3 to 25-3S:  Anomaly Remediation (3/3/16 to 3/4/16)","***MLV 24-3 to 25-3S:  Anomaly Remediation\n--3/3/16 through 3/4/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 24-3 to 25-3S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X14-1178175","***","2015-06-15","2016-03-31","Project Completed",null,null,"Station 63","100","1","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,63,"(X14-1178175) Station 63:  Station Maintenance (6/15/15 to 3/31/16)","***Station 63:  Station Maintenance\n--6/15/15 through 3/31/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Station 63:  Station Maintenance\n***Project Completed\n………………………………"]
["","Project Cancelled","X15-913224","***","2016-04-16","2016-05-21","Project Cancelled",null,null,"MLV 109-2",100,2,"Pipe Replacement","This project will require taking the pipeline section out of service.   This will limit throughput and will result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",109.2,"(X15-913224) MLV 109-2:  Pipe Replacement (4/16/16 to 5/21/16)","***MLV 109-2:  Pipe Replacement\n--4/16/16 through 5/21/16:  This project will require taking the pipeline section out of service.   This will limit throughput and will result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Cancelled\n………………………………","***MLV 109-2:  Pipe Replacement\n***Project Cancelled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-926830","***","2016-03-07","2016-03-11","Project Completed",null,null,"MLV 400-1 to 408-1",100,0,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.","To Be Determined",400.1,"(X15-926830) MLV 400-1 to 408-1:  ILI/Cleaning Pig (3/7/16 to 3/11/16)","***MLV 400-1 to 408-1:  ILI/Cleaning Pig\n--3/7/16 through 3/11/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 400-1 to 408-1:  ILI/Cleaning Pig\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Cancelled","X16-143836","***","2016-03-28","2016-04-04","Project Cancelled",null,null,"Sta. 409",100,0,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.",null,409,"(X16-143836) Sta. 409:  Unit  Maintenance (3/28/16 to 4/4/16)","***Sta. 409:  Unit  Maintenance\n--3/28/16 through 4/4/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\n***Project Cancelled\n………………………………","***Sta. 409:  Unit  Maintenance\n***Project Cancelled\n………………………………"]
["","Project Cancelled","X15-929680","***","2016-04-18","2016-04-27","Project Cancelled",null,null,"SABINE - KINDER LINE to 822-1",800,"L","Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",822.1,"(X15-929680) SABINE - KINDER LINE to 822-1:  Anomaly Remediation (4/18/16 to 4/27/16)","***SABINE - KINDER LINE to 822-1:  Anomaly Remediation\n--4/18/16 through 4/27/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Cancelled\n………………………………","***SABINE - KINDER LINE to 822-1:  Anomaly Remediation\n***Project Cancelled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]

{"sheet":"Sheet1","index":1,"n_rows":479,"n_cols":24,"rows_kept":479,"cut":false,"hidden":false,"merged":[[2,0,2,14]]}
["Updated ","2025-05-15"]
["Tennessee Gas Pipeline 2025 Pipeline Outage and Maintenance Summary"]
["This is a summary of the current status of TGP Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  \nAdditionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
["*** Indicates revision"]
["Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","Location","Leg","Zone","Maintenance Activity","Anticipated Impact","Potential Restriction Level","TOS Potential Restrictions","Meter(s) in Impacted Area","Loc",null,null,null,null,null,null,null,"\\\\houCORP\\TRANS\\TRANSERVICES\\OPPLAN\\COMMON\\Outages\\Outage_DB\\TGP\\Files"]
["X25-173987",null,"2025-04-18","2025-06-03",null,null,null,"MLV 1-1BL to MLV 3-1","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,1.1000000000000001,null,"MLV 1-1BL to MLV 3-1:  Anomaly Remediation\n--4/18/25 through 6/3/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-327344",null,"2025-05-20","2025-06-17",null,null,null,"MLV 4-1 to MLV 5-1","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,4.0999999999999996,null,"MLV 4-1 to MLV 5-1:  Anomaly Remediation\n--5/20/25 through 6/17/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-82097",null,"2025-07-21","2025-08-08",null,null,null,"MLV 8-3 to MLV 9-3","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,4.3,null,"MLV 8-3 to MLV 9-3:  Anomaly Remediation\n--7/21/25 through 8/8/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-475092","***","2025-06-03","2025-06-03","Project Change","2025-05-27","2025-05-27","MLV 5-2 to MLV 9-2S","100","0","Pig Runs - Cleaning 6/3/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","54847 WHISTLEP/TGP WHISTLE RECEIPT NUECES\n53608 VCP/TGP VALLEY CROSSING ALLOCATION",5.2,"--start_date--end_date------mantenance_desc------model_loc--","***MLV 5-2 to MLV 9-2S:  Pig Runs - Cleaning 6/3/25\n--6/3/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n54847 WHISTLEP/TGP WHISTLE RECEIPT NUECES\n53608 VCP/TGP VALLEY CROSSING ALLOCATION\n***\nDate Change, Previously scheduled 5/27/25.\n………………………………"]
["X25-475094","***","2025-06-05","2025-06-05","Project Change","2025-05-29","2025-05-29","MLV 5-2 to MLV 9-2S","100","0","Pig Runs - MFL-A 6/5/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","54847 WHISTLEP/TGP WHISTLE RECEIPT NUECES\n53608 VCP/TGP VALLEY CROSSING ALLOCATION",5.21,"--start_date--end_date------mantenance_desc------model_loc--","***MLV 5-2 to MLV 9-2S:  Pig Runs - MFL-A 6/5/25\n--6/5/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n54847 WHISTLEP/TGP WHISTLE RECEIPT NUECES\n53608 VCP/TGP VALLEY CROSSING ALLOCATION\n***\nDate Change, Previously scheduled 5/29/25.\n………………………………"]
["X25-237824",null,"2025-10-23","2025-10-23",null,null,null,"MLV 5-2 to MLV 1-2D","100","0","Pig Runs - Maintenance Cleaning 10/23","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","412196 ENLINK/TGP NORTH BRAYTON DEHY NUECE\n412062 BANHUB/TGP BANQUETE TRANSPORT NUECE\n412669 ETP/TGP SHOUP NUECES\n412270 LOBO/TGP UDP TRANSAMERICAN INTERCON\n54847 WHISTLEP/TGP WHISTLER RECEIPT NUECE",5.21,null,"MLV 5-2 to MLV 1-2D:  Pig Runs - Maintenance Cleaning 10/23\n--10/23/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n412196 ENLINK/TGP NORTH BRAYTON DEHY NUECE\n412062 BANHUB/TGP BANQUETE TRANSPORT NUECE\n412669 ETP/TGP SHOUP NUECES\n412270 LOBO/TGP UDP TRANSAMERICAN INTERCON\n54847 WHISTLEP/TGP WHISTLER RECEIPT NUECE\n………………………………"]
["X25-327345",null,"2025-06-03","2025-07-02",null,null,null,"MLV 8-1 to MLV9-1","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,8.1,null,"MLV 8-1 to MLV9-1:  Anomaly Remediation\n--6/3/25 through 7/2/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-238186",null,"2025-10-21","2025-10-21",null,null,null,"MLV 9-1S and MLV 1-1D","100","0","Pig Run - Maintenance Cleaning 10/21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","54847 WHISTLEP/TGP WHISTLE RECEIPT NUECES\n53608 VCP/TGP VALLEY CROSSING ALLOCATION",9.1,null,"MLV 9-1S and MLV 1-1D:  Pig Run - Maintenance Cleaning 10/21\n--10/21/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n54847 WHISTLEP/TGP WHISTLE RECEIPT NUECES\n53608 VCP/TGP VALLEY CROSSING ALLOCATION\n………………………………"]
["X25-237991",null,"2025-10-23","2025-10-23",null,null,null,"MLV 9-2 to MLV 5-2","100","0","Pig Runs - Maintenance Cleaning 10/23","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","54847 WHISTLEP/TGP WHISTLE RECEIPT NUECES\n53608 VCP/TGP VALLEY CROSSING ALLOCATION",9.2100000000000009,null,"MLV 9-2 to MLV 5-2:  Pig Runs - Maintenance Cleaning 10/23\n--10/23/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n54847 WHISTLEP/TGP WHISTLE RECEIPT NUECES\n53608 VCP/TGP VALLEY CROSSING ALLOCATION\n………………………………"]
["X25-238099",null,"2025-10-22","2025-10-22",null,null,null,"MLV 9-3 to MLV 4-3","100","0","Pig Runs - Maintenance Cleaning 10/22","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","54847 WHISTLEP/TGP WHISTLE RECEIPT NUECES\n53608 VCP/TGP VALLEY CROSSING ALLOCATION",9.31,null,"MLV 9-3 to MLV 4-3:  Pig Runs - Maintenance Cleaning 10/22\n--10/22/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n54847 WHISTLEP/TGP WHISTLE RECEIPT NUECES\n53608 VCP/TGP VALLEY CROSSING ALLOCATION\n………………………………"]
["X25-82116",null,"2025-06-10","2025-06-10",null,null,null,"MLV 13-3 to MLV 17-3","100","0","Pig Run - Cleaning 6/10/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","411911 ETP/TGP WHARTON COUNTY TRANSPORT EX\n56009 MATTEXPR/TGP BERNARD CREEK RECEIPT\n420190 COKINOS/TGP SULAK FARM TX WHARTON\n421055 TRES PAL/TGP TRES PALACIOS STORAGE:",13.3,null,"MLV 13-3 to MLV 17-3:  Pig Run - Cleaning 6/10/25\n--6/10/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n411911 ETP/TGP WHARTON COUNTY TRANSPORT EX\n56009 MATTEXPR/TGP BERNARD CREEK RECEIPT\n420190 COKINOS/TGP SULAK FARM TX WHARTON\n421055 TRES PAL/TGP TRES PALACIOS STORAGE:\n………………………………"]
["X25-185240",null,"2025-06-12","2025-06-12",null,null,null,"MLV 13-3 to MLV 17-3","100","0","Pig Run - Gauge 6/12/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","411911 ETP/TGP WHARTON COUNTY TRANSPORT EX\n56009 MATTEXPR/TGP BERNARD CREEK RECEIPT\n420190 COKINOS/TGP SULAK FARM TX WHARTON\n421055 TRES PAL/TGP TRES PALACIOS STORAGE:",13.3,null,"MLV 13-3 to MLV 17-3:  Pig Run - Gauge 6/12/25\n--6/12/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n411911 ETP/TGP WHARTON COUNTY TRANSPORT EX\n56009 MATTEXPR/TGP BERNARD CREEK RECEIPT\n420190 COKINOS/TGP SULAK FARM TX WHARTON\n421055 TRES PAL/TGP TRES PALACIOS STORAGE:\n………………………………"]
["X25-173985",null,"2025-06-18","2025-06-18",null,null,null,"MLV 13-3 to MLV 17-3","100","0","Pig Run - MFL-C 6/18/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","411911 ETP/TGP WHARTON COUNTY TRANSPORT EX\n56009 MATTEXPR/TGP BERNARD CREEK RECEIPT\n420190 COKINOS/TGP SULAK FARM TX WHARTON\n421055 TRES PAL/TGP TRES PALACIOS STORAGE:",13.3,null,"MLV 13-3 to MLV 17-3:  Pig Run - MFL-C 6/18/25\n--6/18/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n411911 ETP/TGP WHARTON COUNTY TRANSPORT EX\n56009 MATTEXPR/TGP BERNARD CREEK RECEIPT\n420190 COKINOS/TGP SULAK FARM TX WHARTON\n421055 TRES PAL/TGP TRES PALACIOS STORAGE:\n………………………………"]
["X25-82089",null,"2025-06-16","2025-06-16",null,null,null,"MLV 13-3 to MLV 17-3","100","0","Pig Run - MFL-A 6/16/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","411911 ETP/TGP WHARTON COUNTY TRANSPORT EX\n56009 MATTEXPR/TGP BERNARD CREEK RECEIPT\n420190 COKINOS/TGP SULAK FARM TX WHARTON\n421055 TRES PAL/TGP TRES PALACIOS STORAGE:",13.31,null,"MLV 13-3 to MLV 17-3:  Pig Run - MFL-A 6/16/25\n--6/16/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n411911 ETP/TGP WHARTON COUNTY TRANSPORT EX\n56009 MATTEXPR/TGP BERNARD CREEK RECEIPT\n420190 COKINOS/TGP SULAK FARM TX WHARTON\n421055 TRES PAL/TGP TRES PALACIOS STORAGE:\n………………………………"]
["X25-82092",null,"2025-06-20","2025-06-20",null,null,null,"MLV 13-3 to MLV 17-3","100","0","Pig Run - EMAT 6/20/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","411911 ETP/TGP WHARTON COUNTY TRANSPORT EX\n56009 MATTEXPR/TGP BERNARD CREEK RECEIPT\n420190 COKINOS/TGP SULAK FARM TX WHARTON\n421055 TRES PAL/TGP TRES PALACIOS STORAGE:",13.32,null,"MLV 13-3 to MLV 17-3:  Pig Run - EMAT 6/20/25\n--6/20/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n411911 ETP/TGP WHARTON COUNTY TRANSPORT EX\n56009 MATTEXPR/TGP BERNARD CREEK RECEIPT\n420190 COKINOS/TGP SULAK FARM TX WHARTON\n421055 TRES PAL/TGP TRES PALACIOS STORAGE:\n………………………………"]
["X25-174344",null,"2025-06-09","2025-06-21",null,null,null,"MLV 15N-102BL to MLV 15N-101.1BR","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,15.1,null,"MLV 15N-102BL to MLV 15N-101.1BR:  Anomaly Remediation\n--6/9/25 through 6/21/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-559338","***","2025-05-27","2025-05-27","Added",null,null,"MLV 17-1D to MLV 20-1A","100","0","Pig Run - Cleaning 5/27/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.",null,17.100000000000001,"------","***MLV 17-1D to MLV 20-1A:  Pig Run - Cleaning 5/27/25\n--5/27/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-559339","***","2025-05-28","2025-05-28","Added",null,null,"MLV 17-1D to MLV 20-1A","100","0","Pig Run - Gauge 5/28/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.",null,17.100000000000001,"------","***MLV 17-1D to MLV 20-1A:  Pig Run - Gauge 5/28/25\n--5/28/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-559340","***","2025-05-29","2025-05-29","Added",null,null,"MLV 17-1D to MLV 20-1A","100","0","Pig Run - MFL-A 5/29/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential out of path restrictions may be at risk.",null,17.100000000000001,"------","***MLV 17-1D to MLV 20-1A:  Pig Run - MFL-A 5/29/25\n--5/29/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-82095",null,"2025-06-16","2025-07-04",null,null,null,"MLV 17-1D to MLV 20-1A","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,17.100000000000001,null,"MLV 17-1D to MLV 20-1A:  Anomaly Remediation\n--6/16/25 through 7/4/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-475184",null,"2025-08-28","2025-08-28",null,null,null,"MLV 17-2S to MLV 9-2D","100","0","Pigging Cleaning Run 1","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","49803 KMTEJAS/TGP JACKSON (GANADO)",17.100000000000001,null,"MLV 17-2S to MLV 9-2D:  Pigging Cleaning Run 1\n--8/28/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n49803 KMTEJAS/TGP JACKSON (GANADO)\n………………………………"]
["X25-475185",null,"2025-09-03","2025-09-03",null,null,null,"MLV 17-2S to MLV 9-2D","100","0","Pig Runs - Cleaning Run 2","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","49803 KMTEJAS/TGP JACKSON (GANADO)",17.100000000000001,null,"MLV 17-2S to MLV 9-2D:  Pig Runs - Cleaning Run 2\n--9/3/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n49803 KMTEJAS/TGP JACKSON (GANADO)\n………………………………"]
["X25-475187",null,"2025-09-05","2025-09-05",null,null,null,"MLV 17-2S to MLV 9-2D","100","0","Pig Runs - Cleaning / Gauge","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","49803 KMTEJAS/TGP JACKSON (GANADO)",17.100000000000001,null,"MLV 17-2S to MLV 9-2D:  Pig Runs - Cleaning / Gauge\n--9/5/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n49803 KMTEJAS/TGP JACKSON (GANADO)\n………………………………"]
["X25-475188",null,"2025-09-11","2025-09-11",null,null,null,"MLV 17-2S to MLV 9-2D","100","0","Pig Runs - MFL","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","49803 KMTEJAS/TGP JACKSON (GANADO)",17.100000000000001,null,"MLV 17-2S to MLV 9-2D:  Pig Runs - MFL\n--9/11/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n49803 KMTEJAS/TGP JACKSON (GANADO)\n………………………………"]
["X25-475190",null,"2025-09-16","2025-09-16",null,null,null,"MLV 17-2S to MLV 9-2D","100","0","Pig Runs - Hardspot","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","49803 KMTEJAS/TGP JACKSON (GANADO)",17.100000000000001,null,"MLV 17-2S to MLV 9-2D:  Pig Runs - Hardspot\n--9/16/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n49803 KMTEJAS/TGP JACKSON (GANADO)\n………………………………"]
["X25-82096",null,"2025-07-07","2025-07-11",null,null,null,"MLV 17-2D to MLV 20-2A","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,17.2,null,"MLV 17-2D to MLV 20-2A:  Anomaly Remediation\n--7/7/25 through 7/11/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-547528",null,"2025-06-10","2025-07-03",null,null,null,"MLV 19-3 to MLV 19-3A","100","0","Class Change Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,19.3,null,"MLV 19-3 to MLV 19-3A:  Class Change Pipe Replacement\n--6/10/25 through 7/3/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-82094",null,"2025-05-26","2025-06-13",null,null,null,"MLV 20-1BR to MLV 24-1A","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,20.100000000000001,null,"MLV 20-1BR to MLV 24-1A:  Anomaly Remediation\n--5/26/25 through 6/13/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-547532",null,"2025-07-08","2025-07-24",null,null,null,"MLV 20-1 to MLV 20-1BR","100","0","Class Change Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,20.100000000000001,null,"MLV 20-1 to MLV 20-1BR:  Class Change Pipe Replacement\n--7/8/25 through 7/24/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-82099",null,"2025-08-16","2025-08-26",null,null,null,"MLV 20-1, MLV-20-2, MLV-20-3 Kicker Lines","100","0","ECDA Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,20.100000000000001,null,"MLV 20-1, MLV-20-2, MLV-20-3 Kicker Lines:  ECDA Remediation\n--8/16/25 through 8/26/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-547545",null,"2025-08-11","2025-08-22",null,null,null,"MLV 21-1 to MLV 22-1","100","0","Meter Upgrade (Meter: Tomball PIN: 420898)","This project will require operating at controlled flow rates. Customers \r\nmay experience pressure fluctuations.  The meters listed may be constrained \r\nduring the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420898 SYMMETRY/TGP TOMBALL SALES NORTH MO",21.1,null,"MLV 21-1 to MLV 22-1:  Meter Upgrade (Meter: Tomball PIN: 420898)\n--8/11/25 through 8/22/25:  This project will require operating at controlled flow rates. Customers \r\nmay experience pressure fluctuations.  The meters listed may be constrained \r\nduring the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420898 SYMMETRY/TGP TOMBALL SALES NORTH MO\n………………………………"]
["X25-475072","***","2025-05-05","2025-05-09","Completed",null,null,"MLV 21-3 to MLV 21-3A","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,21.3,"------","***MLV 21-3 to MLV 21-3A:  Anomaly Remediation\n***Completed"]
["X25-406712","***","2025-05-12","2025-05-16","Completed",null,null,"MLV 22-3 to MLV 23-3","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,22.3,"------","***MLV 22-3 to MLV 23-3:  Anomaly Remediation\n***Completed"]
["X25-185341","***","2025-05-06","2025-05-08","Completed",null,null,"MLV 24-2 to MLV 25-2S","100","0","Pig Run - Cleaning / Gauge 5/6 to 5/8","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,24.2,"------","***MLV 24-2 to MLV 25-2S:  Pig Run - Cleaning / Gauge 5/6 to 5/8\n***Completed"]
["X25-185344","***","2025-05-09","2025-05-09","Completed",null,null,"MLV 24-2 to MLV 25-2S","100","0","Pig Run - Combo ILI 5/9","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,24.21,"------","***MLV 24-2 to MLV 25-2S:  Pig Run - Combo ILI 5/9\n***Completed"]
["X24-671169",null,"2025-05-19","2025-06-06",null,null,null,"MLV 25-1 to MLV 26-1 Relocation","100","0","Highway 105 Widening","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,25.1,null,"MLV 25-1 to MLV 26-1 Relocation:  Highway 105 Widening\n--5/19/25 through 6/6/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-286293",null,"2025-05-29","2025-05-29",null,null,null,"MLV 25-2 to MLV 32-2","100","0","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,25.2,null,"MLV 25-2 to MLV 32-2:  Pig Run - Maintenance\n--5/29/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-173989",null,"2025-06-10","2025-06-17",null,null,null,"MLV 25-2 to MLV 26-2","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,25.2,null,"MLV 25-2 to MLV 26-2:  Anomaly Remediation\n--6/10/25 through 6/17/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-152035",null,"2025-05-27","2025-05-27",null,null,null,"MLV 25-3 to MLV 32-3","100","0","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,25.3,null,"MLV 25-3 to MLV 32-3:  Pig Run - Maintenance\n--5/27/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-621358",null,"2025-10-06","2025-11-02",null,null,null,"MLV 26-1 Relocation","100","0","Highway 59 Widening","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,26.1,null,"MLV 26-1 Relocation:  Highway 59 Widening\n--10/6/25 through 11/2/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1148994",null,"2025-10-06","2025-11-02",null,null,null,"MLV 26-1 to MLV 27-1","100","0","Install Road Casing","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,26.1,null,"MLV 26-1 to MLV 27-1:  Install Road Casing\n--10/6/25 through 11/2/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-815863",null,"2025-11-03","2025-11-30",null,null,null,"MLV 26-2 Relocation","100","0","Highway 59 Widening","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,26.2,null,"MLV 26-2 Relocation:  Highway 59 Widening\n--11/3/25 through 11/30/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-815864",null,"2025-12-01","2025-12-28",null,null,null,"MLV 26-3 Relocation","100","0","Highway 59 Widening","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","400448 CICO/TGP MERCY GU 1 LIBERTY",26.3,null,"MLV 26-3 Relocation:  Highway 59 Widening\n--12/1/25 through 12/28/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n400448 CICO/TGP MERCY GU 1 LIBERTY\n………………………………"]
["X25-343656",null,"2025-04-14","2025-07-15",null,null,null,"Sta 32","100","0","Unit 3B - Compressor Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,32.018999999999998,null,"Sta 32:  Unit 3B - Compressor Overhaul\n--4/14/25 through 7/15/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-305536",null,"2025-05-26","2025-06-13",null,null,null,"MLV 32-2 to MLV 33-2","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,32.200000000000003,null,"MLV 32-2 to MLV 33-2:  Anomaly Remediation\n--5/26/25 through 6/13/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-157835",null,"2025-09-16","2025-09-16",null,null,null,"MLV 32-2D TO MLV 40-2S","100","0","Pig Runs - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,32.200000000000003,null,"MLV 32-2D TO MLV 40-2S:  Pig Runs - Maintenance\n--9/16/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-157840",null,"2025-09-23","2025-09-23",null,null,null,"MLV 32-3D to MLV 40-3S","100","0","Pig Runs - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,32.299999999999997,null,"MLV 32-3D to MLV 40-3S:  Pig Runs - Maintenance\n--9/23/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-305537",null,"2025-05-19","2025-05-30",null,null,null,"MLV 34-2 to MLV 35-2","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,34.200000000000003,null,"MLV 34-2 to MLV 35-2:  Anomaly Remediation\n--5/19/25 through 5/30/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-305538",null,"2025-05-19","2025-05-23",null,null,null,"MLV 35-2 to MLV 36-2","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,35.200000000000003,null,"MLV 35-2 to MLV 36-2:  Anomaly Remediation\n--5/19/25 through 5/23/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-157832",null,"2025-05-20","2025-05-20",null,null,null,"MLV 36-1TX to MLV 36-1LA","100","0","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,36.1,null,"MLV 36-1TX to MLV 36-1LA:  Pig Run - Maintenance\n--5/20/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-305543","***","2025-04-14","2025-05-23","Project Change",null,"2025-05-16","MLV 37-2 to MLV 38-2","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,37.200000000000003,"----end_date------------model_loc--","***MLV 37-2 to MLV 38-2:  Anomaly Remediation\n--4/14/25 through 5/23/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 4/14/25 to 5/16/25.\n………………………………"]
["X25-305544","***","2025-04-28","2025-05-23","Project Change",null,"2025-05-16","MLV 38-2 to MLV 39-2","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,38.200000000000003,"----end_date------------model_loc--","***MLV 38-2 to MLV 39-2:  Anomaly Remediation\n--4/28/25 through 5/23/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 4/28/25 to 5/16/25.\n………………………………"]
["X25-173992",null,"2025-06-01","2025-06-21",null,null,null,"MLV 39-1 to MLV 40-1S","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,39.1,null,"MLV 39-1 to MLV 40-1S:  Anomaly Remediation\n--6/1/25 through 6/21/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-173993",null,"2025-06-22","2025-07-15",null,null,null,"MLV 39-2 to MLV 40-2S","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,39.200000000000003,null,"MLV 39-2 to MLV 40-2S:  Anomaly Remediation\n--6/22/25 through 7/15/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-173994",null,"2025-07-16","2025-08-15",null,null,null,"MLV 39-3 to MLV 40-3S","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,39.299999999999997,null,"MLV 39-3 to MLV 40-3S:  Anomaly Remediation\n--7/16/25 through 8/15/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1257780",null,"2025-07-21","2025-07-24",null,null,null,"Sta 40","100","1","Carthage Check Meter","This project will require operating at controlled flow rates. Customers \r\nmay experience pressure fluctuations.  The meters listed may be constrained \r\nduring the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","55661\tKHFS/TGP SOUTH COUCHATTA RECEIPT DE\n410031\tETX GAS/TGP EAST TX PLANT DEHY PANO\n411330\tTEXLA/TGP CHEMARD LAKE DEHY DE SOTO\n412610\tMAGNUMPL/TGP WEST MANSFIELD DE SOTO\n412725\tET G&P/TGP  DE SOTO\n412759\tDIV PROD/TGP BURFORD GATHERING: RIP\n412764\tENT GATH/TGP UDP STATE LINE PROCESS\n412807\tET G&P/TGP LOGANSPORT B: RIP 704H 1\n412819\tLOUISMID/TGP CONVERSE CENTRAL: RIP \n420723\tETP/TGP CARTHAGE GAS UNIT 13 PANOLA",40,null,"Sta 40:  Carthage Check Meter\n--7/21/25 through 7/24/25:  This project will require operating at controlled flow rates. Customers \r\nmay experience pressure fluctuations.  The meters listed may be constrained \r\nduring the project.  Potential secondary restrictions at the meter(s) may be at risk.\n55661\tKHFS/TGP SOUTH COUCHATTA RECEIPT DE\n410031\tETX GAS/TGP EAST TX PLANT DEHY PANO\n411330\tTEXLA/TGP CHEMARD LAKE DEHY DE SOTO\n412610\tMAGNUMPL/TGP WEST MANSFIELD DE SOTO\n412725\tET G&P/TGP  DE SOTO\n412759\tDIV PROD/TGP BURFORD GATHERING: RIP\n412764\tENT GATH/TGP UDP STATE LINE PROCESS\n412807\tET G&P/TGP LOGANSPORT B: RIP 704H 1\n412819\tLOUISMID/TGP CONVERSE CENTRAL: RIP \n420723\tETP/TGP CARTHAGE GAS UNIT 13 PANOLA\n………………………………"]
["X24-1257774",null,"2025-08-04","2025-08-09",null,null,null,"Sta 40","100","1","HP Replacement - 500C1 Mod","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations","SOP","Potential out of path restrictions may be at risk.",null,40.000050000000002,null,"Sta 40:  HP Replacement - 500C1 Mod\n--8/4/25 through 8/9/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-461862",null,"2025-08-22","2025-08-30",null,null,null,"Sta 40","800","L","HP Replacement - 500C1 Mod & 1C KN Line","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations","SOP","Potential out of path restrictions may be at risk.",null,40.000070000000001,null,"Sta 40:  HP Replacement - 500C1 Mod & 1C KN Line\n--8/22/25 through 8/30/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-348491",null,"2025-08-13","2025-08-18",null,null,null,"Sta 40","100","1","HP Replacement - Bldg C Mod","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,40.000100000000003,null,"Sta 40:  HP Replacement - Bldg C Mod\n--8/13/25 through 8/18/25:  This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-348494",null,"2025-08-22","2025-08-30",null,null,null,"Sta 40","100","1","HP Replacement - 500C1 Mod & 1C 100 Line","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,40.0002,null,"Sta 40:  HP Replacement - 500C1 Mod & 1C 100 Line\n--8/22/25 through 8/30/25:  This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-195957",null,"2025-06-05","2025-06-10",null,null,null,"MLV 40-1D to MLV 47-1S","100","1","Pig Runs - Cleaning / Gauge 6/5 - 6/10","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","412809 CRTXLIG/TGP CLEAR LAKE NO. 1: RIP 4",40.1,null,"MLV 40-1D to MLV 47-1S:  Pig Runs - Cleaning / Gauge 6/5 - 6/10\n--6/5/25 through 6/10/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n412809 CRTXLIG/TGP CLEAR LAKE NO. 1: RIP 4\n………………………………"]
["X25-195958",null,"2025-06-11","2025-06-11",null,null,null,"MLV 40-1D to MLV 47-1S","100","1","Pig Runs - TDW MDS 6/11","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","412809 CRTXLIG/TGP CLEAR LAKE NO. 1: RIP 4",40.11,null,"MLV 40-1D to MLV 47-1S:  Pig Runs - TDW MDS 6/11\n--6/11/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n412809 CRTXLIG/TGP CLEAR LAKE NO. 1: RIP 4\n………………………………"]
["X24-1151840",null,"2025-07-09","2025-07-09",null,null,null,"MLV 40-3 to MLV 47-3","100","0","Pig Run - EMAT 7/9/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","49780 GULFSTH/TGP WORTHY ROAD SOUH OUACH",40.32,null,"MLV 40-3 to MLV 47-3:  Pig Run - EMAT 7/9/25\n--7/9/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n49780 GULFSTH/TGP WORTHY ROAD SOUH OUACH\n………………………………"]
["X25-157841",null,"2025-06-10","2025-06-10",null,null,null,"MLV 40-4D to MLV 47-4S","100","0","Pig Runs - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","412105 COMSTRES/TGP UDP CADEVILLE LA OUA",40.4,null,"MLV 40-4D to MLV 47-4S:  Pig Runs - Maintenance\n--6/10/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n412105 COMSTRES/TGP UDP CADEVILLE LA OUA\n………………………………"]
["X25-573425","***","2025-05-21","2025-06-06","Added",null,null,"MLV 41-2 to MLV 41-2A","100","1","PHMSA Immediate Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,41.2,"------","***MLV 41-2 to MLV 41-2A:  PHMSA Immediate Anomaly Remediation\n--5/21/25 through 6/6/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-173995",null,"2025-08-01","2025-09-01",null,null,null,"MLV 41-2 to MLV 42-2","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,41.2,null,"MLV 41-2 to MLV 42-2:  Anomaly Remediation\n--8/1/25 through 9/1/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-196085",null,"2025-10-21","2025-10-27",null,null,null,"Bear Creek Storage","100","1","Shut-in Test","This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","460017 STORAGE – BEAR CREEK",43.1,null,"Bear Creek Storage:  Shut-in Test\n--10/21/25 through 10/27/25:  This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n460017 STORAGE – BEAR CREEK\n………………………………"]
["X25-412644",null,"2025-05-26","2025-05-28",null,null,null,"Sta 47","100","1","Transformer Inspection","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,47,null,"Sta 47:  Transformer Inspection\n--5/26/25 through 5/28/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-25861",null,"2025-09-10","2025-09-10",null,null,null,"Sta 47","100","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,47,null,"Sta 47:  Annual ESD Test\n--9/10/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-25860",null,"2025-06-02","2025-06-06",null,null,null,"Sta 47","100","1","Scrubber Filter Separator Cleaning & Inspection","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,47.000100000000003,null,"Sta 47:  Scrubber Filter Separator Cleaning & Inspection\n--6/2/25 through 6/6/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-500881",null,"2025-06-09","2025-07-25",null,null,null,"Sta 47","100","1","Unit 2D - 16K inspection & turbochargers","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,47.002000000000002,null,"Sta 47:  Unit 2D - 16K inspection & turbochargers\n--6/9/25 through 7/25/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-324226",null,"2025-05-26","2025-05-28",null,null,null,"Sta 47","100","1","B Building - Clean Motor Control Center","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,47.017000000000003,null,"Sta 47:  B Building - Clean Motor Control Center\n--5/26/25 through 5/28/25:  This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-324227",null,"2025-05-26","2025-05-28",null,null,null,"Sta 47","100","1","C Building - Clean Motor Control Center","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,47.033000000000001,null,"Sta 47:  C Building - Clean Motor Control Center\n--5/26/25 through 5/28/25:  This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-324228",null,"2025-05-26","2025-05-28",null,null,null,"Sta 47","100","1","D Building - Clean Motor Control Center","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,47.048999999999999,null,"Sta 47:  D Building - Clean Motor Control Center\n--5/26/25 through 5/28/25:  This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-573537","***","2025-05-13","2025-05-19","Added",null,null,"Sta 47","100","1","Unit 1E - Surge Valve","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,47.064999999999998,"------","***Sta 47:  Unit 1E - Surge Valve\n--5/13/25 through 5/19/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-324229",null,"2025-05-26","2025-05-28",null,null,null,"Sta 47","100","1","E Building - Clean Motor Control Center","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,47.064999999999998,null,"Sta 47:  E Building - Clean Motor Control Center\n--5/26/25 through 5/28/25:  This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-35040",null,"2025-01-06","2025-10-31",null,null,null,"MLV 47-1AT to MLV 49-1","100","1","Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,47.1,null,"MLV 47-1AT to MLV 49-1:  Anomaly Remediation\n--1/6/25 through 10/31/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-82100",null,"2025-06-02","2025-11-30",null,null,null,"MLV 47-1A to MLV 48-1","100","1","Class Change","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,47.1,null,"MLV 47-1A to MLV 48-1:  Class Change\n--6/2/25 through 11/30/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-503626",null,"2025-07-21","2025-07-30",null,null,null,"MLV 47-2A to MLV 48-2","100","1","Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","47872 ATMOS TL/TGP CHAUVIN OUACHITA",47.1,null,"MLV 47-2A to MLV 48-2:  Anomaly Remediation\n--7/21/25 through 7/30/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n47872 ATMOS TL/TGP CHAUVIN OUACHITA\n………………………………"]
["X25-503629",null,"2025-09-01","2025-09-05",null,null,null,"MLV 47-3AT to MLV 47-3A","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,47.1,null,"MLV 47-3AT to MLV 47-3A:  Anomaly Remediation\n--9/1/25 through 9/5/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-195962",null,"2025-05-27","2025-05-31",null,null,null,"MLV 47-3D TO MLV 53-3CR","100","1","Pig Runs - Cleaning & Gauge 5/27 - 5/31","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","421062 ENTRGYLA/TGP PERRYVILLE POWER OUACH\n412352 EGT/TGP GUTHRIE EXCHANGE OUACHITA",47.3,null,"MLV 47-3D TO MLV 53-3CR:  Pig Runs - Cleaning & Gauge 5/27 - 5/31\n--5/27/25 through 5/31/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n421062 ENTRGYLA/TGP PERRYVILLE POWER OUACH\n412352 EGT/TGP GUTHRIE EXCHANGE OUACHITA\n………………………………"]
["X25-195963",null,"2025-06-03","2025-06-03",null,null,null,"MLV 47-3D TO MLV 53-3CR","100","1","Pig Runs - TDW MDS 6/3","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","421062 ENTRGYLA/TGP PERRYVILLE POWER OUACH\n412352 EGT/TGP GUTHRIE EXCHANGE OUACHITA",47.31,null,"MLV 47-3D TO MLV 53-3CR:  Pig Runs - TDW MDS 6/3\n--6/3/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n421062 ENTRGYLA/TGP PERRYVILLE POWER OUACH\n412352 EGT/TGP GUTHRIE EXCHANGE OUACHITA\n………………………………"]
["X25-503630",null,"2025-09-01","2025-09-05",null,null,null,"MLV 48-3 to MLV 49-3","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,48.1,null,"MLV 48-3 to MLV 49-3:  Anomaly Remediation\n--9/1/25 through 9/5/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-222569",null,"2025-03-04","2025-10-31",null,null,null,"MLV 49-1 to MLV 50-1","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,49.1,null,"MLV 49-1 to MLV 50-1:  Anomaly Remediation\n--3/4/25 through 10/31/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-503633",null,"2025-08-25","2025-08-29",null,null,null,"MLV 51-3 to MLV 52-3","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,51.1,null,"MLV 51-3 to MLV 52-3:  Anomaly Remediation\n--8/25/25 through 8/29/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-503632",null,"2025-08-11","2025-08-29",null,null,null,"MLV 52-2 to MLV 53-2","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,52.1,null,"MLV 52-2 to MLV 53-2:  Anomaly Remediation\n--8/11/25 through 8/29/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-503642",null,"2025-07-30","2025-08-08",null,null,null,"MLV 53-2 TO MLV 53-2CBR","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,53.1,null,"MLV 53-2 TO MLV 53-2CBR:  Anomaly Remediation\n--7/30/25 through 8/8/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-503634",null,"2025-08-25","2025-08-29",null,null,null,"MLV 53-3 to MLV 53-3CR","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,53.1,null,"MLV 53-3 to MLV 53-3CR:  Anomaly Remediation\n--8/25/25 through 8/29/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-173996",null,"2025-09-01","2025-10-15",null,null,null,"MLV 53-2BREH to MLV 53-2BR","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,53.2,null,"MLV 53-2BREH to MLV 53-2BR:  Anomaly Remediation\n--9/1/25 through 10/15/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-384736",null,"2025-08-04","2025-08-08",null,null,null,"Sta 54","100","1","Substation Inspection","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,54,null,"Sta 54:  Substation Inspection\n--8/4/25 through 8/8/25:  This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368171",null,"2025-09-08","2025-09-11",null,null,null,"Sta 54 Greenville","100","1","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,54,null,"Sta 54 Greenville:  Annual ESD Test & Maintenance\n--9/8/25 through 9/11/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-446008","***","2025-05-05","2025-05-09","Completed",null,null,"Sta 54","100","1","Unit 2D - Replace Excitation Panels - Siemens Electric","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,54.05,"------","***Sta 54:  Unit 2D - Replace Excitation Panels - Siemens Electric\n***Completed"]
["X25-86678",null,"2025-09-16","2025-09-16",null,null,null,"MLV 54-1D TO MLV 63-1S","100","1","Pig Runs - Cleaning / Gauge 9/16/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,54.1,null,"MLV 54-1D TO MLV 63-1S:  Pig Runs - Cleaning / Gauge 9/16/25\n--9/16/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-86679",null,"2025-09-18","2025-09-18",null,null,null,"MLV 54-1D TO MLV 63-1S","100","1","Pig Runs - CLP / IMU 9/18/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,54.11,null,"MLV 54-1D TO MLV 63-1S:  Pig Runs - CLP / IMU 9/18/25\n--9/18/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-86680",null,"2025-09-23","2025-09-23",null,null,null,"MLV 54-1D TO MLV 63-1S","100","1","Pig Runs - MFL-C 9/23/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,54.12,null,"MLV 54-1D TO MLV 63-1S:  Pig Runs - MFL-C 9/23/25\n--9/23/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-86681",null,"2025-09-25","2025-09-25",null,null,null,"MLV 54-1D TO MLV 63-1S","100","1","Pig Runs - MFL-C 9/25/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,54.13,null,"MLV 54-1D TO MLV 63-1S:  Pig Runs - MFL-C 9/25/25\n--9/25/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1176812","***","2025-05-09","2025-05-09","Completed",null,null,"MLV 54-2D TO MLV 63-2S","100","1","Pig Runs - MFL-A 5/09/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,54.21,"------","***MLV 54-2D TO MLV 63-2S:  Pig Runs - MFL-A 5/09/25\n***Completed"]
["X24-1176845",null,"2025-07-15","2025-07-15",null,null,null,"MLV 54-4D TO MLV 63-4S","100","1","Pig Runs - Cleaning / Gauge 7/15/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,54.4,null,"MLV 54-4D TO MLV 63-4S:  Pig Runs - Cleaning / Gauge 7/15/25\n--7/15/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1176930",null,"2025-07-17","2025-07-17",null,null,null,"MLV 54-4D TO MLV 63-4S","100","1","Pig Runs - Caliper 7/17/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,54.41,null,"MLV 54-4D TO MLV 63-4S:  Pig Runs - Caliper 7/17/25\n--7/17/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1176957",null,"2025-07-22","2025-07-22",null,null,null,"MLV 54-4D TO MLV 63-4S","100","1","Pig Runs - AFD 7/22/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,54.42,null,"MLV 54-4D TO MLV 63-4S:  Pig Runs - AFD 7/22/25\n--7/22/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1176989",null,"2025-07-24","2025-07-24",null,null,null,"MLV 54-4D TO MLV 63-4S","100","1","Pig Runs - EMAT 7/24/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,54.43,null,"MLV 54-4D TO MLV 63-4S:  Pig Runs - EMAT 7/24/25\n--7/24/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-343716",null,"2025-05-05","2025-05-15",null,null,null,"MLV 60-4 to MLV 61-4","100","1","Shallow Pipe Lowering","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,60.4,null,"MLV 60-4 to MLV 61-4:  Shallow Pipe Lowering\n--5/5/25 through 5/15/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368169",null,"2025-08-27","2025-08-27",null,null,null,"Sta 63 Batesville","100","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,63,null,"Sta 63 Batesville:  Annual ESD Test\n--8/27/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-86701",null,"2025-04-07","2025-06-06",null,null,null,"Sta 63","100","1","Unit 1D - Overhaul & Geislinger Coupling Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,63.048999999999999,null,"Sta 63:  Unit 1D - Overhaul & Geislinger Coupling Inspection\n--4/7/25 through 6/6/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-547556",null,"2025-06-24","2025-06-26",null,null,null,"Sta 63","100","1","Unit 1D - Safety Device Checks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,63.048999999999999,null,"Sta 63:  Unit 1D - Safety Device Checks\n--6/24/25 through 6/26/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-547555",null,"2025-07-01","2025-07-03",null,null,null,"Sta 63","100","1","Unit 2D - Safety Device Checks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,63.05,null,"Sta 63:  Unit 2D - Safety Device Checks\n--7/1/25 through 7/3/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-239162",null,"2025-06-17","2025-06-17",null,null,null,"MLV 63-2D to MLV 69-2","100","1","Pig Runs - Cleaning / Gauge 6/17/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,63.2,null,"MLV 63-2D to MLV 69-2:  Pig Runs - Cleaning / Gauge 6/17/25\n--6/17/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-239252",null,"2025-06-19","2025-06-19",null,null,null,"MLV 63-2D to MLV 69-2","100","1","Pig Runs - MDS 6/19/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,63.21,null,"MLV 63-2D to MLV 69-2:  Pig Runs - MDS 6/19/25\n--6/19/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-343764",null,"2025-05-19","2025-05-23",null,null,null,"MLV 63-4 to MLV 64-4","100","1","Shallow Pipe Lowering","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,63.4,null,"MLV 63-4 to MLV 64-4:  Shallow Pipe Lowering\n--5/19/25 through 5/23/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1082065","***","2025-05-08","2025-05-08","Completed",null,null,"MLV 63-2D to MLV 69-2","100","1","Pig Runs - EMAT 5/8/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,69.23,"------","***MLV 63-2D to MLV 69-2:  Pig Runs - EMAT 5/8/25\n***Completed"]
["X24-1368183",null,"2025-05-14","2025-05-15",null,null,null,"Sta 71 Middleton","100","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,71,null,"Sta 71 Middleton:  Annual ESD Test\n--5/14/25 through 5/15/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-1196655",null,"2023-11-28","2025-05-30",null,null,null,"Sta 71","100","1","Unit 3A - Discharge Bottle Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,71.003,null,"Sta 71:  Unit 3A - Discharge Bottle Inspection\n--11/28/23 through 5/30/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-262275",null,"2024-04-08","2025-05-30",null,null,null,"Sta 71","100","1","Unit 7A Replace Crank End Compressor Gasket","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,71.007000000000005,null,"Sta 71:  Unit 7A Replace Crank End Compressor Gasket\n--4/8/24 through 5/30/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-324113",null,"2025-03-17","2025-05-30",null,null,null,"Sta 71","100","1","Unit 2B - Jacket Water System","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,71.018000000000001,null,"Sta 71:  Unit 2B - Jacket Water System\n--3/17/25 through 5/30/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-239540",null,"2025-07-15","2025-07-15",null,null,null,"MLV 71-1D to MLV 77-1A","100","1","Pig Runs - Cleaning / Gauge 7/15/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,71.099999999999994,null,"MLV 71-1D to MLV 77-1A:  Pig Runs - Cleaning / Gauge 7/15/25\n--7/15/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-239670",null,"2025-07-17","2025-07-17",null,null,null,"MLV 71-1D to MLV 77-1A","100","1","Pig Runs - MDS 7/17/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,71.11,null,"MLV 71-1D to MLV 77-1A:  Pig Runs - MDS 7/17/25\n--7/17/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-238597",null,"2025-06-24","2025-06-24",null,null,null,"MLV 71-2D to MLV 79-2S","100","1","Pig Runs - EMAT 6/24/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,71.2,null,"MLV 71-2D to MLV 79-2S:  Pig Runs - EMAT 6/24/25\n--6/24/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1082041",null,"2025-10-28","2025-10-28",null,null,null,"MLV 71-4S to MLV 63-4D","100","1","Pig Runs - Cleaning / Gauge 10/28/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,71.400000000000006,null,"MLV 71-4S to MLV 63-4D:  Pig Runs - Cleaning / Gauge 10/28/25\n--10/28/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1082043",null,"2025-10-30","2025-10-30",null,null,null,"MLV 71-4S to MLV 63-4D","100","4","Pig Runs - Caliper / IMU 10/30/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,71.41,null,"MLV 71-4S to MLV 63-4D:  Pig Runs - Caliper / IMU 10/30/25\n--10/30/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1082045",null,"2025-11-04","2025-11-04",null,null,null,"MLV 71-4S to MLV 63-4D","100","1","Pig Runs - MFL-C 11/4/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,71.42,null,"MLV 71-4S to MLV 63-4D:  Pig Runs - MFL-C 11/4/25\n--11/4/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1082047",null,"2025-11-06","2025-11-06",null,null,null,"MLV 71-4S to MLV 63-4D","100","1","Pig Runs - EMAT 11/6/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,71.430000000000007,null,"MLV 71-4S to MLV 63-4D:  Pig Runs - EMAT 11/6/25\n--11/6/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368189","***","2025-05-08","2025-05-09","Completed",null,null,"Sta 79 Lobelville","100","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,79,"------","***Sta 79 Lobelville:  Annual ESD Test\n***Completed"]
["X25-239817",null,"2025-07-29","2025-07-29",null,null,null,"MLV 82-2C to MLV 87-2S","100","0","Pig Runs - Cleaning / Gauge 7/29/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,82.2,null,"MLV 82-2C to MLV 87-2S:  Pig Runs - Cleaning / Gauge 7/29/25\n--7/29/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-239878",null,"2025-07-31","2025-07-31",null,null,null,"MLV 82-2C to MLV 87-2S","100","1","Pig Runs - MDS 7/31/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,82.21,null,"MLV 82-2C to MLV 87-2S:  Pig Runs - MDS 7/31/25\n--7/31/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368208",null,"2025-10-21","2025-10-22",null,null,null,"Sta 87 Portland","100","2","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,87,null,"Sta 87 Portland:  Annual ESD Test\n--10/21/25 through 10/22/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-276460",null,"2025-04-28","2025-06-13",null,null,null,"Sta 87","100","2","Unit 3D - Turbocharger Exchange","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,87.051000000000002,null,"Sta 87:  Unit 3D - Turbocharger Exchange\n--4/28/25 through 6/13/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-521757",null,"2025-07-08","2025-07-14",null,null,null,"Sta 87","100","2","Unit 1E - Anchor Bolt Repairs","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,87.064999999999998,null,"Sta 87:  Unit 1E - Anchor Bolt Repairs\n--7/8/25 through 7/14/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-521758",null,"2025-07-14","2025-07-21",null,null,null,"Sta 87","100","2","Unit 2E - Anchor Bolt Repairs","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,87.066000000000003,null,"Sta 87:  Unit 2E - Anchor Bolt Repairs\n--7/14/25 through 7/21/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-1009116",null,"2025-11-04","2025-11-04",null,null,null,"MLV 87-4 to MLV 96-4","100","2","Pig Runs - Cleaning / Gauge 11/4/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,87.4,null,"MLV 87-4 to MLV 96-4:  Pig Runs - Cleaning / Gauge 11/4/25\n--11/4/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-69508",null,"2025-11-06","2025-11-06",null,null,null,"MLV 87-4 to MLV 96-4","100","2","Pig Runs - Caliper 11/6/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,87.4,null,"MLV 87-4 to MLV 96-4:  Pig Runs - Caliper 11/6/25\n--11/6/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1009137",null,"2025-11-11","2025-11-11",null,null,null,"MLV 87-4 to MLV 96-4","100","2","Pig Runs - AFD Combo 11/11/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,87.41,null,"MLV 87-4 to MLV 96-4:  Pig Runs - AFD Combo 11/11/25\n--11/11/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1009163",null,"2025-11-13","2025-11-13",null,null,null,"MLV 87-4 to MLV 96-4","100","2","Pig Runs - EMAT 11/13/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,87.42,null,"MLV 87-4 to MLV 96-4:  Pig Runs - EMAT 11/13/25\n--11/13/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-82079",null,"2025-07-21","2025-09-05",null,null,null,"MLV 90-3 to MLV 91-3","100","2","HDD River Crossing Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,90.3,null,"MLV 90-3 to MLV 91-3:  HDD River Crossing Replacement\n--7/21/25 through 9/5/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-82082",null,"2025-07-21","2025-09-05",null,null,null,"MLV 93-3 to MLV 94-3","100","2","HDD River Crossing Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,93.3,null,"MLV 93-3 to MLV 94-3:  HDD River Crossing Replacement\n--7/21/25 through 9/5/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-1368197",null,"2025-06-09","2025-06-12",null,null,null,"Sta 96 Campbellsville","100","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,96,null,"Sta 96 Campbellsville:  Annual ESD Test\n--6/9/25 through 6/12/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-1368198",null,"2025-06-09","2025-06-12",null,null,null,"Sta 96 Campbellsville","100","2","Annual Substation Inspection","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,96.000100000000003,null,"Sta 96 Campbellsville:  Annual Substation Inspection\n--6/9/25 through 6/12/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-573543","***","2025-09-22","2025-09-26","Added",null,null,"Sta 96","100","2","Unit 2D - Compressor Valves","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,96.05,"------","***Sta 96:  Unit 2D - Compressor Valves\n--9/22/25 through 9/26/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-1009324",null,"2025-09-25","2025-09-25",null,null,null,"MLV 96-5 to MLV 102-5","100","2","Pig Runs - Cleaning / Gauge 9/25/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,96.5,null,"MLV 96-5 to MLV 102-5:  Pig Runs - Cleaning / Gauge 9/25/25\n--9/25/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1009338",null,"2025-09-30","2025-09-30",null,null,null,"MLV 96-5 to MLV 102-5","100","2","Pig Runs - AFD Combo 9/30/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,96.51,null,"MLV 96-5 to MLV 102-5:  Pig Runs - AFD Combo 9/30/25\n--9/30/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1009343",null,"2025-10-02","2025-10-02",null,null,null,"MLV 96-5 to MLV 102-5","100","2","Pig Runs - EMAT 10/2/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,96.52,null,"MLV 96-5 to MLV 102-5:  Pig Runs - EMAT 10/2/25\n--10/2/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-324164",null,"2025-10-13","2025-10-18",null,null,null,"MLV 97-1 to MLV 96-1L","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,97.1,null,"MLV 97-1 to MLV 96-1L:  Anomaly Remediation\n--10/13/25 through 10/18/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-324167",null,"2025-10-20","2025-10-25",null,null,null,"MLV 99-1 to MLV 98-1","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,99.1,null,"MLV 99-1 to MLV 98-1:  Anomaly Remediation\n--10/20/25 through 10/25/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-324160",null,"2025-10-06","2025-10-11",null,null,null,"MLV 100-1A to MLV 100-1","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,100.1,null,"MLV 100-1A to MLV 100-1:  Anomaly Remediation\n--10/6/25 through 10/11/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-450067",null,"2025-07-14","2025-08-16",null,null,null,"MLV 101-5 to MLV 102-5","100","2","Class Change Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,101.5,null,"MLV 101-5 to MLV 102-5:  Class Change Pipe Replacement\n--7/14/25 through 8/16/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-1368157",null,"2025-06-02","2025-06-06",null,null,null,"Sta 106 Clay City","100","2","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,106,null,"Sta 106 Clay City:  Annual ESD Test & Maintenance\n--6/2/25 through 6/6/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-445995",null,"2025-06-02","2025-06-06",null,null,null,"Sta 106 Clay City","100","2","Upgrade B Building Jacket Water System","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,106.017,null,"Sta 106 Clay City:  Upgrade B Building Jacket Water System\n--6/2/25 through 6/6/25:  This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-431240","***","2025-06-16","2025-06-20","Project Change","2025-05-15","2025-05-30","Sta 106","100","2","Unit 6B - Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106.02200000000001,"--start_date--end_date------------model_loc--","***Sta 106:  Unit 6B - Engine Inspection\n--6/16/25 through 6/20/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 5/15/25 to 5/30/25.\n………………………………"]
["X25-550068","***","2025-05-06","2025-05-08","Completed",null,null,"Sta 106","100","2","Unit 7B - Punch Carbon","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106.023,"------","***Sta 106:  Unit 7B - Punch Carbon\n***Completed"]
["X25-445886","***","2025-04-14","2025-07-31","Project Change",null,"2025-05-31","Sta 106","100","2","Unit 1C - Replace Power Cylinder Bearing #7","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106.033,"----end_date------------model_loc--","***Sta 106:  Unit 1C - Replace Power Cylinder Bearing #7\n--4/14/25 through 7/31/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 4/14/25 to 5/31/25.\n………………………………"]
["X25-276816",null,"2025-06-08","2025-07-19",null,null,null,"MLV 106-1D to MLV 111-7BR","100","2","Make Piggable Valve MLV 107-7 & MLV 109-7 Replacements","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in during the project.","SIP","Potential secondary restrictions at the meter(s) may be at risk.","420946 MOREHEAD/TGP CITY OF MOREHEAD ROWAN\n55963 AHMLFG/TGP RUMPKE BIOGAS RECEIPT MO\n55964 AHMLFG/TGP RUMPKE BIOGAS BUYBACK DE",106.1,null,"MLV 106-1D to MLV 111-7BR:  Make Piggable Valve MLV 107-7 & MLV 109-7 Replacements\n--6/8/25 through 7/19/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420946 MOREHEAD/TGP CITY OF MOREHEAD ROWAN\n55963 AHMLFG/TGP RUMPKE BIOGAS RECEIPT MO\n55964 AHMLFG/TGP RUMPKE BIOGAS BUYBACK DE\n………………………………"]
["X24-1009349",null,"2025-10-09","2025-10-09",null,null,null,"MLV 106-1 to MLV 111-7","100","2","Pig Runs - Cleaning / Gauge 10/9/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,106.1,null,"MLV 106-1 to MLV 111-7:  Pig Runs - Cleaning / Gauge 10/9/25\n--10/9/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1009358",null,"2025-10-14","2025-10-14",null,null,null,"MLV 106-1 to MLV 111-7","100","2","Pig Runs - AFD Combo 10/14/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,106.11,null,"MLV 106-1 to MLV 111-7:  Pig Runs - AFD Combo 10/14/25\n--10/14/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1009364",null,"2025-10-16","2025-10-16",null,null,null,"MLV 106-1 to MLV 111-7","100","2","Pig Runs - EMAT 10/16/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,106.12,null,"MLV 106-1 to MLV 111-7:  Pig Runs - EMAT 10/16/25\n--10/16/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-200000","***","2025-05-26","2025-06-21","Project Change","2025-06-16",null,"MLV 106-3C to MLV 107-3","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,106.3,"--start_date--------------model_loc--","***MLV 106-3C to MLV 107-3:  Anomaly Remediation\n--5/26/25 through 6/21/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***\nDate Change, Previously scheduled 6/16/25 to 6/21/25.\n………………………………"]
["X25-352394",null,"2025-03-26","2025-05-17",null,null,null,"MLV 106-4 to MLV 108-4","100","2","PHMSA Immediate Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,106.4,null,"MLV 106-4 to MLV 108-4:  PHMSA Immediate Anomaly Remediation\n--3/26/25 through 5/17/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-547524",null,"2025-05-26","2025-05-30",null,null,null,"Sta 106 Clay City","100","2","D Plant MCC building - Replace Batteries","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,106.4,null,"Sta 106 Clay City:  D Plant MCC building - Replace Batteries\n--5/26/25 through 5/30/25:  This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-1368164",null,"2025-10-30","2025-10-30",null,null,null,"Sta 107A North Means","100","2","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,107,null,"Sta 107A North Means:  Annual ESD Test\n--10/30/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-199998",null,"2025-07-14","2025-07-27",null,null,null,"MLV 107-3 to MLV 108-3","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,107.3,null,"MLV 107-3 to MLV 108-3:  Anomaly Remediation\n--7/14/25 through 7/27/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-200017",null,"2025-04-21","2025-05-16",null,null,null,"MLV 107-4 to MLV 108-4","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,107.4,null,"MLV 107-4 to MLV 108-4:  Anomaly Remediation\n--4/21/25 through 5/16/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-276809",null,"2025-10-27","2025-11-28",null,null,null,"MLV 108-2 to MLV 109-2A","100","2","Special Permit Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420212 DELTA NG/TGP SALT LICK KY BATH\n420038 MOREHEAD/TGP MOREHEAD KY ROWAN",108.2,null,"MLV 108-2 to MLV 109-2A:  Special Permit Pipe Replacement\n--10/27/25 through 11/28/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420212 DELTA NG/TGP SALT LICK KY BATH\n420038 MOREHEAD/TGP MOREHEAD KY ROWAN\n………………………………"]
["X25-200004",null,"2025-07-28","2025-08-10",null,null,null,"MLV 108-3 to MLV 109-3","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,108.3,null,"MLV 108-3 to MLV 109-3:  Anomaly Remediation\n--7/28/25 through 8/10/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-276814",null,"2025-09-22","2025-10-24",null,null,null,"MLV 108-3 to MLV 109-3A","100","2","Special Permit Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,108.3,null,"MLV 108-3 to MLV 109-3A:  Special Permit Pipe Replacement\n--9/22/25 through 10/24/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-200016",null,"2025-04-28","2025-05-17",null,null,null,"MLV 108-4 to MLV 109-4","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,108.4,null,"MLV 108-4 to MLV 109-4:  Anomaly Remediation\n--4/28/25 through 5/17/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-199999",null,"2025-08-11","2025-08-24",null,null,null,"MLV 109-3 to MLV 109-3A","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,109.3,null,"MLV 109-3 to MLV 109-3A:  Anomaly Remediation\n--8/11/25 through 8/24/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-276784",null,"2025-09-22","2025-10-24",null,null,null,"MLV 109-3 to MLV 109-3A","100","2","Class Change Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,109.3,null,"MLV 109-3 to MLV 109-3A:  Class Change Pipe Replacement\n--9/22/25 through 10/24/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-200018",null,"2025-05-05","2025-05-17",null,null,null,"MLV 109-4 to MLV 110-4","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,109.4,null,"MLV 109-4 to MLV 110-4:  Anomaly Remediation\n--5/5/25 through 5/17/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-276837",null,"2025-10-06","2025-10-17",null,null,null,"MLV 109-4 to MLV 110-4","100","2","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,109.4,null,"MLV 109-4 to MLV 110-4:  Pipe Replacement\n--10/6/25 through 10/17/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-276785",null,"2025-07-14","2025-07-31",null,null,null,"MLV 109-5 to MLV 109-5A","100","2","Class Change Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,109.9,null,"MLV 109-5 to MLV 109-5A:  Class Change Pipe Replacement\n--7/14/25 through 7/31/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-1368158",null,"2025-05-27","2025-05-30",null,null,null,"Sta 110 Morehead","100","2","Annual ESD Test & Substation Inspection","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,110,null,"Sta 110 Morehead:  Annual ESD Test & Substation Inspection\n--5/27/25 through 5/30/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-579683","***","2025-05-15","2025-05-15","Added",null,null,"Sta 110 Morehead","100","2","Unit 8A - Oil System","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,110.008,"------","***Sta 110 Morehead:  Unit 8A - Oil System\n--5/15/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-547574",null,"2025-05-27","2025-05-30",null,null,null,"Sta 110 Morehead","100","2","Replace Transformers","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,110.1,null,"Sta 110 Morehead:  Replace Transformers\n--5/27/25 through 5/30/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-475029","***","2025-07-07","2025-07-07","Added",null,null,"MLV 110-2 to MLV 106-2","100","2","Pig Runs - Cleaning / Gauge 7/7/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SIP","Potential in the path restrictions may be at risk.",null,110.1,"------","***MLV 110-2 to MLV 106-2:  Pig Runs - Cleaning / Gauge 7/7/25\n--7/7/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential in the path restrictions may be at risk.\n***Added\n………………………………"]
["X25-475038","***","2025-07-08","2025-07-08","Added",null,null,"MLV 110-2 to MLV 106-2","100","2","Pig Runs - ROSEN MFL-A 7/8/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SIP","Potential in the path restrictions may be at risk.",null,110.2,"------","***MLV 110-2 to MLV 106-2:  Pig Runs - ROSEN MFL-A 7/8/25\n--7/8/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential in the path restrictions may be at risk.\n***Added\n………………………………"]
["X25-475036","***","2025-07-10","2025-07-10","Added",null,null,"MLV 110-2 to MLV 106-2","100","2","Pig Runs - TDW Caliper 7/10/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SIP","Potential in the path restrictions may be at risk.",null,110.3,"------","***MLV 110-2 to MLV 106-2:  Pig Runs - TDW Caliper 7/10/25\n--7/10/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential in the path restrictions may be at risk.\n***Added\n………………………………"]
["X25-200001",null,"2025-08-25","2025-08-31",null,null,null,"MLV 110-3 to MLV 111-3A","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,110.3,null,"MLV 110-3 to MLV 111-3A:  Anomaly Remediation\n--8/25/25 through 8/31/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-276834",null,"2025-08-04","2025-08-25",null,null,null,"MLV 111-3B to MLV 112-3","100","2","Make Piggable","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,111.3,null,"MLV 111-3B to MLV 112-3:  Make Piggable\n--8/4/25 through 8/25/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1009371",null,"2025-10-23","2025-10-23",null,null,null,"MLV 111-3 to MLV 114-3","100","2","Pig Runs - Cleaning / Gauge 10/23/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,111.3,null,"MLV 111-3 to MLV 114-3:  Pig Runs - Cleaning / Gauge 10/23/25\n--10/23/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1009383",null,"2025-10-28","2025-10-28",null,null,null,"MLV 111-3 to MLV 114-3","100","2","Pig Runs - AFD Combo 10/28/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,111.31,null,"MLV 111-3 to MLV 114-3:  Pig Runs - AFD Combo 10/28/25\n--10/28/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1009386",null,"2025-10-30","2025-10-30",null,null,null,"MLV 111-3 to MLV 114-3","100","2","Pig Runs - EMAT 10/30/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,111.32,null,"MLV 111-3 to MLV 114-3:  Pig Runs - EMAT 10/30/25\n--10/30/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-276836",null,"2025-08-18","2025-08-29",null,null,null,"MLV 112-3A to MLV 113-3","100","2","Pipe Replacement","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,112.3,null,"MLV 112-3A to MLV 113-3:  Pipe Replacement\n--8/18/25 through 8/29/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-485005",null,"2025-06-02","2025-06-06",null,null,null,"Sta 114 Catlettsburg","100","3","Substation Inspection","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,114,null,"Sta 114 Catlettsburg:  Substation Inspection\n--6/2/25 through 6/6/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-1368160",null,"2025-07-07","2025-07-09",null,null,null,"Sta 114 Catlettsburg","100","3","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,114,null,"Sta 114 Catlettsburg:  Annual ESD Test\n--7/7/25 through 7/9/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-500930","***","2025-07-14","2025-07-19","Project Change","2025-09-08","2025-09-10","Sta 114","100","3","Unit 1D - Turbine Swap","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,114.001,"--start_date--end_date--------prl----model_loc--","***Sta 114:  Unit 1D - Turbine Swap\n--7/14/25 through 7/19/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/8/25 to 9/10/25.\n………………………………"]
["X25-559530","***","2025-06-10","2025-06-11","Added",null,null,"Sta 114","100","3","Bldg D Replacement Batteries","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,114.1,"------","***Sta 114:  Bldg D Replacement Batteries\n--6/10/25 through 6/11/25:  This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-547484",null,"2025-06-02","2025-06-06",null,null,null,"Sta 114 Catlettsburg","100","3","C Building Motor Cleaning & Inspection","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,114.3,null,"Sta 114 Catlettsburg:  C Building Motor Cleaning & Inspection\n--6/2/25 through 6/6/25:  This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-199984","***","2025-05-07","2025-05-17","Completed",null,null,"MLV 115-2A to MLV 116-2","100","3","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,115.2,"------","***MLV 115-2A to MLV 116-2:  Anomaly Remediation\n***Completed"]
["X25-199997","***","2025-05-12","2025-05-25","Project Change","2025-05-18",null,"MLV 115-3 to MLV 116-3","100","3","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","PIP","Potential in the path restrictions may be at risk.","49274 CRANBERY/TGP BEECHFORK DELIVERY WAY",115.3,"--start_date--------------model_loc--","***MLV 115-3 to MLV 116-3:  Anomaly Remediation\n--5/12/25 through 5/25/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential in the path restrictions may be at risk.\n49274 CRANBERY/TGP BEECHFORK DELIVERY WAY\n***\nDate Change, Previously scheduled 5/18/25 to 5/25/25.\n………………………………"]
["X25-343689",null,"2025-05-25","2025-06-06",null,null,null,"MLV 116-3 to MLV 117-3","100","3","Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,116.3,null,"MLV 116-3 to MLV 117-3:  Anomaly Remediation\n--5/25/25 through 6/6/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-343690",null,"2025-05-26","2025-06-08",null,null,null,"MLV 117-3 to MLV 118-3","100","3","Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,117.3,null,"MLV 117-3 to MLV 118-3:  Anomaly Remediation\n--5/26/25 through 6/8/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-1368165",null,"2025-09-16","2025-09-18",null,null,null,"Sta 118A Tyler Mountain","100","3","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,118,null,"Sta 118A Tyler Mountain:  Annual ESD Test\n--9/16/25 through 9/18/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-412717",null,"2025-06-09","2025-06-11",null,null,null,"Sta 118A Tyler Mountain","100","3","Unit 1A - 4k Hr Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,118.001,null,"Sta 118A Tyler Mountain:  Unit 1A - 4k Hr Inspection\n--6/9/25 through 6/11/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-366364",null,"2025-10-06","2025-10-10",null,null,null,"Sta 118A","100","3","Unit 1A - Turbine Exchange","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,118.001,null,"Sta 118A:  Unit 1A - Turbine Exchange\n--10/6/25 through 10/10/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368156",null,"2025-09-09","2025-09-11",null,null,null,"Sta 119A Rocky Fork","100","3","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,119,null,"Sta 119A Rocky Fork:  Annual ESD Test\n--9/9/25 through 9/11/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-480944",null,"2025-08-25","2025-08-27",null,null,null,"Sta 119A Tyler Mountain","100","3","Unit 1A - 4k Hr Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,119.001,null,"Sta 119A Tyler Mountain:  Unit 1A - 4k Hr Inspection\n--8/25/25 through 8/27/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-559531","***","2025-06-12","2025-06-13","Added",null,null,"Sta 119A Tyler Mountain","100","3","Replacement Batteries","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,119.1,"------","***Sta 119A Tyler Mountain:  Replacement Batteries\n--6/12/25 through 6/13/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-199995","***","2025-06-21","2025-06-28","Project Change",null,null,"MLV 119-2BL to MLV 119-2A","100","3","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","PIP","Potential in the path restrictions may be at risk.","420749 CRANBERY/TGP CRANBERRY SALES KANAWH\n54003 BP ENERG/TGP US METHANOL KANAWHA",119.2,"------meters_affected----------model_loc--","***MLV 119-2BL to MLV 119-2A:  Anomaly Remediation\n--6/21/25 through 6/28/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential in the path restrictions may be at risk.\n420749 CRANBERY/TGP CRANBERRY SALES KANAWH\n54003 BP ENERG/TGP US METHANOL KANAWHA\n***Project Change\n………………………………"]
["X25-199992",null,"2025-06-07","2025-06-28",null,null,null,"MLV 120-2 to MLV 121-2","100","3","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,120.2,null,"MLV 120-2 to MLV 121-2:  Anomaly Remediation\n--6/7/25 through 6/28/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-1368163",null,"2025-07-14","2025-07-18",null,null,null,"Sta 200 Greenup","200","4","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,200,null,"Sta 200 Greenup:  Annual ESD Test\n--7/14/25 through 7/18/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-537493","***","2025-05-19","2025-05-23","Project Change","2025-06-30","2025-07-03","Sta 200","200","4","Unit 3A - Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,200.00299999999999,"--start_date--end_date------------model_loc--","***Sta 200:  Unit 3A - Engine Inspection\n--5/19/25 through 5/23/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 6/30/25 to 7/3/25.\n………………………………"]
["X25-537575",null,"2025-07-14","2025-07-17",null,null,null,"Sta 200","200","4","Unit 6A - Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,200.006,null,"Sta 200:  Unit 6A - Engine Inspection\n--7/14/25 through 7/17/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-521748","***","2025-05-12","2025-05-14","Completed",null,null,"Sta 200","200","4","Unit 8A - Investigate oil sample concerns","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,200.00800000000001,"------","***Sta 200:  Unit 8A - Investigate oil sample concerns\n***Completed"]
["X25-537530",null,"2025-07-07","2025-07-10",null,null,null,"Sta 200","200","4","Unit 11A - Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,200.011,null,"Sta 200:  Unit 11A - Engine Inspection\n--7/7/25 through 7/10/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-35008","***","2025-05-13","2025-05-13","Completed",null,null,"MLV 200-2 to MLV 110-4","100","2","Pig Re-Runs - EMAT 5/13/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,200.2,"------","***MLV 200-2 to MLV 110-4:  Pig Re-Runs - EMAT 5/13/25\n***Completed"]
["X25-38342","***","2025-05-05","2025-05-09","Completed",null,null,"Sta 204","200","4","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,204,"------","***Sta 204:  Annual ESD Test & Maintenance\n***Completed"]
["X25-334671",null,"2025-09-22","2025-09-24",null,null,null,"Sta 204","200","4","Scrubber Filter","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,204,null,"Sta 204:  Scrubber Filter\n--9/22/25 through 9/24/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-547462",null,"2025-05-19","2025-05-23",null,null,null,"Sta 204","200","4","Unit 6A - Main Bearing Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,204.006,null,"Sta 204:  Unit 6A - Main Bearing Replacement\n--5/19/25 through 5/23/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-547463",null,"2025-06-16","2025-06-27",null,null,null,"Sta 204","200","4","Unit 11A - Compressor Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,204.011,null,"Sta 204:  Unit 11A - Compressor Inspection\n--6/16/25 through 6/27/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-155912",null,"2025-05-19","2025-06-01",null,null,null,"MLV 204-2 to MLV 205-2","200","4","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,204.2,null,"MLV 204-2 to MLV 205-2:  Anomaly Remediation\n--5/19/25 through 6/1/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1017097",null,"2025-07-29","2025-07-29",null,null,null,"MLV 204-2 to MLV 200-2","200","4","Pig Runs - Cleaning / Gauge 7/29/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","421018 TET/TGP HANGING ROCK SCIOTO",204.2,null,"MLV 204-2 to MLV 200-2:  Pig Runs - Cleaning / Gauge 7/29/25\n--7/29/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n421018 TET/TGP HANGING ROCK SCIOTO\n………………………………"]
["X24-1017099",null,"2025-07-31","2025-07-31",null,null,null,"MLV 204-2 to MLV 200-2","200","4","Pig Runs - MFL-A Combo 7/31/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","421018 TET/TGP HANGING ROCK SCIOTO",204.21,null,"MLV 204-2 to MLV 200-2:  Pig Runs - MFL-A Combo 7/31/25\n--7/31/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n421018 TET/TGP HANGING ROCK SCIOTO\n………………………………"]
["X24-1017102",null,"2025-08-05","2025-08-05",null,null,null,"MLV 204-2 to MLV 200-2","200","4","Pig Runs - Residual 8/5/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","421018 TET/TGP HANGING ROCK SCIOTO",204.22,null,"MLV 204-2 to MLV 200-2:  Pig Runs - Residual 8/5/25\n--8/5/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n421018 TET/TGP HANGING ROCK SCIOTO\n………………………………"]
["X25-35079",null,"2025-08-07","2025-08-07",null,null,null,"MLV 204-2 to MLV 200-2","200","4","Pig Runs - MFL-C 8/7/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","421018 TET/TGP HANGING ROCK SCIOTO",204.23,null,"MLV 204-2 to MLV 200-2:  Pig Runs - MFL-C 8/7/25\n--8/7/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n421018 TET/TGP HANGING ROCK SCIOTO\n………………………………"]
["X25-35083",null,"2025-08-12","2025-08-12",null,null,null,"MLV 204-2 to MLV 200-2","200","4","Pig Runs - EMAT 8/12/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","421018 TET/TGP HANGING ROCK SCIOTO",204.24,null,"MLV 204-2 to MLV 200-2:  Pig Runs - EMAT 8/12/25\n--8/12/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n421018 TET/TGP HANGING ROCK SCIOTO\n………………………………"]
["X25-155911","***","2025-05-05","2025-05-24","Project Change",null,"2025-05-14","MLV 205-2 to MLV 206-2","200","4","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,205.2,"----end_date--------prl----model_loc--","***MLV 205-2 to MLV 206-2:  Anomaly Remediation\n--5/5/25 through 5/24/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 5/5/25 to 5/14/25.\n………………………………"]
["X25-192219",null,"2025-05-19","2025-05-31",null,null,null,"MLV 205-2 to MLV 206-2","200","4","Landslide Mitigation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,205.2,null,"MLV 205-2 to MLV 206-2:  Landslide Mitigation\n--5/19/25 through 5/31/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-219101",null,"2025-07-01","2025-09-01",null,null,null,"MLV 205-2 to MLV 206-2","200","4","Special Permit Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,205.2,null,"MLV 205-2 to MLV 206-2:  Special Permit Replacement\n--7/1/25 through 9/1/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-155908","***","2025-05-05","2025-05-10","Completed",null,null,"MLV 207-2 to MLV 208-2","200","4","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,207.2,"------","***MLV 207-2 to MLV 208-2:  Anomaly Remediation\n***Completed"]
["X25-573779","***","2025-05-14","2025-05-17","Added",null,null,"MLV 207-2 to MLV 208-2","200","4","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,207.2,"------","***MLV 207-2 to MLV 208-2:  Anomaly Remediation\n--5/14/25 through 5/17/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-38343",null,"2025-05-12","2025-05-16",null,null,null,"Sta 209 Cambridge","200","4","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,209,null,"Sta 209 Cambridge:  Annual ESD Test & Maintenance\n--5/12/25 through 5/16/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-334672",null,"2025-09-25","2025-09-27",null,null,null,"Sta 209 Cambridge","200","4","Scrubber Filter","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209,null,"Sta 209 Cambridge:  Scrubber Filter\n--9/25/25 through 9/27/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-218341","***","2025-05-05","2025-05-09","Completed",null,null,"Sta 209","200","4","Unit 13A - Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209.01300000000001,"------","***Sta 209:  Unit 13A - Crankcase Inspection\n***Completed"]
["X25-547465",null,"2025-05-19","2025-05-23",null,null,null,"Sta 209","200","4","Unit 13A - Turbo Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,209.01300000000001,null,"Sta 209:  Unit 13A - Turbo Replacement\n--5/19/25 through 5/23/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1016928",null,"2025-06-03","2025-06-03",null,null,null,"MLV 209-2 to MLV 204-2","200","4","Pig Runs - Cleaning Gauge 7/15/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,209.2,null,"MLV 209-2 to MLV 204-2:  Pig Runs - Cleaning Gauge 7/15/25\n--6/3/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1016946",null,"2025-06-05","2025-06-05",null,null,null,"MLV 209-2 to MLV 204-2","200","4","Pig Runs - MFL-A Combo 7/17/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,209.21,null,"MLV 209-2 to MLV 204-2:  Pig Runs - MFL-A Combo 7/17/25\n--6/5/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1017066",null,"2025-11-11","2025-11-11",null,null,null,"MLV 209-4 to MLV 204-4","200","4","Pig Runs - Cleaning / Gauge 11/11/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,209.4,null,"MLV 209-4 to MLV 204-4:  Pig Runs - Cleaning / Gauge 11/11/25\n--11/11/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1017067",null,"2025-11-13","2025-11-13",null,null,null,"MLV 209-4 to MLV 204-4","200","4","Pig Runs - MFL-A Combo 11/13/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,209.41,null,"MLV 209-4 to MLV 204-4:  Pig Runs - MFL-A Combo 11/13/25\n--11/13/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-219096",null,"2025-05-27","2025-06-30",null,null,null,"MLV 209-3 to MLV 210-3A","200","4","Class Change Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,210.3,null,"MLV 209-3 to MLV 210-3A:  Class Change Replacement\n--5/27/25 through 6/30/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-219100",null,"2025-09-01","2025-10-31",null,null,null,"MLV 213-2A to MLV 214-2","200","4","Special Permit Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,213.2,null,"MLV 213-2A to MLV 214-2:  Special Permit Replacement\n--9/1/25 through 10/31/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-176915",null,"2025-06-09","2025-06-13",null,null,null,"Sta 214","200","4","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,214,null,"Sta 214:  Annual ESD Test & Maintenance\n--6/9/25 through 6/13/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-475076",null,"2025-08-26","2025-08-26",null,null,null,"MLV 214-1 to MLV 209-1","200","4","Pig Re-Runs - EMAT 8/26/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,214.1,null,"MLV 214-1 to MLV 209-1:  Pig Re-Runs - EMAT 8/26/25\n--8/26/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-219099",null,"2025-07-01","2025-09-01",null,null,null,"MLV 216-2 to MLV 216-2A","200","4","Class Change Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,216.2,null,"MLV 216-2 to MLV 216-2A:  Class Change Replacement\n--7/1/25 through 9/1/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-177243",null,"2025-08-04","2025-08-07",null,null,null,"Sta 219","200","4","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,219,null,"Sta 219:  Annual ESD Test\n--8/4/25 through 8/7/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-177114",null,"2025-07-14","2025-07-18",null,null,null,"Sta 219","200","4","Unit 1A to 6A - Protective Device Checks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,219.001,null,"Sta 219:  Unit 1A to 6A - Protective Device Checks\n--7/14/25 through 7/18/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-177247",null,"2025-07-14","2025-07-18",null,null,null,"Sta 219","200","4","Unit 7A to 13A - Protective Device Checks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,219.00700000000001,null,"Sta 219:  Unit 7A to 13A - Protective Device Checks\n--7/14/25 through 7/18/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-449909",null,"2025-05-05","2025-06-13",null,null,null,"Sta 219","200","4","Unit 10A - Install New Foundation Chocks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,219.01,null,"Sta 219:  Unit 10A - Install New Foundation Chocks\n--5/5/25 through 6/13/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-449911",null,"2025-05-05","2025-06-13",null,null,null,"Sta 219","200","4","Unit 11A - Install New Foundation Chocks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,219.011,null,"Sta 219:  Unit 11A - Install New Foundation Chocks\n--5/5/25 through 6/13/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-177123",null,"2025-08-04","2025-08-07",null,null,null,"Sta 219","200","4","Unit 13A - Unit Valve Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,219.01300000000001,null,"Sta 219:  Unit 13A - Unit Valve Replacement\n--8/4/25 through 8/7/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-177124",null,"2025-08-04","2025-08-07",null,null,null,"Sta 219","200","4","Unit 13A - Mounting Valve Operators / Testing","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,219.01310000000001,null,"Sta 219:  Unit 13A - Mounting Valve Operators / Testing\n--8/4/25 through 8/7/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-576582","***","2025-05-19","2025-05-22","Added",null,null,"Sta 219","200","4","Unit 1B - Rod Packing","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,219.017,"------","***Sta 219:  Unit 1B - Rod Packing\n--5/19/25 through 5/22/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-177245",null,"2025-08-04","2025-08-07",null,null,null,"Sta 219","200","4","Unit 1B - Protective Device Checks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,219.017,null,"Sta 219:  Unit 1B - Protective Device Checks\n--8/4/25 through 8/7/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1017104",null,"2025-08-19","2025-08-19",null,null,null,"MLV 219-4 to MLV 214-4","200","4","Pig Runs - Cleaning / Gauge 8/19/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,219.4,null,"MLV 219-4 to MLV 214-4:  Pig Runs - Cleaning / Gauge 8/19/25\n--8/19/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1017105",null,"2025-08-21","2025-08-21",null,null,null,"MLV 219-4 to MLV 214-4","200","4","Pig Runs - MFL-A Combo 8/21/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,219.41,null,"MLV 219-4 to MLV 214-4:  Pig Runs - MFL-A Combo 8/21/25\n--8/21/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1017106",null,"2025-08-26","2025-08-26",null,null,null,"MLV 219-4 to MLV 214-4","200","4","Pig Runs - EMAT 8/26/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,219.42,null,"MLV 219-4 to MLV 214-4:  Pig Runs - EMAT 8/26/25\n--8/26/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-34917",null,"2025-06-10","2025-06-11",null,null,null,"Sta 224","200","5","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,224,null,"Sta 224:  Annual ESD Test\n--6/10/25 through 6/11/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-34918",null,"2025-05-14","2025-05-15",null,null,null,"Sta 229","200","5","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,229,null,"Sta 229:  Annual ESD Test & Maintenance\n--5/14/25 through 5/15/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-34920",null,"2025-07-16","2025-07-17",null,null,null,"Station 230C","200","5","Annual ESD","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.   The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","410902 TRANSCAN/TGP UDP NIAGARA RIVER NIAG\n421079 TRANSCAN/TGP UDP NIAGARA RIVER DELI",230,null,"Station 230C:  Annual ESD\n--7/16/25 through 7/17/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.   The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n410902 TRANSCAN/TGP UDP NIAGARA RIVER NIAG\n421079 TRANSCAN/TGP UDP NIAGARA RIVER DELI\n………………………………"]
["X25-34896",null,"2025-05-20","2025-05-22",null,null,null,"MLV 230B-201 to MLV 230B-207","200","5","Pig Run - Maintenance Cleaning 5/20 - 5/22","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,230.2,null,"MLV 230B-201 to MLV 230B-207:  Pig Run - Maintenance Cleaning 5/20 - 5/22\n--5/20/25 through 5/22/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-155753",null,"2025-05-20","2025-05-20",null,null,null,"Sta 233","300","5","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,233,null,"Sta 233:  Annual ESD Test\n--5/20/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-155755",null,"2025-05-21","2025-05-21",null,null,null,"Sta 233","300","5","Point to Point and Trans Cals","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,233.00001,null,"Sta 233:  Point to Point and Trans Cals\n--5/21/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-219102",null,"2025-08-11","2025-09-12",null,null,null,"MLV 236-1 to MLV 237-1BR","200","5","Special Permit Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be constrained or shut in during the project.","SIP","Potential secondary restrictions at the meter(s) may be at risk.","412856 EMPIREPL/TGP CANANDIAGUA ONTARIO\n420617 EGTS/TGP HOPEWELL SALES ONTARIO",236.1,null,"MLV 236-1 to MLV 237-1BR:  Special Permit Replacement\n--8/11/25 through 9/12/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n412856 EMPIREPL/TGP CANANDIAGUA ONTARIO\n420617 EGTS/TGP HOPEWELL SALES ONTARIO\n………………………………"]
["X25-155770",null,"2025-08-05","2025-08-05",null,null,null,"Station 237","200","5","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,237,null,"Station 237:  Annual ESD Test\n--8/5/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-155771",null,"2025-08-06","2025-08-06",null,null,null,"Station 237","200","5","Point to Point and Trans Cals","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,237.00001,null,"Station 237:  Point to Point and Trans Cals\n--8/6/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-155769",null,"2025-07-23","2025-07-23",null,null,null,"Sta 237","200","5","400 Line Filter/Scrubber Change","This project may require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,237.0001,null,"Sta 237:  400 Line Filter/Scrubber Change\n--7/23/25:  This project may require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-155758",null,"2025-06-26","2025-06-26",null,null,null,"Sta 237","200","5","Unit 3A - Unit 3A Device Tests","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,237.00299999999999,null,"Sta 237:  Unit 3A - Unit 3A Device Tests\n--6/26/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-155961",null,"2025-10-06","2025-10-11",null,null,null,"MLV 240-1A to MLV 241-1","200","5","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,240.1,null,"MLV 240-1A to MLV 241-1:  Anomaly Remediation\n--10/6/25 through 10/11/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-155756",null,"2025-06-17","2025-06-17",null,null,null,"Sta 241","200","5","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,241,null,"Sta 241:  Annual ESD Test\n--6/17/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-155757",null,"2025-06-18","2025-06-18",null,null,null,"Sta 241","200","5","Point to Point and Trans Cals","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,241.00001,null,"Sta 241:  Point to Point and Trans Cals\n--6/18/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-174026","***","2025-05-19","2025-06-21","Project Change",null,null,"Sta 241","200","5","Unit 1A - Main Bearing, Turbo, Compressor Boring & Valve Operator","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,241.001,"------------prl----model_loc--","***Sta 241:  Unit 1A - Main Bearing, Turbo, Compressor Boring & Valve Operator\n--5/19/25 through 6/21/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***Project Change\n………………………………"]
["X25-155760",null,"2025-08-11","2025-08-11",null,null,null,"Sta 241","200","5","Unit 1A - Device and Relief Valve Tests","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,241.001,null,"Sta 241:  Unit 1A - Device and Relief Valve Tests\n--8/11/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-155761",null,"2025-08-12","2025-08-12",null,null,null,"Sta 241","200","5","Unit 2A - Device and Relief Valve Tests","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,241.00200000000001,null,"Sta 241:  Unit 2A - Device and Relief Valve Tests\n--8/12/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-155759",null,"2025-07-15","2025-07-16",null,null,null,"Sta 241","200","5","Unit 3A - Device and Relief Valve Tests","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,241.00299999999999,null,"Sta 241:  Unit 3A - Device and Relief Valve Tests\n--7/15/25 through 7/16/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-174024",null,"2025-09-08","2025-09-27",null,null,null,"Sta 241","200","5","Unit 3A - C3 Cooper Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,241.00299999999999,null,"Sta 241:  Unit 3A - C3 Cooper Upgrade\n--9/8/25 through 9/27/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-155762",null,"2025-08-13","2025-08-13",null,null,null,"Sta 241","200","5","Unit 1B - Device and Relief Valve Tests","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,241.017,null,"Sta 241:  Unit 1B - Device and Relief Valve Tests\n--8/13/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-155765",null,"2025-10-07","2025-10-08",null,null,null,"Sta 241","200","5","Unit 1B - 2K Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,241.0171,null,"Sta 241:  Unit 1B - 2K Maintenance\n--10/7/25 through 10/8/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-155763",null,"2025-08-14","2025-08-14",null,null,null,"Sta 241","200","5","Unit 2B - Device and Relief Valve Tests","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,241.018,null,"Sta 241:  Unit 2B - Device and Relief Valve Tests\n--8/14/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-155764",null,"2025-10-09","2025-10-10",null,null,null,"Sta 241","200","5","Unit 2B - 2K Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,241.0181,null,"Sta 241:  Unit 2B - 2K Maintenance\n--10/9/25 through 10/10/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-155965",null,"2025-10-06","2025-10-11",null,null,null,"MLV 241-1 to MLV 242-1","200","5","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,241.1,null,"MLV 241-1 to MLV 242-1:  Anomaly Remediation\n--10/6/25 through 10/11/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-155964",null,"2025-10-13","2025-10-18",null,null,null,"MLV 242-1 to MLV 243-1","200","5","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,242.1,null,"MLV 242-1 to MLV 243-1:  Anomaly Remediation\n--10/13/25 through 10/18/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-155967",null,"2025-10-13","2025-10-25",null,null,null,"MLV 244-1 to MLV 245-1S","200","5","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,244.1,null,"MLV 244-1 to MLV 245-1S:  Anomaly Remediation\n--10/13/25 through 10/25/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-101287","***","2025-05-14","2025-05-15","Completed",null,null,"Sta 245 West Winfield","200","5","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,245,"------","***Sta 245 West Winfield:  Annual ESD Test\n***Completed"]
["X25-69555",null,"2025-09-08","2025-09-12",null,null,null,"Sta 245","200","5","Unit 1C - Engine Exchange","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,245.03299999999999,null,"Sta 245:  Unit 1C - Engine Exchange\n--9/8/25 through 9/12/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-152224","***","2025-05-27","2025-05-27","Project Change","2025-05-12","2025-05-12","Sta 245-1 to MLV 249-1","200","5","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,245.1,"--start_date--end_date--------prl----model_loc--","***Sta 245-1 to MLV 249-1:  Pig Run - Maintenance\n--5/27/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n***\nDate Change, Previously scheduled 5/12/25.\n………………………………"]
["X25-570911","***","2025-05-27","2025-05-27","Added",null,null,"Sta 249","200","5","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,249,"------","***Sta 249:  Annual ESD Test\n--5/27/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***Added\n………………………………"]
["X25-101468","***","2025-04-28","2025-05-09","Completed",null,null,"Sta 249","200","5","Unit 1A - Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,249.001,"------","***Sta 249:  Unit 1A - Crankcase Inspection\n***Completed"]
["X25-101475",null,"2025-05-12","2025-05-16",null,null,null,"Sta 249","200","5","Unit 2A - Engine Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,249.00200000000001,null,"Sta 249:  Unit 2A - Engine Maintenance\n--5/12/25 through 5/16/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-457603","***","2025-05-16","2025-05-21","Project Change","2025-05-19","2025-05-23","Sta 249","200","5","Unit 2B - Compressor Rod & Packing Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,249.018,"--start_date--end_date------------model_loc--","***Sta 249:  Unit 2B - Compressor Rod & Packing Replacement\n--5/16/25 through 5/21/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 5/19/25 to 5/23/25.\n………………………………"]
["X25-521575","***","2025-05-05","2025-05-15","Project Change",null,"2025-05-09","Sta 254 Nassau","200","5","Units 1A, 2A, 3A & 4A - Engine Inspections","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,254.001,"----end_date------------model_loc--","***Sta 254 Nassau:  Units 1A, 2A, 3A & 4A - Engine Inspections\n--5/5/25 through 5/15/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 5/5/25 to 5/9/25.\n………………………………"]
["X25-174156",null,"2025-09-23","2025-09-23",null,null,null,"MLV 254-1 to MLV 261-1","200","5","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,254.1,null,"MLV 254-1 to MLV 261-1:  Pig Run - Maintenance\n--9/23/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-174157",null,"2025-09-24","2025-09-24",null,null,null,"MLV 254-2 to MLV 261-2","200","5","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,254.2,null,"MLV 254-2 to MLV 261-2:  Pig Run - Maintenance\n--9/24/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-174159",null,"2025-09-25","2025-09-25",null,null,null,"MLV 254-3 to MLV 258-3","200","5","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,254.3,null,"MLV 254-3 to MLV 258-3:  Pig Run - Maintenance\n--9/25/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-573452","***","2025-05-12","2025-05-16","Added",null,null,"MLV 255-1 to MLV 256-1","200","5","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,255.1,"------","***MLV 255-1 to MLV 256-1:  Anomaly Remediation\n--5/12/25 through 5/16/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-445876",null,"2025-06-09","2025-06-21",null,null,null,"MLV 256A-201","200","6","ECDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420102 BERKSHR/TGP PITTSFIELD MA BERKSHIRE",256.2,null,"MLV 256A-201:  ECDA\n--6/9/25 through 6/21/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420102 BERKSHR/TGP PITTSFIELD MA BERKSHIRE\n………………………………"]
["X25-155928",null,"2025-04-28","2025-06-21",null,null,null,"MLV 258-1 to MLV 259-1","200","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,258.10000000000002,null,"MLV 258-1 to MLV 259-1:  Anomaly Remediation\n--4/28/25 through 6/21/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-155930",null,"2025-06-23","2025-07-19",null,null,null,"MLV 259-1 to MLV 260-1","200","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,259.10000000000002,null,"MLV 259-1 to MLV 260-1:  Anomaly Remediation\n--6/23/25 through 7/19/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-104697",null,"2025-09-23","2025-09-23",null,null,null,"Sta 260A Southwick","200","6","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,260,null,"Sta 260A Southwick:  Annual ESD Test\n--9/23/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1020199",null,"2026-05-04","2026-05-04",null,null,null,"MLV 260A-101.1 TO MLV 260A-103","200","6","Pig Runs - MFL-C 7/15/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420104 WESTFLD/TGP WESTFIELD MA HAMPDEN\n420401 HOLYOKE/TGP HOLYOKE MA 2 HAMPDEN\n420292 BERKSHR/TGP GREENFIELD MA HAMPSHIRE\n420106 EVRSRC/TGP GRANITE NORTHAMPTON MA H",260.11,null,"MLV 260A-101.1 TO MLV 260A-103:  Pig Runs - MFL-C 7/15/25\n--5/4/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420104 WESTFLD/TGP WESTFIELD MA HAMPDEN\n420401 HOLYOKE/TGP HOLYOKE MA 2 HAMPDEN\n420292 BERKSHR/TGP GREENFIELD MA HAMPSHIRE\n420106 EVRSRC/TGP GRANITE NORTHAMPTON MA H\n………………………………"]
["X25-445878",null,"2025-05-26","2025-06-07",null,null,null,"MLV 260A-201","200","6","ECDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420106 WESTFLD/GP WESTFIELD MA HAMPDEN",260.2,null,"MLV 260A-201:  ECDA\n--5/26/25 through 6/7/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420106 WESTFLD/GP WESTFIELD MA HAMPDEN\n………………………………"]
["X25-104695",null,"2025-09-16","2025-09-18",null,null,null,"Sta 261 Agawam","200","6","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420901 BERKPWR/TGP BERKSHIRE POWER SALES H",261,null,"Sta 261 Agawam:  Annual ESD Test\n--9/16/25 through 9/18/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420901 BERKPWR/TGP BERKSHIRE POWER SALES H\n………………………………"]
["X25-427478",null,"2025-06-10","2025-06-12",null,null,null,"Sta 261","200","6","Unit 4A - Compressor Rod Packing","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420901 BERKPWR/TGP BERKSHIRE POWER SALES H",261.00400000000002,null,"Sta 261:  Unit 4A - Compressor Rod Packing\n--6/10/25 through 6/12/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420901 BERKPWR/TGP BERKSHIRE POWER SALES H\n………………………………"]
["X25-82384","***","2025-05-14","2025-05-15","Completed",null,null,"Sta 261","200","6","Unit 5A - 4K Maintenance Activity and Water Wash","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,261.005,"------","***Sta 261:  Unit 5A - 4K Maintenance Activity and Water Wash\n***Completed"]
["X25-82379","***","2025-05-12","2025-05-13","Completed",null,null,"Sta 261","200","6","Unit 1C - 4K Maintenance Activity and Water Wash","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,261.03300000000002,"------","***Sta 261:  Unit 1C - 4K Maintenance Activity and Water Wash\n***Completed"]
["X25-427481","***","2025-05-16","2025-05-16","Completed",null,null,"Sta 261","200","6","Unit 2D - Water Wash","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,261.05,"------","***Sta 261:  Unit 2D - Water Wash\n***Completed"]
["X25-386869",null,"2025-05-19","2025-06-07",null,null,null,"MLV 261BP-101","200","6","ECDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420901 BERKPWR/TGP BERKSHIRE POWER SALES H",261.10000000000002,null,"MLV 261BP-101:  ECDA\n--5/19/25 through 6/7/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420901 BERKPWR/TGP BERKSHIRE POWER SALES H\n………………………………"]
["X25-550158",null,"2025-09-16","2025-09-30",null,null,null,"MLV 262-2 to 263-2","200","6","Pipe Replacement & Install New 30\" MLV","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,262.2,null,"MLV 262-2 to 263-2:  Pipe Replacement & Install New 30\" MLV\n--9/16/25 through 9/30/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-550155",null,"2025-08-12","2025-08-30",null,null,null,"MLV 263-2 to 264-2","200","6","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,263.2,null,"MLV 263-2 to 264-2:  Pipe Replacement\n--8/12/25 through 8/30/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-104693",null,"2025-09-25","2025-09-25",null,null,null,"Sta 264 Charlton","200","6","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,264,null,"Sta 264 Charlton:  Annual ESD Test\n--9/25/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-155969",null,"2025-07-21","2025-07-26",null,null,null,"MLV 264B-101.1 to MLV 264B-101.1R","200","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,264.10000000000002,null,"MLV 264B-101.1 to MLV 264B-101.1R:  Anomaly Remediation\n--7/21/25 through 7/26/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-550154",null,"2025-07-15","2025-07-30",null,null,null,"MLV 264-2 to 264-2A","200","6","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,264.2,null,"MLV 264-2 to 264-2A:  Pipe Replacement\n--7/15/25 through 7/30/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-520791",null,"2025-10-03","2025-10-14",null,null,null,"MLV 265E-103 to MLV 265E-104","200","6","Regulator Installation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be constrained or shut in during the project.","PIP","Potential in the path restrictions may be at risk.","420750 NARNGST/TGP CRANSTON SALES PROVIDEN\n420926 RISEC/TGP FPLE RISE PROVIDENCE\n55784 RHOBIO/TGP SCITUATE RNG REC PROVIDE\n55785 RHOBIO/TGP SCITUATE RNG BUYBACK PR\n420910 NARNGST/TGP SMITHFIELD DELIVERY PRO\n420758 NARNGST/TGP LINCOLN SMS PROVIDENCE",265.10000000000002,null,"MLV 265E-103 to MLV 265E-104:  Regulator Installation\n--10/3/25 through 10/14/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be constrained or shut in during the project.  Potential in the path restrictions may be at risk.\n420750 NARNGST/TGP CRANSTON SALES PROVIDEN\n420926 RISEC/TGP FPLE RISE PROVIDENCE\n55784 RHOBIO/TGP SCITUATE RNG REC PROVIDE\n55785 RHOBIO/TGP SCITUATE RNG BUYBACK PR\n420910 NARNGST/TGP SMITHFIELD DELIVERY PRO\n420758 NARNGST/TGP LINCOLN SMS PROVIDENCE\n………………………………"]
["X24-1020284",null,"2025-12-10","2025-12-10",null,null,null,"MLV 265E-201 to MLV 265E-202","200","6","Pig Runs - Cleaning / Gauge 12/10/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420758 NARNGST/TGP LINCOLN SMS PROVIDENCE",265.2,null,"MLV 265E-201 to MLV 265E-202:  Pig Runs - Cleaning / Gauge 12/10/25\n--12/10/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420758 NARNGST/TGP LINCOLN SMS PROVIDENCE\n………………………………"]
["X24-1020336",null,"2025-12-10","2025-12-10",null,null,null,"MLV 265E-201 to MLV 265E-202","200","6","Pig Runs - MFL-A / Cal / IMU Combo 12/10/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420758 NARNGST/TGP LINCOLN SMS PROVIDENCE",265.20999999999998,null,"MLV 265E-201 to MLV 265E-202:  Pig Runs - MFL-A / Cal / IMU Combo 12/10/25\n--12/10/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420758 NARNGST/TGP LINCOLN SMS PROVIDENCE\n………………………………"]
["X25-352408",null,"2025-06-02","2025-06-11",null,null,null,"MLV 266A-102A to 266A-104A","200","6","Make Piggable - Tee Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420135 NARNGST/TGP PAWTUCKET RI PROVIDENCE",266.10000000000002,null,"MLV 266A-102A to 266A-104A:  Make Piggable - Tee Replacement\n--6/2/25 through 6/11/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420135 NARNGST/TGP PAWTUCKET RI PROVIDENCE\n………………………………"]
["X24-1020233",null,"2025-07-22","2025-07-22",null,null,null,"MLV 266A-102A TO MLV 266A-104A","200","6","Pig Runs - Cleaning / Gauge 7/22/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420424 HESS/TGP BELLINGHAM MA NORFOLD\n420135 NARNGST/TGP PAWTUCKET RI PROVIDENCE",266.14,null,"MLV 266A-102A TO MLV 266A-104A:  Pig Runs - Cleaning / Gauge 7/22/25\n--7/22/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420424 HESS/TGP BELLINGHAM MA NORFOLD\n420135 NARNGST/TGP PAWTUCKET RI PROVIDENCE\n………………………………"]
["X24-1020268",null,"2025-07-23","2025-07-23",null,null,null,"MLV 266A-102A TO MLV 266A-104A","200","6","Pig Runs - MFL-A / Cal / IMU Combo 7/23/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420424 HESS/TGP BELLINGHAM MA NORFOLD\n420135 NARNGST/TGP PAWTUCKET RI PROVIDENCE",266.14999999999998,null,"MLV 266A-102A TO MLV 266A-104A:  Pig Runs - MFL-A / Cal / IMU Combo 7/23/25\n--7/23/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420424 HESS/TGP BELLINGHAM MA NORFOLD\n420135 NARNGST/TGP PAWTUCKET RI PROVIDENCE\n………………………………"]
["X25-438209",null,"2025-10-27","2025-12-19",null,null,null,"Sta. 267","200","6","Bldg A Controls Upgrade","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,267.00099999999998,null,"Sta. 267:  Bldg A Controls Upgrade\n--10/27/25 through 12/19/25:  This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-155974",null,"2025-07-14","2025-07-19",null,null,null,"MLV 267-1A to MLV 268-1","200","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,267.10000000000002,null,"MLV 267-1A to MLV 268-1:  Anomaly Remediation\n--7/14/25 through 7/19/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1020346",null,"2025-12-18","2025-12-18",null,null,null,"MLV 268A-301A TO MLV 268A-302","200","6","Pig Runs - Cleaning / Gauge 12/18/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420111 BOSTN/TGP LEOMINSTER MA WORCHESTER",268.3,null,"MLV 268A-301A TO MLV 268A-302:  Pig Runs - Cleaning / Gauge 12/18/25\n--12/18/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420111 BOSTN/TGP LEOMINSTER MA WORCHESTER\n………………………………"]
["X24-1020369",null,"2025-12-18","2025-12-18",null,null,null,"MLV 268A-301A TO MLV 268A-302","200","6","Pig Runs - MFL-A / Cal / IMU Combo 12/18/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420111 BOSTN/TGP LEOMINSTER MA WORCHESTER",268.31,null,"MLV 268A-301A TO MLV 268A-302:  Pig Runs - MFL-A / Cal / IMU Combo 12/18/25\n--12/18/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420111 BOSTN/TGP LEOMINSTER MA WORCHESTER\n………………………………"]
["X24-847658",null,"2025-04-07","2025-06-23",null,null,null,"MLV 270C-103 to MLV 270C-104","200","6","Meter Station Upgrade (Meter Peabody PIN 420658)","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420658 MMWEC/TGP PEABODY SALES ESSEX",270.10000000000002,null,"MLV 270C-103 to MLV 270C-104:  Meter Station Upgrade (Meter Peabody PIN 420658)\n--4/7/25 through 6/23/25:  This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420658 MMWEC/TGP PEABODY SALES ESSEX\n………………………………"]
["X25-334666",null,"2025-05-03","2025-05-16",null,null,null,"MLV 270C-100","200","6","ECDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420658 MMWEC/TGP PEABODY SALES ESSEX",270.10000000000002,null,"MLV 270C-100:  ECDA\n--5/3/25 through 5/16/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential secondary restrictions at the meter(s) may be at risk.\n420658 MMWEC/TGP PEABODY SALES ESSEX\n………………………………"]
["X25-475021",null,"2025-07-21","2025-07-26",null,null,null,"MLV 270-1A to MLV 270-101.1R","200","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,270.10000000000002,null,"MLV 270-1A to MLV 270-101.1R:  Anomaly Remediation\n--7/21/25 through 7/26/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-155979",null,"2025-08-04","2025-08-22",null,null,null,"MLV 270C-101.1 to MLV 270C-101BL","200","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420136 BOST/TGP READING MA MIDDLESEX",270.10000000000002,null,"MLV 270C-101.1 to MLV 270C-101BL:  Anomaly Remediation\n--8/4/25 through 8/22/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420136 BOST/TGP READING MA MIDDLESEX\n………………………………"]
["X25-327428",null,"2025-05-20","2025-05-22",null,null,null,"MLV 270B-104A to 270B-104B","200","6","Meter Station Maintenance (Meter Granite Ridge PIN 420931)","This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420931 LIBERTYU/TGP GRANITE RIDGE ROCKINGH",270.10399999999998,null,"MLV 270B-104A to 270B-104B:  Meter Station Maintenance (Meter Granite Ridge PIN 420931)\n--5/20/25 through 5/22/25:  This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420931 LIBERTYU/TGP GRANITE RIDGE ROCKINGH\n………………………………"]
["X25-330585",null,"2025-05-13","2025-05-21",null,null,null,"MLV 270B-105B to 270B-106C","200","6","Make Piggable - Valve & Tees replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420254 LIBERTYU/TGP HOOKSETT NH MERRIMACK\n47591 CLEANNRG/TGP TOWN OF PEMBROKE MERRI\n49831 NG ADVAN/TGP CNG PEMBROKE RECEIPT M\n420426 LIBERTYU/TGP LACONIA NH MERRIMACK",270.10500000000002,null,"MLV 270B-105B to 270B-106C:  Make Piggable - Valve & Tees replacement\n--5/13/25 through 5/21/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420254 LIBERTYU/TGP HOOKSETT NH MERRIMACK\n47591 CLEANNRG/TGP TOWN OF PEMBROKE MERRI\n49831 NG ADVAN/TGP CNG PEMBROKE RECEIPT M\n420426 LIBERTYU/TGP LACONIA NH MERRIMACK\n………………………………"]
["X24-1017379",null,"2025-06-03","2025-06-03",null,null,null,"MLV 270B-101.1 TO MLV 270B-103","200","6","Pig Runs - Cleaning / Gauge 6/3/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","421025 EVRSRC/TG WYETH GII ESSEX",270.14,null,"MLV 270B-101.1 TO MLV 270B-103:  Pig Runs - Cleaning / Gauge 6/3/25\n--6/3/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n421025 EVRSRC/TG WYETH GII ESSEX\n………………………………"]
["X24-1017377",null,"2025-06-04","2025-06-04",null,null,null,"MLV 270B-101.1 TO MLV 270B-103","200","6","Pig Runs - MFL-C / Cal / IMU Combo 6/4/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","421025 EVRSRC/TG WYETH GII ESSEX",270.14999999999998,null,"MLV 270B-101.1 TO MLV 270B-103:  Pig Runs - MFL-C / Cal / IMU Combo 6/4/25\n--6/4/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n421025 EVRSRC/TG WYETH GII ESSEX\n………………………………"]
["X24-1017380",null,"2025-06-09","2025-06-09",null,null,null,"MLV 270B-104B TO MLV 270B-105A","200","6","Pig Runs - Cleaning / Gauge 6/9/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420132 LIBERTYU/TGP NASHUA NH HILLSBOROUGH\n420931 LIBERTYU/GTGP GRANITE RIDGE ROCKINGH\n420632 LIBERTYU/TGP LONDONDERRY SALES ROCK\n420133 LIBERTYU/TGP MANCHESTER NH HILLSBOR\n420254 LIBERTYU/TGP HOOKSETT NH MERRIMACK\n420451 LIBERTYU/TGP SUNCOOK NH MERRIMACK\n47591 CLEANNRG/TGP TOWN OF PEMBROKE MERRI\n49831 NG ADVAN/TGP CNG PEMBROKE RECEIPT M\n420426 LIBERTYU/TGP LACONIA NH MERRIMACK",270.16000000000003,null,"MLV 270B-104B TO MLV 270B-105A:  Pig Runs - Cleaning / Gauge 6/9/25\n--6/9/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420132 LIBERTYU/TGP NASHUA NH HILLSBOROUGH\n420931 LIBERTYU/GTGP GRANITE RIDGE ROCKINGH\n420632 LIBERTYU/TGP LONDONDERRY SALES ROCK\n420133 LIBERTYU/TGP MANCHESTER NH HILLSBOR\n420254 LIBERTYU/TGP HOOKSETT NH MERRIMACK\n420451 LIBERTYU/TGP SUNCOOK NH MERRIMACK\n47591 CLEANNRG/TGP TOWN OF PEMBROKE MERRI\n49831 NG ADVAN/TGP CNG PEMBROKE RECEIPT M\n420426 LIBERTYU/TGP LACONIA NH MERRIMACK\n………………………………"]
["X24-1017381",null,"2025-06-10","2025-06-10",null,null,null,"MLV 270B-104B TO MLV 270B-105A","200","6","Pig Runs - Cal / IMU 6/10/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420132 LIBERTYU/TGP NASHUA NH HILLSBOROUGH\n420931 LIBERTYU/GTGP GRANITE RIDGE ROCKINGH\n420632 LIBERTYU/TGP LONDONDERRY SALES ROCK\n420133 LIBERTYU/TGP MANCHESTER NH HILLSBOR\n420254 LIBERTYU/TGP HOOKSETT NH MERRIMACK\n420451 LIBERTYU/TGP SUNCOOK NH MERRIMACK\n47591 CLEANNRG/TGP TOWN OF PEMBROKE MERRI\n49831 NG ADVAN/TGP CNG PEMBROKE RECEIPT M\n420426 LIBERTYU/TGP LACONIA NH MERRIMACK",270.17,null,"MLV 270B-104B TO MLV 270B-105A:  Pig Runs - Cal / IMU 6/10/25\n--6/10/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420132 LIBERTYU/TGP NASHUA NH HILLSBOROUGH\n420931 LIBERTYU/GTGP GRANITE RIDGE ROCKINGH\n420632 LIBERTYU/TGP LONDONDERRY SALES ROCK\n420133 LIBERTYU/TGP MANCHESTER NH HILLSBOR\n420254 LIBERTYU/TGP HOOKSETT NH MERRIMACK\n420451 LIBERTYU/TGP SUNCOOK NH MERRIMACK\n47591 CLEANNRG/TGP TOWN OF PEMBROKE MERRI\n49831 NG ADVAN/TGP CNG PEMBROKE RECEIPT M\n420426 LIBERTYU/TGP LACONIA NH MERRIMACK\n………………………………"]
["X25-77460",null,"2025-06-12","2025-06-12",null,null,null,"MLV 270B-104B TO MLV 270B-105A","200","6","Pig Runs - MFL-C 6/12/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420132 LIBERTYU/TGP NASHUA NH HILLSBOROUGH\n420931 LIBERTYU/GTGP GRANITE RIDGE ROCKINGH\n420632 LIBERTYU/TGP LONDONDERRY SALES ROCK\n420133 LIBERTYU/TGP MANCHESTER NH HILLSBOR\n420254 LIBERTYU/TGP HOOKSETT NH MERRIMACK\n420451 LIBERTYU/TGP SUNCOOK NH MERRIMACK\n47591 CLEANNRG/TGP TOWN OF PEMBROKE MERRI\n49831 NG ADVAN/TGP CNG PEMBROKE RECEIPT M\n420426 LIBERTYU/TGP LACONIA NH MERRIMACK",270.17500000000001,null,"MLV 270B-104B TO MLV 270B-105A:  Pig Runs - MFL-C 6/12/25\n--6/12/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420132 LIBERTYU/TGP NASHUA NH HILLSBOROUGH\n420931 LIBERTYU/GTGP GRANITE RIDGE ROCKINGH\n420632 LIBERTYU/TGP LONDONDERRY SALES ROCK\n420133 LIBERTYU/TGP MANCHESTER NH HILLSBOR\n420254 LIBERTYU/TGP HOOKSETT NH MERRIMACK\n420451 LIBERTYU/TGP SUNCOOK NH MERRIMACK\n47591 CLEANNRG/TGP TOWN OF PEMBROKE MERRI\n49831 NG ADVAN/TGP CNG PEMBROKE RECEIPT M\n420426 LIBERTYU/TGP LACONIA NH MERRIMACK\n………………………………"]
["X24-1020093",null,"2025-06-17","2025-06-17",null,null,null,"MLV 270B-105B TO MLV 270B-106","200","6","Pig Runs - Cleaning / Gauge 6/17/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420132 LIBERTYU/TGP NASHUA NH HILLSBOROUGH\n420931 LIBERTYU/TGP GRANITE RIDGE ROCKINGH\n420632 LIBERTYU/TGP LONDONDERRY SALES ROCK\n420133 LIBERTYU/TGP MANCHESTER NH HILLSBOR\n420254 LIBERTYU/TGP HOOKSETT NH MERRIMACK\n420451 LIBERTYU/TGP SUNCOOK NH MERRIMACK\n47591 CLEANNRG/TGP TOWN OF PEMBROKE MERRI\n49831 NG ADVAN/TGP CNG PEMBROKE RECEIPT M\n420426 LIBERTYU/TGP LACONIA NH MERRIMACK",270.18,null,"MLV 270B-105B TO MLV 270B-106:  Pig Runs - Cleaning / Gauge 6/17/25\n--6/17/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420132 LIBERTYU/TGP NASHUA NH HILLSBOROUGH\n420931 LIBERTYU/TGP GRANITE RIDGE ROCKINGH\n420632 LIBERTYU/TGP LONDONDERRY SALES ROCK\n420133 LIBERTYU/TGP MANCHESTER NH HILLSBOR\n420254 LIBERTYU/TGP HOOKSETT NH MERRIMACK\n420451 LIBERTYU/TGP SUNCOOK NH MERRIMACK\n47591 CLEANNRG/TGP TOWN OF PEMBROKE MERRI\n49831 NG ADVAN/TGP CNG PEMBROKE RECEIPT M\n420426 LIBERTYU/TGP LACONIA NH MERRIMACK\n………………………………"]
["X24-1020155",null,"2025-06-18","2025-06-18",null,null,null,"MLV 270B-105B TO MLV 270B-106","200","6","Pig Runs - MFL-A / Cal /IMU Combo 6/18/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420132 LIBERTYU/TGP NASHUA NH HILLSBOROUGH\n420931 LIBERTYU/TGP GRANITE RIDGE ROCKINGH\n420632 LIBERTYU/TGP LONDONDERRY SALES ROCK\n420133 LIBERTYU/TGP MANCHESTER NH HILLSBOR\n420254 LIBERTYU/TGP HOOKSETT NH MERRIMACK\n420451 LIBERTYU/TGP SUNCOOK NH MERRIMACK\n47591 CLEANNRG/TGP TOWN OF PEMBROKE MERRI\n49831 NG ADVAN/TGP CNG PEMBROKE RECEIPT M\n420426 LIBERTYU/TGP LACONIA NH MERRIMACK",270.19,null,"MLV 270B-105B TO MLV 270B-106:  Pig Runs - MFL-A / Cal /IMU Combo 6/18/25\n--6/18/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420132 LIBERTYU/TGP NASHUA NH HILLSBOROUGH\n420931 LIBERTYU/TGP GRANITE RIDGE ROCKINGH\n420632 LIBERTYU/TGP LONDONDERRY SALES ROCK\n420133 LIBERTYU/TGP MANCHESTER NH HILLSBOR\n420254 LIBERTYU/TGP HOOKSETT NH MERRIMACK\n420451 LIBERTYU/TGP SUNCOOK NH MERRIMACK\n47591 CLEANNRG/TGP TOWN OF PEMBROKE MERRI\n49831 NG ADVAN/TGP CNG PEMBROKE RECEIPT M\n420426 LIBERTYU/TGP LACONIA NH MERRIMACK\n………………………………"]
["X25-155981",null,"2025-09-02","2025-09-20",null,null,null,"MLV 270C-501 to MLV 270C-501A","200","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420138 BOSTN/TGP WENHAM MA ESSEX",270.5,null,"MLV 270C-501 to MLV 270C-501A:  Anomaly Remediation\n--9/2/25 through 9/20/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420138 BOSTN/TGP WENHAM MA ESSEX\n………………………………"]
["X25-155983",null,"2025-06-23","2025-06-28",null,null,null,"MLV 273B-101L to MLV 273B-101A","200","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,273.10000000000002,null,"MLV 273B-101L to MLV 273B-101A:  Anomaly Remediation\n--6/23/25 through 6/28/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-177132",null,"2025-05-26","2025-05-30",null,null,null,"Sta 303A","300","4","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,303,null,"Sta 303A:  Annual ESD Test & Maintenance\n--5/26/25 through 5/30/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-177134",null,"2025-05-19","2025-05-20",null,null,null,"Sta 303A","300","4","Unit 1A - Water Wash","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,303.00099999999998,null,"Sta 303A:  Unit 1A - Water Wash\n--5/19/25 through 5/20/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-177133",null,"2025-05-26","2025-05-30",null,null,null,"Sta 303A","300","4","Unit 1A - Protective Device Checks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,303.00099999999998,null,"Sta 303A:  Unit 1A - Protective Device Checks\n--5/26/25 through 5/30/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-177135",null,"2025-11-18","2025-11-19",null,null,null,"Sta 303A","300","4","Unit 1A - Water Wash","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,303.00099999999998,null,"Sta 303A:  Unit 1A - Water Wash\n--11/18/25 through 11/19/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-177137",null,"2025-08-04","2025-08-08",null,null,null,"Sta 307 (Pigeon )","300","4","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,307,null,"Sta 307 (Pigeon ):  Annual ESD Test\n--8/4/25 through 8/8/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-177139",null,"2025-07-21","2025-07-22",null,null,null,"Sta 307","300","4","Unit 1A - Protective Device Checks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,307.00099999999998,null,"Sta 307:  Unit 1A - Protective Device Checks\n--7/21/25 through 7/22/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-177249",null,"2025-07-23","2025-07-25",null,null,null,"Sta 307","300","4","Unit 2A - Protective Device Checks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,307.00200000000001,null,"Sta 307:  Unit 2A - Protective Device Checks\n--7/23/25 through 7/25/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-177141",null,"2025-07-28","2025-07-29",null,null,null,"Sta 307","300","4","Unit 3A - Protective Device Checks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,307.00299999999999,null,"Sta 307:  Unit 3A - Protective Device Checks\n--7/28/25 through 7/29/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-177252",null,"2025-07-30","2025-08-01",null,null,null,"Sta 307","300","4","Unit 4A - Protective Device Checks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,307.00400000000002,null,"Sta 307:  Unit 4A - Protective Device Checks\n--7/30/25 through 8/1/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-547683",null,"2025-05-05","2025-05-16",null,null,null,"Sta 307","300","4","Unit 5A - Power Cylinder Investigation","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,307.005,null,"Sta 307:  Unit 5A - Power Cylinder Investigation\n--5/5/25 through 5/16/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-573416","***","2025-06-16","2025-06-20","Added",null,null,"Sta 307","300","4","Unit 5A - Engine Testing","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,307.005,"------","***Sta 307:  Unit 5A - Engine Testing\n--6/16/25 through 6/20/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-177142",null,"2025-08-04","2025-08-05",null,null,null,"Sta 307","300","4","Unit 5A - Protective Device Checks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,307.005,null,"Sta 307:  Unit 5A - Protective Device Checks\n--8/4/25 through 8/5/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-177254",null,"2025-08-06","2025-08-08",null,null,null,"Sta 307","300","4","Unit 6A - Protective Device Checks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,307.00599999999997,null,"Sta 307:  Unit 6A - Protective Device Checks\n--8/6/25 through 8/8/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-445915",null,"2025-06-17","2025-06-18",null,null,null,"Sta 310","300","4","Unit 1A - Water Wash & Borescope","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,310.00099999999998,null,"Sta 310:  Unit 1A - Water Wash & Borescope\n--6/17/25 through 6/18/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-412720",null,"2025-08-19","2025-08-21",null,null,null,"Sta 313 Coudersport","300","4","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,313,null,"Sta 313 Coudersport:  Annual ESD Test\n--8/19/25 through 8/21/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-219119",null,"2025-10-27","2025-11-07",null,null,null,"MLV 313-0806","300","4","Drip Removal","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,313.8,null,"MLV 313-0806:  Drip Removal\n--10/27/25 through 11/7/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-222807",null,"2025-05-19","2025-05-23",null,null,null,"Sta 315 Wellsboro","300","4","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,315,null,"Sta 315 Wellsboro:  Annual ESD Test\n--5/19/25 through 5/23/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-1090163",null,"2025-05-19","2025-05-23",null,null,null,"Sta 315 Wellsboro","300","4","Station Blowdown Silencer","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,315,null,"Sta 315 Wellsboro:  Station Blowdown Silencer\n--5/19/25 through 5/23/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-445917",null,"2025-06-11","2025-06-12",null,null,null,"Sta 315","300","4","Unit 2A - Water Wash & Borescope","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,315.00200000000001,null,"Sta 315:  Unit 2A - Water Wash & Borescope\n--6/11/25 through 6/12/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-445916",null,"2025-06-09","2025-06-10",null,null,null,"Sta 315","300","4","Unit 1B - Water Wash & Borescope","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,315.017,null,"Sta 315:  Unit 1B - Water Wash & Borescope\n--6/9/25 through 6/10/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-547649",null,"2025-07-14","2025-07-15",null,null,null,"MLV 317-1 to MLV 318-1","300","4","Hot Tap for New Meter (Meter: Port Royal PIN: 57162)","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","412784\tETC NEPL/TGP ALLEN MEADOW DEHY:RIP \n412785\tBLCKHILL/TGP SWAIN ROAD DEHY: RIP 3\n412834\tAPPLACHA/TGP UDP CALKINS DEHY: RIP \n412850\tAPPLACHA/TGP UDP LIBERTY DEHY: RIP \n420216\tVALLEY/TGP TOWANDA PA BRADFORD",317.10000000000002,null,"MLV 317-1 to MLV 318-1:  Hot Tap for New Meter (Meter: Port Royal PIN: 57162)\n--7/14/25 through 7/15/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n412784\tETC NEPL/TGP ALLEN MEADOW DEHY:RIP \n412785\tBLCKHILL/TGP SWAIN ROAD DEHY: RIP 3\n412834\tAPPLACHA/TGP UDP CALKINS DEHY: RIP \n412850\tAPPLACHA/TGP UDP LIBERTY DEHY: RIP \n420216\tVALLEY/TGP TOWANDA PA BRADFORD\n………………………………"]
["X25-547653",null,"2025-07-16","2025-07-17",null,null,null,"MLV 317-2 to MLV 318-2","300","4","Hot Tap for New Meter (Meter: Port Royal PIN: 57162)","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","412784\tETC NEPL/TGP ALLEN MEADOW DEHY:RIP \n412785\tBLCKHILL/TGP SWAIN ROAD DEHY: RIP 3\n412834\tAPPLACHA/TGP UDP CALKINS DEHY: RIP \n412850\tAPPLACHA/TGP UDP LIBERTY DEHY: RIP \n420216\tVALLEY/TGP TOWANDA PA BRADFORD",317.2,null,"MLV 317-2 to MLV 318-2:  Hot Tap for New Meter (Meter: Port Royal PIN: 57162)\n--7/16/25 through 7/17/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n412784\tETC NEPL/TGP ALLEN MEADOW DEHY:RIP \n412785\tBLCKHILL/TGP SWAIN ROAD DEHY: RIP 3\n412834\tAPPLACHA/TGP UDP CALKINS DEHY: RIP \n412850\tAPPLACHA/TGP UDP LIBERTY DEHY: RIP \n420216\tVALLEY/TGP TOWANDA PA BRADFORD\n………………………………"]
["X25-348332",null,"2025-06-12","2025-06-12",null,null,null,"Sta 321","300","4","Station Valves for ESD System","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,321,null,"Sta 321:  Station Valves for ESD System\n--6/12/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-201791","***","2025-02-20","2025-08-31","Completed",null,null,"Sta 321","300","4","Unit 5B - Emergent Repair","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,321.017,"------","***Sta 321:  Unit 5B - Emergent Repair\n***Completed"]
["X25-573667","***","2025-09-29","2025-09-30","Added",null,null,"Sta. 323A Lackawaxen","300","4","Annual ESD Testing","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,323,"------","***Sta. 323A Lackawaxen:  Annual ESD Testing\n--9/29/25 through 9/30/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-573665","***","2025-09-29","2025-10-03","Added",null,null,"Sta 323","300","4","Unit 1A - Drive Modernization Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,323.00099999999998,"------","***Sta 323:  Unit 1A - Drive Modernization Upgrade\n--9/29/25 through 10/3/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-155988",null,"2025-07-28","2025-08-07",null,null,null,"MLV 324-1B to MLV 325-1","300","4","Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420319 UGI UT/TGP MILFORD PA PIKE",324.10000000000002,null,"MLV 324-1B to MLV 325-1:  Anomaly Remediation\n--7/28/25 through 8/7/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420319 UGI UT/TGP MILFORD PA PIKE\n………………………………"]
["X25-537678",null,"2025-06-23","2025-07-01",null,null,null,"Sta 327","300","5","Unit 1A - Solar Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,327.00099999999998,null,"Sta 327:  Unit 1A - Solar Inspection\n--6/23/25 through 7/1/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-155990",null,"2025-07-21","2025-07-26",null,null,null,"MLV 327-2B to MLV 328-2","300","5","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,327.2,null,"MLV 327-2B to MLV 328-2:  Anomaly Remediation\n--7/21/25 through 7/26/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-334667",null,"2025-07-07","2025-07-20",null,null,null,"MLV 339-1","300","5","ECDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","PIP","Potential in the path restrictions may be at risk.","420124 YANK GAS/TGP STAMFORD CT FAIRFIELD",339.1,null,"MLV 339-1:  ECDA\n--7/7/25 through 7/20/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential in the path restrictions may be at risk.\n420124 YANK GAS/TGP STAMFORD CT FAIRFIELD\n………………………………"]
["X25-431154",null,"2025-06-23","2025-07-01",null,null,null,"MLV 346-1","300","6","MLV Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","PIP","Potential in the path restrictions may be at risk.","420425 CONN NG/TGP MILFORD CT NEW HAVEN",346.1,null,"MLV 346-1:  MLV Replacement\n--6/23/25 through 7/1/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  Potential in the path restrictions may be at risk.\n420425 CONN NG/TGP MILFORD CT NEW HAVEN\n………………………………"]
["X25-237175",null,"2025-10-14","2025-10-14",null,null,null,"MLV 400-1 to MLV 409-1","400","0","Pig Run - Maintenance Cleaning 10/14/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","412733  UES/TGP MYRICK BROOKS\n55152   TGP/KMTEJAS KING RANCH EXCH #2 ROLL\n412400  LOBO/TGP KING RANCH JIM WELLS\n410633\tGCENGY/TGP EL EBANITO DEHY STARR\n410729\tKMTEJAS/TGP ZIM DEHYDRATION STARR\n412088\tETP/TGP MONTE CHRISTO EXCH HIDALGO\n412683\tHESCO CO/TGP RAYMONDVILLE HIDALGO\n420878\tGGUC/TGP RINCON DEHYD STARR\n412458\tETP/TGP GILMORE PLANT RESIDUE HIDAL",400.1,null,"MLV 400-1 to MLV 409-1:  Pig Run - Maintenance Cleaning 10/14/25\n--10/14/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n412733  UES/TGP MYRICK BROOKS\n55152   TGP/KMTEJAS KING RANCH EXCH #2 ROLL\n412400  LOBO/TGP KING RANCH JIM WELLS\n410633\tGCENGY/TGP EL EBANITO DEHY STARR\n410729\tKMTEJAS/TGP ZIM DEHYDRATION STARR\n412088\tETP/TGP MONTE CHRISTO EXCH HIDALGO\n412683\tHESCO CO/TGP RAYMONDVILLE HIDALGO\n420878\tGGUC/TGP RINCON DEHYD STARR\n412458\tETP/TGP GILMORE PLANT RESIDUE HIDAL\n………………………………"]
["X25-237319",null,"2025-10-16","2025-10-16",null,null,null,"MLV 400-2 to MLV 409-2","400","0","Pig Run - Maintenance Cleaning 10/16/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","412733  UES/TGP MYRICK BROOKS\n55152   TGP/KMTEJAS KING RANCH EXCH #2 ROLL\n412400  LOBO/TGP KING RANCH JIM WELLS\n410633\tGCENGY/TGP EL EBANITO DEHY STARR\n410729\tKMTEJAS/TGP ZIM DEHYDRATION STARR\n412088\tETP/TGP MONTE CHRISTO EXCH HIDALGO\n412683\tHESCO CO/TGP RAYMONDVILLE HIDALGO\n420878\tGGUC/TGP RINCON DEHYD STARR\n412458\tETP/TGP GILMORE PLANT RESIDUE HIDAL",400.2,null,"MLV 400-2 to MLV 409-2:  Pig Run - Maintenance Cleaning 10/16/25\n--10/16/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n412733  UES/TGP MYRICK BROOKS\n55152   TGP/KMTEJAS KING RANCH EXCH #2 ROLL\n412400  LOBO/TGP KING RANCH JIM WELLS\n410633\tGCENGY/TGP EL EBANITO DEHY STARR\n410729\tKMTEJAS/TGP ZIM DEHYDRATION STARR\n412088\tETP/TGP MONTE CHRISTO EXCH HIDALGO\n412683\tHESCO CO/TGP RAYMONDVILLE HIDALGO\n420878\tGGUC/TGP RINCON DEHYD STARR\n412458\tETP/TGP GILMORE PLANT RESIDUE HIDAL\n………………………………"]
["X25-155740",null,"2025-07-08","2025-07-08",null,null,null,"Sta 405A","300","5","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,405,null,"Sta 405A:  Annual ESD Test\n--7/8/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-155744",null,"2025-07-09","2025-07-09",null,null,null,"Sta 405A","300","5","Filter / Scrubber Change","This project may require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,405.00009999999997,null,"Sta 405A:  Filter / Scrubber Change\n--7/9/25:  This project may require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-155746",null,"2025-07-09","2025-07-09",null,null,null,"Sta 405A","300","5","Point to Point and Trans Cals","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,405.00020000000001,null,"Sta 405A:  Point to Point and Trans Cals\n--7/9/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-155747",null,"2025-07-09","2025-07-09",null,null,null,"Sta 405A","300","5","Unit Protective Device Tests","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,405.00099999999998,null,"Sta 405A:  Unit Protective Device Tests\n--7/9/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-155750",null,"2025-10-15","2025-10-15",null,null,null,"Sta 405A","300","5","Unit 1A - 8K Solar Turbine Borescope Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,405.00099999999998,null,"Sta 405A:  Unit 1A - 8K Solar Turbine Borescope Inspection\n--10/15/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-155749",null,"2025-10-14","2025-10-14",null,null,null,"Sta 405A","300","5","Unit 1A - Water Wash","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,405.00110000000001,null,"Sta 405A:  Unit 1A - Water Wash\n--10/14/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-450008","***","2025-05-07","2025-05-09","Completed",null,null,"Sta 409","400","0","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,409,"------","***Sta 409:  Annual ESD Test & Maintenance\n***Completed"]
["X25-570900","***","2025-05-22","2025-05-22","Added",null,null,"Sta. 409A","100","0","Alamo ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,409,"------","***Sta. 409A:  Alamo ESD Test\n--5/22/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-82098",null,"2025-09-09","2025-09-26",null,null,null,"MLV 409A-101 to MLV 409A-103","400","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,409.1,null,"MLV 409A-101 to MLV 409A-103:  Anomaly Remediation\n--9/9/25 through 9/26/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-53659",null,"2025-10-14","2025-10-14",null,null,null,"MLV 409A-901 to MLV 409A-902","400","L","Pig Run - Cleaning 10/14/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,409.1,null,"MLV 409A-901 to MLV 409A-902:  Pig Run - Cleaning 10/14/25\n--10/14/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-53665",null,"2025-10-15","2025-10-15",null,null,null,"MLV 409A-901 to MLV 409A-902","400","0","Pig Run - Cleaning 10/15/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,409.11,null,"MLV 409A-901 to MLV 409A-902:  Pig Run - Cleaning 10/15/25\n--10/15/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-53666",null,"2025-10-16","2025-10-16",null,null,null,"MLV 409A-901 to MLV 409A-902","400","0","Pig Run - MFL-A 10/16/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,409.12,null,"MLV 409A-901 to MLV 409A-902:  Pig Run - MFL-A 10/16/25\n--10/16/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-123493",null,"2025-06-24","2025-06-24",null,null,null,"Sta 500-1 to Sta 823 (MLV 507-1)","500","L","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420373 TRNSCO/TGP KINDER LA EXCH (BI 1\n420708 ELIZ NG/TGP GRANT LA SALES ALLEN\n420436 VERNON/TGP PITKIN LA VERNON\n420793 ELIZ NG/TGP J R FRANKS 1 VERNON\n420388 PROVNCAL/TGP PROVENCAL LA NATCHITOC",500.1,null,"Sta 500-1 to Sta 823 (MLV 507-1):  Pig Run - Maintenance\n--6/24/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420373 TRNSCO/TGP KINDER LA EXCH (BI 1\n420708 ELIZ NG/TGP GRANT LA SALES ALLEN\n420436 VERNON/TGP PITKIN LA VERNON\n420793 ELIZ NG/TGP J R FRANKS 1 VERNON\n420388 PROVNCAL/TGP PROVENCAL LA NATCHITOC\n………………………………"]
["X25-123495",null,"2025-09-16","2025-09-16",null,null,null,"Sta 500-1 to Sta 823 (MLV 507-1)","500","L","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420373 TRNSCO/TGP KINDER LA EXCH (BI 1\n420708 ELIZ NG/TGP GRANT LA SALES ALLEN\n420436 VERNON/TGP PITKIN LA VERNON\n420793 ELIZ NG/TGP J R FRANKS 1 VERNON\n420388 PROVNCAL/TGP PROVENCAL LA NATCHITOC",500.1,null,"Sta 500-1 to Sta 823 (MLV 507-1):  Pig Run - Maintenance\n--9/16/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420373 TRNSCO/TGP KINDER LA EXCH (BI 1\n420708 ELIZ NG/TGP GRANT LA SALES ALLEN\n420436 VERNON/TGP PITKIN LA VERNON\n420793 ELIZ NG/TGP J R FRANKS 1 VERNON\n420388 PROVNCAL/TGP PROVENCAL LA NATCHITOC\n………………………………"]
["X25-123498",null,"2025-07-09","2025-07-09",null,null,null,"STA 507F to Sta 823","500","L","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","410671\tTARGA/TGP UDP LOWRY PLANT DEHY CAME\n421049\tTGP/TGP GRAND CHENIER PLANT CAMERON",507.1,null,"STA 507F to Sta 823:  Maintenance Pig\n--7/9/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n410671\tTARGA/TGP UDP LOWRY PLANT DEHY CAME\n421049\tTGP/TGP GRAND CHENIER PLANT CAMERON\n………………………………"]
["X25-424749","***","2025-05-01","2025-05-12","Completed",null,null,"MLV 523-AD2","500","L","MLV Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,523,"------","***MLV 523-AD2:  MLV Replacement\n***Completed"]
["X25-59730",null,"2025-04-21","2025-05-24",null,null,null,"MLV 525-2 to MLV 527-2","500","L","Pipeline Tie-In (Muskrat)","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","55833     VG GATOR/TGP EVANGELINE PASS DELIVE\n412658   EXTEX/TGP FLEUR PLAQUEMINES",525.20000000000005,null,"MLV 525-2 to MLV 527-2:  Pipeline Tie-In (Muskrat)\n--4/21/25 through 5/24/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n55833     VG GATOR/TGP EVANGELINE PASS DELIVE\n412658   EXTEX/TGP FLEUR PLAQUEMINES\n………………………………"]
["X24-1063651",null,"2025-04-21","2025-05-24",null,null,null,"MLV 525-2 to MLV 527-2","500","L","Pipeline Tie-In (500 Line)","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","55833     VG GATOR/TGP EVANGELINE PASS DELIVE\n412658   EXTEX/TGP FLEUR PLAQUEMINES",525.21,null,"MLV 525-2 to MLV 527-2:  Pipeline Tie-In (500 Line)\n--4/21/25 through 5/24/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n55833     VG GATOR/TGP EVANGELINE PASS DELIVE\n412658   EXTEX/TGP FLEUR PLAQUEMINES\n………………………………"]
["X25-417340",null,"2025-05-26","2025-05-31",null,null,null,"MLV 533-1 to MLV 533-1","500","L","Hot Tap for Meter Upgrade (Meter: Carnes PIN: 420366)","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in during the project.","SIP","Potential secondary restrictions at the meter(s) may be at risk.","420366 FGT/TGP CARNES MISSISSIPE STONE",533.1,null,"MLV 533-1 to MLV 533-1:  Hot Tap for Meter Upgrade (Meter: Carnes PIN: 420366)\n--5/26/25 through 5/31/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420366 FGT/TGP CARNES MISSISSIPE STONE\n………………………………"]
["X25-417337",null,"2025-05-26","2025-05-31",null,null,null,"MLV 533-2 to MLV 533-2","500","L","Hot Tap for Meter Upgrade (Meter: Carnes PIN: 420366)","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in during the project.","SIP","Potential secondary restrictions at the meter(s) may be at risk.","420366 FGT/TGP CARNES MISSISSIPE STONE\n412750 PRP INC/TGP PISTOL RIDGE: RIP 533B\n412753 PAR MINL/TGP UDP PISTOL RIDGE: RIP\n412758 PETROHRV/TGP HIGHWAY 13 : RIP 533D-",533.20000000000005,null,"MLV 533-2 to MLV 533-2:  Hot Tap for Meter Upgrade (Meter: Carnes PIN: 420366)\n--5/26/25 through 5/31/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420366 FGT/TGP CARNES MISSISSIPE STONE\n412750 PRP INC/TGP PISTOL RIDGE: RIP 533B\n412753 PAR MINL/TGP UDP PISTOL RIDGE: RIP\n412758 PETROHRV/TGP HIGHWAY 13 : RIP 533D-\n………………………………"]
["X25-352306",null,"2025-03-25","2025-08-15",null,null,null,"Sta 534","500","L","Unit 6A - Piston Liner & Unloader Replacements","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,534.00599999999997,null,"Sta 534:  Unit 6A - Piston Liner & Unloader Replacements\n--3/25/25 through 8/15/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-446102","***","2025-05-16","2025-05-17","Project Change","2025-05-15","2025-05-16","MLV 538-1 to MLV 539-1","500","1","Meter Station Maintenance (Meter Heidelberg PIN 420291)","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420291 TGRNSCO/TGP HEIDELBERG MISSISIPPI JA",538.1,"--start_date--end_date------------model_loc--","***MLV 538-1 to MLV 539-1:  Meter Station Maintenance (Meter Heidelberg PIN 420291)\n--5/16/25 through 5/17/25:  This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420291 TGRNSCO/TGP HEIDELBERG MISSISIPPI JA\n***\nDate Change, Previously scheduled 5/15/25 to 5/16/25.\n………………………………"]
["X25-503637",null,"2025-08-19","2025-08-28",null,null,null,"MLV 540-1 to MLV 540-1A","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,540.1,null,"MLV 540-1 to MLV 540-1A:  Anomaly Remediation\n--8/19/25 through 8/28/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-503636",null,"2025-08-19","2025-09-07",null,null,null,"MLV 541-1 to MLV 541-1A","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,541.1,null,"MLV 541-1 to MLV 541-1A:  Anomaly Remediation\n--8/19/25 through 9/7/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-94907",null,"2024-02-12","2025-06-20",null,null,null,"Sta 542","500","1","Unit 3A - Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,542.00300000000004,null,"Sta 542:  Unit 3A - Overhaul\n--2/12/24 through 6/20/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-550114","***","2025-05-19","2025-05-23","Project Change","2025-05-26","2025-05-30","Sta 546","500","1","Unit 1B - Replace Insulation","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,546.01700000000005,"--start_date--end_date------------model_loc--","***Sta 546:  Unit 1B - Replace Insulation\n--5/19/25 through 5/23/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 5/26/25 to 5/30/25.\n………………………………"]
["X25-573699","***","2025-05-23","2025-05-23","Added",null,null,"Sta. 546 (Columbus)","500","1","Line Break System","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,546.1,"------","***Sta. 546 (Columbus):  Line Break System\n--5/23/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-1368175",null,"2025-11-11","2025-11-15",null,null,null,"Sta 550 Hamilton","500","1","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,550,null,"Sta 550 Hamilton:  Annual ESD Test & Maintenance\n--11/11/25 through 11/15/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-500868","***","2025-07-21","2025-08-15","Project Change",null,null,"Sta 550","500","1","Unit 2A - Compressor/Engine Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,550.00199999999995,"------------prl----model_loc--","***Sta 550:  Unit 2A - Compressor/Engine Overhaul\n--7/21/25 through 8/15/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***Project Change\n………………………………"]
["X25-431275","***","2025-06-09","2025-07-18","Project Change",null,null,"Sta 550","500","1","Unit 3A - Turbocharger Exchange & Engine Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,550.00300000000004,"------------prl----model_loc--","***Sta 550:  Unit 3A - Turbocharger Exchange & Engine Overhaul\n--6/9/25 through 7/18/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***Project Change\n………………………………"]
["X25-431272",null,"2025-06-02","2025-06-13",null,null,null,"Sta 550","500","1","Unit 4A - Turbocharger Exchange","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,550.00400000000002,null,"Sta 550:  Unit 4A - Turbocharger Exchange\n--6/2/25 through 6/13/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-477873",null,"2025-08-19","2025-08-19",null,null,null,"MLV 550-2 TO MLV 546-2","500","1","Pig Runs - Cleaning 8/19/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,550.1,null,"MLV 550-2 TO MLV 546-2:  Pig Runs - Cleaning 8/19/25\n--8/19/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-1368176",null,"2025-11-10","2025-11-14",null,null,null,"Sta 550","100","1","A building - Replace SLC 500 Remote PLC","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,550.1,null,"Sta 550:  A building - Replace SLC 500 Remote PLC\n--11/10/25 through 11/14/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1174541",null,"2025-08-21","2025-08-21",null,null,null,"MLV 550-2 TO MLV 546-2","500","1","Pig Runs - EMAT 8/21/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SIP","Potential in the path restrictions may be at risk.",null,550.25,null,"MLV 550-2 TO MLV 546-2:  Pig Runs - EMAT 8/21/25\n--8/21/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-1368191",null,"2025-09-08","2025-09-12",null,null,null,"Sta 555 Collinwood","500","1","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,555,null,"Sta 555 Collinwood:  Annual ESD Test & Maintenance\n--9/8/25 through 9/12/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-434134","***","2025-05-26","2025-05-30","Project Change","2025-05-05","2025-05-09","Sta 555","500","1","Unit 1A - Engine Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,555.00099999999998,"--start_date--end_date------------model_loc--","***Sta 555:  Unit 1A - Engine Maintenance\n--5/26/25 through 5/30/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 5/5/25 to 5/9/25.\n………………………………"]
["X25-445989",null,"2025-04-14","2025-05-30",null,null,null,"Sta 555","500","1","Unit 2A - Air Manifold Pressure","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,555.00199999999995,null,"Sta 555:  Unit 2A - Air Manifold Pressure\n--4/14/25 through 5/30/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-434135","***","2025-06-09","2025-06-13","Project Change","2025-05-19","2025-05-23","Sta 555","500","1","Unit 2A - Engine Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,555.00199999999995,"--start_date--end_date--------prl----model_loc--","***Sta 555:  Unit 2A - Engine Maintenance\n--6/9/25 through 6/13/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***\nDate Change, Previously scheduled 5/19/25 to 5/23/25.\n………………………………"]
["X25-434136","***","2025-05-16","2025-05-23","Project Change","2025-05-27","2025-05-29","Sta 555","500","1","Unit 3A - Engine Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,555.00300000000004,"--start_date--end_date------------model_loc--","***Sta 555:  Unit 3A - Engine Maintenance\n--5/16/25 through 5/23/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 5/27/25 to 5/29/25.\n………………………………"]
["X25-434137","***","2025-04-28","2025-05-22","Project Change",null,"2025-05-12","Sta 555","500","1","Unit 4A - Engine Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,555.00400000000002,"----end_date------------model_loc--","***Sta 555:  Unit 4A - Engine Maintenance\n--4/28/25 through 5/22/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 4/28/25 to 5/12/25.\n………………………………"]
["X25-434138",null,"2025-06-02","2025-06-05",null,null,null,"Sta 555","500","1","Unit 5A - Engine Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,555.005,null,"Sta 555:  Unit 5A - Engine Maintenance\n--6/2/25 through 6/5/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-434139","***","2025-06-16","2025-06-20","Project Change","2025-05-12","2025-05-16","Sta 555","500","1","Unit 6A - Engine Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,555.00599999999997,"--start_date--end_date--------prl----model_loc--","***Sta 555:  Unit 6A - Engine Maintenance\n--6/16/25 through 6/20/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***\nDate Change, Previously scheduled 5/12/25 to 5/16/25.\n………………………………"]
["X25-324265",null,"2025-06-09","2025-06-30",null,null,null,"MLV 556-2","500","1","Make Piggable - Valve Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,556.20000000000005,null,"MLV 556-2:  Make Piggable - Valve Replacement\n--6/9/25 through 6/30/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-324266",null,"2025-06-09","2025-06-30",null,null,null,"MLV 557-2","500","1","Make Piggable - Valve Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,557.20000000000005,null,"MLV 557-2:  Make Piggable - Valve Replacement\n--6/9/25 through 6/30/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-324268",null,"2025-06-09","2025-06-30",null,null,null,"MLV 558-2","500","1","Make Piggable - Valve Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,558.20000000000005,null,"MLV 558-2:  Make Piggable - Valve Replacement\n--6/9/25 through 6/30/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-108472",null,"2025-06-09","2025-06-30",null,null,null,"MLV 560-2","500","1","Make Piggable - Valve Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,559.20000000000005,null,"MLV 560-2:  Make Piggable - Valve Replacement\n--6/9/25 through 6/30/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-276724",null,"2025-11-17","2025-11-21",null,null,null,"MLV 560-1 to MLV 563-1","500","1","HDD River Crossing & MLV 561-1 & MLV 562-1 Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,560.1,null,"MLV 560-1 to MLV 563-1:  HDD River Crossing & MLV 561-1 & MLV 562-1 Replacement\n--11/17/25 through 11/21/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-415282",null,"2025-06-09","2025-07-21",null,null,null,"MLV 560-2 to MLV 561-2","500","1","Class Change Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,560.20000000000005,null,"MLV 560-2 to MLV 561-2:  Class Change Pipe Replacement\n--6/9/25 through 7/21/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-203840",null,"2025-06-09","2025-06-30",null,null,null,"MLV 561-2","500","1","Make Piggable - Valve Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,561.20000000000005,null,"MLV 561-2:  Make Piggable - Valve Replacement\n--6/9/25 through 6/30/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-203841",null,"2025-06-09","2025-06-30",null,null,null,"MLV 562-2","500","1","Make Piggable - Valve Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,562.20000000000005,null,"MLV 562-2:  Make Piggable - Valve Replacement\n--6/9/25 through 6/30/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-1368204",null,"2025-06-02","2025-06-02",null,null,null,"Sta 563 Joelton","500","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,563,null,"Sta 563 Joelton:  Annual ESD Test\n--6/2/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-348490",null,"2025-06-02","2025-06-05",null,null,null,"Sta 563","500","1","2nd Quarterly Safety Checks","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,563,null,"Sta 563:  2nd Quarterly Safety Checks\n--6/2/25 through 6/5/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-348493","***","2025-06-16","2025-06-20","Completed",null,null,"Sta 563 Joelton","500","1","Scrubber/Filter Separator cleaning &  Inspection - Units 1A & 2A","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,563,"------","***Sta 563 Joelton:  Scrubber/Filter Separator cleaning &  Inspection - Units 1A & 2A\n***Completed"]
["X24-1368205",null,"2025-06-02","2025-06-05",null,null,null,"Sta 563 Joelton","100","1","Fuel Gas Filter Changeout & Gas Filtration - Unit 1 & 2","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,563.00009999999997,null,"Sta 563 Joelton:  Fuel Gas Filter Changeout & Gas Filtration - Unit 1 & 2\n--6/2/25 through 6/5/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-203842",null,"2025-06-09","2025-06-30",null,null,null,"MLV 563-2","500","1","Make Piggable - Valve Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,563.20000000000005,null,"MLV 563-2:  Make Piggable - Valve Replacement\n--6/9/25 through 6/30/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-203843",null,"2025-06-09","2025-06-30",null,null,null,"MLV 564-2","500","1","Make Piggable - Valve Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,564.20000000000005,null,"MLV 564-2:  Make Piggable - Valve Replacement\n--6/9/25 through 6/30/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-1178739",null,"2025-12-10","2025-12-10",null,null,null,"MLV 565-1 TO MLV 559-1","500","1","Pig Runs - Cleaning / Gauge 12/10/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,565.1,null,"MLV 565-1 TO MLV 559-1:  Pig Runs - Cleaning / Gauge 12/10/25\n--12/10/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1178795",null,"2025-12-12","2025-12-12",null,null,null,"MLV 565-1 TO MLV 559-1","500","1","Pig Runs - Caliper 12/12/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,565.11,null,"MLV 565-1 TO MLV 559-1:  Pig Runs - Caliper 12/12/25\n--12/12/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1178816",null,"2025-12-15","2025-12-15",null,null,null,"MLV 565-1 TO MLV 559-1","500","1","Pig Runs - AFD 12/15/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,565.12,null,"MLV 565-1 TO MLV 559-1:  Pig Runs - AFD 12/15/25\n--12/15/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1178843",null,"2025-12-19","2025-12-19",null,null,null,"MLV 565-1 TO MLV 559-1","500","1","Pig Runs - EMAT 12/19/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,565.13,null,"MLV 565-1 TO MLV 559-1:  Pig Runs - EMAT 12/19/25\n--12/19/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-86682",null,"2025-12-17","2025-12-17",null,null,null,"MLV 565-1 TO MLV 559-1","500","1","Pig Runs - Residual 12/17/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,565.14,null,"MLV 565-1 TO MLV 559-1:  Pig Runs - Residual 12/17/25\n--12/17/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-157845",null,"2025-09-09","2025-09-09",null,null,null,"MLV 706-1 to MLV 700-1","100","0","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","412819 LOUISMID/TGP CONVERSE CENTRAL: RIP\n410031 ETX GAS/TGP EAST TX PLANT DEHY PANO",706.11,null,"MLV 706-1 to MLV 700-1:  Pig Run - Maintenance\n--9/9/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n412819 LOUISMID/TGP CONVERSE CENTRAL: RIP\n410031 ETX GAS/TGP EAST TX PLANT DEHY PANO\n………………………………"]
["X25-155787",null,"2025-12-02","2025-12-02",null,null,null,"Sta. 820 Starks","800","L","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,820,null,"Sta. 820 Starks:  Annual ESD Test\n--12/2/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-123511",null,"2025-05-16","2025-05-16",null,null,null,"MLV 820-1 to MLV 821R-101.1","800","L","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","412690\tHPL/TGP SABINE NEWTON\n412013\tENTRPRSE/TGP SABINE RIVER TRANS NEW\n401366\tTRNSCO/TGP UTOS EXCH\n400580\tFGT/TGP SABINE EXCH CALCASIEU\n411586\tTRNSCO/TGP STARKS LA TRANSPORT CALC\n412768\tGLDNPASS/TGP STARKS LNG: RIP 820 10\n412737\tCAM IPL/TGP DE QUINCY GAS STORAGE C\n49446\tCAM IPL/TGP BANKEN RD AT  HWY 27 DE\n412461\tOLIPDPII/TGP DEHYDRATION CALCASIEU\n420581\tBDWKLAGT/TGP BECKWITH CREEK CALCASI\n420473\tTRUNKLNE/TGP KINDER LA EXCH JEFFERS\n420227\tCOKINOS/TGP KING FARM LA JEFFERSON",820.1,null,"MLV 820-1 to MLV 821R-101.1:  Pig Run - Maintenance\n--5/16/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n412690\tHPL/TGP SABINE NEWTON\n412013\tENTRPRSE/TGP SABINE RIVER TRANS NEW\n401366\tTRNSCO/TGP UTOS EXCH\n400580\tFGT/TGP SABINE EXCH CALCASIEU\n411586\tTRNSCO/TGP STARKS LA TRANSPORT CALC\n412768\tGLDNPASS/TGP STARKS LNG: RIP 820 10\n412737\tCAM IPL/TGP DE QUINCY GAS STORAGE C\n49446\tCAM IPL/TGP BANKEN RD AT  HWY 27 DE\n412461\tOLIPDPII/TGP DEHYDRATION CALCASIEU\n420581\tBDWKLAGT/TGP BECKWITH CREEK CALCASI\n420473\tTRUNKLNE/TGP KINDER LA EXCH JEFFERS\n420227\tCOKINOS/TGP KING FARM LA JEFFERSON\n………………………………"]
["X25-155784",null,"2025-05-28","2025-05-31",null,null,null,"Meter Station Filter Srubber Maintenance","800","L","Cameron Banken Rd (Pin 49446)","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","49446 CAM IPL/TGP BANKEN RD AT  HWY 27 DE",821,null,"Meter Station Filter Srubber Maintenance:  Cameron Banken Rd (Pin 49446)\n--5/28/25 through 5/31/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n49446 CAM IPL/TGP BANKEN RD AT  HWY 27 DE\n………………………………"]
["X25-155782","***","2025-05-06","2025-05-08","Completed",null,null,"Sta. 823 (Kinder)","800","L","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,823,"------","***Sta. 823 (Kinder):  Annual ESD Test\n***Completed"]
["X25-123508",null,"2025-05-17","2025-05-17",null,null,null,"MLV 823-1 to MLV 821R-101.1","800","L","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","412690\tHPL/TGP SABINE NEWTON\n412013\tENTRPRSE/TGP SABINE RIVER TRANS NEW\n401366\tTRNSCO/TGP UTOS EXCH\n400580\tFGT/TGP SABINE EXCH CALCASIEU\n411586\tTRNSCO/TGP STARKS LA TRANSPORT CALC\n412768\tGLDNPASS/TGP STARKS LNG: RIP 820 10\n412737\tCAM IPL/TGP DE QUINCY GAS STORAGE C\n49446\tCAM IPL/TGP BANKEN RD AT  HWY 27 DE\n412461\tOLIPDPII/TGP DEHYDRATION CALCASIEU\n420581\tBDWKLAGT/TGP BECKWITH CREEK CALCASI\n420473\tTRUNKLNE/TGP KINDER LA EXCH JEFFERS\n420227\tCOKINOS/TGP KING FARM LA JEFFERSON",823.1,null,"MLV 823-1 to MLV 821R-101.1:  Pig Run - Maintenance\n--5/17/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n412690\tHPL/TGP SABINE NEWTON\n412013\tENTRPRSE/TGP SABINE RIVER TRANS NEW\n401366\tTRNSCO/TGP UTOS EXCH\n400580\tFGT/TGP SABINE EXCH CALCASIEU\n411586\tTRNSCO/TGP STARKS LA TRANSPORT CALC\n412768\tGLDNPASS/TGP STARKS LNG: RIP 820 10\n412737\tCAM IPL/TGP DE QUINCY GAS STORAGE C\n49446\tCAM IPL/TGP BANKEN RD AT  HWY 27 DE\n412461\tOLIPDPII/TGP DEHYDRATION CALCASIEU\n420581\tBDWKLAGT/TGP BECKWITH CREEK CALCASI\n420473\tTRUNKLNE/TGP KINDER LA EXCH JEFFERS\n420227\tCOKINOS/TGP KING FARM LA JEFFERSON\n………………………………"]
["X25-123502",null,"2025-07-08","2025-07-08",null,null,null,"STA 823 to STA 507K","500","L","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420493\tCOKINOS/TGP MALLETT FARM LA JEFFERS",823.5,null,"STA 823 to STA 507K:  Pig Run - Maintenance\n--7/8/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420493\tCOKINOS/TGP MALLETT FARM LA JEFFERS\n………………………………"]
["X25-123490",null,"2025-10-01","2025-10-01",null,null,null,"Sta 823 to MLV 516","500","L","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","412398 JEFFSTOR/TGP JEFFERSON ISLAND IBERI\n420915 CEGS/TGP PORT IBERIA SALES IBERIA\n421056 ACADIAN/TGP INDIAN BAYOU: DIP 510B-\n412594 NAUTILUS/TGP GARDEN CITY ST MARY\n412684 ANR/TGP SHADYSIDE ST MARY",823.51,null,"Sta 823 to MLV 516:  Pig Run - Maintenance\n--10/1/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n412398 JEFFSTOR/TGP JEFFERSON ISLAND IBERI\n420915 CEGS/TGP PORT IBERIA SALES IBERIA\n421056 ACADIAN/TGP INDIAN BAYOU: DIP 510B-\n412594 NAUTILUS/TGP GARDEN CITY ST MARY\n412684 ANR/TGP SHADYSIDE ST MARY\n………………………………"]
["X25-40664","***","2025-05-20","2025-05-22","Project Change","2025-05-19","2025-05-21","Station 827 (Alexandria)","800","L","Annual ESD and Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,827,"--start_date--end_date------------model_loc--","***Station 827 (Alexandria):  Annual ESD and Maintenance\n--5/20/25 through 5/22/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 5/19/25 to 5/21/25.\n………………………………"]
["X25-123505","***","2025-05-21","2025-05-21","Project Change","2025-05-20","2025-05-20","Sta 827 to Sta 823","800","L","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","421043 PINE PRA/TGP PINE PRAIRIE NORTH RAP\n412847 ACADIAN/TGP CHENEYVILLE RAPIDES\n412713 HUGHES E/TGP UDP BLACK STONE13 EVAN \n412844 TEXLA/TGP ROY MARTIN GATHERING: RIP\n420296 FORSTHIL/TGP FOREST HILL LA RAPIDES\n420530 GLNMORA/TGP GLENMORA LA EXCH RAPIDE\n421042 ELIZ NG/TGP EVANGELINE SALES EVANGE\n420629 ELIZ NG/TGP OAKDALE DETENTION SALES\n420687 ELIZ NG/TGP ALLEN PARISH PRISON SAL\n420406 ELIZ NG/TGP ELIZABETH LA EMERGENCY\n53483 AIRLIQAT/TGP TIMBERLANE BIOGAS REC",827.1,"--start_date--end_date------------model_loc--","***Sta 827 to Sta 823:  Pig Run - Maintenance\n--5/21/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n421043 PINE PRA/TGP PINE PRAIRIE NORTH RAP\n412847 ACADIAN/TGP CHENEYVILLE RAPIDES\n412713 HUGHES E/TGP UDP BLACK STONE13 EVAN \n412844 TEXLA/TGP ROY MARTIN GATHERING: RIP\n420296 FORSTHIL/TGP FOREST HILL LA RAPIDES\n420530 GLNMORA/TGP GLENMORA LA EXCH RAPIDE\n421042 ELIZ NG/TGP EVANGELINE SALES EVANGE\n420629 ELIZ NG/TGP OAKDALE DETENTION SALES\n420687 ELIZ NG/TGP ALLEN PARISH PRISON SAL\n420406 ELIZ NG/TGP ELIZABETH LA EMERGENCY\n53483 AIRLIQAT/TGP TIMBERLANE BIOGAS REC\n***\nDate Change, Previously scheduled 5/20/25.\n………………………………"]
["X25-123506",null,"2025-11-05","2025-11-05",null,null,null,"Sta 827 to Sta 823","800","L","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","421043 PINE PRA/TGP PINE PRAIRIE NORTH RAP\n412847 ACADIAN/TGP CHENEYVILLE RAPIDES\n412713 HUGHES E/TGP UDP BLACK STONE13 EVAN \n412844 TEXLA/TGP ROY MARTIN GATHERING: RIP\n420296 FORSTHIL/TGP FOREST HILL LA RAPIDES\n420530 GLNMORA/TGP GLENMORA LA EXCH RAPIDE\n421042 ELIZ NG/TGP EVANGELINE SALES EVANGE\n420629 ELIZ NG/TGP OAKDALE DETENTION SALES\n420687 ELIZ NG/TGP ALLEN PARISH PRISON SAL\n420406 ELIZ NG/TGP ELIZABETH LA EMERGENCY\n53483 AIRLIQAT/TGP TIMBERLANE BIOGAS REC",827.11,null,"Sta 827 to Sta 823:  Pig Run - Maintenance\n--11/5/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n421043 PINE PRA/TGP PINE PRAIRIE NORTH RAP\n412847 ACADIAN/TGP CHENEYVILLE RAPIDES\n412713 HUGHES E/TGP UDP BLACK STONE13 EVAN \n412844 TEXLA/TGP ROY MARTIN GATHERING: RIP\n420296 FORSTHIL/TGP FOREST HILL LA RAPIDES\n420530 GLNMORA/TGP GLENMORA LA EXCH RAPIDE\n421042 ELIZ NG/TGP EVANGELINE SALES EVANGE\n420629 ELIZ NG/TGP OAKDALE DETENTION SALES\n420687 ELIZ NG/TGP ALLEN PARISH PRISON SAL\n420406 ELIZ NG/TGP ELIZABETH LA EMERGENCY\n53483 AIRLIQAT/TGP TIMBERLANE BIOGAS REC\n………………………………"]
["X25-149204",null,"2025-09-29","2025-09-29",null,null,null,"Sta 834","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,834,null,"Sta 834:  Annual ESD Test\n--9/29/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-332689",null,"2025-03-17","2025-05-16",null,null,null,"Sta 834","800","1","Unit 5A - Cracked Main Bearing","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,834.005,null,"Sta 834:  Unit 5A - Cracked Main Bearing\n--3/17/25 through 5/16/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1186067",null,"2025-03-03","2025-11-03",null,null,null,"Sta 834","800","1","Unit 6A - Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,834.00599999999997,null,"Sta 834:  Unit 6A - Overhaul\n--3/3/25 through 11/3/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-136331","***","2025-05-21","2025-05-21","Project Change","2025-05-20","2025-05-20","Sta 834 to Sta 827","800","L","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420755 ATMOS TL/TGP LASALLE PARISH NEBO SA\n420447 PELICANG/TGP HARRISONBURG LA CATAHO",834.1,"--start_date--end_date------------model_loc--","***Sta 834 to Sta 827:  Maintenance Pig\n--5/21/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420755 ATMOS TL/TGP LASALLE PARISH NEBO SA\n420447 PELICANG/TGP HARRISONBURG LA CATAHO\n***\nDate Change, Previously scheduled 5/20/25.\n………………………………"]
["X25-136332",null,"2025-11-05","2025-11-05",null,null,null,"Sta 834 to Sta 827","800","L","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","420755 ATMOS TL/TGP LASALLE PARISH NEBO SA\n420447 PELICANG/TGP HARRISONBURG LA CATAHO",834.11,null,"Sta 834 to Sta 827:  Maintenance Pig\n--11/5/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420755 ATMOS TL/TGP LASALLE PARISH NEBO SA\n420447 PELICANG/TGP HARRISONBURG LA CATAHO\n………………………………"]
["X25-25864",null,"2025-09-30","2025-09-30",null,null,null,"Sta 836A","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,836,null,"Sta 836A:  Annual ESD Test\n--9/30/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-195964",null,"2025-06-16","2025-06-18",null,null,null,"MLV 838-1 TO MLV 834-1","800","1","Pig Runs - Cleaning / Gauge 6/16 - 6/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","412691 REGENCY/TGP PEOPLES ROAD FRANKLIN\n49554 BBTMIDLA/TGP NORTH PEOPLES RD FRANK\n420279 ATMOS TL/TGP CROWVILLE LA FRANKLIN\n49585 GULFRUN/TGP BEARFOOT RICHLAND\n49589 ETC TIG/TGP URSUS FRANKLIN\n49587 GULFSTH/TGP LUPE FRANKLIN\n49583 MEP/TGP PILLAR MADISON\n49643 GULFSTH/TGP SKIPPER MADISON",837.1,null,"MLV 838-1 TO MLV 834-1:  Pig Runs - Cleaning / Gauge 6/16 - 6/18\n--6/16/25 through 6/18/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n412691 REGENCY/TGP PEOPLES ROAD FRANKLIN\n49554 BBTMIDLA/TGP NORTH PEOPLES RD FRANK\n420279 ATMOS TL/TGP CROWVILLE LA FRANKLIN\n49585 GULFRUN/TGP BEARFOOT RICHLAND\n49589 ETC TIG/TGP URSUS FRANKLIN\n49587 GULFSTH/TGP LUPE FRANKLIN\n49583 MEP/TGP PILLAR MADISON\n49643 GULFSTH/TGP SKIPPER MADISON\n………………………………"]
["X25-25863",null,"2025-09-10","2025-09-10",null,null,null,"Sta 838","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,838,null,"Sta 838:  Annual ESD Test\n--9/10/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-195965",null,"2025-06-19","2025-06-19",null,null,null,"MLV 838-1 TO MLV 834-1","800","1","Pig Runs - ROSEN CAL / IMU 6/19","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","412691 REGENCY/TGP PEOPLES ROAD FRANKLIN\n49554 BBTMIDLA/TGP NORTH PEOPLES RD FRANK\n420279 ATMOS TL/TGP CROWVILLE LA FRANKLIN\n49585 GULFRUN/TGP BEARFOOT RICHLAND\n49589 ETC TIG/TGP URSUS FRANKLIN\n49587 GULFSTH/TGP LUPE FRANKLIN\n49583 MEP/TGP PILLAR MADISON\n49643 GULFSTH/TGP SKIPPER MADISON",838.11,null,"MLV 838-1 TO MLV 834-1:  Pig Runs - ROSEN CAL / IMU 6/19\n--6/19/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n412691 REGENCY/TGP PEOPLES ROAD FRANKLIN\n49554 BBTMIDLA/TGP NORTH PEOPLES RD FRANK\n420279 ATMOS TL/TGP CROWVILLE LA FRANKLIN\n49585 GULFRUN/TGP BEARFOOT RICHLAND\n49589 ETC TIG/TGP URSUS FRANKLIN\n49587 GULFSTH/TGP LUPE FRANKLIN\n49583 MEP/TGP PILLAR MADISON\n49643 GULFSTH/TGP SKIPPER MADISON\n………………………………"]
["X25-195966",null,"2025-06-24","2025-06-24",null,null,null,"MLV 838-1 TO MLV 834-1","800","1","Pig Runs - ROSEN AFD (MFL-C) 6/24","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","412691 REGENCY/TGP PEOPLES ROAD FRANKLIN\n49554 BBTMIDLA/TGP NORTH PEOPLES RD FRANK\n420279 ATMOS TL/TGP CROWVILLE LA FRANKLIN\n49585 GULFRUN/TGP BEARFOOT RICHLAND\n49589 ETC TIG/TGP URSUS FRANKLIN\n49587 GULFSTH/TGP LUPE FRANKLIN\n49583 MEP/TGP PILLAR MADISON\n49643 GULFSTH/TGP SKIPPER MADISON",838.12,null,"MLV 838-1 TO MLV 834-1:  Pig Runs - ROSEN AFD (MFL-C) 6/24\n--6/24/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n412691 REGENCY/TGP PEOPLES ROAD FRANKLIN\n49554 BBTMIDLA/TGP NORTH PEOPLES RD FRANK\n420279 ATMOS TL/TGP CROWVILLE LA FRANKLIN\n49585 GULFRUN/TGP BEARFOOT RICHLAND\n49589 ETC TIG/TGP URSUS FRANKLIN\n49587 GULFSTH/TGP LUPE FRANKLIN\n49583 MEP/TGP PILLAR MADISON\n49643 GULFSTH/TGP SKIPPER MADISON\n………………………………"]
["X25-195967",null,"2025-06-26","2025-06-26",null,null,null,"MLV 838-1 TO MLV 834-1","800","1","Pig Runs - ROSEN EMAT 6/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","SOP","Potential secondary restrictions at the meter(s) may be at risk.","412691 REGENCY/TGP PEOPLES ROAD FRANKLIN\n49554 BBTMIDLA/TGP NORTH PEOPLES RD FRANK\n420279 ATMOS TL/TGP CROWVILLE LA FRANKLIN\n49585 GULFRUN/TGP BEARFOOT RICHLAND\n49589 ETC TIG/TGP URSUS FRANKLIN\n49587 GULFSTH/TGP LUPE FRANKLIN\n49583 MEP/TGP PILLAR MADISON\n49643 GULFSTH/TGP SKIPPER MADISON",838.13,null,"MLV 838-1 TO MLV 834-1:  Pig Runs - ROSEN EMAT 6/26\n--6/26/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n412691 REGENCY/TGP PEOPLES ROAD FRANKLIN\n49554 BBTMIDLA/TGP NORTH PEOPLES RD FRANK\n420279 ATMOS TL/TGP CROWVILLE LA FRANKLIN\n49585 GULFRUN/TGP BEARFOOT RICHLAND\n49589 ETC TIG/TGP URSUS FRANKLIN\n49587 GULFSTH/TGP LUPE FRANKLIN\n49583 MEP/TGP PILLAR MADISON\n49643 GULFSTH/TGP SKIPPER MADISON\n………………………………"]
["X24-1368167",null,"2025-06-18","2025-06-18",null,null,null,"Sta 843 Isola","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,843,null,"Sta 843 Isola:  Annual ESD Test\n--6/18/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1179060","***","2025-05-13","2025-05-13","Completed",null,null,"MLV 843-1 TO MLV 847-1","800","1","Pig Runs - Cleaning / Gauge 5/13/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,843.1,"------","***MLV 843-1 TO MLV 847-1:  Pig Runs - Cleaning / Gauge 5/13/25\n***Completed"]
["X24-1179091",null,"2025-05-15","2025-05-15",null,null,null,"MLV 843-1 TO MLV 847-1","800","1","Pig Runs - Caliper 5/15/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,843.11,null,"MLV 843-1 TO MLV 847-1:  Pig Runs - Caliper 5/15/25\n--5/15/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1179111",null,"2025-05-20","2025-05-20",null,null,null,"MLV 843-1 TO MLV 847-1","800","1","Pig Runs - AFD 5/20/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,843.12,null,"MLV 843-1 TO MLV 847-1:  Pig Runs - AFD 5/20/25\n--5/20/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1179124",null,"2025-05-22","2025-05-22",null,null,null,"MLV 843-1 TO MLV 847-1","800","1","Pig Runs - EMAT 5/22/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,843.13,null,"MLV 843-1 TO MLV 847-1:  Pig Runs - EMAT 5/22/25\n--5/22/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368168",null,"2025-08-27","2025-08-28",null,null,null,"Sta 847 Coffeeville","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,847,null,"Sta 847 Coffeeville:  Annual ESD Test\n--8/27/25 through 8/28/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368179",null,"2025-10-08","2025-10-08",null,null,null,"Sta 851 New Albany","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,851,null,"Sta 851 New Albany:  Annual ESD Test\n--10/8/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368184",null,"2025-06-10","2025-06-11",null,null,null,"Sta 856 Savannah","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,856,null,"Sta 856 Savannah:  Annual ESD Test\n--6/10/25 through 6/11/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368187","***","2025-06-10","2025-11-26","Project Change",null,"2025-06-11","Sta 856 Savannah","800","1","Replace Leaking ESD Valves on Turbines","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,856.00009999999997,"----end_date------------model_loc--","***Sta 856 Savannah:  Replace Leaking ESD Valves on Turbines\n--6/10/25 through 11/26/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 6/10/25 to 6/11/25.\n………………………………"]
["X25-239936",null,"2025-10-16","2025-10-16",null,null,null,"MLV 856-1 to MLV 860-1","800","1","Pig Runs - Cleaning / Gauge 10/16/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,856.1,null,"MLV 856-1 to MLV 860-1:  Pig Runs - Cleaning / Gauge 10/16/25\n--10/16/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-239996",null,"2025-10-21","2025-10-21",null,null,null,"MLV 856-1 to MLV 860-1","800","1","Pig Runs - Cal / IMU 10/21/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,856.1,null,"MLV 856-1 to MLV 860-1:  Pig Runs - Cal / IMU 10/21/25\n--10/21/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-240033",null,"2025-10-23","2025-10-23",null,null,null,"MLV 856-1 to MLV 860-1","800","1","Pig Runs - MFL-C 10/23/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","SOP","Potential out of path restrictions may be at risk.",null,856.1,null,"MLV 856-1 to MLV 860-1:  Pig Runs - MFL-C 10/23/25\n--10/23/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X23-841261",null,"2023-08-18","TBD",null,null,null,"Sta 860","800","1","Force Majeure","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,860,null,"Sta 860:  Force Majeure\n--8/18/23 through 8/31/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368190",null,"2025-09-17","2025-09-17",null,null,null,"Sta 860","800","1","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,860,null,"Sta 860:  Annual ESD Test & Maintenance\n--9/17/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-640564",null,"2024-06-17","2025-06-28",null,null,null,"Sta 860","800","1","Unit 1A - Aftercooler Jacket Water Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,860.00099999999998,null,"Sta 860:  Unit 1A - Aftercooler Jacket Water Inspection\n--6/17/24 through 6/28/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-571115","***","2025-06-23","2025-07-03","Added",null,null,"Sta 860","800","1","Unit 5A - Electronic Bearing System","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,860.005,"------","***Sta 860:  Unit 5A - Electronic Bearing System\n--6/23/25 through 7/3/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-228334",null,"2025-06-23","2025-07-03",null,null,null,"Sta 860","800","1","Unit 1B - Replace Lubrication System & Electronic Bearing System","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.","PIP","Potential in the path restrictions may be at risk.",null,860.01700000000005,null,"Sta 860:  Unit 1B - Replace Lubrication System & Electronic Bearing System\n--6/23/25 through 7/3/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-450065",null,"2025-08-18","2025-08-30",null,null,null,"MLV 861-1 to MLV 862-1","800","1","Install New 30\" Valve 861-1A","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,861.1,null,"MLV 861-1 to MLV 862-1:  Install New 30\" Valve 861-1A\n--8/18/25 through 8/30/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-475025",null,"2025-09-08","2025-10-04",null,null,null,"MLV 866-1D to MLV 871-1","800","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,866.1,null,"MLV 866-1D to MLV 871-1:  Anomaly Remediation\n--9/8/25 through 10/4/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-200014",null,"2025-09-22","2025-10-10",null,null,null,"MLV 866-1 to MLV 867-1","800","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,866.1,null,"MLV 866-1 to MLV 867-1:  Anomaly Remediation\n--9/22/25 through 10/10/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-200015",null,"2025-09-22","2025-10-10",null,null,null,"MLV 868-1 to MLV 869-1","800","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,868.1,null,"MLV 868-1 to MLV 869-1:  Anomaly Remediation\n--9/22/25 through 10/10/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-200019",null,"2025-09-22","2025-10-10",null,null,null,"MLV 869-1 to MLV 870-1","800","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,869.1,null,"MLV 869-1 to MLV 870-1:  Anomaly Remediation\n--9/22/25 through 10/10/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-200012",null,"2025-09-22","2025-10-10",null,null,null,"MLV 870-1 to MLV 870-1R","800","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,870.1,null,"MLV 870-1 to MLV 870-1R:  Anomaly Remediation\n--9/22/25 through 10/10/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-406864",null,"2025-06-23","2025-06-27",null,null,null,"Sta 871","800","2","Scrubber/Filter/Separator Inspection & Cleaning","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,871,null,"Sta 871:  Scrubber/Filter/Separator Inspection & Cleaning\n--6/23/25 through 6/27/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-1368196",null,"2025-06-24","2025-06-25",null,null,null,"Sta 871 Campbellsville","800","2","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,871,null,"Sta 871 Campbellsville:  Annual ESD Test\n--6/24/25 through 6/25/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-200026",null,"2025-07-28","2025-09-29",null,null,null,"MLV 871-2 to MLV 871-2A","800","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,871.2,null,"MLV 871-2 to MLV 871-2A:  Anomaly Remediation\n--7/28/25 through 9/29/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-200023",null,"2025-07-28","2025-09-29",null,null,null,"MLV 871-2A to MLV 872-2","800","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,871.2,null,"MLV 871-2A to MLV 872-2:  Anomaly Remediation\n--7/28/25 through 9/29/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-1368203",null,"2025-09-18","2025-09-18",null,null,null,"Sta 871A Campbellsville","800","2","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,871.5,null,"Sta 871A Campbellsville:  Annual ESD Test\n--9/18/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-200006",null,"2025-07-14","2025-07-25",null,null,null,"MLV 872-1 to MLV 873-1","800","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,872.1,null,"MLV 872-1 to MLV 873-1:  Anomaly Remediation\n--7/14/25 through 7/25/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-200024",null,"2025-07-28","2025-09-29",null,null,null,"MLV 872-2 to MLV 873-2","800","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,872.2,null,"MLV 872-2 to MLV 873-2:  Anomaly Remediation\n--7/28/25 through 9/29/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-200025",null,"2025-07-28","2025-09-29",null,null,null,"MLV 873-2 to MLV 873-2A","800","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,873.2,null,"MLV 873-2 to MLV 873-2A:  Anomaly Remediation\n--7/28/25 through 9/29/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-200020",null,"2025-10-03","2025-10-18",null,null,null,"MLV 874-2L to MLV 874-2B","800","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,874.2,null,"MLV 874-2L to MLV 874-2B:  Anomaly Remediation\n--10/3/25 through 10/18/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-200022",null,"2025-10-03","2025-10-24",null,null,null,"MLV 874-2B to MLV 874-2A","800","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SOP","Potential out of path restrictions may be at risk.",null,874.2,null,"MLV 874-2B to MLV 874-2A:  Anomaly Remediation\n--10/3/25 through 10/24/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368155",null,"2025-06-10","2025-06-12",null,null,null,"Sta 875 Richmond","800","2","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,875,null,"Sta 875 Richmond:  Annual ESD Test & Maintenance\n--6/10/25 through 6/12/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-200007",null,"2025-07-14","2025-07-25",null,null,null,"MLV 875-1 to MLV 876-1R","800","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","SIP","Potential in the path restrictions may be at risk.",null,875.1,null,"MLV 875-1 to MLV 876-1R:  Anomaly Remediation\n--7/14/25 through 7/25/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]

{"sheet":"Sheet2","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}

{"sheet":"Sheet3","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}