{"text_format":"1","workbook":"xlsx","n_sheets":4,"sheets":["Closed","Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":8,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Closed","index":0,"n_rows":37,"n_cols":22,"rows_kept":37,"cut":false,"hidden":true,"merged":[[1,3,1,15],[2,3,2,15],[3,3,3,15]]}
[null,null,null,"Updated ","2016"]
[null,null,null,"Tennessee Gas Pipeline 2015 Pipeline Outage and Maintenance Summary"]
[null,null,null,"This is a summary of the current status of all TGP Winter 2014-2015 Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  Additionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
[null,null,null,"*** Indicates revision"]
["Date Change","Project New/Completed/Closed","Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","Location","Leg","Zone","Maintenance Activity","Anticipated Impact","Potential Restriction Level","TOS Potential Restrictions","Meter(s) in Impacted Area","Customer Notifications","Loc","Email Text","Posting Text","Completion Text"]
[{"$f":"IF(AND(H6<>\"\",I6<>\"\"), \"Date change. Previously scheduled \" & TEXT(H6,\"m/d/y;@\") &IF(H6=I6,\"\",\" to \" & TEXT(I6,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed",null,{"$f":"IF(G6<>\"\",\"***\",\"\")","v":"***"},"2015-01-11","2016-01-11",{"$f":"IF(AND(A6=\"\",B6=\"\"),\"\",IF(B6=\"\",A6,B6))","v":"Project Completed"},null,null,"MS #412494 DCP Warren","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412494 DCP Warren",401,{"$f":"\"(\"&C6&\") \"&J6&\":  \"&M6&IF(AND(E6=\"\",F6=\"\"),\"\",\" (\")&IF(E6=\"\",\"\",\"\"&TEXT(E6,\"m/d/y;@\"))&IF(OR(F6=E6,E6=\"\",F6=\"\"),\"\",\" to \")&IF(OR(F6=\"\",F6=E6),\"\",TEXT(F6,\"m/d/y;@\"))&IF(AND(E6=\"\",F6=\"\"),\"\",\")\")","v":"() MS #412494 DCP Warren:  Meter Station (1/11/15 to 1/11/16)"},{"$f":"D6&J6&\":  \"&M6&IF(AND(E6=\"\",F6=\"\"),\"\",\"\n\")&IF(E6=\"\",\"\",\"--\"&TEXT(E6,\"m/d/y;@\"))&IF(OR(F6=E6,E6=\"\",F6=\"\"),\"\",\" through \")&IF(OR(F6=\"\",F6=E6),\"\",TEXT(F6,\"m/d/y;@\"))&IF(AND(E6=\"\",F6=\"\"),\"\",\":  \")&N6&\"  \"&P6&IF(Q6=\"\",\"\",\"\n\"&Q6)&IF(G6=\"\",\"\",\"\n***\")&G6&\"\n………………………………\"","v":"***MS #412494 DCP Warren:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412494 DCP Warren\n***Project Completed\n………………………………"},{"$f":"D6&J6&\":  \"&M6&IF(G6=\"\",\"\",\"\n***\")&G6&IF(Q6=\"\",\"\",\"\nThe following meters are available for nominations:\n\")&Q6&\"\n………………………………\"","v":"***MS #412494 DCP Warren:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412494 DCP Warren\n………………………………"}]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412400 King Ranch","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412400 King Ranch",402.1,"() MS #412400 King Ranch:  Meter Station (1/11/15 to 1/11/16)","***MS #412400 King Ranch:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412400 King Ranch\n***Project Completed\n………………………………","***MS #412400 King Ranch:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412400 King Ranch\n………………………………"]
["","Project Completed",null,"***","2015-01-12","2016-01-12","Project Completed",null,null,"MS #410539 Duvak Gas Gathering","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410539 Duvak Gas Gathering",402.1,"() MS #410539 Duvak Gas Gathering:  Meter Station (1/12/15 to 1/12/16)","***MS #410539 Duvak Gas Gathering:  Meter Station\n--1/12/15 through 1/12/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410539 Duvak Gas Gathering\n***Project Completed\n………………………………","***MS #410539 Duvak Gas Gathering:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n410539 Duvak Gas Gathering\n………………………………"]
["","Project Completed",null,"***","2015-01-13","2016-01-13","Project Completed",null,null,"MS #412356 DCP LaGloria","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412356 DCP LaGloria",403.1,"() MS #412356 DCP LaGloria:  Meter Station (1/13/15 to 1/13/16)","***MS #412356 DCP LaGloria:  Meter Station\n--1/13/15 through 1/13/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412356 DCP LaGloria\n***Project Completed\n………………………………","***MS #412356 DCP LaGloria:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412356 DCP LaGloria\n………………………………"]
["","Project Completed",null,"***","2015-01-13","2016-01-13","Project Completed",null,null,"MS #410173 Enterprise LaReforma","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410173 Enterprise LaReforma",406.1,"() MS #410173 Enterprise LaReforma:  Meter Station (1/13/15 to 1/13/16)","***MS #410173 Enterprise LaReforma:  Meter Station\n--1/13/15 through 1/13/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410173 Enterprise LaReforma\n***Project Completed\n………………………………","***MS #410173 Enterprise LaReforma:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n410173 Enterprise LaReforma\n………………………………"]
["","Project Completed",null,"***","2015-01-12","2016-01-12","Project Completed",null,null,"MS #411903 Enterprise El Benito","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","411903 Enterprise El Benito",407.1,"() MS #411903 Enterprise El Benito:  Meter Station (1/12/15 to 1/12/16)","***MS #411903 Enterprise El Benito:  Meter Station\n--1/12/15 through 1/12/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n411903 Enterprise El Benito\n***Project Completed\n………………………………","***MS #411903 Enterprise El Benito:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n411903 Enterprise El Benito\n………………………………"]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412088 Enterprise Sullivan","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412088 Enterprise Sullivan",407.1,"() MS #412088 Enterprise Sullivan:  Meter Station (1/11/15 to 1/11/16)","***MS #412088 Enterprise Sullivan:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412088 Enterprise Sullivan\n***Project Completed\n………………………………","***MS #412088 Enterprise Sullivan:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412088 Enterprise Sullivan\n………………………………"]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412683 HESCO","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412683 HESCO",408.1,"() MS #412683 HESCO:  Meter Station (1/11/15 to 1/11/16)","***MS #412683 HESCO:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412683 HESCO\n***Project Completed\n………………………………","***MS #412683 HESCO:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412683 HESCO\n………………………………"]
[{"$f":"IF(AND(H14<>\"\",I14<>\"\"), \"Date change. Previously scheduled \" & TEXT(H14,\"m/d/y;@\") &IF(H14=I14,\"\",\" to \" & TEXT(I14,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X16-36843",{"$f":"IF(G14<>\"\",\"***\",\"\")","v":"***"},"2016-01-27","2016-01-27","Project Completed",null,null,"Sta. 237",200,5,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,237,"(X16-36843) Sta. 237:  Unit  Maintenance (1/27/16)","***Sta. 237:  Unit  Maintenance\n--1/27/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Sta. 237:  Unit  Maintenance\n***Project Completed\n………………………………"]
[{"$f":"IF(AND(H15<>\"\",I15<>\"\"), \"Date change. Previously scheduled \" & TEXT(H15,\"m/d/y;@\") &IF(H15=I15,\"\",\" to \" & TEXT(I15,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X14-1478563",{"$f":"IF(G15<>\"\",\"***\",\"\")","v":"***"},"2015-11-16","2016-02-12","Project Completed",null,null,"MLV 32-1D to 33-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,32.200000000000003,"(X14-1478563) MLV 32-1D to 33-1:  Hydrotest (11/16/15 to 2/12/16)","***MLV 32-1D to 33-1:  Hydrotest\n--11/16/15 through 2/12/16:  This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***MLV 32-1D to 33-1:  Hydrotest\n***Project Completed\n………………………………"]
[null,"Project Completed","X16-16074",null,"2016-01-18","2016-01-28","Project Completed",null,null,"Station 550","500","1","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,550,"(X16-16074) Station 550:  Station Maintenance (1/18/16 to 1/28/16)","Station 550:  Station Maintenance\n--1/18/16 through 1/28/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","Station 550:  Station Maintenance\n***Project Completed\n………………………………"]
[{"$f":"IF(AND(H17<>\"\",I17<>\"\"), \"Date change. Previously scheduled \" & TEXT(H17,\"m/d/y;@\") &IF(H17=I17,\"\",\" to \" & TEXT(I17,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X16-46202",{"$f":"IF(G17<>\"\",\"***\",\"\")","v":"***"},"2016-02-01","2016-02-07","Project Completed",null,null,"Station 9","100","0","Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.",null,9,"(X16-46202) Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items) (2/1/16 to 2/7/16)","***Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)\n--2/1/16 through 2/7/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\n***Project Completed\n………………………………","***Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)\n***Project Completed\n………………………………"]
["","Project Completed","X15-925633","***","2016-02-09","2016-02-11","Project Completed",null,null,"Sta. 266A",200,6,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,266,"(X15-925633) Sta. 266A:  Unit  Maintenance (2/9/16 to 2/11/16)","***Sta. 266A:  Unit  Maintenance\n--2/9/16 through 2/11/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Sta. 266A:  Unit  Maintenance\n***Project Completed\n………………………………"]
["","Project Completed","X15-929733","***","2016-01-27","2016-02-10","Project Completed",null,null,"MLV 834-1 to 838-1",800,5,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",834.1,"(X15-929733) MLV 834-1 to 838-1:  ILI/Cleaning Pig (1/27/16 to 2/10/16)","***MLV 834-1 to 838-1:  ILI/Cleaning Pig\n--1/27/16 through 2/10/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 834-1 to 838-1:  ILI/Cleaning Pig\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X14-1562506","***","2015-11-02","2016-02-19","Project Completed",null,null,"MLV 5-1 to 6-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410063 ROCHE DEHYDRATION             \n",5.0999999999999996,"(X14-1562506) MLV 5-1 to 6-1:  Hydrotest (11/2/15 to 2/19/16)","***MLV 5-1 to 6-1:  Hydrotest\n--11/2/15 through 2/19/16:  This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410063 ROCHE DEHYDRATION             \n\n***Project Completed\n………………………………","***MLV 5-1 to 6-1:  Hydrotest\n***Project Completed\nThe following meters are available for nominations:\n410063 ROCHE DEHYDRATION             \n\n………………………………"]
["","Project Completed","X14-1562506","***","2015-11-02","2016-02-19","Project Completed",null,null,"MLV 7-1 to 9-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","\n412490 Charro\n421083 Eagle Ford Field Service",5.0999999999999996,"(X14-1562506) MLV 7-1 to 9-1:  Hydrotest (11/2/15 to 2/19/16)","***MLV 7-1 to 9-1:  Hydrotest\n--11/2/15 through 2/19/16:  This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n\n412490 Charro\n421083 Eagle Ford Field Service\n***Project Completed\n………………………………","***MLV 7-1 to 9-1:  Hydrotest\n***Project Completed\nThe following meters are available for nominations:\n\n412490 Charro\n421083 Eagle Ford Field Service\n………………………………"]
["Date change. Previously scheduled 2/18/16 to 2/20/16.","Project Completed","X15-882289","***","2016-02-22","2016-02-24","Project Completed","2016-02-18","2016-02-20","MLV 24-2 to 25-2S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.2,"(X15-882289) MLV 24-2 to 25-2S:  Anomaly Remediation (2/22/16 to 2/24/16)","***MLV 24-2 to 25-2S:  Anomaly Remediation\n--2/22/16 through 2/24/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 24-2 to 25-2S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-925630","***","2016-02-23","2016-02-23","Project Completed",null,null,"WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B)",200,"L","ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,265.10000000000002,"(X15-925630) WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig (2/23/16)","***WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig\n--2/23/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig\n***Project Completed\n………………………………"]
["","Project Completed","X16-23748","***","2016-02-15","2016-02-18","Project Completed",null,null,"MLV 530-3 to 532-3",500,"L","ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,530.29999999999995,"(X16-23748) MLV 530-3 to 532-3:  ILI/Cleaning Pig (2/15/16 to 2/18/16)","***MLV 530-3 to 532-3:  ILI/Cleaning Pig\n--2/15/16 through 2/18/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***MLV 530-3 to 532-3:  ILI/Cleaning Pig\n***Project Completed\n………………………………"]
["","Project Canceled","X16-98720","***","2016-03-06","2016-03-06","Project Canceled",null,null,"Sta. 1",100,0,"Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,1,"(X16-98720) Sta. 1:  Station Maintenance (3/6/16)","***Sta. 1:  Station Maintenance\n--3/6/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Canceled\n………………………………","***Sta. 1:  Station Maintenance\n***Project Canceled\n………………………………"]
["","Project Completed","X14-1562513\nX14-1540661","***","2015-07-01","2016-03-04","Project Completed",null,null,"Station 32","100","0","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,32,"(X14-1562513\nX14-1540661) Station 32:  Station Maintenance (7/1/15 to 3/4/16)","***Station 32:  Station Maintenance\n--7/1/15 through 3/4/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Station 32:  Station Maintenance\n***Project Completed\n………………………………"]
["","Project Canceled","X15-926822","***","2016-06-06","2016-06-11","Project Canceled",null,null,"BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1)",300,6,"Pipe Inspection","This project involves inspecting multiple sites.  We do not anticipate having to do any repairs, however if a repair is needed  there is a potential that the pipe  may require replacement which will require isolation of the pipe.  This may limit throughput and will result in restrictions based on customer nominations.  Customers may experience pressure fluctuations during this timeframe.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",343.1,"(X15-926822) BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection (6/6/16 to 6/11/16)","***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection\n--6/6/16 through 6/11/16:  This project involves inspecting multiple sites.  We do not anticipate having to do any repairs, however if a repair is needed  there is a potential that the pipe  may require replacement which will require isolation of the pipe.  This may limit throughput and will result in restrictions based on customer nominations.  Customers may experience pressure fluctuations during this timeframe.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928271","***","TBD","TBD","Project Canceled",null,null,"MLV 555-1 to 550-1",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.1,"(X15-928271) MLV 555-1 to 550-1:  ILI/Cleaning Pig (TBD)","***MLV 555-1 to 550-1:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-1 to 550-1:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928272","***","TBD","TBD","Project Canceled",null,null,"MLV 555-2 to 550-2",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.20000000000005,"(X15-928272) MLV 555-2 to 550-2:  ILI/Cleaning Pig (TBD)","***MLV 555-2 to 550-2:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-2 to 550-2:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928273","***","TBD","TBD","Project Canceled",null,null,"MLV 555-3 to 552-3",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.29999999999995,"(X15-928273) MLV 555-3 to 552-3:  ILI/Cleaning Pig (TBD)","***MLV 555-3 to 552-3:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-3 to 552-3:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-882281","***","2016-02-24","2016-03-03","Project Completed",null,null,"24-1A to 25-1S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.1,"(X15-882281) 24-1A to 25-1S:  Anomaly Remediation (2/24/16 to 3/3/16)","***24-1A to 25-1S:  Anomaly Remediation\n--2/24/16 through 3/3/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***24-1A to 25-1S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-882291","***","2016-03-03","2016-03-04","Project Completed",null,null,"MLV 24-3 to 25-3S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.3,"(X15-882291) MLV 24-3 to 25-3S:  Anomaly Remediation (3/3/16 to 3/4/16)","***MLV 24-3 to 25-3S:  Anomaly Remediation\n--3/3/16 through 3/4/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 24-3 to 25-3S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X14-1178175","***","2015-06-15","2016-03-31","Project Completed",null,null,"Station 63","100","1","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,63,"(X14-1178175) Station 63:  Station Maintenance (6/15/15 to 3/31/16)","***Station 63:  Station Maintenance\n--6/15/15 through 3/31/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Station 63:  Station Maintenance\n***Project Completed\n………………………………"]
["","Project Cancelled","X15-913224","***","2016-04-16","2016-05-21","Project Cancelled",null,null,"MLV 109-2",100,2,"Pipe Replacement","This project will require taking the pipeline section out of service.   This will limit throughput and will result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",109.2,"(X15-913224) MLV 109-2:  Pipe Replacement (4/16/16 to 5/21/16)","***MLV 109-2:  Pipe Replacement\n--4/16/16 through 5/21/16:  This project will require taking the pipeline section out of service.   This will limit throughput and will result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Cancelled\n………………………………","***MLV 109-2:  Pipe Replacement\n***Project Cancelled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-926830","***","2016-03-07","2016-03-11","Project Completed",null,null,"MLV 400-1 to 408-1",100,0,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.","To Be Determined",400.1,"(X15-926830) MLV 400-1 to 408-1:  ILI/Cleaning Pig (3/7/16 to 3/11/16)","***MLV 400-1 to 408-1:  ILI/Cleaning Pig\n--3/7/16 through 3/11/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 400-1 to 408-1:  ILI/Cleaning Pig\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Cancelled","X16-143836","***","2016-03-28","2016-04-04","Project Cancelled",null,null,"Sta. 409",100,0,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.",null,409,"(X16-143836) Sta. 409:  Unit  Maintenance (3/28/16 to 4/4/16)","***Sta. 409:  Unit  Maintenance\n--3/28/16 through 4/4/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\n***Project Cancelled\n………………………………","***Sta. 409:  Unit  Maintenance\n***Project Cancelled\n………………………………"]
["","Project Cancelled","X15-929680","***","2016-04-18","2016-04-27","Project Cancelled",null,null,"SABINE - KINDER LINE to 822-1",800,"L","Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",822.1,"(X15-929680) SABINE - KINDER LINE to 822-1:  Anomaly Remediation (4/18/16 to 4/27/16)","***SABINE - KINDER LINE to 822-1:  Anomaly Remediation\n--4/18/16 through 4/27/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Cancelled\n………………………………","***SABINE - KINDER LINE to 822-1:  Anomaly Remediation\n***Project Cancelled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]

{"sheet":"Sheet1","index":1,"n_rows":307,"n_cols":22,"rows_kept":307,"cut":false,"hidden":false,"merged":[[2,0,2,12]]}
["Updated ","2025-09-04"]
["Tennessee Gas Pipeline 2025 Pipeline Outage and Maintenance Summary"]
["This is a summary of the current status of TGP Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  \nAdditionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
["*** Indicates revision"]
["Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","Location","Leg","Zone","Maintenance Activity","Anticipated Impact","Meter(s) in Impacted Area","Loc",null,null,null,null,null,null,null,"\\\\houCORP\\TRANS\\TRANSERVICES\\OPPLAN\\COMMON\\Outages\\Outage_DB\\TGP\\Files"]
["X25-237824",null,"2025-10-23","2025-10-23",null,null,null,"MLV 5-2 to MLV 1-2D","100","0","Pig Runs - Maintenance Cleaning 10/23","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","412196 ENLINK/TGP NORTH BRAYTON DEHY NUECE\n412062 BANHUB/TGP BANQUETE TRANSPORT NUECE\n412669 ETP/TGP SHOUP NUECES\n412270 LOBO/TGP UDP TRANSAMERICAN INTERCON\n54847 WHISTLEP/TGP WHISTLER RECEIPT NUECE",5.21,null,"MLV 5-2 to MLV 1-2D:  Pig Runs - Maintenance Cleaning 10/23\n--10/23/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n412196 ENLINK/TGP NORTH BRAYTON DEHY NUECE\n412062 BANHUB/TGP BANQUETE TRANSPORT NUECE\n412669 ETP/TGP SHOUP NUECES\n412270 LOBO/TGP UDP TRANSAMERICAN INTERCON\n54847 WHISTLEP/TGP WHISTLER RECEIPT NUECE\n………………………………"]
["X25-238186",null,"2025-10-21","2025-10-21",null,null,null,"MLV 9-1S and MLV 1-1D","100","0","Pig Run - Maintenance Cleaning 10/21","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","54847 WHISTLEP/TGP WHISTLE RECEIPT NUECES\n53608 VCP/TGP VALLEY CROSSING ALLOCATION",9.1,null,"MLV 9-1S and MLV 1-1D:  Pig Run - Maintenance Cleaning 10/21\n--10/21/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n54847 WHISTLEP/TGP WHISTLE RECEIPT NUECES\n53608 VCP/TGP VALLEY CROSSING ALLOCATION\n………………………………"]
["X25-237991",null,"2025-10-23","2025-10-23",null,null,null,"MLV 9-2 to MLV 5-2","100","0","Pig Runs - Maintenance Cleaning 10/23","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","54847 WHISTLEP/TGP WHISTLE RECEIPT NUECES\n53608 VCP/TGP VALLEY CROSSING ALLOCATION",9.2100000000000009,null,"MLV 9-2 to MLV 5-2:  Pig Runs - Maintenance Cleaning 10/23\n--10/23/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n54847 WHISTLEP/TGP WHISTLE RECEIPT NUECES\n53608 VCP/TGP VALLEY CROSSING ALLOCATION\n………………………………"]
["X25-238099",null,"2025-10-22","2025-10-22",null,null,null,"MLV 9-3 to MLV 4-3","100","0","Pig Runs - Maintenance Cleaning 10/22","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","54847 WHISTLEP/TGP WHISTLE RECEIPT NUECES\n53608 VCP/TGP VALLEY CROSSING ALLOCATION",9.31,null,"MLV 9-3 to MLV 4-3:  Pig Runs - Maintenance Cleaning 10/22\n--10/22/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n54847 WHISTLEP/TGP WHISTLE RECEIPT NUECES\n53608 VCP/TGP VALLEY CROSSING ALLOCATION\n………………………………"]
["X25-963048",null,"2025-10-07","2025-10-07",null,null,null,"Sta 11A","100","0","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,11,null,"Sta 11A:  Annual ESD Test\n--10/7/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-1022152",null,"2025-09-03","2025-09-04",null,null,null,"Sta 11A","100","0","Unit 1A - Engine Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,11.000999999999999,null,"Sta 11A:  Unit 1A - Engine Maintenance\n--9/3/25 through 9/4/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-963050",null,"2025-10-20","2025-10-22",null,null,null,"Sta 11A","100","0","Unit 1A - Safety Devices","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,11.000999999999999,null,"Sta 11A:  Unit 1A - Safety Devices\n--10/20/25 through 10/22/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-475184",null,"2025-09-03","2025-09-03",null,null,null,"MLV 17-2S to MLV 9-2D","100","0","Pigging Cleaning Run 1","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","49803 KMTEJAS/TGP JACKSON (GANADO)",17.100000000000001,null,"MLV 17-2S to MLV 9-2D:  Pigging Cleaning Run 1\n--9/3/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n49803 KMTEJAS/TGP JACKSON (GANADO)\n………………………………"]
["X25-475185",null,"2025-09-05","2025-09-05",null,null,null,"MLV 17-2S to MLV 9-2D","100","0","Pig Runs - Cleaning Run 2","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","49803 KMTEJAS/TGP JACKSON (GANADO)",17.100000000000001,null,"MLV 17-2S to MLV 9-2D:  Pig Runs - Cleaning Run 2\n--9/5/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n49803 KMTEJAS/TGP JACKSON (GANADO)\n………………………………"]
["X25-475187",null,"2025-09-09","2025-09-09",null,null,null,"MLV 17-2S to MLV 9-2D","100","0","Pig Runs - Cleaning / Gauge","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","49803 KMTEJAS/TGP JACKSON (GANADO)",17.100000000000001,null,"MLV 17-2S to MLV 9-2D:  Pig Runs - Cleaning / Gauge\n--9/9/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n49803 KMTEJAS/TGP JACKSON (GANADO)\n………………………………"]
["X25-475188",null,"2025-09-11","2025-09-11",null,null,null,"MLV 17-2S to MLV 9-2D","100","0","Pig Runs - MFL","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","49803 KMTEJAS/TGP JACKSON (GANADO)",17.100000000000001,null,"MLV 17-2S to MLV 9-2D:  Pig Runs - MFL\n--9/11/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n49803 KMTEJAS/TGP JACKSON (GANADO)\n………………………………"]
["X25-559338",null,"2025-09-15","2025-09-15",null,null,null,"MLV 17-1D to MLV 20-1A","100","0","Pig Run - Cleaning 9/15/25","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,17.100000000000001,null,"MLV 17-1D to MLV 20-1A:  Pig Run - Cleaning 9/15/25\n--9/15/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-559339",null,"2025-09-16","2025-09-16",null,null,null,"MLV 17-1D to MLV 20-1A","100","0","Pig Run - Gauge 9/16/25","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,17.100000000000001,null,"MLV 17-1D to MLV 20-1A:  Pig Run - Gauge 9/16/25\n--9/16/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-559340",null,"2025-09-17","2025-09-17",null,null,null,"MLV 17-1D to MLV 20-1A","100","0","Pig Run - MFL-A 9/17/25","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,17.100000000000001,null,"MLV 17-1D to MLV 20-1A:  Pig Run - MFL-A 9/17/25\n--9/17/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-82095",null,"2025-10-13","2025-10-31",null,null,null,"MLV 17-1D to MLV 20-1A","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,17.100000000000001,null,"MLV 17-1D to MLV 20-1A:  Anomaly Remediation\n--10/13/25 through 10/31/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-82099",null,"2025-08-16","2025-09-03",null,null,null,"MLV 20-1, MLV-20-2, MLV-20-3 Kicker Lines","100","0","ECDA Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,20.100000000000001,null,"MLV 20-1, MLV-20-2, MLV-20-3 Kicker Lines:  ECDA Remediation\n--8/16/25 through 9/3/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-942604",null,"2025-07-16","2026-10-31",null,null,null,"Sta 25","100","0","Unit 1C - VFD Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,25.033000000000001,null,"Sta 25:  Unit 1C - VFD Replacement\n--7/16/25 through 10/31/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-671169",null,"2025-08-18","2025-09-06",null,null,null,"MLV 25-1 to MLV 26-1 Relocation","100","0","Highway 105 Widening","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,25.1,null,"MLV 25-1 to MLV 26-1 Relocation:  Highway 105 Widening\n--8/18/25 through 9/6/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-286293",null,"2025-09-09","2025-09-09",null,null,null,"MLV 25-2 to MLV 32-2","100","0","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,25.2,null,"MLV 25-2 to MLV 32-2:  Pig Run - Maintenance\n--9/9/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-152035",null,"2025-09-11","2025-09-11",null,null,null,"MLV 25-3 to MLV 32-3","100","0","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,25.3,null,"MLV 25-3 to MLV 32-3:  Pig Run - Maintenance\n--9/11/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-621358",null,"2025-10-06","2025-11-02",null,null,null,"MLV 26-1 Relocation","100","0","Highway 59 Widening","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,26.1,null,"MLV 26-1 Relocation:  Highway 59 Widening\n--10/6/25 through 11/2/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1148994",null,"2025-10-06","2025-11-02",null,null,null,"MLV 26-1 to MLV 27-1","100","0","Install Road Casing","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,26.1,null,"MLV 26-1 to MLV 27-1:  Install Road Casing\n--10/6/25 through 11/2/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-815863",null,"2025-11-03","2025-11-30",null,null,null,"MLV 26-2 Relocation","100","0","Highway 59 Widening","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,26.2,null,"MLV 26-2 Relocation:  Highway 59 Widening\n--11/3/25 through 11/30/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X22-815864",null,"2025-12-01","2025-12-28",null,null,null,"MLV 26-3 Relocation","100","0","Highway 59 Widening","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","400448 CICO/TGP MERCY GU 1 LIBERTY",26.3,null,"MLV 26-3 Relocation:  Highway 59 Widening\n--12/1/25 through 12/28/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n400448 CICO/TGP MERCY GU 1 LIBERTY\n………………………………"]
["X25-157835",null,"2025-10-28","2025-10-28",null,null,null,"MLV 32-2D TO MLV 40-2S","100","0","Pig Runs - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,32.200000000000003,null,"MLV 32-2D TO MLV 40-2S:  Pig Runs - Maintenance\n--10/28/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-157840",null,"2025-10-21","2025-10-21",null,null,null,"MLV 32-3D to MLV 40-3S","100","0","Pig Runs - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,32.299999999999997,null,"MLV 32-3D to MLV 40-3S:  Pig Runs - Maintenance\n--10/21/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-173992",null,"2025-10-07","2025-10-20",null,null,null,"MLV 39-1 to MLV 40-1S","100","0","Class Change","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,39.1,null,"MLV 39-1 to MLV 40-1S:  Class Change\n--10/7/25 through 10/20/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-173993",null,"2025-09-23","2025-10-06",null,null,null,"MLV 39-2 to MLV 40-2S","100","0","Class Change","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,39.200000000000003,null,"MLV 39-2 to MLV 40-2S:  Class Change\n--9/23/25 through 10/6/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-173994",null,"2025-09-09","2025-09-22",null,null,null,"MLV 39-3 to MLV 40-3S","100","0","Class Change","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,39.299999999999997,null,"MLV 39-3 to MLV 40-3S:  Class Change\n--9/9/25 through 9/22/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-348491","***","2025-08-18","2025-09-03","Project Change",null,"2025-08-28","Sta 40","100","1","HP Replacement - Bldg C Mod","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,40.000100000000003,"----end_date--------------model_loc--","***Sta 40:  HP Replacement - Bldg C Mod\n--8/18/25 through 9/3/25:  This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 8/18/25 to 8/28/25.\n………………………………"]
["X25-348494","***","2025-09-04","2025-09-10","Project Change","2025-08-26","2025-08-31","Sta 40","100","1","HP Replacement - 500C1 Mod","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,40.0002,"--start_date--end_date--------mantenance_desc------model_loc--","***Sta 40:  HP Replacement - 500C1 Mod\n--9/4/25 through 9/10/25:  This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 8/26/25 to 8/31/25.\n………………………………"]
["X25-196085",null,"2025-10-21","2025-10-27",null,null,null,"Bear Creek Storage","100","1","Shut-in Test","This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","460017 STORAGE – BEAR CREEK",43.1,null,"Bear Creek Storage:  Shut-in Test\n--10/21/25 through 10/27/25:  This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n460017 STORAGE – BEAR CREEK\n………………………………"]
["X25-25861",null,"2025-09-10","2025-09-10",null,null,null,"Sta 47","100","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,47,null,"Sta 47:  Annual ESD Test\n--9/10/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-877998",null,"2025-07-21","2026-06-18",null,null,null,"Sta 47","100","1","Unit 8B - SawGrass Power Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,47.02,null,"Sta 47:  Unit 8B - SawGrass Power Overhaul\n--7/21/25 through 6/18/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-877996",null,"2025-07-21","2026-06-18",null,null,null,"Sta 47","100","1","Unit 9B - Sawgrass power overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,47.021000000000001,null,"Sta 47:  Unit 9B - Sawgrass power overhaul\n--7/21/25 through 6/18/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-1022009",null,"2025-09-02","2025-09-04",null,null,null,"Sta 47","100","1","Bldg C Unloader","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,47.033000000000001,null,"Sta 47:  Bldg C Unloader\n--9/2/25 through 9/4/25:  This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-783633",null,"2025-10-20","2025-10-24",null,null,null,"Sta 47",null,null,"Unit 1D - Flush & Clean Cooling Systems","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,47.048000000000002,null,"Sta 47:  Unit 1D - Flush & Clean Cooling Systems\n--10/20/25 through 10/24/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-783637","***","2025-10-20","2025-10-24","Added",null,null,"Sta 47",null,null,"Unit 2D - Flush & Clean Cooling Systems","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,47.064999999999998,"--------anticipated_impact------prl----model_loc--","***Sta 47:  Unit 2D - Flush & Clean Cooling Systems\n--10/20/25 through 10/24/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-35040",null,"2025-01-06","2025-10-31",null,null,null,"MLV 47-1AT to MLV 49-1","100","1","Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,47.1,null,"MLV 47-1AT to MLV 49-1:  Anomaly Remediation\n--1/6/25 through 10/31/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-82100",null,"2025-09-01","2025-12-31",null,null,null,"MLV 47-1A to MLV 48-1","100","1","Class Change","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,47.1,null,"MLV 47-1A to MLV 48-1:  Class Change\n--9/1/25 through 12/31/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-503629",null,"2025-09-01","2025-09-05",null,null,null,"MLV 47-3AT to MLV 47-3A","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,47.1,null,"MLV 47-3AT to MLV 47-3A:  Anomaly Remediation\n--9/1/25 through 9/5/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-996812",null,"2025-10-13","2025-10-24",null,null,null,"MLV 47-2A to MLV 48-2","100","1","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","47872 ATMOS TL/TGP CHAUVIN OUACHITA",47.2,null,"MLV 47-2A to MLV 48-2:  Pipe Replacement\n--10/13/25 through 10/24/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n47872 ATMOS TL/TGP CHAUVIN OUACHITA\n………………………………"]
["X25-996815",null,"2025-10-27","2025-11-07",null,null,null,"MLV 47-3A to MLV 48-3","100","0","Pipe Replacement","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,47.3,null,"MLV 47-3A to MLV 48-3:  Pipe Replacement\n--10/27/25 through 11/7/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-996817",null,"2025-11-10","2025-11-21",null,null,null,"MLV 47-4A to MLV 48-4","100","1","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","421013 BBTMIDLA/TGP FAIRBANKS OUACHITA",47.4,null,"MLV 47-4A to MLV 48-4:  Pipe Replacement\n--11/10/25 through 11/21/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n421013 BBTMIDLA/TGP FAIRBANKS OUACHITA\n………………………………"]
["X25-503630",null,"2025-09-01","2025-09-05",null,null,null,"MLV 48-3 to MLV 49-3","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,48.1,null,"MLV 48-3 to MLV 49-3:  Anomaly Remediation\n--9/1/25 through 9/5/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-222569",null,"2025-03-04","2025-10-31",null,null,null,"MLV 49-1 to MLV 50-1","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,49.1,null,"MLV 49-1 to MLV 50-1:  Anomaly Remediation\n--3/4/25 through 10/31/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-503632","***","2025-08-15","2025-09-05","Project Change",null,"2025-08-30","MLV 52-2 to MLV 53-2","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,52.1,"----end_date--------------model_loc--","***MLV 52-2 to MLV 53-2:  Anomaly Remediation\n--8/15/25 through 9/5/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 8/15/25 to 8/30/25.\n………………………………"]
["X25-994153",null,"2025-09-12","2025-10-15",null,null,null,"MLV 53-2BREH to MLV 53-2BR","100","1","Special Permit Replacement","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,53.2,null,"MLV 53-2BREH to MLV 53-2BR:  Special Permit Replacement\n--9/12/25 through 10/15/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-946952",null,"2025-08-25","2025-10-04",null,null,null,"MLV 53-3BR to MLV 54-3BL","100","1","HydroTest","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,53.3,null,"MLV 53-3BR to MLV 54-3BL:  HydroTest\n--8/25/25 through 10/4/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368171",null,"2025-09-08","2025-09-11",null,null,null,"Sta 54 Greenville","100","1","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,54,null,"Sta 54 Greenville:  Annual ESD Test & Maintenance\n--9/8/25 through 9/11/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-878000",null,"2025-08-18","2025-09-05",null,null,null,"Sta 54","100","1","Unit 6B - Power Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,54.018000000000001,null,"Sta 54:  Unit 6B - Power Overhaul\n--8/18/25 through 9/5/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-878001",null,"2025-08-18","2025-09-05",null,null,null,"Sta 54","100","1","Unit 8B - Power Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,54.02,null,"Sta 54:  Unit 8B - Power Overhaul\n--8/18/25 through 9/5/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-86678",null,"2025-09-16","2025-09-16",null,null,null,"MLV 54-1D TO MLV 63-1S","100","1","Pig Runs - Cleaning / Gauge 9/16/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,54.1,null,"MLV 54-1D TO MLV 63-1S:  Pig Runs - Cleaning / Gauge 9/16/25\n--9/16/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-86679",null,"2025-09-18","2025-09-18",null,null,null,"MLV 54-1D TO MLV 63-1S","100","1","Pig Runs - CLP / IMU 9/18/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,54.11,null,"MLV 54-1D TO MLV 63-1S:  Pig Runs - CLP / IMU 9/18/25\n--9/18/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-86680",null,"2025-09-23","2025-09-23",null,null,null,"MLV 54-1D TO MLV 63-1S","100","1","Pig Runs - MFL-C 9/23/25","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,54.12,null,"MLV 54-1D TO MLV 63-1S:  Pig Runs - MFL-C 9/23/25\n--9/23/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-86681",null,"2025-09-25","2025-09-25",null,null,null,"MLV 54-1D TO MLV 63-1S","100","1","Pig Runs - MFL-C 9/25/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,54.13,null,"MLV 54-1D TO MLV 63-1S:  Pig Runs - MFL-C 9/25/25\n--9/25/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368169","***","2025-08-27","2025-08-28","Completed",null,null,"Sta 63 Batesville","100","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,63,"------","***Sta 63 Batesville:  Annual ESD Test\n***Completed"]
["X23-1196655","***","2023-11-28","2025-12-29","Project Change",null,"2025-09-22","Sta 71","100","1","Unit 3A - Discharge Bottle Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,71.003,"----end_date--------------model_loc--","***Sta 71:  Unit 3A - Discharge Bottle Inspection\n--11/28/23 through 12/29/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 11/28/23 to 9/22/25.\n………………………………"]
["X24-262275","***","2024-04-08","2025-10-31","Project Change",null,"2025-09-30","Sta 71","100","1","Unit 7A Replace Crank End Compressor Gasket","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,71.007000000000005,"----end_date--------------model_loc--","***Sta 71:  Unit 7A Replace Crank End Compressor Gasket\n--4/8/24 through 10/31/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 4/8/24 to 9/30/25.\n………………………………"]
["X25-324113","***","2025-03-17","2025-09-29","Project Change",null,"2025-08-30","Sta 71","100","1","Unit 2B - Jacket Water System","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,71.018000000000001,"----end_date--------------model_loc--","***Sta 71:  Unit 2B - Jacket Water System\n--3/17/25 through 9/29/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 3/17/25 to 8/30/25.\n………………………………"]
["X25-1007503",null,"2025-11-12","2025-11-12",null,null,null,"MLV 71-1D to MLV 77-1A","100","1","Pig Re-Runs - MDS 11/12/25","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,71.099999999999994,null,"MLV 71-1D to MLV 77-1A:  Pig Re-Runs - MDS 11/12/25\n--11/12/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1082041",null,"2025-10-28","2025-10-28",null,null,null,"MLV 63-4D to MLV 71-4S","100","1","Pig Runs - Cleaning / Gauge 10/28/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,71.400000000000006,null,"MLV 63-4D to MLV 71-4S:  Pig Runs - Cleaning / Gauge 10/28/25\n--10/28/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1082043",null,"2025-10-30","2025-10-30",null,null,null,"MLV 63-4D to MLV 71-4S","100","1","Pig Runs - Caliper / IMU 10/30/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,71.41,null,"MLV 63-4D to MLV 71-4S:  Pig Runs - Caliper / IMU 10/30/25\n--10/30/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1082045",null,"2025-11-04","2025-11-04",null,null,null,"MLV 63-4D to MLV 71-4S","100","1","Pig Runs - MFL-C 11/4/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,71.42,null,"MLV 63-4D to MLV 71-4S:  Pig Runs - MFL-C 11/4/25\n--11/4/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1082047",null,"2025-11-06","2025-11-06",null,null,null,"MLV 63-4D to MLV 71-4S","100","1","Pig Runs - EMAT 11/6/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,71.430000000000007,null,"MLV 63-4D to MLV 71-4S:  Pig Runs - EMAT 11/6/25\n--11/6/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-996875",null,"2026-04-14","2026-04-14",null,null,null,"MLV 79-4 to MLV 71-4D","100","1","Pig Runs - Cleaning / Gauge 4/14/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.",null,79.400000000000006,null,"MLV 79-4 to MLV 71-4D:  Pig Runs - Cleaning / Gauge 4/14/26\n--4/14/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-996878",null,"2026-04-16","2026-04-16",null,null,null,"MLV 79-4 to MLV 71-4D","100","1","Pig Runs - CAL / IMU 4/16/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.",null,79.41,null,"MLV 79-4 to MLV 71-4D:  Pig Runs - CAL / IMU 4/16/26\n--4/16/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-996881",null,"2026-04-21","2026-04-21",null,null,null,"MLV 79-4 to MLV 71-4D","100","1","Pig Runs - MFL-C 4/21/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.",null,79.42,null,"MLV 79-4 to MLV 71-4D:  Pig Runs - MFL-C 4/21/26\n--4/21/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-996883",null,"2026-04-23","2026-04-23",null,null,null,"MLV 79-4 to MLV 71-4D","100","1","Pig Runs - EMAT 4/23/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.",null,79.430000000000007,null,"MLV 79-4 to MLV 71-4D:  Pig Runs - EMAT 4/23/26\n--4/23/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-840559","***","2025-10-16","2025-10-31","Project Change","2025-10-01","2025-10-15","MLV 83-3 to MLV 83-3B","100","1","Install Backpressure Regulator","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,83.3,"--start_date--end_date--------------model_loc--","***MLV 83-3 to MLV 83-3B:  Install Backpressure Regulator\n--10/16/25 through 10/31/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 10/1/25 to 10/15/25.\n………………………………"]
["X25-840560","***","2025-10-01","2025-10-15","Project Change","2025-10-16","2025-10-31","MLV 83-4 to MLV 83-4B","100","1","Install Backpressure Regulator","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,83.4,"--start_date--end_date--------------model_loc--","***MLV 83-4 to MLV 83-4B:  Install Backpressure Regulator\n--10/1/25 through 10/15/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 10/16/25 to 10/31/25.\n………………………………"]
["X25-864913",null,"2025-10-06","2025-10-25",null,null,null,"MLV 84-4 to MLV 85-4","100","1","Class Change Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,84.4,null,"MLV 84-4 to MLV 85-4:  Class Change Pipe Replacement\n--10/6/25 through 10/25/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368208",null,"2025-10-14","2025-10-15",null,null,null,"Sta 87 Portland","100","2","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,87,null,"Sta 87 Portland:  Annual ESD Test\n--10/14/25 through 10/15/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-906405","***","2025-09-02","2025-09-24","Project Change","2025-08-29","2025-09-18","Sta 87","100","2","Unit 1D - Oil Cooler Cleaning/Repair","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,87.049000000000007,"--start_date--end_date--------------model_loc--","***Sta 87:  Unit 1D - Oil Cooler Cleaning/Repair\n--9/2/25 through 9/24/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***\nDate Change, Previously scheduled 8/29/25 to 9/18/25.\n………………………………"]
["X25-906404","***","2025-07-30","2025-09-05","Project Change",null,"2025-08-28","Sta 87","100","2","Unit 2D - Oil Cooler Cleaning/Repair","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,87.05,"----end_date--------------model_loc--","***Sta 87:  Unit 2D - Oil Cooler Cleaning/Repair\n--7/30/25 through 9/5/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***\nDate Change, Previously scheduled 7/30/25 to 8/28/25.\n………………………………"]
["X25-906406","***","2025-09-08","2025-10-10","Project Change","2025-09-02",null,"Sta 87","100","2","Unit 1E - Turbocharger Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,87.064999999999998,"--start_date----------------model_loc--","***Sta 87:  Unit 1E - Turbocharger Replacement\n--9/8/25 through 10/10/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/2/25 to 10/10/25.\n………………………………"]
["X25-906408",null,"2025-10-13","2025-11-26",null,null,null,"Sta 87","100","2","Unit 2E - Turbocharger Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,87.066000000000003,null,"Sta 87:  Unit 2E - Turbocharger Replacement\n--10/13/25 through 11/26/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-1075766","***","2025-09-23","2025-09-24","Added",null,null,"Sta 87","100","1","Station Piping - Valve Replacement","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,87.1,"------","***Sta 87:  Station Piping - Valve Replacement\n--9/23/25 through 9/24/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-1009116",null,"2025-11-04","2025-11-04",null,null,null,"MLV 87-4 to MLV 96-4","100","2","Pig Runs - Cleaning / Gauge 11/4/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,87.4,null,"MLV 87-4 to MLV 96-4:  Pig Runs - Cleaning / Gauge 11/4/25\n--11/4/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-69508",null,"2025-11-06","2025-11-06",null,null,null,"MLV 87-4 to MLV 96-4","100","2","Pig Runs - Caliper 11/6/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,87.4,null,"MLV 87-4 to MLV 96-4:  Pig Runs - Caliper 11/6/25\n--11/6/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-1009137",null,"2025-11-11","2025-11-11",null,null,null,"MLV 87-4 to MLV 96-4","100","2","Pig Runs - AFD Combo 11/11/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,87.41,null,"MLV 87-4 to MLV 96-4:  Pig Runs - AFD Combo 11/11/25\n--11/11/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-1009163",null,"2025-11-13","2025-11-13",null,null,null,"MLV 87-4 to MLV 96-4","100","2","Pig Runs - EMAT 11/13/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,87.42,null,"MLV 87-4 to MLV 96-4:  Pig Runs - EMAT 11/13/25\n--11/13/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-82079",null,"2025-10-16","2025-10-27",null,null,null,"MLV 90-3 to MLV 91-3","100","2","HDD River Crossing Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,90.3,null,"MLV 90-3 to MLV 91-3:  HDD River Crossing Replacement\n--10/16/25 through 10/27/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-82082",null,"2025-07-14","2025-09-13",null,null,null,"MLV 93-3 to MLV 94-3","100","2","HDD River Crossing Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,93.3,null,"MLV 93-3 to MLV 94-3:  HDD River Crossing Replacement\n--7/14/25 through 9/13/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-573543",null,"2025-09-22","2025-09-26",null,null,null,"Sta 96","100","2","Unit 2D - Compressor Valves","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,96.05,null,"Sta 96:  Unit 2D - Compressor Valves\n--9/22/25 through 9/26/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-1009324",null,"2025-09-25","2025-09-25",null,null,null,"MLV 96-5 to MLV 102-5","100","2","Pig Runs - Cleaning / Gauge 9/25/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,96.5,null,"MLV 96-5 to MLV 102-5:  Pig Runs - Cleaning / Gauge 9/25/25\n--9/25/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-1039216","***","2025-09-30","2025-09-30","Added",null,null,"MLV 96-5 to MLV 102-5","100","2","Pig Runs - Caliper 9/30/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,96.504999999999995,"------","***MLV 96-5 to MLV 102-5:  Pig Runs - Caliper 9/30/25\n--9/30/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n***Added\n………………………………"]
["X24-1009338","***","2025-10-02","2025-10-02","Project Change","2025-09-30","2025-09-30","MLV 96-5 to MLV 102-5","100","2","Pig Runs - AFD Combo 10/2/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,96.51,"--start_date--end_date--------mantenance_desc------model_loc--","***MLV 96-5 to MLV 102-5:  Pig Runs - AFD Combo 10/2/25\n--10/2/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/30/25.\n………………………………"]
["X24-1009343","***","2025-10-07","2025-10-07","Project Change","2025-10-02","2025-10-02","MLV 96-5 to MLV 102-5","100","2","Pig Runs - EMAT 10/7/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,96.52,"--start_date--end_date--------mantenance_desc------model_loc--","***MLV 96-5 to MLV 102-5:  Pig Runs - EMAT 10/7/25\n--10/7/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n***\nDate Change, Previously scheduled 10/2/25.\n………………………………"]
["X25-450067","***","2025-07-30","2025-09-10","Project Change",null,"2025-08-30","MLV 101-5 to MLV 102-5","100","2","Class Change Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,101.5,"----end_date--------------model_loc--","***MLV 101-5 to MLV 102-5:  Class Change Pipe Replacement\n--7/30/25 through 9/10/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***\nDate Change, Previously scheduled 7/30/25 to 8/30/25.\n………………………………"]
["X25-445995",null,"2025-09-15","2025-10-03",null,null,null,"Sta 106 Clay City","100","2","Upgrade B Building Jacket Water System","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,106.017,null,"Sta 106 Clay City:  Upgrade B Building Jacket Water System\n--9/15/25 through 10/3/25:  This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-445886","***","2025-04-14","2025-10-17","Project Change",null,"2025-09-26","Sta 106","100","2","Unit 1C - Replace Power Cylinder Bearing #7","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,106.033,"----end_date--------------model_loc--","***Sta 106:  Unit 1C - Replace Power Cylinder Bearing #7\n--4/14/25 through 10/17/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***\nDate Change, Previously scheduled 4/14/25 to 9/26/25.\n………………………………"]
["X25-877868",null,"2025-09-22","2025-09-26",null,null,null,"Sta 106","100","2","Unit  1D - Solar 4K/8K Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,106.065,null,"Sta 106:  Unit  1D - Solar 4K/8K Inspection\n--9/22/25 through 9/26/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-877864","***","2025-08-26","2025-08-28","Completed",null,null,"Sta 106","100","2","Unit 2D - Solar 4K/8K Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,106.066,"------","***Sta 106:  Unit 2D - Solar 4K/8K Inspection\n***Completed"]
["X25-276816","***","2025-09-03","2025-09-30","Project Change",null,"2025-09-20","MLV 106-1D to MLV 110-7","100","2","Make Piggable Valve MLV 107-7, MLV 109-7 Replacements & Adding MLV 109-7A","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in during the project.","420946 MOREHEAD/TGP CITY OF MOREHEAD ROWAN",106.1,"----end_date--------------model_loc--","***MLV 106-1D to MLV 110-7:  Make Piggable Valve MLV 107-7, MLV 109-7 Replacements & Adding MLV 109-7A\n--9/3/25 through 9/30/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420946 MOREHEAD/TGP CITY OF MOREHEAD ROWAN\n***\nDate Change, Previously scheduled 9/3/25 to 9/20/25.\n………………………………"]
["X25-996897",null,"2025-09-03","2025-09-11",null,null,null,"MLV 106-1D to MLV 110-7","100","2","Make Piggable Valve Adding MLV 106-7A","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in during the project.","55963 AHMLFG/TGP RUMPKE BIOGAS RECEIPT MO\n55964 AHMLFG/TGP RUMPKE BIOGAS BUYBACK DE",106.1,null,"MLV 106-1D to MLV 110-7:  Make Piggable Valve Adding MLV 106-7A\n--9/3/25 through 9/11/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n55963 AHMLFG/TGP RUMPKE BIOGAS RECEIPT MO\n55964 AHMLFG/TGP RUMPKE BIOGAS BUYBACK DE\n………………………………"]
["X24-1009349",null,"2025-10-09","2025-10-09",null,null,null,"MLV 106-1 to MLV 111-7","100","2","Pig Runs - Cleaning / Gauge 10/9/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,106.1,null,"MLV 106-1 to MLV 111-7:  Pig Runs - Cleaning / Gauge 10/9/25\n--10/9/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-1009358",null,"2025-10-14","2025-10-14",null,null,null,"MLV 106-1 to MLV 111-7","100","2","Pig Runs - AFD Combo 10/14/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,106.11,null,"MLV 106-1 to MLV 111-7:  Pig Runs - AFD Combo 10/14/25\n--10/14/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-1009364",null,"2025-10-16","2025-10-16",null,null,null,"MLV 106-1 to MLV 111-7","100","2","Pig Runs - EMAT 10/16/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,106.12,null,"MLV 106-1 to MLV 111-7:  Pig Runs - EMAT 10/16/25\n--10/16/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-1368164",null,"2025-10-30","2025-10-30",null,null,null,"Sta 107A North Means","100","2","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,107,null,"Sta 107A North Means:  Annual ESD Test\n--10/30/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-276809",null,"2025-11-01","2025-11-30",null,null,null,"MLV 108-2 to MLV 109-2","100","2","Special Permit Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in during the project.","420212 DELTA NG/TGP SALT LICK KY BATH\n420038 MOREHEAD/TGP MOREHEAD KY ROWAN",108.2,null,"MLV 108-2 to MLV 109-2:  Special Permit Pipe Replacement\n--11/1/25 through 11/30/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420212 DELTA NG/TGP SALT LICK KY BATH\n420038 MOREHEAD/TGP MOREHEAD KY ROWAN\n………………………………"]
["X25-276814",null,"2025-09-24","2025-10-15",null,null,null,"MLV 108-3 to MLV 109-3","100","2","Special Permit Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,108.3,null,"MLV 108-3 to MLV 109-3:  Special Permit Pipe Replacement\n--9/24/25 through 10/15/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-840676",null,"2025-10-16","2025-10-31",null,null,null,"MLV 109-2 to 109-2A","100","2","Special Permit Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,109.2,null,"MLV 109-2 to 109-2A:  Special Permit Pipe Replacement\n--10/16/25 through 10/31/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-837504",null,"2025-10-16","2025-10-31",null,null,null,"MLV 109-3 to MLV 109-3A","100","3","Class Change Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,109.3,null,"MLV 109-3 to MLV 109-3A:  Class Change Pipe Replacement\n--10/16/25 through 10/31/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-962837",null,"2025-10-20","2025-10-24",null,null,null,"Sta 110 Morehead","100","3","Unit Inspections","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,110.001,null,"Sta 110 Morehead:  Unit Inspections\n--10/20/25 through 10/24/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-1009371",null,"2025-10-23","2025-10-23",null,null,null,"MLV 111-3 to MLV 114-3","100","2","Pig Runs - Cleaning / Gauge 10/23/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,111.3,null,"MLV 111-3 to MLV 114-3:  Pig Runs - Cleaning / Gauge 10/23/25\n--10/23/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1009383",null,"2025-10-28","2025-10-28",null,null,null,"MLV 111-3 to MLV 114-3","100","2","Pig Runs - AFD Combo 10/28/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,111.31,null,"MLV 111-3 to MLV 114-3:  Pig Runs - AFD Combo 10/28/25\n--10/28/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1009386",null,"2025-10-30","2025-10-30",null,null,null,"MLV 111-3 to MLV 114-3","100","2","Pig Runs - EMAT 10/30/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,111.32,null,"MLV 111-3 to MLV 114-3:  Pig Runs - EMAT 10/30/25\n--10/30/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-994158",null,"2025-10-24","2025-10-25",null,null,null,"Sta 114","100","3","Installation of Unit Valves","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,114,null,"Sta 114:  Installation of Unit Valves\n--10/24/25 through 10/25/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-1079245","***","2025-09-18","2025-09-18","Added",null,null,"Sta 114","100","6","Station Outage - C Units 1-3 - Replace Diodes all C Units","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,114.033,"------","***Sta 114:  Station Outage - C Units 1-3 - Replace Diodes all C Units\n--9/18/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-994162",null,"2025-10-27","2025-10-27",null,null,null,"Sta 114","100","3","Unit 1C - Complete Intallation of Unit Valves","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,114.033,null,"Sta 114:  Unit 1C - Complete Intallation of Unit Valves\n--10/27/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-994166",null,"2025-10-29","2025-10-29",null,null,null,"Sta 114","100","3","Unit 2C - Complete Installation of Unit Valves","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,114.03400000000001,null,"Sta 114:  Unit 2C - Complete Installation of Unit Valves\n--10/29/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368165","***","2025-10-27","2025-10-29","Project Change","2025-09-16","2025-09-18","Sta 118A Tyler Mountain","100","3","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,118,"--start_date--end_date--------------model_loc--","***Sta 118A Tyler Mountain:  Annual ESD Test\n--10/27/25 through 10/29/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/16/25 to 9/18/25.\n………………………………"]
["X25-366364",null,"2025-10-06","2025-10-11",null,null,null,"Sta 118A","100","3","Unit 1A - Turbine Exchange","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,118.001,null,"Sta 118A:  Unit 1A - Turbine Exchange\n--10/6/25 through 10/11/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-1036692",null,"2025-08-29","2025-09-12",null,null,null,"Sta 119A","100","3","Rocky Fork: Force Majeure - Unit 1A","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,119,null,"Sta 119A:  Rocky Fork: Force Majeure - Unit 1A\n--8/29/25 through 9/12/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-480944","***","2025-08-25","2025-08-28","Completed",null,null,"Sta 119A","100","3","Rocky Fork: Unit 1A - 4k Hr Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,119.001,"------","***Sta 119A:  Rocky Fork: Unit 1A - 4k Hr Inspection\n***Completed"]
["X25-878051",null,"2025-08-05","2025-10-19",null,null,null,"Sta 87 to Sta 219","200","4","Cumulative Planned/Unplanned Maintenance-204","This project may require taking pipeline sections out of service which could limit throughput and result in restrictions based on customer nominations.",null,204,null,"Sta 87 to Sta 219:  Cumulative Planned/Unplanned Maintenance-204\n--8/5/25 through 10/19/25:  This project may require taking pipeline sections out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-334671",null,"2025-09-22","2025-09-24",null,null,null,"Sta 204","200","4","Scrubber Filter","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,204,null,"Sta 204:  Scrubber Filter\n--9/22/25 through 9/24/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-976577",null,"2025-09-01","2025-09-02",null,null,null,"Sta 204","200","4","Unit 1A - Turbo Housing","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,204.001,null,"Sta 204:  Unit 1A - Turbo Housing\n--9/1/25 through 9/2/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-976582",null,"2025-09-15","2025-09-16",null,null,null,"Sta 204","200","4","Unit 3A - Turbo Housing","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,204.00299999999999,null,"Sta 204:  Unit 3A - Turbo Housing\n--9/15/25 through 9/16/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-954405","***","2025-08-25","2025-08-28","Completed",null,null,"Sta 204","200","4","Unit 9A - Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,204.00899999999999,"------","***Sta 204:  Unit 9A - Crankcase Inspection\n***Completed"]
["X25-976579",null,"2025-09-08","2025-09-11",null,null,null,"Sta 204","200","4","Unit 10A - Turbo Housing","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,204.01,null,"Sta 204:  Unit 10A - Turbo Housing\n--9/8/25 through 9/11/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-1017097",null,"2025-12-02","2025-12-02",null,null,null,"MLV 204-2 to MLV 200-2","200","4","Pig Runs - Cleaning / Gauge 12/2/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","421018 TET/TGP HANGING ROCK SCIOTO",204.2,null,"MLV 204-2 to MLV 200-2:  Pig Runs - Cleaning / Gauge 12/2/25\n--12/2/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n421018 TET/TGP HANGING ROCK SCIOTO\n………………………………"]
["X25-823240","***","2025-08-28","2025-08-28","Completed",null,null,"MLV 204-2 to MLV 200-2","200","4","Pig Runs - Hard Spot 8/28/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","421018 TET/TGP HANGING ROCK SCIOTO",204.23,"------","***MLV 204-2 to MLV 200-2:  Pig Runs - Hard Spot 8/28/25\n***Completed\nThe following meters are available for nominations:\n421018 TET/TGP HANGING ROCK SCIOTO"]
["X25-35079",null,"2025-12-16","2025-12-16",null,null,null,"MLV 204-2 to MLV 200-2","200","4","Pig Runs - MFL-C 12/16/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","421018 TET/TGP HANGING ROCK SCIOTO",204.25,null,"MLV 204-2 to MLV 200-2:  Pig Runs - MFL-C 12/16/25\n--12/16/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n421018 TET/TGP HANGING ROCK SCIOTO\n………………………………"]
["X25-624941",null,"2025-12-18","2025-12-18",null,null,null,"MLV 204-2 to MLV 200-2","200","4","Pig Runs - EMAT 12/18/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","421018 TET/TGP HANGING ROCK SCIOTO",204.26,null,"MLV 204-2 to MLV 200-2:  Pig Runs - EMAT 12/18/25\n--12/18/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n421018 TET/TGP HANGING ROCK SCIOTO\n………………………………"]
["X25-219101","***","2025-07-16","2025-09-01","Completed",null,null,"MLV 205-2 to MLV 206-2","200","4","Special Permit Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,205.2,"------","***MLV 205-2 to MLV 206-2:  Special Permit Replacement\n***Completed"]
["X25-334672",null,"2025-09-25","2025-09-27",null,null,null,"Sta 209 Cambridge","200","4","Scrubber Filter","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,209,null,"Sta 209 Cambridge:  Scrubber Filter\n--9/25/25 through 9/27/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-954407",null,"2025-09-29","2025-10-02",null,null,null,"Sta 209","200","4","Unit 4A - Packing & Starting Air Valves","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,209.00399999999999,null,"Sta 209:  Unit 4A - Packing & Starting Air Valves\n--9/29/25 through 10/2/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-954406",null,"2025-09-22","2025-09-25",null,null,null,"Sta 209","200","4","Unit 5A - Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,209.005,null,"Sta 209:  Unit 5A - Crankcase Inspection\n--9/22/25 through 9/25/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-882583",null,"2025-09-15","2025-09-18",null,null,null,"Sta 209","200","4","Unit 7A - Install F/W Turbo","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,209.00700000000001,null,"Sta 209:  Unit 7A - Install F/W Turbo\n--9/15/25 through 9/18/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-954408",null,"2025-10-06","2025-10-09",null,null,null,"Sta 209","200","4","Unit 7A - Packing","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,209.00700000000001,null,"Sta 209:  Unit 7A - Packing\n--10/6/25 through 10/9/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-806415","***","2025-09-02","2025-09-05","Project Change","2025-09-08","2025-09-11","Sta 209","200","4","Unit 12A - Install Barring Jack","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,209.012,"--start_date--end_date--------------model_loc--","***Sta 209:  Unit 12A - Install Barring Jack\n--9/2/25 through 9/5/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/8/25 to 9/11/25.\n………………………………"]
["X24-1017066",null,"2025-10-30","2025-10-30",null,null,null,"MLV 209-4 to MLV 204-4","200","4","Pig Runs - Cleaning / Gauge 10/30/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,209.4,null,"MLV 209-4 to MLV 204-4:  Pig Runs - Cleaning / Gauge 10/30/25\n--10/30/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-819246",null,"2025-11-04","2025-11-04",null,null,null,"MLV 209-4 to MLV 204-4","200","4","Pig Runs - Cal & IMU 11/04/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,209.405,null,"MLV 209-4 to MLV 204-4:  Pig Runs - Cal & IMU 11/04/25\n--11/4/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1017067",null,"2025-11-06","2025-11-06",null,null,null,"MLV 209-4 to MLV 204-4","200","4","Pig Runs - MFL-A 11/06/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,209.41,null,"MLV 209-4 to MLV 204-4:  Pig Runs - MFL-A 11/06/25\n--11/6/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-219100",null,"2025-09-23","2025-10-31",null,null,null,"MLV 213-2A to MLV 214-2","200","4","Special Permit Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,213.2,null,"MLV 213-2A to MLV 214-2:  Special Permit Replacement\n--9/23/25 through 10/31/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-1007484",null,"2025-08-21","2025-09-05",null,null,null,"Sta 214","200","4","Unit 2A - Ignition Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,214.00200000000001,null,"Sta 214:  Unit 2A - Ignition Inspection\n--8/21/25 through 9/5/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-475076","***","2025-08-28","2025-08-28","Completed",null,null,"MLV 214-1 to MLV 209-1","200","4","Pig Re-Runs - EMAT 8/28/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,214.1,"------","***MLV 214-1 to MLV 209-1:  Pig Re-Runs - EMAT 8/28/25\n***Completed"]
["X25-219099",null,"2025-08-12","2025-09-09",null,null,null,"MLV 216-2 to MLV 216-2A","200","4","Class Change Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,216.2,null,"MLV 216-2 to MLV 216-2A:  Class Change Replacement\n--8/12/25 through 9/9/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-906300",null,"2025-08-04","2025-10-19",null,null,null,"Sta 87 to Sta 219","200","4","Cumulative Planned/Unplanned Maintenance-217","This project may require taking pipeline sections out of service which could limit throughput and result in restrictions based on customer nominations.",null,217,null,"Sta 87 to Sta 219:  Cumulative Planned/Unplanned Maintenance-217\n--8/4/25 through 10/19/25:  This project may require taking pipeline sections out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-1001014","***","2025-08-25","2025-08-29","Completed",null,null,"Sta 219","200","5","Unit 5A - Engine Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,219.005,"------","***Sta 219:  Unit 5A - Engine Maintenance\n***Completed"]
["X25-898195",null,"2025-11-11","2025-11-11",null,null,null,"MLV 219-4 to MLV 214-4","200","4","Pig Run - Cleaning/Gauge 11/11/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","47882 UGIAPP/TP BRINKER NO.2 COLUMBIANA\n53950 UGIAPP/TGP FARMER BROTHERS COLUMBIA\n47605 GEOPETRO/TGP FIRESTONE HOMESTEAD CO\n420496 NFG/TGP SHARON PA MERCER",219.4,null,"MLV 219-4 to MLV 214-4:  Pig Run - Cleaning/Gauge 11/11/25\n--11/11/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n47882 UGIAPP/TP BRINKER NO.2 COLUMBIANA\n53950 UGIAPP/TGP FARMER BROTHERS COLUMBIA\n47605 GEOPETRO/TGP FIRESTONE HOMESTEAD CO\n420496 NFG/TGP SHARON PA MERCER\n………………………………"]
["X25-898202","***","2025-11-20","2025-11-20","Added",null,null,"MLV 219-4 to MLV 214-4","200","4","Pig Run - EMAT 11/20/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","47882 UGIAPP/TP BRINKER NO.2 COLUMBIANA\n53950 UGIAPP/TGP FARMER BROTHERS COLUMBIA\n47605 GEOPETRO/TGP FIRESTONE HOMESTEAD CO\n420496 NFG/TGP SHARON PA MERCER",219.4,"--------anticipated_impact------prl----model_loc--","***MLV 219-4 to MLV 214-4:  Pig Run - EMAT 11/20/25\n--11/20/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n47882 UGIAPP/TP BRINKER NO.2 COLUMBIANA\n53950 UGIAPP/TGP FARMER BROTHERS COLUMBIA\n47605 GEOPETRO/TGP FIRESTONE HOMESTEAD CO\n420496 NFG/TGP SHARON PA MERCER\n***Added\n………………………………"]
["X25-898201","***","2025-11-18","2025-11-18","Added",null,null,"MLV 219-4 to MLV 214-4","200","4","Pig Run - MFL-C 11/18/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","47882 UGIAPP/TP BRINKER NO.2 COLUMBIANA\n53950 UGIAPP/TGP FARMER BROTHERS COLUMBIA\n47605 GEOPETRO/TGP FIRESTONE HOMESTEAD CO\n420496 NFG/TGP SHARON PA MERCER",219.41,"--------anticipated_impact------prl----model_loc--","***MLV 219-4 to MLV 214-4:  Pig Run - MFL-C 11/18/25\n--11/18/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n47882 UGIAPP/TP BRINKER NO.2 COLUMBIANA\n53950 UGIAPP/TGP FARMER BROTHERS COLUMBIA\n47605 GEOPETRO/TGP FIRESTONE HOMESTEAD CO\n420496 NFG/TGP SHARON PA MERCER\n***Added\n………………………………"]
["X25-898199","***","2025-11-13","2025-11-13","Added",null,null,"MLV 219-4 to MLV 214-4","200","4","Pig Run - IMU/Caliper 11/13/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","47882 UGIAPP/TP BRINKER NO.2 COLUMBIANA\n53950 UGIAPP/TGP FARMER BROTHERS COLUMBIA\n47605 GEOPETRO/TGP FIRESTONE HOMESTEAD CO\n420496 NFG/TGP SHARON PA MERCER",219.43,"--------anticipated_impact------prl----model_loc--","***MLV 219-4 to MLV 214-4:  Pig Run - IMU/Caliper 11/13/25\n--11/13/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n47882 UGIAPP/TP BRINKER NO.2 COLUMBIANA\n53950 UGIAPP/TGP FARMER BROTHERS COLUMBIA\n47605 GEOPETRO/TGP FIRESTONE HOMESTEAD CO\n420496 NFG/TGP SHARON PA MERCER\n***Added\n………………………………"]
["X25-837511",null,"2025-08-11","2025-09-05",null,null,null,"Sta 229","200","5","Automation Upgrade & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,229,null,"Sta 229:  Automation Upgrade & Maintenance\n--8/11/25 through 9/5/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-219102",null,"2025-09-29","2025-10-10",null,null,null,"MLV 236-1 to MLV 237-1BR","200","5","Special Permit Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be constrained or shut in during the project.","412856 EMPIREPL/TGP CANANDIAGUA ONTARIO\n420617 EGTS/TGP HOPEWELL SALES ONTARIO\n420526 HONEOYE/TGP UDP HONEOYE NEW YORK ON",236.1,null,"MLV 236-1 to MLV 237-1BR:  Special Permit Replacement\n--9/29/25 through 10/10/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n412856 EMPIREPL/TGP CANANDIAGUA ONTARIO\n420617 EGTS/TGP HOPEWELL SALES ONTARIO\n420526 HONEOYE/TGP UDP HONEOYE NEW YORK ON\n………………………………"]
["X25-826135",null,"2025-10-10","2025-10-17",null,null,null,"MLV 540-1 to MLV 540-1A","500","1","Shallow Pipe Lowering","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,240.1,null,"MLV 540-1 to MLV 540-1A:  Shallow Pipe Lowering\n--10/10/25 through 10/17/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-1022125",null,"2025-10-06","2025-10-10",null,null,null,"Sta 241","200","5","Unit 1A - Engine Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,241.001,null,"Sta 241:  Unit 1A - Engine Maintenance\n--10/6/25 through 10/10/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-1022128",null,"2025-10-13","2025-10-17",null,null,null,"Sta 241","200","5","Unit 2A - Engine Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,241.00200000000001,null,"Sta 241:  Unit 2A - Engine Maintenance\n--10/13/25 through 10/17/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-174024",null,"2025-09-08","2025-09-27",null,null,null,"Sta 241","200","5","Unit 3A - C3 Cooper Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,241.00299999999999,null,"Sta 241:  Unit 3A - C3 Cooper Upgrade\n--9/8/25 through 9/27/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-155765",null,"2025-10-07","2025-10-08",null,null,null,"Sta 241","200","5","Unit 1B - 2K Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,241.0171,null,"Sta 241:  Unit 1B - 2K Maintenance\n--10/7/25 through 10/8/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-69555",null,"2025-09-08","2025-09-12",null,null,null,"Sta 245","200","5","Unit 1C - Engine Exchange","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,245.03299999999999,null,"Sta 245:  Unit 1C - Engine Exchange\n--9/8/25 through 9/12/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-898209",null,"2025-10-01","2025-10-31",null,null,null,"Sta 249","200","5","Unit 1A - Aftercooler Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,249.001,null,"Sta 249:  Unit 1A - Aftercooler Upgrade\n--10/1/25 through 10/31/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-816748",null,"2025-09-02","2025-09-04",null,null,null,"Sta 249","200","5","Unit 2B - Replace Compressor Rod Packing","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,249.018,null,"Sta 249:  Unit 2B - Replace Compressor Rod Packing\n--9/2/25 through 9/4/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-725630",null,"2025-07-14","2025-11-01",null,null,null,"Sta. 254","200","5","Bldg A Stack Replacement and Unit Upgrades","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,254.001,null,"Sta. 254:  Bldg A Stack Replacement and Unit Upgrades\n--7/14/25 through 11/1/25:  This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-593403",null,"2025-05-16","2025-11-01",null,null,null,"Sta 254","200","5","Unit 4A - Replace Power Cylinder Head","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,254.00399999999999,null,"Sta 254:  Unit 4A - Replace Power Cylinder Head\n--5/16/25 through 11/1/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-1017499",null,"2025-09-15","2025-09-16",null,null,null,"Sta 254","200","4","Unit 2B - HIM Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,254.018,null,"Sta 254:  Unit 2B - HIM Upgrade\n--9/15/25 through 9/16/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-174156",null,"2025-09-23","2025-09-23",null,null,null,"MLV 254-1 to MLV 261-1","200","5","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,254.1,null,"MLV 254-1 to MLV 261-1:  Pig Run - Maintenance\n--9/23/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-174157",null,"2025-09-24","2025-09-24",null,null,null,"MLV 254-2 to MLV 261-2","200","5","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,254.2,null,"MLV 254-2 to MLV 261-2:  Pig Run - Maintenance\n--9/24/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-174159",null,"2025-09-25","2025-09-25",null,null,null,"MLV 254-3 to MLV 258-3","200","5","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,254.3,null,"MLV 254-3 to MLV 258-3:  Pig Run - Maintenance\n--9/25/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-104697",null,"2025-09-23","2025-09-23",null,null,null,"Sta 260A Southwick","200","6","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,260,null,"Sta 260A Southwick:  Annual ESD Test\n--9/23/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1020199",null,"2026-05-04","2026-05-04",null,null,null,"MLV 260A-101.1 TO MLV 260A-103","200","6","Pig Runs - MFL-C 7/15/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420104 WESTFLD/TGP WESTFIELD MA HAMPDEN\n420401 HOLYOKE/TGP HOLYOKE MA 2 HAMPDEN\n420292 BERKSHR/TGP GREENFIELD MA HAMPSHIRE\n420106 EVRSRC/TGP GRANITE NORTHAMPTON MA H",260.11,null,"MLV 260A-101.1 TO MLV 260A-103:  Pig Runs - MFL-C 7/15/25\n--5/4/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420104 WESTFLD/TGP WESTFIELD MA HAMPDEN\n420401 HOLYOKE/TGP HOLYOKE MA 2 HAMPDEN\n420292 BERKSHR/TGP GREENFIELD MA HAMPSHIRE\n420106 EVRSRC/TGP GRANITE NORTHAMPTON MA H\n………………………………"]
["X25-104695",null,"2025-10-13","2025-10-15",null,null,null,"Sta 261 Agawam","200","6","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","420901 BERKPWR/TGP BERKSHIRE POWER SALES H",261,null,"Sta 261 Agawam:  Annual ESD Test\n--10/13/25 through 10/15/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420901 BERKPWR/TGP BERKSHIRE POWER SALES H\n………………………………"]
["X25-427478",null,"2025-10-06","2025-10-09",null,null,null,"Sta 261","200","6","Unit 4A - Compressor Rod Packing","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","420901 BERKPWR/TGP BERKSHIRE POWER SALES H",261.00400000000002,null,"Sta 261:  Unit 4A - Compressor Rod Packing\n--10/6/25 through 10/9/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420901 BERKPWR/TGP BERKSHIRE POWER SALES H\n………………………………"]
["X25-1032027",null,"2025-09-08","2025-09-19",null,null,null,"Sta 261","200","6","Unit 1C - Valve replacement & Solar Commissioning","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,261.03300000000002,null,"Sta 261:  Unit 1C - Valve replacement & Solar Commissioning\n--9/8/25 through 9/19/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-550155","***","2025-08-21","2025-09-12","Completed",null,null,"MLV 263-2 to 264-2","200","6","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,263.2,"------","***MLV 263-2 to 264-2:  Pipe Replacement\n***Completed"]
["X25-104693",null,"2025-09-25","2025-09-25",null,null,null,"Sta 264 Charlton","200","6","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,264,null,"Sta 264 Charlton:  Annual ESD Test\n--9/25/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-520791",null,"2025-10-03","2025-10-14",null,null,null,"MLV 265E-103 to MLV 265E-104","200","6","Regulator Installation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be constrained or shut in during the project.","420750 NARNGST/TGP CRANSTON SALES PROVIDEN\n420926 RISEC/TGP FPLE RISE PROVIDENCE\n55784 RHOBIO/TGP SCITUATE RNG REC PROVIDE\n55785 RHOBIO/TGP SCITUATE RNG BUYBACK PR\n420910 NARNGST/TGP SMITHFIELD DELIVERY PRO\n420758 NARNGST/TGP LINCOLN SMS PROVIDENCE",265.10000000000002,null,"MLV 265E-103 to MLV 265E-104:  Regulator Installation\n--10/3/25 through 10/14/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420750 NARNGST/TGP CRANSTON SALES PROVIDEN\n420926 RISEC/TGP FPLE RISE PROVIDENCE\n55784 RHOBIO/TGP SCITUATE RNG REC PROVIDE\n55785 RHOBIO/TGP SCITUATE RNG BUYBACK PR\n420910 NARNGST/TGP SMITHFIELD DELIVERY PRO\n420758 NARNGST/TGP LINCOLN SMS PROVIDENCE\n………………………………"]
["X25-717174",null,"2025-09-03","2025-09-20",null,null,null,"MLV 265E-201 to 265E-202","200","6","Make Piggable","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","420758 NARNGST/TGP LINCOLN SMS PROVIDENCE",265.2,null,"MLV 265E-201 to 265E-202:  Make Piggable\n--9/3/25 through 9/20/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420758 NARNGST/TGP LINCOLN SMS PROVIDENCE\n………………………………"]
["X24-1020284",null,"2025-12-10","2025-12-10",null,null,null,"MLV 265E-201 to MLV 265E-202","200","6","Pig Runs - Cleaning / Gauge 12/10/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420758 NARNGST/TGP LINCOLN SMS PROVIDENCE",265.2,null,"MLV 265E-201 to MLV 265E-202:  Pig Runs - Cleaning / Gauge 12/10/25\n--12/10/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420758 NARNGST/TGP LINCOLN SMS PROVIDENCE\n………………………………"]
["X24-1020336",null,"2025-12-10","2025-12-10",null,null,null,"MLV 265E-201 to MLV 265E-202","200","6","Pig Runs - MFL-A / Cal / IMU Combo 12/10/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420758 NARNGST/TGP LINCOLN SMS PROVIDENCE",265.20999999999998,null,"MLV 265E-201 to MLV 265E-202:  Pig Runs - MFL-A / Cal / IMU Combo 12/10/25\n--12/10/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420758 NARNGST/TGP LINCOLN SMS PROVIDENCE\n………………………………"]
["X25-438209",null,"2025-09-02","2025-11-26",null,null,null,"Sta. 267","200","6","Bldg A Controls Upgrade","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,267.00099999999998,null,"Sta. 267:  Bldg A Controls Upgrade\n--9/2/25 through 11/26/25:  This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-155974",null,"2025-09-15","2025-09-20",null,null,null,"MLV 267-1A to MLV 268-1","200","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,267.10000000000002,null,"MLV 267-1A to MLV 268-1:  Anomaly Remediation\n--9/15/25 through 9/20/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-717181",null,"2025-09-15","2025-10-11",null,null,null,"MLV 268A-301 to 268A-302","200","6","Make Piggable","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","420111 BOSTN/TGP LEOMINSTER MA WORCHESTER",268.3,null,"MLV 268A-301 to 268A-302:  Make Piggable\n--9/15/25 through 10/11/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420111 BOSTN/TGP LEOMINSTER MA WORCHESTER\n………………………………"]
["X24-1020346",null,"2025-12-18","2025-12-18",null,null,null,"MLV 268A-301A TO MLV 268A-302","200","6","Pig Runs - Cleaning / Gauge 12/18/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420111 BOSTN/TGP LEOMINSTER MA WORCHESTER",268.3,null,"MLV 268A-301A TO MLV 268A-302:  Pig Runs - Cleaning / Gauge 12/18/25\n--12/18/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420111 BOSTN/TGP LEOMINSTER MA WORCHESTER\n………………………………"]
["X24-1020369",null,"2025-12-18","2025-12-18",null,null,null,"MLV 268A-301A TO MLV 268A-302","200","6","Pig Runs - MFL-A / Cal / IMU Combo 12/18/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420111 BOSTN/TGP LEOMINSTER MA WORCHESTER",268.31,null,"MLV 268A-301A TO MLV 268A-302:  Pig Runs - MFL-A / Cal / IMU Combo 12/18/25\n--12/18/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420111 BOSTN/TGP LEOMINSTER MA WORCHESTER\n………………………………"]
["X25-475021",null,"2025-09-09","2025-09-14",null,null,null,"MLV 270-1A to MLV 270-101.1R","200","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,270.10000000000002,null,"MLV 270-1A to MLV 270-101.1R:  Anomaly Remediation\n--9/9/25 through 9/14/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-847658",null,"2026-01-12","2026-01-30",null,null,null,"MLV 270C-103 to MLV 270C-104","200","6","Meter Station Upgrade (Meter Peabody PIN 420658)","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","420658 MMWEC/TGP PEABODY SALES ESSEX",270.10000000000002,null,"MLV 270C-103 to MLV 270C-104:  Meter Station Upgrade (Meter Peabody PIN 420658)\n--1/12/26 through 1/30/26:  This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420658 MMWEC/TGP PEABODY SALES ESSEX\n………………………………"]
["X25-177135",null,"2025-10-07","2025-10-08",null,null,null,"Sta 303A","300","4","Unit 1A - Water Wash","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,303.00099999999998,null,"Sta 303A:  Unit 1A - Water Wash\n--10/7/25 through 10/8/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-177137",null,"2025-09-22","2025-09-26",null,null,null,"Sta 307 (Pigeon )","300","4","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,307,null,"Sta 307 (Pigeon ):  Annual ESD Test\n--9/22/25 through 9/26/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-993857",null,"2025-09-08","2025-09-12",null,null,null,"Sta 307","300","4","Unit 2A - Engine Maintenace","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,307.00200000000001,null,"Sta 307:  Unit 2A - Engine Maintenace\n--9/8/25 through 9/12/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-993859",null,"2025-09-08","2025-09-12",null,null,null,"Sta 307","300","4","Unit 3A - Engine Maintenace","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,307.00299999999999,null,"Sta 307:  Unit 3A - Engine Maintenace\n--9/8/25 through 9/12/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-177254",null,"2025-09-22","2025-09-26",null,null,null,"Sta 307","300","4","Unit 6A - Protective Device Checks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,307.00599999999997,null,"Sta 307:  Unit 6A - Protective Device Checks\n--9/22/25 through 9/26/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-952324",null,"2025-09-10","2025-09-10",null,null,null,"Station 310 Smethport","300","4","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,310,null,"Station 310 Smethport:  Annual ESD Test\n--9/10/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-1001003",null,"2025-11-03","2025-11-07",null,null,null,"Ellisburg Storage","300","4","Shut-in Test","This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","460012 – DOMINION/TGP ELLISBURG INJECTION PO",313.00009999999997,null,"Ellisburg Storage:  Shut-in Test\n--11/3/25 through 11/7/25:  This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n460012 – DOMINION/TGP ELLISBURG INJECTION PO\n………………………………"]
["X25-1001005",null,"2025-10-13","2025-10-17",null,null,null,"Harrison Storage","300","4","Shut-in Test","This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","460004 – DOMINION/TGP HARRISON INJECTION POT",313.00020000000001,null,"Harrison Storage:  Shut-in Test\n--10/13/25 through 10/17/25:  This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n460004 – DOMINION/TGP HARRISON INJECTION POT\n………………………………"]
["X25-1001006",null,"2025-11-03","2025-11-07",null,null,null,"Hebron Storage","300","4","Shut-in Test","This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","400485 HEBRON STORAGE INJECTION POTTER\n470001 HEBRON STORAGE WITHDRAWAL POTTER",313.00029999999998,null,"Hebron Storage:  Shut-in Test\n--11/3/25 through 11/7/25:  This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n400485 HEBRON STORAGE INJECTION POTTER\n470001 HEBRON STORAGE WITHDRAWAL POTTER\n………………………………"]
["X25-742697",null,"2025-09-22","2025-09-26",null,null,null,"Sta 313","300","4","Unit 1C - Capacitor Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,313.03300000000002,null,"Sta 313:  Unit 1C - Capacitor Replacement\n--9/22/25 through 9/26/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-219119",null,"2025-10-27","2025-11-07",null,null,null,"MLV 313-0806","300","4","Drip Removal","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,313.8,null,"MLV 313-0806:  Drip Removal\n--10/27/25 through 11/7/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-837317","***","2025-08-25","2025-08-29","Completed",null,null,"Hebron Storage","300","4","Dehy Facility Maintenance","This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","400485 HEBRON STORAGE INJECTION POTTER\n470001 HEBRON STORAGE WITHDRAWAL POTTER",313.89999999999998,"------","***Hebron Storage:  Dehy Facility Maintenance\n***Completed\nThe following meters are available for nominations:\n400485 HEBRON STORAGE INJECTION POTTER\n470001 HEBRON STORAGE WITHDRAWAL POTTER"]
["X25-1007487",null,"2025-09-17","2025-09-18",null,null,null,"Sta 315","300","4","Unit 2A - Water Wash & Borescope","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,315.00200000000001,null,"Sta 315:  Unit 2A - Water Wash & Borescope\n--9/17/25 through 9/18/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-1007485",null,"2025-09-16","2025-09-16",null,null,null,"Sta 315","300","4","Unit 1B - Water Wash & Borescope","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,315.017,null,"Sta 315:  Unit 1B - Water Wash & Borescope\n--9/16/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-686355",null,"2025-09-09","2025-09-12",null,null,null,"Sta 317","300","4","Unit 1B - Engine Maintenace","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,317.017,null,"Sta 317:  Unit 1B - Engine Maintenace\n--9/9/25 through 9/12/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-1036806","***","2025-09-22","2025-09-23","Added",null,null,"Sta 317","300","4","Units 1C - Water Wash","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,317.03300000000002,"------","***Sta 317:  Units 1C - Water Wash\n--9/22/25 through 9/23/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-547649",null,"2025-09-16","2025-09-17",null,null,null,"MLV 317-1 to MLV 318-1","300","4","Hot Tap for New Meter (Meter: Port Royal PIN: 57162)","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed may be constrained or shut in during the project.","412784\tETC NEPL/TGP ALLEN MEADOW DEHY:RIP \n412785\tBLCKHILL/TGP SWAIN ROAD DEHY: RIP 3\n412834\tAPPLACHA/TGP UDP CALKINS DEHY: RIP \n412850\tAPPLACHA/TGP UDP LIBERTY DEHY: RIP \n420216\tVALLEY/TGP TOWANDA PA BRADFORD",317.10000000000002,null,"MLV 317-1 to MLV 318-1:  Hot Tap for New Meter (Meter: Port Royal PIN: 57162)\n--9/16/25 through 9/17/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n412784\tETC NEPL/TGP ALLEN MEADOW DEHY:RIP \n412785\tBLCKHILL/TGP SWAIN ROAD DEHY: RIP 3\n412834\tAPPLACHA/TGP UDP CALKINS DEHY: RIP \n412850\tAPPLACHA/TGP UDP LIBERTY DEHY: RIP \n420216\tVALLEY/TGP TOWANDA PA BRADFORD\n………………………………"]
["X25-547653",null,"2025-09-18","2025-09-19",null,null,null,"MLV 317-2 to MLV 318-2","300","4","Hot Tap for New Meter (Meter: Port Royal PIN: 57162)","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed may be constrained or shut in during the project.","412784\tETC NEPL/TGP ALLEN MEADOW DEHY:RIP \n412785\tBLCKHILL/TGP SWAIN ROAD DEHY: RIP 3\n412834\tAPPLACHA/TGP UDP CALKINS DEHY: RIP \n412850\tAPPLACHA/TGP UDP LIBERTY DEHY: RIP \n420216\tVALLEY/TGP TOWANDA PA BRADFORD",317.2,null,"MLV 317-2 to MLV 318-2:  Hot Tap for New Meter (Meter: Port Royal PIN: 57162)\n--9/18/25 through 9/19/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations. The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n412784\tETC NEPL/TGP ALLEN MEADOW DEHY:RIP \n412785\tBLCKHILL/TGP SWAIN ROAD DEHY: RIP 3\n412834\tAPPLACHA/TGP UDP CALKINS DEHY: RIP \n412850\tAPPLACHA/TGP UDP LIBERTY DEHY: RIP \n420216\tVALLEY/TGP TOWANDA PA BRADFORD\n………………………………"]
["X25-963193","***","2025-08-25","2025-08-29","Completed",null,null,"Sta 319","300","4","Units 2C - Turbine Exchange","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,319.03399999999999,"------","***Sta 319:  Units 2C - Turbine Exchange\n***Completed"]
["X25-783630",null,"2025-09-15","2025-09-30",null,null,null,"MLV 320-2A to MLV 322-2","300","4","Drip Removal 321-2-1","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.","412854 BRDWLK/TGP VALENTINE DEHY: RIP 320P",320.2,null,"MLV 320-2A to MLV 322-2:  Drip Removal 321-2-1\n--9/15/25 through 9/30/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential secondary restrictions at the meter(s) may be at risk.\n412854 BRDWLK/TGP VALENTINE DEHY: RIP 320P\n………………………………"]
["X25-573667",null,"2025-09-29","2025-09-30",null,null,null,"Sta. 323A Lackawaxen","300","4","Annual ESD Testing","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,323,null,"Sta. 323A Lackawaxen:  Annual ESD Testing\n--9/29/25 through 9/30/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-573665",null,"2025-09-29","2025-10-03",null,null,null,"Sta 323","300","4","Unit 1A - Drive Modernization Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,323.00099999999998,null,"Sta 323:  Unit 1A - Drive Modernization Upgrade\n--9/29/25 through 10/3/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-691002",null,"2025-09-15","2025-10-03",null,null,null,"MLV 400-1 to MLV 401-1","400","0","Immediate Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,400.1,null,"MLV 400-1 to MLV 401-1:  Immediate Anomaly Remediation\n--9/15/25 through 10/3/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-237175",null,"2025-10-14","2025-10-14",null,null,null,"MLV 400-1 to MLV 409-1","400","0","Pig Run - Maintenance Cleaning 10/14/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","412733  UES/TGP MYRICK BROOKS\n55152   TGP/KMTEJAS KING RANCH EXCH #2 ROLL\n412400  LOBO/TGP KING RANCH JIM WELLS\n410633\tGCENGY/TGP EL EBANITO DEHY STARR\n410729\tKMTEJAS/TGP ZIM DEHYDRATION STARR\n412088\tETP/TGP MONTE CHRISTO EXCH HIDALGO\n412683\tHESCO CO/TGP RAYMONDVILLE HIDALGO\n420878\tGGUC/TGP RINCON DEHYD STARR\n412458\tETP/TGP GILMORE PLANT RESIDUE HIDAL",400.1,null,"MLV 400-1 to MLV 409-1:  Pig Run - Maintenance Cleaning 10/14/25\n--10/14/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n412733  UES/TGP MYRICK BROOKS\n55152   TGP/KMTEJAS KING RANCH EXCH #2 ROLL\n412400  LOBO/TGP KING RANCH JIM WELLS\n410633\tGCENGY/TGP EL EBANITO DEHY STARR\n410729\tKMTEJAS/TGP ZIM DEHYDRATION STARR\n412088\tETP/TGP MONTE CHRISTO EXCH HIDALGO\n412683\tHESCO CO/TGP RAYMONDVILLE HIDALGO\n420878\tGGUC/TGP RINCON DEHYD STARR\n412458\tETP/TGP GILMORE PLANT RESIDUE HIDAL\n………………………………"]
["X25-237319",null,"2025-10-16","2025-10-16",null,null,null,"MLV 400-2 to MLV 409-2","400","0","Pig Run - Maintenance Cleaning 10/16/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","412733  UES/TGP MYRICK BROOKS\n55152   TGP/KMTEJAS KING RANCH EXCH #2 ROLL\n412400  LOBO/TGP KING RANCH JIM WELLS\n410633\tGCENGY/TGP EL EBANITO DEHY STARR\n410729\tKMTEJAS/TGP ZIM DEHYDRATION STARR\n412088\tETP/TGP MONTE CHRISTO EXCH HIDALGO\n412683\tHESCO CO/TGP RAYMONDVILLE HIDALGO\n420878\tGGUC/TGP RINCON DEHYD STARR\n412458\tETP/TGP GILMORE PLANT RESIDUE HIDAL",400.2,null,"MLV 400-2 to MLV 409-2:  Pig Run - Maintenance Cleaning 10/16/25\n--10/16/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n412733  UES/TGP MYRICK BROOKS\n55152   TGP/KMTEJAS KING RANCH EXCH #2 ROLL\n412400  LOBO/TGP KING RANCH JIM WELLS\n410633\tGCENGY/TGP EL EBANITO DEHY STARR\n410729\tKMTEJAS/TGP ZIM DEHYDRATION STARR\n412088\tETP/TGP MONTE CHRISTO EXCH HIDALGO\n412683\tHESCO CO/TGP RAYMONDVILLE HIDALGO\n420878\tGGUC/TGP RINCON DEHYD STARR\n412458\tETP/TGP GILMORE PLANT RESIDUE HIDAL\n………………………………"]
["X25-1029964",null,"2025-09-15","2025-10-03",null,null,null,"MLV 401-1 to MLV 402-1","400","0","Immediate Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,401.1,null,"MLV 401-1 to MLV 402-1:  Immediate Anomaly Remediation\n--9/15/25 through 10/3/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-691001",null,"2025-09-15","2025-10-03",null,null,null,"MLV 403-1 to MLV 404-1","400","0","Anomaly Remediation","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","412733 UES/TGP MYRICK BROOKS\n412400 LOBO/TGP KING RANCH JIM WELLS",403.1,null,"MLV 403-1 to MLV 404-1:  Anomaly Remediation\n--9/15/25 through 10/3/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n412733 UES/TGP MYRICK BROOKS\n412400 LOBO/TGP KING RANCH JIM WELLS\n………………………………"]
["X25-155750",null,"2025-10-15","2025-10-15",null,null,null,"Sta 405A","300","5","Unit 1A - 8K Solar Turbine Borescope Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,405.00099999999998,null,"Sta 405A:  Unit 1A - 8K Solar Turbine Borescope Inspection\n--10/15/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-155749",null,"2025-10-14","2025-10-14",null,null,null,"Sta 405A","300","5","Unit 1A - Water Wash","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,405.00110000000001,null,"Sta 405A:  Unit 1A - Water Wash\n--10/14/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-690999",null,"2025-08-26","2025-09-12",null,null,null,"MLV 405-1 to MLV 406-1","400","0","Immediate Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,405.1,null,"MLV 405-1 to MLV 406-1:  Immediate Anomaly Remediation\n--8/26/25 through 9/12/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-950059",null,"2025-09-29","2025-10-03",null,null,null,"Sta 409","400","0","Unit 3A - Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,409.00299999999999,null,"Sta 409:  Unit 3A - Engine Inspection\n--9/29/25 through 10/3/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-82098",null,"2025-09-09","2025-09-26",null,null,null,"MLV 409A-101BL to MLV 409A-101B","400","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be constrained or shut in during the project.","410633\tGCENGY/TGP EL EBANITO DEHY STARR\n410729\tKMTEJAS/TGP ZIM DEHYDRATION STARR\n412088\tETP/TGP MONTE CHRISTO EXCH HIDALGO\n412683\tHESCO CO/TGP RAYMONDVILLE HIDALGO\n420878\tGGUC/TGP RINCON DEHYD STARR\n412458\tETP/TGP GILMORE PLANT RESIDUE HIDAL\n410065\tWAGNER/TGP UDP DONNA DEHY HIDALGO\n421067\tCALPINE/TGP HIDA\n412659\tDEWBRE/TGP CIMMARRON HIDALGO\n421017\tGDR/TGP RIO BRAVO HIDALGO\n450261\tCENAGAS/TGP PEMEX CHECK DELIV SOUTH\n450262\tCENAGAS/TGP REC NORTH HIDALGO",409.1,null,"MLV 409A-101BL to MLV 409A-101B:  Anomaly Remediation\n--9/9/25 through 9/26/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n410633\tGCENGY/TGP EL EBANITO DEHY STARR\n410729\tKMTEJAS/TGP ZIM DEHYDRATION STARR\n412088\tETP/TGP MONTE CHRISTO EXCH HIDALGO\n412683\tHESCO CO/TGP RAYMONDVILLE HIDALGO\n420878\tGGUC/TGP RINCON DEHYD STARR\n412458\tETP/TGP GILMORE PLANT RESIDUE HIDAL\n410065\tWAGNER/TGP UDP DONNA DEHY HIDALGO\n421067\tCALPINE/TGP HIDA\n412659\tDEWBRE/TGP CIMMARRON HIDALGO\n421017\tGDR/TGP RIO BRAVO HIDALGO\n450261\tCENAGAS/TGP PEMEX CHECK DELIV SOUTH\n450262\tCENAGAS/TGP REC NORTH HIDALGO\n………………………………"]
["X25-53659",null,"2025-10-14","2025-10-14",null,null,null,"MLV 409A-901 to MLV 409A-902","400","L","Pig Run - Cleaning 10/14/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,409.1,null,"MLV 409A-901 to MLV 409A-902:  Pig Run - Cleaning 10/14/25\n--10/14/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-53665",null,"2025-10-15","2025-10-15",null,null,null,"MLV 409A-901 to MLV 409A-902","400","0","Pig Run - Cleaning 10/15/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,409.11,null,"MLV 409A-901 to MLV 409A-902:  Pig Run - Cleaning 10/15/25\n--10/15/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-53666",null,"2025-10-16","2025-10-16",null,null,null,"MLV 409A-901 to MLV 409A-902","400","0","Pig Run - MFL-A 10/16/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,409.12,null,"MLV 409A-901 to MLV 409A-902:  Pig Run - MFL-A 10/16/25\n--10/16/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-123495",null,"2025-10-29","2025-10-29",null,null,null,"Sta 500-1 to Sta 823 (MLV 507-1)","500","L","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420373 TRNSCO/TGP KINDER LA EXCH (BI 1\n420708 ELIZ NG/TGP GRANT LA SALES ALLEN\n420436 VERNON/TGP PITKIN LA VERNON\n420793 ELIZ NG/TGP J R FRANKS 1 VERNON\n420388 PROVNCAL/TGP PROVENCAL LA NATCHITOC",500.1,null,"Sta 500-1 to Sta 823 (MLV 507-1):  Pig Run - Maintenance\n--10/29/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420373 TRNSCO/TGP KINDER LA EXCH (BI 1\n420708 ELIZ NG/TGP GRANT LA SALES ALLEN\n420436 VERNON/TGP PITKIN LA VERNON\n420793 ELIZ NG/TGP J R FRANKS 1 VERNON\n420388 PROVNCAL/TGP PROVENCAL LA NATCHITOC\n………………………………"]
["X25-950173",null,"2025-09-03","2025-09-10",null,null,null,"MLV 507F-101 to MLV 507F-104","500","L","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,507.1,null,"MLV 507F-101 to MLV 507F-104:  Anomaly Remediation\n--9/3/25 through 9/10/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-123498","***","2025-10-22","2025-10-22","Project Change","2025-09-17","2025-09-17","STA 507F to Sta 823","500","L","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","410671\tTARGA/TGP UDP LOWRY PLANT DEHY CAME\n421049\tTGP/TGP GRAND CHENIER PLANT CAMERON",507.1,"--start_date--end_date--------------model_loc--","***STA 507F to Sta 823:  Maintenance Pig\n--10/22/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n410671\tTARGA/TGP UDP LOWRY PLANT DEHY CAME\n421049\tTGP/TGP GRAND CHENIER PLANT CAMERON\n***\nDate Change, Previously scheduled 9/17/25.\n………………………………"]
["X25-950055","***","2025-08-06","2025-08-31","Completed",null,null,"Sta 523","500","L","Station Upgrade","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,523,"------","***Sta 523:  Station Upgrade\n***Completed"]
["X25-1022086",null,"2025-08-25","2025-09-26",null,null,null,"Sta 530","500","L","Unit 1A - Bearings","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,530.00099999999998,null,"Sta 530:  Unit 1A - Bearings\n--8/25/25 through 9/26/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-691135",null,"2025-06-09","2026-10-31",null,null,null,"Sta 530","500","L","Unit 3A - Crankshaft Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,530.00300000000004,null,"Sta 530:  Unit 3A - Crankshaft Replacement\n--6/9/25 through 10/31/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-1022087",null,"2025-08-25","2025-09-19",null,null,null,"Sta 530","500","L","Unit 4A - Piston","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,530.00400000000002,null,"Sta 530:  Unit 4A - Piston\n--8/25/25 through 9/19/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-691139",null,"2025-06-09","2026-12-31",null,null,null,"Sta 530","500","L","Unit 5A - Top-End Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,530.005,null,"Sta 530:  Unit 5A - Top-End Overhaul\n--6/9/25 through 12/31/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-1030414",null,"2025-08-26","2025-09-26",null,null,null,"Sta 530","500","L","Unit 1B - Bearings","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,530.01700000000005,null,"Sta 530:  Unit 1B - Bearings\n--8/26/25 through 9/26/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-837507",null,"2025-09-22","2025-09-27",null,null,null,"MLV 530-1 TO MLV 531-1","500","L","Anomaly Remedition","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,530.1,null,"MLV 530-1 TO MLV 531-1:  Anomaly Remedition\n--9/22/25 through 9/27/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-352306",null,"2025-03-25","2025-09-12",null,null,null,"Sta 534","500","L","Unit 6A - Piston Liner & Unloader Replacements","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,534.00599999999997,null,"Sta 534:  Unit 6A - Piston Liner & Unloader Replacements\n--3/25/25 through 9/12/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-596569",null,"2025-05-20","2025-09-26",null,null,null,"Sta 534","500","L","Unit 7A - Startup Sequence","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,534.00699999999995,null,"Sta 534:  Unit 7A - Startup Sequence\n--5/20/25 through 9/26/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-503637",null,"2025-10-10","2025-10-20",null,null,null,"MLV 540-1 to MLV 540-1A","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,540.1,null,"MLV 540-1 to MLV 540-1A:  Anomaly Remediation\n--10/10/25 through 10/20/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-826138",null,"2025-10-23","2025-10-31",null,null,null,"MLV 540-2 to MLV 540-2A","500","1","Shallow Pipe Lowering","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,540.20000000000005,null,"MLV 540-2 to MLV 540-2A:  Shallow Pipe Lowering\n--10/23/25 through 10/31/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-503636",null,"2025-10-10","2025-10-20",null,null,null,"MLV 541-1 to MLV 541-1A","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,541.1,null,"MLV 541-1 to MLV 541-1A:  Anomaly Remediation\n--10/10/25 through 10/20/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-1036922","***","2025-08-29","2025-08-29","Completed",null,null,"Sta 542 Dekalb","500","1","2025 Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,542,"------","***Sta 542 Dekalb:  2025 Annual ESD Test\n***Completed"]
["X25-672312",null,"2025-08-11","2025-10-17",null,null,null,"Sta 546","500","1","Unit 1A - Engine and Compressor Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,546.00099999999998,null,"Sta 546:  Unit 1A - Engine and Compressor Overhaul\n--8/11/25 through 10/17/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-672314",null,"2025-09-29","2025-11-07",null,null,null,"Sta 546","500","1","Unit 4A - Engine and Compressor Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,546.00400000000002,null,"Sta 546:  Unit 4A - Engine and Compressor Overhaul\n--9/29/25 through 11/7/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-840628",null,"2025-07-14","2025-09-05",null,null,null,"Sta 546","500","1","Unit 7A - Metal in Oil","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,546.00699999999995,null,"Sta 546:  Unit 7A - Metal in Oil\n--7/14/25 through 9/5/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368175","***","2025-10-23","2025-10-23","Project Change","2025-11-11","2025-11-15","Sta 550 Hamilton","500","1","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,550,"--start_date--end_date--------------model_loc--","***Sta 550 Hamilton:  Annual ESD Test & Maintenance\n--10/23/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 11/11/25 to 11/15/25.\n………………………………"]
["X25-500868",null,"2025-08-25","2025-10-17",null,null,null,"Sta 550","500","1","Unit 2A - Compressor Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,550.00199999999995,null,"Sta 550:  Unit 2A - Compressor Overhaul\n--8/25/25 through 10/17/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-677109",null,"2025-10-13","2025-11-15",null,null,null,"Sta 550","500","1","Unit 3A - Engine Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,550.00300000000004,null,"Sta 550:  Unit 3A - Engine Overhaul\n--10/13/25 through 11/15/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-431275",null,"2025-10-27","2025-11-07",null,null,null,"Sta 550","500","1","Unit 3A - Turbocharger Exchange","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,550.00300000000004,null,"Sta 550:  Unit 3A - Turbocharger Exchange\n--10/27/25 through 11/7/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368176","***","2025-10-23","2025-10-23","Project Change","2025-11-10","2025-11-14","Sta 550","100","1","A building - Replace SLC 500 Remote PLC","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,550.1,"--start_date--end_date--------------model_loc--","***Sta 550:  A building - Replace SLC 500 Remote PLC\n--10/23/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 11/10/25 to 11/14/25.\n………………………………"]
["X25-996864",null,"2026-03-10","2026-03-10",null,null,null,"MLV 550-2 to MLV 546-2","500","1","Pig Runs - Cleaning / Gauge 3/10/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.",null,550.20000000000005,null,"MLV 550-2 to MLV 546-2:  Pig Runs - Cleaning / Gauge 3/10/26\n--3/10/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-996867",null,"2026-03-12","2026-03-12",null,null,null,"MLV 550-2 to MLV 546-2","500","1","Pig Runs - CAL / IMU 3/12/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.",null,550.21,null,"MLV 550-2 to MLV 546-2:  Pig Runs - CAL / IMU 3/12/26\n--3/12/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-996869",null,"2026-03-17","2026-03-17",null,null,null,"MLV 550-2 to MLV 546-2","500","1","Pig Runs - MFL-C 3/17/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.",null,550.22,null,"MLV 550-2 to MLV 546-2:  Pig Runs - MFL-C 3/17/26\n--3/17/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-996871",null,"2026-03-19","2026-03-19",null,null,null,"MLV 550-2 to MLV 546-2","500","1","Pig Runs - EMAT 3/19/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.",null,550.23,null,"MLV 550-2 to MLV 546-2:  Pig Runs - EMAT 3/19/26\n--3/19/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368191",null,"2025-09-08","2025-09-12",null,null,null,"Sta 555 Collinwood","500","1","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,555,null,"Sta 555 Collinwood:  Annual ESD Test & Maintenance\n--9/8/25 through 9/12/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-434134","***","2025-10-06","2025-10-11","Project Change","2025-09-01","2025-09-05","Sta 555","500","1","Unit 1A - Engine Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,555.00099999999998,"--start_date--end_date--------------model_loc--","***Sta 555:  Unit 1A - Engine Maintenance\n--10/6/25 through 10/11/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/1/25 to 9/5/25.\n………………………………"]
["X25-593528","***","2025-08-04","2025-09-05","Completed",null,null,"Sta 555","500","1","Unit 2A - Oil Seal","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,555.00199999999995,"------","***Sta 555:  Unit 2A - Oil Seal\n***Completed"]
["X25-434135","***","2025-10-06","2025-10-11","Project Change","2025-09-01","2025-09-05","Sta 555","500","1","Unit 2A - Engine Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,555.00199999999995,"--start_date--end_date--------------model_loc--","***Sta 555:  Unit 2A - Engine Maintenance\n--10/6/25 through 10/11/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/1/25 to 9/5/25.\n………………………………"]
["X25-434138","***","2025-10-06","2025-10-11","Project Change","2025-09-01","2025-09-05","Sta 555","500","1","Unit 5A - Engine Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,555.005,"--start_date--end_date--------------model_loc--","***Sta 555:  Unit 5A - Engine Maintenance\n--10/6/25 through 10/11/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/1/25 to 9/5/25.\n………………………………"]
["X25-434139","***","2025-10-06","2025-10-11","Project Change","2025-09-01","2025-09-05","Sta 555","500","1","Unit 6A - Engine Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,555.00599999999997,"--start_date--end_date--------------model_loc--","***Sta 555:  Unit 6A - Engine Maintenance\n--10/6/25 through 10/11/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/1/25 to 9/5/25.\n………………………………"]
["X25-599991",null,"2025-09-08","2025-09-12",null,null,null,"Sta 555","500","1","Unit 1B - Vibration System Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,555.01700000000005,null,"Sta 555:  Unit 1B - Vibration System Upgrade\n--9/8/25 through 9/12/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-942586",null,"2025-09-22","2025-09-26",null,null,null,"Sta 555","500","1","Unit 1B - Install New PLC Program","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,555.01700000000005,null,"Sta 555:  Unit 1B - Install New PLC Program\n--9/22/25 through 9/26/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-996855",null,"2026-02-17","2026-02-17",null,null,null,"MLV 555-2 to MLV 559-2","500","1","Pig Runs - Cleaning / Gauge 2/17/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.",null,555.20000000000005,null,"MLV 555-2 to MLV 559-2:  Pig Runs - Cleaning / Gauge 2/17/26\n--2/17/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-996861",null,"2026-02-19","2026-02-19",null,null,null,"MLV 555-2 to MLV 559-2","500","1","Pig Runs - CAL / IMU 2/19/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.",null,555.21,null,"MLV 555-2 to MLV 559-2:  Pig Runs - CAL / IMU 2/19/26\n--2/19/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-996862",null,"2026-02-24","2026-02-24",null,null,null,"MLV 555-2 to MLV 559-2","500","1","Pig Runs - MFL-C 2/24/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.",null,555.22,null,"MLV 555-2 to MLV 559-2:  Pig Runs - MFL-C 2/24/26\n--2/24/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-996863",null,"2026-02-26","2026-02-26",null,null,null,"MLV 555-2 to MLV 559-2","500","1","Pig Runs - EMAT 2/26/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.",null,555.23,null,"MLV 555-2 to MLV 559-2:  Pig Runs - EMAT 2/26/26\n--2/26/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-276724",null,"2025-11-17","2025-11-21",null,null,null,"MLV 560-1 to MLV 563-1","500","1","HDD River Crossing & MLV 561-1 & MLV 562-1 Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,560.1,null,"MLV 560-1 to MLV 563-1:  HDD River Crossing & MLV 561-1 & MLV 562-1 Replacement\n--11/17/25 through 11/21/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-415282",null,"2025-06-09","2025-09-16",null,null,null,"MLV 560-2 to MLV 561-2","500","1","Class Change Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,560.20000000000005,null,"MLV 560-2 to MLV 561-2:  Class Change Pipe Replacement\n--6/9/25 through 9/16/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-946902","***","2025-09-11","2025-09-12","Project Change",null,"2025-09-14","Sta 563","500","1","Unit 1A - Annual Inspection & Safety Device Check","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,563.00099999999998,"----end_date--------------model_loc--","***Sta 563:  Unit 1A - Annual Inspection & Safety Device Check\n--9/11/25 through 9/12/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/11/25 to 9/14/25.\n………………………………"]
["X25-1032042","***","2025-11-19","2025-11-21","Added",null,null,"Sta 563",null,null,"Unit 1A - Lube Oil Varnish Installation","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,563.00099999999998,"------","***Sta 563:  Unit 1A - Lube Oil Varnish Installation\n--11/19/25 through 11/21/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X25-946901",null,"2025-09-08","2025-09-11",null,null,null,"Sta 563","500","1","Unit 2A - Overhaul Inspection & Safety Device Check","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,563.00199999999995,null,"Sta 563:  Unit 2A - Overhaul Inspection & Safety Device Check\n--9/8/25 through 9/11/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-1032039","***","2025-11-17","2025-11-19","Added",null,null,"Sta 563",null,null,"Unit 2A - Lube Oil Varnish Installation","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,563.00199999999995,"------","***Sta 563:  Unit 2A - Lube Oil Varnish Installation\n--11/17/25 through 11/19/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***Added\n………………………………"]
["X24-1178739",null,"2025-12-10","2025-12-10",null,null,null,"MLV 565-1 TO MLV 559-1","500","1","Pig Runs - Cleaning / Gauge 12/10/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,565.1,null,"MLV 565-1 TO MLV 559-1:  Pig Runs - Cleaning / Gauge 12/10/25\n--12/10/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1178795",null,"2025-12-12","2025-12-12",null,null,null,"MLV 565-1 TO MLV 559-1","500","1","Pig Runs - Caliper 12/12/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,565.11,null,"MLV 565-1 TO MLV 559-1:  Pig Runs - Caliper 12/12/25\n--12/12/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1178816",null,"2025-12-15","2025-12-15",null,null,null,"MLV 565-1 TO MLV 559-1","500","1","Pig Runs - AFD 12/15/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,565.12,null,"MLV 565-1 TO MLV 559-1:  Pig Runs - AFD 12/15/25\n--12/15/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1178843",null,"2025-12-19","2025-12-19",null,null,null,"MLV 565-1 TO MLV 559-1","500","1","Pig Runs - EMAT 12/19/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,565.13,null,"MLV 565-1 TO MLV 559-1:  Pig Runs - EMAT 12/19/25\n--12/19/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-86682",null,"2025-12-17","2025-12-17",null,null,null,"MLV 565-1 TO MLV 559-1","500","1","Pig Runs - Residual 12/17/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,565.14,null,"MLV 565-1 TO MLV 559-1:  Pig Runs - Residual 12/17/25\n--12/17/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-157845",null,"2025-09-09","2025-09-09",null,null,null,"MLV 706-1 to MLV 700-1","100","0","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","412819 LOUISMID/TGP CONVERSE CENTRAL: RIP\n410031 ETX GAS/TGP EAST TX PLANT DEHY PANO",706.11,null,"MLV 706-1 to MLV 700-1:  Pig Run - Maintenance\n--9/9/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n412819 LOUISMID/TGP CONVERSE CENTRAL: RIP\n410031 ETX GAS/TGP EAST TX PLANT DEHY PANO\n………………………………"]
["X25-155787",null,"2025-12-02","2025-12-02",null,null,null,"Sta. 820 Starks","800","L","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,820,null,"Sta. 820 Starks:  Annual ESD Test\n--12/2/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-123502","***","2025-10-21","2025-10-21","Project Change","2025-09-16","2025-09-16","STA 823 to STA 507K","500","L","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420493\tCOKINOS/TGP MALLETT FARM LA JEFFERS",823.5,"--start_date--end_date--------------model_loc--","***STA 823 to STA 507K:  Pig Run - Maintenance\n--10/21/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420493\tCOKINOS/TGP MALLETT FARM LA JEFFERS\n***\nDate Change, Previously scheduled 9/16/25.\n………………………………"]
["X25-123490",null,"2025-10-01","2025-10-01",null,null,null,"Sta 823 to MLV 516","500","L","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","412398 JEFFSTOR/TGP JEFFERSON ISLAND IBERI\n420915 CEGS/TGP PORT IBERIA SALES IBERIA\n421056 ACADIAN/TGP INDIAN BAYOU: DIP 510B-\n412594 NAUTILUS/TGP GARDEN CITY ST MARY\n412684 ANR/TGP SHADYSIDE ST MARY",823.51,null,"Sta 823 to MLV 516:  Pig Run - Maintenance\n--10/1/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n412398 JEFFSTOR/TGP JEFFERSON ISLAND IBERI\n420915 CEGS/TGP PORT IBERIA SALES IBERIA\n421056 ACADIAN/TGP INDIAN BAYOU: DIP 510B-\n412594 NAUTILUS/TGP GARDEN CITY ST MARY\n412684 ANR/TGP SHADYSIDE ST MARY\n………………………………"]
["X25-869773",null,"2025-09-09","2025-09-11",null,null,null,"Station 827 (Alexandria)","800","L","Station Recycle Valve","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,827,null,"Station 827 (Alexandria):  Station Recycle Valve\n--9/9/25 through 9/11/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-123506",null,"2025-11-05","2025-11-05",null,null,null,"Sta 827 to Sta 823","800","L","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","421043 PINE PRA/TGP PINE PRAIRIE NORTH RAP\n412847 ACADIAN/TGP CHENEYVILLE RAPIDES\n412713 HUGHES E/TGP UDP BLACK STONE13 EVAN \n412844 TEXLA/TGP ROY MARTIN GATHERING: RIP\n420296 FORSTHIL/TGP FOREST HILL LA RAPIDES\n420530 GLNMORA/TGP GLENMORA LA EXCH RAPIDE\n421042 ELIZ NG/TGP EVANGELINE SALES EVANGE\n420629 ELIZ NG/TGP OAKDALE DETENTION SALES\n420687 ELIZ NG/TGP ALLEN PARISH PRISON SAL\n420406 ELIZ NG/TGP ELIZABETH LA EMERGENCY\n53483 AIRLIQAT/TGP TIMBERLANE BIOGAS REC",827.11,null,"Sta 827 to Sta 823:  Pig Run - Maintenance\n--11/5/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n421043 PINE PRA/TGP PINE PRAIRIE NORTH RAP\n412847 ACADIAN/TGP CHENEYVILLE RAPIDES\n412713 HUGHES E/TGP UDP BLACK STONE13 EVAN \n412844 TEXLA/TGP ROY MARTIN GATHERING: RIP\n420296 FORSTHIL/TGP FOREST HILL LA RAPIDES\n420530 GLNMORA/TGP GLENMORA LA EXCH RAPIDE\n421042 ELIZ NG/TGP EVANGELINE SALES EVANGE\n420629 ELIZ NG/TGP OAKDALE DETENTION SALES\n420687 ELIZ NG/TGP ALLEN PARISH PRISON SAL\n420406 ELIZ NG/TGP ELIZABETH LA EMERGENCY\n53483 AIRLIQAT/TGP TIMBERLANE BIOGAS REC\n………………………………"]
["X25-149204",null,"2025-09-29","2025-09-29",null,null,null,"Sta 834","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,834,null,"Sta 834:  Annual ESD Test\n--9/29/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1186067",null,"2025-03-03","2025-11-03",null,null,null,"Sta 834","800","1","Unit 6A - Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,834.00599999999997,null,"Sta 834:  Unit 6A - Overhaul\n--3/3/25 through 11/3/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-136332",null,"2025-11-05","2025-11-05",null,null,null,"Sta 834 to Sta 827","800","L","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420755 ATMOS TL/TGP LASALLE PARISH NEBO SA\n420447 PELICANG/TGP HARRISONBURG LA CATAHO",834.11,null,"Sta 834 to Sta 827:  Maintenance Pig\n--11/5/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420755 ATMOS TL/TGP LASALLE PARISH NEBO SA\n420447 PELICANG/TGP HARRISONBURG LA CATAHO\n………………………………"]
["X25-1007535",null,"2025-09-03","2025-09-03",null,null,null,"MLV 836B-102L to MLV 836B-101R","800","1","Pig Run - Maintenance 9/3/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","49585 GULFRUN/TGP BEARFOOT RICHLAND\n49587 GULFSTH/TGP LUPE FRANKLIN\n49589 ETC TIG/TGP URSUS FRANKLIN",836.1,null,"MLV 836B-102L to MLV 836B-101R:  Pig Run - Maintenance 9/3/25\n--9/3/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n49585 GULFRUN/TGP BEARFOOT RICHLAND\n49587 GULFSTH/TGP LUPE FRANKLIN\n49589 ETC TIG/TGP URSUS FRANKLIN\n………………………………"]
["X25-25863",null,"2025-09-10","2025-09-10",null,null,null,"Sta 838","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,838,null,"Sta 838:  Annual ESD Test\n--9/10/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-869737",null,"2025-09-15","2025-09-17",null,null,null,"MLV 838-1 TO MLV 834-1","800","1","Pig Runs - Cleaning  9/15 - 9/17","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","412691 REGENCY/TGP PEOPLES ROAD FRANKLIN\n49554 BBTMIDLA/TGP NORTH PEOPLES RD FRANK\n420279 ATMOS TL/TGP CROWVILLE LA FRANKLIN\n49585 GULFRUN/TGP BEARFOOT RICHLAND\n49589 ETC TIG/TGP URSUS FRANKLIN\n49587 GULFSTH/TGP LUPE FRANKLIN\n49583 MEP/TGP PILLAR MADISON\n49643 GULFSTH/TGP SKIPPER MADISON",838.1,null,"MLV 838-1 TO MLV 834-1:  Pig Runs - Cleaning  9/15 - 9/17\n--9/15/25 through 9/17/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n412691 REGENCY/TGP PEOPLES ROAD FRANKLIN\n49554 BBTMIDLA/TGP NORTH PEOPLES RD FRANK\n420279 ATMOS TL/TGP CROWVILLE LA FRANKLIN\n49585 GULFRUN/TGP BEARFOOT RICHLAND\n49589 ETC TIG/TGP URSUS FRANKLIN\n49587 GULFSTH/TGP LUPE FRANKLIN\n49583 MEP/TGP PILLAR MADISON\n49643 GULFSTH/TGP SKIPPER MADISON\n………………………………"]
["X25-869735",null,"2025-09-18","2025-09-18",null,null,null,"MLV 838-1 TO MLV 834-1","800","1","Pig Re-Runs - ROSEN EMAT 9/18","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","412691 REGENCY/TGP PEOPLES ROAD FRANKLIN\n49554 BBTMIDLA/TGP NORTH PEOPLES RD FRANK\n420279 ATMOS TL/TGP CROWVILLE LA FRANKLIN\n49585 GULFRUN/TGP BEARFOOT RICHLAND\n49589 ETC TIG/TGP URSUS FRANKLIN\n49587 GULFSTH/TGP LUPE FRANKLIN\n49583 MEP/TGP PILLAR MADISON\n49643 GULFSTH/TGP SKIPPER MADISON",838.11,null,"MLV 838-1 TO MLV 834-1:  Pig Re-Runs - ROSEN EMAT 9/18\n--9/18/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n412691 REGENCY/TGP PEOPLES ROAD FRANKLIN\n49554 BBTMIDLA/TGP NORTH PEOPLES RD FRANK\n420279 ATMOS TL/TGP CROWVILLE LA FRANKLIN\n49585 GULFRUN/TGP BEARFOOT RICHLAND\n49589 ETC TIG/TGP URSUS FRANKLIN\n49587 GULFSTH/TGP LUPE FRANKLIN\n49583 MEP/TGP PILLAR MADISON\n49643 GULFSTH/TGP SKIPPER MADISON\n………………………………"]
["X24-1368179",null,"2025-10-08","2025-10-08",null,null,null,"Sta 851 New Albany","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,851,null,"Sta 851 New Albany:  Annual ESD Test\n--10/8/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-1368187",null,"2025-11-01","2025-12-31",null,null,null,"Sta 856 Savannah","800","1","Replace Leaking ESD Valves on Turbines","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,856.00009999999997,null,"Sta 856 Savannah:  Replace Leaking ESD Valves on Turbines\n--11/1/25 through 12/31/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-239936",null,"2025-10-16","2025-10-16",null,null,null,"MLV 856-1 to MLV 860-1","800","1","Pig Runs - Cleaning / Gauge 10/16/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,856.1,null,"MLV 856-1 to MLV 860-1:  Pig Runs - Cleaning / Gauge 10/16/25\n--10/16/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-239996",null,"2025-10-21","2025-10-21",null,null,null,"MLV 856-1 to MLV 860-1","800","1","Pig Runs - Cal / IMU 10/21/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,856.11,null,"MLV 856-1 to MLV 860-1:  Pig Runs - Cal / IMU 10/21/25\n--10/21/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-240033",null,"2025-10-23","2025-10-23",null,null,null,"MLV 856-1 to MLV 860-1","800","1","Pig Runs - MFL-C 10/23/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,856.12,null,"MLV 856-1 to MLV 860-1:  Pig Runs - MFL-C 10/23/25\n--10/23/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-996852",null,"2026-02-10","2026-02-10",null,null,null,"MLV 856-1 to MLV 860-1","800","1","Pig Runs - Cleaning / Gauge 2/10/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.",null,856.13,null,"MLV 856-1 to MLV 860-1:  Pig Runs - Cleaning / Gauge 2/10/26\n--2/10/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-996854",null,"2026-02-12","2026-02-12",null,null,null,"MLV 856-1 to MLV 860-1","800","1","Pig Runs - EMAT 2/12/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.",null,856.14,null,"MLV 856-1 to MLV 860-1:  Pig Runs - EMAT 2/12/26\n--2/12/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential out of path restrictions may be at risk.\n………………………………"]
["X24-640564",null,"2024-06-17","2025-12-31",null,null,null,"Sta 860","800","1","Unit 1A - Aftercooler Jacket Water Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,860.00099999999998,null,"Sta 860:  Unit 1A - Aftercooler Jacket Water Inspection\n--6/17/24 through 12/31/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-450065",null,"2025-09-24","2025-10-04",null,null,null,"MLV 861-1 to MLV 862-1","800","1","Install New 30\" Valve 861-1A","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,861.1,null,"MLV 861-1 to MLV 862-1:  Install New 30\" Valve 861-1A\n--9/24/25 through 10/4/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-947012",null,"2025-09-20","2025-10-25",null,null,null,"MLV 867-2 to MLV 868-2","800","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,867.2,null,"MLV 867-2 to MLV 868-2:  Anomaly Remediation\n--9/20/25 through 10/25/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-947011",null,"2025-09-15","2025-09-20",null,null,null,"MLV 868-2 to MLV 869-2","800","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,868.2,null,"MLV 868-2 to MLV 869-2:  Anomaly Remediation\n--9/15/25 through 9/20/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-200019",null,"2025-08-22","2025-09-04",null,null,null,"MLV 869-1 to MLV 870-1","800","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,869.1,null,"MLV 869-1 to MLV 870-1:  Anomaly Remediation\n--8/22/25 through 9/4/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-947010",null,"2025-09-09","2025-09-14",null,null,null,"MLV 870-2 to MLV 870-2R","800","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,870.2,null,"MLV 870-2 to MLV 870-2R:  Anomaly Remediation\n--9/9/25 through 9/14/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-799693","***","2025-12-31","2025-12-31","Project Change","2025-09-09","2025-09-09","Sta 871","800","2","Unit 1A - 3Q Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,871.00099999999998,"--start_date--end_date--------------model_loc--","***Sta 871:  Unit 1A - 3Q Engine Inspection\n--12/31/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/9/25.\n………………………………"]
["X25-799692","***","2025-12-31","2025-12-31","Project Change","2025-09-10","2025-09-10","Sta 871","800","2","Unit 2A - 3Q Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,871.00199999999995,"--start_date--end_date--------------model_loc--","***Sta 871:  Unit 2A - 3Q Engine Inspection\n--12/31/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/10/25.\n………………………………"]
["X25-1022170",null,"2025-08-22","2025-09-19",null,null,null,"Sta 871","800","2","Unit 3A - Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,871.00300000000004,null,"Sta 871:  Unit 3A - Engine Inspection\n--8/22/25 through 9/19/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-200023",null,"2025-10-26","2025-11-26",null,null,null,"MLV 871-2A to MLV 872-2","800","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,871.2,null,"MLV 871-2A to MLV 872-2:  Anomaly Remediation\n--10/26/25 through 11/26/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-200026",null,"2025-10-26","2025-11-26",null,null,null,"MLV 871-2L to MLV 871-2A","800","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,871.2,null,"MLV 871-2L to MLV 871-2A:  Anomaly Remediation\n--10/26/25 through 11/26/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X24-1368203",null,"2025-09-18","2025-09-18",null,null,null,"Sta 871A Campbellsville","800","2","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,871.5,null,"Sta 871A Campbellsville:  Annual ESD Test\n--9/18/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-200024",null,"2025-10-26","2025-11-26",null,null,null,"MLV 872-2 to MLV 873-2","800","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,872.2,null,"MLV 872-2 to MLV 873-2:  Anomaly Remediation\n--10/26/25 through 11/26/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-200025",null,"2025-10-26","2025-11-26",null,null,null,"MLV 873-2 to MLV 873-2A","800","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,873.2,null,"MLV 873-2 to MLV 873-2A:  Anomaly Remediation\n--10/26/25 through 11/26/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-200020",null,"2025-09-02","2025-09-06",null,null,null,"MLV 874-2 to MLV 874-2B","800","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,874.2,null,"MLV 874-2 to MLV 874-2B:  Anomaly Remediation\n--9/2/25 through 9/6/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-902943",null,"2025-09-09","2025-09-11",null,null,null,"Sta 875","800","2","Unit 1A - 4K/8K Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,875.00099999999998,null,"Sta 875:  Unit 1A - 4K/8K Inspection\n--9/9/25 through 9/11/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]

{"sheet":"Sheet2","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}

{"sheet":"Sheet3","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}