{"text_format":"1","workbook":"xlsx","n_sheets":4,"sheets":["Closed","Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":8,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Closed","index":0,"n_rows":37,"n_cols":22,"rows_kept":37,"cut":false,"hidden":true,"merged":[[1,3,1,15],[2,3,2,15],[3,3,3,15]]}
[null,null,null,"Updated ","2016"]
[null,null,null,"Tennessee Gas Pipeline 2015 Pipeline Outage and Maintenance Summary"]
[null,null,null,"This is a summary of the current status of all TGP Winter 2014-2015 Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  Additionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
[null,null,null,"*** Indicates revision"]
["Date Change","Project New/Completed/Closed","Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","Location","Leg","Zone","Maintenance Activity","Anticipated Impact","Potential Restriction Level","TOS Potential Restrictions","Meter(s) in Impacted Area","Customer Notifications","Loc","Email Text","Posting Text","Completion Text"]
[{"$f":"IF(AND(H6<>\"\",I6<>\"\"), \"Date change. Previously scheduled \" & TEXT(H6,\"m/d/y;@\") &IF(H6=I6,\"\",\" to \" & TEXT(I6,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed",null,{"$f":"IF(G6<>\"\",\"***\",\"\")","v":"***"},"2015-01-11","2016-01-11",{"$f":"IF(AND(A6=\"\",B6=\"\"),\"\",IF(B6=\"\",A6,B6))","v":"Project Completed"},null,null,"MS #412494 DCP Warren","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412494 DCP Warren",401,{"$f":"\"(\"&C6&\") \"&J6&\":  \"&M6&IF(AND(E6=\"\",F6=\"\"),\"\",\" (\")&IF(E6=\"\",\"\",\"\"&TEXT(E6,\"m/d/y;@\"))&IF(OR(F6=E6,E6=\"\",F6=\"\"),\"\",\" to \")&IF(OR(F6=\"\",F6=E6),\"\",TEXT(F6,\"m/d/y;@\"))&IF(AND(E6=\"\",F6=\"\"),\"\",\")\")","v":"() MS #412494 DCP Warren:  Meter Station (1/11/15 to 1/11/16)"},{"$f":"D6&J6&\":  \"&M6&IF(AND(E6=\"\",F6=\"\"),\"\",\"\n\")&IF(E6=\"\",\"\",\"--\"&TEXT(E6,\"m/d/y;@\"))&IF(OR(F6=E6,E6=\"\",F6=\"\"),\"\",\" through \")&IF(OR(F6=\"\",F6=E6),\"\",TEXT(F6,\"m/d/y;@\"))&IF(AND(E6=\"\",F6=\"\"),\"\",\":  \")&N6&\"  \"&P6&IF(Q6=\"\",\"\",\"\n\"&Q6)&IF(G6=\"\",\"\",\"\n***\")&G6&\"\n………………………………\"","v":"***MS #412494 DCP Warren:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412494 DCP Warren\n***Project Completed\n………………………………"},{"$f":"D6&J6&\":  \"&M6&IF(G6=\"\",\"\",\"\n***\")&G6&IF(Q6=\"\",\"\",\"\nThe following meters are available for nominations:\n\")&Q6&\"\n………………………………\"","v":"***MS #412494 DCP Warren:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412494 DCP Warren\n………………………………"}]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412400 King Ranch","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412400 King Ranch",402.1,"() MS #412400 King Ranch:  Meter Station (1/11/15 to 1/11/16)","***MS #412400 King Ranch:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412400 King Ranch\n***Project Completed\n………………………………","***MS #412400 King Ranch:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412400 King Ranch\n………………………………"]
["","Project Completed",null,"***","2015-01-12","2016-01-12","Project Completed",null,null,"MS #410539 Duvak Gas Gathering","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410539 Duvak Gas Gathering",402.1,"() MS #410539 Duvak Gas Gathering:  Meter Station (1/12/15 to 1/12/16)","***MS #410539 Duvak Gas Gathering:  Meter Station\n--1/12/15 through 1/12/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410539 Duvak Gas Gathering\n***Project Completed\n………………………………","***MS #410539 Duvak Gas Gathering:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n410539 Duvak Gas Gathering\n………………………………"]
["","Project Completed",null,"***","2015-01-13","2016-01-13","Project Completed",null,null,"MS #412356 DCP LaGloria","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412356 DCP LaGloria",403.1,"() MS #412356 DCP LaGloria:  Meter Station (1/13/15 to 1/13/16)","***MS #412356 DCP LaGloria:  Meter Station\n--1/13/15 through 1/13/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412356 DCP LaGloria\n***Project Completed\n………………………………","***MS #412356 DCP LaGloria:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412356 DCP LaGloria\n………………………………"]
["","Project Completed",null,"***","2015-01-13","2016-01-13","Project Completed",null,null,"MS #410173 Enterprise LaReforma","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410173 Enterprise LaReforma",406.1,"() MS #410173 Enterprise LaReforma:  Meter Station (1/13/15 to 1/13/16)","***MS #410173 Enterprise LaReforma:  Meter Station\n--1/13/15 through 1/13/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410173 Enterprise LaReforma\n***Project Completed\n………………………………","***MS #410173 Enterprise LaReforma:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n410173 Enterprise LaReforma\n………………………………"]
["","Project Completed",null,"***","2015-01-12","2016-01-12","Project Completed",null,null,"MS #411903 Enterprise El Benito","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","411903 Enterprise El Benito",407.1,"() MS #411903 Enterprise El Benito:  Meter Station (1/12/15 to 1/12/16)","***MS #411903 Enterprise El Benito:  Meter Station\n--1/12/15 through 1/12/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n411903 Enterprise El Benito\n***Project Completed\n………………………………","***MS #411903 Enterprise El Benito:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n411903 Enterprise El Benito\n………………………………"]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412088 Enterprise Sullivan","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412088 Enterprise Sullivan",407.1,"() MS #412088 Enterprise Sullivan:  Meter Station (1/11/15 to 1/11/16)","***MS #412088 Enterprise Sullivan:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412088 Enterprise Sullivan\n***Project Completed\n………………………………","***MS #412088 Enterprise Sullivan:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412088 Enterprise Sullivan\n………………………………"]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412683 HESCO","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412683 HESCO",408.1,"() MS #412683 HESCO:  Meter Station (1/11/15 to 1/11/16)","***MS #412683 HESCO:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412683 HESCO\n***Project Completed\n………………………………","***MS #412683 HESCO:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412683 HESCO\n………………………………"]
[{"$f":"IF(AND(H14<>\"\",I14<>\"\"), \"Date change. Previously scheduled \" & TEXT(H14,\"m/d/y;@\") &IF(H14=I14,\"\",\" to \" & TEXT(I14,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X16-36843",{"$f":"IF(G14<>\"\",\"***\",\"\")","v":"***"},"2016-01-27","2016-01-27","Project Completed",null,null,"Sta. 237",200,5,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,237,"(X16-36843) Sta. 237:  Unit  Maintenance (1/27/16)","***Sta. 237:  Unit  Maintenance\n--1/27/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Sta. 237:  Unit  Maintenance\n***Project Completed\n………………………………"]
[{"$f":"IF(AND(H15<>\"\",I15<>\"\"), \"Date change. Previously scheduled \" & TEXT(H15,\"m/d/y;@\") &IF(H15=I15,\"\",\" to \" & TEXT(I15,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X14-1478563",{"$f":"IF(G15<>\"\",\"***\",\"\")","v":"***"},"2015-11-16","2016-02-12","Project Completed",null,null,"MLV 32-1D to 33-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,32.200000000000003,"(X14-1478563) MLV 32-1D to 33-1:  Hydrotest (11/16/15 to 2/12/16)","***MLV 32-1D to 33-1:  Hydrotest\n--11/16/15 through 2/12/16:  This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***MLV 32-1D to 33-1:  Hydrotest\n***Project Completed\n………………………………"]
[null,"Project Completed","X16-16074",null,"2016-01-18","2016-01-28","Project Completed",null,null,"Station 550","500","1","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,550,"(X16-16074) Station 550:  Station Maintenance (1/18/16 to 1/28/16)","Station 550:  Station Maintenance\n--1/18/16 through 1/28/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","Station 550:  Station Maintenance\n***Project Completed\n………………………………"]
[{"$f":"IF(AND(H17<>\"\",I17<>\"\"), \"Date change. Previously scheduled \" & TEXT(H17,\"m/d/y;@\") &IF(H17=I17,\"\",\" to \" & TEXT(I17,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X16-46202",{"$f":"IF(G17<>\"\",\"***\",\"\")","v":"***"},"2016-02-01","2016-02-07","Project Completed",null,null,"Station 9","100","0","Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.",null,9,"(X16-46202) Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items) (2/1/16 to 2/7/16)","***Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)\n--2/1/16 through 2/7/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\n***Project Completed\n………………………………","***Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)\n***Project Completed\n………………………………"]
["","Project Completed","X15-925633","***","2016-02-09","2016-02-11","Project Completed",null,null,"Sta. 266A",200,6,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,266,"(X15-925633) Sta. 266A:  Unit  Maintenance (2/9/16 to 2/11/16)","***Sta. 266A:  Unit  Maintenance\n--2/9/16 through 2/11/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Sta. 266A:  Unit  Maintenance\n***Project Completed\n………………………………"]
["","Project Completed","X15-929733","***","2016-01-27","2016-02-10","Project Completed",null,null,"MLV 834-1 to 838-1",800,5,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",834.1,"(X15-929733) MLV 834-1 to 838-1:  ILI/Cleaning Pig (1/27/16 to 2/10/16)","***MLV 834-1 to 838-1:  ILI/Cleaning Pig\n--1/27/16 through 2/10/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 834-1 to 838-1:  ILI/Cleaning Pig\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X14-1562506","***","2015-11-02","2016-02-19","Project Completed",null,null,"MLV 5-1 to 6-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410063 ROCHE DEHYDRATION             \n",5.0999999999999996,"(X14-1562506) MLV 5-1 to 6-1:  Hydrotest (11/2/15 to 2/19/16)","***MLV 5-1 to 6-1:  Hydrotest\n--11/2/15 through 2/19/16:  This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410063 ROCHE DEHYDRATION             \n\n***Project Completed\n………………………………","***MLV 5-1 to 6-1:  Hydrotest\n***Project Completed\nThe following meters are available for nominations:\n410063 ROCHE DEHYDRATION             \n\n………………………………"]
["","Project Completed","X14-1562506","***","2015-11-02","2016-02-19","Project Completed",null,null,"MLV 7-1 to 9-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","\n412490 Charro\n421083 Eagle Ford Field Service",5.0999999999999996,"(X14-1562506) MLV 7-1 to 9-1:  Hydrotest (11/2/15 to 2/19/16)","***MLV 7-1 to 9-1:  Hydrotest\n--11/2/15 through 2/19/16:  This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n\n412490 Charro\n421083 Eagle Ford Field Service\n***Project Completed\n………………………………","***MLV 7-1 to 9-1:  Hydrotest\n***Project Completed\nThe following meters are available for nominations:\n\n412490 Charro\n421083 Eagle Ford Field Service\n………………………………"]
["Date change. Previously scheduled 2/18/16 to 2/20/16.","Project Completed","X15-882289","***","2016-02-22","2016-02-24","Project Completed","2016-02-18","2016-02-20","MLV 24-2 to 25-2S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.2,"(X15-882289) MLV 24-2 to 25-2S:  Anomaly Remediation (2/22/16 to 2/24/16)","***MLV 24-2 to 25-2S:  Anomaly Remediation\n--2/22/16 through 2/24/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 24-2 to 25-2S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-925630","***","2016-02-23","2016-02-23","Project Completed",null,null,"WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B)",200,"L","ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,265.10000000000002,"(X15-925630) WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig (2/23/16)","***WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig\n--2/23/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig\n***Project Completed\n………………………………"]
["","Project Completed","X16-23748","***","2016-02-15","2016-02-18","Project Completed",null,null,"MLV 530-3 to 532-3",500,"L","ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,530.29999999999995,"(X16-23748) MLV 530-3 to 532-3:  ILI/Cleaning Pig (2/15/16 to 2/18/16)","***MLV 530-3 to 532-3:  ILI/Cleaning Pig\n--2/15/16 through 2/18/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***MLV 530-3 to 532-3:  ILI/Cleaning Pig\n***Project Completed\n………………………………"]
["","Project Canceled","X16-98720","***","2016-03-06","2016-03-06","Project Canceled",null,null,"Sta. 1",100,0,"Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,1,"(X16-98720) Sta. 1:  Station Maintenance (3/6/16)","***Sta. 1:  Station Maintenance\n--3/6/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Canceled\n………………………………","***Sta. 1:  Station Maintenance\n***Project Canceled\n………………………………"]
["","Project Completed","X14-1562513\nX14-1540661","***","2015-07-01","2016-03-04","Project Completed",null,null,"Station 32","100","0","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,32,"(X14-1562513\nX14-1540661) Station 32:  Station Maintenance (7/1/15 to 3/4/16)","***Station 32:  Station Maintenance\n--7/1/15 through 3/4/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Station 32:  Station Maintenance\n***Project Completed\n………………………………"]
["","Project Canceled","X15-926822","***","2016-06-06","2016-06-11","Project Canceled",null,null,"BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1)",300,6,"Pipe Inspection","This project involves inspecting multiple sites.  We do not anticipate having to do any repairs, however if a repair is needed  there is a potential that the pipe  may require replacement which will require isolation of the pipe.  This may limit throughput and will result in restrictions based on customer nominations.  Customers may experience pressure fluctuations during this timeframe.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",343.1,"(X15-926822) BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection (6/6/16 to 6/11/16)","***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection\n--6/6/16 through 6/11/16:  This project involves inspecting multiple sites.  We do not anticipate having to do any repairs, however if a repair is needed  there is a potential that the pipe  may require replacement which will require isolation of the pipe.  This may limit throughput and will result in restrictions based on customer nominations.  Customers may experience pressure fluctuations during this timeframe.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928271","***","TBD","TBD","Project Canceled",null,null,"MLV 555-1 to 550-1",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.1,"(X15-928271) MLV 555-1 to 550-1:  ILI/Cleaning Pig (TBD)","***MLV 555-1 to 550-1:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-1 to 550-1:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928272","***","TBD","TBD","Project Canceled",null,null,"MLV 555-2 to 550-2",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.20000000000005,"(X15-928272) MLV 555-2 to 550-2:  ILI/Cleaning Pig (TBD)","***MLV 555-2 to 550-2:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-2 to 550-2:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928273","***","TBD","TBD","Project Canceled",null,null,"MLV 555-3 to 552-3",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.29999999999995,"(X15-928273) MLV 555-3 to 552-3:  ILI/Cleaning Pig (TBD)","***MLV 555-3 to 552-3:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-3 to 552-3:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-882281","***","2016-02-24","2016-03-03","Project Completed",null,null,"24-1A to 25-1S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.1,"(X15-882281) 24-1A to 25-1S:  Anomaly Remediation (2/24/16 to 3/3/16)","***24-1A to 25-1S:  Anomaly Remediation\n--2/24/16 through 3/3/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***24-1A to 25-1S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-882291","***","2016-03-03","2016-03-04","Project Completed",null,null,"MLV 24-3 to 25-3S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.3,"(X15-882291) MLV 24-3 to 25-3S:  Anomaly Remediation (3/3/16 to 3/4/16)","***MLV 24-3 to 25-3S:  Anomaly Remediation\n--3/3/16 through 3/4/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 24-3 to 25-3S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X14-1178175","***","2015-06-15","2016-03-31","Project Completed",null,null,"Station 63","100","1","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,63,"(X14-1178175) Station 63:  Station Maintenance (6/15/15 to 3/31/16)","***Station 63:  Station Maintenance\n--6/15/15 through 3/31/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Station 63:  Station Maintenance\n***Project Completed\n………………………………"]
["","Project Cancelled","X15-913224","***","2016-04-16","2016-05-21","Project Cancelled",null,null,"MLV 109-2",100,2,"Pipe Replacement","This project will require taking the pipeline section out of service.   This will limit throughput and will result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",109.2,"(X15-913224) MLV 109-2:  Pipe Replacement (4/16/16 to 5/21/16)","***MLV 109-2:  Pipe Replacement\n--4/16/16 through 5/21/16:  This project will require taking the pipeline section out of service.   This will limit throughput and will result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Cancelled\n………………………………","***MLV 109-2:  Pipe Replacement\n***Project Cancelled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-926830","***","2016-03-07","2016-03-11","Project Completed",null,null,"MLV 400-1 to 408-1",100,0,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.","To Be Determined",400.1,"(X15-926830) MLV 400-1 to 408-1:  ILI/Cleaning Pig (3/7/16 to 3/11/16)","***MLV 400-1 to 408-1:  ILI/Cleaning Pig\n--3/7/16 through 3/11/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 400-1 to 408-1:  ILI/Cleaning Pig\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Cancelled","X16-143836","***","2016-03-28","2016-04-04","Project Cancelled",null,null,"Sta. 409",100,0,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.",null,409,"(X16-143836) Sta. 409:  Unit  Maintenance (3/28/16 to 4/4/16)","***Sta. 409:  Unit  Maintenance\n--3/28/16 through 4/4/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\n***Project Cancelled\n………………………………","***Sta. 409:  Unit  Maintenance\n***Project Cancelled\n………………………………"]
["","Project Cancelled","X15-929680","***","2016-04-18","2016-04-27","Project Cancelled",null,null,"SABINE - KINDER LINE to 822-1",800,"L","Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",822.1,"(X15-929680) SABINE - KINDER LINE to 822-1:  Anomaly Remediation (4/18/16 to 4/27/16)","***SABINE - KINDER LINE to 822-1:  Anomaly Remediation\n--4/18/16 through 4/27/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Cancelled\n………………………………","***SABINE - KINDER LINE to 822-1:  Anomaly Remediation\n***Project Cancelled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]

{"sheet":"Sheet1","index":1,"n_rows":366,"n_cols":22,"rows_kept":366,"cut":false,"hidden":false,"merged":[[2,0,2,12]]}
["Updated ","2025-12-18"]
["Tennessee Gas Pipeline 2025 Pipeline Outage and Maintenance Summary"]
["This is a summary of the current status of TGP Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  \nAdditionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
["*** Indicates revision"]
["Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","Location","Leg","Zone","Maintenance Activity","Anticipated Impact","Meter(s) in Impacted Area","Loc",null,null,null,null,null,null,null,"\\\\houCORP\\TRANS\\TRANSERVICES\\OPPLAN\\COMMON\\Outages\\Outage_DB\\TGP\\Files"]
["X25-1259255",null,"2025-10-10","2026-12-31",null,null,null,"Sta 1","100","0","Unit 6A - Engine Overhaul and Regrout","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,1.006,null,"Sta 1:  Unit 6A - Engine Overhaul and Regrout\n--10/10/25 through 12/31/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1480079","***","2026-01-06","2026-01-06","Project Change",null,null,"MLV 1-1D to MLV 9-1S","100","0","Pig Run - Gauge/Cleaning","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","421083 - ENLINK/TGP PORT OF VICTORIA: DIP 8H",1.1000000000000001,"------meters_affected------------model_loc--","***MLV 1-1D to MLV 9-1S:  Pig Run - Gauge/Cleaning\n--1/6/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n421083 - ENLINK/TGP PORT OF VICTORIA: DIP 8H\n***Project Change\n………………………………"]
["X25-1480080","***","2026-01-07","2026-01-07","Project Change",null,null,"MLV 1-1D to MLV 9-1S","100","0","Pig Run - Gauge/Cleaning","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","421083 - ENLINK/TGP PORT OF VICTORIA: DIP 8H",1.1000000000000001,"------meters_affected------------model_loc--","***MLV 1-1D to MLV 9-1S:  Pig Run - Gauge/Cleaning\n--1/7/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n421083 - ENLINK/TGP PORT OF VICTORIA: DIP 8H\n***Project Change\n………………………………"]
["X25-1480081","***","2026-01-08","2026-01-08","Project Change",null,null,"MLV 1-1D to MLV 9-1S","100","0","Pig Run - Gauge/Cleaning","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","421083 - ENLINK/TGP PORT OF VICTORIA: DIP 8H",1.1000000000000001,"------meters_affected------------model_loc--","***MLV 1-1D to MLV 9-1S:  Pig Run - Gauge/Cleaning\n--1/8/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n421083 - ENLINK/TGP PORT OF VICTORIA: DIP 8H\n***Project Change\n………………………………"]
["X25-1480082","***","2026-01-09","2026-01-09","Project Change",null,null,"MLV 1-1D to MLV 9-1S","100","0","Pig Run - Gauge/Cleaning","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","421083 - ENLINK/TGP PORT OF VICTORIA: DIP 8H",1.1000000000000001,"------meters_affected------------model_loc--","***MLV 1-1D to MLV 9-1S:  Pig Run - Gauge/Cleaning\n--1/9/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n421083 - ENLINK/TGP PORT OF VICTORIA: DIP 8H\n***Project Change\n………………………………"]
["X25-1480083","***","2026-01-10","2026-01-10","Project Change",null,null,"MLV 1-1D to MLV 9-1S",null,null,"Pig Run - Gauge/Cleaning","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","421083 - ENLINK/TGP PORT OF VICTORIA: DIP 8H",1.1000000000000001,"------meters_affected------------model_loc--","***MLV 1-1D to MLV 9-1S:  Pig Run - Gauge/Cleaning\n--1/10/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n421083 - ENLINK/TGP PORT OF VICTORIA: DIP 8H\n***Project Change\n………………………………"]
["X25-1480084","***","2026-01-13","2026-01-13","Project Change",null,null,"MLV 1-1D to MLV 9-1S","100","0","Pig Run - CLP/MFL/IMU","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","421083 - ENLINK/TGP PORT OF VICTORIA: DIP 8H",1.1000000000000001,"------meters_affected------------model_loc--","***MLV 1-1D to MLV 9-1S:  Pig Run - CLP/MFL/IMU\n--1/13/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n421083 - ENLINK/TGP PORT OF VICTORIA: DIP 8H\n***Project Change\n………………………………"]
["X25-1480085","***","2026-01-15","2026-01-15","Project Change",null,null,"MLV 1-1D to MLV 9-1S","100","0","Pig Run - TDW MDS","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","421083 - ENLINK/TGP PORT OF VICTORIA: DIP 8H",1.1000000000000001,"------meters_affected------------model_loc--","***MLV 1-1D to MLV 9-1S:  Pig Run - TDW MDS\n--1/15/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n421083 - ENLINK/TGP PORT OF VICTORIA: DIP 8H\n***Project Change\n………………………………"]
["X25-1480087","***","2026-01-20","2026-01-20","Project Change",null,null,"MLV 1-1D to MLV 9-1S","100","0","Pig Run - EMAT","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","421083 - ENLINK/TGP PORT OF VICTORIA: DIP 8H",1.1000000000000001,"------meters_affected------------model_loc--","***MLV 1-1D to MLV 9-1S:  Pig Run - EMAT\n--1/20/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n421083 - ENLINK/TGP PORT OF VICTORIA: DIP 8H\n***Project Change\n………………………………"]
["X25-1480091","***","2026-01-22","2026-01-22","Project Change",null,null,"MLV 1-1D to MLV 9-1S","100","0","Pig Run - EMAT","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.","421083 - ENLINK/TGP PORT OF VICTORIA: DIP 8H",1.1000000000000001,"------meters_affected------------model_loc--","***MLV 1-1D to MLV 9-1S:  Pig Run - EMAT\n--1/22/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n421083 - ENLINK/TGP PORT OF VICTORIA: DIP 8H\n***Project Change\n………………………………"]
["X25-1389520",null,"2026-09-14","2026-10-02",null,null,null,"MLV 1-2D to MLV 5-2","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,1.2,null,"MLV 1-2D to MLV 5-2:  Anomaly Remediation\n--9/14/26 through 10/2/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1389555",null,"2026-05-11","2026-06-19",null,null,null,"MLV 5-2 to MLV 9-2S","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,5.2,null,"MLV 5-2 to MLV 9-2S:  Anomaly Remediation\n--5/11/26 through 6/19/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1354994",null,"2026-06-01","2026-09-01",null,null,null,"MLV 8-1 TO MLV 10-1","100","0","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,8.1,null,"MLV 8-1 TO MLV 10-1:  Pipe Replacement\n--6/1/26 through 9/1/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1389521",null,"2026-07-27","2026-08-14",null,null,null,"MLV 9-1D to MLV 17-1S","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,9.1,null,"MLV 9-1D to MLV 17-1S:  Anomaly Remediation\n--7/27/26 through 8/14/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1389553",null,"2026-04-20","2026-05-01",null,null,null,"MLV 17-2D to MLV 20-2A","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,17.2,null,"MLV 17-2D to MLV 20-2A:  Anomaly Remediation\n--4/20/26 through 5/1/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1354988",null,"2026-03-16","2026-05-15",null,null,null,"MLV 19-1 TO MLV 20-1A","100","0","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,19.100000000000001,null,"MLV 19-1 TO MLV 20-1A:  Pipe Replacement\n--3/16/26 through 5/15/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1354990",null,"2026-05-16","2026-07-15",null,null,null,"MLV 19-2 TO MLV 20-2A","100","0","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,19.2,null,"MLV 19-2 TO MLV 20-2A:  Pipe Replacement\n--5/16/26 through 7/15/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1354992",null,"2026-07-16","2026-09-15",null,null,null,"MLV 19-3 TO MLV 20-3A","100","0","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,19.3,null,"MLV 19-3 TO MLV 20-3A:  Pipe Replacement\n--7/16/26 through 9/15/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-942604",null,"2025-07-16","2026-10-31",null,null,null,"Sta 25","100","0","Unit 1C - VFD Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,25.033000000000001,null,"Sta 25:  Unit 1C - VFD Replacement\n--7/16/25 through 10/31/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1389522",null,"2026-04-06","2026-04-17",null,null,null,"MLV 25-2D to MLV 32-2S","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,25.2,null,"MLV 25-2D to MLV 32-2S:  Anomaly Remediation\n--4/6/26 through 4/17/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X22-621358",null,"2026-02-20","2026-03-14",null,null,null,"MLV 26-1 Relocation","100","0","Highway 59 Widening","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,26.1,null,"MLV 26-1 Relocation:  Highway 59 Widening\n--2/20/26 through 3/14/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X24-1148994",null,"2026-02-20","2026-03-14",null,null,null,"MLV 26-1 to MLV 27-1","100","0","Install Road Casing","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,26.1,null,"MLV 26-1 to MLV 27-1:  Install Road Casing\n--2/20/26 through 3/14/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X22-815863",null,"2026-03-14","2026-04-06",null,null,null,"MLV 26-2 Relocation","100","0","Highway 59 Widening","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,26.2,null,"MLV 26-2 Relocation:  Highway 59 Widening\n--3/14/26 through 4/6/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X22-815864",null,"2026-04-06","2026-04-28",null,null,null,"MLV 26-3 Relocation","100","0","Highway 59 Widening","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","400448 CICO/TGP MERCY GU 1 LIBERTY",26.3,null,"MLV 26-3 Relocation:  Highway 59 Widening\n--4/6/26 through 4/28/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  \n400448 CICO/TGP MERCY GU 1 LIBERTY\n………………………………"]
["X25-1466180","***","2025-11-24","2026-01-05","Project Change",null,"2025-12-15","Sta 32","100","0","Unit 7B - Compressor Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,32.023000000000003,"----end_date--------------model_loc--","***Sta 32:  Unit 7B - Compressor Overhaul\n--11/24/25 through 1/5/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***\nDate Change, Previously scheduled 11/24/25 to 12/15/25.\n………………………………"]
["X25-1389357",null,"2026-03-16","2026-03-20",null,null,null,"MLV 32-1D to MLV 36-1TXR","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,32.1,null,"MLV 32-1D to MLV 36-1TXR:  Anomaly Remediation\n--3/16/26 through 3/20/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1389542",null,"2026-03-16","2026-03-20",null,null,null,"MLV 32-1D to MLV 36-1TXR","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,32.1,null,"MLV 32-1D to MLV 36-1TXR:  Anomaly Remediation\n--3/16/26 through 3/20/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1389356","***","2026-04-27","2026-05-15","Project Change",null,null,"MLV 32-2D to MLV 40-2S","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,32.200000000000003,"--------------prl----model_loc--","***MLV 32-2D to MLV 40-2S:  Anomaly Remediation\n--4/27/26 through 5/15/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n***Project Change\n………………………………"]
["X25-157840","***","2025-12-10","2025-12-10","Completed",null,null,"MLV 32-3D to MLV 40-3S","100","0","Pig Runs - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,32.299999999999997,"------","***MLV 32-3D to MLV 40-3S:  Pig Runs - Maintenance\n***Completed"]
["X25-1389528",null,"2026-03-30","2026-04-17",null,null,null,"MLV 40-1D to MLV 47-1S","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,40.1,null,"MLV 40-1D to MLV 47-1S:  Anomaly Remediation\n--3/30/26 through 4/17/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1389530",null,"2026-03-23","2026-03-27",null,null,null,"MLV 40-2D to MLV 42-2BR",null,null,"Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,40.200000000000003,null,"MLV 40-2D to MLV 42-2BR:  Anomaly Remediation\n--3/23/26 through 3/27/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1389533",null,"2026-04-20","2026-05-08",null,null,null,"MLV 42-2BL to MLV 47-2S","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,42.2,null,"MLV 42-2BL to MLV 47-2S:  Anomaly Remediation\n--4/20/26 through 5/8/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1389545",null,"2026-05-04","2026-05-08",null,null,null,"MLV 42-2BL to MLV 47-2S",null,null,"Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,42.2,null,"MLV 42-2BL to MLV 47-2S:  Anomaly Remediation\n--5/4/26 through 5/8/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1389544",null,"2026-05-11","2026-05-22",null,null,null,"MLV 42-2BL to MLV 47-2S","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,42.2,null,"MLV 42-2BL to MLV 47-2S:  Anomaly Remediation\n--5/11/26 through 5/22/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1216073",null,"2026-04-21","2026-04-27",null,null,null,"Bear Creek Storage","100","1","Shut-in Test","This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","460017 STORAGE – BEAR CREEK",43.11,null,"Bear Creek Storage:  Shut-in Test\n--4/21/26 through 4/27/26:  This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  \n460017 STORAGE – BEAR CREEK\n………………………………"]
["X25-1216076",null,"2026-10-20","2026-10-26",null,null,null,"Bear Creek Storage","100","1","Shut-in Test","This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","460017 STORAGE – BEAR CREEK",43.12,null,"Bear Creek Storage:  Shut-in Test\n--10/20/26 through 10/26/26:  This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  \n460017 STORAGE – BEAR CREEK\n………………………………"]
["X25-1411913",null,"2026-09-09","2026-09-09",null,null,null,"Sta 47","100","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,47,null,"Sta 47:  Annual ESD Test\n--9/9/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-877998",null,"2025-07-21","2026-06-18",null,null,null,"Sta 47","100","1","Unit 8B - SawGrass Power Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,47.02,null,"Sta 47:  Unit 8B - SawGrass Power Overhaul\n--7/21/25 through 6/18/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-877996",null,"2025-07-21","2026-06-18",null,null,null,"Sta 47","100","1","Unit 9B - Sawgrass power overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,47.021000000000001,null,"Sta 47:  Unit 9B - Sawgrass power overhaul\n--7/21/25 through 6/18/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-82100",null,"2025-09-01","2026-03-16",null,null,null,"MLV 47-1A to MLV 48-1","100","1","Class Change","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,47.1,null,"MLV 47-1A to MLV 48-1:  Class Change\n--9/1/25 through 3/16/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1389534",null,"2026-05-11","2026-06-05",null,null,null,"MLV 47-1D to MLV 54-1S","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,47.1,null,"MLV 47-1D to MLV 54-1S:  Anomaly Remediation\n--5/11/26 through 6/5/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1389535",null,"2026-06-08","2026-06-26",null,null,null,"MLV 47-1D to MLV 54-1S","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,47.1,null,"MLV 47-1D to MLV 54-1S:  Anomaly Remediation\n--6/8/26 through 6/26/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1389538",null,"2026-06-29","2026-07-17",null,null,null,"MLV 47-1D to MLV 54-1S","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,47.1,null,"MLV 47-1D to MLV 54-1S:  Anomaly Remediation\n--6/29/26 through 7/17/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1479658","***","2025-12-11","2025-12-11","Completed",null,null,"MLV 53-1BR","100","1","RCV Installation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,53.1,"------","***MLV 53-1BR:  RCV Installation\n***Completed"]
["X25-946952","***","2025-11-12","2025-12-16","Completed",null,null,"MLV 53-3BR to MLV 54-3BL","100","1","HydroTest","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,53.3,"------","***MLV 53-3BR to MLV 54-3BL:  HydroTest\n***Completed"]
["X25-1411466",null,"2026-09-08","2026-09-10",null,null,null,"Sta 54 Greenville","100","1","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,54,null,"Sta 54 Greenville:  Annual ESD Test & Maintenance\n--9/8/26 through 9/10/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1479823",null,"2026-08-14","2026-08-18",null,null,null,"Sta 54","100","1","Sub-Station Transformer Inspection & Cleaning","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,54.01,null,"Sta 54:  Sub-Station Transformer Inspection & Cleaning\n--8/14/26 through 8/18/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-878000","***","2025-10-01","2025-12-12","Completed",null,null,"Sta 54","100","1","Unit 6B - Power Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,54.018000000000001,"------","***Sta 54:  Unit 6B - Power Overhaul\n***Completed"]
["X25-878001","***","2025-10-01","2025-12-12","Completed",null,null,"Sta 54","100","1","Unit 8B - Power Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,54.02,"------","***Sta 54:  Unit 8B - Power Overhaul\n***Completed"]
["X25-1320455","***","2025-12-08","2025-12-09","Completed",null,null,"Sta 54","100","1","Unit 1D - Replace Control Boxes and Blocks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,54.064,"------","***Sta 54:  Unit 1D - Replace Control Boxes and Blocks\n***Completed"]
["X25-1492863","***","2026-09-09","2026-09-09","Added",null,null,"Sta 54","100","3","Unit 1D - Annual Safety Device Checks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,54.064,"------","***Sta 54:  Unit 1D - Annual Safety Device Checks\n--9/9/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***Added\n………………………………"]
["X25-1320481","***","2025-12-15","2025-12-18","Project Change","2025-12-10","2025-12-11","Sta 54","100","1","Unit 2D - Replace Control Boxes and Blocks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,54.064999999999998,"--start_date--end_date--------------model_loc--","***Sta 54:  Unit 2D - Replace Control Boxes and Blocks\n--12/15/25 through 12/18/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***\nDate Change, Previously scheduled 12/10/25 to 12/11/25.\n………………………………"]
["X25-1389358",null,"2026-04-05","2026-04-16",null,null,null,"MLV 54-1D to 63-1S","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,54.1,null,"MLV 54-1D to 63-1S:  Anomaly Remediation\n--4/5/26 through 4/16/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1411366",null,"2026-08-25","2026-08-27",null,null,null,"Sta 63 Batesville","100","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,63,null,"Sta 63 Batesville:  Annual ESD Test\n--8/25/26 through 8/27/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1492861","***","2026-08-10","2026-08-21","Added",null,null,"Sta 63","100","1","Building B - Valve Replacement & Pump Modification","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,63.02,"------","***Sta 63:  Building B - Valve Replacement & Pump Modification\n--8/10/26 through 8/21/26:  This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***Added\n………………………………"]
["X25-1479828",null,"2026-06-21","2026-06-23",null,null,null,"Sta 63","100","1","Unit 1D - Safety Device Checks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,63.064,null,"Sta 63:  Unit 1D - Safety Device Checks\n--6/21/26 through 6/23/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1479829",null,"2026-06-30","2026-07-02",null,null,null,"Sta 63","100","1","Unit 2D - Safety Device Checks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,63.066000000000003,null,"Sta 63:  Unit 2D - Safety Device Checks\n--6/30/26 through 7/2/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1244238","***","2025-11-26","2025-12-09","Completed",null,null,"MLV 65-2 to MLV 66-2","100","1","Immediate Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,65.2,"------","***MLV 65-2 to MLV 66-2:  Immediate Anomaly Remediation\n***Completed"]
["X25-1244240","***","2025-11-26","2026-01-09","Project Change",null,"2025-12-17","MLV 66-2 to MLV 67-2","100","1","Immediate Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,66.2,"----end_date--------------model_loc--","***MLV 66-2 to MLV 67-2:  Immediate Anomaly Remediation\n--11/26/25 through 1/9/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 11/26/25 to 12/17/25.\n………………………………"]
["X25-1479667",null,"2026-05-12","2026-05-12",null,null,null,"MLV 69-1L to MLV 69-1CR","100","1","Pig Runs - Cleaning / Gauge 5/12/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,69.099999999999994,null,"MLV 69-1L to MLV 69-1CR:  Pig Runs - Cleaning / Gauge 5/12/26\n--5/12/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1479668",null,"2026-05-14","2026-05-14",null,null,null,"MLV 69-1L to MLV 69-1CR","100","1","Pig Runs - Cal / IMU MFL-A 5/14/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,69.099999999999994,null,"MLV 69-1L to MLV 69-1CR:  Pig Runs - Cal / IMU MFL-A 5/14/26\n--5/14/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1411658",null,"2026-05-13","2026-05-14",null,null,null,"Sta 71 Middleton","100","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,71,null,"Sta 71 Middleton:  Annual ESD Test\n--5/13/26 through 5/14/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X23-1196655",null,"2023-11-28","2026-04-30",null,null,null,"Sta 71","100","1","Unit 3A - Discharge Bottle Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,71.003,null,"Sta 71:  Unit 3A - Discharge Bottle Inspection\n--11/28/23 through 4/30/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X24-262275",null,"2024-04-08","2026-01-27",null,null,null,"Sta 71","100","1","Unit 7A Replace Crank End Compressor Gasket","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,71.007000000000005,null,"Sta 71:  Unit 7A Replace Crank End Compressor Gasket\n--4/8/24 through 1/27/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1389352",null,"2026-05-05","2026-05-16",null,null,null,"MLV 71-2D to MLV 79-2S","100","3","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,71.2,null,"MLV 71-2D to MLV 79-2S:  Anomaly Remediation\n--5/5/26 through 5/16/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1411667",null,"2026-05-06","2026-05-06",null,null,null,"Sta 79 Lobelville","100","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,79,null,"Sta 79 Lobelville:  Annual ESD Test\n--5/6/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-996875",null,"2026-04-14","2026-04-14",null,null,null,"MLV 79-4 to MLV 71-4D","100","1","Pig Runs - Cleaning / Gauge 4/14/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,79.400000000000006,null,"MLV 79-4 to MLV 71-4D:  Pig Runs - Cleaning / Gauge 4/14/26\n--4/14/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-996878",null,"2026-04-16","2026-04-16",null,null,null,"MLV 79-4 to MLV 71-4D","100","1","Pig Runs - CAL / IMU 4/16/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,79.41,null,"MLV 79-4 to MLV 71-4D:  Pig Runs - CAL / IMU 4/16/26\n--4/16/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-996881",null,"2026-04-21","2026-04-21",null,null,null,"MLV 79-4 to MLV 71-4D","100","1","Pig Runs - MFL-C 4/21/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,79.42,null,"MLV 79-4 to MLV 71-4D:  Pig Runs - MFL-C 4/21/26\n--4/21/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-996883","***","2026-04-23","2026-04-23","Project Change",null,null,"MLV 79-4 to MLV 71-4D","100","1","Pig Runs - EMAT 4/23/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,79.430000000000007,"--------------prl----model_loc--","***MLV 79-4 to MLV 71-4D:  Pig Runs - EMAT 4/23/26\n--4/23/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n***Project Change\n………………………………"]
["X25-1385295",null,"2026-10-06","2026-10-06",null,null,null,"MLV 82-1 to MLV 87-1","100","2","Pig Run - Cleaning / Gauge","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,82.1,null,"MLV 82-1 to MLV 87-1:  Pig Run - Cleaning / Gauge\n--10/6/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1385297",null,"2026-10-08","2026-10-08",null,null,null,"MLV 82-1 to MLV 87-1","100","2","Pig Run - AFD/Cal/IMU","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,82.1,null,"MLV 82-1 to MLV 87-1:  Pig Run - AFD/Cal/IMU\n--10/8/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1385298",null,"2026-10-13","2026-10-13",null,null,null,"MLV 82-1 to MLV 87-1","100","2","Pig Run - EMAT","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,82.1,null,"MLV 82-1 to MLV 87-1:  Pig Run - EMAT\n--10/13/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1389406",null,"2026-11-02","2026-11-13",null,null,null,"MLV 82-1C to MLV 87-1S","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,82.1,null,"MLV 82-1C to MLV 87-1S:  Anomaly Remediation\n--11/2/26 through 11/13/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1411809",null,"2026-10-21","2026-10-22",null,null,null,"Sta 87 Portland","100","2","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,87,null,"Sta 87 Portland:  Annual ESD Test\n--10/21/26 through 10/22/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1415642","***","2025-12-11","2025-12-11","Completed",null,null,"Sta 87","100","2","Unit 3D - Safety Device Tests","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,87.034999999999997,"------","***Sta 87:  Unit 3D - Safety Device Tests\n***Completed"]
["X25-1392132","***","2025-12-10","2025-12-10","Completed",null,null,"Sta 87","100","2","Unit 2D - Safety Device Tests","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,87.05,"------","***Sta 87:  Unit 2D - Safety Device Tests\n***Completed"]
["X25-906408","***","2025-10-27","2025-12-12","Completed",null,null,"Sta 87","100","2","Unit 2E - Turbocharger Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,87.066000000000003,"------","***Sta 87:  Unit 2E - Turbocharger Replacement\n***Completed"]
["X25-1490252","***","2025-12-15","2025-12-16","Completed",null,null,"Sta 87","100","1","Unit 1E - Safety Device Testing","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,87.08,"------","***Sta 87:  Unit 1E - Safety Device Testing\n***Completed"]
["X25-1385285",null,"2026-03-03","2026-03-03",null,null,null,"MLV 87-3 to MLV 96-3","100","2","Pig Run - Cleaning/Gauge","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,87.3,null,"MLV 87-3 to MLV 96-3:  Pig Run - Cleaning/Gauge\n--3/3/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1385286",null,"2026-03-05","2026-03-05",null,null,null,"MLV 87-3 to MLV 96-3","100","2","Pig Run - AFD","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,87.3,null,"MLV 87-3 to MLV 96-3:  Pig Run - AFD\n--3/5/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1385288",null,"2026-03-10","2026-03-10",null,null,null,"MLV 87-3 to MLV 96-3","100","2","Pig Run - EMAT","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,87.3,null,"MLV 87-3 to MLV 96-3:  Pig Run - EMAT\n--3/10/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-82079",null,"2025-10-23","2025-12-19",null,null,null,"MLV 90-3 to MLV 91-3","100","2","HDD River Crossing Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,90.3,null,"MLV 90-3 to MLV 91-3:  HDD River Crossing Replacement\n--10/23/25 through 12/19/25:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-1411830",null,"2026-06-09","2026-06-10",null,null,null,"Sta 96 Campbellsville","100","2","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,96,null,"Sta 96 Campbellsville:  Annual ESD Test\n--6/9/26 through 6/10/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1411869",null,"2026-06-09","2026-06-12",null,null,null,"Sta 96 Campbellsville","100","2","Annual Substation Inspection","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,96.000100000000003,null,"Sta 96 Campbellsville:  Annual Substation Inspection\n--6/9/26 through 6/12/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1288900",null,"2025-12-29","2026-01-09",null,null,null,"Sta 96","100","2","Unit 1D - Compressor Valves","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,96.063999999999993,null,"Sta 96:  Unit 1D - Compressor Valves\n--12/29/25 through 1/9/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1406582",null,"2026-08-24","2026-08-28",null,null,null,"MLV 96-1 to MLV 101-1","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,96.1,null,"MLV 96-1 to MLV 101-1:  Anomaly Remediation\n--8/24/26 through 8/28/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1385299",null,"2026-10-19","2026-10-19",null,null,null,"MLV 96-3 to MLV 106-3","100","2","Pig Run - Cleaning / Gauge","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,96.3,null,"MLV 96-3 to MLV 106-3:  Pig Run - Cleaning / Gauge\n--10/19/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1385301",null,"2026-10-20","2026-10-20",null,null,null,"MLV 96-3 to MLV 106-3","100","2","Pig Run - AFD","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,96.3,null,"MLV 96-3 to MLV 106-3:  Pig Run - AFD\n--10/20/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1385302",null,"2026-10-21","2026-10-21",null,null,null,"MLV 96-3 to MLV 106-3","100","2","Pig Run - EMAT","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,96.3,null,"MLV 96-3 to MLV 106-3:  Pig Run - EMAT\n--10/21/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1385303",null,"2026-10-22","2026-10-22",null,null,null,"MLV 96-3 to MLV 106-3","100","2","Pig Run - MDS","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,96.3,null,"MLV 96-3 to MLV 106-3:  Pig Run - MDS\n--10/22/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1385304",null,"2026-10-27","2026-10-27",null,null,null,"MLV 96-3 to MLV 106-3","100","2","Pig Run - Cleaning / Gauge","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,96.3,null,"MLV 96-3 to MLV 106-3:  Pig Run - Cleaning / Gauge\n--10/27/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1385305",null,"2026-10-29","2026-10-29",null,null,null,"MLV 96-3 to MLV 106-3","100","2","Pig Run - MDS","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,96.3,null,"MLV 96-3 to MLV 106-3:  Pig Run - MDS\n--10/29/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1385306",null,"2026-11-03","2026-11-03",null,null,null,"MLV 96-3 to MLV 106-3","100","2","Pig Run - AFD","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,96.3,null,"MLV 96-3 to MLV 106-3:  Pig Run - AFD\n--11/3/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1385307",null,"2026-11-05","2026-11-05",null,null,null,"MLV 96-3 to MLV 106-3","100","2","Pig Run - EMAT","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,96.3,null,"MLV 96-3 to MLV 106-3:  Pig Run - EMAT\n--11/5/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1474700",null,"2025-12-15","2025-12-19",null,null,null,"MLV 102-1A to MLV 103-1","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","420208 NG/TGP BEREA KY MADISON",102.1,null,"MLV 102-1A to MLV 103-1:  Anomaly Remediation\n--12/15/25 through 12/19/25:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  \n420208 NG/TGP BEREA KY MADISON\n………………………………"]
["X25-1389401",null,"2026-09-30","2026-10-04",null,null,null,"MLV 102-1A1 to MLV 106-1S","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,102.1,null,"MLV 102-1A1 to MLV 106-1S:  Anomaly Remediation\n--9/30/26 through 10/4/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1385289",null,"2026-03-24","2026-03-24",null,null,null,"MLV 105-2 to MLV 106-2","100","3","Pig Run - Cleaning / Gauge","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,105.2,null,"MLV 105-2 to MLV 106-2:  Pig Run - Cleaning / Gauge\n--3/24/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1385290",null,"2026-03-24","2026-03-24",null,null,null,"MLV 105-2 to MLV 106-2","100","3","Pig Run - MDS","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,105.2,null,"MLV 105-2 to MLV 106-2:  Pig Run - MDS\n--3/24/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1411071",null,"2026-06-02","2026-06-05",null,null,null,"Sta 106 Clay City","100","2","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,106,null,"Sta 106 Clay City:  Annual ESD Test & Maintenance\n--6/2/26 through 6/5/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1392016","***","2025-12-08","2025-12-12","Completed",null,null,"Sta 106","100","2","Unit 1B - Install 12\" Suction Unit Valve","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,106.017,"------","***Sta 106:  Unit 1B - Install 12\" Suction Unit Valve\n***Completed"]
["X25-1392014","***","2025-12-08","2025-12-12","Completed",null,null,"Sta 106","100",null,"Unit 9B - Install 12\" Suction Unit Valve","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,106.02500000000001,"------","***Sta 106:  Unit 9B - Install 12\" Suction Unit Valve\n***Completed"]
["X25-1428453",null,"2025-11-24","2026-01-30",null,null,null,"Sta 106","100","2","Unit 1C - Replace Power Cylinder Bearing #9","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,106.033,null,"Sta 106:  Unit 1C - Replace Power Cylinder Bearing #9\n--11/24/25 through 1/30/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1477455",null,"2026-03-03","2026-03-05",null,null,null,"Sta 106",null,null,"Unit 1D -  8K Solar Turbine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,106.06399999999999,null,"Sta 106:  Unit 1D -  8K Solar Turbine Inspection\n--3/3/26 through 3/5/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1477457",null,"2026-08-18","2026-08-20",null,null,null,"Sta 106","100","2","Unit 1D -  4K Solar Turbine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,106.06399999999999,null,"Sta 106:  Unit 1D -  4K Solar Turbine Inspection\n--8/18/26 through 8/20/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1477458",null,"2026-02-03","2026-02-05",null,null,null,"Sta 106","100","2","Unit 2D -  8K Solar Turbine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,106.065,null,"Sta 106:  Unit 2D -  8K Solar Turbine Inspection\n--2/3/26 through 2/5/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1477460",null,"2026-09-22","2026-09-24",null,null,null,"Sta 106","100","2","Unit 2D -  4K Solar Turbine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,106.065,null,"Sta 106:  Unit 2D -  4K Solar Turbine Inspection\n--9/22/26 through 9/24/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1385292",null,"2026-03-31","2026-03-31",null,null,null,"MLV 106-2 to MLV 110-2","100","3","Pig Run - Cleaning / Gauge","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,106.2,null,"MLV 106-2 to MLV 110-2:  Pig Run - Cleaning / Gauge\n--3/31/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1385293",null,"2026-04-02","2026-04-02",null,null,null,"MLV 106-2 to MLV 110-2","100","3","Pig Run - Cal / IMU","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,106.2,null,"MLV 106-2 to MLV 110-2:  Pig Run - Cal / IMU\n--4/2/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1385294",null,"2026-04-07","2026-04-07",null,null,null,"MLV 106-2 to MLV 110-2","100","3","Pig Run - MFL-A","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,106.2,null,"MLV 106-2 to MLV 110-2:  Pig Run - MFL-A\n--4/7/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1411131",null,"2026-10-06","2026-10-06",null,null,null,"Sta 107A North Means","100","2","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,107,null,"Sta 107A North Means:  Annual ESD Test\n--10/6/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-276809","***","2025-11-01","2025-12-17","Completed",null,null,"MLV 108-2 to MLV 109-2","100","2","Special Permit Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in during the project.","420212 DELTA NG/TGP SALT LICK KY BATH\n420038 MOREHEAD/TGP MOREHEAD KY ROWAN",108.2,"------","***MLV 108-2 to MLV 109-2:  Special Permit Pipe Replacement\n***Completed\nThe following meters are available for nominations:\n420212 DELTA NG/TGP SALT LICK KY BATH\n420038 MOREHEAD/TGP MOREHEAD KY ROWAN"]
["X25-1240781",null,"2026-03-02","2026-03-08",null,null,null,"MLV 109--3","100","2","Crossover to Ln 4 Valve Replacements","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,109.3,null,"MLV 109--3:  Crossover to Ln 4 Valve Replacements\n--3/2/26 through 3/8/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1240788",null,"2026-03-09","2026-03-15",null,null,null,"MLV 109--3","100","2","Crossover to Ln 5 Valve Replacements","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,109.3,null,"MLV 109--3:  Crossover to Ln 5 Valve Replacements\n--3/9/26 through 3/15/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1411039",null,"2026-05-18","2026-05-22",null,null,null,"Sta 110 Morehead","100","2","Annual ESD Test & Substation Inspection","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,110,null,"Sta 110 Morehead:  Annual ESD Test & Substation Inspection\n--5/18/26 through 5/22/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1380234",null,"2026-03-17","2026-03-17",null,null,null,"MLV 110-2 to MLV 114-2S","100","3","Pig Run - Gauge","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,110.2,null,"MLV 110-2 to MLV 114-2S:  Pig Run - Gauge\n--3/17/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1380237",null,"2026-03-19","2026-03-19",null,null,null,"MLV 110-2 to MLV 114-2S","100","3","Pig Run - MFL-C","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,110.2,null,"MLV 110-2 to MLV 114-2S:  Pig Run - MFL-C\n--3/19/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1355308",null,"2026-05-18","2026-05-20",null,null,null,"Sta 114 Catlettsburg","100","3","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,114,null,"Sta 114 Catlettsburg:  Annual ESD Test\n--5/18/26 through 5/20/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1355200",null,"2026-06-29","2026-07-01",null,null,null,"Sta 114","100","3","Unit 1D - Solar Turbine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,114.04900000000001,null,"Sta 114:  Unit 1D - Solar Turbine Inspection\n--6/29/26 through 7/1/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1355203",null,"2026-12-14","2026-12-16",null,null,null,"Sta 114","100","3","Unit 1D - Solar Turbine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,114.04900000000001,null,"Sta 114:  Unit 1D - Solar Turbine Inspection\n--12/14/26 through 12/16/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1355199",null,"2026-01-13","2026-01-13",null,null,null,"Sta 114","100","3","Unit 1D - Solar Turbine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,114.06399999999999,null,"Sta 114:  Unit 1D - Solar Turbine Inspection\n--1/13/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1355309",null,"2026-10-05","2026-10-06",null,null,null,"Sta 118A Tyler Mountain","100","3","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,118,null,"Sta 118A Tyler Mountain:  Annual ESD Test\n--10/5/26 through 10/6/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1355204",null,"2026-03-30","2026-04-01",null,null,null,"Sta 118A","100","3","Solar Turbine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,118.001,null,"Sta 118A:  Solar Turbine Inspection\n--3/30/26 through 4/1/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1355206",null,"2026-09-14","2026-09-16",null,null,null,"Sta 118A","100","3","Solar Turbine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,118.001,null,"Sta 118A:  Solar Turbine Inspection\n--9/14/26 through 9/16/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1355311",null,"2026-06-22","2026-06-23",null,null,null,"Sta 119A Rocky Fork","100","3","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,119,null,"Sta 119A Rocky Fork:  Annual ESD Test\n--6/22/26 through 6/23/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1355209",null,"2026-02-10","2026-02-10",null,null,null,"Sta 119A","100","3","Unit 1A - Solar Turbine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,119.001,null,"Sta 119A:  Unit 1A - Solar Turbine Inspection\n--2/10/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1355210",null,"2026-08-10","2026-08-12",null,null,null,"Sta 119A","100","3","Unit 1A - Solar Turbine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,119.001,null,"Sta 119A:  Unit 1A - Solar Turbine Inspection\n--8/10/26 through 8/12/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1411167",null,"2026-06-09","2026-06-12",null,null,null,"Sta 200 Greenup","200","4","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,200,null,"Sta 200 Greenup:  Annual ESD Test\n--6/9/26 through 6/12/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1418531","***","2025-12-08","2025-12-12","Completed",null,null,"Sta 200","200","4","Unit 12A - Engine Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,200.012,"------","***Sta 200:  Unit 12A - Engine Maintenance\n***Completed"]
["X25-1479841","***","2026-01-26","2026-01-30","Project Change","2025-12-15","2025-12-19","Sta 200","200","4","Unit 1B - GHG Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,200.017,"--start_date--end_date--------------model_loc--","***Sta 200:  Unit 1B - GHG Maintenance\n--1/26/26 through 1/30/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***\nDate Change, Previously scheduled 12/15/25 to 12/19/25.\n………………………………"]
["X25-1432124",null,"2026-01-05","2026-01-23",null,null,null,"Sta 204","200","4","Unit 1A - Turbo Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,204.001,null,"Sta 204:  Unit 1A - Turbo Replacement\n--1/5/26 through 1/23/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1494396","***","2026-01-12","2026-02-05","Added",null,null,"Sta 204","200","4","Unit 1A - Repair Turbo","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,204.001,"------","***Sta 204:  Unit 1A - Repair Turbo\n--1/12/26 through 2/5/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***Added\n………………………………"]
["X25-1440168",null,"2025-12-15","2025-12-18",null,null,null,"Sta 204","200","4","Unit 2A - Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,204.00200000000001,null,"Sta 204:  Unit 2A - Crankcase Inspection\n--12/15/25 through 12/18/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1380228",null,"2026-02-03","2026-02-03",null,null,null,"MLV 204-1 to MLV 209-1","200","4","Pig Run - Gauge","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,204.1,null,"MLV 204-1 to MLV 209-1:  Pig Run - Gauge\n--2/3/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1380230",null,"2026-02-05","2026-02-05",null,null,null,"MLV 204-1 to MLV 209-1","200","4","Pig Run - Cal/IMU","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,204.1,null,"MLV 204-1 to MLV 209-1:  Pig Run - Cal/IMU\n--2/5/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1380231",null,"2026-02-10","2026-02-10",null,null,null,"MLV 204-1 to MLV 209-1","200","4","Pig Run - MFL-C","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,204.1,null,"MLV 204-1 to MLV 209-1:  Pig Run - MFL-C\n--2/10/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1380233",null,"2026-02-12","2026-02-12",null,null,null,"MLV 204-1 to MLV 209-1","200","4","Pig Run - EMAT","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,204.1,null,"MLV 204-1 to MLV 209-1:  Pig Run - EMAT\n--2/12/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-35079","***","2025-12-16","2025-12-16","Completed",null,null,"MLV 204-2 to MLV 200-2","200","4","Pig Runs - MFL-C 12/16/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","421018 TET/TGP HANGING ROCK SCIOTO",204.25,"------","***MLV 204-2 to MLV 200-2:  Pig Runs - MFL-C 12/16/25\n***Completed\nThe following meters are available for nominations:\n421018 TET/TGP HANGING ROCK SCIOTO"]
["X25-624941",null,"2025-12-18","2025-12-18",null,null,null,"MLV 204-2 to MLV 200-2","200","4","Pig Runs - EMAT 12/18/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","421018 TET/TGP HANGING ROCK SCIOTO",204.26,null,"MLV 204-2 to MLV 200-2:  Pig Runs - EMAT 12/18/25\n--12/18/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n421018 TET/TGP HANGING ROCK SCIOTO\n………………………………"]
["X25-1428261",null,"2026-04-14","2026-04-14",null,null,null,"MLV 204-3 to MLV 209-3","200","4","Pig Run - Gauge/Cleaning","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,204.3,null,"MLV 204-3 to MLV 209-3:  Pig Run - Gauge/Cleaning\n--4/14/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1428264",null,"2026-04-16","2026-04-16",null,null,null,"MLV 204-3 to MLV 209-3","200","4","Pig Run - Cal/IMU","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,204.3,null,"MLV 204-3 to MLV 209-3:  Pig Run - Cal/IMU\n--4/16/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1428270",null,"2026-04-21","2026-04-21",null,null,null,"MLV 204-3 to MLV 209-3","200","4","Pig Run - MFL-C","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,204.3,null,"MLV 204-3 to MLV 209-3:  Pig Run - MFL-C\n--4/21/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1428273","***","2026-04-26","2026-04-26","Project Change",null,null,"MLV 204-3 to MLV 209-3","200","4","Pig Run - EMAT","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,204.3,"--------------prl----model_loc--","***MLV 204-3 to MLV 209-3:  Pig Run - EMAT\n--4/26/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n***Project Change\n………………………………"]
["X25-1380238",null,"2026-11-10","2026-11-10",null,null,null,"MLV 204-4 to MLV 209-4","200","4","Pig Run - Gauge","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,204.4,null,"MLV 204-4 to MLV 209-4:  Pig Run - Gauge\n--11/10/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1380240",null,"2026-11-12","2026-11-12",null,null,null,"MLV 204-4 to MLV 209-4","200","4","Pig Run - Cal/IMU","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,204.4,null,"MLV 204-4 to MLV 209-4:  Pig Run - Cal/IMU\n--11/12/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1380242",null,"2026-11-17","2026-11-17",null,null,null,"MLV 204-4 to MLV 209-4","200","4","Pig Run - MFL-C","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,204.4,null,"MLV 204-4 to MLV 209-4:  Pig Run - MFL-C\n--11/17/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1380243",null,"2026-11-19","2026-11-19",null,null,null,"MLV 204-4 to MLV 209-4","200","4","Pig Run - EMAT","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,204.4,null,"MLV 204-4 to MLV 209-4:  Pig Run - EMAT\n--11/19/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1412849",null,"2026-05-04","2026-08-01",null,null,null,"MLV 205-3 to MLV 206-3","200","4","Landslide Mitigation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,205.3,null,"MLV 205-3 to MLV 206-3:  Landslide Mitigation\n--5/4/26 through 8/1/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1412791",null,"2026-05-04","2026-08-01",null,null,null,"MLV 205-4 to MLV 206-4","200","4","Landslide Mitigation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,205.4,null,"MLV 205-4 to MLV 206-4:  Landslide Mitigation\n--5/4/26 through 8/1/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1412769",null,"2026-05-04","2026-08-01",null,null,null,"MLV 206-3 to MLV 207-3","200","4","Landslide Mitigation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,206.3,null,"MLV 206-3 to MLV 207-3:  Landslide Mitigation\n--5/4/26 through 8/1/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1412818",null,"2026-05-04","2026-08-01",null,null,null,"MLV 206-4 to MLV 207-4","200","4","Landslide Mitigation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,206.4,null,"MLV 206-4 to MLV 207-4:  Landslide Mitigation\n--5/4/26 through 8/1/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1494397","***","2026-01-12","2026-01-15","Added",null,null,"Sta 209","200","4","Unit 3A - Engine Mainteance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,209.00299999999999,"------","***Sta 209:  Unit 3A - Engine Mainteance\n--1/12/26 through 1/15/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***Added\n………………………………"]
["X25-1338426",null,"2026-01-05","2026-01-08",null,null,null,"Sta 209","200","4","Unit 7A - C1 Pressure Packing","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,209.00700000000001,null,"Sta 209:  Unit 7A - C1 Pressure Packing\n--1/5/26 through 1/8/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1370010","***","2025-12-08","2025-12-11","Completed",null,null,"Sta 209","200","4","Unit 8A - Inspect for High Iron Levels","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,209.00800000000001,"------","***Sta 209:  Unit 8A - Inspect for High Iron Levels\n***Completed"]
["X25-1370012",null,"2025-12-15","2025-12-18",null,null,null,"Sta 209","200","4","Unit 10A - Inspect for High Iron Levels","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,209.01,null,"Sta 209:  Unit 10A - Inspect for High Iron Levels\n--12/15/25 through 12/18/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1428244",null,"2026-03-10","2026-03-10",null,null,null,"MLV 209-2 to MLV 214-2","200","4","Pig Run - Gauge/Cleaning","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,209.2,null,"MLV 209-2 to MLV 214-2:  Pig Run - Gauge/Cleaning\n--3/10/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1428245",null,"2026-03-12","2026-03-12",null,null,null,"MLV 209-2 to MLV 214-2","200","4","Pig Run - Cal/IMU","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,209.2,null,"MLV 209-2 to MLV 214-2:  Pig Run - Cal/IMU\n--3/12/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1428247",null,"2026-03-17","2026-03-17",null,null,null,"MLV 209-2 to MLV 214-2","200","4","Pig Run - MFL-C","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,209.2,null,"MLV 209-2 to MLV 214-2:  Pig Run - MFL-C\n--3/17/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1428248",null,"2026-03-19","2026-03-19",null,null,null,"MLV 209-2 to MLV 214-2","200","4","Pig Run - EMAT","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,209.2,null,"MLV 209-2 to MLV 214-2:  Pig Run - EMAT\n--3/19/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1406725",null,"2025-12-08","2025-12-19",null,null,null,"Sta 214","200","4","Unit 7A - PLC Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,214.00700000000001,null,"Sta 214:  Unit 7A - PLC Replacement\n--12/8/25 through 12/19/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1406723",null,"2025-12-08","2025-12-19",null,null,null,"Sta 214","200","4","Unit 8A - PLC Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,214.00800000000001,null,"Sta 214:  Unit 8A - PLC Replacement\n--12/8/25 through 12/19/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1406721",null,"2025-12-08","2025-12-19",null,null,null,"Sta 214","200","4","Unit 9A - PLC Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,214.00899999999999,null,"Sta 214:  Unit 9A - PLC Replacement\n--12/8/25 through 12/19/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1479961","***","2025-12-08","2025-12-11","Completed",null,null,"Sta 214","200","4","Unit 10A - Engine Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,214.01,"------","***Sta 214:  Unit 10A - Engine Maintenance\n***Completed"]
["X25-1355266",null,"2025-09-15","2026-01-12",null,null,null,"Sta 214","200","4","Unit 12A - Engine Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,214.012,null,"Sta 214:  Unit 12A - Engine Maintenance\n--9/15/25 through 1/12/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1494596","***","2025-12-15","2025-12-18","Added",null,null,"Sta 214","200","4","Unit 13A - Engine Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,214.01300000000001,"------","***Sta 214:  Unit 13A - Engine Maintenance\n--12/15/25 through 12/18/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***Added\n………………………………"]
["X25-1428303",null,"2026-10-15","2026-10-15",null,null,null,"MLV 214-1 to MLV 219-1","200","4","Pig Run - Gauge/Cleaning","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,214.1,null,"MLV 214-1 to MLV 219-1:  Pig Run - Gauge/Cleaning\n--10/15/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1428304",null,"2026-10-20","2026-10-20",null,null,null,"MLV 214-1 to MLV 219-1","200","4","Pig Run - Cal/IMU","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,214.1,null,"MLV 214-1 to MLV 219-1:  Pig Run - Cal/IMU\n--10/20/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1428305",null,"2026-10-22","2026-10-22",null,null,null,"MLV 214-1 to MLV 219-1","200","4","Pig Run - MFL-C","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,214.1,null,"MLV 214-1 to MLV 219-1:  Pig Run - MFL-C\n--10/22/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1428274","***","2026-04-28","2026-04-28","Project Change",null,null,"MLV 214-2 to MLV 219-2","200","4","Pig Run - Gauge/Cleaning","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","50561 - UGIAPP/TGP MARTIN RECEIPT NEW CASTL",214.2,"--------------prl----model_loc--","***MLV 214-2 to MLV 219-2:  Pig Run - Gauge/Cleaning\n--4/28/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  \n50561 - UGIAPP/TGP MARTIN RECEIPT NEW CASTL\n***Project Change\n………………………………"]
["X25-1428275","***","2026-04-30","2026-04-30","Project Change",null,null,"MLV 214-2 to MLV 219-2","200","4","Pig Run - Cal/IMU","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","50561 - UGIAPP/TGP MARTIN RECEIPT NEW CASTL",214.2,"--------------prl----model_loc--","***MLV 214-2 to MLV 219-2:  Pig Run - Cal/IMU\n--4/30/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  \n50561 - UGIAPP/TGP MARTIN RECEIPT NEW CASTL\n***Project Change\n………………………………"]
["X25-1428277",null,"2026-05-04","2026-05-04",null,null,null,"MLV 214-2 to MLV 219-2","200","4","Pig Run - MFL-C","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","50561 - UGIAPP/TGP MARTIN RECEIPT NEW CASTL",214.2,null,"MLV 214-2 to MLV 219-2:  Pig Run - MFL-C\n--5/4/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  \n50561 - UGIAPP/TGP MARTIN RECEIPT NEW CASTL\n………………………………"]
["X25-1428279",null,"2026-05-06","2026-05-06",null,null,null,"MLV 214-2 to MLV 219-2","200","4","Pig Run - EMAT","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","50561 - UGIAPP/TGP MARTIN RECEIPT NEW CASTL",214.2,null,"MLV 214-2 to MLV 219-2:  Pig Run - EMAT\n--5/6/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  \n50561 - UGIAPP/TGP MARTIN RECEIPT NEW CASTL\n………………………………"]
["X25-1428299",null,"2026-09-15","2026-09-15",null,null,null,"MLV 214-3 to MLV 219-3","200","4","Pig Run - Gauge/Cleaning","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","420932 E OH GAS/TGP PETERSBURG MAHONING",214.3,null,"MLV 214-3 to MLV 219-3:  Pig Run - Gauge/Cleaning\n--9/15/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  \n420932 E OH GAS/TGP PETERSBURG MAHONING\n………………………………"]
["X25-1428301",null,"2026-09-17","2026-09-17",null,null,null,"MLV 214-3 to MLV 219-3","200","4","Pig Run - Cal/IMU/MFL-A Combo","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","420932 E OH GAS/TGP PETERSBURG MAHONING",214.3,null,"MLV 214-3 to MLV 219-3:  Pig Run - Cal/IMU/MFL-A Combo\n--9/17/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  \n420932 E OH GAS/TGP PETERSBURG MAHONING\n………………………………"]
["X25-1428250",null,"2026-04-06","2026-04-06",null,null,null,"MLV 217A-101.1 to 217A-104","200","4","Pig Run - Gauge/Cleaning","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","412863 - GEOPETRO/TGP LITTLE BEAVER: RIP 217\n421075 - LINDYPAV/TGP BIG BEAVER: DIP 217A-1\n420063 - COL GAS/TGP UNIONVILLE PA BEAVER\n420385 - PEOPLES/TGP PITTSBURG TERMINAL PA A\n420078 - EQUITRNS/TGP PITTSBURGH TERMINAL PA\n420199 - PEOPLES/TGP PITTSBURGH TERMINAL PA\n420306 - COL GAS/TGP PITTSBURGH TERMINAL PA",217.1,null,"MLV 217A-101.1 to 217A-104:  Pig Run - Gauge/Cleaning\n--4/6/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  \n412863 - GEOPETRO/TGP LITTLE BEAVER: RIP 217\n421075 - LINDYPAV/TGP BIG BEAVER: DIP 217A-1\n420063 - COL GAS/TGP UNIONVILLE PA BEAVER\n420385 - PEOPLES/TGP PITTSBURG TERMINAL PA A\n420078 - EQUITRNS/TGP PITTSBURGH TERMINAL PA\n420199 - PEOPLES/TGP PITTSBURGH TERMINAL PA\n420306 - COL GAS/TGP PITTSBURGH TERMINAL PA\n………………………………"]
["X25-1428252",null,"2026-04-07","2026-04-07",null,null,null,"MLV 217A-101.1 to 217A-104","200","4","Pig Runs - Cal/IMU","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","412863 - GEOPETRO/TGP LITTLE BEAVER: RIP 217\n421075 - LINDYPAV/TGP BIG BEAVER: DIP 217A-1\n420063 - COL GAS/TGP UNIONVILLE PA BEAVER\n420385 - PEOPLES/TGP PITTSBURG TERMINAL PA A\n420078 - EQUITRNS/TGP PITTSBURGH TERMINAL PA\n420199 - PEOPLES/TGP PITTSBURGH TERMINAL PA\n420306 - COL GAS/TGP PITTSBURGH TERMINAL PA",217.1,null,"MLV 217A-101.1 to 217A-104:  Pig Runs - Cal/IMU\n--4/7/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  \n412863 - GEOPETRO/TGP LITTLE BEAVER: RIP 217\n421075 - LINDYPAV/TGP BIG BEAVER: DIP 217A-1\n420063 - COL GAS/TGP UNIONVILLE PA BEAVER\n420385 - PEOPLES/TGP PITTSBURG TERMINAL PA A\n420078 - EQUITRNS/TGP PITTSBURGH TERMINAL PA\n420199 - PEOPLES/TGP PITTSBURGH TERMINAL PA\n420306 - COL GAS/TGP PITTSBURGH TERMINAL PA\n………………………………"]
["X25-1428257",null,"2026-04-21","2026-04-21",null,null,null,"MLV 217A-101.1 to 217A-104","200","4","Pig Run - MFL-C","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","412863 - GEOPETRO/TGP LITTLE BEAVER: RIP 217\n421075 - LINDYPAV/TGP BIG BEAVER: DIP 217A-1\n420063 - COL GAS/TGP UNIONVILLE PA BEAVER\n420385 - PEOPLES/TGP PITTSBURG TERMINAL PA A\n420078 - EQUITRNS/TGP PITTSBURGH TERMINAL PA\n420199 - PEOPLES/TGP PITTSBURGH TERMINAL PA\n420306 - COL GAS/TGP PITTSBURGH TERMINAL PA",217.1,null,"MLV 217A-101.1 to 217A-104:  Pig Run - MFL-C\n--4/21/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  \n412863 - GEOPETRO/TGP LITTLE BEAVER: RIP 217\n421075 - LINDYPAV/TGP BIG BEAVER: DIP 217A-1\n420063 - COL GAS/TGP UNIONVILLE PA BEAVER\n420385 - PEOPLES/TGP PITTSBURG TERMINAL PA A\n420078 - EQUITRNS/TGP PITTSBURGH TERMINAL PA\n420199 - PEOPLES/TGP PITTSBURGH TERMINAL PA\n420306 - COL GAS/TGP PITTSBURGH TERMINAL PA\n………………………………"]
["X25-1428258","***","2026-04-26","2026-04-26","Project Change",null,null,"MLV 217A-101.1 to 217A-104",null,null,"Pig Run - EMAT","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","412863 - GEOPETRO/TGP LITTLE BEAVER: RIP 217\n421075 - LINDYPAV/TGP BIG BEAVER: DIP 217A-1\n420063 - COL GAS/TGP UNIONVILLE PA BEAVER\n420385 - PEOPLES/TGP PITTSBURG TERMINAL PA A\n420078 - EQUITRNS/TGP PITTSBURGH TERMINAL PA\n420199 - PEOPLES/TGP PITTSBURGH TERMINAL PA\n420306 - COL GAS/TGP PITTSBURGH TERMINAL PA",217.1,"--------------prl----model_loc--","***MLV 217A-101.1 to 217A-104:  Pig Run - EMAT\n--4/26/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  \n412863 - GEOPETRO/TGP LITTLE BEAVER: RIP 217\n421075 - LINDYPAV/TGP BIG BEAVER: DIP 217A-1\n420063 - COL GAS/TGP UNIONVILLE PA BEAVER\n420385 - PEOPLES/TGP PITTSBURG TERMINAL PA A\n420078 - EQUITRNS/TGP PITTSBURGH TERMINAL PA\n420199 - PEOPLES/TGP PITTSBURGH TERMINAL PA\n420306 - COL GAS/TGP PITTSBURGH TERMINAL PA\n***Project Change\n………………………………"]
["X25-1492880","***","2025-12-29","2026-01-01","Added",null,null,"Sta 219","200","4","Unit 2A - Engine Inspections","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,219.00200000000001,"------","***Sta 219:  Unit 2A - Engine Inspections\n--12/29/25 through 1/1/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***Added\n………………………………"]
["X25-1479892",null,"2025-12-15","2025-12-18",null,null,null,"Sta 219","200","4","Unit 6A - Power Cylinder Inspections","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,219.006,null,"Sta 219:  Unit 6A - Power Cylinder Inspections\n--12/15/25 through 12/18/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1428341",null,"2026-04-04","2026-04-04",null,null,null,"MLV 230-1 to MLV 237-1","200","5","Pig Run - Gauge/Cleaning","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","420688    EGTS/TGP LAKEVILLE SALES LIVINGSTON\n450421\tTGP/TGP CRAIGS CHECK LIVINGSTON\n411106\tHONEOYE/TGP STORAGE  WDL ONTARIO\n420690    EGTS/TGP NORTH SHELDON SALES WYOMIN\n412856\tEMPIREPL/TGP CANANDAIGUA ONTARIO\n420617\tEGTS/TGP HOPEWELL SALES ONTARIO",230.1,null,"MLV 230-1 to MLV 237-1:  Pig Run - Gauge/Cleaning\n--4/4/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  \n420688    EGTS/TGP LAKEVILLE SALES LIVINGSTON\n450421\tTGP/TGP CRAIGS CHECK LIVINGSTON\n411106\tHONEOYE/TGP STORAGE  WDL ONTARIO\n420690    EGTS/TGP NORTH SHELDON SALES WYOMIN\n412856\tEMPIREPL/TGP CANANDAIGUA ONTARIO\n420617\tEGTS/TGP HOPEWELL SALES ONTARIO\n………………………………"]
["X25-1428344",null,"2026-04-06","2026-04-06",null,null,null,"MLV 230-1 to MLV 237-1","200","5","Pig Run - CAL/IMU/MFL-C","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","420688    EGTS/TGP LAKEVILLE SALES LIVINGSTON\n450421\tTGP/TGP CRAIGS CHECK LIVINGSTON\n411106\tHONEOYE/TGP STORAGE  WDL ONTARIO\n420690    EGTS/TGP NORTH SHELDON SALES WYOMIN\n412856\tEMPIREPL/TGP CANANDAIGUA ONTARIO\n420617\tEGTS/TGP HOPEWELL SALES ONTARIO",230.1,null,"MLV 230-1 to MLV 237-1:  Pig Run - CAL/IMU/MFL-C\n--4/6/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  \n420688    EGTS/TGP LAKEVILLE SALES LIVINGSTON\n450421\tTGP/TGP CRAIGS CHECK LIVINGSTON\n411106\tHONEOYE/TGP STORAGE  WDL ONTARIO\n420690    EGTS/TGP NORTH SHELDON SALES WYOMIN\n412856\tEMPIREPL/TGP CANANDAIGUA ONTARIO\n420617\tEGTS/TGP HOPEWELL SALES ONTARIO\n………………………………"]
["X25-1428345",null,"2026-04-08","2026-04-08",null,null,null,"MLV 230-1 to MLV 237-1","200","5","Pig Run - EMAT","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","420688    EGTS/TGP LAKEVILLE SALES LIVINGSTON\n450421\tTGP/TGP CRAIGS CHECK LIVINGSTON\n411106\tHONEOYE/TGP STORAGE  WDL ONTARIO\n420690    EGTS/TGP NORTH SHELDON SALES WYOMIN\n412856\tEMPIREPL/TGP CANANDAIGUA ONTARIO\n420617\tEGTS/TGP HOPEWELL SALES ONTARIO",230.1,null,"MLV 230-1 to MLV 237-1:  Pig Run - EMAT\n--4/8/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  \n420688    EGTS/TGP LAKEVILLE SALES LIVINGSTON\n450421\tTGP/TGP CRAIGS CHECK LIVINGSTON\n411106\tHONEOYE/TGP STORAGE  WDL ONTARIO\n420690    EGTS/TGP NORTH SHELDON SALES WYOMIN\n412856\tEMPIREPL/TGP CANANDAIGUA ONTARIO\n420617\tEGTS/TGP HOPEWELL SALES ONTARIO\n………………………………"]
["X25-1428285",null,"2026-07-08","2026-07-08",null,null,null,"MLV 230B-201 to MLV 230B-205","200","5","Pig Run - Gauge/Cleaning","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,230.2,null,"MLV 230B-201 to MLV 230B-205:  Pig Run - Gauge/Cleaning\n--7/8/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1428288",null,"2026-07-09","2026-07-09",null,null,null,"MLV 230B-201 to MLV 230B-205","200","5","Pig Run - Cal/IMU/MFL-A Combo","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,230.2,null,"MLV 230B-201 to MLV 230B-205:  Pig Run - Cal/IMU/MFL-A Combo\n--7/9/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1428290",null,"2026-07-14","2026-07-14",null,null,null,"MLV 230B-205 to MLV 230B-206A","200","5","Pig Run - Gauge/Cleaning","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,230.2,null,"MLV 230B-205 to MLV 230B-206A:  Pig Run - Gauge/Cleaning\n--7/14/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1428294",null,"2026-07-15","2026-07-15",null,null,null,"MLV 230B-205 to MLV 230B-206A","200","5","Pig Run - Cal/IMU/MFL-A Combo","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,230.2,null,"MLV 230B-205 to MLV 230B-206A:  Pig Run - Cal/IMU/MFL-A Combo\n--7/15/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-219102",null,"2026-05-15","2026-06-06",null,null,null,"MLV 236-1 to MLV 237-1BR","200","5","Special Permit Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be constrained or shut in during the project.","412856 EMPIREPL/TGP CANANDIAGUA ONTARIO\n420617 EGTS/TGP HOPEWELL SALES ONTARIO\n420526 HONEOYE/TGP UDP HONEOYE NEW YORK ON",236.1,null,"MLV 236-1 to MLV 237-1BR:  Special Permit Replacement\n--5/15/26 through 6/6/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n412856 EMPIREPL/TGP CANANDIAGUA ONTARIO\n420617 EGTS/TGP HOPEWELL SALES ONTARIO\n420526 HONEOYE/TGP UDP HONEOYE NEW YORK ON\n………………………………"]
["X25-1320307",null,"2026-05-12","2026-05-12",null,null,null,"MLV 237-2 to MLV 245-2","200","4","Pig Run - Gauge/Cleaning Tool","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420086 EGTS/TGP PHELPS NY ONTARIO\n420732 POA/TGP SYRACUSE COGEN SALES ONONDA\n412065 EGTS/TGP MORRISVILLE TRANSPORT MADI\n47592 HAMVIL/TGP VILLAGE OF HAMILTON NY M",237.2,null,"MLV 237-2 to MLV 245-2:  Pig Run - Gauge/Cleaning Tool\n--5/12/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  \n420086 EGTS/TGP PHELPS NY ONTARIO\n420732 POA/TGP SYRACUSE COGEN SALES ONONDA\n412065 EGTS/TGP MORRISVILLE TRANSPORT MADI\n47592 HAMVIL/TGP VILLAGE OF HAMILTON NY M\n………………………………"]
["X25-1428334",null,"2026-05-12","2026-05-12",null,null,null,"MLV 237-2 to MLV 245-2","200","5","Pig Run - Gauge/Cleaning","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","420086 - EGTS/TGP PHELPS NY ONTARIO\n420732 - POA/TGP SYRACUSE COGEN SALES ONONDA\n412065 - EGTS/TGP MORRISVILLE TRANSPORT MADI\n47592 - HAMVIL/TGP VILLAGE OF HAMILTON NY M",237.2,null,"MLV 237-2 to MLV 245-2:  Pig Run - Gauge/Cleaning\n--5/12/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  \n420086 - EGTS/TGP PHELPS NY ONTARIO\n420732 - POA/TGP SYRACUSE COGEN SALES ONONDA\n412065 - EGTS/TGP MORRISVILLE TRANSPORT MADI\n47592 - HAMVIL/TGP VILLAGE OF HAMILTON NY M\n………………………………"]
["X25-1428337",null,"2026-05-14","2026-05-14",null,null,null,"MLV 237-2 to MLV 245-2","200","5","Pig Run - CAL/IMU","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","420086 - EGTS/TGP PHELPS NY ONTARIO\n420732 - POA/TGP SYRACUSE COGEN SALES ONONDA\n412065 - EGTS/TGP MORRISVILLE TRANSPORT MADI\n47592 - HAMVIL/TGP VILLAGE OF HAMILTON NY M",237.2,null,"MLV 237-2 to MLV 245-2:  Pig Run - CAL/IMU\n--5/14/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  \n420086 - EGTS/TGP PHELPS NY ONTARIO\n420732 - POA/TGP SYRACUSE COGEN SALES ONONDA\n412065 - EGTS/TGP MORRISVILLE TRANSPORT MADI\n47592 - HAMVIL/TGP VILLAGE OF HAMILTON NY M\n………………………………"]
["X25-1320310",null,"2026-05-14","2026-05-14",null,null,null,"MLV 237-2 to MLV 245-2","200","4","Pig Run - CAL/IMU","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420086 EGTS/TGP PHELPS NY ONTARIO\n420732 POA/TGP SYRACUSE COGEN SALES ONONDA\n412065 EGTS/TGP MORRISVILLE TRANSPORT MADI\n47592 HAMVIL/TGP VILLAGE OF HAMILTON NY M",237.2,null,"MLV 237-2 to MLV 245-2:  Pig Run - CAL/IMU\n--5/14/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  \n420086 EGTS/TGP PHELPS NY ONTARIO\n420732 POA/TGP SYRACUSE COGEN SALES ONONDA\n412065 EGTS/TGP MORRISVILLE TRANSPORT MADI\n47592 HAMVIL/TGP VILLAGE OF HAMILTON NY M\n………………………………"]
["X25-1320311",null,"2026-05-18","2026-05-18",null,null,null,"MLV 237-2 to MLV 245-2","200","4","Pig Run - MFL-A","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420086 EGTS/TGP PHELPS NY ONTARIO\n420732 POA/TGP SYRACUSE COGEN SALES ONONDA\n412065 EGTS/TGP MORRISVILLE TRANSPORT MADI\n47592 HAMVIL/TGP VILLAGE OF HAMILTON NY M",237.2,null,"MLV 237-2 to MLV 245-2:  Pig Run - MFL-A\n--5/18/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  \n420086 EGTS/TGP PHELPS NY ONTARIO\n420732 POA/TGP SYRACUSE COGEN SALES ONONDA\n412065 EGTS/TGP MORRISVILLE TRANSPORT MADI\n47592 HAMVIL/TGP VILLAGE OF HAMILTON NY M\n………………………………"]
["X25-1428338",null,"2026-05-18","2026-05-18",null,null,null,"MLV 237-2 to MLV 245-2","200","5","Pig Run - MFL-A","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","420086 - EGTS/TGP PHELPS NY ONTARIO\n420732 - POA/TGP SYRACUSE COGEN SALES ONONDA\n412065 - EGTS/TGP MORRISVILLE TRANSPORT MADI\n47592 - HAMVIL/TGP VILLAGE OF HAMILTON NY M",237.2,null,"MLV 237-2 to MLV 245-2:  Pig Run - MFL-A\n--5/18/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  \n420086 - EGTS/TGP PHELPS NY ONTARIO\n420732 - POA/TGP SYRACUSE COGEN SALES ONONDA\n412065 - EGTS/TGP MORRISVILLE TRANSPORT MADI\n47592 - HAMVIL/TGP VILLAGE OF HAMILTON NY M\n………………………………"]
["X25-1288928",null,"2026-07-14","2026-07-14",null,null,null,"Sta 245-1 to MLV 249-1","200","5","Pig Run - Gauge/Cleaning tool","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,245.1,null,"Sta 245-1 to MLV 249-1:  Pig Run - Gauge/Cleaning tool\n--7/14/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1288931",null,"2026-07-15","2026-07-15",null,null,null,"Sta 245-1 to MLV 249-1","200","5","Pig Run - Cal/IMU","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,245.1,null,"Sta 245-1 to MLV 249-1:  Pig Run - Cal/IMU\n--7/15/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1288932",null,"2026-07-16","2026-07-16",null,null,null,"Sta 245-1 to MLV 249-1","200","5","Pig Run - MFL-C","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,245.1,null,"Sta 245-1 to MLV 249-1:  Pig Run - MFL-C\n--7/16/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1288933",null,"2026-10-27","2026-10-27",null,null,null,"Sta 245-1 to MLV 249-1",null,null,"Pig Run - EMAT","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,245.1,null,"Sta 245-1 to MLV 249-1:  Pig Run - EMAT\n--10/27/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1288891","***","2026-04-28","2026-04-28","Project Change",null,null,"MLV 249-2 to MLV 254-2","200","5","Gauge/Cleaning tool","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,249.2,"--------------prl----model_loc--","***MLV 249-2 to MLV 254-2:  Gauge/Cleaning tool\n--4/28/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n***Project Change\n………………………………"]
["X25-1288892","***","2026-04-29","2026-04-29","Project Change",null,null,"MLV 249-2 to MLV 254-2","200","5","Cal/IMU","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,249.2,"--------------prl----model_loc--","***MLV 249-2 to MLV 254-2:  Cal/IMU\n--4/29/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n***Project Change\n………………………………"]
["X25-1288894","***","2026-04-30","2026-04-30","Project Change",null,null,"MLV 249-2 to MLV 254-2","200","5","MFL-C","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,249.2,"--------------prl----model_loc--","***MLV 249-2 to MLV 254-2:  MFL-C\n--4/30/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n***Project Change\n………………………………"]
["X25-1288916",null,"2026-06-23","2026-06-23",null,null,null,"MLV 249-3A to MLV 251-3","200","5","Pig Run - Gauge/Cleaning tool","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,249.3,null,"MLV 249-3A to MLV 251-3:  Pig Run - Gauge/Cleaning tool\n--6/23/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1288920",null,"2026-06-24","2026-06-24",null,null,null,"MLV 249-3A to MLV 251-3","200","5","Pig Run - Cal/IMU/MFL-A Combo","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,249.3,null,"MLV 249-3A to MLV 251-3:  Pig Run - Cal/IMU/MFL-A Combo\n--6/24/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1288901",null,"2026-05-27","2026-05-27",null,null,null,"MLV 254-2 to MLV 261-2","200","5","Pig Run - Gauge/Cleaning tool","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,254.2,null,"MLV 254-2 to MLV 261-2:  Pig Run - Gauge/Cleaning tool\n--5/27/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1288904",null,"2026-05-28","2026-05-28",null,null,null,"MLV 254-2 to MLV 261-2","200","5","Pig Run - Cal/IMU/MFL-A Combo","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,254.2,null,"MLV 254-2 to MLV 261-2:  Pig Run - Cal/IMU/MFL-A Combo\n--5/28/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1288752",null,"2026-04-13","2026-04-13",null,null,null,"MLV 254-3 to MLV 258-3A","200","6","Pig Runs - Gauge/Cleaning tool - 4/13/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,254.3,null,"MLV 254-3 to MLV 258-3A:  Pig Runs - Gauge/Cleaning tool - 4/13/26\n--4/13/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1288753",null,"2026-04-14","2026-04-14",null,null,null,"MLV 254-3 to MLV 258-3A","200","6","Pig Runs - Cal/IMU/MFL-A Combo - 4/14/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,254.3,null,"MLV 254-3 to MLV 258-3A:  Pig Runs - Cal/IMU/MFL-A Combo - 4/14/26\n--4/14/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1369747",null,"2026-07-09","2026-07-09",null,null,null,"MLV 255","200","4","ECDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,255,null,"MLV 255:  ECDA\n--7/9/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1482735","***","2025-12-16","2025-12-16","Completed",null,null,"MLVS 256A-121 to MLV 256C-131","200","6","Meter Station Maintenance (PIN: 420747 Meter: Bousquet)",null,null,256.10000000000002,"------","***MLVS 256A-121 to MLV 256C-131:  Meter Station Maintenance (PIN: 420747 Meter: Bousquet)\n***Completed"]
["X25-1288883",null,"2026-04-16","2026-04-16",null,null,null,"MLV 256C-101.1 to MLV 256C-102","200","6","Pig Runs - Gauge/Cleaning tool","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.","420638 - BERKSHR/TGP WEST PITTSFIELD SALES B\n420747 - BERKSHR/TGP BOUSQUET SMS BERKSHIRE\n420102 - BERKSHR/TGP PITTSFIELD MA BERKSHIRE",256.101,null,"MLV 256C-101.1 to MLV 256C-102:  Pig Runs - Gauge/Cleaning tool\n--4/16/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.  \n420638 - BERKSHR/TGP WEST PITTSFIELD SALES B\n420747 - BERKSHR/TGP BOUSQUET SMS BERKSHIRE\n420102 - BERKSHR/TGP PITTSFIELD MA BERKSHIRE\n………………………………"]
["X25-1288887",null,"2026-04-17","2026-04-17",null,null,null,"MLV 256C-101.1 to MLV 256C-102","200","6","Pig Runs - Cal/IMU/MFL-A Combo","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.","420638 - BERKSHR/TGP WEST PITTSFIELD SALES B\n420747 - BERKSHR/TGP BOUSQUET SMS BERKSHIRE\n420102 - BERKSHR/TGP PITTSFIELD MA BERKSHIRE",256.101,null,"MLV 256C-101.1 to MLV 256C-102:  Pig Runs - Cal/IMU/MFL-A Combo\n--4/17/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.  \n420638 - BERKSHR/TGP WEST PITTSFIELD SALES B\n420747 - BERKSHR/TGP BOUSQUET SMS BERKSHIRE\n420102 - BERKSHR/TGP PITTSFIELD MA BERKSHIRE\n………………………………"]
["X25-1288907",null,"2026-06-01","2026-06-01",null,null,null,"MLV 256A-101.1 to MLV 256A-103","200","5","PIG RUNS - Gauge/Cleaning tool","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.","420638 - BERKSHR/TGP WEST PITTSFIELD SALES B\n420102 - BERKSHR/TGP PITTSFIELD MA BERKSHIRE\n420747 - BERKSHR/TGP BOUSQUET SMS BERKSHIRE\n420103 - BERKSHR/TGP NORTH ADAMS MA BERKSHIRE",256.101,null,"MLV 256A-101.1 to MLV 256A-103:  PIG RUNS - Gauge/Cleaning tool\n--6/1/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.  \n420638 - BERKSHR/TGP WEST PITTSFIELD SALES B\n420102 - BERKSHR/TGP PITTSFIELD MA BERKSHIRE\n420747 - BERKSHR/TGP BOUSQUET SMS BERKSHIRE\n420103 - BERKSHR/TGP NORTH ADAMS MA BERKSHIRE\n………………………………"]
["X25-1288909",null,"2026-06-04","2026-06-04",null,null,null,"MLV 256A-101.1 to MLV 256A-103","200","5","PIG RUNS - Cal/IMU","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.","420638 - BERKSHR/TGP WEST PITTSFIELD SALES B\n420102 - BERKSHR/TGP PITTSFIELD MA BERKSHIRE\n420747 - BERKSHR/TGP BOUSQUET SMS BERKSHIRE\n420103 - BERKSHR/TGP NORTH ADAMS MA BERKSHIRE",256.101,null,"MLV 256A-101.1 to MLV 256A-103:  PIG RUNS - Cal/IMU\n--6/4/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.  \n420638 - BERKSHR/TGP WEST PITTSFIELD SALES B\n420102 - BERKSHR/TGP PITTSFIELD MA BERKSHIRE\n420747 - BERKSHR/TGP BOUSQUET SMS BERKSHIRE\n420103 - BERKSHR/TGP NORTH ADAMS MA BERKSHIRE\n………………………………"]
["X25-1288910",null,"2026-06-04","2026-06-04",null,null,null,"MLV 256A-101.1 to MLV 256A-103","200","5","PIG RUNS - MFL-C","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.","420638 - BERKSHR/TGP WEST PITTSFIELD SALES B\n420102 - BERKSHR/TGP PITTSFIELD MA BERKSHIRE\n420747 - BERKSHR/TGP BOUSQUET SMS BERKSHIRE\n420103 - BERKSHR/TGP NORTH ADAMS MA BERKSHIRE",256.101,null,"MLV 256A-101.1 to MLV 256A-103:  PIG RUNS - MFL-C\n--6/4/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.  \n420638 - BERKSHR/TGP WEST PITTSFIELD SALES B\n420102 - BERKSHR/TGP PITTSFIELD MA BERKSHIRE\n420747 - BERKSHR/TGP BOUSQUET SMS BERKSHIRE\n420103 - BERKSHR/TGP NORTH ADAMS MA BERKSHIRE\n………………………………"]
["X25-1369748",null,"2026-06-22","2026-06-22",null,null,null,"MLV 257","200","4","ECDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,257,null,"MLV 257:  ECDA\n--6/22/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X24-1020199",null,"2026-05-04","2026-05-04",null,null,null,"MLV 260A-101.1 TO MLV 260A-103","200","6","Pig Runs - MFL-C 7/15/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420104 WESTFLD/TGP WESTFIELD MA HAMPDEN\n420401 HOLYOKE/TGP HOLYOKE MA 2 HAMPDEN\n420292 BERKSHR/TGP GREENFIELD MA HAMPSHIRE\n420106 EVRSRC/TGP GRANITE NORTHAMPTON MA H",260.11,null,"MLV 260A-101.1 TO MLV 260A-103:  Pig Runs - MFL-C 7/15/25\n--5/4/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420104 WESTFLD/TGP WESTFIELD MA HAMPDEN\n420401 HOLYOKE/TGP HOLYOKE MA 2 HAMPDEN\n420292 BERKSHR/TGP GREENFIELD MA HAMPSHIRE\n420106 EVRSRC/TGP GRANITE NORTHAMPTON MA H\n………………………………"]
["X25-1369750",null,"2026-08-05","2026-08-05",null,null,null,"MLV 265A-100","200","6","ECDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,265.10000000000002,null,"MLV 265A-100:  ECDA\n--8/5/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1288895",null,"2026-05-05","2026-05-05",null,null,null,"MLV 265E-101.1 to MLV 265E-104","200","6","PIG RUNS - Gauge/Cleaning tool","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420707 OCEAN ST/TGP PROVIDENCE\n55258 NSTAR/TGP SUTTON DELIVERY WORCHESTE\n420758 NARNGST/TGP LINCOLN SMS PROVIDENCE\n420910 NARNGST/TGP SMITHFIELD DELIVERY PRO\n420926 RISEC/TGP FPLE RISE PROVIDENCE\n420750 NARNGST/TGP CRANSTON SALES PROVIDENCE\n55784 RHOBIO/TGP SCITUATE RNG REC PRO\n55785 RHOBIO/TGP SCITUATE RNG BUY BACK PR",265.101,null,"MLV 265E-101.1 to MLV 265E-104:  PIG RUNS - Gauge/Cleaning tool\n--5/5/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  \n420707 OCEAN ST/TGP PROVIDENCE\n55258 NSTAR/TGP SUTTON DELIVERY WORCHESTE\n420758 NARNGST/TGP LINCOLN SMS PROVIDENCE\n420910 NARNGST/TGP SMITHFIELD DELIVERY PRO\n420926 RISEC/TGP FPLE RISE PROVIDENCE\n420750 NARNGST/TGP CRANSTON SALES PROVIDENCE\n55784 RHOBIO/TGP SCITUATE RNG REC PRO\n55785 RHOBIO/TGP SCITUATE RNG BUY BACK PR\n………………………………"]
["X25-1288898",null,"2026-05-06","2026-05-06",null,null,null,"MLV 265E-101.1 to MLV 265E-104","200","6","PIG RUNS - Cal/IMU","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420707 OCEAN ST/TGP PROVIDENCE\n55258 NSTAR/TGP SUTTON DELIVERY WORCHESTE\n420758 NARNGST/TGP LINCOLN SMS PROVIDENCE\n420910 NARNGST/TGP SMITHFIELD DELIVERY PRO\n420926 RISEC/TGP FPLE RISE PROVIDENCE\n420750 NARNGST/TGP CRANSTON SALES PROVIDENCE\n55784 RHOBIO/TGP SCITUATE RNG REC PRO\n55785 RHOBIO/TGP SCITUATE RNG BUY BACK PR",265.101,null,"MLV 265E-101.1 to MLV 265E-104:  PIG RUNS - Cal/IMU\n--5/6/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  \n420707 OCEAN ST/TGP PROVIDENCE\n55258 NSTAR/TGP SUTTON DELIVERY WORCHESTE\n420758 NARNGST/TGP LINCOLN SMS PROVIDENCE\n420910 NARNGST/TGP SMITHFIELD DELIVERY PRO\n420926 RISEC/TGP FPLE RISE PROVIDENCE\n420750 NARNGST/TGP CRANSTON SALES PROVIDENCE\n55784 RHOBIO/TGP SCITUATE RNG REC PRO\n55785 RHOBIO/TGP SCITUATE RNG BUY BACK PR\n………………………………"]
["X25-1288899",null,"2026-05-07","2026-05-07",null,null,null,"MLV 265E-101.1 to MLV 265E-104","200","6","PIG RUNS - MFL-A","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420707 OCEAN ST/TGP PROVIDENCE\n55258 NSTAR/TGP SUTTON DELIVERY WORCHESTE\n420758 NARNGST/TGP LINCOLN SMS PROVIDENCE\n420910 NARNGST/TGP SMITHFIELD DELIVERY PRO\n420926 RISEC/TGP FPLE RISE PROVIDENCE\n420750 NARNGST/TGP CRANSTON SALES PROVIDENCE\n55784 RHOBIO/TGP SCITUATE RNG REC PRO\n55785 RHOBIO/TGP SCITUATE RNG BUY BACK PR",265.101,null,"MLV 265E-101.1 to MLV 265E-104:  PIG RUNS - MFL-A\n--5/7/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  \n420707 OCEAN ST/TGP PROVIDENCE\n55258 NSTAR/TGP SUTTON DELIVERY WORCHESTE\n420758 NARNGST/TGP LINCOLN SMS PROVIDENCE\n420910 NARNGST/TGP SMITHFIELD DELIVERY PRO\n420926 RISEC/TGP FPLE RISE PROVIDENCE\n420750 NARNGST/TGP CRANSTON SALES PROVIDENCE\n55784 RHOBIO/TGP SCITUATE RNG REC PRO\n55785 RHOBIO/TGP SCITUATE RNG BUY BACK PR\n………………………………"]
["X25-1369752",null,"2026-07-27","2026-07-27",null,null,null,"MLV 265E-121","200","6","ECDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,265.12,null,"MLV 265E-121:  ECDA\n--7/27/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X24-1020284","***","2025-12-10","2025-12-10","Completed",null,null,"MLV 265E-201 to MLV 265E-202","200","6","Pig Runs - Cleaning / Gauge 12/10/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420758 NARNGST/TGP LINCOLN SMS PROVIDENCE",265.2,"------","***MLV 265E-201 to MLV 265E-202:  Pig Runs - Cleaning / Gauge 12/10/25\n***Completed\nThe following meters are available for nominations:\n420758 NARNGST/TGP LINCOLN SMS PROVIDENCE"]
["X24-1020336","***","2025-12-10","2025-12-10","Completed",null,null,"MLV 265E-201 to MLV 265E-202","200","6","Pig Runs - MFL-A / Cal / IMU Combo 12/10/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420758 NARNGST/TGP LINCOLN SMS PROVIDENCE",265.20999999999998,"------","***MLV 265E-201 to MLV 265E-202:  Pig Runs - MFL-A / Cal / IMU Combo 12/10/25\n***Completed\nThe following meters are available for nominations:\n420758 NARNGST/TGP LINCOLN SMS PROVIDENCE"]
["X25-438209","***","2025-09-02","2025-12-31","Project Change",null,"2025-12-19","Sta 267","200","6","Bldg A Controls Upgrade","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,267.00099999999998,"----end_date--------------model_loc--","***Sta 267:  Bldg A Controls Upgrade\n--9/2/25 through 12/31/25:  This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n***\nDate Change, Previously scheduled 9/2/25 to 12/19/25.\n………………………………"]
["X25-1385273",null,"2026-08-17","2026-08-21",null,null,null,"MLV 267-1 to MLV 270C","200","5","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,267.10000000000002,null,"MLV 267-1 to MLV 270C:  Anomaly Remediation\n--8/17/26 through 8/21/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1369754",null,"2026-10-05","2026-10-05",null,null,null,"MLV 268","200","6","DA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,268,null,"MLV 268:  DA\n--10/5/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X24-1020369","***","2025-12-17","2025-12-17","Completed",null,null,"MLV 268A-301A TO MLV 268A-302","200","6","Pig Runs - MFL-A / Cal / IMU Combo 12/18/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420111 BOSTN/TGP LEOMINSTER MA WORCHESTER",268.31,"------","***MLV 268A-301A TO MLV 268A-302:  Pig Runs - MFL-A / Cal / IMU Combo 12/18/25\n***Completed\nThe following meters are available for nominations:\n420111 BOSTN/TGP LEOMINSTER MA WORCHESTER"]
["X25-1406733",null,"2025-12-17","2025-12-18",null,null,null,"Sta. 270B Pelham","200","6","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,270,null,"Sta. 270B Pelham:  Annual ESD Test\n--12/17/25 through 12/18/25:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X24-847658",null,"2026-04-03","2026-04-21",null,null,null,"MLV 270C-103 to MLV 270C-104","200","6","Meter Station Upgrade (Meter Peabody PIN 420658)","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","420658 MMWEC/TGP PEABODY SALES ESSEX",270.10000000000002,null,"MLV 270C-103 to MLV 270C-104:  Meter Station Upgrade (Meter Peabody PIN 420658)\n--4/3/26 through 4/21/26:  This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.  \n420658 MMWEC/TGP PEABODY SALES ESSEX\n………………………………"]
["X25-1369755",null,"2026-08-31","2026-08-31",null,null,null,"MLV 270A-100","200","6","ECDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,270.10000000000002,null,"MLV 270A-100:  ECDA\n--8/31/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1369758",null,"2026-08-17","2026-08-17",null,null,null,"MLV 270C-1100","200","6","ECDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,270.11,null,"MLV 270C-1100:  ECDA\n--8/17/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1369757",null,"2026-09-10","2026-09-10",null,null,null,"MLV 270C-111","200","6","ECDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,270.11,null,"MLV 270C-111:  ECDA\n--9/10/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1288911",null,"2026-06-16","2026-06-16",null,null,null,"MLV 270C-301 to MLV 270C-302","200","6","Pig Run - Gauge/Cleaning tool","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.","420848 - WAKEFLD/TGP WAKEFIELD SALES ESSEX\n412513 - CONSTGEN/TGP DISTRIGAS RECEIPT MIDD",270.30099999999999,null,"MLV 270C-301 to MLV 270C-302:  Pig Run - Gauge/Cleaning tool\n--6/16/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.  \n420848 - WAKEFLD/TGP WAKEFIELD SALES ESSEX\n412513 - CONSTGEN/TGP DISTRIGAS RECEIPT MIDD\n………………………………"]
["X25-1288914",null,"2026-06-17","2026-06-17",null,null,null,"MLV 270C-301 to MLV 270C-302","200","6","Pig Run - Cal/IMU/MFL-A Combo","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.","420848 - WAKEFLD/TGP WAKEFIELD SALES ESSEX\n412513 - CONSTGEN/TGP DISTRIGAS RECEIPT MIDD",270.30099999999999,null,"MLV 270C-301 to MLV 270C-302:  Pig Run - Cal/IMU/MFL-A Combo\n--6/17/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.  \n420848 - WAKEFLD/TGP WAKEFIELD SALES ESSEX\n412513 - CONSTGEN/TGP DISTRIGAS RECEIPT MIDD\n………………………………"]
["X25-1288742",null,"2026-03-24","2026-03-24",null,null,null,"MLV 270C-501 to MLV 270C-502","200","6","Pig Runs - Gauge/Cleaning tool - 3/24/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.","420935 BOSTN/TGP DANVERS ESSES\n420138 BOSTN/TGP WENHAM MA ESSEX\n420323 BOSTN/TGP ESSEX MA ESSEX\n420119 BOSTN/TGP GLOUCHESTER MA ESSEX",270.5,null,"MLV 270C-501 to MLV 270C-502:  Pig Runs - Gauge/Cleaning tool - 3/24/26\n--3/24/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.  \n420935 BOSTN/TGP DANVERS ESSES\n420138 BOSTN/TGP WENHAM MA ESSEX\n420323 BOSTN/TGP ESSEX MA ESSEX\n420119 BOSTN/TGP GLOUCHESTER MA ESSEX\n………………………………"]
["X25-1288744",null,"2026-03-25","2026-03-25",null,null,null,"MLV 270C-501 to MLV 270C-502","200","6","Pig Runs - Cal/IMU - 3/25/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.","420935 BOSTN/TGP DANVERS ESSES\n420138 BOSTN/TGP WENHAM MA ESSEX\n420323 BOSTN/TGP ESSEX MA ESSEX\n420119 BOSTN/TGP GLOUCHESTER MA ESSEX",270.51,null,"MLV 270C-501 to MLV 270C-502:  Pig Runs - Cal/IMU - 3/25/26\n--3/25/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.  \n420935 BOSTN/TGP DANVERS ESSES\n420138 BOSTN/TGP WENHAM MA ESSEX\n420323 BOSTN/TGP ESSEX MA ESSEX\n420119 BOSTN/TGP GLOUCHESTER MA ESSEX\n………………………………"]
["X25-1288750",null,"2026-03-27","2026-03-27",null,null,null,"MLV 270C-501 to MLV 270C-502","200","6","Pig Runs - MFL-C - 3/27/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.","420935 BOSTN/TGP DANVERS ESSES\n420138 BOSTN/TGP WENHAM MA ESSEX\n420323 BOSTN/TGP ESSEX MA ESSEX\n420119 BOSTN/TGP GLOUCHESTER MA ESSEX",270.52,null,"MLV 270C-501 to MLV 270C-502:  Pig Runs - MFL-C - 3/27/26\n--3/27/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.  \n420935 BOSTN/TGP DANVERS ESSES\n420138 BOSTN/TGP WENHAM MA ESSEX\n420323 BOSTN/TGP ESSEX MA ESSEX\n420119 BOSTN/TGP GLOUCHESTER MA ESSEX\n………………………………"]
["X25-1288735",null,"2026-03-17","2026-03-17",null,null,null,"MLV 270B-601 to EOL","200","6","Gauge/Cleaning tool: 3/17/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.","421025 - EVRSRC/TGP WYETH GII ESSEX",270.601,null,"MLV 270B-601 to EOL:  Gauge/Cleaning tool: 3/17/26\n--3/17/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.  \n421025 - EVRSRC/TGP WYETH GII ESSEX\n………………………………"]
["X25-1288740",null,"2026-03-18","2026-03-18",null,null,null,"MLV 270B-601 to EOL","200","6","Cal/IMU/MFL-A Combo: 3/18/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.","421025 - EVRSRC/TGP WYETH GII ESSEX",270.601,null,"MLV 270B-601 to EOL:  Cal/IMU/MFL-A Combo: 3/18/26\n--3/18/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.  \n421025 - EVRSRC/TGP WYETH GII ESSEX\n………………………………"]
["X25-1369759",null,"2026-09-21","2026-09-21",null,null,null,"MLV 273","200","6","ECDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,273,null,"MLV 273:  ECDA\n--9/21/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1479893","***","2025-12-15","2025-12-16","Completed",null,null,"Sta 303","300","4","Unit 1A - Lubrication Pump","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,303.00099999999998,"------","***Sta 303:  Unit 1A - Lubrication Pump\n***Completed"]
["X25-1385274",null,"2026-06-01","2026-06-05",null,null,null,"MLV 313A-101 to MLV 313A-4010A","300","5","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,313.5,null,"MLV 313A-101 to MLV 313A-4010A:  Anomaly Remediation\n--6/1/26 through 6/5/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1421698","***","2025-12-11","2025-12-11","Completed",null,null,"Sta 315","300","4","Station Software Updates - UPS Install - Catalyst Cleaning","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,315,"------","***Sta 315:  Station Software Updates - UPS Install - Catalyst Cleaning\n***Completed"]
["X25-1369746",null,"2026-06-08","2026-06-08",null,null,null,"MLV 317-1 to MLV 319-1","300","4","SCCDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,317.10000000000002,null,"MLV 317-1 to MLV 319-1:  SCCDA\n--6/8/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1320304",null,"2026-06-09","2026-06-09",null,null,null,"MLV 325-1 to MLV 329-1","300","5","Pig runs - Cleaning/Gauge 6/10/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420410 ELIZTOWN/TGP SUSSEX NJ SUSSEX\n420450 ELIZTOWN/TGP VERNON NJ SUSSEX\n420608 NJ NATGS/TGP NEW CLINTON ROAD NJ BE\n420339 PSEG/TGP WEST MILFORD NJ PASSAIC\n420516 PSEG/TGP RINGWOOD NJ PASSAIC\n420226 PSEG/TGP RAMSEY NJ BERGEN",325.10000000000002,null,"MLV 325-1 to MLV 329-1:  Pig runs - Cleaning/Gauge 6/10/26\n--6/9/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  \n420410 ELIZTOWN/TGP SUSSEX NJ SUSSEX\n420450 ELIZTOWN/TGP VERNON NJ SUSSEX\n420608 NJ NATGS/TGP NEW CLINTON ROAD NJ BE\n420339 PSEG/TGP WEST MILFORD NJ PASSAIC\n420516 PSEG/TGP RINGWOOD NJ PASSAIC\n420226 PSEG/TGP RAMSEY NJ BERGEN\n………………………………"]
["X25-1428325",null,"2026-06-09","2026-06-09",null,null,null,"MLV 325-1 to MLV 329-1","300","5","Pig runs - Gauge/Cleaning","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420410 ELIZTOWN/TGP SUSSEX NJ SUSSEX\n420450 ELIZTOWN/TGP VERNON NJ SUSSEX\n420608 NJ NATGS/TGP NEW CLINTON ROAD NJ BE\n420339 PSEG/TGP WEST MILFORD NJ PASSAIC\n420516 PSEG/TGP RINGWOOD NJ PASSAIC\n420226 PSEG/TGP RAMSEY NJ BERGEN",325.10000000000002,null,"MLV 325-1 to MLV 329-1:  Pig runs - Gauge/Cleaning\n--6/9/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  \n420410 ELIZTOWN/TGP SUSSEX NJ SUSSEX\n420450 ELIZTOWN/TGP VERNON NJ SUSSEX\n420608 NJ NATGS/TGP NEW CLINTON ROAD NJ BE\n420339 PSEG/TGP WEST MILFORD NJ PASSAIC\n420516 PSEG/TGP RINGWOOD NJ PASSAIC\n420226 PSEG/TGP RAMSEY NJ BERGEN\n………………………………"]
["X25-1428331",null,"2026-06-11","2026-06-11",null,null,null,"MLV 325-1 to MLV 329-1","300","5","Pig runs - CAL/IMU/MFL-C","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420410 ELIZTOWN/TGP SUSSEX NJ SUSSEX\n420450 ELIZTOWN/TGP VERNON NJ SUSSEX\n420608 NJ NATGS/TGP NEW CLINTON ROAD NJ BE\n420339 PSEG/TGP WEST MILFORD NJ PASSAIC\n420516 PSEG/TGP RINGWOOD NJ PASSAIC\n420226 PSEG/TGP RAMSEY NJ BERGEN",325.10000000000002,null,"MLV 325-1 to MLV 329-1:  Pig runs - CAL/IMU/MFL-C\n--6/11/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  \n420410 ELIZTOWN/TGP SUSSEX NJ SUSSEX\n420450 ELIZTOWN/TGP VERNON NJ SUSSEX\n420608 NJ NATGS/TGP NEW CLINTON ROAD NJ BE\n420339 PSEG/TGP WEST MILFORD NJ PASSAIC\n420516 PSEG/TGP RINGWOOD NJ PASSAIC\n420226 PSEG/TGP RAMSEY NJ BERGEN\n………………………………"]
["X25-1320305",null,"2026-06-11","2026-06-11",null,null,null,"MLV 325-1 to MLV 329-1","300","5","Pig runs - Cal / IMU 6/11/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420410 ELIZTOWN/TGP SUSSEX NJ SUSSEX\n420450 ELIZTOWN/TGP VERNON NJ SUSSEX\n420608 NJ NATGS/TGP NEW CLINTON ROAD NJ BE\n420339 PSEG/TGP WEST MILFORD NJ PASSAIC\n420516 PSEG/TGP RINGWOOD NJ PASSAIC\n420226 PSEG/TGP RAMSEY NJ BERGEN",325.10000000000002,null,"MLV 325-1 to MLV 329-1:  Pig runs - Cal / IMU 6/11/26\n--6/11/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  \n420410 ELIZTOWN/TGP SUSSEX NJ SUSSEX\n420450 ELIZTOWN/TGP VERNON NJ SUSSEX\n420608 NJ NATGS/TGP NEW CLINTON ROAD NJ BE\n420339 PSEG/TGP WEST MILFORD NJ PASSAIC\n420516 PSEG/TGP RINGWOOD NJ PASSAIC\n420226 PSEG/TGP RAMSEY NJ BERGEN\n………………………………"]
["X25-1320372",null,"2026-10-19","2026-10-19",null,null,null,"MLV 325-1 to MLV 329-1","300","5","Pig runs - Cleaning/Gauge 6/10/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420410 ELIZTOWN/TGP SUSSEX NJ SUSSEX\n420450 ELIZTOWN/TGP VERNON NJ SUSSEX\n420608 NJ NATGS/TGP NEW CLINTON ROAD NJ BE\n420339 PSEG/TGP WEST MILFORD NJ PASSAIC\n420516 PSEG/TGP RINGWOOD NJ PASSAIC\n420226 PSEG/TGP RAMSEY NJ BERGEN",325.10000000000002,null,"MLV 325-1 to MLV 329-1:  Pig runs - Cleaning/Gauge 6/10/26\n--10/19/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  \n420410 ELIZTOWN/TGP SUSSEX NJ SUSSEX\n420450 ELIZTOWN/TGP VERNON NJ SUSSEX\n420608 NJ NATGS/TGP NEW CLINTON ROAD NJ BE\n420339 PSEG/TGP WEST MILFORD NJ PASSAIC\n420516 PSEG/TGP RINGWOOD NJ PASSAIC\n420226 PSEG/TGP RAMSEY NJ BERGEN\n………………………………"]
["X25-1428332",null,"2026-10-19","2026-10-19",null,null,null,"MLV 325-1 to MLV 329-1","300","5","Pig runs - Cleaning Tool","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420410 ELIZTOWN/TGP SUSSEX NJ SUSSEX\n420450 ELIZTOWN/TGP VERNON NJ SUSSEX\n420608 NJ NATGS/TGP NEW CLINTON ROAD NJ BE\n420339 PSEG/TGP WEST MILFORD NJ PASSAIC\n420516 PSEG/TGP RINGWOOD NJ PASSAIC\n420226 PSEG/TGP RAMSEY NJ BERGEN",325.10000000000002,null,"MLV 325-1 to MLV 329-1:  Pig runs - Cleaning Tool\n--10/19/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  \n420410 ELIZTOWN/TGP SUSSEX NJ SUSSEX\n420450 ELIZTOWN/TGP VERNON NJ SUSSEX\n420608 NJ NATGS/TGP NEW CLINTON ROAD NJ BE\n420339 PSEG/TGP WEST MILFORD NJ PASSAIC\n420516 PSEG/TGP RINGWOOD NJ PASSAIC\n420226 PSEG/TGP RAMSEY NJ BERGEN\n………………………………"]
["X25-1428333",null,"2026-10-20","2026-10-20",null,null,null,"MLV 325-1 to MLV 329-1","300","5","Pig runs - EMAT","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420410 ELIZTOWN/TGP SUSSEX NJ SUSSEX\n420450 ELIZTOWN/TGP VERNON NJ SUSSEX\n420608 NJ NATGS/TGP NEW CLINTON ROAD NJ BE\n420339 PSEG/TGP WEST MILFORD NJ PASSAIC\n420516 PSEG/TGP RINGWOOD NJ PASSAIC\n420226 PSEG/TGP RAMSEY NJ BERGEN",325.10000000000002,null,"MLV 325-1 to MLV 329-1:  Pig runs - EMAT\n--10/20/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  \n420410 ELIZTOWN/TGP SUSSEX NJ SUSSEX\n420450 ELIZTOWN/TGP VERNON NJ SUSSEX\n420608 NJ NATGS/TGP NEW CLINTON ROAD NJ BE\n420339 PSEG/TGP WEST MILFORD NJ PASSAIC\n420516 PSEG/TGP RINGWOOD NJ PASSAIC\n420226 PSEG/TGP RAMSEY NJ BERGEN\n………………………………"]
["X25-1320306",null,"2026-10-20","2026-10-20",null,null,null,"MLV 325-1 to MLV 329-1","300","5","Pig runs - EMAT 10/20/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420410 ELIZTOWN/TGP SUSSEX NJ SUSSEX\n420450 ELIZTOWN/TGP VERNON NJ SUSSEX\n420608 NJ NATGS/TGP NEW CLINTON ROAD NJ BE\n420339 PSEG/TGP WEST MILFORD NJ PASSAIC\n420516 PSEG/TGP RINGWOOD NJ PASSAIC\n420226 PSEG/TGP RAMSEY NJ BERGEN",325.10000000000002,null,"MLV 325-1 to MLV 329-1:  Pig runs - EMAT 10/20/26\n--10/20/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  \n420410 ELIZTOWN/TGP SUSSEX NJ SUSSEX\n420450 ELIZTOWN/TGP VERNON NJ SUSSEX\n420608 NJ NATGS/TGP NEW CLINTON ROAD NJ BE\n420339 PSEG/TGP WEST MILFORD NJ PASSAIC\n420516 PSEG/TGP RINGWOOD NJ PASSAIC\n420226 PSEG/TGP RAMSEY NJ BERGEN\n………………………………"]
["X25-1369761","***","2026-04-27","2026-04-27","Project Change",null,null,"MLV 335-1","300","5","ECDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,328,"--------------prl----model_loc--","***MLV 335-1:  ECDA\n--4/27/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n***Project Change\n………………………………"]
["X25-1369760",null,"2026-05-07","2026-05-07",null,null,null,"MLV 328","300","5","ECDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,328,null,"MLV 328:  ECDA\n--5/7/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1385270",null,"2026-04-06","2026-06-12",null,null,null,"MLV 336-1 to MLV 356-1","300","4","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,336.1,null,"MLV 336-1 to MLV 356-1:  Anomaly Remediation\n--4/6/26 through 6/12/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1369765",null,"2026-04-13","2026-04-13",null,null,null,"MLV 345-1","300","5","ECDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,345.1,null,"MLV 345-1:  ECDA\n--4/13/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-123495","***","2025-12-18","2025-12-18","Project Change","2025-12-16","2025-12-16","Sta 500-1 to Sta 823 (MLV 507-1)","500","L","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420373 TRNSCO/TGP KINDER LA EXCH (BI 1\n420708 ELIZ NG/TGP GRANT LA SALES ALLEN\n420436 VERNON/TGP PITKIN LA VERNON\n420793 ELIZ NG/TGP J R FRANKS 1 VERNON\n420388 PROVNCAL/TGP PROVENCAL LA NATCHITOC",500.1,"--start_date--end_date--------------model_loc--","***Sta 500-1 to Sta 823 (MLV 507-1):  Pig Run - Maintenance\n--12/18/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420373 TRNSCO/TGP KINDER LA EXCH (BI 1\n420708 ELIZ NG/TGP GRANT LA SALES ALLEN\n420436 VERNON/TGP PITKIN LA VERNON\n420793 ELIZ NG/TGP J R FRANKS 1 VERNON\n420388 PROVNCAL/TGP PROVENCAL LA NATCHITOC\n***\nDate Change, Previously scheduled 12/16/25.\n………………………………"]
["X25-1389565",null,"2026-09-07","2026-09-11",null,null,null,"MLV 507F-101 to MLV 507F-104","500","L","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,507.1,null,"MLV 507F-101 to MLV 507F-104:  Anomaly Remediation\n--9/7/26 through 9/11/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1389563",null,"2026-09-14","2026-09-25",null,null,null,"MLV 507F-101 to MLV 507F-104","500","L","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,507.1,null,"MLV 507F-101 to MLV 507F-104:  Anomaly Remediation\n--9/14/26 through 9/25/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1367826",null,"2026-04-18","2026-04-22",null,null,null,"MLV 516 to Sta 523","100","L","Pig Run - Cleaning / Gauge 4/18/26 to 4/22/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","412705 MTBB/TGP MARTIN WELL 1 ST MARY\n412189 CRTXLIG/TGP DOG LAKE TERREBONNE",516.00099999999998,null,"MLV 516 to Sta 523:  Pig Run - Cleaning / Gauge 4/18/26 to 4/22/26\n--4/18/26 through 4/22/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  \n412705 MTBB/TGP MARTIN WELL 1 ST MARY\n412189 CRTXLIG/TGP DOG LAKE TERREBONNE\n………………………………"]
["X25-1367829","***","2026-04-24","2026-04-24","Project Change",null,null,"MLV 516 to Sta 523","500","L","Pig Run - MFL-A 4/24/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","412705 MTBB/TGP MARTIN WELL 1 ST MARY\n412189 CRTXLIG/TGP DOG LAKE TERREBONNE",516.00199999999995,"--------------prl----model_loc--","***MLV 516 to Sta 523:  Pig Run - MFL-A 4/24/26\n--4/24/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  \n412705 MTBB/TGP MARTIN WELL 1 ST MARY\n412189 CRTXLIG/TGP DOG LAKE TERREBONNE\n***Project Change\n………………………………"]
["X25-1022086",null,"2025-08-25","2026-03-31",null,null,null,"Sta 530","500","L","Unit 1A - Bearings","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,530.00099999999998,null,"Sta 530:  Unit 1A - Bearings\n--8/25/25 through 3/31/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-1094319",null,"2025-08-26","2026-03-31",null,null,null,"Sta 530","500","L","Unit 2A - Bearings","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,530.00199999999995,null,"Sta 530:  Unit 2A - Bearings\n--8/26/25 through 3/31/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-691135",null,"2025-06-09","2026-12-31",null,null,null,"Sta 530","500","L","Unit 3A - Crankshaft Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,530.00300000000004,null,"Sta 530:  Unit 3A - Crankshaft Replacement\n--6/9/25 through 12/31/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-1022087",null,"2025-08-25","2025-12-12",null,null,null,"Sta 530","500","L","Unit 4A - Piston","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,530.00400000000002,null,"Sta 530:  Unit 4A - Piston\n--8/25/25 through 12/12/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-691139",null,"2025-06-09","2026-12-31",null,null,null,"Sta 530","500","L","Unit 5A - Top-End Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,530.005,null,"Sta 530:  Unit 5A - Top-End Overhaul\n--6/9/25 through 12/31/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-1237337",null,"2025-10-06","2026-03-31",null,null,null,"Sta 530","500","L","Unit 6A - Bearings","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,530.00599999999997,null,"Sta 530:  Unit 6A - Bearings\n--10/6/25 through 3/31/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1237339",null,"2025-10-06","2026-03-31",null,null,null,"Sta 530","500","L","Unit 7A - Bearings","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,530.00699999999995,null,"Sta 530:  Unit 7A - Bearings\n--10/6/25 through 3/31/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1162179",null,"2025-09-23","2025-12-31",null,null,null,"Sta 530","500","L","Unit 8A - Power Cylinders","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,530.00800000000004,null,"Sta 530:  Unit 8A - Power Cylinders\n--9/23/25 through 12/31/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-352306",null,"2025-03-25","2026-03-27",null,null,null,"Sta 534","500","L","Unit 6A - Piston Liner & Unloader Replacements","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,534.00599999999997,null,"Sta 534:  Unit 6A - Piston Liner & Unloader Replacements\n--3/25/25 through 3/27/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-596569","***","2025-05-20","2026-01-09","Project Change",null,"2026-12-31","Sta 534","500","L","Unit 7A - Piston / Liner","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,534.00699999999995,"----end_date--------------model_loc--","***Sta 534:  Unit 7A - Piston / Liner\n--5/20/25 through 1/9/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 5/20/25 to 12/31/26.\n………………………………"]
["X25-1389380",null,"2026-06-01","2026-06-15",null,null,null,"MLV 534-2 to MLV 538-2","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,534.20000000000005,null,"MLV 534-2 to MLV 538-2:  Anomaly Remediation\n--6/1/26 through 6/15/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1389568",null,"2026-06-16","2026-06-30",null,null,null,"MLV 534-2 to MLV 538-2","500","0","SCCDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,534.20000000000005,null,"MLV 534-2 to MLV 538-2:  SCCDA\n--6/16/26 through 6/30/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1360637","***","2025-12-22","2025-12-22","Added",null,null,"Sta 538","500","1","Unit 1A - Replace Air Filter Housing","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,538.00099999999998,"------","***Sta 538:  Unit 1A - Replace Air Filter Housing\n--12/22/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***Added\n………………………………"]
["X25-1360640","***","2025-12-22","2025-12-22","Added",null,null,"Sta 538","500","1","Unit 3A - Replace Air Filter Housing","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,538.00300000000004,"------","***Sta 538:  Unit 3A - Replace Air Filter Housing\n--12/22/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***Added\n………………………………"]
["X25-1360641","***","2025-12-23","2025-12-23","Added",null,null,"Sta 538","500","1","Unit 5A - Replace Air Filter Housing","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,538.005,"------","***Sta 538:  Unit 5A - Replace Air Filter Housing\n--12/23/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***Added\n………………………………"]
["X25-1360644","***","2025-12-18","2025-12-18","Added",null,null,"Sta 538","500","1","Unit 7A - Replace Air Filter Housing","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,538.00699999999995,"------","***Sta 538:  Unit 7A - Replace Air Filter Housing\n--12/18/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***Added\n………………………………"]
["X25-1360646","***","2025-12-19","2025-12-19","Added",null,null,"Sta 538","500","1","Unit 8A - Replace Air Filter Housing","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,538.00800000000004,"------","***Sta 538:  Unit 8A - Replace Air Filter Housing\n--12/19/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***Added\n………………………………"]
["X25-1389376",null,"2026-07-20","2026-08-07",null,null,null,"MLV 538-2 to MLV 542-2","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,538.20000000000005,null,"MLV 538-2 to MLV 542-2:  Anomaly Remediation\n--7/20/26 through 8/7/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1389222","***","2025-12-15","2025-12-16","Completed",null,null,"Sta 542","500","1","Unit 4A - Cooler Fan","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,542.00400000000002,"------","***Sta 542:  Unit 4A - Cooler Fan\n***Completed"]
["X25-672314","***","2025-11-03","2025-12-12","Completed",null,null,"Sta 546","500","1","Unit 4A - Engine and Compressor Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,546.00400000000002,"------","***Sta 546:  Unit 4A - Engine and Compressor Overhaul\n***Completed"]
["X25-1499002","***","2025-12-18","2025-12-18","Added",null,null,"Sta 546","500","1","Unit 5A - Safety Device Checks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,546.005,"------","***Sta 546:  Unit 5A - Safety Device Checks\n--12/18/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***Added\n………………………………"]
["X25-840628",null,"2025-07-14","2026-01-31",null,null,null,"Sta 546","500","1","Unit 7A - Metal in Oil","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,546.00699999999995,null,"Sta 546:  Unit 7A - Metal in Oil\n--7/14/25 through 1/31/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-1411337",null,"2026-10-05","2026-10-09",null,null,null,"Sta 550 Hamilton","500","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,550,null,"Sta 550 Hamilton:  Annual ESD Test\n--10/5/26 through 10/9/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-500868",null,"2025-08-25","2025-12-12",null,null,null,"Sta 550","500","1","Unit 2A - Compressor Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,550.00199999999995,null,"Sta 550:  Unit 2A - Compressor Overhaul\n--8/25/25 through 12/12/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-431275",null,"2026-03-02","2026-03-20",null,null,null,"Sta 550","500","1","Unit 3A - Turbocharger Exchange","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,550.00300000000004,null,"Sta 550:  Unit 3A - Turbocharger Exchange\n--3/2/26 through 3/20/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-1162197",null,"2026-03-10","2026-03-10",null,null,null,"MLV 550-1 to MLV 546-1","500","1","Pig Runs - Cleaning / Gauge 3/10/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,550.1,null,"MLV 550-1 to MLV 546-1:  Pig Runs - Cleaning / Gauge 3/10/26\n--3/10/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1389366",null,"2026-04-13","2026-04-17",null,null,null,"MLV 550-1 to MLV 555-1","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,550.1,null,"MLV 550-1 to MLV 555-1:  Anomaly Remediation\n--4/13/26 through 4/17/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1389369",null,"2026-04-20","2026-04-24",null,null,null,"MLV 550-1 to MLV 555-1","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,550.1,null,"MLV 550-1 to MLV 555-1:  Anomaly Remediation\n--4/20/26 through 4/24/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1162192",null,"2026-03-12","2026-03-12",null,null,null,"MLV 550-1 to MLV 546-1","500","1","Pig Runs - CAL / IMU 3/12/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,550.12,null,"MLV 550-1 to MLV 546-1:  Pig Runs - CAL / IMU 3/12/26\n--3/12/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1162198",null,"2026-03-17","2026-03-17",null,null,null,"MLV 550-1 to MLV 546-1","500","1","Pig Runs - MFL-C 3/17/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,550.14,null,"MLV 550-1 to MLV 546-1:  Pig Runs - MFL-C 3/17/26\n--3/17/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1162199",null,"2026-03-19","2026-03-19",null,null,null,"MLV 550-1 to MLV 546-1","500","1","Pig Runs - EMAT 3/19/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,550.16,null,"MLV 550-1 to MLV 546-1:  Pig Runs - EMAT 3/19/26\n--3/19/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1389350",null,"2026-10-05","2026-10-23",null,null,null,"MLV 550-2 to MLV 555-2","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,550.20000000000005,null,"MLV 550-2 to MLV 555-2:  Anomaly Remediation\n--10/5/26 through 10/23/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1389387","***","2026-04-27","2026-05-01","Project Change",null,null,"MLV 552-3 to MLV 555-3","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,552.29999999999995,"--------------prl----model_loc--","***MLV 552-3 to MLV 555-3:  Anomaly Remediation\n--4/27/26 through 5/1/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n***Project Change\n………………………………"]
["X25-1411671",null,"2026-04-21","2026-04-24",null,null,null,"Sta 555 Collinwood","500","1","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,555,null,"Sta 555 Collinwood:  Annual ESD Test & Maintenance\n--4/21/26 through 4/24/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1479838","***","2026-09-28","2026-10-09","Completed",null,null,"Sta 555",null,null,"Unit 1B - Juction Box Rewire & Unit Valves","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,555.01700000000005,"------","***Sta 555:  Unit 1B - Juction Box Rewire & Unit Valves\n***Completed"]
["X25-1479836","***","2026-10-05","2026-10-09","Completed",null,null,"Sta 555",null,null,"Unit 1B - Annual Safety Device Checks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,555.01700000000005,"------","***Sta 555:  Unit 1B - Annual Safety Device Checks\n***Completed"]
["X25-1389371",null,"2026-03-16","2026-04-03",null,null,null,"MLV 555-1L to MLV 558-1R","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,555.1,null,"MLV 555-1L to MLV 558-1R:  Anomaly Remediation\n--3/16/26 through 4/3/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1389372",null,"2026-04-06","2026-04-10",null,null,null,"MLV 555-1L to MLV 558-1R","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,555.1,null,"MLV 555-1L to MLV 558-1R:  Anomaly Remediation\n--4/6/26 through 4/10/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-996855",null,"2026-02-17","2026-02-17",null,null,null,"MLV 555-2 to MLV 559-2","500","1","Pig Runs - Cleaning / Gauge 2/17/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,555.20000000000005,null,"MLV 555-2 to MLV 559-2:  Pig Runs - Cleaning / Gauge 2/17/26\n--2/17/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-996861",null,"2026-02-19","2026-02-19",null,null,null,"MLV 555-2 to MLV 559-2","500","1","Pig Runs - CAL / IMU 2/19/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,555.21,null,"MLV 555-2 to MLV 559-2:  Pig Runs - CAL / IMU 2/19/26\n--2/19/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-996862",null,"2026-02-24","2026-02-24",null,null,null,"MLV 555-2 to MLV 559-2","500","1","Pig Runs - MFL-C 2/24/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,555.22,null,"MLV 555-2 to MLV 559-2:  Pig Runs - MFL-C 2/24/26\n--2/24/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-996863",null,"2026-02-26","2026-02-26",null,null,null,"MLV 555-2 to MLV 559-2","500","1","Pig Runs - EMAT 2/26/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,555.23,null,"MLV 555-2 to MLV 559-2:  Pig Runs - EMAT 2/26/26\n--2/26/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1479662",null,"2026-06-02","2026-06-02",null,null,null,"MLV 557-3 to MLV 559-3","500","1","Pig Runs - Cleaning / Gauge 6/2/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,557.29999999999995,null,"MLV 557-3 to MLV 559-3:  Pig Runs - Cleaning / Gauge 6/2/26\n--6/2/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1479665",null,"2026-06-04","2026-06-04",null,null,null,"MLV 557-3 to MLV 559-3","500","1","Pig Runs - Cal / IMU & MFL-A 6/4/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,557.29999999999995,null,"MLV 557-3 to MLV 559-3:  Pig Runs - Cal / IMU & MFL-A 6/4/26\n--6/4/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1380244",null,"2026-12-08","2026-12-08",null,null,null,"MLV 559-1 to 565-1","500","1","Pig Run - Gauge","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,559.1,null,"MLV 559-1 to 565-1:  Pig Run - Gauge\n--12/8/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1380248",null,"2026-12-10","2026-12-10",null,null,null,"MLV 559-1 to 565-1","500","1","Pig Run - EMAT","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,559.1,null,"MLV 559-1 to 565-1:  Pig Run - EMAT\n--12/10/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1380221","***","2025-12-10","2025-12-10","Completed",null,null,"MLV 559-2 to MLV 565-2","500","1","Pig Run - Gauge","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,559.20000000000005,"------","***MLV 559-2 to MLV 565-2:  Pig Run - Gauge\n***Completed"]
["X25-1380222","***","2025-12-12","2025-12-12","Completed",null,null,"MLV 559-2 to MLV 565-2","500","1","Pig Run - Caliper","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,559.20000000000005,"------","***MLV 559-2 to MLV 565-2:  Pig Run - Caliper\n***Completed"]
["X25-1380224","***","2025-12-16","2025-12-16","Completed",null,null,"MLV 559-2 to MLV 565-2","500","1","Pig Run - MFL","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,559.20000000000005,"------","***MLV 559-2 to MLV 565-2:  Pig Run - MFL\n***Completed"]
["X25-1380225","***","2025-12-20","2025-12-20","Project Change","2025-12-18","2025-12-18","MLV 559-2 to MLV 565-2","500","1","Pig Run - EMAT","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,559.20000000000005,"--start_date--end_date--------------model_loc--","***MLV 559-2 to MLV 565-2:  Pig Run - EMAT\n--12/20/25:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n***\nDate Change, Previously scheduled 12/18/25.\n………………………………"]
["X25-1389390",null,"2026-03-02","2026-03-20",null,null,null,"MLV 559-2 to MLV 565-2","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,559.20000000000005,null,"MLV 559-2 to MLV 565-2:  Anomaly Remediation\n--3/2/26 through 3/20/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1411725",null,"2026-06-02","2026-06-02",null,null,null,"Sta 563 Joelton","500","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,563,null,"Sta 563 Joelton:  Annual ESD Test\n--6/2/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1490251","***","2025-12-10","2025-12-10","Completed",null,null,"Sta 563","500","1","Unit 1A - Fuel Injectors","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,563.00099999999998,"------","***Sta 563:  Unit 1A - Fuel Injectors\n***Completed"]
["X25-1487481","***","2025-12-10","2025-12-10","Completed",null,null,"Sta 563 Joelton",null,null,"Unit 1A - Fuel Injector Swap","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,563.00099999999998,"------","***Sta 563 Joelton:  Unit 1A - Fuel Injector Swap\n***Completed"]
["X25-1250007",null,"2026-05-07","2026-05-07",null,null,null,"MLV 706-1 to MLV 700-1","100","0","Pig Run - Cleaning 5/7/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","412819 LOUISMID/TGP CONVERSE CENTRAL: RIP\n410031 ETX GAS/TGP EAST TX PLANT DEHY PANO",706.11,null,"MLV 706-1 to MLV 700-1:  Pig Run - Cleaning 5/7/26\n--5/7/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n412819 LOUISMID/TGP CONVERSE CENTRAL: RIP\n410031 ETX GAS/TGP EAST TX PLANT DEHY PANO\n………………………………"]
["X25-1250009",null,"2026-05-12","2026-05-12",null,null,null,"MLV 706-1 to MLV 700-1","100","0","Pig Run - Cleaning 5/12/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","412819 LOUISMID/TGP CONVERSE CENTRAL: RIP\n410031 ETX GAS/TGP EAST TX PLANT DEHY PANO",706.12,null,"MLV 706-1 to MLV 700-1:  Pig Run - Cleaning 5/12/26\n--5/12/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n412819 LOUISMID/TGP CONVERSE CENTRAL: RIP\n410031 ETX GAS/TGP EAST TX PLANT DEHY PANO\n………………………………"]
["X25-1250011",null,"2026-05-14","2026-05-14",null,null,null,"MLV 706-1 to MLV 700-1","100","0","Pig Run - Caliper 5/14/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","412819 LOUISMID/TGP CONVERSE CENTRAL: RIP\n410031 ETX GAS/TGP EAST TX PLANT DEHY PANO",706.13,null,"MLV 706-1 to MLV 700-1:  Pig Run - Caliper 5/14/26\n--5/14/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n412819 LOUISMID/TGP CONVERSE CENTRAL: RIP\n410031 ETX GAS/TGP EAST TX PLANT DEHY PANO\n………………………………"]
["X25-1389566",null,"2026-03-02","2026-03-13",null,null,null,"MLV 827-1 to MLV 834-1","800","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,827.1,null,"MLV 827-1 to MLV 834-1:  Anomaly Remediation\n--3/2/26 through 3/13/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1411914",null,"2026-09-29","2026-09-30",null,null,null,"Sta 834","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,834,null,"Sta 834:  Annual ESD Test\n--9/29/26 through 9/30/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1480003",null,"2026-05-05","2026-05-06",null,null,null,"Sta 834","800","1","Unit 1A - Replace Insulation Blanket","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,834.00099999999998,null,"Sta 834:  Unit 1A - Replace Insulation Blanket\n--5/5/26 through 5/6/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1480006",null,"2026-05-07","2026-05-08",null,null,null,"Sta 834","800","1","Unit 2A - Replace Insulation Blanket","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,834.00199999999995,null,"Sta 834:  Unit 2A - Replace Insulation Blanket\n--5/7/26 through 5/8/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1480008",null,"2026-05-12","2026-05-13",null,null,null,"Sta 834","800","1","Unit 3A - Replace Insulation Blanket","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,834.00300000000004,null,"Sta 834:  Unit 3A - Replace Insulation Blanket\n--5/12/26 through 5/13/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1479999",null,"2026-04-13","2026-04-17",null,null,null,"Sta 834","800","1","Unit 4A - Replace Lubrication System","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,834.00400000000002,null,"Sta 834:  Unit 4A - Replace Lubrication System\n--4/13/26 through 4/17/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1480009",null,"2026-05-14","2026-05-15",null,null,null,"Sta 834","800","1","Unit 4A - Replace Insulation Blanket","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,834.00400000000002,null,"Sta 834:  Unit 4A - Replace Insulation Blanket\n--5/14/26 through 5/15/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1480012",null,"2026-05-19","2026-05-20",null,null,null,"Sta 834","800","1","Unit 5A - Replace Insulation Blanket","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,834.005,null,"Sta 834:  Unit 5A - Replace Insulation Blanket\n--5/19/26 through 5/20/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1479988",null,"2026-09-21","2026-10-02",null,null,null,"Sta 834","800","1","unit 5A - Controls/Fuel System Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,834.005,null,"Sta 834:  unit 5A - Controls/Fuel System Upgrade\n--9/21/26 through 10/2/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X24-1186067",null,"2025-03-03","2026-01-02",null,null,null,"Sta 834","800","1","Unit 6A - Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,834.00599999999997,null,"Sta 834:  Unit 6A - Overhaul\n--3/3/25 through 1/2/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-1480014",null,"2026-05-21","2026-05-22",null,null,null,"Sta 834","800","1","Unit 6A - Replace Insulation Blanket","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,834.00599999999997,null,"Sta 834:  Unit 6A - Replace Insulation Blanket\n--5/21/26 through 5/22/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1480019",null,"2026-05-27","2026-05-28",null,null,null,"Sta 834","800","1","Unit 7A - Replace Insulation Blanket","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,834.00699999999995,null,"Sta 834:  Unit 7A - Replace Insulation Blanket\n--5/27/26 through 5/28/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1479985",null,"2026-06-26","2026-06-26",null,null,null,"Sta 834","800","1","Scrubber Filter Changeout","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,834.01,null,"Sta 834:  Scrubber Filter Changeout\n--6/26/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1479979",null,"2026-05-21","2026-05-21",null,null,null,"Sta 834 to Sta 827","800","L","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,834.1,null,"Sta 834 to Sta 827:  Maintenance Pig\n--5/21/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1179520",null,"2026-06-08","2026-06-10",null,null,null,"Sta 834 to Sta 827","800","L","Pig Run - Cleaning / Gauge 6/8/26 to 6/10/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420755 ATMOS TL/TGP LASALLE PARISH NEBO SA\n420447 PELICANG/TGP HARRISONBURG LA CATAHO",834.1,null,"Sta 834 to Sta 827:  Pig Run - Cleaning / Gauge 6/8/26 to 6/10/26\n--6/8/26 through 6/10/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420755 ATMOS TL/TGP LASALLE PARISH NEBO SA\n420447 PELICANG/TGP HARRISONBURG LA CATAHO\n………………………………"]
["X25-1479981",null,"2026-11-05","2026-11-05",null,null,null,"Sta 834 to Sta 827","800","L","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420755 ATMOS TL/TGP LASALLE PARISH NEBO SA\n420447 PELICANG/TGP HARRISONBURG LA CATAHO",834.1,null,"Sta 834 to Sta 827:  Maintenance Pig\n--11/5/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  \n420755 ATMOS TL/TGP LASALLE PARISH NEBO SA\n420447 PELICANG/TGP HARRISONBURG LA CATAHO\n………………………………"]
["X25-1179521",null,"2026-06-11","2026-06-11",null,null,null,"Sta 834 to Sta 827","800","L","Pig Run - BH Combo 6/11/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420755 ATMOS TL/TGP LASALLE PARISH NEBO SA\n420447 PELICANG/TGP HARRISONBURG LA CATAHO",834.12,null,"Sta 834 to Sta 827:  Pig Run - BH Combo 6/11/26\n--6/11/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420755 ATMOS TL/TGP LASALLE PARISH NEBO SA\n420447 PELICANG/TGP HARRISONBURG LA CATAHO\n………………………………"]
["X25-1179524",null,"2026-06-15","2026-06-15",null,null,null,"Sta 834 to Sta 827","800","L","Pig Run - BH Hard Spot 6/15/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420755 ATMOS TL/TGP LASALLE PARISH NEBO SA\n420447 PELICANG/TGP HARRISONBURG LA CATAHO",834.14,null,"Sta 834 to Sta 827:  Pig Run - BH Hard Spot 6/15/26\n--6/15/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  Potential secondary restrictions at the meter(s) may be at risk.\n420755 ATMOS TL/TGP LASALLE PARISH NEBO SA\n420447 PELICANG/TGP HARRISONBURG LA CATAHO\n………………………………"]
["X25-1411910",null,"2026-08-26","2026-08-26",null,null,null,"Sta 836A","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,836,null,"Sta 836A:  Annual ESD Test\n--8/26/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1411912",null,"2026-09-10","2026-09-10",null,null,null,"Sta 838","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,838,null,"Sta 838:  Annual ESD Test\n--9/10/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1411559",null,"2026-06-17","2026-06-17",null,null,null,"Sta 843 Isola","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,843,null,"Sta 843 Isola:  Annual ESD Test\n--6/17/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1411496",null,"2026-08-18","2026-08-20",null,null,null,"Sta 847 Coffeeville","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,847,null,"Sta 847 Coffeeville:  Annual ESD Test\n--8/18/26 through 8/20/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1479660","***","2026-04-28","2026-04-28","Project Change","2026-04-21","2026-04-21","MLV 847-1 to MLV 851-1","800","1","Pig Runs - Cleaning / Gauge 4/21/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,847.1,"--start_date--end_date--------------model_loc--","***MLV 847-1 to MLV 851-1:  Pig Runs - Cleaning / Gauge 4/21/26\n--4/28/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n***\nDate Change, Previously scheduled 4/21/26.\n………………………………"]
["X25-1479661","***","2026-04-30","2026-04-30","Project Change","2026-04-23","2026-04-23","MLV 847-1 to MLV 851-1","800","1","Pig Runs - Cal / IMU & MFL-A 4/23/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,847.1,"--start_date--end_date----------prl----model_loc--","***MLV 847-1 to MLV 851-1:  Pig Runs - Cal / IMU & MFL-A 4/23/26\n--4/30/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n***\nDate Change, Previously scheduled 4/23/26.\n………………………………"]
["X25-1411286",null,"2026-10-19","2026-10-21",null,null,null,"Sta 851 New Albany","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,851,null,"Sta 851 New Albany:  Annual ESD Test\n--10/19/26 through 10/21/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1479848",null,"2026-05-12","2026-05-13",null,null,null,"Sta 851","800","1","Scrubber Filter Change Out","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,851.01,null,"Sta 851:  Scrubber Filter Change Out\n--5/12/26 through 5/13/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1411665",null,"2026-06-10","2026-06-11",null,null,null,"Sta 856 Savannah","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,856,null,"Sta 856 Savannah:  Annual ESD Test\n--6/10/26 through 6/11/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X24-1368187","***","2025-11-01","2025-12-31","Completed",null,null,"Sta 856 Savannah","800","1","Replace Leaking ESD Valves on Turbines","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,856.00009999999997,"------","***Sta 856 Savannah:  Replace Leaking ESD Valves on Turbines\n***Completed"]
["X25-240033","***","2025-12-11","2025-12-11","Completed",null,null,"MLV 856-1 to MLV 860-1","800","1","Pig Runs - MFL-C 12/11/25","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,856.12,"------","***MLV 856-1 to MLV 860-1:  Pig Runs - MFL-C 12/11/25\n***Completed"]
["X25-996852",null,"2026-02-10","2026-02-10",null,null,null,"MLV 856-1 to MLV 860-1","800","1","Pig Runs - Cleaning / Gauge 2/10/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,856.13,null,"MLV 856-1 to MLV 860-1:  Pig Runs - Cleaning / Gauge 2/10/26\n--2/10/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-996854",null,"2026-02-12","2026-02-12",null,null,null,"MLV 856-1 to MLV 860-1","800","1","Pig Runs - EMAT 2/12/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,856.14,null,"MLV 856-1 to MLV 860-1:  Pig Runs - EMAT 2/12/26\n--2/12/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1411669",null,"2026-05-13","2026-05-14",null,null,null,"Sta 860","800","1","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,860,null,"Sta 860:  Annual ESD Test & Maintenance\n--5/13/26 through 5/14/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1284312",null,"2025-06-17","2026-12-31",null,null,null,"Sta 860","800","1","Unit 1A - Aftercooler Jacket Water Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,860.00099999999998,null,"Sta 860:  Unit 1A - Aftercooler Jacket Water Inspection\n--6/17/25 through 12/31/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-1411788",null,"2026-06-23","2026-06-23",null,null,null,"Sta 871 Campbellsville","800","2","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,871,null,"Sta 871 Campbellsville:  Annual ESD Test\n--6/23/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-799693","***","2026-02-04","2026-02-04","Project Change",null,null,"Sta 871","800","2","Unit 1A - 1Q Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,871.00099999999998,"------------mantenance_desc------model_loc--","***Sta 871:  Unit 1A - 1Q Engine Inspection\n--2/4/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***Project Change\n………………………………"]
["X25-1369931",null,"2025-11-06","2025-12-23",null,null,null,"Sta 871","800","2","Unit 2A - Turbo","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,871.00199999999995,null,"Sta 871:  Unit 2A - Turbo\n--11/6/25 through 12/23/25:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-799692","***","2026-02-03","2026-02-03","Project Change",null,null,"Sta 871","800","2","Unit 2A - 1Q Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,871.00199999999995,"------------mantenance_desc------model_loc--","***Sta 871:  Unit 2A - 1Q Engine Inspection\n--2/3/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***Project Change\n………………………………"]
["X25-1022170",null,"2025-08-22","2026-01-30",null,null,null,"Sta 871","800","2","Unit 3A - Engine Crankshaft Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,871.00300000000004,null,"Sta 871:  Unit 3A - Engine Crankshaft Inspection\n--8/22/25 through 1/30/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X25-1411765",null,"2026-11-11","2026-11-11",null,null,null,"Sta 871A Campbellsville","800","2","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,871.5,null,"Sta 871A Campbellsville:  Annual ESD Test\n--11/11/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1411088",null,"2026-06-09","2026-06-12",null,null,null,"Sta 875 Richmond","800","2","Annual ESD Test & Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,875,null,"Sta 875 Richmond:  Annual ESD Test & Maintenance\n--6/9/26 through 6/12/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1477461",null,"2026-01-20","2026-01-22",null,null,null,"Sta 875","800","2","Unit 1A-  4K Solar Turbine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,875.00099999999998,null,"Sta 875:  Unit 1A-  4K Solar Turbine Inspection\n--1/20/26 through 1/22/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1477462",null,"2026-09-08","2026-09-10",null,null,null,"Sta 875","800","2","Unit 1A-  8K Solar Turbine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,875.00099999999998,null,"Sta 875:  Unit 1A-  8K Solar Turbine Inspection\n--9/8/26 through 9/10/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1490624","***","2026-01-14","2026-01-14","Completed",null,null,"MLV 209-4 to MLV 204-4","200","4","Pig Run - MFL-A Rerun","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","44423 REX/TGP BIG MUSKIE GUERNSEY",2093.4,"------","***MLV 209-4 to MLV 204-4:  Pig Run - MFL-A Rerun\n***Completed\nThe following meters are available for nominations:\n44423 REX/TGP BIG MUSKIE GUERNSEY"]

{"sheet":"Sheet2","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}

{"sheet":"Sheet3","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}