{"text_format":"1","workbook":"xlsx","n_sheets":4,"sheets":["Closed","Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":8,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Closed","index":0,"n_rows":37,"n_cols":22,"rows_kept":37,"cut":false,"hidden":true,"merged":[[1,3,1,15],[2,3,2,15],[3,3,3,15]]}
[null,null,null,"Updated ","2016"]
[null,null,null,"Tennessee Gas Pipeline 2015 Pipeline Outage and Maintenance Summary"]
[null,null,null,"This is a summary of the current status of all TGP Winter 2014-2015 Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  Additionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
[null,null,null,"*** Indicates revision"]
["Date Change","Project New/Completed/Closed","Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","Location","Leg","Zone","Maintenance Activity","Anticipated Impact","Potential Restriction Level","TOS Potential Restrictions","Meter(s) in Impacted Area","Customer Notifications","Loc","Email Text","Posting Text","Completion Text"]
[{"$f":"IF(AND(H6<>\"\",I6<>\"\"), \"Date change. Previously scheduled \" & TEXT(H6,\"m/d/y;@\") &IF(H6=I6,\"\",\" to \" & TEXT(I6,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed",null,{"$f":"IF(G6<>\"\",\"***\",\"\")","v":"***"},"2015-01-11","2016-01-11",{"$f":"IF(AND(A6=\"\",B6=\"\"),\"\",IF(B6=\"\",A6,B6))","v":"Project Completed"},null,null,"MS #412494 DCP Warren","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412494 DCP Warren",401,{"$f":"\"(\"&C6&\") \"&J6&\":  \"&M6&IF(AND(E6=\"\",F6=\"\"),\"\",\" (\")&IF(E6=\"\",\"\",\"\"&TEXT(E6,\"m/d/y;@\"))&IF(OR(F6=E6,E6=\"\",F6=\"\"),\"\",\" to \")&IF(OR(F6=\"\",F6=E6),\"\",TEXT(F6,\"m/d/y;@\"))&IF(AND(E6=\"\",F6=\"\"),\"\",\")\")","v":"() MS #412494 DCP Warren:  Meter Station (1/11/15 to 1/11/16)"},{"$f":"D6&J6&\":  \"&M6&IF(AND(E6=\"\",F6=\"\"),\"\",\"\n\")&IF(E6=\"\",\"\",\"--\"&TEXT(E6,\"m/d/y;@\"))&IF(OR(F6=E6,E6=\"\",F6=\"\"),\"\",\" through \")&IF(OR(F6=\"\",F6=E6),\"\",TEXT(F6,\"m/d/y;@\"))&IF(AND(E6=\"\",F6=\"\"),\"\",\":  \")&N6&\"  \"&P6&IF(Q6=\"\",\"\",\"\n\"&Q6)&IF(G6=\"\",\"\",\"\n***\")&G6&\"\n………………………………\"","v":"***MS #412494 DCP Warren:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412494 DCP Warren\n***Project Completed\n………………………………"},{"$f":"D6&J6&\":  \"&M6&IF(G6=\"\",\"\",\"\n***\")&G6&IF(Q6=\"\",\"\",\"\nThe following meters are available for nominations:\n\")&Q6&\"\n………………………………\"","v":"***MS #412494 DCP Warren:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412494 DCP Warren\n………………………………"}]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412400 King Ranch","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412400 King Ranch",402.1,"() MS #412400 King Ranch:  Meter Station (1/11/15 to 1/11/16)","***MS #412400 King Ranch:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412400 King Ranch\n***Project Completed\n………………………………","***MS #412400 King Ranch:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412400 King Ranch\n………………………………"]
["","Project Completed",null,"***","2015-01-12","2016-01-12","Project Completed",null,null,"MS #410539 Duvak Gas Gathering","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410539 Duvak Gas Gathering",402.1,"() MS #410539 Duvak Gas Gathering:  Meter Station (1/12/15 to 1/12/16)","***MS #410539 Duvak Gas Gathering:  Meter Station\n--1/12/15 through 1/12/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410539 Duvak Gas Gathering\n***Project Completed\n………………………………","***MS #410539 Duvak Gas Gathering:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n410539 Duvak Gas Gathering\n………………………………"]
["","Project Completed",null,"***","2015-01-13","2016-01-13","Project Completed",null,null,"MS #412356 DCP LaGloria","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412356 DCP LaGloria",403.1,"() MS #412356 DCP LaGloria:  Meter Station (1/13/15 to 1/13/16)","***MS #412356 DCP LaGloria:  Meter Station\n--1/13/15 through 1/13/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412356 DCP LaGloria\n***Project Completed\n………………………………","***MS #412356 DCP LaGloria:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412356 DCP LaGloria\n………………………………"]
["","Project Completed",null,"***","2015-01-13","2016-01-13","Project Completed",null,null,"MS #410173 Enterprise LaReforma","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410173 Enterprise LaReforma",406.1,"() MS #410173 Enterprise LaReforma:  Meter Station (1/13/15 to 1/13/16)","***MS #410173 Enterprise LaReforma:  Meter Station\n--1/13/15 through 1/13/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410173 Enterprise LaReforma\n***Project Completed\n………………………………","***MS #410173 Enterprise LaReforma:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n410173 Enterprise LaReforma\n………………………………"]
["","Project Completed",null,"***","2015-01-12","2016-01-12","Project Completed",null,null,"MS #411903 Enterprise El Benito","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","411903 Enterprise El Benito",407.1,"() MS #411903 Enterprise El Benito:  Meter Station (1/12/15 to 1/12/16)","***MS #411903 Enterprise El Benito:  Meter Station\n--1/12/15 through 1/12/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n411903 Enterprise El Benito\n***Project Completed\n………………………………","***MS #411903 Enterprise El Benito:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n411903 Enterprise El Benito\n………………………………"]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412088 Enterprise Sullivan","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412088 Enterprise Sullivan",407.1,"() MS #412088 Enterprise Sullivan:  Meter Station (1/11/15 to 1/11/16)","***MS #412088 Enterprise Sullivan:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412088 Enterprise Sullivan\n***Project Completed\n………………………………","***MS #412088 Enterprise Sullivan:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412088 Enterprise Sullivan\n………………………………"]
["","Project Completed",null,"***","2015-01-11","2016-01-11","Project Completed",null,null,"MS #412683 HESCO","400","0","Meter Station","This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","412683 HESCO",408.1,"() MS #412683 HESCO:  Meter Station (1/11/15 to 1/11/16)","***MS #412683 HESCO:  Meter Station\n--1/11/15 through 1/11/16:  This project will require isolating the pipeline section.  Physical flow will be suspended.  No other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n412683 HESCO\n***Project Completed\n………………………………","***MS #412683 HESCO:  Meter Station\n***Project Completed\nThe following meters are available for nominations:\n412683 HESCO\n………………………………"]
[{"$f":"IF(AND(H14<>\"\",I14<>\"\"), \"Date change. Previously scheduled \" & TEXT(H14,\"m/d/y;@\") &IF(H14=I14,\"\",\" to \" & TEXT(I14,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X16-36843",{"$f":"IF(G14<>\"\",\"***\",\"\")","v":"***"},"2016-01-27","2016-01-27","Project Completed",null,null,"Sta. 237",200,5,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,237,"(X16-36843) Sta. 237:  Unit  Maintenance (1/27/16)","***Sta. 237:  Unit  Maintenance\n--1/27/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Sta. 237:  Unit  Maintenance\n***Project Completed\n………………………………"]
[{"$f":"IF(AND(H15<>\"\",I15<>\"\"), \"Date change. Previously scheduled \" & TEXT(H15,\"m/d/y;@\") &IF(H15=I15,\"\",\" to \" & TEXT(I15,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X14-1478563",{"$f":"IF(G15<>\"\",\"***\",\"\")","v":"***"},"2015-11-16","2016-02-12","Project Completed",null,null,"MLV 32-1D to 33-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,32.200000000000003,"(X14-1478563) MLV 32-1D to 33-1:  Hydrotest (11/16/15 to 2/12/16)","***MLV 32-1D to 33-1:  Hydrotest\n--11/16/15 through 2/12/16:  This project will require taking the pipeline section out of service.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***MLV 32-1D to 33-1:  Hydrotest\n***Project Completed\n………………………………"]
[null,"Project Completed","X16-16074",null,"2016-01-18","2016-01-28","Project Completed",null,null,"Station 550","500","1","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,550,"(X16-16074) Station 550:  Station Maintenance (1/18/16 to 1/28/16)","Station 550:  Station Maintenance\n--1/18/16 through 1/28/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","Station 550:  Station Maintenance\n***Project Completed\n………………………………"]
[{"$f":"IF(AND(H17<>\"\",I17<>\"\"), \"Date change. Previously scheduled \" & TEXT(H17,\"m/d/y;@\") &IF(H17=I17,\"\",\" to \" & TEXT(I17,\"m/d/y;@\")) & \".\",\"\")","v":""},"Project Completed","X16-46202",{"$f":"IF(G17<>\"\",\"***\",\"\")","v":"***"},"2016-02-01","2016-02-07","Project Completed",null,null,"Station 9","100","0","Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.",null,9,"(X16-46202) Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items) (2/1/16 to 2/7/16)","***Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)\n--2/1/16 through 2/7/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\n***Project Completed\n………………………………","***Station 9:  Station Maintenance\n (station tie-ins associated with the hydrotest from MLV 5-1 to 9-1 *see above items)\n***Project Completed\n………………………………"]
["","Project Completed","X15-925633","***","2016-02-09","2016-02-11","Project Completed",null,null,"Sta. 266A",200,6,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,266,"(X15-925633) Sta. 266A:  Unit  Maintenance (2/9/16 to 2/11/16)","***Sta. 266A:  Unit  Maintenance\n--2/9/16 through 2/11/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Sta. 266A:  Unit  Maintenance\n***Project Completed\n………………………………"]
["","Project Completed","X15-929733","***","2016-01-27","2016-02-10","Project Completed",null,null,"MLV 834-1 to 838-1",800,5,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",834.1,"(X15-929733) MLV 834-1 to 838-1:  ILI/Cleaning Pig (1/27/16 to 2/10/16)","***MLV 834-1 to 838-1:  ILI/Cleaning Pig\n--1/27/16 through 2/10/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 834-1 to 838-1:  ILI/Cleaning Pig\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X14-1562506","***","2015-11-02","2016-02-19","Project Completed",null,null,"MLV 5-1 to 6-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","410063 ROCHE DEHYDRATION             \n",5.0999999999999996,"(X14-1562506) MLV 5-1 to 6-1:  Hydrotest (11/2/15 to 2/19/16)","***MLV 5-1 to 6-1:  Hydrotest\n--11/2/15 through 2/19/16:  This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n410063 ROCHE DEHYDRATION             \n\n***Project Completed\n………………………………","***MLV 5-1 to 6-1:  Hydrotest\n***Project Completed\nThe following meters are available for nominations:\n410063 ROCHE DEHYDRATION             \n\n………………………………"]
["","Project Completed","X14-1562506","***","2015-11-02","2016-02-19","Project Completed",null,null,"MLV 7-1 to 9-1","100","0","Hydrotest","This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","\n412490 Charro\n421083 Eagle Ford Field Service",5.0999999999999996,"(X14-1562506) MLV 7-1 to 9-1:  Hydrotest (11/2/15 to 2/19/16)","***MLV 7-1 to 9-1:  Hydrotest\n--11/2/15 through 2/19/16:  This project will require taking the pipeline section out of service.  The listed meters will be shut in during the outage.  This will limit throughput and may result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n\n412490 Charro\n421083 Eagle Ford Field Service\n***Project Completed\n………………………………","***MLV 7-1 to 9-1:  Hydrotest\n***Project Completed\nThe following meters are available for nominations:\n\n412490 Charro\n421083 Eagle Ford Field Service\n………………………………"]
["Date change. Previously scheduled 2/18/16 to 2/20/16.","Project Completed","X15-882289","***","2016-02-22","2016-02-24","Project Completed","2016-02-18","2016-02-20","MLV 24-2 to 25-2S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.2,"(X15-882289) MLV 24-2 to 25-2S:  Anomaly Remediation (2/22/16 to 2/24/16)","***MLV 24-2 to 25-2S:  Anomaly Remediation\n--2/22/16 through 2/24/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 24-2 to 25-2S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-925630","***","2016-02-23","2016-02-23","Project Completed",null,null,"WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B)",200,"L","ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,265.10000000000002,"(X15-925630) WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig (2/23/16)","***WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig\n--2/23/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***WORCESTER DELIVERY NO. 2 LINE \n(265C-101.1 to 265C-101B):  ILI/Cleaning Pig\n***Project Completed\n………………………………"]
["","Project Completed","X16-23748","***","2016-02-15","2016-02-18","Project Completed",null,null,"MLV 530-3 to 532-3",500,"L","ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,530.29999999999995,"(X16-23748) MLV 530-3 to 532-3:  ILI/Cleaning Pig (2/15/16 to 2/18/16)","***MLV 530-3 to 532-3:  ILI/Cleaning Pig\n--2/15/16 through 2/18/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***MLV 530-3 to 532-3:  ILI/Cleaning Pig\n***Project Completed\n………………………………"]
["","Project Canceled","X16-98720","***","2016-03-06","2016-03-06","Project Canceled",null,null,"Sta. 1",100,0,"Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,1,"(X16-98720) Sta. 1:  Station Maintenance (3/6/16)","***Sta. 1:  Station Maintenance\n--3/6/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Canceled\n………………………………","***Sta. 1:  Station Maintenance\n***Project Canceled\n………………………………"]
["","Project Completed","X14-1562513\nX14-1540661","***","2015-07-01","2016-03-04","Project Completed",null,null,"Station 32","100","0","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,32,"(X14-1562513\nX14-1540661) Station 32:  Station Maintenance (7/1/15 to 3/4/16)","***Station 32:  Station Maintenance\n--7/1/15 through 3/4/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Station 32:  Station Maintenance\n***Project Completed\n………………………………"]
["","Project Canceled","X15-926822","***","2016-06-06","2016-06-11","Project Canceled",null,null,"BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1)",300,6,"Pipe Inspection","This project involves inspecting multiple sites.  We do not anticipate having to do any repairs, however if a repair is needed  there is a potential that the pipe  may require replacement which will require isolation of the pipe.  This may limit throughput and will result in restrictions based on customer nominations.  Customers may experience pressure fluctuations during this timeframe.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",343.1,"(X15-926822) BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection (6/6/16 to 6/11/16)","***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection\n--6/6/16 through 6/11/16:  This project involves inspecting multiple sites.  We do not anticipate having to do any repairs, however if a repair is needed  there is a potential that the pipe  may require replacement which will require isolation of the pipe.  This may limit throughput and will result in restrictions based on customer nominations.  Customers may experience pressure fluctuations during this timeframe.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***BRIDGEPORT DELIVERY LINE NO. 2 (343A-101.1):  Pipe Inspection\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928271","***","TBD","TBD","Project Canceled",null,null,"MLV 555-1 to 550-1",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.1,"(X15-928271) MLV 555-1 to 550-1:  ILI/Cleaning Pig (TBD)","***MLV 555-1 to 550-1:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-1 to 550-1:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928272","***","TBD","TBD","Project Canceled",null,null,"MLV 555-2 to 550-2",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.20000000000005,"(X15-928272) MLV 555-2 to 550-2:  ILI/Cleaning Pig (TBD)","***MLV 555-2 to 550-2:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-2 to 550-2:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Canceled","X15-928273","***","TBD","TBD","Project Canceled",null,null,"MLV 555-3 to 552-3",500,1,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",555.29999999999995,"(X15-928273) MLV 555-3 to 552-3:  ILI/Cleaning Pig (TBD)","***MLV 555-3 to 552-3:  ILI/Cleaning Pig\n--TBD:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Canceled\n………………………………","***MLV 555-3 to 552-3:  ILI/Cleaning Pig\n***Project Canceled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-882281","***","2016-02-24","2016-03-03","Project Completed",null,null,"24-1A to 25-1S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.1,"(X15-882281) 24-1A to 25-1S:  Anomaly Remediation (2/24/16 to 3/3/16)","***24-1A to 25-1S:  Anomaly Remediation\n--2/24/16 through 3/3/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***24-1A to 25-1S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-882291","***","2016-03-03","2016-03-04","Project Completed",null,null,"MLV 24-3 to 25-3S",100,0,"Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",24.3,"(X15-882291) MLV 24-3 to 25-3S:  Anomaly Remediation (3/3/16 to 3/4/16)","***MLV 24-3 to 25-3S:  Anomaly Remediation\n--3/3/16 through 3/4/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 24-3 to 25-3S:  Anomaly Remediation\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X14-1178175","***","2015-06-15","2016-03-31","Project Completed",null,null,"Station 63","100","1","Station Maintenance","This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.",null,63,"(X14-1178175) Station 63:  Station Maintenance (6/15/15 to 3/31/16)","***Station 63:  Station Maintenance\n--6/15/15 through 3/31/16:  This project will require a station outage, which will limit throughput through the station and may result in restrictions based on customer nominations. Customers may experience an increase in pressures during this time.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\n***Project Completed\n………………………………","***Station 63:  Station Maintenance\n***Project Completed\n………………………………"]
["","Project Cancelled","X15-913224","***","2016-04-16","2016-05-21","Project Cancelled",null,null,"MLV 109-2",100,2,"Pipe Replacement","This project will require taking the pipeline section out of service.   This will limit throughput and will result in restrictions based on customer nominations.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",109.2,"(X15-913224) MLV 109-2:  Pipe Replacement (4/16/16 to 5/21/16)","***MLV 109-2:  Pipe Replacement\n--4/16/16 through 5/21/16:  This project will require taking the pipeline section out of service.   This will limit throughput and will result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Cancelled\n………………………………","***MLV 109-2:  Pipe Replacement\n***Project Cancelled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Completed","X15-926830","***","2016-03-07","2016-03-11","Project Completed",null,null,"MLV 400-1 to 408-1",100,0,"ILI/Cleaning Pig","This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated. ","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.","To Be Determined",400.1,"(X15-926830) MLV 400-1 to 408-1:  ILI/Cleaning Pig (3/7/16 to 3/11/16)","***MLV 400-1 to 408-1:  ILI/Cleaning Pig\n--3/7/16 through 3/11/16:  This activity will require operating at controlled flow rates.   Customers may experience pressure fluctuations, however, no other service impact is anticipated.   Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\nTo Be Determined\n***Project Completed\n………………………………","***MLV 400-1 to 408-1:  ILI/Cleaning Pig\n***Project Completed\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]
["","Project Cancelled","X16-143836","***","2016-03-28","2016-04-04","Project Cancelled",null,null,"Sta. 409",100,0,"Unit  Maintenance","This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.","SIP","Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.",null,409,"(X16-143836) Sta. 409:  Unit  Maintenance (3/28/16 to 4/4/16)","***Sta. 409:  Unit  Maintenance\n--3/28/16 through 4/4/16:  This project will require a unit outage, which could limit throughput through the station and result in restrictions based on customer nominations.  Potential restrictions through a pro-rata portion of Secondary in the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP, SIP) nominations.\n***Project Cancelled\n………………………………","***Sta. 409:  Unit  Maintenance\n***Project Cancelled\n………………………………"]
["","Project Cancelled","X15-929680","***","2016-04-18","2016-04-27","Project Cancelled",null,null,"SABINE - KINDER LINE to 822-1",800,"L","Anomaly Remediation","This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.","SOP","Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.","To Be Determined",822.1,"(X15-929680) SABINE - KINDER LINE to 822-1:  Anomaly Remediation (4/18/16 to 4/27/16)","***SABINE - KINDER LINE to 822-1:  Anomaly Remediation\n--4/18/16 through 4/27/16:  This outage will require pressure reductions and possibly line isolations.  However no other service impact is anticipated.  Potential restrictions through a pro-rata portion of Secondary out of the Path (PAL-D (Park Withdrawals/Loans), IT, AOT, EDS/ERS, Payback From Tennessee, PAL-T (Park Withdrawals/Loans), SOP) nominations.\nTo Be Determined\n***Project Cancelled\n………………………………","***SABINE - KINDER LINE to 822-1:  Anomaly Remediation\n***Project Cancelled\nThe following meters are available for nominations:\nTo Be Determined\n………………………………"]

{"sheet":"Sheet1","index":1,"n_rows":632,"n_cols":22,"rows_kept":632,"cut":false,"hidden":false,"merged":[[2,0,2,12]]}
["Updated ","2026-04-02"]
["Tennessee Gas Pipeline 2026 Pipeline Outage and Maintenance Summary"]
["This is a summary of the current status of TGP Pipeline Outages and Maintenance Projects.  This document is subject to change as the season progresses to reflect the updated status of all outages and maintenance projects including, but not limited to, project delays, cancellations and additions.  \nAdditionally, anticipated impact and restrictions are subject to change.   \n*Unless otherwise noted, all listed meters will be physically shut-in for the duration of the project.\n*Unless otherwise noted, all scheduled dates represent gas days as defined in the Tennessee Gas Pipeline tariff to mean a period of twenty-four consecutive hours, beginning and ending at 9:00 a.m. (Central Clock Time)."]
["*** Indicates revision"]
["Outage #","Revised","Start Date","End Date","Reason Changed","Prev. Start Date","Prev. End Date","Location","Leg","Zone","Maintenance Activity","Anticipated Impact","Meter(s) in Impacted Area","Loc",null,null,null,null,null,null,null,"\\\\houCORP\\TRANS\\TRANSERVICES\\OPPLAN\\COMMON\\Outages\\Outage_DB\\TGP\\Files"]
["X25-1259255",null,"2025-10-10","2026-12-31",null,null,null,"Sta 1","100","0","Unit 6A - Engine Overhaul and Regrout","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,1.006,null,"Sta 1:  Unit 6A - Engine Overhaul and Regrout\n--10/10/25 through 12/31/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-299678",null,"2026-09-01","2026-10-31",null,null,null,"MLV 1-1D to MLV 5-1","100","0","Spike Test","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,1.1000000000000001,null,"MLV 1-1D to MLV 5-1:  Spike Test\n--9/1/26 through 10/31/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-318382",null,"2026-07-13","2026-07-13",null,null,null,"MLV 1-2D to MLV 5-2","100","1","Pig Run - Cleaning Gauge","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,1.2,null,"MLV 1-2D to MLV 5-2:  Pig Run - Cleaning Gauge\n--7/13/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1389520",null,"2026-09-14","2026-10-02",null,null,null,"MLV 1-2D to MLV 5-2","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,1.2,null,"MLV 1-2D to MLV 5-2:  Anomaly Remediation\n--9/14/26 through 10/2/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-318386",null,"2026-07-14","2026-07-14",null,null,null,"MLV 1-2D to MLV 5-2","100","1","Pig Run - Cleaning Gauge","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,1.21,null,"MLV 1-2D to MLV 5-2:  Pig Run - Cleaning Gauge\n--7/14/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X26-318387",null,"2026-07-15","2026-07-15",null,null,null,"MLV 1-2D to MLV 5-2","100","1","Pig Run - Cleaning Gauge","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,1.22,null,"MLV 1-2D to MLV 5-2:  Pig Run - Cleaning Gauge\n--7/15/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X26-318389",null,"2026-07-16","2026-07-16",null,null,null,"MLV 1-2D to MLV 5-2","100","1","Pig Run - Cleaning Gauge","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,1.23,null,"MLV 1-2D to MLV 5-2:  Pig Run - Cleaning Gauge\n--7/16/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X26-318391",null,"2026-07-17","2026-07-17",null,null,null,"MLV 1-2D to MLV 5-2","100","1","Pig Run - Cleaning Gauge","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,1.24,null,"MLV 1-2D to MLV 5-2:  Pig Run - Cleaning Gauge\n--7/17/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X26-318392",null,"2026-07-21","2026-07-21",null,null,null,"MLV 1-2D to MLV 5-2","100","1","Pig Run - TDW MDS","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,1.25,null,"MLV 1-2D to MLV 5-2:  Pig Run - TDW MDS\n--7/21/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1389555",null,"2026-05-11","2026-06-19",null,null,null,"MLV 5-2 to MLV 9-2S","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,5.2,null,"MLV 5-2 to MLV 9-2S:  Anomaly Remediation\n--5/11/26 through 6/19/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1354994",null,"2026-06-01","2026-09-01",null,null,null,"MLV 8-1 TO MLV 10-1","100","0","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,8.1,null,"MLV 8-1 TO MLV 10-1:  Pipe Replacement\n--6/1/26 through 9/1/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-282177",null,"2026-09-23","2026-09-23",null,null,null,"Station 9 Victoria","100","0","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,9,null,"Station 9 Victoria:  Annual ESD Test\n--9/23/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1389521","***","2026-07-27","2026-08-14","Project Change",null,null,"MLV 9-1D to MLV 10-1","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,9.1,"----------RestrictedPress--------model_loc--","***MLV 9-1D to MLV 10-1:  Anomaly Remediation\n--7/27/26 through 8/14/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n***Project Change\n………………………………"]
["X25-1566610",null,"2026-04-13","2026-04-13",null,null,null,"MLV 9-3D to MLV 11-3","100","0","Pig Run - Cleaning","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,9.3000000000000007,null,"MLV 9-3D to MLV 11-3:  Pig Run - Cleaning\n--4/13/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1566643",null,"2026-04-14","2026-04-14",null,null,null,"MLV 9-3D to MLV 11-3","100","0","Pig Run - Gauge","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,9.3000000000000007,null,"MLV 9-3D to MLV 11-3:  Pig Run - Gauge\n--4/14/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1566661",null,"2026-04-15","2026-04-15",null,null,null,"MLV 9-3D to MLV 11-3","100","0","Pig Run - MFL-A","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,9.3000000000000007,null,"MLV 9-3D to MLV 11-3:  Pig Run - MFL-A\n--4/15/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X26-282160",null,"2026-09-22","2026-09-22",null,null,null,"Sta 11A","100","0","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,11,null,"Sta 11A:  Annual ESD Test\n--9/22/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-364126","***","2026-07-27","2026-08-14","Added",null,null,"MLV 11-1A to MLV 11-1","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,11.1,"------","***MLV 11-1A to MLV 11-1:  Anomaly Remediation\n--7/27/26 through 8/14/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n***Added\n………………………………"]
["X26-364133","***","2026-07-27","2026-08-13","Added",null,null,"MLV 13-1 to MLV 12-1","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,13.1,"------","***MLV 13-1 to MLV 12-1:  Anomaly Remediation\n--7/27/26 through 8/13/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n***Added\n………………………………"]
["X26-302797",null,"2026-06-15","2026-07-10",null,null,null,"MLV 14-2 to MLV 15-2","100","1","Anomaly Redmediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,14.2,null,"MLV 14-2 to MLV 15-2:  Anomaly Redmediation\n--6/15/26 through 7/10/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-282409",null,"2026-10-06","2026-10-06",null,null,null,"Sta 17","100","0","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,17,null,"Sta 17:  Annual ESD Test\n--10/6/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-116338",null,"2026-05-18","2026-05-22",null,null,null,"MLV 17-2DL TO MLV 18-2","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,17.2,null,"MLV 17-2DL TO MLV 18-2:  Anomaly Remediation\n--5/18/26 through 5/22/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-176302",null,"2026-06-15","2026-06-22",null,null,null,"MLV 17-3DL to MLV 18-3A","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,17.3,null,"MLV 17-3DL to MLV 18-3A:  Anomaly Remediation\n--6/15/26 through 6/22/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-116424",null,"2026-05-25","2026-05-29",null,null,null,"MLV 18-2 TO MLV 18-2A","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,18.2,null,"MLV 18-2 TO MLV 18-2A:  Anomaly Remediation\n--5/25/26 through 5/29/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1354988",null,"2026-08-08","2026-09-21",null,null,null,"MLV 19-1 TO MLV 20-1A","100","0","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","412100 ATMOS-TX/TGP KATY EXCH WALLER",19.100000000000001,null,"MLV 19-1 TO MLV 20-1A:  Pipe Replacement\n--8/8/26 through 9/21/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  \n412100 ATMOS-TX/TGP KATY EXCH WALLER\n………………………………"]
["X25-1354990","***","2026-04-21","2026-06-09","Project Change","2026-04-07","2026-05-26","MLV 19-2 TO MLV 20-2A","100","0","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","411788 DCP GLP/TGP KATY TRANSPORT WALLER",19.2,"--start_date--end_date--------------model_loc--","***MLV 19-2 TO MLV 20-2A:  Pipe Replacement\n--4/21/26 through 6/9/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  \n411788 DCP GLP/TGP KATY TRANSPORT WALLER\n***\nDate Change, Previously scheduled 4/7/26 to 5/26/26.\n………………………………"]
["X25-1354992",null,"2026-05-27","2026-08-07",null,null,null,"MLV 19-3 TO MLV 20-3A","100","0","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in during the project.","421085 SYMMETRY/TGP PEDERSON ROAD WALLER\n412100 ATMOS-TX/TGP KATY EXCH WALLER",19.3,null,"MLV 19-3 TO MLV 20-3A:  Pipe Replacement\n--5/27/26 through 8/7/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed will be shut in during the project.  \n421085 SYMMETRY/TGP PEDERSON ROAD WALLER\n412100 ATMOS-TX/TGP KATY EXCH WALLER\n………………………………"]
["X26-44361","***","2026-07-06","2026-07-16","Completed",null,null,"MLV 20M-102 TO MLV 20M-102A","100","0","Hydrotest","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations",null,20.100000000000001,"------","***MLV 20M-102 TO MLV 20M-102A:  Hydrotest\n***Completed"]
["X26-176307",null,"2026-06-23","2026-06-30",null,null,null,"MLV 20-3 to MLV 20-3R","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,20.3,null,"MLV 20-3 to MLV 20-3R:  Anomaly Remediation\n--6/23/26 through 6/30/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1389551",null,"2026-07-06","2026-07-24",null,null,null,"MLV 21-1ABD to MLV 21-1ABD1","100","0","ECDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,21.1,null,"MLV 21-1ABD to MLV 21-1ABD1:  ECDA\n--7/6/26 through 7/24/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-44441",null,"2026-07-27","2026-08-11",null,null,null,"MLV 21B-101.1 TO MLV 21B-121A","100","0","Hydrotest","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.    The meters listed may be constrained or shut in during the project.","421028 CNTRPT/TGP DOWDELL ROAD HARRIS\n420898 SYMMETRY/TGP TOMBALL SALES NORTH MO\n410306 TEXLA/TGP UDP TOMBALL DEHY HARRIS",21.1,null,"MLV 21B-101.1 TO MLV 21B-121A:  Hydrotest\n--7/27/26 through 8/11/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.    The meters listed may be constrained or shut in during the project.  \n421028 CNTRPT/TGP DOWDELL ROAD HARRIS\n420898 SYMMETRY/TGP TOMBALL SALES NORTH MO\n410306 TEXLA/TGP UDP TOMBALL DEHY HARRIS\n………………………………"]
["X26-110268","***","2026-03-23","2026-03-27","Completed",null,null,"MLV 24-1BR1 TO MLV 24-1A","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,24.1,"------","***MLV 24-1BR1 TO MLV 24-1A:  Anomaly Remediation\n***Completed"]
["X26-279085",null,"2026-07-21","2026-07-21",null,null,null,"Sta 25","100","0","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,25,null,"Sta 25:  Annual ESD Test\n--7/21/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-942604",null,"2025-07-16","2026-09-01",null,null,null,"Sta 25","100","0","Unit 1C - VFD Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,25.033000000000001,null,"Sta 25:  Unit 1C - VFD Replacement\n--7/16/25 through 9/1/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1389522",null,"2026-04-06","2026-04-17",null,null,null,"MLV 31-2 to MLV 32-2S","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,25.2,null,"MLV 31-2 to MLV 32-2S:  Anomaly Remediation\n--4/6/26 through 4/17/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X22-621358",null,"2026-04-06","2026-04-23",null,null,null,"MLV 26-1 Relocation","100","0","Highway 59 Widening","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,26.1,null,"MLV 26-1 Relocation:  Highway 59 Widening\n--4/6/26 through 4/23/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X22-815863",null,"2026-04-24","2026-05-12",null,null,null,"MLV 26-2 Relocation","100","0","Highway 59 Widening","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,26.2,null,"MLV 26-2 Relocation:  Highway 59 Widening\n--4/24/26 through 5/12/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X22-815864",null,"2026-05-13","2026-05-30",null,null,null,"MLV 26-3 Relocation","100","0","Highway 59 Widening","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","400448 CICO/TGP MERCY GU 1 LIBERTY",26.3,null,"MLV 26-3 Relocation:  Highway 59 Widening\n--5/13/26 through 5/30/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  \n400448 CICO/TGP MERCY GU 1 LIBERTY\n………………………………"]
["X26-201546",null,"2026-04-24","2026-05-04",null,null,null,"MLV 27-1 to MLV 27-1A","100","1","Meter Maintenance - TIP Coley Creek Meter","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,27.1,null,"MLV 27-1 to MLV 27-1A:  Meter Maintenance - TIP Coley Creek Meter\n--4/24/26 through 5/4/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-286246",null,"2026-11-17","2026-11-18",null,null,null,"Sta 32","100","0","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,32,null,"Sta 32:  Annual ESD Test\n--11/17/26 through 11/18/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-228232","***","2026-02-26","2026-05-29","Project Change",null,"2026-03-25","Sta 32","100","0","Unit 6A - Power Cylinder","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,32.006,"----end_date--------------model_loc--","***Sta 32:  Unit 6A - Power Cylinder\n--2/26/26 through 5/29/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***\nDate Change, Previously scheduled 2/26/26 to 3/25/26.\n………………………………"]
["X26-158867",null,"2026-02-04","2026-04-17",null,null,null,"Sta 32","100","0","Unit 11A - Power Cylinder","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,32.011000000000003,null,"Sta 32:  Unit 11A - Power Cylinder\n--2/4/26 through 4/17/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-377013","***","2026-03-27","2026-04-02","Added",null,null,"Sta 32","100","0","Unit 3B - Fuel System DP","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,32.018999999999998,"------","***Sta 32:  Unit 3B - Fuel System DP\n--3/27/26 through 4/2/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***Added\n………………………………"]
["X26-211801","***","2026-02-23","2026-06-26","Project Change",null,"2026-03-31","Sta 32","100","0","Unit 5B - Compressor Cylinder","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,32.021000000000001,"----end_date--------------model_loc--","***Sta 32:  Unit 5B - Compressor Cylinder\n--2/23/26 through 6/26/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***\nDate Change, Previously scheduled 2/23/26 to 3/31/26.\n………………………………"]
["X26-221776",null,"2026-02-23","2026-04-17",null,null,null,"Sta 32","100","0","Unit 9B - Air Starters","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,32.024999999999999,null,"Sta 32:  Unit 9B - Air Starters\n--2/23/26 through 4/17/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1389356",null,"2026-04-20","2026-05-08",null,null,null,"MLV 37-2 to MLV 38-2","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,32.200000000000003,null,"MLV 37-2 to MLV 38-2:  Anomaly Remediation\n--4/20/26 through 5/8/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-318414",null,"2026-05-12","2026-05-12",null,null,null,"MLV 32-2 to MLV 40-2S","100","1","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,32.200000000000003,null,"MLV 32-2 to MLV 40-2S:  Pig Run - Maintenance\n--5/12/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X26-318416",null,"2026-05-13","2026-05-13",null,null,null,"MLV 32-3 to MLV 40-3S","100","0","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,32.299999999999997,null,"MLV 32-3 to MLV 40-3S:  Pig Run - Maintenance\n--5/13/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1389493","***","2026-03-23","2026-03-27","Completed",null,null,"MLV 33-3D to MLV 34-3S","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,33.299999999999997,"------","***MLV 33-3D to MLV 34-3S:  Anomaly Remediation\n***Completed"]
["X26-220987",null,"2026-03-30","2026-04-03",null,null,null,"MLV 35-1 to MLV 36-1","100","0","Anomaly Remediation","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,35.1,null,"MLV 35-1 to MLV 36-1:  Anomaly Remediation\n--3/30/26 through 4/3/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-318411",null,"2026-04-29","2026-04-29",null,null,null,"MLV 36-1TX to MLV 36-1LAL","100","1","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,36.1,null,"MLV 36-1TX to MLV 36-1LAL:  Pig Run - Maintenance\n--4/29/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1389528",null,"2026-03-23","2026-04-10",null,null,null,"MLV 41-1 to MLV 41-1A","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.    The meters listed may be constrained or shut in during the project.","412809 CRTXLIG/TGP CLEAR LAKE NO. 1: RIP 4",40.1,null,"MLV 41-1 to MLV 41-1A:  Anomaly Remediation\n--3/23/26 through 4/10/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.    The meters listed may be constrained or shut in during the project.  \n412809 CRTXLIG/TGP CLEAR LAKE NO. 1: RIP 4\n………………………………"]
["X25-1514110",null,"2026-07-14","2026-07-14",null,null,null,"MLV 40-1D to MLV 47-1S","100","1","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,40.1,null,"MLV 40-1D to MLV 47-1S:  Pig Run - Maintenance\n--7/14/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1389530",null,"2026-03-23","2026-04-10",null,null,null,"MLV 41-2 to MLV 41-2A","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,40.200000000000003,null,"MLV 41-2 to MLV 41-2A:  Anomaly Remediation\n--3/23/26 through 4/10/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1514111",null,"2026-08-10","2026-08-13",null,null,null,"MLV 40-2L to MLV 47-2S","100","1","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,40.200000000000003,null,"MLV 40-2L to MLV 47-2S:  Pig Run - Maintenance\n--8/10/26 through 8/13/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X26-231366",null,"2026-08-11","2026-08-11",null,null,null,"MLV 40-2DBL to MLV 42-2R","100","1","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,40.200000000000003,null,"MLV 40-2DBL to MLV 42-2R:  Pig Run - Maintenance\n--8/11/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1514082",null,"2026-06-09","2026-06-09",null,null,null,"MLV 40-3D to MLV 47-3S","100","1","Pig Run - Maintenance Cleaning","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,40.299999999999997,null,"MLV 40-3D to MLV 47-3S:  Pig Run - Maintenance Cleaning\n--6/9/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1514032",null,"2026-07-09","2026-07-09",null,null,null,"MLV 40-4D to MLV 47-4S","100","1","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,40.4,null,"MLV 40-4D to MLV 47-4S:  Pig Run - Maintenance\n--7/9/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X26-296729",null,"2026-03-30","2026-04-17",null,null,null,"MLV 42-1 to MLV 43-1","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,42.1,null,"MLV 42-1 to MLV 43-1:  Anomaly Remediation\n--3/30/26 through 4/17/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1389533",null,"2026-04-20","2026-05-08",null,null,null,"MLV 44-2 to MLV 45-2","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,42.2,null,"MLV 44-2 to MLV 45-2:  Anomaly Remediation\n--4/20/26 through 5/8/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1389545",null,"2026-05-04","2026-05-08",null,null,null,"MLV 42-2BL to MLV 47-2S","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,42.2,null,"MLV 42-2BL to MLV 47-2S:  Anomaly Remediation\n--5/4/26 through 5/8/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1389544",null,"2026-05-11","2026-05-22",null,null,null,"MLV 42-2BL to MLV 47-2S","100","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,42.2,null,"MLV 42-2BL to MLV 47-2S:  Anomaly Remediation\n--5/11/26 through 5/22/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-75379",null,"2026-08-10","2026-08-10",null,null,null,"MLV 42-2BL to MLV 47-2S","100","1","Pig Run - Cleaning Gauge","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,42.2,null,"MLV 42-2BL to MLV 47-2S:  Pig Run - Cleaning Gauge\n--8/10/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X26-75382",null,"2026-08-12","2026-08-12",null,null,null,"MLV 42-2BL to MLV 47-2S","100","1","Pig Run - Cleaning Gauge","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,42.21,null,"MLV 42-2BL to MLV 47-2S:  Pig Run - Cleaning Gauge\n--8/12/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X26-75383",null,"2026-08-13","2026-08-13",null,null,null,"MLV 42-2BL to MLV 47-2S","100","1","Pig Run - Rosen Hart Spot","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,42.22,null,"MLV 42-2BL to MLV 47-2S:  Pig Run - Rosen Hart Spot\n--8/13/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1216073",null,"2026-05-05","2026-05-11",null,null,null,"Bear Creek Storage","100","1","Shut-in Test","This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","460017 STORAGE – BEAR CREEK",43.11,null,"Bear Creek Storage:  Shut-in Test\n--5/5/26 through 5/11/26:  This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  \n460017 STORAGE – BEAR CREEK\n………………………………"]
["X25-1216076",null,"2026-10-20","2026-10-26",null,null,null,"Bear Creek Storage","100","1","Shut-in Test","This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","460017 STORAGE – BEAR CREEK",43.12,null,"Bear Creek Storage:  Shut-in Test\n--10/20/26 through 10/26/26:  This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  \n460017 STORAGE – BEAR CREEK\n………………………………"]
["X25-1508651",null,"2026-04-06","2026-04-10",null,null,null,"Sta. 47","100","1","Scrubber/Filter/Separator Cleaning/Inspection/Changeout","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,47,null,"Sta. 47:  Scrubber/Filter/Separator Cleaning/Inspection/Changeout\n--4/6/26 through 4/10/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1508644",null,"2026-05-04","2026-05-05",null,null,null,"Sta. 47","100","1","Station Transformer Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,47,null,"Sta. 47:  Station Transformer Maintenance\n--5/4/26 through 5/5/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1411913",null,"2026-09-09","2026-09-09",null,null,null,"Sta 47","100","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,47,null,"Sta 47:  Annual ESD Test\n--9/9/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-877998",null,"2025-07-21","2026-06-18",null,null,null,"Sta 47","100","1","Unit 8B - SawGrass Power Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,47.02,null,"Sta 47:  Unit 8B - SawGrass Power Overhaul\n--7/21/25 through 6/18/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-877996",null,"2025-07-21","2026-06-18",null,null,null,"Sta 47","100","1","Unit 9B - Sawgrass power overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,47.021000000000001,null,"Sta 47:  Unit 9B - Sawgrass power overhaul\n--7/21/25 through 6/18/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-161768","***","2026-03-30","2026-04-17","Project Change","2026-04-06",null,"Sta 47","100","1","Unit 1C thru 6C - Installing Unloaders","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,47.033000000000001,"--start_date----------------model_loc--","***Sta 47:  Unit 1C thru 6C - Installing Unloaders\n--3/30/26 through 4/17/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***\nDate Change, Previously scheduled 4/6/26 to 4/17/26.\n………………………………"]
["X25-1508675",null,"2026-08-03","2026-08-06",null,null,null,"Sta. 47","100","1","C Building Unit 2C - Install Suction/Discharge Valves","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,47.048000000000002,null,"Sta. 47:  C Building Unit 2C - Install Suction/Discharge Valves\n--8/3/26 through 8/6/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1508659",null,"2026-06-29","2026-07-10",null,null,null,"Sta. 47","100","1","Unit 1D - 16K hour Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,47.064,null,"Sta. 47:  Unit 1D - 16K hour Overhaul\n--6/29/26 through 7/10/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1508641",null,"2026-04-20","2026-04-24",null,null,null,"Sta 47","100","1","Unit 1E - Annual Turbine Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,47.08,null,"Sta 47:  Unit 1E - Annual Turbine Maintenance\n--4/20/26 through 4/24/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1508647",null,"2026-09-14","2026-09-18",null,null,null,"Sta. 47","100","1","Unit 1E - Solar Seal Gas System Filtration Install","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,47.08,null,"Sta. 47:  Unit 1E - Solar Seal Gas System Filtration Install\n--9/14/26 through 9/18/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-82100","***","2025-09-01","2026-03-25","Completed",null,null,"MLV 47-1A to MLV 48-1","100","1","Class Change","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,47.1,"------","***MLV 47-1A to MLV 48-1:  Class Change\n***Completed"]
["X25-1389534",null,"2026-06-01","2026-06-05",null,null,null,"MLV 47-1D to MLV 47-1A","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,47.1,null,"MLV 47-1D to MLV 47-1A:  Anomaly Remediation\n--6/1/26 through 6/5/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1389535",null,"2026-06-01","2026-06-05",null,null,null,"MLV 47-1A to MLV 47-1C","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,47.1,null,"MLV 47-1A to MLV 47-1C:  Anomaly Remediation\n--6/1/26 through 6/5/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-318569",null,"2026-06-08","2026-06-12",null,null,null,"MLV 47-1C to MLV 48-1","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,47.1,null,"MLV 47-1C to MLV 48-1:  Anomaly Remediation\n--6/8/26 through 6/12/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1389538",null,"2026-06-29","2026-07-17",null,null,null,"MLV 47-1D to MLV 54-1S","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,47.1,null,"MLV 47-1D to MLV 54-1S:  Anomaly Remediation\n--6/29/26 through 7/17/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1508712",null,"2026-10-05","2026-10-05",null,null,null,"Atmos Chauvin Meter","100","1","Meter Scrubber Inspection (47872)","This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.    The meter listed may be constrained or shut in during the project","421062 ENTRGYLA/TGP PERRYVILLE POWER OUACH",47.1,null,"Atmos Chauvin Meter:  Meter Scrubber Inspection (47872)\n--10/5/26:  This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.    The meter listed may be constrained or shut in during the project  \n421062 ENTRGYLA/TGP PERRYVILLE POWER OUACH\n………………………………"]
["X25-1508715",null,"2026-10-06","2026-10-06",null,null,null,"Meter Scrubber Inspection","100","1","Boardwalk Interconnect Meter (47980)","This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.    The meter listed may be constrained or shut in during the project","47980 - Boardwalk Interconnect",47.1,null,"Meter Scrubber Inspection:  Boardwalk Interconnect Meter (47980)\n--10/6/26:  This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.    The meter listed may be constrained or shut in during the project  \n47980 - Boardwalk Interconnect\n………………………………"]
["X25-1508708",null,"2026-10-07","2026-10-08",null,null,null,"Entergy","100","1","Meter Scrubber Inspection (421062)","This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.    The meter listed may be constrained or shut in during the project","421062 ENTRGYLA/TGP PERRYVILLE POWER OUACH",47.1,null,"Entergy:  Meter Scrubber Inspection (421062)\n--10/7/26 through 10/8/26:  This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.    The meter listed may be constrained or shut in during the project  \n421062 ENTRGYLA/TGP PERRYVILLE POWER OUACH\n………………………………"]
["X26-53699",null,"2026-05-11","2026-05-11",null,null,null,"MLV 47-4D to MLV 54-4S","100","1","Pig Run - Gauge Cleaning","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.    The meters listed may be constrained or shut in during the project","421013 BBTMIDLA/TGP FAIRBANKS OUACHITA\n420911 ATMOS-MS/TGP GREENVILLE DELIVERY WA",47.4,null,"MLV 47-4D to MLV 54-4S:  Pig Run - Gauge Cleaning\n--5/11/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.    The meters listed may be constrained or shut in during the project  \n421013 BBTMIDLA/TGP FAIRBANKS OUACHITA\n420911 ATMOS-MS/TGP GREENVILLE DELIVERY WA\n………………………………"]
["X26-53700",null,"2026-05-12","2026-05-12",null,null,null,"MLV 47-4D to MLV 54-4S","100","1","Pig Run - Gauge Cleaning","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.    The meters listed may be constrained or shut in during the project","421013 BBTMIDLA/TGP FAIRBANKS OUACHITA\n420911 ATMOS-MS/TGP GREENVILLE DELIVERY WA",47.41,null,"MLV 47-4D to MLV 54-4S:  Pig Run - Gauge Cleaning\n--5/12/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.    The meters listed may be constrained or shut in during the project  \n421013 BBTMIDLA/TGP FAIRBANKS OUACHITA\n420911 ATMOS-MS/TGP GREENVILLE DELIVERY WA\n………………………………"]
["X26-53701",null,"2026-05-13","2026-05-13",null,null,null,"MLV 47-4D to MLV 54-4S","100","1","Pig Run - Gauge Cleaning","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.    The meters listed may be constrained or shut in during the project","421013 BBTMIDLA/TGP FAIRBANKS OUACHITA\n420911 ATMOS-MS/TGP GREENVILLE DELIVERY WA",47.42,null,"MLV 47-4D to MLV 54-4S:  Pig Run - Gauge Cleaning\n--5/13/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.    The meters listed may be constrained or shut in during the project  \n421013 BBTMIDLA/TGP FAIRBANKS OUACHITA\n420911 ATMOS-MS/TGP GREENVILLE DELIVERY WA\n………………………………"]
["X26-53702",null,"2026-05-15","2026-05-15",null,null,null,"MLV 47-4D to MLV 54-4S","100","1","Pig Run - AFD Combo","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.    The meters listed may be constrained or shut in during the project","421013 BBTMIDLA/TGP FAIRBANKS OUACHITA\n420911 ATMOS-MS/TGP GREENVILLE DELIVERY WA",47.43,null,"MLV 47-4D to MLV 54-4S:  Pig Run - AFD Combo\n--5/15/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.    The meters listed may be constrained or shut in during the project  \n421013 BBTMIDLA/TGP FAIRBANKS OUACHITA\n420911 ATMOS-MS/TGP GREENVILLE DELIVERY WA\n………………………………"]
["X26-53703",null,"2026-05-18","2026-05-18",null,null,null,"MLV 47-4D to MLV 54-4S","100","1","Pig Run - EMAT","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.    The meters listed may be constrained or shut in during the project","421013 BBTMIDLA/TGP FAIRBANKS OUACHITA\n420911 ATMOS-MS/TGP GREENVILLE DELIVERY WA",47.44,null,"MLV 47-4D to MLV 54-4S:  Pig Run - EMAT\n--5/18/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.    The meters listed may be constrained or shut in during the project  \n421013 BBTMIDLA/TGP FAIRBANKS OUACHITA\n420911 ATMOS-MS/TGP GREENVILLE DELIVERY WA\n………………………………"]
["X26-318572",null,"2026-06-08","2026-06-26",null,null,null,"MLV 48-1 to MLV 49-1","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,48.1,null,"MLV 48-1 to MLV 49-1:  Anomaly Remediation\n--6/8/26 through 6/26/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-318586",null,"2026-06-22","2026-07-17",null,null,null,"MLV 49-1 to MLV 50-1","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,49.1,null,"MLV 49-1 to MLV 50-1:  Anomaly Remediation\n--6/22/26 through 7/17/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-318592",null,"2026-07-13","2026-07-20",null,null,null,"MLV 50-1 to MLV 51-1","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,50.1,null,"MLV 50-1 to MLV 51-1:  Anomaly Remediation\n--7/13/26 through 7/20/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-318605",null,"2026-07-20","2026-07-31",null,null,null,"MLV 52-1 to MLV 53-1","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,52.1,null,"MLV 52-1 to MLV 53-1:  Anomaly Remediation\n--7/20/26 through 7/31/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-318619",null,"2026-07-22","2026-08-07",null,null,null,"MLV 53-1 to MLV 53-1S","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,53.1,null,"MLV 53-1 to MLV 53-1S:  Anomaly Remediation\n--7/22/26 through 8/7/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-192494","***","2026-03-30","2026-03-30","Completed",null,null,"MLV 53-3F to MLV 54-3S","100","1","Pig Run - Cleaning/Gauge","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,53.3,"------","***MLV 53-3F to MLV 54-3S:  Pig Run - Cleaning/Gauge\n***Completed"]
["X26-192497","***","2026-03-31","2026-03-31","Completed",null,null,"MLV 53-3F to MLV 54-3S","100","1","Pig Run - Cleaning/Gauge","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,53.3,"------","***MLV 53-3F to MLV 54-3S:  Pig Run - Cleaning/Gauge\n***Completed"]
["X26-192498","***","2026-04-01","2026-04-01","Completed",null,null,"MLV 53-3F to MLV 54-3S","100","1","Pig Run - Cleaning/Gauge","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,53.31,"------","***MLV 53-3F to MLV 54-3S:  Pig Run - Cleaning/Gauge\n***Completed"]
["X26-192500","***","2026-04-02","2026-04-02","Completed",null,null,"MLV 53-3F to MLV 54-3S","100","1","Pig Run - TDW MDS","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,53.32,"------","***MLV 53-3F to MLV 54-3S:  Pig Run - TDW MDS\n***Completed"]
["X25-1411466",null,"2026-09-08","2026-09-10",null,null,null,"Sta 54 Greenville","100","1","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,54,null,"Sta 54 Greenville:  Annual ESD Test & Maintenance\n--9/8/26 through 9/10/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1479823",null,"2026-08-14","2026-08-18",null,null,null,"Sta 54","100","1","Sub-Station Transformer Inspection & Cleaning","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,54.01,null,"Sta 54:  Sub-Station Transformer Inspection & Cleaning\n--8/14/26 through 8/18/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-282643",null,"2026-05-18","2026-05-29",null,null,null,"Sta 54","100","1","Unit 2D - 4K Inpection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,54.05,null,"Sta 54:  Unit 2D - 4K Inpection\n--5/18/26 through 5/29/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1492863",null,"2026-09-09","2026-09-09",null,null,null,"Sta 54","100","3","Unit 1D - Annual Safety Device Checks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,54.064,null,"Sta 54:  Unit 1D - Annual Safety Device Checks\n--9/9/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-225137",null,"2026-02-26","2026-12-31",null,null,null,"MLV 54-3 to MLV 106-3","100","1","Emergent Repair - CAO","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,54.31,null,"MLV 54-3 to MLV 106-3:  Emergent Repair - CAO\n--2/26/26 through 12/31/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-225132",null,"2026-02-26","2026-12-31",null,null,null,"MLV 54-3 to MLV 106-3","100","1","Emergent Repair - CAO","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,54.32,null,"MLV 54-3 to MLV 106-3:  Emergent Repair - CAO\n--2/26/26 through 12/31/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-149115",null,"2026-05-04","2026-06-26",null,null,null,"MLV 55-1 to MLV 56-1","100","1","PHMSA Immediate","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,55.1,null,"MLV 55-1 to MLV 56-1:  PHMSA Immediate\n--5/4/26 through 6/26/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-149116",null,"2026-03-18","2026-04-24",null,null,null,"MLV 56-1 to MLV 57-1","100","1","PHMSA Immediate","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,56.1,null,"MLV 56-1 to MLV 57-1:  PHMSA Immediate\n--3/18/26 through 4/24/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-300067",null,"2026-07-13","2026-07-27",null,null,null,"MLV 59-3A to MLV 63-3S","100","1","Pipe Replacements","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,59.3,null,"MLV 59-3A to MLV 63-3S:  Pipe Replacements\n--7/13/26 through 7/27/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1411366",null,"2026-08-25","2026-08-27",null,null,null,"Sta 63 Batesville","100","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,63,null,"Sta 63 Batesville:  Annual ESD Test\n--8/25/26 through 8/27/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1492861",null,"2026-08-10","2026-08-21",null,null,null,"Sta 63","100","1","Building B - Valve Replacement & Pump Modification","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,63.02,null,"Sta 63:  Building B - Valve Replacement & Pump Modification\n--8/10/26 through 8/21/26:  This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1479828",null,"2026-06-21","2026-06-23",null,null,null,"Sta 63","100","1","Unit 1D - Safety Device Checks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,63.064,null,"Sta 63:  Unit 1D - Safety Device Checks\n--6/21/26 through 6/23/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1479829",null,"2026-06-30","2026-07-02",null,null,null,"Sta 63","100","1","Unit 2D - Safety Device Checks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,63.066000000000003,null,"Sta 63:  Unit 2D - Safety Device Checks\n--6/30/26 through 7/2/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1479667",null,"2026-05-12","2026-05-12",null,null,null,"MLV 69-1L to MLV 69-1CR","100","1","Pig Runs - Cleaning / Gauge 5/12/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,69.099999999999994,null,"MLV 69-1L to MLV 69-1CR:  Pig Runs - Cleaning / Gauge 5/12/26\n--5/12/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1479668",null,"2026-05-14","2026-05-14",null,null,null,"MLV 69-1L to MLV 69-1CR","100","1","Pig Runs - Cal / IMU MFL-A 5/14/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,69.099999999999994,null,"MLV 69-1L to MLV 69-1CR:  Pig Runs - Cal / IMU MFL-A 5/14/26\n--5/14/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X26-318620",null,"2026-05-18","2026-05-22",null,null,null,"Sta 71","100","1","Scrubber/Filter/Separator Clean, Inspect & Filter Change","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,71,null,"Sta 71:  Scrubber/Filter/Separator Clean, Inspect & Filter Change\n--5/18/26 through 5/22/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1411658",null,"2026-05-19","2026-05-20",null,null,null,"Sta 71 Middleton","100","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,71,null,"Sta 71 Middleton:  Annual ESD Test\n--5/19/26 through 5/20/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-178172",null,"2026-03-30","2026-04-03",null,null,null,"Sta 71","100","1","Unit 1A - Engine Inspections","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,71.001000000000005,null,"Sta 71:  Unit 1A - Engine Inspections\n--3/30/26 through 4/3/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X23-1196655",null,"2023-11-28","2026-04-30",null,null,null,"Sta 71","100","1","Unit 3A - Discharge Bottle Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,71.003,null,"Sta 71:  Unit 3A - Discharge Bottle Inspection\n--11/28/23 through 4/30/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-178176",null,"2026-05-04","2026-05-07",null,null,null,"Sta 71","100","1","Unit 5A - Engine Inspections","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,71.004999999999995,null,"Sta 71:  Unit 5A - Engine Inspections\n--5/4/26 through 5/7/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-178177","***","2026-03-09","2026-04-10","Project Change",null,"2026-03-27","Sta 71","100","1","Unit 6A - Engine Inspections","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,71.006,"----end_date--------------model_loc--","***Sta 71:  Unit 6A - Engine Inspections\n--3/9/26 through 4/10/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***\nDate Change, Previously scheduled 3/9/26 to 3/27/26.\n………………………………"]
["X24-262275",null,"2024-04-08","2026-12-31",null,null,null,"Sta 71","100","1","Unit 7A Replace Crank End Compressor Gasket","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,71.007000000000005,null,"Sta 71:  Unit 7A Replace Crank End Compressor Gasket\n--4/8/24 through 12/31/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-178178",null,"2026-03-30","2026-04-03",null,null,null,"Sta 71","100","1","Unit 8A - Engine Inspections","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,71.007999999999996,null,"Sta 71:  Unit 8A - Engine Inspections\n--3/30/26 through 4/3/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-299688","***","2026-04-13","2026-04-16","Project Change","2026-04-06","2026-04-09","Sta 71","500","1","Unit 5B - Engine Inspections","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,71.021000000000001,"--start_date--end_date--------------model_loc--","***Sta 71:  Unit 5B - Engine Inspections\n--4/13/26 through 4/16/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***\nDate Change, Previously scheduled 4/6/26 to 4/9/26.\n………………………………"]
["X26-378894","***","2026-04-06","2026-04-08","Added",null,null,"Sta 71","100","1","Unit 6B - GHG Leaks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,71.022999999999996,"------","***Sta 71:  Unit 6B - GHG Leaks\n--4/6/26 through 4/8/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***Added\n………………………………"]
["X26-378895","***","2026-04-08","2026-04-10","Added",null,null,"Sta 71","100","1","Unit 7B - GHG Leaks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,71.024000000000001,"------","***Sta 71:  Unit 7B - GHG Leaks\n--4/8/26 through 4/10/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***Added\n………………………………"]
["X26-178179","***","2026-03-09","2026-04-10","Project Change",null,"2026-03-27","Sta 71","100","1","Unit 2B - Engine Inspections","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,71.033000000000001,"----end_date--------------model_loc--","***Sta 71:  Unit 2B - Engine Inspections\n--3/9/26 through 4/10/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***\nDate Change, Previously scheduled 3/9/26 to 3/27/26.\n………………………………"]
["X26-178180","***","2026-02-16","2026-04-24","Project Change",null,"2026-03-27","Sta 71","100","1","Unit 3B - Engine Inspections","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,71.034999999999997,"----end_date--------------model_loc--","***Sta 71:  Unit 3B - Engine Inspections\n--2/16/26 through 4/24/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***\nDate Change, Previously scheduled 2/16/26 to 3/27/26.\n………………………………"]
["X26-178182",null,"2026-04-13","2026-04-16",null,null,null,"Sta 71","100","1","Unit 6B - Engine Inspections","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,71.037000000000006,null,"Sta 71:  Unit 6B - Engine Inspections\n--4/13/26 through 4/16/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-178183",null,"2026-04-20","2026-04-23",null,null,null,"Sta 71","100","1","Unit 7B - Engine Inspections","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,71.037999999999997,null,"Sta 71:  Unit 7B - Engine Inspections\n--4/20/26 through 4/23/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-178184",null,"2026-04-27","2026-04-30",null,null,null,"Sta 71","100","1","Unit 8B - Engine Inspections","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,71.039000000000001,null,"Sta 71:  Unit 8B - Engine Inspections\n--4/27/26 through 4/30/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1411667",null,"2026-05-26","2026-05-26",null,null,null,"Sta 79 Lobelville","100","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,79,null,"Sta 79 Lobelville:  Annual ESD Test\n--5/26/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1527940",null,"2026-05-26","2026-05-29",null,null,null,"Sta 79","100","2","Scrubber/Filter/Separator Clean, Inspect & Filter Change","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,79.099999999999994,null,"Sta 79:  Scrubber/Filter/Separator Clean, Inspect & Filter Change\n--5/26/26 through 5/29/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-309693","***","2026-04-13","2026-06-05","Completed",null,null,"MLV 79-3L to MLV 80-3","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,79.3,"------","***MLV 79-3L to MLV 80-3:  Anomaly Remediation\n***Completed"]
["X25-996875",null,"2026-04-14","2026-04-14",null,null,null,"MLV 79-4 to MLV 71-4D","100","1","Pig Runs - Cleaning / Gauge 4/14/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,79.400000000000006,null,"MLV 79-4 to MLV 71-4D:  Pig Runs - Cleaning / Gauge 4/14/26\n--4/14/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-996878",null,"2026-04-16","2026-04-16",null,null,null,"MLV 79-4 to MLV 71-4D","100","1","Pig Runs - CAL / IMU 4/16/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,79.41,null,"MLV 79-4 to MLV 71-4D:  Pig Runs - CAL / IMU 4/16/26\n--4/16/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-996881",null,"2026-04-21","2026-04-21",null,null,null,"MLV 79-4 to MLV 71-4D","100","1","Pig Runs - MFL-C 4/21/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,79.42,null,"MLV 79-4 to MLV 71-4D:  Pig Runs - MFL-C 4/21/26\n--4/21/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-996883",null,"2026-04-23","2026-04-23",null,null,null,"MLV 79-4 to MLV 71-4D","100","1","Pig Runs - EMAT 4/23/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,79.430000000000007,null,"MLV 79-4 to MLV 71-4D:  Pig Runs - EMAT 4/23/26\n--4/23/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X26-309694","***","2026-06-08","2026-06-19","Completed",null,null,"MLV 81-3 to MLV 82-3","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,81.3,"------","***MLV 81-3 to MLV 82-3:  Anomaly Remediation\n***Completed"]
["X25-1385295",null,"2026-10-06","2026-10-06",null,null,null,"MLV 82-1 to MLV 87-1","100","2","Pig Run - Cleaning / Gauge","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,82.1,null,"MLV 82-1 to MLV 87-1:  Pig Run - Cleaning / Gauge\n--10/6/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1385297",null,"2026-10-08","2026-10-08",null,null,null,"MLV 82-1 to MLV 87-1","100","2","Pig Run - AFD/Cal/IMU","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,82.1,null,"MLV 82-1 to MLV 87-1:  Pig Run - AFD/Cal/IMU\n--10/8/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1385298",null,"2026-10-13","2026-10-13",null,null,null,"MLV 82-1 to MLV 87-1","100","2","Pig Run - EMAT","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,82.1,null,"MLV 82-1 to MLV 87-1:  Pig Run - EMAT\n--10/13/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1389406",null,"2026-11-02","2026-11-13",null,null,null,"MLV 82-1C to MLV 87-1S","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,82.1,null,"MLV 82-1C to MLV 87-1S:  Anomaly Remediation\n--11/2/26 through 11/13/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-309961",null,"2026-08-03","2026-08-07",null,null,null,"MLV 82-2C to MLV 87-2S","100","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,82.2,null,"MLV 82-2C to MLV 87-2S:  Anomaly Remediation\n--8/3/26 through 8/7/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1411809",null,"2026-10-21","2026-10-22",null,null,null,"Sta 87 Portland","100","2","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,87,null,"Sta 87 Portland:  Annual ESD Test\n--10/21/26 through 10/22/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1514691",null,"2026-12-08","2026-12-08",null,null,null,"Sta 87","100","1","Unit 1D - Safety Device Tests","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,87.063999999999993,null,"Sta 87:  Unit 1D - Safety Device Tests\n--12/8/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1525763",null,"2026-10-20","2026-10-21",null,null,null,"Sta 87","100","1","Unit 1E - Scrubber/Filter/Separator Clean, Inspect & Filter Change","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,87.064999999999998,null,"Sta 87:  Unit 1E - Scrubber/Filter/Separator Clean, Inspect & Filter Change\n--10/20/26 through 10/21/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1514696",null,"2026-12-15","2026-12-15",null,null,null,"Sta 87","100","1","Unit 1E - Safety Device Testing","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,87.064999999999998,null,"Sta 87:  Unit 1E - Safety Device Testing\n--12/15/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1525761",null,"2026-02-20","2026-04-10",null,null,null,"Sta 87","100","1","Unit 2E Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,87.066000000000003,null,"Sta 87:  Unit 2E Overhaul\n--2/20/26 through 4/10/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1525762",null,"2026-09-01","2026-09-30",null,null,null,"Sta 87","100","1","Unit 2E - Replace Compressor Valves","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,87.066000000000003,null,"Sta 87:  Unit 2E - Replace Compressor Valves\n--9/1/26 through 9/30/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1525766",null,"2026-10-22","2026-10-23",null,null,null,"Sta 87","100","1","Unit 2E - Scrubber/Filter/Separator Clean, Inspect & Filter Change","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,87.066000000000003,null,"Sta 87:  Unit 2E - Scrubber/Filter/Separator Clean, Inspect & Filter Change\n--10/22/26 through 10/23/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1514693",null,"2026-12-09","2026-12-09",null,null,null,"Sta 87","100","1","Unit 2D - Safety Device Tests","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,87.066000000000003,null,"Sta 87:  Unit 2D - Safety Device Tests\n--12/9/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1514697",null,"2026-12-16","2026-12-16",null,null,null,"Sta 87","100","1","Unit 2E - Safety Device Tests","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,87.066000000000003,null,"Sta 87:  Unit 2E - Safety Device Tests\n--12/16/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1525771",null,"2026-06-01","2026-09-30",null,null,null,"Sta 87","100","1","Unit 3D - Power side Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,87.066999999999993,null,"Sta 87:  Unit 3D - Power side Overhaul\n--6/1/26 through 9/30/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1514694",null,"2026-12-10","2026-12-10",null,null,null,"Sta 87","100","1","Unit 3D - Safety Device Tests","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,87.066999999999993,null,"Sta 87:  Unit 3D - Safety Device Tests\n--12/10/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1385285",null,"2026-05-14","2026-05-14",null,null,null,"MLV 87-3 to MLV 96-3","100","2","Pig Run - Cleaning/Gauge","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,87.3,null,"MLV 87-3 to MLV 96-3:  Pig Run - Cleaning/Gauge\n--5/14/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1385286",null,"2026-05-19","2026-05-19",null,null,null,"MLV 87-3 to MLV 96-3","100","2","Pig Run - AFD","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,87.3,null,"MLV 87-3 to MLV 96-3:  Pig Run - AFD\n--5/19/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1385288",null,"2026-05-21","2026-05-21",null,null,null,"MLV 87-3 to MLV 96-3","100","2","Pig Run - EMAT","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,87.3,null,"MLV 87-3 to MLV 96-3:  Pig Run - EMAT\n--5/21/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X26-203398",null,"2026-05-26","2026-05-26",null,null,null,"MLV 87-3 to MLV 96-3","100","2","Pig Run - MDS","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,87.3,null,"MLV 87-3 to MLV 96-3:  Pig Run - MDS\n--5/26/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1411830",null,"2026-06-09","2026-06-10",null,null,null,"Sta 96 Campbellsville","100","2","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,96,null,"Sta 96 Campbellsville:  Annual ESD Test\n--6/9/26 through 6/10/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1411869",null,"2026-06-09","2026-06-12",null,null,null,"Sta 96 Campbellsville","100","2","Annual Substation Inspection","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,96.000100000000003,null,"Sta 96 Campbellsville:  Annual Substation Inspection\n--6/9/26 through 6/12/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1288900","***","2026-03-16","2026-04-03","Completed",null,null,"Sta 96","100","2","Unit 1D - Compressor Valves","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,96.063999999999993,"------","***Sta 96:  Unit 1D - Compressor Valves\n***Completed"]
["X25-1525756",null,"2026-08-10","2026-08-17",null,null,null,"Sta 96","100","2","Unit 1D - Install Ball Grove Valve","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,96.063999999999993,null,"Sta 96:  Unit 1D - Install Ball Grove Valve\n--8/10/26 through 8/17/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1525755",null,"2026-07-05","2026-07-09",null,null,null,"Sta 96","100","2","Unit 2D Replace Compressor Valves","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,96.064999999999998,null,"Sta 96:  Unit 2D Replace Compressor Valves\n--7/5/26 through 7/9/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1525757",null,"2026-08-03","2026-08-07",null,null,null,"Sta 96","100","2","Unit 2D - Install Ball Grove Valve","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,96.064999999999998,null,"Sta 96:  Unit 2D - Install Ball Grove Valve\n--8/3/26 through 8/7/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1406582",null,"2026-03-23","2026-04-04",null,null,null,"MLV 100-1A to MLV 101-1R","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,96.1,null,"MLV 100-1A to MLV 101-1R:  Anomaly Remediation\n--3/23/26 through 4/4/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-288371",null,"2026-04-13","2026-04-17",null,null,null,"MLV 96-1L to MLV 97-1","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,96.1,null,"MLV 96-1L to MLV 97-1:  Anomaly Remediation\n--4/13/26 through 4/17/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-159443",null,"2026-05-27","2026-06-10",null,null,null,"MLV 96-3BR to MLV 96-3BL","100","2","Spike Test","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,96.3,null,"MLV 96-3BR to MLV 96-3BL:  Spike Test\n--5/27/26 through 6/10/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1385299",null,"2026-10-19","2026-10-19",null,null,null,"MLV 96-3 to MLV 97-3","100","2","Pig Run - Cleaning / Gauge","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,96.3,null,"MLV 96-3 to MLV 97-3:  Pig Run - Cleaning / Gauge\n--10/19/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1385301",null,"2026-10-20","2026-10-20",null,null,null,"MLV 96-3 to MLV 97-3","100","2","Pig Run - AFD","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,96.3,null,"MLV 96-3 to MLV 97-3:  Pig Run - AFD\n--10/20/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1385302",null,"2026-10-21","2026-10-21",null,null,null,"MLV 96-3 to MLV 97-3","100","2","Pig Run - EMAT","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,96.3,null,"MLV 96-3 to MLV 97-3:  Pig Run - EMAT\n--10/21/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1385303",null,"2026-10-22","2026-10-22",null,null,null,"MLV 96-3 to MLV 97-3","100","2","Pig Run - MDS","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,96.3,null,"MLV 96-3 to MLV 97-3:  Pig Run - MDS\n--10/22/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X26-159442",null,"2026-06-11","2026-06-20",null,null,null,"MLV 96-4D to MLV 96-4BL","100","2","Spike Test","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,96.4,null,"MLV 96-4D to MLV 96-4BL:  Spike Test\n--6/11/26 through 6/20/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-159448",null,"2026-06-22","2026-07-13",null,null,null,"MLV 96-5S to MLV 96-5BL","100","2","Spike Test","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,96.5,null,"MLV 96-5S to MLV 96-5BL:  Spike Test\n--6/22/26 through 7/13/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-36674",null,"2026-10-27","2026-10-27",null,null,null,"MLV 97-3 to MLV 106-3","100","2","Pig Run - Cleaning / Gauge","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,97.3,null,"MLV 97-3 to MLV 106-3:  Pig Run - Cleaning / Gauge\n--10/27/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X26-36679",null,"2026-10-29","2026-10-29",null,null,null,"MLV 97-3 to MLV 106-3","100","2","Pig Run - MFL-S","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,97.3,null,"MLV 97-3 to MLV 106-3:  Pig Run - MFL-S\n--10/29/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X26-36682",null,"2026-11-03","2026-11-03",null,null,null,"MLV 97-3 to MLV 106-3","100","2","Pig Run - MFL-C","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,97.3,null,"MLV 97-3 to MLV 106-3:  Pig Run - MFL-C\n--11/3/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X26-36685",null,"2026-11-05","2026-11-05",null,null,null,"MLV 97-3 to MLV 106-3","100","2","Pig Run - EMAT","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,97.3,null,"MLV 97-3 to MLV 106-3:  Pig Run - EMAT\n--11/5/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X26-288369","***","2026-03-27","2026-04-02","Project Change","2026-04-06","2026-04-10","MLV 98-1 to MLV 99-1","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,98.1,"--start_date--end_date--------------model_loc--","***MLV 98-1 to MLV 99-1:  Anomaly Remediation\n--3/27/26 through 4/2/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n***\nDate Change, Previously scheduled 4/6/26 to 4/10/26.\n………………………………"]
["X26-309960",null,"2026-05-26","2026-06-26",null,null,null,"MLV 102-1A1 to MLV 106-1S","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,102.1,null,"MLV 102-1A1 to MLV 106-1S:  Anomaly Remediation\n--5/26/26 through 6/26/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1389401",null,"2026-09-30","2026-10-04",null,null,null,"MLV 102-2A to MLV 106-1S","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,102.1,null,"MLV 102-2A to MLV 106-1S:  Anomaly Remediation\n--9/30/26 through 10/4/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-173448",null,"2026-08-10","2026-08-31",null,null,null,"MLV 102-3 to MLV 103-3","100","2","Special Permit Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,102.3,null,"MLV 102-3 to MLV 103-3:  Special Permit Pipe Replacement\n--8/10/26 through 8/31/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-176234",null,"2026-05-27","2026-06-10",null,null,null,"MLV 104-1 to MLV 105-1","200","4","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,104.1,null,"MLV 104-1 to MLV 105-1:  Anomaly Remediation\n--5/27/26 through 6/10/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1411071",null,"2026-06-02","2026-06-05",null,null,null,"Sta 106 Clay City","100","2","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,106,null,"Sta 106 Clay City:  Annual ESD Test & Maintenance\n--6/2/26 through 6/5/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1508335",null,"2026-05-18","2026-05-20",null,null,null,"Sta. 106","100","2","Unit 4B - Replace Exhaust Silencer","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,106.004,null,"Sta. 106:  Unit 4B - Replace Exhaust Silencer\n--5/18/26 through 5/20/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1428453","***","2025-11-24","2026-04-02","Project Change",null,"2026-03-30","Sta 106","100","2","Unit 1C - Replace Power Cylinder Bearing #9","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,106.033,"----end_date--------------model_loc--","***Sta 106:  Unit 1C - Replace Power Cylinder Bearing #9\n--11/24/25 through 4/2/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***\nDate Change, Previously scheduled 11/24/25 to 3/30/26.\n………………………………"]
["X25-1508342",null,"2026-06-08","2026-06-12",null,null,null,"Sta. 106","100","2","C Building - Install Water Trech System","This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,106.04,null,"Sta. 106:  C Building - Install Water Trech System\n--6/8/26 through 6/12/26:  This project will require a building outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1508339","***","2026-04-06","2026-04-10","Project Change","2026-08-17","2026-08-21","Sta. 106","100","2","Unit 1D - Exhaust Collector","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,106.06399999999999,"--start_date--end_date--------------model_loc--","***Sta. 106:  Unit 1D - Exhaust Collector\n--4/6/26 through 4/10/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***\nDate Change, Previously scheduled 8/17/26 to 8/21/26.\n………………………………"]
["X25-1477455",null,"2026-04-06","2026-04-10",null,null,null,"Sta 106","100","2","Unit 1D -  8K Solar Turbine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,106.06399999999999,null,"Sta 106:  Unit 1D -  8K Solar Turbine Inspection\n--4/6/26 through 4/10/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1477457",null,"2026-08-18","2026-08-20",null,null,null,"Sta 106","100","2","Unit 1D -  4K Solar Turbine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,106.06399999999999,null,"Sta 106:  Unit 1D -  4K Solar Turbine Inspection\n--8/18/26 through 8/20/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1477460",null,"2026-09-22","2026-09-24",null,null,null,"Sta 106","100","2","Unit 2D -  4K Solar Turbine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,106.065,null,"Sta 106:  Unit 2D -  4K Solar Turbine Inspection\n--9/22/26 through 9/24/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1385292","***","2026-03-31","2026-03-31","Completed",null,null,"MLV 106-2 to MLV 110-2","100","3","Pig Run - Cleaning / Gauge","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.","420038 MOREHEAD/TGP MOREHEAD KY ROWAN\n420462 DELTA NG/TGP DELTA FARMERS KY ROWAN\n420212 DELTA NG/TGP SALT LICK KY BATH\n420430 DELTA NG/TGP JEFFERSONVILLE KY MONT",106.2,"------","***MLV 106-2 to MLV 110-2:  Pig Run - Cleaning / Gauge\n***Completed\nThe following meters are available for nominations:\n420038 MOREHEAD/TGP MOREHEAD KY ROWAN\n420462 DELTA NG/TGP DELTA FARMERS KY ROWAN\n420212 DELTA NG/TGP SALT LICK KY BATH\n420430 DELTA NG/TGP JEFFERSONVILLE KY MONT"]
["X25-1385293",null,"2026-04-02","2026-04-02",null,null,null,"MLV 106-2 to MLV 110-2","100","3","Pig Run - Cal / IMU","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.","420038 MOREHEAD/TGP MOREHEAD KY ROWAN\n420462 DELTA NG/TGP DELTA FARMERS KY ROWAN\n420212 DELTA NG/TGP SALT LICK KY BATH\n420430 DELTA NG/TGP JEFFERSONVILLE KY MONT",106.2,null,"MLV 106-2 to MLV 110-2:  Pig Run - Cal / IMU\n--4/2/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.  \n420038 MOREHEAD/TGP MOREHEAD KY ROWAN\n420462 DELTA NG/TGP DELTA FARMERS KY ROWAN\n420212 DELTA NG/TGP SALT LICK KY BATH\n420430 DELTA NG/TGP JEFFERSONVILLE KY MONT\n………………………………"]
["X25-1385294",null,"2026-04-07","2026-04-07",null,null,null,"MLV 106-2 to MLV 110-2","100","3","Pig Run - MFL-A","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.","420038 MOREHEAD/TGP MOREHEAD KY ROWAN\n420462 DELTA NG/TGP DELTA FARMERS KY ROWAN\n420212 DELTA NG/TGP SALT LICK KY BATH\n420430 DELTA NG/TGP JEFFERSONVILLE KY MONT",106.2,null,"MLV 106-2 to MLV 110-2:  Pig Run - MFL-A\n--4/7/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.  \n420038 MOREHEAD/TGP MOREHEAD KY ROWAN\n420462 DELTA NG/TGP DELTA FARMERS KY ROWAN\n420212 DELTA NG/TGP SALT LICK KY BATH\n420430 DELTA NG/TGP JEFFERSONVILLE KY MONT\n………………………………"]
["X26-309955",null,"2026-04-06","2026-04-17",null,null,null,"MLV 106-4D to MLV 110-4","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,106.4,null,"MLV 106-4D to MLV 110-4:  Anomaly Remediation\n--4/6/26 through 4/17/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1411131",null,"2026-10-06","2026-10-06",null,null,null,"Sta 107A North Means","100","2","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,107,null,"Sta 107A North Means:  Annual ESD Test\n--10/6/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-352467","***","2026-07-06","2026-07-27","Project Change","2026-05-04","2026-05-18","MLV 107-7 to 110-7","100","2","Valve Installation & Crossover Work","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,107.7,"--start_date--end_date--------------model_loc--","***MLV 107-7 to 110-7:  Valve Installation & Crossover Work\n--7/6/26 through 7/27/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n***\nDate Change, Previously scheduled 5/4/26 to 5/18/26.\n………………………………"]
["X26-279078","***","2026-05-19","2026-05-21","Project Change","2026-05-05","2026-05-07","Sta 409","400","0","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,109,"--start_date--end_date--------------model_loc--","***Sta 409:  Annual ESD Test & Maintenance\n--5/19/26 through 5/21/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***\nDate Change, Previously scheduled 5/5/26 to 5/7/26.\n………………………………"]
["X25-1240781",null,"2026-05-18","2026-05-26",null,null,null,"MLV 109-3","100","2","Crossover to Ln 4 Valve Replacements","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,109.3,null,"MLV 109-3:  Crossover to Ln 4 Valve Replacements\n--5/18/26 through 5/26/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1240788",null,"2026-05-27","2026-06-10",null,null,null,"MLV 109-3","100","2","Crossover to Ln 5 Valve Replacements","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,109.3,null,"MLV 109-3:  Crossover to Ln 5 Valve Replacements\n--5/27/26 through 6/10/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-102537",null,"2026-08-24","2026-08-31",null,null,null,"MLV 109-3A to MLV 110-3","100","2","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,109.35,null,"MLV 109-3A to MLV 110-3:  Pipe Replacement\n--8/24/26 through 8/31/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-102484",null,"2026-06-17","2026-07-02",null,null,null,"MLV 109-4 to MLV 110-4","100","2","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,109.4,null,"MLV 109-4 to MLV 110-4:  Pipe Replacement\n--6/17/26 through 7/2/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-352507","***","2026-07-28","2026-08-11","Project Change","2026-05-25","2026-06-15","MLV 109-4 to 110-4","100","2","Valve Installation & Crossover Work","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,109.4,"--start_date--end_date--------------model_loc--","***MLV 109-4 to 110-4:  Valve Installation & Crossover Work\n--7/28/26 through 8/11/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n***\nDate Change, Previously scheduled 5/25/26 to 6/15/26.\n………………………………"]
["X26-102511",null,"2026-07-27","2026-08-03",null,null,null,"MLV 109-5 to MLV 109-5A","100","2","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,109.5,null,"MLV 109-5 to MLV 109-5A:  Pipe Replacement\n--7/27/26 through 8/3/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-102524",null,"2026-08-10","2026-08-17",null,null,null,"MLV 109-5A to MLV 110-5","100","2","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,109.55,null,"MLV 109-5A to MLV 110-5:  Pipe Replacement\n--8/10/26 through 8/17/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-102503",null,"2026-07-13","2026-07-20",null,null,null,"MLV 109-7 to MLV 110-7","100","2","Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,109.7,null,"MLV 109-7 to MLV 110-7:  Pipe Replacement\n--7/13/26 through 7/20/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1411039",null,"2026-06-08","2026-06-12",null,null,null,"Sta 110 Morehead","100","2","Annual ESD Test & Substation Inspection","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,110,null,"Sta 110 Morehead:  Annual ESD Test & Substation Inspection\n--6/8/26 through 6/12/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1508327",null,"2026-08-24","2026-08-28",null,null,null,"Sta 110","100","2","Install ESD Silence Covers","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,110,null,"Sta 110:  Install ESD Silence Covers\n--8/24/26 through 8/28/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1508320","***","2026-05-18","2026-05-19","Project Change","2026-05-19",null,"Sta 110","100","2","Unit 6A - Motor Cleaning","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,110.006,"--start_date----------------model_loc--","***Sta 110:  Unit 6A - Motor Cleaning\n--5/18/26 through 5/19/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***\nDate Change, Previously scheduled 5/19/26 to 5/19/26.\n………………………………"]
["X25-1508313",null,"2026-10-13","2026-10-13",null,null,null,"Sta. 110","100","2","Unit 6A - VOITH Health Checks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,110.006,null,"Sta. 110:  Unit 6A - VOITH Health Checks\n--10/13/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1508322","***","2026-05-20","2026-05-21","Project Change",null,"2026-05-20","Sta 110","100","2","Unit 7A - Motor Cleaning","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,110.00700000000001,"----end_date--------------model_loc--","***Sta 110:  Unit 7A - Motor Cleaning\n--5/20/26 through 5/21/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***\nDate Change, Previously scheduled 5/20/26 to 5/20/26.\n………………………………"]
["X25-1508315",null,"2026-10-14","2026-10-14",null,null,null,"Sta. 110","100","2","Unit 7A - VOITH Health Checks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,110.00700000000001,null,"Sta. 110:  Unit 7A - VOITH Health Checks\n--10/14/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1508323","***","2026-05-26","2026-05-27","Project Change",null,"2026-05-26","Sta 110","100","2","Unit 8A - Motor Cleaning","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,110.008,"----end_date--------------model_loc--","***Sta 110:  Unit 8A - Motor Cleaning\n--5/26/26 through 5/27/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***\nDate Change, Previously scheduled 5/26/26 to 5/26/26.\n………………………………"]
["X25-1508317",null,"2026-10-15","2026-10-15",null,null,null,"Sta. 110","100","2","Unit  8A - VOITH Health Checks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,110.008,null,"Sta. 110:  Unit  8A - VOITH Health Checks\n--10/15/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1508324","***","2026-05-28","2026-05-29","Project Change","2026-05-27","2026-05-27","Sta 110","100","2","Unit 9A - Motor Cleaning","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,110.009,"--start_date--end_date--------------model_loc--","***Sta 110:  Unit 9A - Motor Cleaning\n--5/28/26 through 5/29/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***\nDate Change, Previously scheduled 5/27/26.\n………………………………"]
["X25-1508319",null,"2026-10-16","2026-10-16",null,null,null,"Sta. 110","100","2","Unit  9A - VOITH Health Checks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,110.009,null,"Sta. 110:  Unit  9A - VOITH Health Checks\n--10/16/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-302552",null,"2026-07-20","2026-07-25",null,null,null,"MLV 110-4 to MLV 111-4","100","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,110.4,null,"MLV 110-4 to MLV 111-4:  Anomaly Remediation\n--7/20/26 through 7/25/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1355308",null,"2026-04-28","2026-04-29",null,null,null,"Sta 114 Catlettsburg","100","3","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,114,null,"Sta 114 Catlettsburg:  Annual ESD Test\n--4/28/26 through 4/29/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1508332",null,"2026-05-18","2026-05-20",null,null,null,"Sta 114","100","2","Annual Substation Inspection","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,114,null,"Sta 114:  Annual Substation Inspection\n--5/18/26 through 5/20/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1355200",null,"2026-06-29","2026-07-01",null,null,null,"Sta 114","100","3","Unit 1D - Solar Turbine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,114.04900000000001,null,"Sta 114:  Unit 1D - Solar Turbine Inspection\n--6/29/26 through 7/1/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1355203",null,"2026-12-14","2026-12-16",null,null,null,"Sta 114","100","3","Unit 1D - Solar Turbine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,114.04900000000001,null,"Sta 114:  Unit 1D - Solar Turbine Inspection\n--12/14/26 through 12/16/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-173447",null,"2026-08-10","2026-08-31",null,null,null,"MLV 117-3 to MLV 118-3","100","2","Special Permit Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,117.3,null,"MLV 117-3 to MLV 118-3:  Special Permit Pipe Replacement\n--8/10/26 through 8/31/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1355309",null,"2026-10-05","2026-10-06",null,null,null,"Sta 118A Tyler Mountain","100","3","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,118,null,"Sta 118A Tyler Mountain:  Annual ESD Test\n--10/5/26 through 10/6/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1355204","***","2026-03-30","2026-04-01","Completed",null,null,"Sta 118A","100","3","Solar Turbine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,118.001,"------","***Sta 118A:  Solar Turbine Inspection\n***Completed"]
["X25-1355206",null,"2026-09-14","2026-09-16",null,null,null,"Sta 118A","100","3","Solar Turbine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,118.001,null,"Sta 118A:  Solar Turbine Inspection\n--9/14/26 through 9/16/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1355311",null,"2026-04-28","2026-04-29",null,null,null,"Sta 119A Rocky Fork","100","3","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,119,null,"Sta 119A Rocky Fork:  Annual ESD Test\n--4/28/26 through 4/29/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1355210",null,"2026-08-10","2026-08-12",null,null,null,"Sta 119A","100","3","Unit 1A - Solar Turbine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,119.001,null,"Sta 119A:  Unit 1A - Solar Turbine Inspection\n--8/10/26 through 8/12/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-78121",null,"2026-04-13","2026-05-22",null,null,null,"MLV 118-1 to MLV 121-1","100","3","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,119.1,null,"MLV 118-1 to MLV 121-1:  Anomaly Remediation\n--4/13/26 through 5/22/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-173444",null,"2026-08-10","2026-08-31",null,null,null,"MLV 119-2 to MLV 119-2A","100","2","Special Permit Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,119.2,null,"MLV 119-2 to MLV 119-2A:  Special Permit Pipe Replacement\n--8/10/26 through 8/31/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1411167",null,"2026-06-16","2026-06-19",null,null,null,"Sta 200 Greenup","200","4","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,200,null,"Sta 200 Greenup:  Annual ESD Test\n--6/16/26 through 6/19/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-352324",null,"2026-04-20","2026-04-24",null,null,null,"Sta 200","200","4","Unit 3A - Packing","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,200.00299999999999,null,"Sta 200:  Unit 3A - Packing\n--4/20/26 through 4/24/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-352315",null,"2026-04-13","2026-04-17",null,null,null,"Sta 200","200","4","Unit 12A - Packing","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,200.012,null,"Sta 200:  Unit 12A - Packing\n--4/13/26 through 4/17/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-302551",null,"2026-07-13","2026-07-18",null,null,null,"MLV 200-3L to MLV 200-3AR","200","4","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,200.3,null,"MLV 200-3L to MLV 200-3AR:  Anomaly Remediation\n--7/13/26 through 7/18/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-302550",null,"2026-07-06","2026-07-11",null,null,null,"MLV 202-1 to MLV 203-1","200","4","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,202.1,null,"MLV 202-1 to MLV 203-1:  Anomaly Remediation\n--7/6/26 through 7/11/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1368005",null,"2026-08-17","2026-09-26",null,null,null,"MLV 202-2 to MLV 203-2","200","2","CLASS CHANGE REPLACEMENT TGP 202-2","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,202.2,null,"MLV 202-2 to MLV 203-2:  CLASS CHANGE REPLACEMENT TGP 202-2\n--8/17/26 through 9/26/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-302549",null,"2026-05-25","2026-05-30",null,null,null,"MLV 202-3 to MLV 203-3","200","4","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,202.3,null,"MLV 202-3 to MLV 203-3:  Anomaly Remediation\n--5/25/26 through 5/30/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-155602",null,"2026-09-24","2026-09-26",null,null,null,"Sta 204","200","4","Scrubber Filter Change","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,204,null,"Sta 204:  Scrubber Filter Change\n--9/24/26 through 9/26/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-309988",null,"2027-03-08","2027-03-11",null,null,null,"Sta 204","200","4","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,204,null,"Sta 204:  Annual ESD Test\n--3/8/27 through 3/11/27:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-364035","***","2026-04-13","2026-04-16","Added",null,null,"Sta 204","200","4","Unit 1A - P4 & P6 Pull Piston","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,204.001,"------","***Sta 204:  Unit 1A - P4 & P6 Pull Piston\n--4/13/26 through 4/16/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***Added\n………………………………"]
["X26-343094","***","2026-03-23","2026-03-26","Completed",null,null,"Sta 204","100","0","Unit 11A - P10 Knock / Water Leak","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,204.011,"------","***Sta 204:  Unit 11A - P10 Knock / Water Leak\n***Completed"]
["X25-1428261",null,"2026-04-14","2026-04-14",null,null,null,"MLV 204-3 to MLV 209-3","200","4","Pig Run - Gauge/Cleaning","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,204.3,null,"MLV 204-3 to MLV 209-3:  Pig Run - Gauge/Cleaning\n--4/14/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1428264",null,"2026-04-16","2026-04-16",null,null,null,"MLV 204-3 to MLV 209-3","200","4","Pig Run - Cal/IMU","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,204.3,null,"MLV 204-3 to MLV 209-3:  Pig Run - Cal/IMU\n--4/16/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1428270",null,"2026-04-21","2026-04-21",null,null,null,"MLV 204-3 to MLV 209-3","200","4","Pig Run - MFL-C","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,204.3,null,"MLV 204-3 to MLV 209-3:  Pig Run - MFL-C\n--4/21/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1428273",null,"2026-04-23","2026-04-23",null,null,null,"MLV 204-3 to MLV 209-3","200","4","Pig Run - EMAT","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,204.3,null,"MLV 204-3 to MLV 209-3:  Pig Run - EMAT\n--4/23/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1365480",null,"2026-05-27","2026-06-10",null,null,null,"MLV 204-4 to MLV 206-4","200","4","Replace MLV 205-4","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","44423 REX/TGP BIG MUSKIE GUERNSEY",204.4,null,"MLV 204-4 to MLV 206-4:  Replace MLV 205-4\n--5/27/26 through 6/10/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  \n44423 REX/TGP BIG MUSKIE GUERNSEY\n………………………………"]
["X25-1380238",null,"2026-11-10","2026-11-10",null,null,null,"MLV 204-4 to MLV 209-4","200","4","Pig Run - Gauge","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,204.4,null,"MLV 204-4 to MLV 209-4:  Pig Run - Gauge\n--11/10/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1380240",null,"2026-11-12","2026-11-12",null,null,null,"MLV 204-4 to MLV 209-4","200","4","Pig Run - Cal/IMU","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,204.4,null,"MLV 204-4 to MLV 209-4:  Pig Run - Cal/IMU\n--11/12/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1380242",null,"2026-11-17","2026-11-17",null,null,null,"MLV 204-4 to MLV 209-4","200","4","Pig Run - MFL-C","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,204.4,null,"MLV 204-4 to MLV 209-4:  Pig Run - MFL-C\n--11/17/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1380243",null,"2026-11-19","2026-11-19",null,null,null,"MLV 204-4 to MLV 209-4","200","4","Pig Run - EMAT","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,204.4,null,"MLV 204-4 to MLV 209-4:  Pig Run - EMAT\n--11/19/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1412849",null,"2026-05-18","2026-08-18",null,null,null,"MLV 205-3 to MLV 206-3","200","4","Landslide Mitigation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,205.3,null,"MLV 205-3 to MLV 206-3:  Landslide Mitigation\n--5/18/26 through 8/18/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1412791",null,"2026-05-18","2026-08-18",null,null,null,"MLV 205-4 to MLV 206-4","200","4","Landslide Mitigation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,205.4,null,"MLV 205-4 to MLV 206-4:  Landslide Mitigation\n--5/18/26 through 8/18/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1365484",null,"2026-05-27","2026-06-10",null,null,null,"MLV 205-4 to MLV 207-4","200","4","Replace MLV 206-4","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","44423 REX/TGP BIG MUSKIE GUERNSEY",205.4,null,"MLV 205-4 to MLV 207-4:  Replace MLV 206-4\n--5/27/26 through 6/10/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  \n44423 REX/TGP BIG MUSKIE GUERNSEY\n………………………………"]
["X26-302553",null,"2026-07-27","2026-08-01",null,null,null,"MLV 206-2 to MLV 207-2","200","4","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,206.2,null,"MLV 206-2 to MLV 207-2:  Anomaly Remediation\n--7/27/26 through 8/1/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1412769",null,"2026-05-18","2026-08-18",null,null,null,"MLV 206-3 to MLV 207-3","200","4","Landslide Mitigation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,206.3,null,"MLV 206-3 to MLV 207-3:  Landslide Mitigation\n--5/18/26 through 8/18/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1412818",null,"2026-05-18","2026-08-18",null,null,null,"MLV 206-4 to MLV 207-4","200","4","Landslide Mitigation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,206.4,null,"MLV 206-4 to MLV 207-4:  Landslide Mitigation\n--5/18/26 through 8/18/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1365485",null,"2026-05-27","2026-06-10",null,null,null,"MLV 206-4 to MLV 208-4","200","4","Replace MLV 207-4","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","44423 REX/TGP BIG MUSKIE GUERNSEY",206.4,null,"MLV 206-4 to MLV 208-4:  Replace MLV 207-4\n--5/27/26 through 6/10/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  \n44423 REX/TGP BIG MUSKIE GUERNSEY\n………………………………"]
["X25-1365487",null,"2026-05-27","2026-06-10",null,null,null,"MLV 207-4 to MLV 209-4","200","4","Replace Valve MLV 208-4","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","44423 REX/TGP BIG MUSKIE GUERNSEY",207.4,null,"MLV 207-4 to MLV 209-4:  Replace Valve MLV 208-4\n--5/27/26 through 6/10/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  \n44423 REX/TGP BIG MUSKIE GUERNSEY\n………………………………"]
["X26-25158",null,"2026-04-20","2026-05-01",null,null,null,"Sta 209 Cambridge","200","4","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations",null,209,null,"Sta 209 Cambridge:  Annual ESD Test & Maintenance\n--4/20/26 through 5/1/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations  \n………………………………"]
["X26-155600",null,"2026-09-21","2026-09-23",null,null,null,"Sta 209 Cambridge","200","4","Scrubber Filter","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,209,null,"Sta 209 Cambridge:  Scrubber Filter\n--9/21/26 through 9/23/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1566810","***","2026-04-13","2026-04-16","Project Change","2026-03-30","2026-04-02","Sta 209","200","4","Unit 6A - Punch Carbon","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,209.006,"--start_date--end_date--------------model_loc--","***Sta 209:  Unit 6A - Punch Carbon\n--4/13/26 through 4/16/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***\nDate Change, Previously scheduled 3/30/26 to 4/2/26.\n………………………………"]
["X26-364074","***","2026-04-01","2026-04-03","Added",null,null,"Sta 209","200","4","Unit 7A - Pain Suction Header","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,209.00700000000001,"------","***Sta 209:  Unit 7A - Pain Suction Header\n--4/1/26 through 4/3/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***Added\n………………………………"]
["X26-343123",null,"2026-05-04","2026-05-07",null,null,null,"Sta 209","200","4","Unit 8A - Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,209.00800000000001,null,"Sta 209:  Unit 8A - Crankcase Inspection\n--5/4/26 through 5/7/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1566840","***","2026-04-20","2026-04-24","Project Change","2026-04-06","2026-04-09","Sta 209","200","4","Unit 9A - Punch Carbon","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,209.00899999999999,"--start_date--end_date--------------model_loc--","***Sta 209:  Unit 9A - Punch Carbon\n--4/20/26 through 4/24/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***\nDate Change, Previously scheduled 4/6/26 to 4/9/26.\n………………………………"]
["X25-1566861","***","2026-04-27","2026-04-30","Project Change","2026-04-13","2026-04-16","Sta 209","200","4","Unit 10A - Punch Carbon","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,209.01,"--start_date--end_date--------------model_loc--","***Sta 209:  Unit 10A - Punch Carbon\n--4/27/26 through 4/30/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***\nDate Change, Previously scheduled 4/13/26 to 4/16/26.\n………………………………"]
["X26-231424","***","2026-03-23","2026-03-26","Completed",null,null,"Sta 209","200","4","Unit 11A - Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,209.011,"------","***Sta 209:  Unit 11A - Crankcase Inspection\n***Completed"]
["X26-231426","***","2026-04-06","2026-04-09","Project Change","2026-04-20","2026-04-23","Sta 209","200","4","Unit 13A - Punch Carbon","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,209.01300000000001,"--start_date--end_date--------------model_loc--","***Sta 209:  Unit 13A - Punch Carbon\n--4/6/26 through 4/9/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***\nDate Change, Previously scheduled 4/20/26 to 4/23/26.\n………………………………"]
["X25-1428248",null,"2026-11-04","2026-11-04",null,null,null,"MLV 209-2 to MLV 214-2","200","4","Pig Run - EMAT","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,209.24,null,"MLV 209-2 to MLV 214-2:  Pig Run - EMAT\n--11/4/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1368009","***","2026-04-01","2026-05-22","Completed",null,null,"MLV 213-1A to MLV 213-1BR","200","3","SPECIAL PERMIT REPLACEMENT TGP 213-1","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","49198 CARROLL/TGP COUNTY HOME CARROLL",213.1,"------","***MLV 213-1A to MLV 213-1BR:  SPECIAL PERMIT REPLACEMENT TGP 213-1\n***Completed\nThe following meters are available for nominations:\n49198 CARROLL/TGP COUNTY HOME CARROLL"]
["X25-1368010","***","2026-06-08","2026-07-31","Completed",null,null,"MLV 213-4A to MLV 213-4BR","200","3","SPECIAL PERMIT REPLACEMENT TGP 213-4","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","49198 CARROLL/TGP COUNTY HOME CARROLL",213.4,"------","***MLV 213-4A to MLV 213-4BR:  SPECIAL PERMIT REPLACEMENT TGP 213-4\n***Completed\nThe following meters are available for nominations:\n49198 CARROLL/TGP COUNTY HOME CARROLL"]
["X26-221133",null,"2026-03-23","2026-04-17",null,null,null,"Sta 214","200","4","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,214,null,"Sta 214:  Annual ESD Test & Maintenance\n--3/23/26 through 4/17/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1428303",null,"2026-10-15","2026-10-15",null,null,null,"MLV 214-1 to MLV 219-1","200","4","Pig Run - Gauge/Cleaning","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,214.1,null,"MLV 214-1 to MLV 219-1:  Pig Run - Gauge/Cleaning\n--10/15/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1428304",null,"2026-10-20","2026-10-20",null,null,null,"MLV 214-1 to MLV 219-1","200","4","Pig Run - Cal/IMU","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,214.1,null,"MLV 214-1 to MLV 219-1:  Pig Run - Cal/IMU\n--10/20/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1428305",null,"2026-10-22","2026-10-22",null,null,null,"MLV 214-1 to MLV 219-1","200","4","Pig Run - MFL-C","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,214.1,null,"MLV 214-1 to MLV 219-1:  Pig Run - MFL-C\n--10/22/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1428274",null,"2026-04-28","2026-04-28",null,null,null,"MLV 214-2 to MLV 219-2","200","4","Pig Run - Gauge/Cleaning","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","50561 - UGIAPP/TGP MARTIN RECEIPT NEW CASTL",214.2,null,"MLV 214-2 to MLV 219-2:  Pig Run - Gauge/Cleaning\n--4/28/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  \n50561 - UGIAPP/TGP MARTIN RECEIPT NEW CASTL\n………………………………"]
["X25-1428275",null,"2026-04-30","2026-04-30",null,null,null,"MLV 214-2 to MLV 219-2","200","4","Pig Run - Cal/IMU","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","50561 - UGIAPP/TGP MARTIN RECEIPT NEW CASTL",214.2,null,"MLV 214-2 to MLV 219-2:  Pig Run - Cal/IMU\n--4/30/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  \n50561 - UGIAPP/TGP MARTIN RECEIPT NEW CASTL\n………………………………"]
["X25-1428277",null,"2026-05-04","2026-05-04",null,null,null,"MLV 214-2 to MLV 219-2","200","4","Pig Run - MFL-C","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","50561 - UGIAPP/TGP MARTIN RECEIPT NEW CASTL",214.2,null,"MLV 214-2 to MLV 219-2:  Pig Run - MFL-C\n--5/4/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  \n50561 - UGIAPP/TGP MARTIN RECEIPT NEW CASTL\n………………………………"]
["X25-1428279",null,"2026-05-06","2026-05-06",null,null,null,"MLV 214-2 to MLV 219-2","200","4","Pig Run - EMAT","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","50561 - UGIAPP/TGP MARTIN RECEIPT NEW CASTL",214.2,null,"MLV 214-2 to MLV 219-2:  Pig Run - EMAT\n--5/6/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  \n50561 - UGIAPP/TGP MARTIN RECEIPT NEW CASTL\n………………………………"]
["X26-203372",null,"2026-05-18","2026-05-23",null,null,null,"MLV 214-3 to MLV 215-3","200","4","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,214.3,null,"MLV 214-3 to MLV 215-3:  Anomaly Remediation\n--5/18/26 through 5/23/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-78364",null,"2026-05-18","2026-05-23",null,null,null,"MLV 214-3 to MLV 215-3","200","4","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,214.3,null,"MLV 214-3 to MLV 215-3:  Anomaly Remediation\n--5/18/26 through 5/23/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1428299",null,"2026-09-15","2026-09-15",null,null,null,"MLV 214-3 to MLV 219-3","200","4","Pig Run - Gauge/Cleaning","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","420932 E OH GAS/TGP PETERSBURG MAHONING",214.3,null,"MLV 214-3 to MLV 219-3:  Pig Run - Gauge/Cleaning\n--9/15/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  \n420932 E OH GAS/TGP PETERSBURG MAHONING\n………………………………"]
["X25-1428301",null,"2026-09-17","2026-09-17",null,null,null,"MLV 214-3 to MLV 219-3","200","4","Pig Run - Cal/IMU/MFL-A Combo","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","420932 E OH GAS/TGP PETERSBURG MAHONING",214.3,null,"MLV 214-3 to MLV 219-3:  Pig Run - Cal/IMU/MFL-A Combo\n--9/17/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  \n420932 E OH GAS/TGP PETERSBURG MAHONING\n………………………………"]
["X25-1368013",null,"2026-08-17","2026-10-31",null,null,null,"MLV 215-1 to MLV 216-1","200","3","SPECIAL PERMIT REPLACEMENT TGP 215-1","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.   The meter listed may be constrained or shut in during the project","400480 COL GAS/TGP BRINKER OH COLUMBIANA",215.1,null,"MLV 215-1 to MLV 216-1:  SPECIAL PERMIT REPLACEMENT TGP 215-1\n--8/17/26 through 10/31/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.   The meter listed may be constrained or shut in during the project  \n400480 COL GAS/TGP BRINKER OH COLUMBIANA\n………………………………"]
["X25-1428250","***","2026-12-07","2026-12-07","Project Change","2026-04-06","2026-04-06","MLV 217A-101.1 to 217A-104","200","4","Pig Run - Gauge/Cleaning","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","412863 - GEOPETRO/TGP LITTLE BEAVER: RIP 217\n421075 - LINDYPAV/TGP BIG BEAVER: DIP 217A-1\n420063 - COL GAS/TGP UNIONVILLE PA BEAVER\n420385 - PEOPLES/TGP PITTSBURG TERMINAL PA A\n420078 - EQUITRNS/TGP PITTSBURGH TERMINAL PA\n420199 - PEOPLES/TGP PITTSBURGH TERMINAL PA\n420306 - COL GAS/TGP PITTSBURGH TERMINAL PA",217.1,"--start_date--end_date--------------model_loc--","***MLV 217A-101.1 to 217A-104:  Pig Run - Gauge/Cleaning\n--12/7/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  \n412863 - GEOPETRO/TGP LITTLE BEAVER: RIP 217\n421075 - LINDYPAV/TGP BIG BEAVER: DIP 217A-1\n420063 - COL GAS/TGP UNIONVILLE PA BEAVER\n420385 - PEOPLES/TGP PITTSBURG TERMINAL PA A\n420078 - EQUITRNS/TGP PITTSBURGH TERMINAL PA\n420199 - PEOPLES/TGP PITTSBURGH TERMINAL PA\n420306 - COL GAS/TGP PITTSBURGH TERMINAL PA\n***\nDate Change, Previously scheduled 4/6/26.\n………………………………"]
["X25-1428252","***","2026-12-08","2026-12-08","Project Change","2026-04-07","2026-04-07","MLV 217A-101.1 to 217A-104","200","4","Pig Runs - Cal/IMU","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","412863 - GEOPETRO/TGP LITTLE BEAVER: RIP 217\n421075 - LINDYPAV/TGP BIG BEAVER: DIP 217A-1\n420063 - COL GAS/TGP UNIONVILLE PA BEAVER\n420385 - PEOPLES/TGP PITTSBURG TERMINAL PA A\n420078 - EQUITRNS/TGP PITTSBURGH TERMINAL PA\n420199 - PEOPLES/TGP PITTSBURGH TERMINAL PA\n420306 - COL GAS/TGP PITTSBURGH TERMINAL PA",217.1,"--start_date--end_date--------------model_loc--","***MLV 217A-101.1 to 217A-104:  Pig Runs - Cal/IMU\n--12/8/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  \n412863 - GEOPETRO/TGP LITTLE BEAVER: RIP 217\n421075 - LINDYPAV/TGP BIG BEAVER: DIP 217A-1\n420063 - COL GAS/TGP UNIONVILLE PA BEAVER\n420385 - PEOPLES/TGP PITTSBURG TERMINAL PA A\n420078 - EQUITRNS/TGP PITTSBURGH TERMINAL PA\n420199 - PEOPLES/TGP PITTSBURGH TERMINAL PA\n420306 - COL GAS/TGP PITTSBURGH TERMINAL PA\n***\nDate Change, Previously scheduled 4/7/26.\n………………………………"]
["X25-1428257","***","2026-12-09","2026-12-09","Project Change","2026-04-08","2026-04-08","MLV 217A-101.1 to 217A-104","200","4","Pig Run - MFL-C","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","412863 - GEOPETRO/TGP LITTLE BEAVER: RIP 217\n421075 - LINDYPAV/TGP BIG BEAVER: DIP 217A-1\n420063 - COL GAS/TGP UNIONVILLE PA BEAVER\n420385 - PEOPLES/TGP PITTSBURG TERMINAL PA A\n420078 - EQUITRNS/TGP PITTSBURGH TERMINAL PA\n420199 - PEOPLES/TGP PITTSBURGH TERMINAL PA\n420306 - COL GAS/TGP PITTSBURGH TERMINAL PA",217.1,"--start_date--end_date--------------model_loc--","***MLV 217A-101.1 to 217A-104:  Pig Run - MFL-C\n--12/9/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  \n412863 - GEOPETRO/TGP LITTLE BEAVER: RIP 217\n421075 - LINDYPAV/TGP BIG BEAVER: DIP 217A-1\n420063 - COL GAS/TGP UNIONVILLE PA BEAVER\n420385 - PEOPLES/TGP PITTSBURG TERMINAL PA A\n420078 - EQUITRNS/TGP PITTSBURGH TERMINAL PA\n420199 - PEOPLES/TGP PITTSBURGH TERMINAL PA\n420306 - COL GAS/TGP PITTSBURGH TERMINAL PA\n***\nDate Change, Previously scheduled 4/8/26.\n………………………………"]
["X25-1428258","***","2026-12-10","2026-12-10","Project Change","2026-04-09","2026-04-09","MLV 217A-101.1 to 217A-104","200","4","Pig Run - EMAT","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","412863 - GEOPETRO/TGP LITTLE BEAVER: RIP 217\n421075 - LINDYPAV/TGP BIG BEAVER: DIP 217A-1\n420063 - COL GAS/TGP UNIONVILLE PA BEAVER\n420385 - PEOPLES/TGP PITTSBURG TERMINAL PA A\n420078 - EQUITRNS/TGP PITTSBURGH TERMINAL PA\n420199 - PEOPLES/TGP PITTSBURGH TERMINAL PA\n420306 - COL GAS/TGP PITTSBURGH TERMINAL PA",217.1,"--start_date--end_date--------------model_loc--","***MLV 217A-101.1 to 217A-104:  Pig Run - EMAT\n--12/10/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  \n412863 - GEOPETRO/TGP LITTLE BEAVER: RIP 217\n421075 - LINDYPAV/TGP BIG BEAVER: DIP 217A-1\n420063 - COL GAS/TGP UNIONVILLE PA BEAVER\n420385 - PEOPLES/TGP PITTSBURG TERMINAL PA A\n420078 - EQUITRNS/TGP PITTSBURGH TERMINAL PA\n420199 - PEOPLES/TGP PITTSBURGH TERMINAL PA\n420306 - COL GAS/TGP PITTSBURGH TERMINAL PA\n***\nDate Change, Previously scheduled 4/9/26.\n………………………………"]
["X26-75111",null,"2026-08-17","2026-08-21",null,null,null,"Sta 219","200","4","Annual ESD Test & Scrubber Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,219,null,"Sta 219:  Annual ESD Test & Scrubber Maintenance\n--8/17/26 through 8/21/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-353224","***","2026-05-18","2026-05-22","Added",null,null,"Sta 219","200","4","Unit 1A - Ignition Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,219.001,"------","***Sta 219:  Unit 1A - Ignition Upgrade\n--5/18/26 through 5/22/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***Added\n………………………………"]
["X26-75114",null,"2026-07-13","2026-07-17",null,null,null,"Sta 219","200","4","Unit 1A to 6A - Protective Device Checks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,219.001,null,"Sta 219:  Unit 1A to 6A - Protective Device Checks\n--7/13/26 through 7/17/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-75104",null,"2026-08-17","2026-08-21",null,null,null,"Sta 219","200","4","Unit 1A - Valve Actuators & Ignition","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,219.001,null,"Sta 219:  Unit 1A - Valve Actuators & Ignition\n--8/17/26 through 8/21/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-75107",null,"2026-09-07","2026-09-11",null,null,null,"Sta 219","200","4","Unit 2A - Trabon","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,219.00200000000001,null,"Sta 219:  Unit 2A - Trabon\n--9/7/26 through 9/11/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-75108",null,"2026-03-16","2026-04-17",null,null,null,"Sta 219","200","4","Unit 4A - Rechock","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,219.00399999999999,null,"Sta 219:  Unit 4A - Rechock\n--3/16/26 through 4/17/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-75109",null,"2026-03-16","2026-04-17",null,null,null,"Sta 219","200","4","Unit 5A - Rechock","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,219.005,null,"Sta 219:  Unit 5A - Rechock\n--3/16/26 through 4/17/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-75115",null,"2026-07-13","2026-07-17",null,null,null,"Sta 219","200","4","Unit 7A to 13A - Protective Device Checks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,219.00700000000001,null,"Sta 219:  Unit 7A to 13A - Protective Device Checks\n--7/13/26 through 7/17/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-75113",null,"2026-06-08","2026-06-12",null,null,null,"Sta 219","200","4","Unit 1B - Protective Device Checks & GHG","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,219.017,null,"Sta 219:  Unit 1B - Protective Device Checks & GHG\n--6/8/26 through 6/12/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-75105",null,"2026-07-20","2026-07-31",null,null,null,"Sta 219","200","4","Unit 1B - Save Air System","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,219.017,null,"Sta 219:  Unit 1B - Save Air System\n--7/20/26 through 7/31/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-75135",null,"2026-06-16","2026-06-16",null,null,null,"MLV 219-1D to MLV 224-1","200","4","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,219.1,null,"MLV 219-1D to MLV 224-1:  Pig Run - Maintenance\n--6/16/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X26-51845",null,"2026-06-03","2026-06-04",null,null,null,"Sta 224","200","5","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,224,null,"Sta 224:  Annual ESD Test\n--6/3/26 through 6/4/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-51842",null,"2026-08-25","2026-08-26",null,null,null,"Station 224","200","5","Scrubber Inspections & Filter Change","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,224.0001,null,"Station 224:  Scrubber Inspections & Filter Change\n--8/25/26 through 8/26/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-51846",null,"2026-05-11","2026-05-12",null,null,null,"Sta 229","200","5","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,229,null,"Sta 229:  Annual ESD Test & Maintenance\n--5/11/26 through 5/12/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-335110","***","2026-03-23","2026-03-26","Completed",null,null,"Sta 229","200","5","Unit 5A - Engine Analysis","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,229.005,"------","***Sta 229:  Unit 5A - Engine Analysis\n***Completed"]
["X26-51851",null,"2026-04-08","2026-04-09",null,null,null,"MLV 229-2 to MLV 232-2","200","5","Pig runs - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.    The meters listed may be constrained or shut in during the project","420690 EGTS/TGP NORTH SHELDON SALES WYOMIN\n420076 NFG/TGP HAMBURG NY ERIE",229.2,null,"MLV 229-2 to MLV 232-2:  Pig runs - Maintenance\n--4/8/26 through 4/9/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.    The meters listed may be constrained or shut in during the project  \n420690 EGTS/TGP NORTH SHELDON SALES WYOMIN\n420076 NFG/TGP HAMBURG NY ERIE\n………………………………"]
["X26-51847",null,"2026-07-13","2026-07-14",null,null,null,"Sta 230C","200","5","Annual ESD","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","410902 TRANSCAN/TGP UDP NIAGARA RIVER NIAG\n421079 TRANSCAN/TGP UDP NIAGARA RIVER DELI",230,null,"Sta 230C:  Annual ESD\n--7/13/26 through 7/14/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  \n410902 TRANSCAN/TGP UDP NIAGARA RIVER NIAG\n421079 TRANSCAN/TGP UDP NIAGARA RIVER DELI\n………………………………"]
["X26-51848",null,"2026-09-09","2026-09-10",null,null,null,"Sta 230C","200","5","Scrubber / Filter Inspection","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","410902 TRANSCAN/TGP UDP NIAGARA RIVER NIAG\n421079 TRANSCAN/TGP UDP NIAGARA RIVER DELI",230.00001,null,"Sta 230C:  Scrubber / Filter Inspection\n--9/9/26 through 9/10/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  \n410902 TRANSCAN/TGP UDP NIAGARA RIVER NIAG\n421079 TRANSCAN/TGP UDP NIAGARA RIVER DELI\n………………………………"]
["X26-51850",null,"2026-07-06","2026-07-09",null,null,null,"Station 230C","200","5","Unit 1A - Turbine Exchange","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,230.001,null,"Station 230C:  Unit 1A - Turbine Exchange\n--7/6/26 through 7/9/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1428341","***","2026-03-30","2026-03-30","Completed",null,null,"MLV 230-1 to MLV 237-1","200","5","Pig Run - Gauge/Cleaning","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","420688    EGTS/TGP LAKEVILLE SALES LIVINGSTON\n450421\tTGP/TGP CRAIGS CHECK LIVINGSTON\n411106\tHONEOYE/TGP STORAGE  WDL ONTARIO\n420690    EGTS/TGP NORTH SHELDON SALES WYOMIN\n412856\tEMPIREPL/TGP CANANDAIGUA ONTARIO\n420617\tEGTS/TGP HOPEWELL SALES ONTARIO",230.1,"------","***MLV 230-1 to MLV 237-1:  Pig Run - Gauge/Cleaning\n***Completed\nThe following meters are available for nominations:\n420688    EGTS/TGP LAKEVILLE SALES LIVINGSTON\n450421\tTGP/TGP CRAIGS CHECK LIVINGSTON\n411106\tHONEOYE/TGP STORAGE  WDL ONTARIO\n420690    EGTS/TGP NORTH SHELDON SALES WYOMIN\n412856\tEMPIREPL/TGP CANANDAIGUA ONTARIO\n420617\tEGTS/TGP HOPEWELL SALES ONTARIO"]
["X25-1428344","***","2026-04-01","2026-04-01","Completed",null,null,"MLV 230-1 to MLV 237-1","200","5","Pig Run - CAL/IMU/MFL-C","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","420688    EGTS/TGP LAKEVILLE SALES LIVINGSTON\n450421\tTGP/TGP CRAIGS CHECK LIVINGSTON\n411106\tHONEOYE/TGP STORAGE  WDL ONTARIO\n420690    EGTS/TGP NORTH SHELDON SALES WYOMIN\n412856\tEMPIREPL/TGP CANANDAIGUA ONTARIO\n420617\tEGTS/TGP HOPEWELL SALES ONTARIO",230.1,"------","***MLV 230-1 to MLV 237-1:  Pig Run - CAL/IMU/MFL-C\n***Completed\nThe following meters are available for nominations:\n420688    EGTS/TGP LAKEVILLE SALES LIVINGSTON\n450421\tTGP/TGP CRAIGS CHECK LIVINGSTON\n411106\tHONEOYE/TGP STORAGE  WDL ONTARIO\n420690    EGTS/TGP NORTH SHELDON SALES WYOMIN\n412856\tEMPIREPL/TGP CANANDAIGUA ONTARIO\n420617\tEGTS/TGP HOPEWELL SALES ONTARIO"]
["X26-363029","***","2026-04-06","2026-04-06","Added",null,null,"MLV 230-1 to MLV 237-1","200","5","Pig Run - MFL-C","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.    The meters listed may be constrained or shut in during the project","420688    EGTS/TGP LAKEVILLE SALES LIVINGSTON\n450421\tTGP/TGP CRAIGS CHECK LIVINGSTON\n411106\tHONEOYE/TGP STORAGE  WDL ONTARIO\n420690    EGTS/TGP NORTH SHELDON SALES WYOMIN\n412856\tEMPIREPL/TGP CANANDAIGUA ONTARIO\n420617\tEGTS/TGP HOPEWELL SALES ONTARIO",230.1,"------","***MLV 230-1 to MLV 237-1:  Pig Run - MFL-C\n--4/6/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.    The meters listed may be constrained or shut in during the project  \n420688    EGTS/TGP LAKEVILLE SALES LIVINGSTON\n450421\tTGP/TGP CRAIGS CHECK LIVINGSTON\n411106\tHONEOYE/TGP STORAGE  WDL ONTARIO\n420690    EGTS/TGP NORTH SHELDON SALES WYOMIN\n412856\tEMPIREPL/TGP CANANDAIGUA ONTARIO\n420617\tEGTS/TGP HOPEWELL SALES ONTARIO\n***Added\n………………………………"]
["X25-1428345","***","2026-04-08","2026-04-08","Project Change","2026-04-06","2026-04-06","MLV 230-1 to MLV 237-1","200","5","Pig Run - EMAT","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","420688    EGTS/TGP LAKEVILLE SALES LIVINGSTON\n450421\tTGP/TGP CRAIGS CHECK LIVINGSTON\n411106\tHONEOYE/TGP STORAGE  WDL ONTARIO\n420690    EGTS/TGP NORTH SHELDON SALES WYOMIN\n412856\tEMPIREPL/TGP CANANDAIGUA ONTARIO\n420617\tEGTS/TGP HOPEWELL SALES ONTARIO",230.1,"--start_date--end_date--------------model_loc--","***MLV 230-1 to MLV 237-1:  Pig Run - EMAT\n--4/8/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  \n420688    EGTS/TGP LAKEVILLE SALES LIVINGSTON\n450421\tTGP/TGP CRAIGS CHECK LIVINGSTON\n411106\tHONEOYE/TGP STORAGE  WDL ONTARIO\n420690    EGTS/TGP NORTH SHELDON SALES WYOMIN\n412856\tEMPIREPL/TGP CANANDAIGUA ONTARIO\n420617\tEGTS/TGP HOPEWELL SALES ONTARIO\n***\nDate Change, Previously scheduled 4/6/26.\n………………………………"]
["X26-51853",null,"2026-04-28","2026-04-29",null,null,null,"MLV 230B-101BL to MLV 230B-105ARB","200","5","Pig run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.    The meters listed may be constrained or shut in during the project","412865\tNFG/TGP EAST AURORA NEW YORK ERIE\n420502\tEGTS/TGP MARILLA NY ERIE\n420497\tNFG/TGP CLARENCE NY ERIE\n420221\tNYSEG/TGP LOCKPORT NY NIAGARA\n420739\tSHELL/TGP HARRISON CO GEN SALES NIA\n54378\tCAMBRIAA/TGP SHELBY CRUSHED STONE N",230.1,null,"MLV 230B-101BL to MLV 230B-105ARB:  Pig run - Maintenance\n--4/28/26 through 4/29/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.    The meters listed may be constrained or shut in during the project  \n412865\tNFG/TGP EAST AURORA NEW YORK ERIE\n420502\tEGTS/TGP MARILLA NY ERIE\n420497\tNFG/TGP CLARENCE NY ERIE\n420221\tNYSEG/TGP LOCKPORT NY NIAGARA\n420739\tSHELL/TGP HARRISON CO GEN SALES NIA\n54378\tCAMBRIAA/TGP SHELBY CRUSHED STONE N\n………………………………"]
["X25-1428285",null,"2026-07-08","2026-07-08",null,null,null,"MLV 230B-201 to MLV 230B-205","200","5","Pig Run - Gauge/Cleaning","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,230.2,null,"MLV 230B-201 to MLV 230B-205:  Pig Run - Gauge/Cleaning\n--7/8/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1428288",null,"2026-07-09","2026-07-09",null,null,null,"MLV 230B-201 to MLV 230B-205","200","5","Pig Run - Cal/IMU/MFL-A Combo","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,230.2,null,"MLV 230B-201 to MLV 230B-205:  Pig Run - Cal/IMU/MFL-A Combo\n--7/9/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1428290",null,"2026-07-14","2026-07-14",null,null,null,"MLV 230B-205 to MLV 230B-206A","200","5","Pig Run - Gauge/Cleaning","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,230.2,null,"MLV 230B-205 to MLV 230B-206A:  Pig Run - Gauge/Cleaning\n--7/14/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1428294",null,"2026-07-15","2026-07-15",null,null,null,"MLV 230B-205 to MLV 230B-206A","200","5","Pig Run - Cal/IMU/MFL-A Combo","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,230.2,null,"MLV 230B-205 to MLV 230B-206A:  Pig Run - Cal/IMU/MFL-A Combo\n--7/15/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X26-39644",null,"2026-05-19","2026-05-19",null,null,null,"Sta 233","200","5","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,233,null,"Sta 233:  Annual ESD Test\n--5/19/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-39646",null,"2026-05-20","2026-05-20",null,null,null,"Sta 233","200","5","Transmitter Calibrations Spot Checks / Filter Scrubber Inspection","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,233,null,"Sta 233:  Transmitter Calibrations Spot Checks / Filter Scrubber Inspection\n--5/20/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-219102","***","2026-05-15","2026-06-06","Completed",null,null,"MLV 236-1 to MLV 237-1BR","200","5","Special Permit Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meters listed may be constrained or shut in during the project.","412856 EMPIREPL/TGP CANANDIAGUA ONTARIO\n420617 EGTS/TGP HOPEWELL SALES ONTARIO\n420526 HONEOYE/TGP UDP HONEOYE NEW YORK ON",236.1,"------","***MLV 236-1 to MLV 237-1BR:  Special Permit Replacement\n***Completed\nThe following meters are available for nominations:\n412856 EMPIREPL/TGP CANANDIAGUA ONTARIO\n420617 EGTS/TGP HOPEWELL SALES ONTARIO\n420526 HONEOYE/TGP UDP HONEOYE NEW YORK ON"]
["X26-39847",null,"2026-08-04","2026-08-06",null,null,null,"Sta 237","200","5","Annual ESD Test and Transmitter Cal Spot Checks","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,237,null,"Sta 237:  Annual ESD Test and Transmitter Cal Spot Checks\n--8/4/26 through 8/6/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-39833",null,"2026-06-23","2026-06-23",null,null,null,"Sta 237","200","5","Unit 3A - Safety Device Test","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,237.00299999999999,null,"Sta 237:  Unit 3A - Safety Device Test\n--6/23/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-39868",null,"2026-09-15","2026-09-15",null,null,null,"MLV 237-1 to MLV 245-1","200","5","Pig Run","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,237.1,null,"MLV 237-1 to MLV 245-1:  Pig Run\n--9/15/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1320307",null,"2026-05-12","2026-05-12",null,null,null,"MLV 237-2 to MLV 245-2","200","4","Pig Run - Gauge/Cleaning Tool","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420086 EGTS/TGP PHELPS NY ONTARIO\n420732 POA/TGP SYRACUSE COGEN SALES ONONDA\n412065 EGTS/TGP MORRISVILLE TRANSPORT MADI\n47592 HAMVIL/TGP VILLAGE OF HAMILTON NY M",237.2,null,"MLV 237-2 to MLV 245-2:  Pig Run - Gauge/Cleaning Tool\n--5/12/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  \n420086 EGTS/TGP PHELPS NY ONTARIO\n420732 POA/TGP SYRACUSE COGEN SALES ONONDA\n412065 EGTS/TGP MORRISVILLE TRANSPORT MADI\n47592 HAMVIL/TGP VILLAGE OF HAMILTON NY M\n………………………………"]
["X25-1320310",null,"2026-05-19","2026-05-19",null,null,null,"MLV 237-2 to MLV 245-2","200","4","Pig Run - CAL/IMU","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420086 EGTS/TGP PHELPS NY ONTARIO\n420732 POA/TGP SYRACUSE COGEN SALES ONONDA\n412065 EGTS/TGP MORRISVILLE TRANSPORT MADI\n47592 HAMVIL/TGP VILLAGE OF HAMILTON NY M",237.2,null,"MLV 237-2 to MLV 245-2:  Pig Run - CAL/IMU\n--5/19/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  \n420086 EGTS/TGP PHELPS NY ONTARIO\n420732 POA/TGP SYRACUSE COGEN SALES ONONDA\n412065 EGTS/TGP MORRISVILLE TRANSPORT MADI\n47592 HAMVIL/TGP VILLAGE OF HAMILTON NY M\n………………………………"]
["X25-1320311",null,"2026-05-21","2026-05-21",null,null,null,"MLV 237-2 to MLV 245-2","200","4","Pig Run - MFL-A","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420086 EGTS/TGP PHELPS NY ONTARIO\n420732 POA/TGP SYRACUSE COGEN SALES ONONDA\n412065 EGTS/TGP MORRISVILLE TRANSPORT MADI\n47592 HAMVIL/TGP VILLAGE OF HAMILTON NY M",237.2,null,"MLV 237-2 to MLV 245-2:  Pig Run - MFL-A\n--5/21/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  \n420086 EGTS/TGP PHELPS NY ONTARIO\n420732 POA/TGP SYRACUSE COGEN SALES ONONDA\n412065 EGTS/TGP MORRISVILLE TRANSPORT MADI\n47592 HAMVIL/TGP VILLAGE OF HAMILTON NY M\n………………………………"]
["X26-39843",null,"2026-07-22","2026-07-22",null,null,null,"Sta 237","200","5","200 Line Filter/Scrubber Change","This project may require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,237.2,null,"Sta 237:  200 Line Filter/Scrubber Change\n--7/22/26:  This project may require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-39870",null,"2026-10-06","2026-10-06",null,null,null,"MLV 233-2 to MLV 235-2","200","5","Pig Run","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,237.2,null,"MLV 233-2 to MLV 235-2:  Pig Run\n--10/6/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X26-39842",null,"2026-07-21","2026-07-21",null,null,null,"Sta 237","200","5","400 Line Filter/Scrubber Change","This project may require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,237.4,null,"Sta 237:  400 Line Filter/Scrubber Change\n--7/21/26:  This project may require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-299827",null,"2026-05-04","2026-05-15",null,null,null,"Sta 241","200","4","Unit 3A - Turbocharger","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,240.00299999999999,null,"Sta 241:  Unit 3A - Turbocharger\n--5/4/26 through 5/15/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-39827",null,"2026-06-16","2026-06-16",null,null,null,"Sta 241","200","5","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,241,null,"Sta 241:  Annual ESD Test\n--6/16/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-39831",null,"2026-06-17","2026-06-17",null,null,null,"Sta 241","200","5","Transmitter Cal / Spot Checks","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,241,null,"Sta 241:  Transmitter Cal / Spot Checks\n--6/17/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-39856",null,"2026-08-10","2026-08-10",null,null,null,"Sta 241","200","5","Unit 1A - Device Test and Relief Valve","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,241.001,null,"Sta 241:  Unit 1A - Device Test and Relief Valve\n--8/10/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-39861",null,"2026-08-11","2026-08-11",null,null,null,"Sta 241","200","5","Unit 2A - Device Test and Relief Valve","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,241.00200000000001,null,"Sta 241:  Unit 2A - Device Test and Relief Valve\n--8/11/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-39838",null,"2026-07-14","2026-07-14",null,null,null,"Sta 241","200","5","Unit 3A - Safety Device Test & Relief Valve","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,241.00299999999999,null,"Sta 241:  Unit 3A - Safety Device Test & Relief Valve\n--7/14/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-110469",null,"2026-06-02","2026-06-04",null,null,null,"Sta 241","200","5","Unit 1B - Oil System","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,241.017,null,"Sta 241:  Unit 1B - Oil System\n--6/2/26 through 6/4/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-39863",null,"2026-08-12","2026-08-12",null,null,null,"Sta 241","200","5","Unit 1B - Device Test and Relief Valve","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,241.017,null,"Sta 241:  Unit 1B - Device Test and Relief Valve\n--8/12/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-39866",null,"2026-09-08","2026-09-08",null,null,null,"Sta 241","200","5","Unit 1B - 2k Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,241.017,null,"Sta 241:  Unit 1B - 2k Maintenance\n--9/8/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-110470",null,"2026-06-09","2026-06-11",null,null,null,"Sta 241","200","5","Unit 2B - Oil System","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,241.018,null,"Sta 241:  Unit 2B - Oil System\n--6/9/26 through 6/11/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-39864",null,"2026-08-13","2026-08-13",null,null,null,"Sta 241","200","5","Unit 2B - Device Test and Relief Valve","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,241.018,null,"Sta 241:  Unit 2B - Device Test and Relief Valve\n--8/13/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-39865",null,"2026-09-09","2026-09-09",null,null,null,"Sta 241","200","5","Unit 2B - 2k Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,241.018,null,"Sta 241:  Unit 2B - 2k Maintenance\n--9/9/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-51834",null,"2026-04-30","2026-05-08",null,null,null,"Sta 245 West Winfield","200","5","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,245,null,"Sta 245 West Winfield:  Annual ESD Test & Maintenance\n--4/30/26 through 5/8/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-302918",null,"2026-03-23","2026-04-17",null,null,null,"Sta 245","200","5","Unit 1A & 2A - Automation Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,245.001,null,"Sta 245:  Unit 1A & 2A - Automation Upgrade\n--3/23/26 through 4/17/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-110081",null,"2026-04-06","2026-04-07",null,null,null,"Sta 245","200","5","Unit 1A - Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,245.001,null,"Sta 245:  Unit 1A - Crankcase Inspection\n--4/6/26 through 4/7/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-110117",null,"2026-04-08","2026-04-10",null,null,null,"Sta 245","200","5","Unit 2A - Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,245.00200000000001,null,"Sta 245:  Unit 2A - Crankcase Inspection\n--4/8/26 through 4/10/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1288928",null,"2026-07-14","2026-07-14",null,null,null,"Sta 245-1 to MLV 249-1","200","5","Pig Run - Gauge/Cleaning tool","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,245.1,null,"Sta 245-1 to MLV 249-1:  Pig Run - Gauge/Cleaning tool\n--7/14/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1288931",null,"2026-07-15","2026-07-15",null,null,null,"Sta 245-1 to MLV 249-1","200","5","Pig Run - Cal/IMU","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,245.1,null,"Sta 245-1 to MLV 249-1:  Pig Run - Cal/IMU\n--7/15/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1288932",null,"2026-07-16","2026-07-16",null,null,null,"Sta 245-1 to MLV 249-1","200","5","Pig Run - MFL-C","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,245.1,null,"Sta 245-1 to MLV 249-1:  Pig Run - MFL-C\n--7/16/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1288933",null,"2026-10-27","2026-10-27",null,null,null,"Sta 245-1 to MLV 249-1","200","5","Pig Run - EMAT","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,245.1,null,"Sta 245-1 to MLV 249-1:  Pig Run - EMAT\n--10/27/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X26-110163",null,"2026-05-19","2026-05-25",null,null,null,"Sta 249","200","5","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,249,null,"Sta 249:  Annual ESD Test & Maintenance\n--5/19/26 through 5/25/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-110135",null,"2026-04-27","2026-05-01",null,null,null,"Sta 249","200","5","Unit 1A - Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,249.001,null,"Sta 249:  Unit 1A - Crankcase Inspection\n--4/27/26 through 5/1/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-110197",null,"2026-05-04","2026-05-08",null,null,null,"Sta 249","200","5","Unit 2A - Crankcase Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,249.00200000000001,null,"Sta 249:  Unit 2A - Crankcase Inspection\n--5/4/26 through 5/8/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-110203",null,"2026-06-01","2026-06-26",null,null,null,"Sta 249","200","5","Unit 2B - 25k Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,249.018,null,"Sta 249:  Unit 2B - 25k Overhaul\n--6/1/26 through 6/26/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-299808",null,"2026-05-20","2026-05-26",null,null,null,"MLV 249-1A to MLV 250-1","200","5","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,249.1,null,"MLV 249-1A to MLV 250-1:  Anomaly Remediation\n--5/20/26 through 5/26/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1288891",null,"2026-04-28","2026-04-28",null,null,null,"MLV 249-2 to MLV 254-2","200","5","Gauge/Cleaning tool","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,249.2,null,"MLV 249-2 to MLV 254-2:  Gauge/Cleaning tool\n--4/28/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1288892",null,"2026-04-29","2026-04-29",null,null,null,"MLV 249-2 to MLV 254-2","200","5","Cal/IMU","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,249.2,null,"MLV 249-2 to MLV 254-2:  Cal/IMU\n--4/29/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1288894",null,"2026-04-30","2026-04-30",null,null,null,"MLV 249-2 to MLV 254-2","200","5","MFL-C","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,249.2,null,"MLV 249-2 to MLV 254-2:  MFL-C\n--4/30/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1288916","***","2026-07-20","2026-07-20","Project Change","2026-07-07","2026-07-07","MLV 249-3A to MLV 251-3","200","5","Pig Run - Gauge/Cleaning tool","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,249.3,"--start_date--end_date--------------model_loc--","***MLV 249-3A to MLV 251-3:  Pig Run - Gauge/Cleaning tool\n--7/20/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n***\nDate Change, Previously scheduled 7/7/26.\n………………………………"]
["X25-1288920","***","2026-07-21","2026-07-21","Project Change","2026-07-08","2026-07-08","MLV 249-3A to MLV 251-3","200","5","Pig Run - Cal/IMU/MFL-A Combo","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,249.3,"--start_date--end_date--------------model_loc--","***MLV 249-3A to MLV 251-3:  Pig Run - Cal/IMU/MFL-A Combo\n--7/21/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n***\nDate Change, Previously scheduled 7/8/26.\n………………………………"]
["X26-299812",null,"2026-05-25","2026-05-30",null,null,null,"MLV 253-1 to MLV 253-1R","200","5","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,253.1,null,"MLV 253-1 to MLV 253-1R:  Anomaly Remediation\n--5/25/26 through 5/30/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-51885",null,"2026-05-12","2026-05-12",null,null,null,"Sta 254 Nassau","200","5","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,254,null,"Sta 254 Nassau:  Annual ESD Test\n--5/12/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-318195",null,"2026-04-10","2026-04-15",null,null,null,"Sta 254","200","5","Unit 1A - Power Cylinder Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,254.001,null,"Sta 254:  Unit 1A - Power Cylinder Maintenance\n--4/10/26 through 4/15/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-318197",null,"2026-04-20","2026-04-22",null,null,null,"Sta 254","200","5","Unit 2A - Power Cylinder Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,254.00200000000001,null,"Sta 254:  Unit 2A - Power Cylinder Maintenance\n--4/20/26 through 4/22/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-318199",null,"2026-04-27","2026-04-29",null,null,null,"Sta 254","200","5","Unit 6A - Power Cylinder Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,254.006,null,"Sta 254:  Unit 6A - Power Cylinder Maintenance\n--4/27/26 through 4/29/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-51888",null,"2026-05-13","2026-05-14",null,null,null,"Sta 254","200","5","Unit 2B - 4k / 8k Service Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,254.018,null,"Sta 254:  Unit 2B - 4k / 8k Service Inspection\n--5/13/26 through 5/14/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1288901",null,"2026-05-27","2026-05-27",null,null,null,"MLV 254-2 to MLV 261-2","200","5","Pig Run - Gauge/Cleaning tool","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,254.2,null,"MLV 254-2 to MLV 261-2:  Pig Run - Gauge/Cleaning tool\n--5/27/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1288904",null,"2026-05-28","2026-05-28",null,null,null,"MLV 254-2 to MLV 261-2","200","5","Pig Run - Cal/IMU/MFL-A Combo","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,254.2,null,"MLV 254-2 to MLV 261-2:  Pig Run - Cal/IMU/MFL-A Combo\n--5/28/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1288752","***","2026-04-16","2026-04-16","Project Change","2026-04-13","2026-04-13","MLV 254-3 to MLV 258-3A","200","6","Pig Runs - Gauge/Cleaning tool - 4/16/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,254.3,"--start_date--end_date--------mantenance_desc------model_loc--","***MLV 254-3 to MLV 258-3A:  Pig Runs - Gauge/Cleaning tool - 4/16/26\n--4/16/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n***\nDate Change, Previously scheduled 4/13/26.\n………………………………"]
["X25-1288753","***","2026-04-17","2026-04-17","Project Change","2026-04-14","2026-04-14","MLV 254-3 to MLV 258-3A","200","6","Pig Runs - Cal/IMU/MFL-A Combo - 4/17/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,254.3,"--start_date--end_date--------mantenance_desc------model_loc--","***MLV 254-3 to MLV 258-3A:  Pig Runs - Cal/IMU/MFL-A Combo - 4/17/26\n--4/17/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n***\nDate Change, Previously scheduled 4/14/26.\n………………………………"]
["X25-1369747",null,"2026-07-09","2026-07-25",null,null,null,"MLV 255","200","4","ECDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,255,null,"MLV 255:  ECDA\n--7/9/26 through 7/25/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1288883","***","2026-04-13","2026-04-13","Project Change","2026-04-16","2026-04-16","MLV 256C-101.1 to MLV 256C-102","200","6","Pig Runs - Gauge/Cleaning tool","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.","420638 - BERKSHR/TGP WEST PITTSFIELD SALES B\n420747 - BERKSHR/TGP BOUSQUET SMS BERKSHIRE\n420102 - BERKSHR/TGP PITTSFIELD MA BERKSHIRE",256.101,"--start_date--end_date--------------model_loc--","***MLV 256C-101.1 to MLV 256C-102:  Pig Runs - Gauge/Cleaning tool\n--4/13/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.  \n420638 - BERKSHR/TGP WEST PITTSFIELD SALES B\n420747 - BERKSHR/TGP BOUSQUET SMS BERKSHIRE\n420102 - BERKSHR/TGP PITTSFIELD MA BERKSHIRE\n***\nDate Change, Previously scheduled 4/16/26.\n………………………………"]
["X25-1288887","***","2026-04-14","2026-04-14","Project Change","2026-04-17","2026-04-17","MLV 256C-101.1 to MLV 256C-102","200","6","Pig Runs - Cal/IMU/MFL-A Combo","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.","420638 - BERKSHR/TGP WEST PITTSFIELD SALES B\n420747 - BERKSHR/TGP BOUSQUET SMS BERKSHIRE\n420102 - BERKSHR/TGP PITTSFIELD MA BERKSHIRE",256.101,"--start_date--end_date--------------model_loc--","***MLV 256C-101.1 to MLV 256C-102:  Pig Runs - Cal/IMU/MFL-A Combo\n--4/14/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.  \n420638 - BERKSHR/TGP WEST PITTSFIELD SALES B\n420747 - BERKSHR/TGP BOUSQUET SMS BERKSHIRE\n420102 - BERKSHR/TGP PITTSFIELD MA BERKSHIRE\n***\nDate Change, Previously scheduled 4/17/26.\n………………………………"]
["X25-1288907",null,"2026-06-01","2026-06-01",null,null,null,"MLV 256A-101.1 to MLV 256A-103","200","5","PIG RUNS - Gauge/Cleaning tool","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.","420638 - BERKSHR/TGP WEST PITTSFIELD SALES B\n420102 - BERKSHR/TGP PITTSFIELD MA BERKSHIRE\n420747 - BERKSHR/TGP BOUSQUET SMS BERKSHIRE\n420103 - BERKSHR/TGP NORTH ADAMS MA BERKSHIRE",256.101,null,"MLV 256A-101.1 to MLV 256A-103:  PIG RUNS - Gauge/Cleaning tool\n--6/1/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.  \n420638 - BERKSHR/TGP WEST PITTSFIELD SALES B\n420102 - BERKSHR/TGP PITTSFIELD MA BERKSHIRE\n420747 - BERKSHR/TGP BOUSQUET SMS BERKSHIRE\n420103 - BERKSHR/TGP NORTH ADAMS MA BERKSHIRE\n………………………………"]
["X25-1288909",null,"2026-06-02","2026-06-02",null,null,null,"MLV 256A-101.1 to MLV 256A-103","200","5","PIG RUNS - Cal/IMU","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.","420638 - BERKSHR/TGP WEST PITTSFIELD SALES B\n420102 - BERKSHR/TGP PITTSFIELD MA BERKSHIRE\n420747 - BERKSHR/TGP BOUSQUET SMS BERKSHIRE\n420103 - BERKSHR/TGP NORTH ADAMS MA BERKSHIRE",256.101,null,"MLV 256A-101.1 to MLV 256A-103:  PIG RUNS - Cal/IMU\n--6/2/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.  \n420638 - BERKSHR/TGP WEST PITTSFIELD SALES B\n420102 - BERKSHR/TGP PITTSFIELD MA BERKSHIRE\n420747 - BERKSHR/TGP BOUSQUET SMS BERKSHIRE\n420103 - BERKSHR/TGP NORTH ADAMS MA BERKSHIRE\n………………………………"]
["X25-1288910",null,"2026-06-03","2026-06-03",null,null,null,"MLV 256A-101.1 to MLV 256A-103","200","5","PIG RUNS - MFL-C","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.","420638 - BERKSHR/TGP WEST PITTSFIELD SALES B\n420102 - BERKSHR/TGP PITTSFIELD MA BERKSHIRE\n420747 - BERKSHR/TGP BOUSQUET SMS BERKSHIRE\n420103 - BERKSHR/TGP NORTH ADAMS MA BERKSHIRE",256.101,null,"MLV 256A-101.1 to MLV 256A-103:  PIG RUNS - MFL-C\n--6/3/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.  \n420638 - BERKSHR/TGP WEST PITTSFIELD SALES B\n420102 - BERKSHR/TGP PITTSFIELD MA BERKSHIRE\n420747 - BERKSHR/TGP BOUSQUET SMS BERKSHIRE\n420103 - BERKSHR/TGP NORTH ADAMS MA BERKSHIRE\n………………………………"]
["X25-1369748",null,"2026-06-22","2026-07-08",null,null,null,"MLV 257","200","4","ECDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,257,null,"MLV 257:  ECDA\n--6/22/26 through 7/8/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-299751","***","2026-03-23","2026-03-27","Completed",null,null,"MLV 257-1 to MLV 258-1","200","5","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,257.10000000000002,"------","***MLV 257-1 to MLV 258-1:  Anomaly Remediation\n***Completed"]
["X26-299753",null,"2026-03-28","2026-04-06",null,null,null,"MLV 258-1 to MLV 259-1","200","5","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,258.10000000000002,null,"MLV 258-1 to MLV 259-1:  Anomaly Remediation\n--3/28/26 through 4/6/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-299754",null,"2026-04-07","2026-04-11",null,null,null,"MLV 259-1 to MLV 260-1","200","5","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,259.10000000000002,null,"MLV 259-1 to MLV 260-1:  Anomaly Remediation\n--4/7/26 through 4/11/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-299792",null,"2026-06-01","2026-06-06",null,null,null,"MLV 249-1L to MLV 249-1A","200","5","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,259.10000000000002,null,"MLV 249-1L to MLV 249-1A:  Anomaly Remediation\n--6/1/26 through 6/6/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-279051",null,"2026-09-21","2026-09-21",null,null,null,"Sta 260A Southwick","200","6","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,260,null,"Sta 260A Southwick:  Annual ESD Test\n--9/21/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-279048",null,"2026-08-10","2026-08-14",null,null,null,"Sta 260A","200","6","Unit 1A - Protective Device, VFD and Medium Voltage Inspections","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,260.00099999999998,null,"Sta 260A:  Unit 1A - Protective Device, VFD and Medium Voltage Inspections\n--8/10/26 through 8/14/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-279050",null,"2026-09-28","2026-10-02",null,null,null,"Sta 261 Agawam","200","6","Annual ESD test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.","420901 SHELL/TGP BERKSHIRE POWER SALES HAM",261,null,"Sta 261 Agawam:  Annual ESD test\n--9/28/26 through 10/2/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n420901 SHELL/TGP BERKSHIRE POWER SALES HAM\n………………………………"]
["X26-279046",null,"2026-08-03","2026-08-07",null,null,null,"Sta 261","200","6","Unit 2D - Engine Inspection & Borescope","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,261.05,null,"Sta 261:  Unit 2D - Engine Inspection & Borescope\n--8/3/26 through 8/7/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1394098",null,"2026-07-05","2026-07-28",null,null,null,"MLV 261F-101 to MLV 261F-102","200","6","Make Piggable","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","420318 YANK GAS/TGP THOMPSONVILLE CT EXCH",261.10000000000002,null,"MLV 261F-101 to MLV 261F-102:  Make Piggable\n--7/5/26 through 7/28/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  \n420318 YANK GAS/TGP THOMPSONVILLE CT EXCH\n………………………………"]
["X26-279049",null,"2026-08-18","2026-08-19",null,null,null,"Sta 264 Charlton","200","6","Protective Devices","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,264,null,"Sta 264 Charlton:  Protective Devices\n--8/18/26 through 8/19/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-279053",null,"2026-09-23","2026-09-24",null,null,null,"Sta 264 Charlton","200","6","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,264,null,"Sta 264 Charlton:  Annual ESD Test\n--9/23/26 through 9/24/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1369750",null,"2026-08-05","2026-08-15",null,null,null,"MLV 265A-100","200","6","ECDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,265.10000000000002,null,"MLV 265A-100:  ECDA\n--8/5/26 through 8/15/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-288373",null,"2026-10-19","2026-10-24",null,null,null,"MLV 265E-111","200","6","ECDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,265.10000000000002,null,"MLV 265E-111:  ECDA\n--10/19/26 through 10/24/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1288895",null,"2026-06-22","2026-06-22",null,null,null,"MLV 265E-101.1 to MLV 265E-104","200","6","PIG RUNS - Gauge/Cleaning tool","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420707 OCEAN ST/TGP PROVIDENCE\n55258 NSTAR/TGP SUTTON DELIVERY WORCHESTE\n420758 NARNGST/TGP LINCOLN SMS PROVIDENCE\n420910 NARNGST/TGP SMITHFIELD DELIVERY PRO\n420926 RISEC/TGP FPLE RISE PROVIDENCE\n420750 NARNGST/TGP CRANSTON SALES PROVIDENCE\n55784 RHOBIO/TGP SCITUATE RNG REC PRO\n55785 RHOBIO/TGP SCITUATE RNG BUY BACK PR",265.101,null,"MLV 265E-101.1 to MLV 265E-104:  PIG RUNS - Gauge/Cleaning tool\n--6/22/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  \n420707 OCEAN ST/TGP PROVIDENCE\n55258 NSTAR/TGP SUTTON DELIVERY WORCHESTE\n420758 NARNGST/TGP LINCOLN SMS PROVIDENCE\n420910 NARNGST/TGP SMITHFIELD DELIVERY PRO\n420926 RISEC/TGP FPLE RISE PROVIDENCE\n420750 NARNGST/TGP CRANSTON SALES PROVIDENCE\n55784 RHOBIO/TGP SCITUATE RNG REC PRO\n55785 RHOBIO/TGP SCITUATE RNG BUY BACK PR\n………………………………"]
["X25-1288898",null,"2026-06-23","2026-06-23",null,null,null,"MLV 265E-101.1 to MLV 265E-104","200","6","PIG RUNS - Cal/IMU","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420707 OCEAN ST/TGP PROVIDENCE\n55258 NSTAR/TGP SUTTON DELIVERY WORCHESTE\n420758 NARNGST/TGP LINCOLN SMS PROVIDENCE\n420910 NARNGST/TGP SMITHFIELD DELIVERY PRO\n420926 RISEC/TGP FPLE RISE PROVIDENCE\n420750 NARNGST/TGP CRANSTON SALES PROVIDENCE\n55784 RHOBIO/TGP SCITUATE RNG REC PRO\n55785 RHOBIO/TGP SCITUATE RNG BUY BACK PR",265.101,null,"MLV 265E-101.1 to MLV 265E-104:  PIG RUNS - Cal/IMU\n--6/23/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  \n420707 OCEAN ST/TGP PROVIDENCE\n55258 NSTAR/TGP SUTTON DELIVERY WORCHESTE\n420758 NARNGST/TGP LINCOLN SMS PROVIDENCE\n420910 NARNGST/TGP SMITHFIELD DELIVERY PRO\n420926 RISEC/TGP FPLE RISE PROVIDENCE\n420750 NARNGST/TGP CRANSTON SALES PROVIDENCE\n55784 RHOBIO/TGP SCITUATE RNG REC PRO\n55785 RHOBIO/TGP SCITUATE RNG BUY BACK PR\n………………………………"]
["X25-1288899",null,"2026-06-24","2026-06-24",null,null,null,"MLV 265E-101.1 to MLV 265E-104","200","6","PIG RUNS - MFL-A","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420707 OCEAN ST/TGP PROVIDENCE\n55258 NSTAR/TGP SUTTON DELIVERY WORCHESTE\n420758 NARNGST/TGP LINCOLN SMS PROVIDENCE\n420910 NARNGST/TGP SMITHFIELD DELIVERY PRO\n420926 RISEC/TGP FPLE RISE PROVIDENCE\n420750 NARNGST/TGP CRANSTON SALES PROVIDENCE\n55784 RHOBIO/TGP SCITUATE RNG REC PRO\n55785 RHOBIO/TGP SCITUATE RNG BUY BACK PR",265.101,null,"MLV 265E-101.1 to MLV 265E-104:  PIG RUNS - MFL-A\n--6/24/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  \n420707 OCEAN ST/TGP PROVIDENCE\n55258 NSTAR/TGP SUTTON DELIVERY WORCHESTE\n420758 NARNGST/TGP LINCOLN SMS PROVIDENCE\n420910 NARNGST/TGP SMITHFIELD DELIVERY PRO\n420926 RISEC/TGP FPLE RISE PROVIDENCE\n420750 NARNGST/TGP CRANSTON SALES PROVIDENCE\n55784 RHOBIO/TGP SCITUATE RNG REC PRO\n55785 RHOBIO/TGP SCITUATE RNG BUY BACK PR\n………………………………"]
["X25-1369752",null,"2026-07-27","2026-08-01",null,null,null,"MLV 265E-121","200","6","ECDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,265.12,null,"MLV 265E-121:  ECDA\n--7/27/26 through 8/1/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-176029",null,"2026-08-03","2026-08-22",null,null,null,"MLV 266A-103A to 266A-103BR","200","6","Meter Station Work","This project may require a facility outage which could limit throughput and result in restrictions based on customer nominations.  Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420135 NARNGST/TGP PAWTUCKET RI PROVIDENCE",266.10000000000002,null,"MLV 266A-103A to 266A-103BR:  Meter Station Work\n--8/3/26 through 8/22/26:  This project may require a facility outage which could limit throughput and result in restrictions based on customer nominations.  Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  \n420135 NARNGST/TGP PAWTUCKET RI PROVIDENCE\n………………………………"]
["X26-176034",null,"2026-08-11","2026-08-13",null,null,null,"MLV 266A-103A to 266A-103BR","200","6","Meter Station Pipe Replacement","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","420135 NARNGST/TGP PAWTUCKET RI PROVIDENCE",266.11,null,"MLV 266A-103A to 266A-103BR:  Meter Station Pipe Replacement\n--8/11/26 through 8/13/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  \n420135 NARNGST/TGP PAWTUCKET RI PROVIDENCE\n………………………………"]
["X25-1385273",null,"2026-08-17","2026-08-21",null,null,null,"MLV 267-1 to MLV 270C","200","5","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,267.10000000000002,null,"MLV 267-1 to MLV 270C:  Anomaly Remediation\n--8/17/26 through 8/21/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1369754",null,"2026-10-05","2026-10-17",null,null,null,"MLV 268","200","6","DA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,268,null,"MLV 268:  DA\n--10/5/26 through 10/17/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X24-847658",null,"2026-04-03","2026-04-21",null,null,null,"MLV 270C-103 to MLV 270C-104","200","6","Meter Station Upgrade (Meter Peabody PIN 420658)","This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.","420658 MMWEC/TGP PEABODY SALES ESSEX",270.10000000000002,null,"MLV 270C-103 to MLV 270C-104:  Meter Station Upgrade (Meter Peabody PIN 420658)\n--4/3/26 through 4/21/26:  This project will require the facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed below will be shut-in during the project.  \n420658 MMWEC/TGP PEABODY SALES ESSEX\n………………………………"]
["X26-299795",null,"2026-06-08","2026-06-13",null,null,null,"MLV 270C-103 to MLV 270C-103R","200","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,270.10000000000002,null,"MLV 270C-103 to MLV 270C-103R:  Anomaly Remediation\n--6/8/26 through 6/13/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1369755",null,"2026-08-31","2026-09-09",null,null,null,"MLV 270A-100","200","6","ECDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,270.10000000000002,null,"MLV 270A-100:  ECDA\n--8/31/26 through 9/9/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1369758",null,"2026-08-17","2026-08-29",null,null,null,"MLV 270C-1100","200","6","ECDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,270.11,null,"MLV 270C-1100:  ECDA\n--8/17/26 through 8/29/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1369757",null,"2026-09-10","2026-09-19",null,null,null,"MLV 270C-111","200","6","ECDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,270.11,null,"MLV 270C-111:  ECDA\n--9/10/26 through 9/19/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-299756",null,"2026-04-16","2026-04-22",null,null,null,"MLV 270-2 to MLV 271-2","200","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,270.2,null,"MLV 270-2 to MLV 271-2:  Anomaly Remediation\n--4/16/26 through 4/22/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1288911",null,"2026-06-16","2026-06-16",null,null,null,"MLV 270C-301 to MLV 270C-302","200","6","Pig Run - Gauge/Cleaning tool","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.","420116 - BOSTN/TGP REVERE MA MIDDLESEX\n420117 - BOSTN/TGP LYNN MA ESSEX\n420343 - BOSTN/TGP LYNN FIELD MA ESSEX\n412513 - CONSTGEN/TGP DISTRIGAS RECEIPT MIDD\n420848 - WAKEFLD/TGP WAKEFIELD SALES ESSEX",270.30099999999999,null,"MLV 270C-301 to MLV 270C-302:  Pig Run - Gauge/Cleaning tool\n--6/16/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.  \n420116 - BOSTN/TGP REVERE MA MIDDLESEX\n420117 - BOSTN/TGP LYNN MA ESSEX\n420343 - BOSTN/TGP LYNN FIELD MA ESSEX\n412513 - CONSTGEN/TGP DISTRIGAS RECEIPT MIDD\n420848 - WAKEFLD/TGP WAKEFIELD SALES ESSEX\n………………………………"]
["X25-1288914",null,"2026-06-17","2026-06-17",null,null,null,"MLV 270C-301 to MLV 270C-302","200","6","Pig Run - Cal/IMU/MFL-A Combo","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.","420116 - BOSTN/TGP REVERE MA MIDDLESEX\n420117 - BOSTN/TGP LYNN MA ESSEX\n420343 - BOSTN/TGP LYNN FIELD MA ESSEX\n412513 - CONSTGEN/TGP DISTRIGAS RECEIPT MIDD\n420848 - WAKEFLD/TGP WAKEFIELD SALES ESSEX",270.30099999999999,null,"MLV 270C-301 to MLV 270C-302:  Pig Run - Cal/IMU/MFL-A Combo\n--6/17/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.  \n420116 - BOSTN/TGP REVERE MA MIDDLESEX\n420117 - BOSTN/TGP LYNN MA ESSEX\n420343 - BOSTN/TGP LYNN FIELD MA ESSEX\n412513 - CONSTGEN/TGP DISTRIGAS RECEIPT MIDD\n420848 - WAKEFLD/TGP WAKEFIELD SALES ESSEX\n………………………………"]
["X25-1288750","***","2026-03-27","2026-03-27","Completed",null,null,"MLV 270C-501 to MLV 270C-502","200","6","Pig Runs - MFL-C - 3/27/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meter listed may be constrained or shut in during the project.","420935 BOSTN/TGP DANVERS ESSES\n420138 BOSTN/TGP WENHAM MA ESSEX\n420323 BOSTN/TGP ESSEX MA ESSEX\n420119 BOSTN/TGP GLOUCHESTER MA ESSEX",270.52,"------","***MLV 270C-501 to MLV 270C-502:  Pig Runs - MFL-C - 3/27/26\n***Completed\nThe following meters are available for nominations:\n420935 BOSTN/TGP DANVERS ESSES\n420138 BOSTN/TGP WENHAM MA ESSEX\n420323 BOSTN/TGP ESSEX MA ESSEX\n420119 BOSTN/TGP GLOUCHESTER MA ESSEX"]
["X25-1369759",null,"2026-09-21","2026-10-03",null,null,null,"MLV 273","200","6","ECDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,273,null,"MLV 273:  ECDA\n--9/21/26 through 10/3/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-299757",null,"2026-04-23","2026-05-01",null,null,null,"MLV 273-2A to MLV 273-2AR","200","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,273.2,null,"MLV 273-2A to MLV 273-2AR:  Anomaly Remediation\n--4/23/26 through 5/1/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-299803",null,"2026-06-01","2026-06-06",null,null,null,"MLV 302-2 to MLV 303-2","300","4","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,302.2,null,"MLV 302-2 to MLV 303-2:  Anomaly Remediation\n--6/1/26 through 6/6/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-75116",null,"2026-06-01","2026-06-05",null,null,null,"Sta 303A","300","4","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,303,null,"Sta 303A:  Annual ESD Test & Maintenance\n--6/1/26 through 6/5/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-75119",null,"2026-06-01","2026-06-05",null,null,null,"Sta 303A","300","4","Unit 1A - Protective Device Checks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,303.00099999999998,null,"Sta 303A:  Unit 1A - Protective Device Checks\n--6/1/26 through 6/5/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-75121",null,"2026-06-01","2026-06-05",null,null,null,"Sta 303A","300","4","Unit 1A - Water Wash","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,303.00099999999998,null,"Sta 303A:  Unit 1A - Water Wash\n--6/1/26 through 6/5/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-75120",null,"2026-10-06","2026-10-07",null,null,null,"Sta 303A","300","4","Unit 1A - Water Wash","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,303.00099999999998,null,"Sta 303A:  Unit 1A - Water Wash\n--10/6/26 through 10/7/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-299984",null,"2026-05-04","2026-05-23",null,null,null,"MLV 304-1 to MLV 305-1","300","4","Anomaly Remediation","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,304.10000000000002,null,"MLV 304-1 to MLV 305-1:  Anomaly Remediation\n--5/4/26 through 5/23/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-75128",null,"2026-08-03","2026-08-07",null,null,null,"Sta 307 (Pigeon)","300","4","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,307,null,"Sta 307 (Pigeon):  Annual ESD Test & Maintenance\n--8/3/26 through 8/7/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-231386","***","2026-02-09","2026-03-27","Completed",null,null,"Sta 307","300","4","Units 1A to 4A - Replace JW Pipe","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,307.00099999999998,"------","***Sta 307:  Units 1A to 4A - Replace JW Pipe\n***Completed"]
["X26-75129",null,"2026-07-20","2026-07-24",null,null,null,"Sta 307","300","4","Unit 1A - Protective Device Checks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,307.00099999999998,null,"Sta 307:  Unit 1A - Protective Device Checks\n--7/20/26 through 7/24/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-75130",null,"2026-07-20","2026-07-24",null,null,null,"Sta 307","300","4","Unit 2A - Protective Device Checks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,307.00200000000001,null,"Sta 307:  Unit 2A - Protective Device Checks\n--7/20/26 through 7/24/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-75122",null,"2026-06-08","2026-06-12",null,null,null,"Sta 307","300","4","Unit 3A - Turbocharger swap","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,307.00299999999999,null,"Sta 307:  Unit 3A - Turbocharger swap\n--6/8/26 through 6/12/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-75131",null,"2026-07-20","2026-07-24",null,null,null,"Sta 307","300","4","Unit 3A - Protective Device Checks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,307.00299999999999,null,"Sta 307:  Unit 3A - Protective Device Checks\n--7/20/26 through 7/24/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-75132",null,"2026-07-20","2026-07-24",null,null,null,"Sta 307","300","4","Unit 4A - Protective Device Checks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,307.00400000000002,null,"Sta 307:  Unit 4A - Protective Device Checks\n--7/20/26 through 7/24/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-75126",null,"2026-08-03","2026-08-07",null,null,null,"Sta 307","300","4","Unit 4A - Turbocharger Swap","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,307.00400000000002,null,"Sta 307:  Unit 4A - Turbocharger Swap\n--8/3/26 through 8/7/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-75124",null,"2026-09-29","2026-10-02",null,null,null,"Sta 307","300","4","Unit 4A - Trabon","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,307.00400000000002,null,"Sta 307:  Unit 4A - Trabon\n--9/29/26 through 10/2/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-377799","***","2026-03-29","2026-04-17","Added",null,null,"Sta 307","300","4","Unit 5A - Liner","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,307.005,"------","***Sta 307:  Unit 5A - Liner\n--3/29/26 through 4/17/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***Added\n………………………………"]
["X26-365960","***","2026-04-13","2026-04-17","Added",null,null,"Sta 307","300","4","Unit 5A - Exhaust Bellows Change Out","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,307.005,"------","***Sta 307:  Unit 5A - Exhaust Bellows Change Out\n--4/13/26 through 4/17/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***Added\n………………………………"]
["X26-75133",null,"2026-08-03","2026-08-07",null,null,null,"Sta 307","300","4","Unit 5A - Protective Device Checks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,307.005,null,"Sta 307:  Unit 5A - Protective Device Checks\n--8/3/26 through 8/7/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-75134",null,"2026-08-03","2026-08-07",null,null,null,"Sta 307","300","4","Unit 6A - Protective Device Checks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,307.00599999999997,null,"Sta 307:  Unit 6A - Protective Device Checks\n--8/3/26 through 8/7/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-279198",null,"2026-09-08","2026-09-08",null,null,null,"Station 310 Smethport","300","4","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,310,null,"Station 310 Smethport:  Annual ESD Test\n--9/8/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-53663",null,"2026-04-13","2026-04-23",null,null,null,"Ellisburg Storage","300","4","Shut-in Test","This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","460012 – DOMINION/TGP ELLISBURG INJECTION PO",312.99,null,"Ellisburg Storage:  Shut-in Test\n--4/13/26 through 4/23/26:  This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  \n460012 – DOMINION/TGP ELLISBURG INJECTION PO\n………………………………"]
["X26-279200",null,"2026-08-17","2026-08-20",null,null,null,"Sta 313 Coudersport","300","4","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,313,null,"Sta 313 Coudersport:  Annual ESD Test & Maintenance\n--8/17/26 through 8/20/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-398913","***","2026-04-06","2026-04-09","Added",null,null,"Sta 313","300","4","Unit 5A - Compressor Inspections","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,313.005,"------","***Sta 313:  Unit 5A - Compressor Inspections\n--4/6/26 through 4/9/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***Added\n………………………………"]
["X26-228676",null,"2026-04-21","2026-04-21",null,null,null,"Sta 313","300","4","Unit 1C - Power Company Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,313.03300000000002,null,"Sta 313:  Unit 1C - Power Company Maintenance\n--4/21/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-53666",null,"2026-04-13","2026-04-23",null,null,null,"Hebron Storage","300","4","Shut-in Test","This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","400485 HEBRON STORAGE INJECTION POTTER\n470001 HEBRON STORAGE WITHDRAWAL POTTER",313.33,null,"Hebron Storage:  Shut-in Test\n--4/13/26 through 4/23/26:  This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  \n400485 HEBRON STORAGE INJECTION POTTER\n470001 HEBRON STORAGE WITHDRAWAL POTTER\n………………………………"]
["X26-39654",null,"2026-04-07","2026-04-07",null,null,null,"Sta 313 to Sta 237","300","5","Pig Run - Cleaning Run (HC Line)","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.    The meters listed may be constrained or shut in during the project",null,313.39999999999998,null,"Sta 313 to Sta 237:  Pig Run - Cleaning Run (HC Line)\n--4/7/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.    The meters listed may be constrained or shut in during the project  \n………………………………"]
["X26-53664",null,"2026-04-06","2026-04-13",null,null,null,"Harrison Storage","300","4","Shut-in Test","This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.","460004 – DOMINION/TGP HARRISON INJECTION POT",313.5,null,"Harrison Storage:  Shut-in Test\n--4/6/26 through 4/13/26:  This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  The meter listed may be constrained or shut in during the project.  \n460004 – DOMINION/TGP HARRISON INJECTION POT\n………………………………"]
["X25-1385274",null,"2026-06-01","2026-06-05",null,null,null,"MLV 313A-101 to MLV 313A-4010A","300","5","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,313.5,null,"MLV 313A-101 to MLV 313A-4010A:  Anomaly Remediation\n--6/1/26 through 6/5/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-299798",null,"2026-06-29","2026-07-03",null,null,null,"MLV 313A-101L to MLV 313A-101A","300","5","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,313.5,null,"MLV 313A-101L to MLV 313A-101A:  Anomaly Remediation\n--6/29/26 through 7/3/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-299786",null,"2026-07-06","2026-07-10",null,null,null,"MLV 313A-101A to MLV 313A-401","300","5","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,313.51,null,"MLV 313A-101A to MLV 313A-401:  Anomaly Remediation\n--7/6/26 through 7/10/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-299788",null,"2026-07-10","2026-07-14",null,null,null,"MLV 313A-403 to MLV 313A-404","300","5","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,313.52,null,"MLV 313A-403 to MLV 313A-404:  Anomaly Remediation\n--7/10/26 through 7/14/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-299789",null,"2026-07-15","2026-07-23",null,null,null,"MLV 313A-405A to MLV 313A-406","300","5","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,313.52999999999997,null,"MLV 313A-405A to MLV 313A-406:  Anomaly Remediation\n--7/15/26 through 7/23/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-330225",null,"2026-05-05","2026-05-05",null,null,null,"MLV 314-3BR to MLV 315-3L","300","4","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,314.3,null,"MLV 314-3BR to MLV 315-3L:  Pig Run - Maintenance\n--5/5/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X26-279197",null,"2026-05-26","2026-05-26",null,null,null,"Sta 315 Wellsboro","300","4","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,315,null,"Sta 315 Wellsboro:  Annual ESD Test\n--5/26/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-330221",null,"2026-05-05","2026-05-05",null,null,null,"MLV 315H-3AL to MLV 315-3L","300","4","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,315.3,null,"MLV 315H-3AL to MLV 315-3L:  Pig Run - Maintenance\n--5/5/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X26-279075",null,"2026-08-24","2026-08-28",null,null,null,"Sta 317","300","4","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,317,null,"Sta 317:  Annual ESD Test & Maintenance\n--8/24/26 through 8/28/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1369746",null,"2026-06-08","2026-06-20",null,null,null,"MLV 317-1 to MLV 319-1","300","4","SCCDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,317.10000000000002,null,"MLV 317-1 to MLV 319-1:  SCCDA\n--6/8/26 through 6/20/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-279072",null,"2026-07-07","2026-07-08",null,null,null,"Sta 319","300","4","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,319,null,"Sta 319:  Annual ESD Test\n--7/7/26 through 7/8/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-279069",null,"2026-07-21","2026-07-23",null,null,null,"Sta 321","300","5","Station Valves for ESD System","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,321,null,"Sta 321:  Station Valves for ESD System\n--7/21/26 through 7/23/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-175978","***","2026-03-24","2026-03-27","Completed",null,null,"Sta 321","300","4","Unit 5B - Turbine Inspections","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,321.017,"------","***Sta 321:  Unit 5B - Turbine Inspections\n***Completed"]
["X26-175982","***","2026-03-26","2026-03-26","Completed",null,null,"Sta 321","300","4","Unit 6B - Turbine Inspections","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,321.01799999999997,"------","***Sta 321:  Unit 6B - Turbine Inspections\n***Completed"]
["X26-175984","***","2026-03-27","2026-03-27","Completed",null,null,"Sta 321","300","4","Unit 7B - Turbine Inspections","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,321.01900000000001,"------","***Sta 321:  Unit 7B - Turbine Inspections\n***Completed"]
["X26-175971","***","2026-03-23","2026-03-26","Completed",null,null,"Sta 321","300","4","Unit 1C - Turbine Inspections","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,321.03300000000002,"------","***Sta 321:  Unit 1C - Turbine Inspections\n***Completed"]
["X26-175979","***","2026-03-25","2026-03-26","Completed",null,null,"Sta 321","300","4","Unit 2C - Turbine Inspections","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,321.03399999999999,"------","***Sta 321:  Unit 2C - Turbine Inspections\n***Completed"]
["X26-299805",null,"2026-08-03","2026-08-08",null,null,null,"MLV 321-1L to MLV 322-1","300","5","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,321.10000000000002,null,"MLV 321-1L to MLV 322-1:  Anomaly Remediation\n--8/3/26 through 8/8/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-169174",null,"2026-05-04","2026-05-07",null,null,null,"Sta 323A Lackawaxen","300","4","Annual ESD Testing & Valve Replacement","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,323,null,"Sta 323A Lackawaxen:  Annual ESD Testing & Valve Replacement\n--5/4/26 through 5/7/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-169183",null,"2026-05-04","2026-05-22",null,null,null,"Sta. 323A","300","4","Unit 1A - ABB Drive Modernization","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,323.00099999999998,null,"Sta. 323A:  Unit 1A - ABB Drive Modernization\n--5/4/26 through 5/22/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-299771",null,"2026-07-26","2026-08-01",null,null,null,"MLV 324-1 to MLV 324-1A","300","5","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,324.10000000000002,null,"MLV 324-1 to MLV 324-1A:  Anomaly Remediation\n--7/26/26 through 8/1/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-362883","***","2026-06-10","2026-06-10","Added",null,null,"MLV 325-1 to MLV 329-1","300","5","Pig runs - Cal/IMU","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.    The meters listed may be constrained or shut in during the project","420410 ELIZTOWN/TGP SUSSEX NJ SUSSEX\n420450 ELIZTOWN/TGP VERNON NJ SUSSEX\n420608 NJ NATGS/TGP NEW CLINTON ROAD NJ BE\n420339 PSEG/TGP WEST MILFORD NJ PASSAIC\n420516 PSEG/TGP RINGWOOD NJ PASSAIC\n420226 PSEG/TGP RAMSEY NJ BERGEN",325.00099999999998,"------","***MLV 325-1 to MLV 329-1:  Pig runs - Cal/IMU\n--6/10/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.    The meters listed may be constrained or shut in during the project  \n420410 ELIZTOWN/TGP SUSSEX NJ SUSSEX\n420450 ELIZTOWN/TGP VERNON NJ SUSSEX\n420608 NJ NATGS/TGP NEW CLINTON ROAD NJ BE\n420339 PSEG/TGP WEST MILFORD NJ PASSAIC\n420516 PSEG/TGP RINGWOOD NJ PASSAIC\n420226 PSEG/TGP RAMSEY NJ BERGEN\n***Added\n………………………………"]
["X26-60761",null,"2026-07-07","2026-07-08",null,null,null,"Sta 325","300","5","Units 3A - Water Wash & Borescope","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,325.00299999999999,null,"Sta 325:  Units 3A - Water Wash & Borescope\n--7/7/26 through 7/8/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-335417","***","2026-03-31","2026-04-01","Completed",null,null,"Sta 325","300","4","Units 4A - Solar Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,325.00400000000002,"------","***Sta 325:  Units 4A - Solar Inspection\n***Completed"]
["X26-60759",null,"2026-07-06","2026-07-07",null,null,null,"Sta 325","300","5","Units 4A - Water Wash & Borescope","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,325.00400000000002,null,"Sta 325:  Units 4A - Water Wash & Borescope\n--7/6/26 through 7/7/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-60765",null,"2026-07-08","2026-07-09",null,null,null,"Sta 325","300","5","Units 1B - Water Wash & Borescope","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,325.017,null,"Sta 325:  Units 1B - Water Wash & Borescope\n--7/8/26 through 7/9/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1293066",null,"2026-05-01","2026-05-31",null,null,null,"MLV 325-1 to MLV 329-1","300","6","Make Piggable","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,325.10000000000002,null,"MLV 325-1 to MLV 329-1:  Make Piggable\n--5/1/26 through 5/31/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1320304",null,"2026-06-09","2026-06-09",null,null,null,"MLV 325-1 to MLV 329-1","300","5","Pig runs - Cleaning/Gauge 6/9/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420410 ELIZTOWN/TGP SUSSEX NJ SUSSEX\n420450 ELIZTOWN/TGP VERNON NJ SUSSEX\n420608 NJ NATGS/TGP NEW CLINTON ROAD NJ BE\n420339 PSEG/TGP WEST MILFORD NJ PASSAIC\n420516 PSEG/TGP RINGWOOD NJ PASSAIC\n420226 PSEG/TGP RAMSEY NJ BERGEN",325.10000000000002,null,"MLV 325-1 to MLV 329-1:  Pig runs - Cleaning/Gauge 6/9/26\n--6/9/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  \n420410 ELIZTOWN/TGP SUSSEX NJ SUSSEX\n420450 ELIZTOWN/TGP VERNON NJ SUSSEX\n420608 NJ NATGS/TGP NEW CLINTON ROAD NJ BE\n420339 PSEG/TGP WEST MILFORD NJ PASSAIC\n420516 PSEG/TGP RINGWOOD NJ PASSAIC\n420226 PSEG/TGP RAMSEY NJ BERGEN\n………………………………"]
["X25-1320305","***","2026-06-11","2026-06-11","Project Change",null,null,"MLV 325-1 to MLV 329-1","300","5","Pig runs - MFL-C 6/11/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420410 ELIZTOWN/TGP SUSSEX NJ SUSSEX\n420450 ELIZTOWN/TGP VERNON NJ SUSSEX\n420608 NJ NATGS/TGP NEW CLINTON ROAD NJ BE\n420339 PSEG/TGP WEST MILFORD NJ PASSAIC\n420516 PSEG/TGP RINGWOOD NJ PASSAIC\n420226 PSEG/TGP RAMSEY NJ BERGEN",325.10000000000002,"------------mantenance_desc------model_loc--","***MLV 325-1 to MLV 329-1:  Pig runs - MFL-C 6/11/26\n--6/11/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  \n420410 ELIZTOWN/TGP SUSSEX NJ SUSSEX\n420450 ELIZTOWN/TGP VERNON NJ SUSSEX\n420608 NJ NATGS/TGP NEW CLINTON ROAD NJ BE\n420339 PSEG/TGP WEST MILFORD NJ PASSAIC\n420516 PSEG/TGP RINGWOOD NJ PASSAIC\n420226 PSEG/TGP RAMSEY NJ BERGEN\n***Project Change\n………………………………"]
["X25-1320372",null,"2026-10-19","2026-10-19",null,null,null,"MLV 325-1 to MLV 329-1","300","5","Pig runs - Cleaning/Gauge 6/10/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420410 ELIZTOWN/TGP SUSSEX NJ SUSSEX\n420450 ELIZTOWN/TGP VERNON NJ SUSSEX\n420608 NJ NATGS/TGP NEW CLINTON ROAD NJ BE\n420339 PSEG/TGP WEST MILFORD NJ PASSAIC\n420516 PSEG/TGP RINGWOOD NJ PASSAIC\n420226 PSEG/TGP RAMSEY NJ BERGEN",325.10000000000002,null,"MLV 325-1 to MLV 329-1:  Pig runs - Cleaning/Gauge 6/10/26\n--10/19/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  \n420410 ELIZTOWN/TGP SUSSEX NJ SUSSEX\n420450 ELIZTOWN/TGP VERNON NJ SUSSEX\n420608 NJ NATGS/TGP NEW CLINTON ROAD NJ BE\n420339 PSEG/TGP WEST MILFORD NJ PASSAIC\n420516 PSEG/TGP RINGWOOD NJ PASSAIC\n420226 PSEG/TGP RAMSEY NJ BERGEN\n………………………………"]
["X25-1320306",null,"2026-10-20","2026-10-20",null,null,null,"MLV 325-1 to MLV 329-1","300","5","Pig runs - EMAT 10/20/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420410 ELIZTOWN/TGP SUSSEX NJ SUSSEX\n420450 ELIZTOWN/TGP VERNON NJ SUSSEX\n420608 NJ NATGS/TGP NEW CLINTON ROAD NJ BE\n420339 PSEG/TGP WEST MILFORD NJ PASSAIC\n420516 PSEG/TGP RINGWOOD NJ PASSAIC\n420226 PSEG/TGP RAMSEY NJ BERGEN",325.10000000000002,null,"MLV 325-1 to MLV 329-1:  Pig runs - EMAT 10/20/26\n--10/20/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  \n420410 ELIZTOWN/TGP SUSSEX NJ SUSSEX\n420450 ELIZTOWN/TGP VERNON NJ SUSSEX\n420608 NJ NATGS/TGP NEW CLINTON ROAD NJ BE\n420339 PSEG/TGP WEST MILFORD NJ PASSAIC\n420516 PSEG/TGP RINGWOOD NJ PASSAIC\n420226 PSEG/TGP RAMSEY NJ BERGEN\n………………………………"]
["X25-1369761",null,"2026-04-27","2026-05-06",null,null,null,"MLV 335-1","300","5","ECDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,328,null,"MLV 335-1:  ECDA\n--4/27/26 through 5/6/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1369760",null,"2026-05-07","2026-05-16",null,null,null,"MLV 328","300","5","ECDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,328,null,"MLV 328:  ECDA\n--5/7/26 through 5/16/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1293073",null,"2026-07-20","2026-08-30",null,null,null,"MLV 329AS-1 to MLV 329AD-1","300","6","Valve Replacement - MLV 329-1","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,329.1,null,"MLV 329AS-1 to MLV 329AD-1:  Valve Replacement - MLV 329-1\n--7/20/26 through 8/30/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-54701",null,"2026-04-06","2026-04-10",null,null,null,"MLV 336-1 to MLV 337-1","300","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,336.1,null,"MLV 336-1 to MLV 337-1:  Anomaly Remediation\n--4/6/26 through 4/10/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-54702",null,"2026-04-11","2026-04-15",null,null,null,"MLV 337-1 to MLV 338-1","300","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,337.1,null,"MLV 337-1 to MLV 338-1:  Anomaly Remediation\n--4/11/26 through 4/15/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-54703",null,"2026-04-16","2026-04-20",null,null,null,"MLV 338-1 to MLV 339-1","300","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,338.1,null,"MLV 338-1 to MLV 339-1:  Anomaly Remediation\n--4/16/26 through 4/20/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-54707",null,"2026-04-21","2026-04-25",null,null,null,"MLV 339-1 to MLV 340-1","300","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,339.1,null,"MLV 339-1 to MLV 340-1:  Anomaly Remediation\n--4/21/26 through 4/25/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-54711",null,"2026-04-26","2026-04-30",null,null,null,"MLV 340-1 to MLV 341-1","300","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,340.1,null,"MLV 340-1 to MLV 341-1:  Anomaly Remediation\n--4/26/26 through 4/30/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-54713",null,"2026-05-01","2026-05-05",null,null,null,"MLV 341-1 to MLV 342-1","300","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,341.1,null,"MLV 341-1 to MLV 342-1:  Anomaly Remediation\n--5/1/26 through 5/5/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-54717",null,"2026-05-06","2026-05-10",null,null,null,"MLV 342-1 to MLV 343-1","300","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,342.1,null,"MLV 342-1 to MLV 343-1:  Anomaly Remediation\n--5/6/26 through 5/10/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-54718",null,"2026-05-11","2026-05-15",null,null,null,"MLV 343-1 to MLV 344-1","300","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,343.1,null,"MLV 343-1 to MLV 344-1:  Anomaly Remediation\n--5/11/26 through 5/15/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-54719",null,"2026-05-16","2026-05-20",null,null,null,"MLV 344-1 to MLV 345-1","300","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,344.1,null,"MLV 344-1 to MLV 345-1:  Anomaly Remediation\n--5/16/26 through 5/20/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1369765",null,"2026-04-13","2026-04-25",null,null,null,"MLV 345-1","300","5","ECDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,345.1,null,"MLV 345-1:  ECDA\n--4/13/26 through 4/25/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-54721",null,"2026-05-21","2026-05-25",null,null,null,"MLV 345-1 to MLV 346-1","300","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.","420425 CONN NG/TGP MILFORD CT NEW HAVEN",345.1,null,"MLV 345-1 to MLV 346-1:  Anomaly Remediation\n--5/21/26 through 5/25/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  The meter listed will be shut in during the project.  \n420425 CONN NG/TGP MILFORD CT NEW HAVEN\n………………………………"]
["X26-54736",null,"2026-05-26","2026-05-30",null,null,null,"MLV 346-1 to MLV 347-1","300","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,346.1,null,"MLV 346-1 to MLV 347-1:  Anomaly Remediation\n--5/26/26 through 5/30/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-54739",null,"2026-05-31","2026-06-04",null,null,null,"MLV 347-1 to MLV 348-1","300","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,347.1,null,"MLV 347-1 to MLV 348-1:  Anomaly Remediation\n--5/31/26 through 6/4/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-54744",null,"2026-06-05","2026-06-09",null,null,null,"MLV 349-1 to MLV 350-1","300","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,349.1,null,"MLV 349-1 to MLV 350-1:  Anomaly Remediation\n--6/5/26 through 6/9/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-54748",null,"2026-06-10","2026-06-14",null,null,null,"MLV 350-1 to MLV 351-1","300","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,350.1,null,"MLV 350-1 to MLV 351-1:  Anomaly Remediation\n--6/10/26 through 6/14/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-54750",null,"2026-06-15","2026-06-19",null,null,null,"MLV 351-1 to MLV 352-1","300","6","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,351.1,null,"MLV 351-1 to MLV 352-1:  Anomaly Remediation\n--6/15/26 through 6/19/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-148537",null,"2026-06-20","2026-06-23",null,null,null,"MLV 353-1 to MLV 354-1","300","5","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,353.1,null,"MLV 353-1 to MLV 354-1:  Anomaly Remediation\n--6/20/26 through 6/23/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-39835",null,"2026-07-07","2026-07-09",null,null,null,"Sta 405A","300","5","Annual ESD Test / Filter Scrubber","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,405,null,"Sta 405A:  Annual ESD Test / Filter Scrubber\n--7/7/26 through 7/9/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-39652",null,"2026-04-07","2026-04-07",null,null,null,"Sta 405A","200","5","Unit Water Wash","This project will require a unit outage, which will limit throughput through the station and result in resThis project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.trictions based on customer nominations.",null,405.00099999999998,null,"Sta 405A:  Unit Water Wash\n--4/7/26:  This project will require a unit outage, which will limit throughput through the station and result in resThis project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.trictions based on customer nominations.  \n………………………………"]
["X26-39867",null,"2026-10-13","2026-10-13",null,null,null,"Sta 405A","300","5","Unit 1A - 4k Waterwash","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,405.00099999999998,null,"Sta 405A:  Unit 1A - 4k Waterwash\n--10/13/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-39653",null,"2026-10-14","2026-10-14",null,null,null,"Sta 405A","200","5","Unit 1A - 8K Solar Turbine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,405.00099999999998,null,"Sta 405A:  Unit 1A - 8K Solar Turbine Inspection\n--10/14/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-259019",null,"2026-06-22","2026-06-28",null,null,null,"Sta 409","400","0","Unit 2A - 8k Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,409.00200000000001,null,"Sta 409:  Unit 2A - 8k Maintenance\n--6/22/26 through 6/28/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-169003",null,"2026-04-06","2026-04-10",null,null,null,"MLV 409A-102 to MLV 409A-102BR","400","0","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,409.1,null,"MLV 409A-102 to MLV 409A-102BR:  Anomaly Remediation\n--4/6/26 through 4/10/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-299679",null,"2026-09-01","2026-10-31",null,null,null,"MLV 409-1 to MLV 406-1","100","0","Spike Test","This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,409.1,null,"MLV 409-1 to MLV 406-1:  Spike Test\n--9/1/26 through 10/31/26:  This project will require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-296601",null,"2026-09-01","2026-10-31",null,null,null,"MLV 409A-102 to MLV 409A-103","400","0","Special Permit Stopple Project","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,409.4,null,"MLV 409A-102 to MLV 409A-103:  Special Permit Stopple Project\n--9/1/26 through 10/31/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-279080","***","2026-04-14","2026-04-16","Project Change","2026-05-19","2026-05-19","Sta. 409A Alamo","400","0","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,409.5,"--start_date--end_date--------------model_loc--","***Sta. 409A Alamo:  Annual ESD Test\n--4/14/26 through 4/16/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***\nDate Change, Previously scheduled 5/19/26.\n………………………………"]
["X26-192475",null,"2026-09-09","2026-09-09",null,null,null,"Sta 500-1 to Sta 823 (MLV 507-1)","500","L","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.    The meters listed may be constrained or shut in during the project.","420373 TRNSCO/TGP KINDER LA EXCH (BI 1\n420708 ELIZ NG/TGP GRANT LA SALES ALLEN\n420436 VERNON/TGP PITKIN LA VERNON\n420793 ELIZ NG/TGP J R FRANKS 1 VERNON\n420388 PROVNCAL/TGP PROVENCAL LA NATCHITOC",500.1,null,"Sta 500-1 to Sta 823 (MLV 507-1):  Pig Run - Maintenance\n--9/9/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.    The meters listed may be constrained or shut in during the project.  \n420373 TRNSCO/TGP KINDER LA EXCH (BI 1\n420708 ELIZ NG/TGP GRANT LA SALES ALLEN\n420436 VERNON/TGP PITKIN LA VERNON\n420793 ELIZ NG/TGP J R FRANKS 1 VERNON\n420388 PROVNCAL/TGP PROVENCAL LA NATCHITOC\n………………………………"]
["X25-1389565",null,"2026-09-07","2026-09-11",null,null,null,"MLV 507F-101 to MLV 507F-104","500","L","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,507.1,null,"MLV 507F-101 to MLV 507F-104:  Anomaly Remediation\n--9/7/26 through 9/11/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1389563",null,"2026-09-14","2026-09-25",null,null,null,"MLV 507F-101 to MLV 507F-104","500","L","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,507.1,null,"MLV 507F-101 to MLV 507F-104:  Anomaly Remediation\n--9/14/26 through 9/25/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-326921","***","2026-04-01","2026-04-01","Completed",null,null,"MLV 516 to Sta 523","500","L","Pig Run - Cleaning / Gauge","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.    The meters listed may be constrained or shut in during the project.","412705 MTBB/TGP MARTIN WELL 1 ST MARY\n412189 CRTXLIG/TGP DOG LAKE TERREBONNE",516,"------","***MLV 516 to Sta 523:  Pig Run - Cleaning / Gauge\n***Completed\nThe following meters are available for nominations:\n412705 MTBB/TGP MARTIN WELL 1 ST MARY\n412189 CRTXLIG/TGP DOG LAKE TERREBONNE"]
["X25-1367826","***","2026-07-06","2026-07-10","Project Change","2026-04-18","2026-04-23","Sta 523 to MLV 516","100","L","Pig Run - Cleaning / Gauge 7/6/26 to 7/10/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","412705 MTBB/TGP MARTIN WELL 1 ST MARY\n412189 CRTXLIG/TGP DOG LAKE TERREBONNE\n412684 ANR/TGP SHADYSIDE ST MARY",516.00099999999998,"--start_date--end_date--meters_affected------mantenance_desc------model_loc--","***Sta 523 to MLV 516:  Pig Run - Cleaning / Gauge 7/6/26 to 7/10/26\n--7/6/26 through 7/10/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  \n412705 MTBB/TGP MARTIN WELL 1 ST MARY\n412189 CRTXLIG/TGP DOG LAKE TERREBONNE\n412684 ANR/TGP SHADYSIDE ST MARY\n***\nDate Change, Previously scheduled 4/18/26 to 4/23/26.\n………………………………"]
["X25-1367829","***","2026-07-11","2026-07-11","Project Change","2026-04-24","2026-04-24","Sta 523 to MLV 516","500","L","Pig Run - MFL-A 7/11/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","412705 MTBB/TGP MARTIN WELL 1 ST MARY\n412189 CRTXLIG/TGP DOG LAKE TERREBONNE\n412684 ANR/TGP SHADYSIDE ST MARY",516.00199999999995,"--start_date--end_date--meters_affected------mantenance_desc------model_loc--","***Sta 523 to MLV 516:  Pig Run - MFL-A 7/11/26\n--7/11/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  \n412705 MTBB/TGP MARTIN WELL 1 ST MARY\n412189 CRTXLIG/TGP DOG LAKE TERREBONNE\n412684 ANR/TGP SHADYSIDE ST MARY\n***\nDate Change, Previously scheduled 4/24/26.\n………………………………"]
["X26-221794","***","2026-03-26","2026-03-27","Completed",null,null,"Sta 523","500","L","Unit 2B - 4k Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,523.01800000000003,"------","***Sta 523:  Unit 2B - 4k Maintenance\n***Completed"]
["X26-176247",null,"2026-04-06","2026-04-10",null,null,null,"Sta 529","500","L","Annual ESD & 4k Inspection","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,527,null,"Sta 529:  Annual ESD & 4k Inspection\n--4/6/26 through 4/10/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-279065",null,"2026-05-07","2026-05-07",null,null,null,"Sta. 527 Port Sulphur","500","L","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,527,null,"Sta. 527 Port Sulphur:  Annual ESD Test\n--5/7/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-195296","***","2026-02-04","2026-04-17","Project Change",null,"2026-03-27","Sta 527","500","0","Unit 1C - High Vibration","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,527.03300000000002,"----end_date--------------model_loc--","***Sta 527:  Unit 1C - High Vibration\n--2/4/26 through 4/17/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***\nDate Change, Previously scheduled 2/4/26 to 3/27/26.\n………………………………"]
["X26-326909",null,"2026-05-07","2026-05-07",null,null,null,"Sta 530","500","L","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,530,null,"Sta 530:  Annual ESD Test\n--5/7/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1022086",null,"2025-08-25","2026-06-30",null,null,null,"Sta 530","500","L","Unit 1A - Bearings","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,530.00099999999998,null,"Sta 530:  Unit 1A - Bearings\n--8/25/25 through 6/30/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-1094319","***","2025-08-26","2026-03-31","Completed",null,null,"Sta 530","500","L","Unit 2A - Bearings","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,530.00199999999995,"------","***Sta 530:  Unit 2A - Bearings\n***Completed"]
["X25-691135",null,"2025-06-09","2026-12-31",null,null,null,"Sta 530","500","L","Unit 3A - Crankshaft Replacement","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,530.00300000000004,null,"Sta 530:  Unit 3A - Crankshaft Replacement\n--6/9/25 through 12/31/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-691139",null,"2025-06-09","2026-12-31",null,null,null,"Sta 530","500","L","Unit 5A - Top-End Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,530.005,null,"Sta 530:  Unit 5A - Top-End Overhaul\n--6/9/25 through 12/31/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n………………………………"]
["X25-1237337","***","2025-10-06","2026-03-31","Completed",null,null,"Sta 530","500","L","Unit 6A - Bearings","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,530.00599999999997,"------","***Sta 530:  Unit 6A - Bearings\n***Completed"]
["X26-220272",null,"2026-04-13","2026-04-17",null,null,null,"Sta 530","500","L","Unit 1B - Engine Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,530.01700000000005,null,"Sta 530:  Unit 1B - Engine Maintenance\n--4/13/26 through 4/17/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-326911",null,"2026-05-26","2026-05-26",null,null,null,"Sta 534","500","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,534,null,"Sta 534:  Annual ESD Test\n--5/26/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-352306","***","2025-03-25","2026-05-29","Project Change",null,"2026-05-04","Sta 534","500","L","Unit 6A - Piston Liner & Unloader Replacements","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,534.00599999999997,"----end_date--------------model_loc--","***Sta 534:  Unit 6A - Piston Liner & Unloader Replacements\n--3/25/25 through 5/29/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 3/25/25 to 5/4/26.\n………………………………"]
["X25-596569","***","2025-05-20","2026-03-27","Completed",null,null,"Sta 534","500","L","Unit 7A - Piston / Liner","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,534.00699999999995,"------","***Sta 534:  Unit 7A - Piston / Liner\n***Completed"]
["X25-1389380",null,"2026-06-01","2026-06-15",null,null,null,"MLV 534-2 to MLV 538-2","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,534.20000000000005,null,"MLV 534-2 to MLV 538-2:  Anomaly Remediation\n--6/1/26 through 6/15/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1389568",null,"2026-06-16","2026-06-30",null,null,null,"MLV 534-2 to MLV 538-2","500","0","SCCDA","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,534.20000000000005,null,"MLV 534-2 to MLV 538-2:  SCCDA\n--6/16/26 through 6/30/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-307472",null,"2026-04-21","2026-04-21",null,null,null,"Sta 538 Heidelberg","500","1","Station ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,538,null,"Sta 538 Heidelberg:  Station ESD Test\n--4/21/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-309942",null,"2026-06-22","2026-06-26",null,null,null,"MLV 538-2L to MLV 539-2","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,538.20000000000005,null,"MLV 538-2L to MLV 539-2:  Anomaly Remediation\n--6/22/26 through 6/26/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1389376",null,"2026-07-20","2026-08-07",null,null,null,"MLV 538-2 to MLV 542-2","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,538.20000000000005,null,"MLV 538-2 to MLV 542-2:  Anomaly Remediation\n--7/20/26 through 8/7/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-309941",null,"2026-06-18","2026-06-20",null,null,null,"MLV 539-2 to MLV 540-2","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,539.20000000000005,null,"MLV 539-2 to MLV 540-2:  Anomaly Remediation\n--6/18/26 through 6/20/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-309936",null,"2026-06-01","2026-06-17",null,null,null,"MLV 540-2 to MLV 540-2A","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,540.20000000000005,null,"MLV 540-2 to MLV 540-2A:  Anomaly Remediation\n--6/1/26 through 6/17/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-279102",null,"2026-08-25","2026-08-27",null,null,null,"Sta 542 Dekalb","500","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,542,null,"Sta 542 Dekalb:  Annual ESD Test\n--8/25/26 through 8/27/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-39749","***","2026-01-01","2026-06-28","Project Change",null,"2026-04-17","Sta 542","500","1","Unit 1A - Emergent Repair","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,542.00099999999998,"----end_date--------------model_loc--","***Sta 542:  Unit 1A - Emergent Repair\n--1/1/26 through 6/28/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***\nDate Change, Previously scheduled 1/1/26 to 4/17/26.\n………………………………"]
["X26-377735","***","2026-03-26","2026-06-28","Added",null,null,"Sta 542","500","1","Unit 3A - Emergent Repair","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,542.00300000000004,"------","***Sta 542:  Unit 3A - Emergent Repair\n--3/26/26 through 6/28/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***Added\n………………………………"]
["X26-279099",null,"2026-08-04","2026-08-06",null,null,null,"Sta 546","500","1","Annual ESD Tests & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,546,null,"Sta 546:  Annual ESD Tests & Maintenance\n--8/4/26 through 8/6/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-220304","***","2026-01-22","2026-04-08","Project Change",null,"2026-03-31","Sta 546","500","1","Unit 3A - Engine Maintenance","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,546.00300000000004,"----end_date--------------model_loc--","***Sta 546:  Unit 3A - Engine Maintenance\n--1/22/26 through 4/8/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***\nDate Change, Previously scheduled 1/22/26 to 3/31/26.\n………………………………"]
["X25-840628","***","2025-07-14","2026-04-17","Project Change",null,"2026-03-27","Sta 546","500","1","Unit 7A - Metal in Oil","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,546.00699999999995,"----end_date--------------model_loc--","***Sta 546:  Unit 7A - Metal in Oil\n--7/14/25 through 4/17/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential out of path restrictions may be at risk.\n***\nDate Change, Previously scheduled 7/14/25 to 3/27/26.\n………………………………"]
["X25-1411337",null,"2026-10-05","2026-10-09",null,null,null,"Sta 550 Hamilton","500","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,550,null,"Sta 550 Hamilton:  Annual ESD Test\n--10/5/26 through 10/9/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-431275","***","2026-03-16","2026-03-27","Completed",null,null,"Sta 550","500","1","Unit 3A - Turbocharger Exchange","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,550.00300000000004,"------","***Sta 550:  Unit 3A - Turbocharger Exchange\n***Completed"]
["X26-357041","***","2026-04-06","2026-05-18","Added",null,null,"Sta 550","500","1","Unit 3A - Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,550.00300000000004,"------","***Sta 550:  Unit 3A - Overhaul\n--4/6/26 through 5/18/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***Added\n………………………………"]
["X25-1508269",null,"2026-09-28","2026-10-09",null,null,null,"Sta 550","500","1","Unit 1B - Juction Box Rewire & Unit Valves","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,550.03200000000004,null,"Sta 550:  Unit 1B - Juction Box Rewire & Unit Valves\n--9/28/26 through 10/9/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1508270",null,"2026-10-05","2026-10-09",null,null,null,"Sta 550","500","1","Unit 1B - Annual Safety Device Checks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,550.03200000000004,null,"Sta 550:  Unit 1B - Annual Safety Device Checks\n--10/5/26 through 10/9/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1389366",null,"2026-04-13","2026-04-17",null,null,null,"MLV 550-1 to MLV 555-1","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,550.1,null,"MLV 550-1 to MLV 555-1:  Anomaly Remediation\n--4/13/26 through 4/17/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1389369",null,"2026-05-18","2026-06-19",null,null,null,"MLV 550-1 to MLV 555-1","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,550.1,null,"MLV 550-1 to MLV 555-1:  Anomaly Remediation\n--5/18/26 through 6/19/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1389350",null,"2026-10-05","2026-10-23",null,null,null,"MLV 550-2 to MLV 555-2","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,550.20000000000005,null,"MLV 550-2 to MLV 555-2:  Anomaly Remediation\n--10/5/26 through 10/23/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-309921",null,"2026-05-18","2026-05-29",null,null,null,"MLV 551-2 to MLV 552-2","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,551.20000000000005,null,"MLV 551-2 to MLV 552-2:  Anomaly Remediation\n--5/18/26 through 5/29/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-309919",null,"2026-05-04","2026-05-15",null,null,null,"MLV 552-2 to MLV 553-2","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,552.20000000000005,null,"MLV 552-2 to MLV 553-2:  Anomaly Remediation\n--5/4/26 through 5/15/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1389387",null,"2026-04-27","2026-05-01",null,null,null,"MLV 552-3 to MLV 555-3","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,552.29999999999995,null,"MLV 552-3 to MLV 555-3:  Anomaly Remediation\n--4/27/26 through 5/1/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-309916",null,"2026-04-27","2026-05-02",null,null,null,"MLV 554-2R to MLV 554-2","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,554.20000000000005,null,"MLV 554-2R to MLV 554-2:  Anomaly Remediation\n--4/27/26 through 5/2/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1411671",null,"2026-04-21","2026-04-24",null,null,null,"Sta 555 Collinwood","500","1","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,555,null,"Sta 555 Collinwood:  Annual ESD Test & Maintenance\n--4/21/26 through 4/24/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1527850",null,"2026-04-21","2026-04-24",null,null,null,"Sta 555","500","1","Scrubber/Filter/Separator Clean, Inspect & Filter Change","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,555,null,"Sta 555:  Scrubber/Filter/Separator Clean, Inspect & Filter Change\n--4/21/26 through 4/24/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-343475","***","2026-04-07","2026-04-07","Completed",null,null,"Sta 555","500","1","Units 1A & 2A - GHG Leaks","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,555.00099999999998,"------","***Sta 555:  Units 1A & 2A - GHG Leaks\n***Completed"]
["X26-44741",null,"2026-01-20","2026-06-05",null,null,null,"Sta 555","500","1","Unit 5A - Foundation Regrout","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,555.005,null,"Sta 555:  Unit 5A - Foundation Regrout\n--1/20/26 through 6/5/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-282625",null,"2026-04-28","2026-04-28",null,null,null,"Sta 555","500","1","Unit 1B - Replace Recycle Valve Seal","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,555.01700000000005,null,"Sta 555:  Unit 1B - Replace Recycle Valve Seal\n--4/28/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1527836",null,"2026-04-28","2026-04-29",null,null,null,"Sta 555","500","1","Unit 1B - Protective Device Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,555.03200000000004,null,"Sta 555:  Unit 1B - Protective Device Inspection\n--4/28/26 through 4/29/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1389371",null,"2026-04-27","2026-05-01",null,null,null,"MLV 555-1L to MLV 556-1","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,555.1,null,"MLV 555-1L to MLV 556-1:  Anomaly Remediation\n--4/27/26 through 5/1/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-309944",null,"2026-05-04","2026-05-08",null,null,null,"MLV 557-1 to MLV 558-1R","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,555.1,null,"MLV 557-1 to MLV 558-1R:  Anomaly Remediation\n--5/4/26 through 5/8/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-332611",null,"2026-04-20","2026-04-24",null,null,null,"MLV 556-1 to MLV 557-1","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,556.1,null,"MLV 556-1 to MLV 557-1:  Anomaly Remediation\n--4/20/26 through 4/24/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1479662",null,"2026-06-02","2026-06-02",null,null,null,"MLV 557-3 to MLV 559-3","500","1","Pig Runs - Cleaning / Gauge 6/2/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,557.29999999999995,null,"MLV 557-3 to MLV 559-3:  Pig Runs - Cleaning / Gauge 6/2/26\n--6/2/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1479665",null,"2026-06-04","2026-06-04",null,null,null,"MLV 557-3 to MLV 559-3","500","1","Pig Runs - Cal / IMU & MFL-A 6/4/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,557.29999999999995,null,"MLV 557-3 to MLV 559-3:  Pig Runs - Cal / IMU & MFL-A 6/4/26\n--6/4/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1380244",null,"2026-12-08","2026-12-08",null,null,null,"MLV 559-1 to 565-1","500","1","Pig Run - Gauge","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,559.1,null,"MLV 559-1 to 565-1:  Pig Run - Gauge\n--12/8/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1380248",null,"2026-12-10","2026-12-10",null,null,null,"MLV 559-1 to 565-1","500","1","Pig Run - EMAT","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,559.1,null,"MLV 559-1 to 565-1:  Pig Run - EMAT\n--12/10/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1389390",null,"2026-04-06","2026-04-24",null,null,null,"MLV 559-2 to MLV 565-2","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,559.20000000000005,null,"MLV 559-2 to MLV 565-2:  Anomaly Remediation\n--4/6/26 through 4/24/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-288410",null,"2026-12-08","2026-12-08",null,null,null,"MLV 559-2 to MLV 565-2","500","1","Pig Run - Cleaning / Gauge","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,559.20000000000005,null,"MLV 559-2 to MLV 565-2:  Pig Run - Cleaning / Gauge\n--12/8/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X26-78268",null,"2026-12-15","2026-12-15",null,null,null,"MLV 559-2 to MLV 565-2","500","1","Pig Run - Hard Spot","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,559.26,null,"MLV 559-2 to MLV 565-2:  Pig Run - Hard Spot\n--12/15/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X26-288368",null,"2026-04-13","2026-04-25",null,null,null,"MLV 562-2 to MLV 563-2","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,562.20000000000005,null,"MLV 562-2 to MLV 563-2:  Anomaly Remediation\n--4/13/26 through 4/25/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1411725",null,"2026-04-29","2026-04-29",null,null,null,"Sta 563 Joelton","500","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,563,null,"Sta 563 Joelton:  Annual ESD Test\n--4/29/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1514567","***","2026-06-15","2026-06-18","Project Change",null,null,"Sta 563 Joelton","500","1","Scrubber Filter Changeout","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,563,"------------mantenance_desc------model_loc--","***Sta 563 Joelton:  Scrubber Filter Changeout\n--6/15/26 through 6/18/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***Project Change\n………………………………"]
["X25-1514617",null,"2026-04-29","2026-05-01",null,null,null,"Sta 563 Joelton","500","1","Unit 1A - Lube Oil Varnish System Installation","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,563.00099999999998,null,"Sta 563 Joelton:  Unit 1A - Lube Oil Varnish System Installation\n--4/29/26 through 5/1/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1514627",null,"2026-09-15","2026-09-16",null,null,null,"Sta 563","500","1","Unit 1A - Annual Inspection & Safety Device Check","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,563.00099999999998,null,"Sta 563:  Unit 1A - Annual Inspection & Safety Device Check\n--9/15/26 through 9/16/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1514620",null,"2026-04-27","2026-04-29",null,null,null,"Sta 563 Joelton","500","1","Unit 2A - Lube Oil Varnish System Installation","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,563.00199999999995,null,"Sta 563 Joelton:  Unit 2A - Lube Oil Varnish System Installation\n--4/27/26 through 4/29/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1514616",null,"2026-05-11","2026-05-22",null,null,null,"Sta 563 Joelton","500","1","Unit 2A - Solar Turbine Exchange","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,563.00199999999995,null,"Sta 563 Joelton:  Unit 2A - Solar Turbine Exchange\n--5/11/26 through 5/22/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1514628",null,"2026-09-16","2026-09-17",null,null,null,"Sta 563","500","1","Unit 2A - Annual Inspection/CAV","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,563.00199999999995,null,"Sta 563:  Unit 2A - Annual Inspection/CAV\n--9/16/26 through 9/17/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-288367",null,"2026-04-06","2026-04-11",null,null,null,"MLV 564-2R to MLV 564-2","500","1","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,564.20000000000005,null,"MLV 564-2R to MLV 564-2:  Anomaly Remediation\n--4/6/26 through 4/11/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1250007",null,"2026-05-07","2026-05-07",null,null,null,"MLV 706-1 to MLV 700-1","100","0","Pig Run - Cleaning 5/7/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","412819 LOUISMID/TGP CONVERSE CENTRAL: RIP\n410031 ETX GAS/TGP EAST TX PLANT DEHY PANO",706.11,null,"MLV 706-1 to MLV 700-1:  Pig Run - Cleaning 5/7/26\n--5/7/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  \n412819 LOUISMID/TGP CONVERSE CENTRAL: RIP\n410031 ETX GAS/TGP EAST TX PLANT DEHY PANO\n………………………………"]
["X25-1250009",null,"2026-05-12","2026-05-12",null,null,null,"MLV 706-1 to MLV 700-1","100","0","Pig Run - Cleaning 5/12/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","412819 LOUISMID/TGP CONVERSE CENTRAL: RIP\n410031 ETX GAS/TGP EAST TX PLANT DEHY PANO",706.12,null,"MLV 706-1 to MLV 700-1:  Pig Run - Cleaning 5/12/26\n--5/12/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  \n412819 LOUISMID/TGP CONVERSE CENTRAL: RIP\n410031 ETX GAS/TGP EAST TX PLANT DEHY PANO\n………………………………"]
["X25-1250011",null,"2026-05-14","2026-05-14",null,null,null,"MLV 706-1 to MLV 700-1","100","0","Pig Run - Caliper 5/14/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","412819 LOUISMID/TGP CONVERSE CENTRAL: RIP\n410031 ETX GAS/TGP EAST TX PLANT DEHY PANO",706.13,null,"MLV 706-1 to MLV 700-1:  Pig Run - Caliper 5/14/26\n--5/14/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  \n412819 LOUISMID/TGP CONVERSE CENTRAL: RIP\n410031 ETX GAS/TGP EAST TX PLANT DEHY PANO\n………………………………"]
["X26-282285",null,"2026-11-10","2026-11-10",null,null,null,"Sta 820 Starks","800","L","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,820,null,"Sta 820 Starks:  Annual ESD Test\n--11/10/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-192473",null,"2026-05-06","2026-05-06",null,null,null,"MLV 820-1 to MLV 821R-101.1","500","L","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.    The meters listed may be constrained or shut in during the project.","412690\tHPL/TGP SABINE NEWTON\n412013\tENTRPRSE/TGP SABINE RIVER TRANS NEW\n401366\tTRNSCO/TGP UTOS EXCH\n400580\tFGT/TGP SABINE EXCH CALCASIEU\n411586\tTRNSCO/TGP STARKS LA TRANSPORT CALC\n412768\tGLDNPASS/TGP STARKS LNG: RIP 820 10\n412737\tCAM IPL/TGP DE QUINCY GAS STORAGE C\n49446\tCAM IPL/TGP BANKEN RD AT  HWY 27 DE\n412461\tOLIPDPII/TGP DEHYDRATION CALCASIEU\n420581\tBDWKLAGT/TGP BECKWITH CREEK CALCASI\n420473\tTRUNKLNE/TGP KINDER LA EXCH JEFFERS\n420227\tCOKINOS/TGP KING FARM LA JEFFERSON",820.1,null,"MLV 820-1 to MLV 821R-101.1:  Pig Run - Maintenance\n--5/6/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.    The meters listed may be constrained or shut in during the project.  \n412690\tHPL/TGP SABINE NEWTON\n412013\tENTRPRSE/TGP SABINE RIVER TRANS NEW\n401366\tTRNSCO/TGP UTOS EXCH\n400580\tFGT/TGP SABINE EXCH CALCASIEU\n411586\tTRNSCO/TGP STARKS LA TRANSPORT CALC\n412768\tGLDNPASS/TGP STARKS LNG: RIP 820 10\n412737\tCAM IPL/TGP DE QUINCY GAS STORAGE C\n49446\tCAM IPL/TGP BANKEN RD AT  HWY 27 DE\n412461\tOLIPDPII/TGP DEHYDRATION CALCASIEU\n420581\tBDWKLAGT/TGP BECKWITH CREEK CALCASI\n420473\tTRUNKLNE/TGP KINDER LA EXCH JEFFERS\n420227\tCOKINOS/TGP KING FARM LA JEFFERSON\n………………………………"]
["X26-36416",null,"2026-05-05","2026-05-07",null,null,null,"Sta 823 (Kinder)","800","L","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,823,null,"Sta 823 (Kinder):  Annual ESD Test\n--5/5/26 through 5/7/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-36406",null,"2026-01-06","2026-04-09",null,null,null,"Sta 823","800","L","Unit 11A - Jacket Water Pump","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,823.01099999999997,null,"Sta 823:  Unit 11A - Jacket Water Pump\n--1/6/26 through 4/9/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-192471",null,"2026-05-05","2026-05-05",null,null,null,"MLV 823-1 to MLV 821R-101.1","500","L","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.    The meters listed may be constrained or shut in during the project.","412690\tHPL/TGP SABINE NEWTON\n412013\tENTRPRSE/TGP SABINE RIVER TRANS NEW\n401366\tTRNSCO/TGP UTOS EXCH\n400580\tFGT/TGP SABINE EXCH CALCASIEU\n411586\tTRNSCO/TGP STARKS LA TRANSPORT CALC\n412768\tGLDNPASS/TGP STARKS LNG: RIP 820 10\n412737\tCAM IPL/TGP DE QUINCY GAS STORAGE C\n49446\tCAM IPL/TGP BANKEN RD AT  HWY 27 DE\n412461\tOLIPDPII/TGP DEHYDRATION CALCASIEU\n420581\tBDWKLAGT/TGP BECKWITH CREEK CALCASI\n420473\tTRUNKLNE/TGP KINDER LA EXCH JEFFERS\n420227\tCOKINOS/TGP KING FARM LA JEFFERSON",823.1,null,"MLV 823-1 to MLV 821R-101.1:  Pig Run - Maintenance\n--5/5/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.    The meters listed may be constrained or shut in during the project.  \n412690\tHPL/TGP SABINE NEWTON\n412013\tENTRPRSE/TGP SABINE RIVER TRANS NEW\n401366\tTRNSCO/TGP UTOS EXCH\n400580\tFGT/TGP SABINE EXCH CALCASIEU\n411586\tTRNSCO/TGP STARKS LA TRANSPORT CALC\n412768\tGLDNPASS/TGP STARKS LNG: RIP 820 10\n412737\tCAM IPL/TGP DE QUINCY GAS STORAGE C\n49446\tCAM IPL/TGP BANKEN RD AT  HWY 27 DE\n412461\tOLIPDPII/TGP DEHYDRATION CALCASIEU\n420581\tBDWKLAGT/TGP BECKWITH CREEK CALCASI\n420473\tTRUNKLNE/TGP KINDER LA EXCH JEFFERS\n420227\tCOKINOS/TGP KING FARM LA JEFFERSON\n………………………………"]
["X26-192452","***","2026-06-30","2026-06-30","Project Change","2026-03-30","2026-03-31","Sta 823 to MLV 516","500","L","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.    The meters listed may be constrained or shut in during the project.","412398 JEFFSTOR/TGP JEFFERSON ISLAND IBERI\n420915 CEGS/TGP PORT IBERIA SALES IBERIA\n421056 ACADIAN/TGP INDIAN BAYOU: DIP 510B-\n412594 NAUTILUS/TGP GARDEN CITY ST MARY",823.1,"--start_date--end_date--meters_affected------------model_loc--","***Sta 823 to MLV 516:  Pig Run - Maintenance\n--6/30/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.    The meters listed may be constrained or shut in during the project.  \n412398 JEFFSTOR/TGP JEFFERSON ISLAND IBERI\n420915 CEGS/TGP PORT IBERIA SALES IBERIA\n421056 ACADIAN/TGP INDIAN BAYOU: DIP 510B-\n412594 NAUTILUS/TGP GARDEN CITY ST MARY\n***\nDate Change, Previously scheduled 3/30/26 to 3/31/26.\n………………………………"]
["X26-63488",null,"2026-06-08","2026-06-11",null,null,null,"Sta 827 (Alexandria)","800","L","Annual ESD and Maintenance","This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,827,null,"Sta 827 (Alexandria):  Annual ESD and Maintenance\n--6/8/26 through 6/11/26:  This project will require a facility outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-192465",null,"2026-06-03","2026-06-03",null,null,null,"Sta 827 to Sta 823","800","L","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.    The meters listed may be constrained or shut in during the project.","421043 PINE PRA/TGP PINE PRAIRIE NORTH RAP\n412847 ACADIAN/TGP CHENEYVILLE RAPIDES\n412713 HUGHES E/TGP UDP BLACK STONE13 EVAN \n412844 TEXLA/TGP ROY MARTIN GATHERING: RIP\n420296 FORSTHIL/TGP FOREST HILL LA RAPIDES\n420530 GLNMORA/TGP GLENMORA LA EXCH RAPIDE\n421042 ELIZ NG/TGP EVANGELINE SALES EVANGE\n420629 ELIZ NG/TGP OAKDALE DETENTION SALES\n420687 ELIZ NG/TGP ALLEN PARISH PRISON SAL\n420406 ELIZ NG/TGP ELIZABETH LA EMERGENCY\n53483 AIRLIQAT/TGP TIMBERLANE BIOGAS REC\n49446 CAM IPL/TGP BANKEN RD AT HWY 27 DE",827.1,null,"Sta 827 to Sta 823:  Pig Run - Maintenance\n--6/3/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.    The meters listed may be constrained or shut in during the project.  \n421043 PINE PRA/TGP PINE PRAIRIE NORTH RAP\n412847 ACADIAN/TGP CHENEYVILLE RAPIDES\n412713 HUGHES E/TGP UDP BLACK STONE13 EVAN \n412844 TEXLA/TGP ROY MARTIN GATHERING: RIP\n420296 FORSTHIL/TGP FOREST HILL LA RAPIDES\n420530 GLNMORA/TGP GLENMORA LA EXCH RAPIDE\n421042 ELIZ NG/TGP EVANGELINE SALES EVANGE\n420629 ELIZ NG/TGP OAKDALE DETENTION SALES\n420687 ELIZ NG/TGP ALLEN PARISH PRISON SAL\n420406 ELIZ NG/TGP ELIZABETH LA EMERGENCY\n53483 AIRLIQAT/TGP TIMBERLANE BIOGAS REC\n49446 CAM IPL/TGP BANKEN RD AT HWY 27 DE\n………………………………"]
["X26-192469",null,"2026-10-07","2026-10-07",null,null,null,"Sta 827 to Sta 823","800","L","Pig Run - Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.    The meters listed may be constrained or shut in during the project.","421043 PINE PRA/TGP PINE PRAIRIE NORTH RAP\n412847 ACADIAN/TGP CHENEYVILLE RAPIDES\n412713 HUGHES E/TGP UDP BLACK STONE13 EVAN \n412844 TEXLA/TGP ROY MARTIN GATHERING: RIP\n420296 FORSTHIL/TGP FOREST HILL LA RAPIDES\n420530 GLNMORA/TGP GLENMORA LA EXCH RAPIDE\n421042 ELIZ NG/TGP EVANGELINE SALES EVANGE\n420629 ELIZ NG/TGP OAKDALE DETENTION SALES\n420687 ELIZ NG/TGP ALLEN PARISH PRISON SAL\n420406 ELIZ NG/TGP ELIZABETH LA EMERGENCY\n53483 AIRLIQAT/TGP TIMBERLANE BIOGAS REC",827.11,null,"Sta 827 to Sta 823:  Pig Run - Maintenance\n--10/7/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.    The meters listed may be constrained or shut in during the project.  \n421043 PINE PRA/TGP PINE PRAIRIE NORTH RAP\n412847 ACADIAN/TGP CHENEYVILLE RAPIDES\n412713 HUGHES E/TGP UDP BLACK STONE13 EVAN \n412844 TEXLA/TGP ROY MARTIN GATHERING: RIP\n420296 FORSTHIL/TGP FOREST HILL LA RAPIDES\n420530 GLNMORA/TGP GLENMORA LA EXCH RAPIDE\n421042 ELIZ NG/TGP EVANGELINE SALES EVANGE\n420629 ELIZ NG/TGP OAKDALE DETENTION SALES\n420687 ELIZ NG/TGP ALLEN PARISH PRISON SAL\n420406 ELIZ NG/TGP ELIZABETH LA EMERGENCY\n53483 AIRLIQAT/TGP TIMBERLANE BIOGAS REC\n………………………………"]
["X25-1411914",null,"2026-09-29","2026-09-30",null,null,null,"Sta 834","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,834,null,"Sta 834:  Annual ESD Test\n--9/29/26 through 9/30/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-198063",null,"2026-03-30","2026-04-03",null,null,null,"Sta 834","800","1","Unit 1A - Turbocharger","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,834.00099999999998,null,"Sta 834:  Unit 1A - Turbocharger\n--3/30/26 through 4/3/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1480003",null,"2026-05-05","2026-05-06",null,null,null,"Sta 834","800","1","Unit 1A - Replace Insulation Blanket","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,834.00099999999998,null,"Sta 834:  Unit 1A - Replace Insulation Blanket\n--5/5/26 through 5/6/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1480006",null,"2026-05-07","2026-05-08",null,null,null,"Sta 834","800","1","Unit 2A - Replace Insulation Blanket","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,834.00199999999995,null,"Sta 834:  Unit 2A - Replace Insulation Blanket\n--5/7/26 through 5/8/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1480008",null,"2026-05-12","2026-05-13",null,null,null,"Sta 834","800","1","Unit 3A - Replace Insulation Blanket","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,834.00300000000004,null,"Sta 834:  Unit 3A - Replace Insulation Blanket\n--5/12/26 through 5/13/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1480009",null,"2026-05-14","2026-05-15",null,null,null,"Sta 834","800","1","Unit 4A - Replace Insulation Blanket","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,834.00400000000002,null,"Sta 834:  Unit 4A - Replace Insulation Blanket\n--5/14/26 through 5/15/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1479999",null,"2026-09-07","2026-09-11",null,null,null,"Sta 834","800","1","Unit 4A - Replace Lubrication System","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,834.00400000000002,null,"Sta 834:  Unit 4A - Replace Lubrication System\n--9/7/26 through 9/11/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1480012",null,"2026-05-19","2026-05-20",null,null,null,"Sta 834","800","1","Unit 5A - Replace Insulation Blanket","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,834.005,null,"Sta 834:  Unit 5A - Replace Insulation Blanket\n--5/19/26 through 5/20/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1479988",null,"2026-09-21","2026-10-02",null,null,null,"Sta 834","800","1","unit 5A - Controls/Fuel System Upgrade","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,834.005,null,"Sta 834:  unit 5A - Controls/Fuel System Upgrade\n--9/21/26 through 10/2/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X24-1186067","***","2025-03-03","2026-04-24","Project Change",null,"2026-04-03","Sta 834","800","1","Unit 6A - Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,834.00599999999997,"----end_date--------------model_loc--","***Sta 834:  Unit 6A - Overhaul\n--3/3/25 through 4/24/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***\nDate Change, Previously scheduled 3/3/25 to 4/3/26.\n………………………………"]
["X25-1480014",null,"2026-05-21","2026-05-22",null,null,null,"Sta 834","800","1","Unit 6A - Replace Insulation Blanket","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,834.00599999999997,null,"Sta 834:  Unit 6A - Replace Insulation Blanket\n--5/21/26 through 5/22/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-330160",null,"2026-04-27","2026-05-08",null,null,null,"Sta 834","800","1","Unit 7A - Turbocharger/Overhaul","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,834.00699999999995,null,"Sta 834:  Unit 7A - Turbocharger/Overhaul\n--4/27/26 through 5/8/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1480019",null,"2026-05-27","2026-05-28",null,null,null,"Sta 834","800","1","Unit 7A - Replace Insulation Blanket","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,834.00699999999995,null,"Sta 834:  Unit 7A - Replace Insulation Blanket\n--5/27/26 through 5/28/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1479985",null,"2026-06-26","2026-06-26",null,null,null,"Sta 834","800","1","Scrubber Filter Changeout","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,834.01,null,"Sta 834:  Scrubber Filter Changeout\n--6/26/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1479979",null,"2026-05-21","2026-05-21",null,null,null,"Sta 834 to Sta 827","800","L","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,834.1,null,"Sta 834 to Sta 827:  Maintenance Pig\n--5/21/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1179520",null,"2026-06-08","2026-06-10",null,null,null,"Sta 834 to Sta 827","800","L","Pig Run - Cleaning / Gauge 6/8/26 to 6/10/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420755 ATMOS TL/TGP LASALLE PARISH NEBO SA\n420447 PELICANG/TGP HARRISONBURG LA CATAHO",834.1,null,"Sta 834 to Sta 827:  Pig Run - Cleaning / Gauge 6/8/26 to 6/10/26\n--6/8/26 through 6/10/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  \n420755 ATMOS TL/TGP LASALLE PARISH NEBO SA\n420447 PELICANG/TGP HARRISONBURG LA CATAHO\n………………………………"]
["X25-1479981",null,"2026-11-05","2026-11-05",null,null,null,"Sta 834 to Sta 827","800","L","Maintenance Pig","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420755 ATMOS TL/TGP LASALLE PARISH NEBO SA\n420447 PELICANG/TGP HARRISONBURG LA CATAHO",834.1,null,"Sta 834 to Sta 827:  Maintenance Pig\n--11/5/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  \n420755 ATMOS TL/TGP LASALLE PARISH NEBO SA\n420447 PELICANG/TGP HARRISONBURG LA CATAHO\n………………………………"]
["X25-1179521",null,"2026-06-11","2026-06-11",null,null,null,"Sta 834 to Sta 827","800","L","Pig Run - BH Combo 6/11/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420755 ATMOS TL/TGP LASALLE PARISH NEBO SA\n420447 PELICANG/TGP HARRISONBURG LA CATAHO",834.12,null,"Sta 834 to Sta 827:  Pig Run - BH Combo 6/11/26\n--6/11/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  \n420755 ATMOS TL/TGP LASALLE PARISH NEBO SA\n420447 PELICANG/TGP HARRISONBURG LA CATAHO\n………………………………"]
["X25-1179524",null,"2026-06-15","2026-06-15",null,null,null,"Sta 834 to Sta 827","800","L","Pig Run - BH Hard Spot 6/15/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.","420755 ATMOS TL/TGP LASALLE PARISH NEBO SA\n420447 PELICANG/TGP HARRISONBURG LA CATAHO",834.14,null,"Sta 834 to Sta 827:  Pig Run - BH Hard Spot 6/15/26\n--6/15/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations.  The meters listed may be constrained or shut in during the project.  \n420755 ATMOS TL/TGP LASALLE PARISH NEBO SA\n420447 PELICANG/TGP HARRISONBURG LA CATAHO\n………………………………"]
["X25-1411910",null,"2026-08-26","2026-08-26",null,null,null,"Sta 836A","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,836,null,"Sta 836A:  Annual ESD Test\n--8/26/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1411912",null,"2026-09-10","2026-09-10",null,null,null,"Sta 838","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,838,null,"Sta 838:  Annual ESD Test\n--9/10/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1411559",null,"2026-06-17","2026-06-17",null,null,null,"Sta 843 Isola","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,843,null,"Sta 843 Isola:  Annual ESD Test\n--6/17/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1411496",null,"2026-08-18","2026-08-20",null,null,null,"Sta 847 Coffeeville","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,847,null,"Sta 847 Coffeeville:  Annual ESD Test\n--8/18/26 through 8/20/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1479660",null,"2026-04-28","2026-04-28",null,null,null,"MLV 847-1 to MLV 851-1","800","1","Pig Runs - Cleaning / Gauge 4/28/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,847.1,null,"MLV 847-1 to MLV 851-1:  Pig Runs - Cleaning / Gauge 4/28/26\n--4/28/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1479661",null,"2026-04-30","2026-04-30",null,null,null,"MLV 847-1 to MLV 851-1","800","1","Pig Runs - Cal / IMU & MFL-A 4/30/26","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,847.1,null,"MLV 847-1 to MLV 851-1:  Pig Runs - Cal / IMU & MFL-A 4/30/26\n--4/30/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1411286",null,"2026-10-19","2026-10-21",null,null,null,"Sta 851 New Albany","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,851,null,"Sta 851 New Albany:  Annual ESD Test\n--10/19/26 through 10/21/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1479848",null,"2026-05-12","2026-05-13",null,null,null,"Sta 851","800","1","Scrubber Filter Change Out","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,851.01,null,"Sta 851:  Scrubber Filter Change Out\n--5/12/26 through 5/13/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1411665",null,"2026-06-10","2026-06-11",null,null,null,"Sta 856 Savannah","800","1","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,856,null,"Sta 856 Savannah:  Annual ESD Test\n--6/10/26 through 6/11/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1411669",null,"2026-05-11","2026-05-12",null,null,null,"Sta 860","800","1","Annual ESD Test & Maintenance","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,860,null,"Sta 860:  Annual ESD Test & Maintenance\n--5/11/26 through 5/12/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1284312",null,"2025-06-17","2026-12-31",null,null,null,"Sta 860","800","1","Unit 1A - Aftercooler Jacket Water Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,860.00099999999998,null,"Sta 860:  Unit 1A - Aftercooler Jacket Water Inspection\n--6/17/25 through 12/31/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-379013","***","2026-03-30","2026-05-25","Added",null,null,"Sta 860","800","1","Unit 7A - Compressor Rods","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,860.00699999999995,"------","***Sta 860:  Unit 7A - Compressor Rods\n--3/30/26 through 5/25/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***Added\n………………………………"]
["X25-1527929",null,"2026-04-06","2026-04-08",null,null,null,"Sta 860","800","1","Unit 1C - 4K/Turbine Waterwash/Boroscope","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,860.048,null,"Sta 860:  Unit 1C - 4K/Turbine Waterwash/Boroscope\n--4/6/26 through 4/8/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1527862",null,"2026-08-13","2026-08-13",null,null,null,"Sta 860","800","1","Unit 1C - Protective Device Check","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,860.048,null,"Sta 860:  Unit 1C - Protective Device Check\n--8/13/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1527872",null,"2026-10-06","2026-10-07",null,null,null,"Sta 860","800","1","Unit 1C - 4K/Turbine Waterwash/Boroscope","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,860.048,null,"Sta 860:  Unit 1C - 4K/Turbine Waterwash/Boroscope\n--10/6/26 through 10/7/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1527922",null,"2026-10-06","2026-10-06",null,null,null,"Sta 860","800","1","Unit 1C - Engine Inspection/CAV","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,860.048,null,"Sta 860:  Unit 1C - Engine Inspection/CAV\n--10/6/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1527931",null,"2026-04-09","2026-04-10",null,null,null,"Sta 860","800","1","Unit  2C - 4K/Turbine Waterwash/Boroscope","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,860.04899999999998,null,"Sta 860:  Unit  2C - 4K/Turbine Waterwash/Boroscope\n--4/9/26 through 4/10/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1527866",null,"2026-08-14","2026-08-14",null,null,null,"Sta 860","800","1","Unit 2C - Protective Device Check","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,860.04899999999998,null,"Sta 860:  Unit 2C - Protective Device Check\n--8/14/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1527906",null,"2026-10-07","2026-10-08",null,null,null,"Sta 860","800","1","Unit 2C - 4K/Turbine Waterwash/Boroscope","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,860.04899999999998,null,"Sta 860:  Unit 2C - 4K/Turbine Waterwash/Boroscope\n--10/7/26 through 10/8/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1527919",null,"2026-10-07","2026-10-07",null,null,null,"Sta 860","800","1","Unit 2C - Engine Inspection/CAV","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,860.04899999999998,null,"Sta 860:  Unit 2C - Engine Inspection/CAV\n--10/7/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1527938",null,"2026-05-11","2026-05-15",null,null,null,"Sta 860","800","1","Scrubber/Filter/Separator Clean, Inspect & Filter Change","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,860.1,null,"Sta 860:  Scrubber/Filter/Separator Clean, Inspect & Filter Change\n--5/11/26 through 5/15/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1411788",null,"2026-06-23","2026-06-23",null,null,null,"Sta 871 Campbellsville","800","2","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,871,null,"Sta 871 Campbellsville:  Annual ESD Test\n--6/23/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1514679",null,"2026-06-02","2026-06-02",null,null,null,"Sta 871","800","2","Unit 1A - 2Q Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,871.00099999999998,null,"Sta 871:  Unit 1A - 2Q Engine Inspection\n--6/2/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1514681",null,"2026-09-02","2026-09-02",null,null,null,"Sta 871","800","2","Unit 1A - 3Q Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,871.00099999999998,null,"Sta 871:  Unit 1A - 3Q Engine Inspection\n--9/2/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1514682",null,"2026-12-08","2026-12-08",null,null,null,"Sta 871","800","2","Unit 1A - 4Q Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,871.00099999999998,null,"Sta 871:  Unit 1A - 4Q Engine Inspection\n--12/8/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1514684",null,"2026-06-03","2026-06-03",null,null,null,"Sta 871","800","2","Unit 2A - 2Q Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,871.00199999999995,null,"Sta 871:  Unit 2A - 2Q Engine Inspection\n--6/3/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1514685",null,"2026-09-03","2026-09-03",null,null,null,"Sta 871","800","2","Unit 2A - 3Q Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,871.00199999999995,null,"Sta 871:  Unit 2A - 3Q Engine Inspection\n--9/3/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1514687",null,"2026-12-09","2026-12-09",null,null,null,"Sta 871","800","2","Unit 2A - 4Q Engine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,871.00199999999995,null,"Sta 871:  Unit 2A - 4Q Engine Inspection\n--12/9/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1022170",null,"2025-08-22","2026-05-31",null,null,null,"Sta 871","800","2","Unit 3A - Engine Crankshaft Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,871.00300000000004,null,"Sta 871:  Unit 3A - Engine Crankshaft Inspection\n--8/22/25 through 5/31/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  Potential in the path restrictions may be at risk.\n………………………………"]
["X26-285934",null,"2025-08-22","2026-05-31",null,null,null,"Sta 871","800","2","Unit 3A - Main Bearing","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,871.00300000000004,null,"Sta 871:  Unit 3A - Main Bearing\n--8/22/25 through 5/31/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1411765",null,"2026-11-11","2026-11-11",null,null,null,"Sta 871A Campbellsville","800","2","Annual ESD Test","This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,871.5,null,"Sta 871A Campbellsville:  Annual ESD Test\n--11/11/26:  This project will require a station outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n………………………………"]
["X26-278936",null,"2026-06-01","2026-06-06",null,null,null,"MLV 874-2A to MLV 874-2B","800","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,874.2,null,"MLV 874-2A to MLV 874-2B:  Anomaly Remediation\n--6/1/26 through 6/6/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X26-278937",null,"2026-06-08","2026-06-13",null,null,null,"MLV 874-2B to MLV 874-2","800","2","Anomaly Remediation","This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.",null,874.2,null,"MLV 874-2B to MLV 874-2:  Anomaly Remediation\n--6/8/26 through 6/13/26:  This project may require taking the pipeline section out of service which could limit throughput and result in restrictions based on customer nominations.  \n………………………………"]
["X25-1411088",null,"2026-06-09","2026-06-12",null,null,null,"Sta 875 Richmond","800","2","Annual ESD Test & Maintenance","This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.",null,875,null,"Sta 875 Richmond:  Annual ESD Test & Maintenance\n--6/9/26 through 6/12/26:  This activity will require operating at controlled flow rates. Customers may experience pressure fluctuations; however, no other service impact is anticipated.  \n………………………………"]
["X25-1477462","***","2026-08-17","2026-08-21","Project Change","2026-04-06","2026-04-10","Sta 875","800","2","Unit 1A-  8K Solar Turbine Inspection","This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.",null,875.00099999999998,"--start_date--end_date--------------model_loc--","***Sta 875:  Unit 1A-  8K Solar Turbine Inspection\n--8/17/26 through 8/21/26:  This project will require a unit outage, which will limit throughput through the station and result in restrictions based on customer nominations.  \n***\nDate Change, Previously scheduled 4/6/26 to 4/10/26.\n………………………………"]

{"sheet":"Sheet2","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}

{"sheet":"Sheet3","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}